## Forecast_Data
Programme_ID | Commodity | Supplier_ID | Forecast_Period | Forecast_Version_Date | Forecast_Spend | Actual_Spend | Variance | Absolute_Error | Forecast_Failed_Flag | Forecast_Period_End_Date | Revision_Number | Previous_Forecast_Spend | Forecast_Change | Forecast_Change_Direction | Forecast_Stability_Score | Days_Before_Period | Confidence_Band | Committed_Spend | Commitment_Ratio | PO_Count | Actual_Minus_Committed | Programme_Change_Count | Programme_Scope_Churn_Index | Programme_Change_Impact_Index
P001 | Electronics | SUP007 | 2025-01 | 2024-08-08 | 2754195.78 | 1111691 | -1642504.78 | 1642504.78 | 1 | 2025-01-28 | 1 |  |  |  |  | 173 | Low | 315800.82 | 0.115 | 0 | 795890.18 | 19 | 1.97 | 1.9
P001 | Electronics | SUP007 | 2025-01 | 2024-08-20 | 2215663.95 | 1111691 | -1103972.95 | 1103972.95 | 1 | 2025-01-28 | 2 | 2754195.78 | -538531.83 | DOWN | 0.2431 | 161 | Low | 305810.52 | 0.144 | 0 | 805880.48 | 19 | 1.97 | 1.9
P001 | Electronics | SUP007 | 2025-01 | 2024-09-03 | 1787945.03 | 1111691 | -676254.03 | 676254.03 | 1 | 2025-01-28 | 3 | 2215663.95 | -427718.92 | DOWN | 0.2392 | 147 | Low | 328731.84 | 0.178 | 0 | 782959.16 | 19 | 1.97 | 1.9
P001 | Electronics | SUP007 | 2025-01 | 2024-09-06 | 1545630.82 | 1111691 | -433939.82 | 433939.82 | 1 | 2025-01-28 | 4 | 1787945.03 | -242314.21 | DOWN | 0.1568 | 144 | Low | 278450.19 | 0.186 | 1 | 833240.81 | 19 | 1.97 | 1.9
P001 | Electronics | SUP007 | 2025-01 | 2024-10-09 | 1430254.77 | 1111691 | -318563.77 | 318563.77 | 1 | 2025-01-28 | 5 | 1545630.82 | -115376.05 | DOWN | 0.0807 | 111 | Low | 406093.65 | 0.266 | 4 | 705597.35 | 19 | 1.97 | 1.9
P001 | Electronics | SUP007 | 2025-01 | 2024-11-16 | 1316497.41 | 1111691 | -204806.41 | 204806.41 | 1 | 2025-01-28 | 6 | 1430254.77 | -113757.36 | DOWN | 0.0864 | 73 | Low | 484457.02 | 0.359 | 2 | 627233.98 | 19 | 1.97 | 1.9
P001 | Software | SUP007 | 2025-02 | 2024-10-22 | 3186121.23 | 1452198 | -1733923.23 | 1733923.23 | 1 | 2025-02-28 | 1 |  |  |  |  | 129 | Low | 691246.9 | 0.226 | 0 | 760951.1 | 18 | 1.81 | 1.54
P001 | Software | SUP007 | 2025-02 | 2024-12-04 | 2581730.63 | 1452198 | -1129532.63 | 1129532.63 | 1 | 2025-02-28 | 2 | 3186121.23 | -604390.6 | DOWN | 0.2341 | 86 | Low | 909533.46 | 0.333 | 4 | 542664.54 | 18 | 1.81 | 1.54
P001 | Software | SUP007 | 2025-02 | 2024-12-12 | 2159324.36 | 1452198 | -707126.36 | 707126.36 | 1 | 2025-02-28 | 3 | 2581730.63 | -422406.27 | DOWN | 0.1956 | 78 | Low | 736486.23 | 0.353 | 2 | 715711.77 | 18 | 1.81 | 1.54
P001 | Software | SUP007 | 2025-02 | 2024-12-15 | 1891430.16 | 1452198 | -439232.16 | 439232.16 | 1 | 2025-02-28 | 4 | 2159324.36 | -267894.2 | DOWN | 0.1416 | 75 | Low | 659911.74 | 0.36 | 1 | 792286.26 | 18 | 1.81 | 1.54
P001 | Software | SUP007 | 2025-02 | 2024-12-16 | 1748530.57 | 1452198 | -296332.57 | 296332.57 | 1 | 2025-02-28 | 5 | 1891430.16 | -142899.59 | DOWN | 0.0817 | 74 | Low | 641042.06 | 0.363 | 3 | 811155.94 | 18 | 1.81 | 1.54
P001 | Software | SUP007 | 2025-02 | 2025-01-19 | 1659010.63 | 1452198 | -206812.63 | 206812.63 | 0 | 2025-02-28 | 6 | 1748530.57 | -89519.94 | DOWN | 0.054 | 40 | Low | 715418.19 | 0.447 | 2 | 736779.81 | 18 | 1.81 | 1.54
P001 | Materials | SUP007 | 2025-03 | 2024-11-19 | 601367.03 | 279189 | -322178.03 | 322178.03 | 1 | 2025-03-28 | 1 |  |  |  |  | 129 | Low | 153133.86 | 0.248 | 0 | 126055.14 | 20 | 0.93 | 1.57
P001 | Materials | SUP007 | 2025-03 | 2024-12-06 | 492427.11 | 279189 | -213238.11 | 213238.11 | 1 | 2025-03-28 | 2 | 601367.03 | -108939.92 | DOWN | 0.2212 | 112 | Low | 143045.8 | 0.295 | 1 | 136143.2 | 20 | 0.93 | 1.57
P001 | Materials | SUP007 | 2025-03 | 2025-01-04 | 420729.65 | 279189 | -141540.65 | 141540.65 | 1 | 2025-03-28 | 3 | 492427.11 | -71697.46 | DOWN | 0.1704 | 83 | Low | 163936.43 | 0.374 | 0 | 115252.57 | 20 | 0.93 | 1.57
P001 | Materials | SUP007 | 2025-03 | 2025-01-08 | 371831.48 | 279189 | -92642.48 | 92642.48 | 1 | 2025-03-28 | 4 | 420729.65 | -48898.17 | DOWN | 0.1315 | 79 | Low | 146042.49 | 0.385 | 2 | 133146.51 | 20 | 0.93 | 1.57
P001 | Services | SUP007 | 2025-04 | 2024-10-30 | 2705033.66 | 1133633 | -1571400.66 | 1571400.66 | 1 | 2025-04-28 | 1 |  |  |  |  | 180 | Low | 273253.57 | 0.105 | 2 | 860379.43 | 22 | 2.23 | 1.91
P001 | Services | SUP007 | 2025-04 | 2025-01-10 | 2186112.44 | 1133633 | -1052479.44 | 1052479.44 | 1 | 2025-04-28 | 2 | 2705033.66 | -518921.22 | DOWN | 0.2374 | 108 | Low | 588323.43 | 0.266 | 6 | 545309.57 | 22 | 2.23 | 1.91
P001 | Services | SUP007 | 2025-04 | 2025-02-07 | 1766790.65 | 1133633 | -633157.65 | 633157.65 | 1 | 2025-04-28 | 3 | 2186112.44 | -419321.79 | DOWN | 0.2373 | 80 | Low | 592761.99 | 0.333 | 3 | 540871.01 | 22 | 2.23 | 1.91
P001 | Electronics | SUP007 | 2025-05 | 2025-01-15 | 2315149.57 | 1293625 | -1021524.57 | 1021524.57 | 1 | 2025-05-28 | 1 |  |  |  |  | 133 | Low | 465381.41 | 0.215 | 5 | 828243.59 | 21 | 1.86 | 0.96
P001 | Electronics | SUP007 | 2025-05 | 2025-01-18 | 1964084.26 | 1293625 | -670459.26 | 670459.26 | 1 | 2025-05-28 | 2 | 2315149.57 | -351065.31 | DOWN | 0.1787 | 130 | Low | 408178.18 | 0.222 | 0 | 885446.82 | 21 | 1.86 | 0.96
P001 | Electronics | SUP007 | 2025-05 | 2025-01-30 | 1723120.76 | 1293625 | -429495.76 | 429495.76 | 1 | 2025-05-28 | 3 | 1964084.26 | -240963.5 | DOWN | 0.1398 | 118 | Low | 426786.31 | 0.252 | 3 | 866838.69 | 21 | 1.86 | 0.96
P001 | Electronics | SUP007 | 2025-05 | 2025-03-21 | 1538200.2 | 1293625 | -244575.2 | 244575.2 | 1 | 2025-05-28 | 4 | 1723120.76 | -184920.56 | DOWN | 0.1202 | 68 | Low | 561166.48 | 0.376 | 5 | 732458.52 | 21 | 1.86 | 0.96
P001 | Electronics | SUP007 | 2025-05 | 2025-03-28 | 1418944.51 | 1293625 | -125319.51 | 125319.51 | 0 | 2025-05-28 | 5 | 1538200.2 | -119255.69 | DOWN | 0.084 | 61 | Low | 597609.24 | 0.393 | 1 | 696015.76 | 21 | 1.86 | 0.96
P001 | Services | SUP007 | 2025-06 | 2025-01-10 | 1004252.38 | 452937 | -551315.38 | 551315.38 | 1 | 2025-06-28 | 1 |  |  |  |  | 169 | Low | 121315.79 | 0.128 | 0 | 331621.21 | 18 | 1.75 | 1.8
P001 | Services | SUP007 | 2025-06 | 2025-01-30 | 827617.46 | 452937 | -374680.46 | 374680.46 | 1 | 2025-06-28 | 2 | 1004252.38 | -176634.92 | DOWN | 0.2134 | 149 | Low | 148580.24 | 0.178 | 2 | 304356.76 | 18 | 1.75 | 1.8
P001 | Services | SUP007 | 2025-06 | 2025-03-19 | 698096.23 | 452937 | -245159.23 | 245159.23 | 1 | 2025-06-28 | 3 | 827617.46 | -129521.23 | DOWN | 0.1855 | 101 | Low | 208945.65 | 0.298 | 5 | 243991.35 | 18 | 1.75 | 1.8
P001 | Logistics | SUP007 | 2025-07 | 2025-03-04 | 2865941.84 | 1427620 | -1438321.84 | 1438321.84 | 1 | 2025-07-28 | 1 |  |  |  |  | 146 | Low | 600756.98 | 0.195 | 1 | 826863.02 | 17 | 1.27 | 1.46
P001 | Logistics | SUP007 | 2025-07 | 2025-03-25 | 2363556.95 | 1427620 | -935936.95 | 935936.95 | 1 | 2025-07-28 | 2 | 2865941.84 | -502384.89 | DOWN | 0.2126 | 125 | Low | 573130 | 0.251 | 0 | 854490 | 17 | 1.27 | 1.46
P001 | Logistics | SUP007 | 2025-07 | 2025-04-12 | 2070497.41 | 1427620 | -642877.41 | 642877.41 | 1 | 2025-07-28 | 3 | 2363556.95 | -293059.54 | DOWN | 0.1415 | 107 | Low | 650910.41 | 0.299 | 5 | 776709.59 | 17 | 1.27 | 1.46
P001 | Logistics | SUP007 | 2025-07 | 2025-06-09 | 1874307.39 | 1427620 | -446687.39 | 446687.39 | 1 | 2025-07-28 | 4 | 2070497.41 | -196190.02 | DOWN | 0.1047 | 49 | Medium | 873285.91 | 0.452 | 5 | 554334.09 | 17 | 1.27 | 1.46
P001 | Logistics | SUP007 | 2025-07 | 2025-07-10 | 1708670.67 | 1427620 | -281050.67 | 281050.67 | 1 | 2025-07-28 | 5 | 1874307.39 | -165636.72 | DOWN | 0.0969 | 18 | Medium | 980684.08 | 0.534 | 2 | 446935.92 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP007 | 2025-08 | 2025-03-06 | 2661321.21 | 1359265 | -1302056.21 | 1302056.21 | 1 | 2025-08-28 | 1 |  |  |  |  | 175 | Low | 300766.92 | 0.115 | 2 | 1058498.08 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP007 | 2025-08 | 2025-08-01 | 2222937.58 | 1359265 | -863672.58 | 863672.58 | 1 | 2025-08-28 | 2 | 2661321.21 | -438383.63 | DOWN | 0.1972 | 27 | Low | 1168493.95 | 0.494 | 2 | 190771.05 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP007 | 2025-08 | 2025-08-18 | 1920859.71 | 1359265 | -561594.71 | 561594.71 | 1 | 2025-08-28 | 3 | 2222937.58 | -302077.87 | DOWN | 0.1573 | 10 | Low | 948984.65 | 0.535 | 5 | 410280.35 | 21 | 1.54 | 1.03
P001 | Logistics | SUP007 | 2025-09 | 2025-04-13 | 1606095.67 | 802674 | -803421.67 | 803421.67 | 1 | 2025-09-28 | 1 |  |  |  |  | 168 | Low | 207196.51 | 0.139 | 0 | 595477.49 | 15 | 1.16 | 1.5
P001 | Logistics | SUP007 | 2025-09 | 2025-06-20 | 1293238.28 | 802674 | -490564.28 | 490564.28 | 1 | 2025-09-28 | 2 | 1606095.67 | -312857.39 | DOWN | 0.2419 | 100 | Low | 437725.96 | 0.321 | 1 | 364948.04 | 15 | 1.16 | 1.5
P001 | Logistics | SUP007 | 2025-09 | 2025-06-26 | 1133250.97 | 802674 | -330576.97 | 330576.97 | 1 | 2025-09-28 | 3 | 1293238.28 | -159987.31 | DOWN | 0.1412 | 94 | Low | 378272.87 | 0.337 | 1 | 424401.13 | 15 | 1.16 | 1.5
P001 | Logistics | SUP007 | 2025-09 | 2025-07-12 | 994838.72 | 802674 | -192164.72 | 192164.72 | 1 | 2025-09-28 | 4 | 1133250.97 | -138412.25 | DOWN | 0.1391 | 78 | Low | 357040.16 | 0.38 | 6 | 445633.84 | 15 | 1.16 | 1.5
P001 | Logistics | SUP007 | 2025-09 | 2025-08-03 | 935085.96 | 802674 | -132411.96 | 132411.96 | 0 | 2025-09-28 | 5 | 994838.72 | -59752.76 | DOWN | 0.0639 | 56 | Low | 410492.74 | 0.439 | 0 | 392181.26 | 15 | 1.16 | 1.5
P001 | Logistics | SUP007 | 2025-09 | 2025-08-10 | 877012.44 | 802674 | -74338.44 | 74338.44 | 0 | 2025-09-28 | 6 | 935085.96 | -58073.52 | DOWN | 0.0662 | 49 | Medium | 381468.32 | 0.458 | 3 | 421205.68 | 15 | 1.16 | 1.5
P001 | Electronics | SUP007 | 2025-10 | 2025-05-14 | 1686152.93 | 765096 | -921056.93 | 921056.93 | 1 | 2025-10-28 | 1 |  |  |  |  | 167 | Low | 230202.25 | 0.132 | 3 | 534893.75 | 18 | 1.81 | 1.33
P001 | Electronics | SUP007 | 2025-10 | 2025-05-31 | 1347078.46 | 765096 | -581982.46 | 581982.46 | 1 | 2025-10-28 | 2 | 1686152.93 | -339074.47 | DOWN | 0.2517 | 150 | Low | 223834.5 | 0.174 | 4 | 541261.5 | 18 | 1.81 | 1.33
P001 | Electronics | SUP007 | 2025-10 | 2025-06-23 | 1151463.17 | 765096 | -386367.17 | 386367.17 | 1 | 2025-10-28 | 3 | 1347078.46 | -195615.29 | DOWN | 0.1699 | 127 | Low | 255529.65 | 0.231 | 5 | 509566.35 | 18 | 1.81 | 1.33
P001 | Electronics | SUP007 | 2025-10 | 2025-07-09 | 1029431.73 | 765096 | -264335.73 | 264335.73 | 1 | 2025-10-28 | 4 | 1151463.17 | -122031.44 | DOWN | 0.1185 | 111 | Low | 264014.22 | 0.271 | 1 | 501081.78 | 18 | 1.81 | 1.33
P001 | Electronics | SUP007 | 2025-10 | 2025-08-13 | 942885.63 | 765096 | -177789.63 | 177789.63 | 1 | 2025-10-28 | 5 | 1029431.73 | -86546.1 | DOWN | 0.0918 | 76 | Low | 323891.95 | 0.358 | 2 | 441204.05 | 18 | 1.81 | 1.33
P001 | Electronics | SUP007 | 2025-10 | 2025-08-22 | 873105.53 | 765096 | -108009.53 | 108009.53 | 0 | 2025-10-28 | 6 | 942885.63 | -69780.1 | DOWN | 0.0799 | 67 | Low | 318004.57 | 0.38 | 0 | 447091.43 | 18 | 1.81 | 1.33
P001 | Logistics | SUP007 | 2025-11 | 2025-06-24 | 4016178.35 | 2082503 | -1933675.35 | 1933675.35 | 1 | 2025-11-28 | 1 |  |  |  |  | 157 | Low | 627168.98 | 0.17 | 0 | 1455334.02 | 26 | 1.11 | 1.53
P001 | Logistics | SUP007 | 2025-11 | 2025-07-13 | 3302666.49 | 2082503 | -1220163.49 | 1220163.49 | 1 | 2025-11-28 | 2 | 4016178.35 | -713511.86 | DOWN | 0.216 | 138 | Low | 769021.94 | 0.221 | 3 | 1313481.06 | 26 | 1.11 | 1.53
P001 | Logistics | SUP007 | 2025-11 | 2025-07-18 | 2919068.42 | 2082503 | -836565.42 | 836565.42 | 1 | 2025-11-28 | 3 | 3302666.49 | -383598.07 | DOWN | 0.1314 | 133 | Low | 696736.67 | 0.234 | 0 | 1385766.33 | 26 | 1.11 | 1.53
P001 | Logistics | SUP007 | 2025-11 | 2025-08-26 | 2612052.72 | 2082503 | -529549.72 | 529549.72 | 1 | 2025-11-28 | 4 | 2919068.42 | -307015.7 | DOWN | 0.1175 | 94 | Low | 859735.78 | 0.339 | 2 | 1222767.22 | 26 | 1.11 | 1.53
P001 | Logistics | SUP007 | 2025-11 | 2025-10-20 | 2413085.21 | 2082503 | -330582.21 | 330582.21 | 0 | 2025-11-28 | 5 | 2612052.72 | -198967.51 | DOWN | 0.0825 | 39 | Medium | 1237175.73 | 0.487 | 1 | 845327.27 | 26 | 1.11 | 1.53
P001 | Logistics | SUP007 | 2025-11 | 2025-11-09 | 2315347.39 | 2082503 | -232844.39 | 232844.39 | 0 | 2025-11-28 | 6 | 2413085.21 | -97737.82 | DOWN | 0.0422 | 19 | Medium | 1305174.58 | 0.541 | 2 | 777328.42 | 26 | 1.11 | 1.53
P001 | Electronics | SUP007 | 2025-12 | 2025-07-12 | 2580565.16 | 1389700 | -1190865.16 | 1190865.16 | 1 | 2025-12-28 | 1 |  |  |  |  | 169 | Low | 360816.56 | 0.132 | 0 | 1028883.44 | 17 | 1.45 | 1.29
P001 | Electronics | SUP007 | 2025-12 | 2025-07-18 | 2205757.24 | 1389700 | -816057.24 | 816057.24 | 1 | 2025-12-28 | 2 | 2580565.16 | -374807.92 | DOWN | 0.1699 | 163 | Low | 340338.16 | 0.147 | 0 | 1049361.84 | 17 | 1.45 | 1.29
P001 | Electronics | SUP007 | 2025-12 | 2025-08-14 | 1911828.58 | 1389700 | -522128.58 | 522128.58 | 1 | 2025-12-28 | 3 | 2205757.24 | -293928.66 | DOWN | 0.1537 | 136 | Low | 435920.53 | 0.217 | 1 | 953779.47 | 17 | 1.45 | 1.29
P001 | Electronics | SUP007 | 2025-12 | 2025-09-12 | 1753905.7 | 1389700 | -364205.7 | 364205.7 | 1 | 2025-12-28 | 4 | 1911828.58 | -157922.88 | DOWN | 0.09 | 107 | Low | 532976.81 | 0.292 | 3 | 856723.19 | 17 | 1.45 | 1.29
P001 | Electronics | SUP007 | 2025-12 | 2025-10-20 | 1608578.32 | 1389700 | -218878.32 | 218878.32 | 0 | 2025-12-28 | 5 | 1753905.7 | -145327.38 | DOWN | 0.0903 | 69 | Low | 634551.52 | 0.391 | 4 | 755148.48 | 17 | 1.45 | 1.29
P001 | Electronics | SUP007 | 2025-12 | 2025-11-05 | 1525355.82 | 1389700 | -135655.82 | 135655.82 | 0 | 2025-12-28 | 6 | 1608578.32 | -83222.5 | DOWN | 0.0546 | 53 | Low | 671588.92 | 0.432 | 0 | 718111.08 | 17 | 1.45 | 1.29
P001 | Software | SUP015 | 2025-01 | 2024-08-04 | 3912645.78 | 1967766 | -1944879.78 | 1944879.78 | 1 | 2025-01-28 | 1 |  |  |  |  | 177 | Low | 548044.29 | 0.14 | 0 | 1419721.71 | 19 | 1.97 | 1.9
P001 | Software | SUP015 | 2025-01 | 2024-10-30 | 2784074.56 | 1967766 | -816308.56 | 816308.56 | 1 | 2025-01-28 | 2 | 3912645.78 | -1128571.22 | DOWN | 0.4054 | 90 | Low | 1192950.84 | 0.413 | 4 | 774815.16 | 19 | 1.97 | 1.9
P001 | Software | SUP015 | 2025-01 | 2024-11-10 | 2284081.8 | 1967766 | -316315.8 | 316315.8 | 0 | 2025-01-28 | 3 | 2784074.56 | -499992.76 | DOWN | 0.2189 | 79 | Low | 955394.65 | 0.448 | 2 | 1012371.35 | 19 | 1.97 | 1.9
P001 | Software | SUP015 | 2025-01 | 2024-12-29 | 2094310.6 | 1967766 | -126544.6 | 126544.6 | 0 | 2025-01-28 | 4 | 2284081.8 | -189771.2 | DOWN | 0.0906 | 30 | Low | 1230898.97 | 0.603 | 4 | 736867.03 | 19 | 1.97 | 1.9
P001 | Logistics | SUP015 | 2025-02 | 2024-09-18 | 4378585.09 | 2273460 | -2105125.09 | 2105125.09 | 1 | 2025-02-28 | 1 |  |  |  |  | 163 | Low | 791597.12 | 0.184 | 2 | 1481862.88 | 18 | 1.81 | 1.54
P001 | Logistics | SUP015 | 2025-02 | 2024-10-04 | 3168797.09 | 2273460 | -895337.09 | 895337.09 | 1 | 2025-02-28 | 2 | 4378585.09 | -1209788 | DOWN | 0.3818 | 147 | Low | 803861.12 | 0.236 | 1 | 1469598.88 | 18 | 1.81 | 1.54
P001 | Logistics | SUP015 | 2025-02 | 2024-10-20 | 2667029.76 | 2273460 | -393569.76 | 393569.76 | 0 | 2025-02-28 | 3 | 3168797.09 | -501767.33 | DOWN | 0.1881 | 131 | Low | 737650.58 | 0.288 | 2 | 1535809.42 | 18 | 1.81 | 1.54
P001 | Logistics | SUP015 | 2025-03 | 2024-11-01 | 3117613.44 | 1596294 | -1521319.44 | 1521319.44 | 1 | 2025-03-28 | 1 |  |  |  |  | 147 | Low | 762722.07 | 0.259 | 0 | 833571.93 | 20 | 0.93 | 1.57
P001 | Logistics | SUP015 | 2025-03 | 2024-11-25 | 2259962.28 | 1596294 | -663668.28 | 663668.28 | 1 | 2025-03-28 | 2 | 3117613.44 | -857651.16 | DOWN | 0.3795 | 123 | Low | 732933.2 | 0.344 | 1 | 863360.8 | 20 | 0.93 | 1.57
P001 | Logistics | SUP015 | 2025-03 | 2024-12-19 | 1862385.52 | 1596294 | -266091.52 | 266091.52 | 0 | 2025-03-28 | 3 | 2259962.28 | -397576.76 | DOWN | 0.2135 | 99 | Low | 795191.25 | 0.429 | 3 | 801102.75 | 20 | 0.93 | 1.57
P001 | Logistics | SUP015 | 2025-03 | 2025-01-26 | 1699618.51 | 1596294 | -103324.51 | 103324.51 | 0 | 2025-03-28 | 4 | 1862385.52 | -162767.01 | DOWN | 0.0958 | 61 | Low | 943677.69 | 0.564 | 0 | 652616.31 | 20 | 0.93 | 1.57
P001 | Logistics | SUP015 | 2025-03 | 2025-02-06 | 1634120.82 | 1596294 | -37826.82 | 37826.82 | 0 | 2025-03-28 | 5 | 1699618.51 | -65497.69 | DOWN | 0.0401 | 50 | Medium | 956765.95 | 0.603 | 5 | 639528.05 | 20 | 0.93 | 1.57
P001 | Logistics | SUP015 | 2025-03 | 2025-03-17 | 1580993.11 | 1596294 | 15300.89 | 15300.89 | 0 | 2025-03-28 | 6 | 1634120.82 | -53127.71 | DOWN | 0.0336 | 11 | High | 1108813.45 | 0.741 | 5 | 487480.55 | 20 | 0.93 | 1.57
P001 | Software | SUP015 | 2025-04 | 2024-11-20 | 2513831.26 | 1192567 | -1321264.26 | 1321264.26 | 1 | 2025-04-28 | 1 |  |  |  |  | 159 | Low | 499511.57 | 0.188 | 3 | 693055.43 | 22 | 2.23 | 1.91
P001 | Software | SUP015 | 2025-04 | 2024-11-28 | 1798592.02 | 1192567 | -606025.02 | 606025.02 | 1 | 2025-04-28 | 2 | 2513831.26 | -715239.24 | DOWN | 0.3977 | 151 | Low | 356381.71 | 0.213 | 3 | 836185.29 | 22 | 2.23 | 1.91
P001 | Software | SUP015 | 2025-04 | 2024-12-10 | 1496493.24 | 1192567 | -303926.24 | 303926.24 | 1 | 2025-04-28 | 3 | 1798592.02 | -302098.78 | DOWN | 0.2019 | 139 | Low | 375388.4 | 0.25 | 4 | 817178.6 | 22 | 2.23 | 1.91
P001 | Software | SUP015 | 2025-04 | 2025-02-03 | 1302406.22 | 1192567 | -109839.22 | 109839.22 | 0 | 2025-04-28 | 4 | 1496493.24 | -194087.02 | DOWN | 0.149 | 84 | Low | 575526.79 | 0.42 | 5 | 617040.21 | 22 | 2.23 | 1.91
P001 | Software | SUP015 | 2025-04 | 2025-03-13 | 1189597.55 | 1192567 | 2969.45 | 2969.45 | 0 | 2025-04-28 | 5 | 1302406.22 | -112808.67 | DOWN | 0.0948 | 46 | Low | 648110.41 | 0.538 | 4 | 544456.59 | 22 | 2.23 | 1.91
P001 | Software | SUP015 | 2025-04 | 2025-03-29 | 1188033.19 | 1192567 | 4533.81 | 4533.81 | 0 | 2025-04-28 | 6 | 1189597.55 | -1564.36 | DOWN | 0.0013 | 30 | Low | 656446.95 | 0.587 | 4 | 536120.05 | 22 | 2.23 | 1.91
P001 | Materials | SUP015 | 2025-05 | 2024-12-23 | 2047232.69 | 1146611 | -900621.69 | 900621.69 | 1 | 2025-05-28 | 1 |  |  |  |  | 156 | Low | 391067.08 | 0.206 | 0 | 755543.92 | 21 | 1.86 | 0.96
P001 | Materials | SUP015 | 2025-05 | 2025-02-15 | 1516184.19 | 1146611 | -369573.19 | 369573.19 | 1 | 2025-05-28 | 2 | 2047232.69 | -531048.5 | DOWN | 0.3503 | 102 | Low | 578178.7 | 0.379 | 3 | 568432.3 | 21 | 1.86 | 0.96
P001 | Materials | SUP015 | 2025-05 | 2025-03-14 | 1318583.28 | 1146611 | -171972.28 | 171972.28 | 0 | 2025-05-28 | 3 | 1516184.19 | -197600.91 | DOWN | 0.1499 | 75 | Low | 585637.57 | 0.466 | 4 | 560973.43 | 21 | 1.86 | 0.96
P001 | Electronics | SUP015 | 2025-06 | 2025-01-08 | 602971.59 | 304257 | -298714.59 | 298714.59 | 1 | 2025-06-28 | 1 |  |  |  |  | 171 | Low | 90716.84 | 0.159 | 0 | 213540.16 | 18 | 1.75 | 1.8
P001 | Electronics | SUP015 | 2025-06 | 2025-01-16 | 436179.55 | 304257 | -131922.55 | 131922.55 | 1 | 2025-06-28 | 2 | 602971.59 | -166792.04 | DOWN | 0.3824 | 163 | Low | 86002.41 | 0.185 | 0 | 218254.59 | 18 | 1.75 | 1.8
P001 | Electronics | SUP015 | 2025-06 | 2025-02-15 | 364300.3 | 304257 | -60043.3 | 60043.3 | 1 | 2025-06-28 | 3 | 436179.55 | -71879.25 | DOWN | 0.1973 | 133 | Low | 107451.75 | 0.283 | 1 | 196805.25 | 18 | 1.75 | 1.8
P001 | Electronics | SUP015 | 2025-06 | 2025-04-19 | 333612.33 | 304257 | -29355.33 | 29355.33 | 0 | 2025-06-28 | 4 | 364300.3 | -30687.97 | DOWN | 0.092 | 70 | Low | 170623.05 | 0.488 | 1 | 133633.95 | 18 | 1.75 | 1.8
P001 | Materials | SUP015 | 2025-07 | 2025-01-30 | 2346034.04 | 1276557 | -1069477.04 | 1069477.04 | 1 | 2025-07-28 | 1 |  |  |  |  | 179 | Low | 340399.06 | 0.151 | 0 | 936157.94 | 17 | 1.27 | 1.46
P001 | Materials | SUP015 | 2025-07 | 2025-03-31 | 1760315.96 | 1276557 | -483758.96 | 483758.96 | 1 | 2025-07-28 | 2 | 2346034.04 | -585718.08 | DOWN | 0.3327 | 119 | Low | 612037.88 | 0.347 | 2 | 664519.12 | 17 | 1.27 | 1.46
P001 | Materials | SUP015 | 2025-07 | 2025-05-07 | 1499908.19 | 1276557 | -223351.19 | 223351.19 | 0 | 2025-07-28 | 3 | 1760315.96 | -260407.77 | DOWN | 0.1736 | 82 | Low | 699822.59 | 0.474 | 5 | 576734.41 | 17 | 1.27 | 1.46
P001 | Materials | SUP015 | 2025-07 | 2025-06-17 | 1368569.99 | 1276557 | -92012.99 | 92012.99 | 0 | 2025-07-28 | 4 | 1499908.19 | -131338.2 | DOWN | 0.096 | 41 | Medium | 827213.12 | 0.615 | 5 | 449343.88 | 17 | 1.27 | 1.46
P001 | Electronics | SUP015 | 2025-08 | 2025-04-25 | 4358121.72 | 2892379 | -1465742.72 | 1465742.72 | 1 | 2025-08-28 | 1 |  |  |  |  | 125 | Low | 1398656.17 | 0.316 | 0 | 1493722.83 | 21 | 1.54 | 1.03
P001 | Electronics | SUP015 | 2025-08 | 2025-05-06 | 3537540.83 | 2892379 | -645161.83 | 645161.83 | 1 | 2025-08-28 | 2 | 4358121.72 | -820580.89 | DOWN | 0.232 | 114 | Low | 1160150.03 | 0.353 | 1 | 1732228.97 | 21 | 1.54 | 1.03
P001 | Electronics | SUP015 | 2025-08 | 2025-06-04 | 3223673.43 | 2892379 | -331294.43 | 331294.43 | 0 | 2025-08-28 | 3 | 3537540.83 | -313867.4 | DOWN | 0.0974 | 85 | Low | 1530396.98 | 0.45 | 8 | 1361982.02 | 21 | 1.54 | 1.03
P001 | Electronics | SUP015 | 2025-08 | 2025-07-19 | 3032708.59 | 2892379 | -140329.59 | 140329.59 | 0 | 2025-08-28 | 4 | 3223673.43 | -190964.84 | DOWN | 0.063 | 40 | Medium | 1818103.12 | 0.599 | 4 | 1074275.88 | 21 | 1.54 | 1.03
P001 | Electronics | SUP015 | 2025-08 | 2025-08-04 | 2935038.38 | 2892379 | -42659.38 | 42659.38 | 0 | 2025-08-28 | 5 | 3032708.59 | -97670.21 | DOWN | 0.0333 | 24 | Medium | 1791005.02 | 0.653 | 6 | 1101373.98 | 21 | 1.54 | 1.03
P001 | Materials | SUP015 | 2025-09 | 2025-04-08 | 1180734.71 | 772091 | -408643.71 | 408643.71 | 1 | 2025-09-28 | 1 |  |  |  |  | 173 | Low | 187652.95 | 0.163 | 0 | 584438.05 | 15 | 1.16 | 1.5
P001 | Materials | SUP015 | 2025-09 | 2025-08-05 | 962220.55 | 772091 | -190129.55 | 190129.55 | 1 | 2025-09-28 | 2 | 1180734.71 | -218514.16 | DOWN | 0.2271 | 54 | Low | 538546.02 | 0.577 | 5 | 233544.98 | 15 | 1.16 | 1.5
P001 | Materials | SUP015 | 2025-09 | 2025-08-05 | 860856.93 | 772091 | -88765.93 | 88765.93 | 0 | 2025-09-28 | 3 | 962220.55 | -101363.62 | DOWN | 0.1177 | 54 | Medium | 521944.05 | 0.577 | 3 | 250146.95 | 15 | 1.16 | 1.5
P001 | Materials | SUP015 | 2025-09 | 2025-08-29 | 811033.81 | 772091 | -38942.81 | 38942.81 | 0 | 2025-09-28 | 4 | 860856.93 | -49823.12 | DOWN | 0.0614 | 30 | Medium | 576355.13 | 0.661 | 5 | 195735.87 | 15 | 1.16 | 1.5
P001 | Software | SUP015 | 2025-10 | 2025-05-01 | 2320940.53 | 1234545 | -1086395.53 | 1086395.53 | 1 | 2025-10-28 | 1 |  |  |  |  | 180 | Low | 312292.88 | 0.142 | 1 | 922252.12 | 18 | 1.81 | 1.33
P001 | Software | SUP015 | 2025-10 | 2025-06-29 | 1750412.8 | 1234545 | -515867.8 | 515867.8 | 1 | 2025-10-28 | 2 | 2320940.53 | -570527.73 | DOWN | 0.3259 | 121 | Low | 596340.84 | 0.32 | 1 | 638204.16 | 18 | 1.81 | 1.33
P001 | Software | SUP015 | 2025-10 | 2025-08-04 | 1454702.14 | 1234545 | -220157.14 | 220157.14 | 1 | 2025-10-28 | 3 | 1750412.8 | -295710.66 | DOWN | 0.2033 | 85 | Low | 587354.71 | 0.436 | 1 | 647190.29 | 18 | 1.81 | 1.33
P001 | Software | SUP015 | 2025-10 | 2025-09-19 | 1312044.84 | 1234545 | -77499.84 | 77499.84 | 0 | 2025-10-28 | 4 | 1454702.14 | -142657.3 | DOWN | 0.1087 | 39 | Medium | 716888.94 | 0.585 | 5 | 517656.06 | 18 | 1.81 | 1.33
P001 | Software | SUP015 | 2025-10 | 2025-09-20 | 1291341.19 | 1234545 | -56796.19 | 56796.19 | 0 | 2025-10-28 | 5 | 1312044.84 | -20703.65 | DOWN | 0.016 | 38 | Medium | 809154.49 | 0.588 | 4 | 425390.51 | 18 | 1.81 | 1.33
P001 | Software | SUP015 | 2025-10 | 2025-09-28 | 1254513.45 | 1234545 | -19968.45 | 19968.45 | 0 | 2025-10-28 | 6 | 1291341.19 | -36827.74 | DOWN | 0.0294 | 30 | Medium | 823697.13 | 0.614 | 7 | 410847.87 | 18 | 1.81 | 1.33
P001 | Mechanical | SUP015 | 2025-11 | 2025-06-03 | 2477351.49 | 1681085 | -796266.49 | 796266.49 | 1 | 2025-11-28 | 1 |  |  |  |  | 178 | Low | 397873.31 | 0.154 | 0 | 1283211.69 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP015 | 2025-11 | 2025-07-22 | 2053181.26 | 1681085 | -372096.26 | 372096.26 | 1 | 2025-11-28 | 2 | 2477351.49 | -424170.23 | DOWN | 0.2066 | 129 | Low | 687531.36 | 0.318 | 0 | 993553.64 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP015 | 2025-11 | 2025-08-18 | 1840393.24 | 1681085 | -159308.24 | 159308.24 | 0 | 2025-11-28 | 3 | 2053181.26 | -212788.02 | DOWN | 0.1156 | 102 | Low | 715080.28 | 0.413 | 0 | 966004.72 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP015 | 2025-11 | 2025-08-24 | 1758291.9 | 1681085 | -77206.9 | 77206.9 | 0 | 2025-11-28 | 4 | 1840393.24 | -82101.34 | DOWN | 0.0467 | 96 | Low | 781517.5 | 0.434 | 3 | 899567.5 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP015 | 2025-11 | 2025-09-02 | 1720207.91 | 1681085 | -39122.91 | 39122.91 | 0 | 2025-11-28 | 5 | 1758291.9 | -38083.99 | DOWN | 0.0221 | 87 | Low | 830567.57 | 0.465 | 2 | 850517.43 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP015 | 2025-11 | 2025-10-16 | 1691376.54 | 1681085 | -10291.54 | 10291.54 | 0 | 2025-11-28 | 6 | 1720207.91 | -28831.37 | DOWN | 0.017 | 43 | Medium | 1032932.8 | 0.619 | 4 | 648152.2 | 26 | 1.11 | 1.53
P001 | Logistics | SUP015 | 2025-12 | 2025-07-06 | 809820.36 | 432468 | -377352.36 | 377352.36 | 1 | 2025-12-28 | 1 |  |  |  |  | 175 | Low | 121594.2 | 0.151 | 0 | 310873.8 | 17 | 1.45 | 1.29
P001 | Logistics | SUP015 | 2025-12 | 2025-07-22 | 595310.68 | 432468 | -162842.68 | 162842.68 | 1 | 2025-12-28 | 2 | 809820.36 | -214509.68 | DOWN | 0.3603 | 159 | Low | 123534.99 | 0.205 | 2 | 308933.01 | 17 | 1.45 | 1.29
P001 | Logistics | SUP015 | 2025-12 | 2025-10-25 | 490987.09 | 432468 | -58519.09 | 58519.09 | 0 | 2025-12-28 | 3 | 595310.68 | -104323.59 | DOWN | 0.2125 | 64 | Low | 266443.78 | 0.525 | 4 | 166024.22 | 17 | 1.45 | 1.29
P001 | Logistics | SUP015 | 2025-12 | 2025-10-27 | 470820.38 | 432468 | -38352.38 | 38352.38 | 0 | 2025-12-28 | 4 | 490987.09 | -20166.71 | DOWN | 0.0428 | 62 | Low | 266301.35 | 0.531 | 4 | 166166.65 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP012 | 2025-01 | 2024-09-13 | 4126092.56 | 2130182 | -1995910.56 | 1995910.56 | 1 | 2025-01-28 | 1 |  |  |  |  | 137 | Low | 1010505.79 | 0.264 | 3 | 1119676.21 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP012 | 2025-01 | 2024-09-27 | 3014385.07 | 2130182 | -884203.07 | 884203.07 | 1 | 2025-01-28 | 2 | 4126092.56 | -1111707.49 | DOWN | 0.3688 | 123 | Low | 914876.86 | 0.308 | 2 | 1215305.14 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP012 | 2025-01 | 2024-12-05 | 2509661.59 | 2130182 | -379479.59 | 379479.59 | 1 | 2025-01-28 | 3 | 3014385.07 | -504723.48 | DOWN | 0.2011 | 54 | Low | 1340759.22 | 0.527 | 3 | 789422.78 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP012 | 2025-01 | 2024-12-07 | 2325616.49 | 2130182 | -195434.49 | 195434.49 | 0 | 2025-01-28 | 4 | 2509661.59 | -184045.1 | DOWN | 0.0791 | 52 | Low | 1310725.19 | 0.534 | 3 | 819456.81 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP012 | 2025-01 | 2025-01-02 | 2244231.98 | 2130182 | -114049.98 | 114049.98 | 0 | 2025-01-28 | 5 | 2325616.49 | -81384.51 | DOWN | 0.0363 | 26 | Low | 1484850.78 | 0.616 | 1 | 645331.22 | 19 | 1.97 | 1.9
P001 | Software | SUP012 | 2025-02 | 2024-09-21 | 2034925.3 | 1167128 | -867797.3 | 867797.3 | 1 | 2025-02-28 | 1 |  |  |  |  | 160 | Low | 399845.2 | 0.194 | 0 | 767282.8 | 18 | 1.81 | 1.54
P001 | Software | SUP012 | 2025-02 | 2024-09-28 | 1532705.73 | 1167128 | -365577.73 | 365577.73 | 1 | 2025-02-28 | 2 | 2034925.3 | -502219.57 | DOWN | 0.3277 | 153 | Low | 310701.24 | 0.217 | 0 | 856426.76 | 18 | 1.81 | 1.54
P001 | Software | SUP012 | 2025-02 | 2024-10-21 | 1335786.28 | 1167128 | -168658.28 | 168658.28 | 0 | 2025-02-28 | 3 | 1532705.73 | -196919.45 | DOWN | 0.1474 | 130 | Low | 394513.03 | 0.291 | 1 | 772614.97 | 18 | 1.81 | 1.54
P001 | Software | SUP012 | 2025-02 | 2024-12-19 | 1261563.54 | 1167128 | -94435.54 | 94435.54 | 0 | 2025-02-28 | 4 | 1335786.28 | -74222.74 | DOWN | 0.0588 | 71 | Low | 590222.81 | 0.481 | 5 | 576905.19 | 18 | 1.81 | 1.54
P001 | Software | SUP012 | 2025-02 | 2025-02-15 | 1235728.69 | 1167128 | -68600.69 | 68600.69 | 0 | 2025-02-28 | 5 | 1261563.54 | -25834.85 | DOWN | 0.0209 | 13 | Medium | 855421.55 | 0.669 | 7 | 311706.45 | 18 | 1.81 | 1.54
P001 | Services | SUP012 | 2025-03 | 2024-10-05 | 1349768.82 | 892617 | -457151.82 | 457151.82 | 1 | 2025-03-28 | 1 |  |  |  |  | 174 | Low | 213933.26 | 0.163 | 0 | 678683.74 | 20 | 0.93 | 1.57
P001 | Services | SUP012 | 2025-03 | 2024-10-06 | 1098961.16 | 892617 | -206344.16 | 206344.16 | 1 | 2025-03-28 | 2 | 1349768.82 | -250807.66 | DOWN | 0.2282 | 173 | Low | 180588.24 | 0.167 | 0 | 712028.76 | 20 | 0.93 | 1.57
P001 | Services | SUP012 | 2025-03 | 2025-01-25 | 983723.76 | 892617 | -91106.76 | 91106.76 | 0 | 2025-03-28 | 3 | 1098961.16 | -115237.4 | DOWN | 0.1171 | 62 | Low | 563253.33 | 0.56 | 2 | 329363.67 | 20 | 0.93 | 1.57
P001 | Services | SUP012 | 2025-04 | 2024-12-26 | 1738665.68 | 883843 | -854822.68 | 854822.68 | 1 | 2025-04-28 | 1 |  |  |  |  | 123 | Low | 513727.9 | 0.3 | 1 | 370115.1 | 22 | 2.23 | 1.91
P001 | Services | SUP012 | 2025-04 | 2025-01-16 | 1297004.22 | 883843 | -413161.22 | 413161.22 | 1 | 2025-04-28 | 2 | 1738665.68 | -441661.46 | DOWN | 0.3405 | 102 | Low | 452117.11 | 0.365 | 1 | 431725.89 | 22 | 2.23 | 1.91
P001 | Services | SUP012 | 2025-04 | 2025-01-24 | 1074283.18 | 883843 | -190440.18 | 190440.18 | 1 | 2025-04-28 | 3 | 1297004.22 | -222721.04 | DOWN | 0.2073 | 94 | Low | 407995.68 | 0.389 | 3 | 475847.32 | 22 | 2.23 | 1.91
P001 | Services | SUP012 | 2025-04 | 2025-04-04 | 950100.79 | 883843 | -66257.79 | 66257.79 | 0 | 2025-04-28 | 4 | 1074283.18 | -124182.39 | DOWN | 0.1307 | 24 | Low | 587101.73 | 0.606 | 5 | 296741.27 | 22 | 2.23 | 1.91
P001 | Materials | SUP012 | 2025-05 | 2025-01-26 | 2777084.8 | 1477054 | -1300030.8 | 1300030.8 | 1 | 2025-05-28 | 1 |  |  |  |  | 122 | Low | 873104.48 | 0.315 | 2 | 603949.52 | 21 | 1.86 | 0.96
P001 | Materials | SUP012 | 2025-05 | 2025-02-02 | 2092457.93 | 1477054 | -615403.93 | 615403.93 | 1 | 2025-05-28 | 2 | 2777084.8 | -684626.87 | DOWN | 0.3272 | 115 | Low | 725455.55 | 0.337 | 0 | 751598.45 | 21 | 1.86 | 0.96
P001 | Materials | SUP012 | 2025-05 | 2025-02-07 | 1758760.89 | 1477054 | -281706.89 | 281706.89 | 1 | 2025-05-28 | 3 | 2092457.93 | -333697.04 | DOWN | 0.1897 | 110 | Low | 640465.92 | 0.354 | 3 | 836588.08 | 21 | 1.86 | 0.96
P001 | Materials | SUP012 | 2025-05 | 2025-04-05 | 1619819.11 | 1477054 | -142765.11 | 142765.11 | 0 | 2025-05-28 | 4 | 1758760.89 | -138941.78 | DOWN | 0.0858 | 53 | Medium | 843015.02 | 0.537 | 3 | 634038.98 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP012 | 2025-06 | 2025-02-19 | 2239795.29 | 1408617 | -831178.29 | 831178.29 | 1 | 2025-06-28 | 1 |  |  |  |  | 129 | Low | 611151.33 | 0.296 | 0 | 797465.67 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP012 | 2025-06 | 2025-03-08 | 1769005.98 | 1408617 | -360388.98 | 360388.98 | 1 | 2025-06-28 | 2 | 2239795.29 | -470789.31 | DOWN | 0.2661 | 112 | Low | 628106.84 | 0.351 | 2 | 780510.16 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP012 | 2025-06 | 2025-03-12 | 1572886.71 | 1408617 | -164269.71 | 164269.71 | 0 | 2025-06-28 | 3 | 1769005.98 | -196119.27 | DOWN | 0.1247 | 108 | Low | 577897.62 | 0.364 | 2 | 830719.38 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP012 | 2025-06 | 2025-03-29 | 1478181.52 | 1408617 | -69564.52 | 69564.52 | 0 | 2025-06-28 | 4 | 1572886.71 | -94705.19 | DOWN | 0.0641 | 91 | Low | 596376.37 | 0.42 | 4 | 812240.63 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP012 | 2025-06 | 2025-04-08 | 1435722.64 | 1408617 | -27105.64 | 27105.64 | 0 | 2025-06-28 | 5 | 1478181.52 | -42458.88 | DOWN | 0.0296 | 81 | Low | 666219.55 | 0.452 | 4 | 742397.45 | 18 | 1.75 | 1.8
P001 | Materials | SUP012 | 2025-07 | 2025-03-30 | 2851967.32 | 1694026 | -1157941.32 | 1157941.32 | 1 | 2025-07-28 | 1 |  |  |  |  | 120 | Low | 1009549.25 | 0.343 | 1 | 684476.75 | 17 | 1.27 | 1.46
P001 | Materials | SUP012 | 2025-07 | 2025-04-17 | 2235682.56 | 1694026 | -541656.56 | 541656.56 | 1 | 2025-07-28 | 2 | 2851967.32 | -616284.76 | DOWN | 0.2757 | 102 | Low | 859969.18 | 0.405 | 0 | 834056.82 | 17 | 1.27 | 1.46
P001 | Materials | SUP012 | 2025-07 | 2025-05-29 | 1920799.77 | 1694026 | -226773.77 | 226773.77 | 0 | 2025-07-28 | 3 | 2235682.56 | -314882.79 | DOWN | 0.1639 | 60 | Low | 1131216.47 | 0.549 | 4 | 562809.53 | 17 | 1.27 | 1.46
P001 | Materials | SUP012 | 2025-07 | 2025-06-02 | 1819244.06 | 1694026 | -125218.06 | 125218.06 | 0 | 2025-07-28 | 4 | 1920799.77 | -101555.71 | DOWN | 0.0558 | 56 | Medium | 1003939.76 | 0.563 | 3 | 690086.24 | 17 | 1.27 | 1.46
P001 | Materials | SUP012 | 2025-07 | 2025-06-24 | 1746537.75 | 1694026 | -52511.75 | 52511.75 | 0 | 2025-07-28 | 5 | 1819244.06 | -72706.31 | DOWN | 0.0416 | 34 | Medium | 1099643.83 | 0.639 | 4 | 594382.17 | 17 | 1.27 | 1.46
P001 | Materials | SUP012 | 2025-08 | 2025-04-16 | 3359937.22 | 1975890 | -1384047.22 | 1384047.22 | 1 | 2025-08-28 | 1 |  |  |  |  | 134 | Low | 897993.44 | 0.286 | 4 | 1077896.56 | 21 | 1.54 | 1.03
P001 | Materials | SUP012 | 2025-08 | 2025-06-23 | 2587290.85 | 1975890 | -611400.85 | 611400.85 | 1 | 2025-08-28 | 2 | 3359937.22 | -772646.37 | DOWN | 0.2986 | 66 | Low | 1375978.19 | 0.513 | 4 | 599911.81 | 21 | 1.54 | 1.03
P001 | Materials | SUP012 | 2025-08 | 2025-06-29 | 2251252.7 | 1975890 | -275362.7 | 275362.7 | 0 | 2025-08-28 | 3 | 2587290.85 | -336038.15 | DOWN | 0.1493 | 60 | Low | 1245557.42 | 0.533 | 6 | 730332.58 | 21 | 1.54 | 1.03
P001 | Materials | SUP012 | 2025-08 | 2025-07-13 | 2107660.56 | 1975890 | -131770.56 | 131770.56 | 0 | 2025-08-28 | 4 | 2251252.7 | -143592.14 | DOWN | 0.0681 | 46 | Medium | 1152881.8 | 0.579 | 5 | 823008.2 | 21 | 1.54 | 1.03
P001 | Electronics | SUP012 | 2025-09 | 2025-05-01 | 1805560.81 | 1063625 | -741935.81 | 741935.81 | 1 | 2025-09-28 | 1 |  |  |  |  | 150 | Low | 422223.33 | 0.244 | 0 | 641401.67 | 15 | 1.16 | 1.5
P001 | Electronics | SUP012 | 2025-09 | 2025-07-12 | 1409482.75 | 1063625 | -345857.75 | 345857.75 | 1 | 2025-09-28 | 2 | 1805560.81 | -396078.06 | DOWN | 0.281 | 78 | Low | 665833.62 | 0.494 | 7 | 397791.38 | 15 | 1.16 | 1.5
P001 | Electronics | SUP012 | 2025-09 | 2025-07-24 | 1217655.81 | 1063625 | -154030.81 | 154030.81 | 0 | 2025-09-28 | 3 | 1409482.75 | -191826.94 | DOWN | 0.1575 | 66 | Low | 651831.26 | 0.536 | 2 | 411793.74 | 15 | 1.16 | 1.5
P001 | Electronics | SUP012 | 2025-09 | 2025-08-27 | 1122840.55 | 1063625 | -59215.55 | 59215.55 | 0 | 2025-09-28 | 4 | 1217655.81 | -94815.26 | DOWN | 0.0844 | 32 | Medium | 783499.57 | 0.654 | 5 | 280125.43 | 15 | 1.16 | 1.5
P001 | Electronics | SUP012 | 2025-09 | 2025-09-06 | 1102532.1 | 1063625 | -38907.1 | 38907.1 | 0 | 2025-09-28 | 5 | 1122840.55 | -20308.45 | DOWN | 0.0184 | 22 | High | 770449.24 | 0.689 | 7 | 293175.76 | 15 | 1.16 | 1.5
P001 | Services | SUP012 | 2025-10 | 2025-05-19 | 983770.58 | 514807 | -468963.58 | 468963.58 | 1 | 2025-10-28 | 1 |  |  |  |  | 162 | Low | 181446.24 | 0.187 | 2 | 333360.76 | 18 | 1.81 | 1.33
P001 | Services | SUP012 | 2025-10 | 2025-05-21 | 728157.4 | 514807 | -213350.4 | 213350.4 | 1 | 2025-10-28 | 2 | 983770.58 | -255613.18 | DOWN | 0.351 | 160 | Low | 146324.79 | 0.194 | 3 | 368482.21 | 18 | 1.81 | 1.33
P001 | Services | SUP012 | 2025-10 | 2025-08-15 | 618328.75 | 514807 | -103521.75 | 103521.75 | 1 | 2025-10-28 | 3 | 728157.4 | -109828.65 | DOWN | 0.1776 | 74 | Low | 297863.33 | 0.472 | 3 | 216943.67 | 18 | 1.81 | 1.33
P001 | Services | SUP012 | 2025-10 | 2025-08-29 | 548296.62 | 514807 | -33489.62 | 33489.62 | 0 | 2025-10-28 | 4 | 618328.75 | -70032.13 | DOWN | 0.1277 | 60 | Low | 271482.9 | 0.517 | 3 | 243324.1 | 18 | 1.81 | 1.33
P001 | Services | SUP012 | 2025-10 | 2025-09-02 | 529784 | 514807 | -14977 | 14977 | 0 | 2025-10-28 | 5 | 548296.62 | -18512.62 | DOWN | 0.0349 | 56 | Medium | 266493.34 | 0.53 | 4 | 248313.66 | 18 | 1.81 | 1.33
P001 | Services | SUP012 | 2025-10 | 2025-09-24 | 511909.83 | 514807 | 2897.17 | 2897.17 | 0 | 2025-10-28 | 6 | 529784 | -17874.17 | DOWN | 0.0349 | 34 | Medium | 320573.03 | 0.601 | 5 | 194233.97 | 18 | 1.81 | 1.33
P001 | Software | SUP012 | 2025-11 | 2025-07-06 | 793787.27 | 396047 | -397740.27 | 397740.27 | 1 | 2025-11-28 | 1 |  |  |  |  | 145 | Low | 207542.99 | 0.262 | 2 | 188504.01 | 26 | 1.11 | 1.53
P001 | Software | SUP012 | 2025-11 | 2025-07-15 | 580638.61 | 396047 | -184591.61 | 184591.61 | 1 | 2025-11-28 | 2 | 793787.27 | -213148.66 | DOWN | 0.3671 | 136 | Low | 177949.94 | 0.294 | 0 | 218097.06 | 26 | 1.11 | 1.53
P001 | Software | SUP012 | 2025-11 | 2025-09-21 | 483233 | 396047 | -87186 | 87186 | 1 | 2025-11-28 | 3 | 580638.61 | -97405.61 | DOWN | 0.2016 | 68 | Low | 251828.27 | 0.532 | 9 | 144218.73 | 26 | 1.11 | 1.53
P001 | Software | SUP012 | 2025-11 | 2025-11-15 | 434515.5 | 396047 | -38468.5 | 38468.5 | 0 | 2025-11-28 | 4 | 483233 | -48717.5 | DOWN | 0.1121 | 13 | Medium | 302151.49 | 0.724 | 5 | 93895.51 | 26 | 1.11 | 1.53
P001 | Services | SUP012 | 2025-12 | 2025-07-23 | 696832.34 | 410433 | -286399.34 | 286399.34 | 1 | 2025-12-28 | 1 |  |  |  |  | 158 | Low | 141371.44 | 0.209 | 1 | 269061.56 | 17 | 1.45 | 1.29
P001 | Services | SUP012 | 2025-12 | 2025-08-18 | 533958.25 | 410433 | -123525.25 | 123525.25 | 1 | 2025-12-28 | 2 | 696832.34 | -162874.09 | DOWN | 0.305 | 132 | Low | 169847.95 | 0.296 | 3 | 240585.05 | 17 | 1.45 | 1.29
P001 | Services | SUP012 | 2025-12 | 2025-08-26 | 461908.48 | 410433 | -51475.48 | 51475.48 | 0 | 2025-12-28 | 3 | 533958.25 | -72049.77 | DOWN | 0.156 | 124 | Low | 150419.44 | 0.323 | 2 | 260013.56 | 17 | 1.45 | 1.29
P001 | Services | SUP012 | 2025-12 | 2025-09-06 | 434103.14 | 410433 | -23670.14 | 23670.14 | 0 | 2025-12-28 | 4 | 461908.48 | -27805.34 | DOWN | 0.0641 | 113 | Low | 159506.51 | 0.36 | 5 | 250926.49 | 17 | 1.45 | 1.29
P001 | Services | SUP012 | 2025-12 | 2025-09-17 | 413367.53 | 410433 | -2934.53 | 2934.53 | 0 | 2025-12-28 | 5 | 434103.14 | -20735.61 | DOWN | 0.0502 | 102 | Low | 171340.85 | 0.397 | 1 | 239092.15 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP048 | 2025-01 | 2024-08-19 | 2401991.46 | 1195505 | -1206486.46 | 1206486.46 | 1 | 2025-01-28 | 1 |  |  |  |  | 162 | Low | 284126.08 | 0.118 | 0 | 911378.92 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP048 | 2025-01 | 2024-08-26 | 2111659.71 | 1195505 | -916154.71 | 916154.71 | 1 | 2025-01-28 | 2 | 2401991.46 | -290331.75 | DOWN | 0.1375 | 155 | Low | 299638.21 | 0.132 | 4 | 895866.79 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP048 | 2025-01 | 2024-12-08 | 1846875.43 | 1195505 | -651370.43 | 651370.43 | 1 | 2025-01-28 | 3 | 2111659.71 | -264784.28 | DOWN | 0.1434 | 51 | Low | 626861.54 | 0.344 | 3 | 568643.46 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP048 | 2025-02 | 2024-09-02 | 944280.22 | 430087 | -514193.22 | 514193.22 | 1 | 2025-02-28 | 1 |  |  |  |  | 179 | Low | 83830.39 | 0.091 | 4 | 346256.61 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP048 | 2025-02 | 2024-10-16 | 812025.74 | 430087 | -381938.74 | 381938.74 | 1 | 2025-02-28 | 2 | 944280.22 | -132254.48 | DOWN | 0.1629 | 135 | Low | 142891.95 | 0.176 | 1 | 287195.05 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP048 | 2025-02 | 2024-11-25 | 707891.62 | 430087 | -277804.62 | 277804.62 | 1 | 2025-02-28 | 3 | 812025.74 | -104134.12 | DOWN | 0.1471 | 95 | Low | 182728.91 | 0.259 | 0 | 247358.09 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP048 | 2025-02 | 2024-12-30 | 640660.13 | 430087 | -210573.13 | 210573.13 | 1 | 2025-02-28 | 4 | 707891.62 | -67231.49 | DOWN | 0.1049 | 60 | Low | 215913.1 | 0.331 | 5 | 214173.9 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP048 | 2025-02 | 2025-02-10 | 590820.77 | 430087 | -160733.77 | 160733.77 | 1 | 2025-02-28 | 5 | 640660.13 | -49839.36 | DOWN | 0.0844 | 18 | Low | 255653.11 | 0.418 | 2 | 174433.89 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP048 | 2025-03 | 2024-10-22 | 435895.29 | 257634 | -178261.29 | 178261.29 | 1 | 2025-03-28 | 1 |  |  |  |  | 157 | Low | 64990.67 | 0.143 | 3 | 192643.33 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP048 | 2025-03 | 2024-11-13 | 389291.66 | 257634 | -131657.66 | 131657.66 | 1 | 2025-03-28 | 2 | 435895.29 | -46603.63 | DOWN | 0.1197 | 135 | Low | 79048.5 | 0.193 | 0 | 178585.5 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP048 | 2025-03 | 2024-11-29 | 354536.65 | 257634 | -96902.65 | 96902.65 | 1 | 2025-03-28 | 3 | 389291.66 | -34755.01 | DOWN | 0.098 | 119 | Low | 78539.34 | 0.23 | 1 | 179094.66 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP048 | 2025-03 | 2025-01-11 | 328931.91 | 257634 | -71297.91 | 71297.91 | 1 | 2025-03-28 | 4 | 354536.65 | -25604.74 | DOWN | 0.0778 | 76 | Low | 105228.86 | 0.327 | 1 | 152405.14 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP048 | 2025-03 | 2025-02-21 | 310441 | 257634 | -52807 | 52807 | 1 | 2025-03-28 | 5 | 328931.91 | -18490.91 | DOWN | 0.0596 | 35 | Low | 133567.12 | 0.42 | 4 | 124066.88 | 20 | 0.93 | 1.57
P001 | Logistics | SUP048 | 2025-04 | 2024-12-18 | 4350107.09 | 1489195 | -2860912.09 | 2860912.09 | 1 | 2025-04-28 | 1 |  |  |  |  | 131 | Low | 735846.93 | 0.176 | 1 | 753348.07 | 22 | 2.23 | 1.91
P001 | Logistics | SUP048 | 2025-04 | 2025-01-14 | 3555271.04 | 1489195 | -2066076.04 | 2066076.04 | 1 | 2025-04-28 | 2 | 4350107.09 | -794836.05 | DOWN | 0.2236 | 104 | Low | 811814.84 | 0.23 | 1 | 677380.16 | 22 | 2.23 | 1.91
P001 | Logistics | SUP048 | 2025-04 | 2025-01-14 | 3021564.98 | 1489195 | -1532369.98 | 1532369.98 | 1 | 2025-04-28 | 3 | 3555271.04 | -533706.06 | DOWN | 0.1766 | 104 | Low | 726025.17 | 0.23 | 0 | 763169.83 | 22 | 2.23 | 1.91
P001 | Logistics | SUP048 | 2025-04 | 2025-01-21 | 2642188.65 | 1489195 | -1152993.65 | 1152993.65 | 1 | 2025-04-28 | 4 | 3021564.98 | -379376.33 | DOWN | 0.1436 | 97 | Low | 666390.08 | 0.244 | 3 | 822804.92 | 22 | 2.23 | 1.91
P001 | Electronics | SUP048 | 2025-05 | 2024-12-13 | 4654521.06 | 2111166 | -2543355.06 | 2543355.06 | 1 | 2025-05-28 | 1 |  |  |  |  | 166 | Low | 502600.53 | 0.111 | 3 | 1608565.47 | 21 | 1.86 | 0.96
P001 | Electronics | SUP048 | 2025-05 | 2024-12-19 | 4065468.26 | 2111166 | -1954302.26 | 1954302.26 | 1 | 2025-05-28 | 2 | 4654521.06 | -589052.8 | DOWN | 0.1449 | 160 | Low | 481210.05 | 0.124 | 1 | 1629955.95 | 21 | 1.86 | 0.96
P001 | Electronics | SUP048 | 2025-05 | 2024-12-20 | 3575787.25 | 2111166 | -1464621.25 | 1464621.25 | 1 | 2025-05-28 | 3 | 4065468.26 | -489681.01 | DOWN | 0.1369 | 159 | Low | 484192.65 | 0.126 | 0 | 1626973.35 | 21 | 1.86 | 0.96
P001 | Electronics | SUP048 | 2025-05 | 2025-03-19 | 3195165.73 | 2111166 | -1083999.73 | 1083999.73 | 1 | 2025-05-28 | 4 | 3575787.25 | -380621.52 | DOWN | 0.1191 | 70 | Low | 1013500.69 | 0.309 | 0 | 1097665.31 | 21 | 1.86 | 0.96
P001 | Electronics | SUP048 | 2025-05 | 2025-03-24 | 2927285.34 | 2111166 | -816119.34 | 816119.34 | 1 | 2025-05-28 | 5 | 3195165.73 | -267880.39 | DOWN | 0.0915 | 65 | Low | 867401.89 | 0.319 | 0 | 1243764.11 | 21 | 1.86 | 0.96
P001 | Electronics | SUP048 | 2025-05 | 2025-04-21 | 2726129.58 | 2111166 | -614963.58 | 614963.58 | 1 | 2025-05-28 | 6 | 2927285.34 | -201155.76 | DOWN | 0.0738 | 37 | Low | 956431.68 | 0.377 | 4 | 1154734.32 | 21 | 1.86 | 0.96
P001 | Services | SUP048 | 2025-06 | 2025-01-23 | 6089876.67 | 2425658 | -3664218.67 | 3664218.67 | 1 | 2025-06-28 | 1 |  |  |  |  | 156 | Low | 862818.39 | 0.133 | 2 | 1562839.61 | 18 | 1.75 | 1.8
P001 | Services | SUP048 | 2025-06 | 2025-03-02 | 5224594.63 | 2425658 | -2798936.63 | 2798936.63 | 1 | 2025-06-28 | 2 | 6089876.67 | -865282.04 | DOWN | 0.1656 | 118 | Low | 1148564.58 | 0.213 | 3 | 1277093.42 | 18 | 1.75 | 1.8
P001 | Services | SUP048 | 2025-06 | 2025-05-10 | 4528505 | 2425658 | -2102847 | 2102847 | 1 | 2025-06-28 | 3 | 5224594.63 | -696089.63 | DOWN | 0.1537 | 49 | Low | 1656950.33 | 0.357 | 1 | 768707.67 | 18 | 1.75 | 1.8
P001 | Services | SUP048 | 2025-07 | 2025-02-11 | 3658421.43 | 1784106 | -1874315.43 | 1874315.43 | 1 | 2025-07-28 | 1 |  |  |  |  | 167 | Low | 453750.49 | 0.117 | 1 | 1330355.51 | 17 | 1.27 | 1.46
P001 | Services | SUP048 | 2025-07 | 2025-05-30 | 3237733.07 | 1784106 | -1453627.07 | 1453627.07 | 1 | 2025-07-28 | 2 | 3658421.43 | -420688.36 | DOWN | 0.1299 | 59 | Low | 1236824.84 | 0.354 | 2 | 547281.16 | 17 | 1.27 | 1.46
P001 | Services | SUP048 | 2025-07 | 2025-05-30 | 2839166.8 | 1784106 | -1055060.8 | 1055060.8 | 1 | 2025-07-28 | 3 | 3237733.07 | -398566.27 | DOWN | 0.1404 | 59 | Low | 1075979.14 | 0.354 | 3 | 708126.86 | 17 | 1.27 | 1.46
P001 | Materials | SUP048 | 2025-08 | 2025-05-08 | 1188573.03 | 564224 | -624349.03 | 624349.03 | 1 | 2025-08-28 | 1 |  |  |  |  | 112 | Low | 275833.44 | 0.231 | 5 | 288390.56 | 21 | 1.54 | 1.03
P001 | Materials | SUP048 | 2025-08 | 2025-06-03 | 1023018.55 | 564224 | -458794.55 | 458794.55 | 1 | 2025-08-28 | 2 | 1188573.03 | -165554.48 | DOWN | 0.1618 | 86 | Low | 315833.61 | 0.286 | 0 | 248390.39 | 21 | 1.54 | 1.03
P001 | Materials | SUP048 | 2025-08 | 2025-06-10 | 909443.43 | 564224 | -345219.43 | 345219.43 | 1 | 2025-08-28 | 3 | 1023018.55 | -113575.12 | DOWN | 0.1249 | 79 | Low | 287969.97 | 0.301 | 1 | 276254.03 | 21 | 1.54 | 1.03
P001 | Materials | SUP048 | 2025-08 | 2025-06-10 | 815279.23 | 564224 | -251055.23 | 251055.23 | 1 | 2025-08-28 | 4 | 909443.43 | -94164.2 | DOWN | 0.1155 | 79 | Low | 250212.19 | 0.301 | 3 | 314011.81 | 21 | 1.54 | 1.03
P001 | Materials | SUP048 | 2025-08 | 2025-06-30 | 742568.83 | 564224 | -178344.83 | 178344.83 | 1 | 2025-08-28 | 5 | 815279.23 | -72710.4 | DOWN | 0.0979 | 59 | Low | 247018.32 | 0.344 | 1 | 317205.68 | 21 | 1.54 | 1.03
P001 | Materials | SUP048 | 2025-08 | 2025-08-15 | 700725.5 | 564224 | -136501.5 | 136501.5 | 1 | 2025-08-28 | 6 | 742568.83 | -41843.33 | DOWN | 0.0597 | 13 | Low | 314032.31 | 0.442 | 4 | 250191.69 | 21 | 1.54 | 1.03
P001 | Logistics | SUP048 | 2025-09 | 2025-04-12 | 1507311.93 | 683730 | -823581.93 | 823581.93 | 1 | 2025-09-28 | 1 |  |  |  |  | 169 | Low | 160280.47 | 0.114 | 0 | 523449.53 | 15 | 1.16 | 1.5
P001 | Logistics | SUP048 | 2025-09 | 2025-04-25 | 1308225.53 | 683730 | -624495.53 | 624495.53 | 1 | 2025-09-28 | 2 | 1507311.93 | -199086.4 | DOWN | 0.1522 | 156 | Low | 188095.54 | 0.143 | 0 | 495634.46 | 15 | 1.16 | 1.5
P001 | Logistics | SUP048 | 2025-09 | 2025-05-08 | 1144871.05 | 683730 | -461141.05 | 461141.05 | 1 | 2025-09-28 | 3 | 1308225.53 | -163354.48 | DOWN | 0.1427 | 143 | Low | 200075.69 | 0.172 | 2 | 483654.31 | 15 | 1.16 | 1.5
P001 | Logistics | SUP048 | 2025-09 | 2025-05-29 | 1027313.81 | 683730 | -343583.81 | 343583.81 | 1 | 2025-09-28 | 4 | 1144871.05 | -117557.24 | DOWN | 0.1144 | 122 | Low | 232429.04 | 0.219 | 1 | 451300.96 | 15 | 1.16 | 1.5
P001 | Logistics | SUP048 | 2025-09 | 2025-06-28 | 953029.56 | 683730 | -269299.56 | 269299.56 | 1 | 2025-09-28 | 5 | 1027313.81 | -74284.25 | DOWN | 0.0779 | 92 | Low | 262069.68 | 0.285 | 0 | 421660.32 | 15 | 1.16 | 1.5
P001 | Logistics | SUP048 | 2025-09 | 2025-08-16 | 875726.82 | 683730 | -191996.82 | 191996.82 | 1 | 2025-09-28 | 6 | 953029.56 | -77302.74 | DOWN | 0.0883 | 43 | Low | 344267.93 | 0.395 | 1 | 339462.07 | 15 | 1.16 | 1.5
P001 | Services | SUP048 | 2025-10 | 2025-05-20 | 1616878.33 | 822342 | -794536.33 | 794536.33 | 1 | 2025-10-28 | 1 |  |  |  |  | 161 | Low | 192371.02 | 0.122 | 1 | 629970.98 | 18 | 1.81 | 1.33
P001 | Services | SUP048 | 2025-10 | 2025-05-24 | 1383683.17 | 822342 | -561341.17 | 561341.17 | 1 | 2025-10-28 | 2 | 1616878.33 | -233195.16 | DOWN | 0.1685 | 157 | Low | 170120.98 | 0.13 | 0 | 652221.02 | 18 | 1.81 | 1.33
P001 | Services | SUP048 | 2025-10 | 2025-08-09 | 1265732.26 | 822342 | -443390.26 | 443390.26 | 1 | 2025-10-28 | 3 | 1383683.17 | -117950.91 | DOWN | 0.0932 | 80 | Low | 392549.24 | 0.29 | 1 | 429792.76 | 18 | 1.81 | 1.33
P001 | Software | SUP048 | 2025-11 | 2025-06-01 | 1244827.04 | 461954 | -782873.04 | 782873.04 | 1 | 2025-11-28 | 1 |  |  |  |  | 180 | Low | 116555.25 | 0.099 | 0 | 345398.75 | 26 | 1.11 | 1.53
P001 | Software | SUP048 | 2025-11 | 2025-06-11 | 1042255.71 | 461954 | -580301.71 | 580301.71 | 1 | 2025-11-28 | 2 | 1244827.04 | -202571.33 | DOWN | 0.1944 | 170 | Low | 115909.54 | 0.112 | 0 | 346044.46 | 26 | 1.11 | 1.53
P001 | Software | SUP048 | 2025-11 | 2025-07-20 | 893705.76 | 461954 | -431751.76 | 431751.76 | 1 | 2025-11-28 | 3 | 1042255.71 | -148549.95 | DOWN | 0.1662 | 131 | Low | 175490.75 | 0.2 | 1 | 286463.25 | 26 | 1.11 | 1.53
P001 | Software | SUP048 | 2025-11 | 2025-07-23 | 792349.35 | 461954 | -330395.35 | 330395.35 | 1 | 2025-11-28 | 4 | 893705.76 | -101356.41 | DOWN | 0.1279 | 128 | Low | 173209.51 | 0.206 | 3 | 288744.49 | 26 | 1.11 | 1.53
P001 | Software | SUP048 | 2025-11 | 2025-08-20 | 709879.18 | 461954 | -247925.18 | 247925.18 | 1 | 2025-11-28 | 5 | 792349.35 | -82470.17 | DOWN | 0.1162 | 100 | Low | 192601.53 | 0.269 | 3 | 269352.47 | 26 | 1.11 | 1.53
P001 | Software | SUP048 | 2025-11 | 2025-11-03 | 644664.99 | 461954 | -182710.99 | 182710.99 | 1 | 2025-11-28 | 6 | 709879.18 | -65214.19 | DOWN | 0.1012 | 25 | Low | 289983.69 | 0.437 | 2 | 171970.31 | 26 | 1.11 | 1.53
P001 | Logistics | SUP048 | 2025-12 | 2025-07-14 | 2503086.38 | 1067072 | -1436014.38 | 1436014.38 | 1 | 2025-12-28 | 1 |  |  |  |  | 167 | Low | 269353.28 | 0.114 | 6 | 797718.72 | 17 | 1.45 | 1.29
P001 | Logistics | SUP048 | 2025-12 | 2025-09-13 | 2078690.51 | 1067072 | -1011618.51 | 1011618.51 | 1 | 2025-12-28 | 2 | 2503086.38 | -424395.87 | DOWN | 0.2042 | 106 | Low | 507032.33 | 0.246 | 0 | 560039.67 | 17 | 1.45 | 1.29
P001 | Logistics | SUP048 | 2025-12 | 2025-12-07 | 1804680.13 | 1067072 | -737608.13 | 737608.13 | 1 | 2025-12-28 | 3 | 2078690.51 | -274010.38 | DOWN | 0.1518 | 21 | Low | 760306.99 | 0.429 | 2 | 306765.01 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP006 | 2025-01 | 2024-08-27 | 1031938.48 | 572994 | -458944.48 | 458944.48 | 1 | 2025-01-28 | 1 |  |  |  |  | 154 | Low | 157468.38 | 0.148 | 1 | 415525.62 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP006 | 2025-01 | 2024-11-10 | 846797.47 | 572994 | -273803.47 | 273803.47 | 1 | 2025-01-28 | 2 | 1031938.48 | -185141.01 | DOWN | 0.2186 | 79 | Low | 257157.04 | 0.316 | 5 | 315836.96 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP006 | 2025-01 | 2024-12-14 | 745953.18 | 572994 | -172959.18 | 172959.18 | 1 | 2025-01-28 | 3 | 846797.47 | -100844.29 | DOWN | 0.1352 | 45 | Low | 276159.61 | 0.392 | 2 | 296834.39 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP006 | 2025-01 | 2024-12-14 | 666273.01 | 572994 | -93279.01 | 93279.01 | 0 | 2025-01-28 | 4 | 745953.18 | -79680.17 | DOWN | 0.1196 | 45 | Low | 260339.85 | 0.392 | 4 | 312654.15 | 19 | 1.97 | 1.9
P001 | Materials | SUP006 | 2025-02 | 2024-09-27 | 4266829.35 | 2259682 | -2007147.35 | 2007147.35 | 1 | 2025-02-28 | 1 |  |  |  |  | 154 | Low | 660603.57 | 0.15 | 2 | 1599078.43 | 18 | 1.81 | 1.54
P001 | Materials | SUP006 | 2025-02 | 2024-09-29 | 3508549.85 | 2259682 | -1248867.85 | 1248867.85 | 1 | 2025-02-28 | 2 | 4266829.35 | -758279.5 | DOWN | 0.2161 | 152 | Low | 521667.89 | 0.155 | 0 | 1738014.11 | 18 | 1.81 | 1.54
P001 | Materials | SUP006 | 2025-02 | 2024-10-25 | 3023887.63 | 2259682 | -764205.63 | 764205.63 | 1 | 2025-02-28 | 3 | 3508549.85 | -484662.22 | DOWN | 0.1603 | 126 | Low | 644140.59 | 0.214 | 2 | 1615541.41 | 18 | 1.81 | 1.54
P001 | Materials | SUP006 | 2025-02 | 2024-12-11 | 2696569.21 | 2259682 | -436887.21 | 436887.21 | 1 | 2025-02-28 | 4 | 3023887.63 | -327318.42 | DOWN | 0.1214 | 79 | Low | 840444.45 | 0.321 | 1 | 1419237.55 | 18 | 1.81 | 1.54
P001 | Materials | SUP006 | 2025-02 | 2024-12-14 | 2513290.15 | 2259682 | -253608.15 | 253608.15 | 0 | 2025-02-28 | 5 | 2696569.21 | -183279.06 | DOWN | 0.0729 | 76 | Low | 784808.82 | 0.328 | 7 | 1474873.18 | 18 | 1.81 | 1.54
P001 | Materials | SUP006 | 2025-02 | 2024-12-15 | 2458993.09 | 2259682 | -199311.09 | 199311.09 | 0 | 2025-02-28 | 6 | 2513290.15 | -54297.06 | DOWN | 0.0221 | 75 | Low | 775908.78 | 0.33 | 1 | 1483773.22 | 18 | 1.81 | 1.54
P001 | Services | SUP006 | 2025-03 | 2025-01-07 | 4049878.31 | 2183367 | -1866511.31 | 1866511.31 | 1 | 2025-03-28 | 1 |  |  |  |  | 80 | Low | 1482976.01 | 0.35 | 1 | 700390.99 | 20 | 0.93 | 1.57
P001 | Services | SUP006 | 2025-03 | 2025-02-01 | 3289141.1 | 2183367 | -1105774.1 | 1105774.1 | 1 | 2025-03-28 | 2 | 4049878.31 | -760737.21 | DOWN | 0.2313 | 55 | Low | 1269501.05 | 0.413 | 1 | 913865.95 | 20 | 0.93 | 1.57
P001 | Services | SUP006 | 2025-03 | 2025-02-16 | 2797716.94 | 2183367 | -614349.94 | 614349.94 | 1 | 2025-03-28 | 3 | 3289141.1 | -491424.16 | DOWN | 0.1757 | 40 | Low | 1218313.85 | 0.45 | 2 | 965053.15 | 20 | 0.93 | 1.57
P001 | Services | SUP006 | 2025-03 | 2025-02-20 | 2552417.38 | 2183367 | -369050.38 | 369050.38 | 0 | 2025-03-28 | 4 | 2797716.94 | -245299.56 | DOWN | 0.0961 | 36 | Medium | 1100054.18 | 0.46 | 2 | 1083312.82 | 20 | 0.93 | 1.57
P001 | Services | SUP006 | 2025-03 | 2025-02-26 | 2430278.48 | 2183367 | -246911.48 | 246911.48 | 0 | 2025-03-28 | 5 | 2552417.38 | -122138.9 | DOWN | 0.0503 | 30 | Medium | 1070640 | 0.475 | 4 | 1112727 | 20 | 0.93 | 1.57
P001 | Services | SUP006 | 2025-04 | 2024-12-26 | 3376759.77 | 1712534 | -1664225.77 | 1664225.77 | 1 | 2025-04-28 | 1 |  |  |  |  | 123 | Low | 718986.28 | 0.211 | 4 | 993547.72 | 22 | 2.23 | 1.91
P001 | Services | SUP006 | 2025-04 | 2025-02-02 | 2736793.4 | 1712534 | -1024259.4 | 1024259.4 | 1 | 2025-04-28 | 2 | 3376759.77 | -639966.37 | DOWN | 0.2338 | 85 | Low | 868791.25 | 0.294 | 7 | 843742.75 | 22 | 2.23 | 1.91
P001 | Services | SUP006 | 2025-04 | 2025-03-12 | 2417451.6 | 1712534 | -704917.6 | 704917.6 | 1 | 2025-04-28 | 3 | 2736793.4 | -319341.8 | DOWN | 0.1321 | 47 | Low | 841763.48 | 0.377 | 1 | 870770.52 | 22 | 2.23 | 1.91
P001 | Services | SUP006 | 2025-04 | 2025-03-19 | 2094936.9 | 1712534 | -382402.9 | 382402.9 | 1 | 2025-04-28 | 4 | 2417451.6 | -322514.7 | DOWN | 0.1539 | 40 | Low | 810403.44 | 0.392 | 0 | 902130.56 | 22 | 2.23 | 1.91
P001 | Services | SUP006 | 2025-04 | 2025-03-28 | 1913798.32 | 1712534 | -201264.32 | 201264.32 | 0 | 2025-04-28 | 5 | 2094936.9 | -181138.58 | DOWN | 0.0946 | 31 | Low | 796733.52 | 0.412 | 0 | 915800.48 | 22 | 2.23 | 1.91
P001 | Electronics | SUP006 | 2025-05 | 2024-12-15 | 5462723.9 | 2389357 | -3073366.9 | 3073366.9 | 1 | 2025-05-28 | 1 |  |  |  |  | 164 | Low | 664889.01 | 0.127 | 1 | 1724467.99 | 21 | 1.86 | 0.96
P001 | Electronics | SUP006 | 2025-05 | 2024-12-15 | 4130176.6 | 2389357 | -1740819.6 | 1740819.6 | 1 | 2025-05-28 | 2 | 5462723.9 | -1332547.3 | DOWN | 0.3226 | 164 | Low | 546054.46 | 0.127 | 5 | 1843302.54 | 21 | 1.86 | 0.96
P001 | Electronics | SUP006 | 2025-05 | 2025-04-09 | 3409919.07 | 2389357 | -1020562.07 | 1020562.07 | 1 | 2025-05-28 | 3 | 4130176.6 | -720257.53 | DOWN | 0.2112 | 49 | Low | 1293696.82 | 0.388 | 0 | 1095660.18 | 21 | 1.86 | 0.96
P001 | Electronics | SUP006 | 2025-05 | 2025-05-10 | 2955697.98 | 2389357 | -566340.98 | 566340.98 | 1 | 2025-05-28 | 4 | 3409919.07 | -454221.09 | DOWN | 0.1537 | 18 | Low | 1358570.51 | 0.458 | 3 | 1030786.49 | 21 | 1.86 | 0.96
P001 | Electronics | SUP006 | 2025-05 | 2025-05-13 | 2679333.14 | 2389357 | -289976.14 | 289976.14 | 0 | 2025-05-28 | 5 | 2955697.98 | -276364.84 | DOWN | 0.1031 | 15 | Medium | 1217560.28 | 0.465 | 0 | 1171796.72 | 21 | 1.86 | 0.96
P001 | Logistics | SUP006 | 2025-06 | 2025-01-24 | 2546561.25 | 1258559 | -1288002.25 | 1288002.25 | 1 | 2025-06-28 | 1 |  |  |  |  | 155 | Low | 408272.22 | 0.149 | 0 | 850286.78 | 18 | 1.75 | 1.8
P001 | Logistics | SUP006 | 2025-06 | 2025-01-28 | 1993758.35 | 1258559 | -735199.35 | 735199.35 | 1 | 2025-06-28 | 2 | 2546561.25 | -552802.9 | DOWN | 0.2773 | 151 | Low | 302257.43 | 0.158 | 1 | 956301.57 | 18 | 1.75 | 1.8
P001 | Logistics | SUP006 | 2025-06 | 2025-02-26 | 1699603.48 | 1258559 | -441044.48 | 441044.48 | 1 | 2025-06-28 | 3 | 1993758.35 | -294154.87 | DOWN | 0.1731 | 122 | Low | 374263.64 | 0.225 | 3 | 884295.36 | 18 | 1.75 | 1.8
P001 | Logistics | SUP006 | 2025-06 | 2025-03-02 | 1471202.16 | 1258559 | -212643.16 | 212643.16 | 0 | 2025-06-28 | 4 | 1699603.48 | -228401.32 | DOWN | 0.1552 | 118 | Low | 365844.14 | 0.234 | 0 | 892714.86 | 18 | 1.75 | 1.8
P001 | Logistics | SUP006 | 2025-06 | 2025-04-27 | 1355109.21 | 1258559 | -96550.21 | 96550.21 | 0 | 2025-06-28 | 5 | 1471202.16 | -116092.95 | DOWN | 0.0857 | 62 | Low | 464938.73 | 0.362 | 1 | 793620.27 | 18 | 1.75 | 1.8
P001 | Logistics | SUP006 | 2025-06 | 2025-06-07 | 1312939.43 | 1258559 | -54380.43 | 54380.43 | 0 | 2025-06-28 | 6 | 1355109.21 | -42169.78 | DOWN | 0.0321 | 21 | Medium | 584510.41 | 0.456 | 4 | 674048.59 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP006 | 2025-07 | 2025-04-08 | 447284.89 | 280776 | -166508.89 | 166508.89 | 1 | 2025-07-28 | 1 |  |  |  |  | 111 | Low | 117617.14 | 0.264 | 3 | 163158.86 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP006 | 2025-07 | 2025-04-14 | 381642.01 | 280776 | -100866.01 | 100866.01 | 1 | 2025-07-28 | 2 | 447284.89 | -65642.88 | DOWN | 0.172 | 105 | Low | 109977.29 | 0.278 | 3 | 170798.71 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP006 | 2025-07 | 2025-05-05 | 341143.17 | 280776 | -60367.17 | 60367.17 | 1 | 2025-07-28 | 3 | 381642.01 | -40498.84 | DOWN | 0.1187 | 84 | Low | 113606.94 | 0.329 | 4 | 167169.06 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP006 | 2025-07 | 2025-05-31 | 313447.76 | 280776 | -32671.76 | 32671.76 | 0 | 2025-07-28 | 4 | 341143.17 | -27695.41 | DOWN | 0.0884 | 58 | Low | 123905.29 | 0.392 | 2 | 156870.71 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP006 | 2025-08 | 2025-05-06 | 3536165.74 | 1991790 | -1544375.74 | 1544375.74 | 1 | 2025-08-28 | 1 |  |  |  |  | 114 | Low | 823711.47 | 0.249 | 4 | 1168078.53 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP006 | 2025-08 | 2025-08-01 | 2944313.05 | 1991790 | -952523.05 | 952523.05 | 1 | 2025-08-28 | 2 | 3536165.74 | -591852.69 | DOWN | 0.201 | 27 | Low | 1322624.79 | 0.453 | 7 | 669165.21 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP006 | 2025-08 | 2025-08-13 | 2550473.8 | 1991790 | -558683.8 | 558683.8 | 1 | 2025-08-28 | 3 | 2944313.05 | -393839.25 | DOWN | 0.1544 | 15 | Low | 1313446.08 | 0.481 | 3 | 678343.92 | 21 | 1.54 | 1.03
P001 | Electronics | SUP006 | 2025-09 | 2025-04-03 | 5775916.73 | 2841509 | -2934407.73 | 2934407.73 | 1 | 2025-09-28 | 1 |  |  |  |  | 178 | Low | 604666.56 | 0.108 | 2 | 2236842.44 | 15 | 1.16 | 1.5
P001 | Electronics | SUP006 | 2025-09 | 2025-04-18 | 4642393.8 | 2841509 | -1800884.8 | 1800884.8 | 1 | 2025-09-28 | 2 | 5775916.73 | -1133522.93 | DOWN | 0.2442 | 163 | Low | 609189.31 | 0.14 | 1 | 2232319.69 | 15 | 1.16 | 1.5
P001 | Electronics | SUP006 | 2025-09 | 2025-06-01 | 3944046.95 | 2841509 | -1102537.95 | 1102537.95 | 1 | 2025-09-28 | 3 | 4642393.8 | -698346.85 | DOWN | 0.1771 | 119 | Low | 1005077.23 | 0.248 | 0 | 1836431.77 | 15 | 1.16 | 1.5
P001 | Electronics | SUP006 | 2025-09 | 2025-09-02 | 3535270.35 | 2841509 | -693761.35 | 693761.35 | 1 | 2025-09-28 | 4 | 3944046.95 | -408776.6 | DOWN | 0.1156 | 26 | Medium | 1787511.03 | 0.476 | 1 | 1053997.97 | 15 | 1.16 | 1.5
P001 | Electronics | SUP006 | 2025-09 | 2025-09-07 | 3261242.81 | 2841509 | -419733.81 | 419733.81 | 0 | 2025-09-28 | 5 | 3535270.35 | -274027.54 | DOWN | 0.084 | 21 | Medium | 1547473.12 | 0.488 | 0 | 1294035.88 | 15 | 1.16 | 1.5
P001 | Electronics | SUP006 | 2025-10 | 2025-05-01 | 1203352.12 | 575639 | -627713.12 | 627713.12 | 1 | 2025-10-28 | 1 |  |  |  |  | 180 | Low | 123704.76 | 0.1 | 0 | 451934.24 | 18 | 1.81 | 1.33
P001 | Electronics | SUP006 | 2025-10 | 2025-06-15 | 964950.44 | 575639 | -389311.44 | 389311.44 | 1 | 2025-10-28 | 2 | 1203352.12 | -238401.68 | DOWN | 0.2471 | 135 | Low | 182488.92 | 0.194 | 4 | 393150.08 | 18 | 1.81 | 1.33
P001 | Electronics | SUP006 | 2025-10 | 2025-06-30 | 802987.6 | 575639 | -227348.6 | 227348.6 | 1 | 2025-10-28 | 3 | 964950.44 | -161962.84 | DOWN | 0.2017 | 120 | Low | 188049.6 | 0.228 | 5 | 387589.4 | 18 | 1.81 | 1.33
P001 | Electronics | SUP006 | 2025-10 | 2025-09-04 | 715192.73 | 575639 | -139553.73 | 139553.73 | 1 | 2025-10-28 | 4 | 802987.6 | -87794.87 | DOWN | 0.1228 | 54 | Low | 272981.39 | 0.378 | 0 | 302657.61 | 18 | 1.81 | 1.33
P001 | Electronics | SUP006 | 2025-10 | 2025-09-10 | 664912.85 | 575639 | -89273.85 | 89273.85 | 0 | 2025-10-28 | 5 | 715192.73 | -50279.88 | DOWN | 0.0756 | 48 | Low | 260354.32 | 0.392 | 0 | 315284.68 | 18 | 1.81 | 1.33
P001 | Electronics | SUP006 | 2025-11 | 2025-07-07 | 2272667.22 | 1430215 | -842452.22 | 842452.22 | 1 | 2025-11-28 | 1 |  |  |  |  | 144 | Low | 446332.5 | 0.188 | 4 | 983882.5 | 26 | 1.11 | 1.53
P001 | Electronics | SUP006 | 2025-11 | 2025-07-20 | 1949633.95 | 1430215 | -519418.95 | 519418.95 | 1 | 2025-11-28 | 2 | 2272667.22 | -323033.27 | DOWN | 0.1657 | 131 | Low | 417606.46 | 0.22 | 0 | 1012608.54 | 26 | 1.11 | 1.53
P001 | Electronics | SUP006 | 2025-11 | 2025-08-13 | 1730318.66 | 1430215 | -300103.66 | 300103.66 | 1 | 2025-11-28 | 3 | 1949633.95 | -219315.29 | DOWN | 0.1267 | 107 | Low | 462285.46 | 0.279 | 1 | 967929.54 | 26 | 1.11 | 1.53
P001 | Electronics | SUP006 | 2025-11 | 2025-09-08 | 1627815.37 | 1430215 | -197600.37 | 197600.37 | 0 | 2025-11-28 | 4 | 1730318.66 | -102503.29 | DOWN | 0.063 | 81 | Low | 533948.46 | 0.343 | 5 | 896266.54 | 26 | 1.11 | 1.53
P001 | Electronics | SUP006 | 2025-11 | 2025-10-10 | 1560002.14 | 1430215 | -129787.14 | 129787.14 | 0 | 2025-11-28 | 5 | 1627815.37 | -67813.23 | DOWN | 0.0435 | 49 | Low | 709001.01 | 0.422 | 2 | 721213.99 | 26 | 1.11 | 1.53
P001 | Software | SUP006 | 2025-12 | 2025-08-05 | 610501.06 | 311424 | -299077.06 | 299077.06 | 1 | 2025-12-28 | 1 |  |  |  |  | 145 | Low | 101579.69 | 0.178 | 3 | 209844.31 | 17 | 1.45 | 1.29
P001 | Software | SUP006 | 2025-12 | 2025-08-15 | 485912.22 | 311424 | -174488.22 | 174488.22 | 1 | 2025-12-28 | 2 | 610501.06 | -124588.84 | DOWN | 0.2564 | 135 | Low | 93719.8 | 0.202 | 0 | 217704.2 | 17 | 1.45 | 1.29
P001 | Software | SUP006 | 2025-12 | 2025-12-14 | 417333.12 | 311424 | -105909.12 | 105909.12 | 1 | 2025-12-28 | 3 | 485912.22 | -68579.1 | DOWN | 0.1643 | 14 | Low | 194392.2 | 0.489 | 5 | 117031.8 | 17 | 1.45 | 1.29
P001 | Services | SUP049 | 2025-01 | 2024-09-30 | 2644199.03 | 1163958 | -1480241.03 | 1480241.03 | 1 | 2025-01-28 | 1 |  |  |  |  | 120 | Low | 553025.9 | 0.224 | 1 | 610932.1 | 19 | 1.97 | 1.9
P001 | Services | SUP049 | 2025-01 | 2024-10-05 | 1984367.64 | 1163958 | -820409.64 | 820409.64 | 1 | 2025-01-28 | 2 | 2644199.03 | -659831.39 | DOWN | 0.3325 | 115 | Low | 473179.28 | 0.235 | 0 | 690778.72 | 19 | 1.97 | 1.9
P001 | Services | SUP049 | 2025-01 | 2024-10-22 | 1632351.64 | 1163958 | -468393.64 | 468393.64 | 1 | 2025-01-28 | 3 | 1984367.64 | -352016 | DOWN | 0.2156 | 98 | Low | 421711.77 | 0.273 | 1 | 742246.23 | 19 | 1.97 | 1.9
P001 | Services | SUP049 | 2025-01 | 2024-11-21 | 1418327.67 | 1163958 | -254369.67 | 254369.67 | 1 | 2025-01-28 | 4 | 1632351.64 | -214023.97 | DOWN | 0.1509 | 68 | Low | 458439.22 | 0.34 | 2 | 705518.78 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP049 | 2025-02 | 2024-10-28 | 3283885.14 | 1859572 | -1424313.14 | 1424313.14 | 1 | 2025-02-28 | 1 |  |  |  |  | 123 | Low | 691121.68 | 0.221 | 0 | 1168450.32 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP049 | 2025-02 | 2025-01-11 | 2725913.89 | 1859572 | -866341.89 | 866341.89 | 1 | 2025-02-28 | 2 | 3283885.14 | -557971.25 | DOWN | 0.2047 | 48 | Low | 1073994.48 | 0.392 | 5 | 785577.52 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP049 | 2025-02 | 2025-02-12 | 2357456.14 | 1859572 | -497884.14 | 497884.14 | 1 | 2025-02-28 | 3 | 2725913.89 | -368457.75 | DOWN | 0.1563 | 16 | Low | 1121240.53 | 0.465 | 3 | 738331.47 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP049 | 2025-03 | 2024-10-09 | 2659081.54 | 1629989 | -1029092.54 | 1029092.54 | 1 | 2025-03-28 | 1 |  |  |  |  | 170 | Low | 352380.9 | 0.125 | 4 | 1277608.1 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP049 | 2025-03 | 2024-12-03 | 2257317.6 | 1629989 | -627328.6 | 627328.6 | 1 | 2025-03-28 | 2 | 2659081.54 | -401763.94 | DOWN | 0.178 | 115 | Low | 549132.94 | 0.263 | 1 | 1080856.06 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP049 | 2025-03 | 2024-12-07 | 2011057.3 | 1629989 | -381068.3 | 381068.3 | 1 | 2025-03-28 | 3 | 2257317.6 | -246260.3 | DOWN | 0.1225 | 111 | Low | 506609.23 | 0.273 | 3 | 1123379.77 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP049 | 2025-03 | 2024-12-11 | 1848636.97 | 1629989 | -218647.97 | 218647.97 | 0 | 2025-03-28 | 4 | 2011057.3 | -162420.33 | DOWN | 0.0879 | 107 | Low | 558468.67 | 0.283 | 0 | 1071520.33 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP049 | 2025-03 | 2024-12-11 | 1750818.5 | 1629989 | -120829.5 | 120829.5 | 0 | 2025-03-28 | 5 | 1848636.97 | -97818.47 | DOWN | 0.0559 | 107 | Low | 471081.96 | 0.283 | 2 | 1158907.04 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP049 | 2025-03 | 2025-02-25 | 1710847.55 | 1629989 | -80858.55 | 80858.55 | 0 | 2025-03-28 | 6 | 1750818.5 | -39970.95 | DOWN | 0.0234 | 31 | Medium | 793550.36 | 0.473 | 4 | 836438.64 | 20 | 0.93 | 1.57
P001 | Materials | SUP049 | 2025-04 | 2024-11-09 | 2755201.83 | 1268197 | -1487004.83 | 1487004.83 | 1 | 2025-04-28 | 1 |  |  |  |  | 170 | Low | 289397.6 | 0.109 | 2 | 978799.4 | 22 | 2.23 | 1.91
P001 | Materials | SUP049 | 2025-04 | 2024-12-01 | 2196495.96 | 1268197 | -928298.96 | 928298.96 | 1 | 2025-04-28 | 2 | 2755201.83 | -558705.87 | DOWN | 0.2544 | 148 | Low | 327222.68 | 0.157 | 0 | 940974.32 | 22 | 2.23 | 1.91
P001 | Materials | SUP049 | 2025-04 | 2024-12-16 | 1833382.23 | 1268197 | -565185.23 | 565185.23 | 1 | 2025-04-28 | 3 | 2196495.96 | -363113.73 | DOWN | 0.1981 | 133 | Low | 336525.84 | 0.19 | 0 | 931671.16 | 22 | 2.23 | 1.91
P001 | Materials | SUP049 | 2025-04 | 2024-12-16 | 1592148.83 | 1268197 | -323951.83 | 323951.83 | 1 | 2025-04-28 | 4 | 1833382.23 | -241233.4 | DOWN | 0.1515 | 133 | Low | 323390.42 | 0.19 | 0 | 944806.58 | 22 | 2.23 | 1.91
P001 | Materials | SUP049 | 2025-04 | 2024-12-28 | 1493143.68 | 1268197 | -224946.68 | 224946.68 | 1 | 2025-04-28 | 5 | 1592148.83 | -99005.15 | DOWN | 0.0663 | 121 | Low | 302220.34 | 0.216 | 4 | 965976.66 | 22 | 2.23 | 1.91
P001 | Materials | SUP049 | 2025-04 | 2025-03-28 | 1382330.06 | 1268197 | -114133.06 | 114133.06 | 0 | 2025-04-28 | 6 | 1493143.68 | -110813.62 | DOWN | 0.0802 | 31 | Low | 577593.18 | 0.412 | 2 | 690603.82 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP049 | 2025-05 | 2024-12-24 | 1569951.22 | 944350 | -625601.22 | 625601.22 | 1 | 2025-05-28 | 1 |  |  |  |  | 155 | Low | 220619.32 | 0.147 | 2 | 723730.68 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP049 | 2025-05 | 2024-12-26 | 1335448.18 | 944350 | -391098.18 | 391098.18 | 1 | 2025-05-28 | 2 | 1569951.22 | -234503.04 | DOWN | 0.1756 | 153 | Low | 215951.78 | 0.152 | 4 | 728398.22 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP049 | 2025-05 | 2025-02-14 | 1159275.73 | 944350 | -214925.73 | 214925.73 | 1 | 2025-05-28 | 3 | 1335448.18 | -176172.45 | DOWN | 0.152 | 103 | Low | 310635.29 | 0.265 | 0 | 633714.71 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP049 | 2025-05 | 2025-02-22 | 1056142.09 | 944350 | -111792.09 | 111792.09 | 0 | 2025-05-28 | 4 | 1159275.73 | -103133.64 | DOWN | 0.0977 | 95 | Low | 287851.19 | 0.283 | 1 | 656498.81 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP049 | 2025-05 | 2025-03-15 | 1019746.18 | 944350 | -75396.18 | 75396.18 | 0 | 2025-05-28 | 5 | 1056142.09 | -36395.91 | DOWN | 0.0357 | 74 | Low | 330415.58 | 0.331 | 4 | 613934.42 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP049 | 2025-05 | 2025-04-16 | 992052.35 | 944350 | -47702.35 | 47702.35 | 0 | 2025-05-28 | 6 | 1019746.18 | -27693.83 | DOWN | 0.0279 | 42 | Low | 377190.9 | 0.403 | 3 | 567159.1 | 21 | 1.86 | 0.96
P001 | Materials | SUP049 | 2025-06 | 2025-02-02 | 904829.56 | 562190 | -342639.56 | 342639.56 | 1 | 2025-06-28 | 1 |  |  |  |  | 146 | Low | 156152.44 | 0.17 | 1 | 406037.56 | 18 | 1.75 | 1.8
P001 | Materials | SUP049 | 2025-06 | 2025-02-25 | 773980.29 | 562190 | -211790.29 | 211790.29 | 1 | 2025-06-28 | 2 | 904829.56 | -130849.27 | DOWN | 0.1691 | 123 | Low | 170499.98 | 0.222 | 2 | 391690.02 | 18 | 1.75 | 1.8
P001 | Materials | SUP049 | 2025-06 | 2025-03-12 | 682721.53 | 562190 | -120531.53 | 120531.53 | 1 | 2025-06-28 | 3 | 773980.29 | -91258.76 | DOWN | 0.1337 | 108 | Low | 175019.53 | 0.257 | 2 | 387170.47 | 18 | 1.75 | 1.8
P001 | Materials | SUP049 | 2025-06 | 2025-04-09 | 636913.35 | 562190 | -74723.35 | 74723.35 | 0 | 2025-06-28 | 4 | 682721.53 | -45808.18 | DOWN | 0.0719 | 80 | Low | 216141.28 | 0.321 | 3 | 346048.72 | 18 | 1.75 | 1.8
P001 | Materials | SUP049 | 2025-06 | 2025-05-10 | 604003.4 | 562190 | -41813.4 | 41813.4 | 0 | 2025-06-28 | 5 | 636913.35 | -32909.95 | DOWN | 0.0545 | 49 | Low | 237968.64 | 0.392 | 6 | 324221.36 | 18 | 1.75 | 1.8
P001 | Materials | SUP049 | 2025-06 | 2025-05-26 | 579841.1 | 562190 | -17651.1 | 17651.1 | 0 | 2025-06-28 | 6 | 604003.4 | -24162.3 | DOWN | 0.0417 | 33 | Low | 232169.22 | 0.429 | 3 | 330020.78 | 18 | 1.75 | 1.8
P001 | Services | SUP049 | 2025-07 | 2025-02-26 | 1730695.55 | 826619 | -904076.55 | 904076.55 | 1 | 2025-07-28 | 1 |  |  |  |  | 152 | Low | 288284.23 | 0.165 | 0 | 538334.77 | 17 | 1.27 | 1.46
P001 | Services | SUP049 | 2025-07 | 2025-03-24 | 1383712.48 | 826619 | -557093.48 | 557093.48 | 1 | 2025-07-28 | 2 | 1730695.55 | -346983.07 | DOWN | 0.2508 | 126 | Low | 289798.03 | 0.228 | 3 | 536820.97 | 17 | 1.27 | 1.46
P001 | Services | SUP049 | 2025-07 | 2025-05-14 | 1163133.08 | 826619 | -336514.08 | 336514.08 | 1 | 2025-07-28 | 3 | 1383712.48 | -220579.4 | DOWN | 0.1896 | 75 | Low | 430667.03 | 0.351 | 4 | 395951.97 | 17 | 1.27 | 1.46
P001 | Services | SUP049 | 2025-07 | 2025-07-14 | 1038045.92 | 826619 | -211426.92 | 211426.92 | 1 | 2025-07-28 | 4 | 1163133.08 | -125087.16 | DOWN | 0.1205 | 14 | Low | 491579.03 | 0.499 | 2 | 335039.97 | 17 | 1.27 | 1.46
P001 | Software | SUP049 | 2025-08 | 2025-04-11 | 5245715.35 | 2149275 | -3096440.35 | 3096440.35 | 1 | 2025-08-28 | 1 |  |  |  |  | 139 | Low | 1011956.15 | 0.19 | 2 | 1137318.85 | 21 | 1.54 | 1.03
P001 | Software | SUP049 | 2025-08 | 2025-05-21 | 4040656.29 | 2149275 | -1891381.29 | 1891381.29 | 1 | 2025-08-28 | 2 | 5245715.35 | -1205059.06 | DOWN | 0.2982 | 99 | Low | 1112253.48 | 0.284 | 1 | 1037021.52 | 21 | 1.54 | 1.03
P001 | Software | SUP049 | 2025-08 | 2025-07-21 | 3370215.16 | 2149275 | -1220940.16 | 1220940.16 | 1 | 2025-08-28 | 3 | 4040656.29 | -670441.13 | DOWN | 0.1989 | 38 | Low | 1530795.95 | 0.427 | 8 | 618479.05 | 21 | 1.54 | 1.03
P001 | Electronics | SUP049 | 2025-09 | 2025-04-23 | 3772593.73 | 1971898 | -1800695.73 | 1800695.73 | 1 | 2025-09-28 | 1 |  |  |  |  | 158 | Low | 569247.99 | 0.152 | 0 | 1402650.01 | 15 | 1.16 | 1.5
P001 | Electronics | SUP049 | 2025-09 | 2025-05-12 | 3081126.5 | 1971898 | -1109228.5 | 1109228.5 | 1 | 2025-09-28 | 2 | 3772593.73 | -691467.23 | DOWN | 0.2244 | 139 | Low | 568224.12 | 0.199 | 0 | 1403673.88 | 15 | 1.16 | 1.5
P001 | Electronics | SUP049 | 2025-09 | 2025-07-24 | 2634211.06 | 1971898 | -662313.06 | 662313.06 | 1 | 2025-09-28 | 3 | 3081126.5 | -446915.44 | DOWN | 0.1697 | 66 | Low | 972192.15 | 0.378 | 2 | 999705.85 | 15 | 1.16 | 1.5
P001 | Electronics | SUP049 | 2025-09 | 2025-08-08 | 2371840.93 | 1971898 | -399942.93 | 399942.93 | 1 | 2025-09-28 | 4 | 2634211.06 | -262370.13 | DOWN | 0.1106 | 51 | Low | 949690.21 | 0.415 | 3 | 1022207.79 | 15 | 1.16 | 1.5
P001 | Electronics | SUP049 | 2025-09 | 2025-08-14 | 2198724.12 | 1971898 | -226826.12 | 226826.12 | 0 | 2025-09-28 | 5 | 2371840.93 | -173116.81 | DOWN | 0.0787 | 45 | Low | 886711.08 | 0.429 | 4 | 1085186.92 | 15 | 1.16 | 1.5
P001 | Electronics | SUP049 | 2025-10 | 2025-05-02 | 1896507.3 | 1043507 | -853000.3 | 853000.3 | 1 | 2025-10-28 | 1 |  |  |  |  | 179 | Low | 183007.02 | 0.1 | 2 | 860499.98 | 18 | 1.81 | 1.33
P001 | Electronics | SUP049 | 2025-10 | 2025-06-04 | 1592843.18 | 1043507 | -549336.18 | 549336.18 | 1 | 2025-10-28 | 2 | 1896507.3 | -303664.12 | DOWN | 0.1906 | 146 | Low | 271825.06 | 0.169 | 0 | 771681.94 | 18 | 1.81 | 1.33
P001 | Electronics | SUP049 | 2025-10 | 2025-07-25 | 1392613.26 | 1043507 | -349106.26 | 349106.26 | 1 | 2025-10-28 | 3 | 1592843.18 | -200229.92 | DOWN | 0.1438 | 95 | Low | 414923.76 | 0.285 | 4 | 628583.24 | 18 | 1.81 | 1.33
P001 | Electronics | SUP049 | 2025-10 | 2025-10-04 | 1258749.02 | 1043507 | -215242.02 | 215242.02 | 1 | 2025-10-28 | 4 | 1392613.26 | -133864.24 | DOWN | 0.1063 | 24 | Low | 540907.91 | 0.447 | 3 | 502599.09 | 18 | 1.81 | 1.33
P001 | Mechanical | SUP049 | 2025-11 | 2025-07-14 | 3301906.98 | 2086674 | -1215232.98 | 1215232.98 | 1 | 2025-11-28 | 1 |  |  |  |  | 137 | Low | 664596.61 | 0.205 | 3 | 1422077.39 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP049 | 2025-11 | 2025-08-04 | 2826168.15 | 2086674 | -739494.15 | 739494.15 | 1 | 2025-11-28 | 2 | 3301906.98 | -475738.83 | DOWN | 0.1683 | 116 | Low | 702713.6 | 0.257 | 0 | 1383960.4 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP049 | 2025-11 | 2025-08-06 | 2520957.74 | 2086674 | -434283.74 | 434283.74 | 1 | 2025-11-28 | 3 | 2826168.15 | -305210.41 | DOWN | 0.1211 | 114 | Low | 696767.88 | 0.262 | 3 | 1389906.12 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP049 | 2025-11 | 2025-10-22 | 2349952.49 | 2086674 | -263278.49 | 263278.49 | 0 | 2025-11-28 | 4 | 2520957.74 | -171005.25 | DOWN | 0.0728 | 37 | Medium | 1118310.01 | 0.452 | 0 | 968363.99 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP049 | 2025-11 | 2025-11-07 | 2250329.96 | 2086674 | -163655.96 | 163655.96 | 0 | 2025-11-28 | 5 | 2349952.49 | -99622.53 | DOWN | 0.0443 | 21 | Medium | 1170988.88 | 0.491 | 7 | 915685.12 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP049 | 2025-11 | 2025-11-18 | 2188010.58 | 2086674 | -101336.58 | 101336.58 | 0 | 2025-11-28 | 6 | 2250329.96 | -62319.38 | DOWN | 0.0285 | 10 | Medium | 1077648.57 | 0.516 | 5 | 1009025.43 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP049 | 2025-12 | 2025-08-18 | 3091286.52 | 1708212 | -1383074.52 | 1383074.52 | 1 | 2025-12-28 | 1 |  |  |  |  | 132 | Low | 673149.54 | 0.209 | 0 | 1035062.46 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP049 | 2025-12 | 2025-09-06 | 2553991.27 | 1708212 | -845779.27 | 845779.27 | 1 | 2025-12-28 | 2 | 3091286.52 | -537295.25 | DOWN | 0.2104 | 113 | Low | 686374.52 | 0.254 | 0 | 1021837.48 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP049 | 2025-12 | 2025-11-14 | 2228357.06 | 1708212 | -520145.06 | 520145.06 | 1 | 2025-12-28 | 3 | 2553991.27 | -325634.21 | DOWN | 0.1461 | 44 | Low | 893290.15 | 0.417 | 2 | 814921.85 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP049 | 2025-12 | 2025-12-02 | 2008367.89 | 1708212 | -300155.89 | 300155.89 | 0 | 2025-12-28 | 4 | 2228357.06 | -219989.17 | DOWN | 0.1095 | 26 | Medium | 980017.47 | 0.46 | 0 | 728194.53 | 17 | 1.45 | 1.29
P001 | Materials | SUP031 | 2025-01 | 2024-08-07 | 3548226.11 | 2023984 | -1524242.11 | 1524242.11 | 1 | 2025-01-28 | 1 |  |  |  |  | 174 | Low | 548012.71 | 0.146 | 4 | 1475971.29 | 19 | 1.97 | 1.9
P001 | Materials | SUP031 | 2025-01 | 2024-08-19 | 2727737.5 | 2023984 | -703753.5 | 703753.5 | 1 | 2025-01-28 | 2 | 3548226.11 | -820488.61 | DOWN | 0.3008 | 162 | Low | 540035.69 | 0.184 | 3 | 1483948.31 | 19 | 1.97 | 1.9
P001 | Materials | SUP031 | 2025-01 | 2024-10-18 | 2350875.86 | 2023984 | -326891.86 | 326891.86 | 0 | 2025-01-28 | 3 | 2727737.5 | -376861.64 | DOWN | 0.1603 | 102 | Low | 928531.39 | 0.375 | 0 | 1095452.61 | 19 | 1.97 | 1.9
P001 | Materials | SUP031 | 2025-02 | 2024-10-01 | 5188970.1 | 2647184 | -2541786.1 | 2541786.1 | 1 | 2025-02-28 | 1 |  |  |  |  | 150 | Low | 1253662.15 | 0.226 | 0 | 1393521.85 | 18 | 1.81 | 1.54
P001 | Materials | SUP031 | 2025-02 | 2024-10-06 | 3675646.95 | 2647184 | -1028462.95 | 1028462.95 | 1 | 2025-02-28 | 2 | 5188970.1 | -1513323.15 | DOWN | 0.4117 | 145 | Low | 958612.07 | 0.242 | 0 | 1688571.93 | 18 | 1.81 | 1.54
P001 | Materials | SUP031 | 2025-02 | 2024-10-28 | 3188989.83 | 2647184 | -541805.83 | 541805.83 | 1 | 2025-02-28 | 3 | 3675646.95 | -486657.12 | DOWN | 0.1526 | 123 | Low | 1072962.37 | 0.313 | 1 | 1574221.63 | 18 | 1.81 | 1.54
P001 | Materials | SUP031 | 2025-02 | 2025-01-07 | 2919877.71 | 2647184 | -272693.71 | 272693.71 | 0 | 2025-02-28 | 4 | 3188989.83 | -269112.12 | DOWN | 0.0922 | 52 | Medium | 1498064.19 | 0.543 | 3 | 1149119.81 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP031 | 2025-03 | 2024-10-07 | 3628631.27 | 2270310 | -1358321.27 | 1358321.27 | 1 | 2025-03-28 | 1 |  |  |  |  | 172 | Low | 620342.85 | 0.17 | 0 | 1649967.15 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP031 | 2025-03 | 2024-10-25 | 2875803.52 | 2270310 | -605493.52 | 605493.52 | 1 | 2025-03-28 | 2 | 3628631.27 | -752827.75 | DOWN | 0.2618 | 154 | Low | 696566.28 | 0.234 | 1 | 1573743.72 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP031 | 2025-03 | 2024-12-10 | 2529284.37 | 2270310 | -258974.37 | 258974.37 | 0 | 2025-03-28 | 3 | 2875803.52 | -346519.15 | DOWN | 0.137 | 108 | Low | 1079470.4 | 0.397 | 1 | 1190839.6 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP031 | 2025-03 | 2025-01-07 | 2380140.78 | 2270310 | -109830.78 | 109830.78 | 0 | 2025-03-28 | 4 | 2529284.37 | -149143.59 | DOWN | 0.0627 | 80 | Low | 1146426.9 | 0.496 | 2 | 1123883.1 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP031 | 2025-04 | 2024-11-03 | 854251.4 | 468005 | -386246.4 | 386246.4 | 1 | 2025-04-28 | 1 |  |  |  |  | 176 | Low | 108322.18 | 0.136 | 0 | 359682.82 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP031 | 2025-04 | 2024-11-29 | 651207.55 | 468005 | -183202.55 | 183202.55 | 1 | 2025-04-28 | 2 | 854251.4 | -203043.85 | DOWN | 0.3118 | 150 | Low | 137511.93 | 0.216 | 0 | 330493.07 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP031 | 2025-04 | 2025-02-28 | 555410.01 | 468005 | -87405.01 | 87405.01 | 1 | 2025-04-28 | 3 | 651207.55 | -95797.54 | DOWN | 0.1725 | 59 | Low | 270007.17 | 0.497 | 3 | 197997.83 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP031 | 2025-04 | 2025-03-23 | 501963.71 | 468005 | -33958.71 | 33958.71 | 0 | 2025-04-28 | 4 | 555410.01 | -53446.3 | DOWN | 0.1065 | 36 | Low | 266239.59 | 0.568 | 3 | 201765.41 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP031 | 2025-04 | 2025-04-10 | 475819.2 | 468005 | -7814.2 | 7814.2 | 0 | 2025-04-28 | 5 | 501963.71 | -26144.51 | DOWN | 0.0549 | 18 | Low | 286743.58 | 0.624 | 7 | 181261.42 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP031 | 2025-04 | 2025-04-18 | 464565.55 | 468005 | 3439.45 | 3439.45 | 0 | 2025-04-28 | 6 | 475819.2 | -11253.65 | DOWN | 0.0242 | 10 | Low | 288331.87 | 0.646 | 7 | 179673.13 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP031 | 2025-05 | 2024-12-07 | 2555237.99 | 1436424 | -1118813.99 | 1118813.99 | 1 | 2025-05-28 | 1 |  |  |  |  | 172 | Low | 394076.34 | 0.154 | 0 | 1042347.66 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP031 | 2025-05 | 2025-01-12 | 1945361.51 | 1436424 | -508937.51 | 508937.51 | 1 | 2025-05-28 | 2 | 2555237.99 | -609876.48 | DOWN | 0.3135 | 136 | Low | 544782.67 | 0.27 | 0 | 891641.33 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP031 | 2025-05 | 2025-01-26 | 1637349.79 | 1436424 | -200925.79 | 200925.79 | 0 | 2025-05-28 | 3 | 1945361.51 | -308011.72 | DOWN | 0.1881 | 122 | Low | 520085.91 | 0.315 | 5 | 916338.09 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP031 | 2025-05 | 2025-02-06 | 1512479.44 | 1436424 | -76055.44 | 76055.44 | 0 | 2025-05-28 | 4 | 1637349.79 | -124870.35 | DOWN | 0.0826 | 111 | Low | 537197.24 | 0.35 | 4 | 899226.76 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP031 | 2025-05 | 2025-02-14 | 1460199.34 | 1436424 | -23775.34 | 23775.34 | 0 | 2025-05-28 | 5 | 1512479.44 | -52280.1 | DOWN | 0.0358 | 103 | Low | 583050.31 | 0.376 | 0 | 853373.69 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP031 | 2025-06 | 2025-01-03 | 4627957.41 | 2724626 | -1903331.41 | 1903331.41 | 1 | 2025-06-28 | 1 |  |  |  |  | 176 | Low | 626734.39 | 0.143 | 2 | 2097891.61 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP031 | 2025-06 | 2025-01-18 | 3604622.49 | 2724626 | -879996.49 | 879996.49 | 1 | 2025-06-28 | 2 | 4627957.41 | -1023334.92 | DOWN | 0.2839 | 161 | Low | 655803.21 | 0.192 | 0 | 2068822.79 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP031 | 2025-06 | 2025-01-21 | 3082818.63 | 2724626 | -358192.63 | 358192.63 | 0 | 2025-06-28 | 3 | 3604622.49 | -521803.86 | DOWN | 0.1693 | 158 | Low | 603550.21 | 0.202 | 0 | 2121075.79 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP031 | 2025-06 | 2025-03-08 | 2866834.72 | 2724626 | -142208.72 | 142208.72 | 0 | 2025-06-28 | 4 | 3082818.63 | -215983.91 | DOWN | 0.0753 | 112 | Low | 1033503.45 | 0.351 | 6 | 1691122.55 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP031 | 2025-06 | 2025-03-17 | 2773751.85 | 2724626 | -49125.85 | 49125.85 | 0 | 2025-06-28 | 5 | 2866834.72 | -93082.87 | DOWN | 0.0336 | 103 | Low | 1060217.7 | 0.381 | 3 | 1664408.3 | 18 | 1.75 | 1.8
P001 | Services | SUP031 | 2025-07 | 2025-03-07 | 610601.51 | 362113 | -248488.51 | 248488.51 | 1 | 2025-07-28 | 1 |  |  |  |  | 143 | Low | 174074.57 | 0.264 | 0 | 188038.43 | 17 | 1.27 | 1.46
P001 | Services | SUP031 | 2025-07 | 2025-03-25 | 476174.05 | 362113 | -114061.05 | 114061.05 | 1 | 2025-07-28 | 2 | 610601.51 | -134427.46 | DOWN | 0.2823 | 125 | Low | 162088.28 | 0.326 | 0 | 200024.72 | 17 | 1.27 | 1.46
P001 | Services | SUP031 | 2025-07 | 2025-04-13 | 408900.33 | 362113 | -46787.33 | 46787.33 | 0 | 2025-07-28 | 3 | 476174.05 | -67273.72 | DOWN | 0.1645 | 106 | Low | 170548.91 | 0.391 | 2 | 191564.09 | 17 | 1.27 | 1.46
P001 | Services | SUP031 | 2025-07 | 2025-06-14 | 384077.43 | 362113 | -21964.43 | 21964.43 | 0 | 2025-07-28 | 4 | 408900.33 | -24822.9 | DOWN | 0.0646 | 44 | Medium | 238401.77 | 0.604 | 4 | 123711.23 | 17 | 1.27 | 1.46
P001 | Services | SUP031 | 2025-07 | 2025-06-20 | 369418.27 | 362113 | -7305.27 | 7305.27 | 0 | 2025-07-28 | 5 | 384077.43 | -14659.16 | DOWN | 0.0397 | 38 | Medium | 215650.9 | 0.625 | 1 | 146462.1 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP031 | 2025-08 | 2025-04-30 | 1577092.09 | 1032712 | -544380.09 | 544380.09 | 1 | 2025-08-28 | 1 |  |  |  |  | 120 | Low | 547894.47 | 0.333 | 0 | 484817.53 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP031 | 2025-08 | 2025-05-20 | 1289294.07 | 1032712 | -256582.07 | 256582.07 | 1 | 2025-08-28 | 2 | 1577092.09 | -287798.02 | DOWN | 0.2232 | 100 | Low | 548092.24 | 0.4 | 0 | 484619.76 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP031 | 2025-08 | 2025-08-06 | 1145613.88 | 1032712 | -112901.88 | 112901.88 | 0 | 2025-08-28 | 3 | 1289294.07 | -143680.19 | DOWN | 0.1254 | 22 | Low | 698293.63 | 0.659 | 4 | 334418.37 | 21 | 1.54 | 1.03
P001 | Logistics | SUP031 | 2025-09 | 2025-05-17 | 3104607.3 | 1504216 | -1600391.3 | 1600391.3 | 1 | 2025-09-28 | 1 |  |  |  |  | 134 | Low | 933986.2 | 0.299 | 2 | 570229.8 | 15 | 1.16 | 1.5
P001 | Logistics | SUP031 | 2025-09 | 2025-06-23 | 2258630.43 | 1504216 | -754414.43 | 754414.43 | 1 | 2025-09-28 | 2 | 3104607.3 | -845976.87 | DOWN | 0.3746 | 97 | Low | 943278.5 | 0.428 | 3 | 560937.5 | 15 | 1.16 | 1.5
P001 | Logistics | SUP031 | 2025-09 | 2025-07-07 | 1848863.69 | 1504216 | -344647.69 | 344647.69 | 1 | 2025-09-28 | 3 | 2258630.43 | -409766.74 | DOWN | 0.2216 | 83 | Low | 917353.64 | 0.477 | 5 | 586862.36 | 15 | 1.16 | 1.5
P001 | Logistics | SUP031 | 2025-09 | 2025-07-24 | 1647900.48 | 1504216 | -143684.48 | 143684.48 | 0 | 2025-09-28 | 4 | 1848863.69 | -200963.21 | DOWN | 0.122 | 66 | Low | 906201.19 | 0.536 | 3 | 598014.81 | 15 | 1.16 | 1.5
P001 | Electronics | SUP031 | 2025-10 | 2025-06-03 | 424927.19 | 236969 | -187958.19 | 187958.19 | 1 | 2025-10-28 | 1 |  |  |  |  | 147 | Low | 105994.77 | 0.236 | 0 | 130974.23 | 18 | 1.81 | 1.33
P001 | Electronics | SUP031 | 2025-10 | 2025-06-26 | 325602.23 | 236969 | -88633.23 | 88633.23 | 1 | 2025-10-28 | 2 | 424927.19 | -99324.96 | DOWN | 0.305 | 124 | Low | 107700.42 | 0.31 | 5 | 129268.58 | 18 | 1.81 | 1.33
P001 | Electronics | SUP031 | 2025-10 | 2025-07-08 | 277460.07 | 236969 | -40491.07 | 40491.07 | 0 | 2025-10-28 | 3 | 325602.23 | -48142.16 | DOWN | 0.1735 | 112 | Low | 92404.25 | 0.349 | 1 | 144564.75 | 18 | 1.81 | 1.33
P001 | Electronics | SUP031 | 2025-10 | 2025-09-23 | 251347.77 | 236969 | -14378.77 | 14378.77 | 0 | 2025-10-28 | 4 | 277460.07 | -26112.3 | DOWN | 0.1039 | 35 | Medium | 155484.58 | 0.598 | 1 | 81484.42 | 18 | 1.81 | 1.33
P001 | Electronics | SUP031 | 2025-10 | 2025-10-08 | 245006.5 | 236969 | -8037.5 | 8037.5 | 0 | 2025-10-28 | 5 | 251347.77 | -6341.27 | DOWN | 0.0259 | 20 | Medium | 147848.76 | 0.646 | 6 | 89120.24 | 18 | 1.81 | 1.33
P001 | Materials | SUP031 | 2025-11 | 2025-08-03 | 1476843.47 | 899317 | -577526.47 | 577526.47 | 1 | 2025-11-28 | 1 |  |  |  |  | 117 | Low | 536862.66 | 0.36 | 4 | 362454.34 | 26 | 1.11 | 1.53
P001 | Materials | SUP031 | 2025-11 | 2025-08-06 | 1159807.3 | 899317 | -260490.3 | 260490.3 | 1 | 2025-11-28 | 2 | 1476843.47 | -317036.17 | DOWN | 0.2734 | 114 | Low | 407434.96 | 0.371 | 4 | 491882.04 | 26 | 1.11 | 1.53
P001 | Materials | SUP031 | 2025-11 | 2025-08-25 | 1017854.58 | 899317 | -118537.58 | 118537.58 | 0 | 2025-11-28 | 3 | 1159807.3 | -141952.72 | DOWN | 0.1395 | 95 | Low | 465895.85 | 0.437 | 3 | 433421.15 | 26 | 1.11 | 1.53
P001 | Materials | SUP031 | 2025-11 | 2025-11-08 | 956582.01 | 899317 | -57265.01 | 57265.01 | 0 | 2025-11-28 | 4 | 1017854.58 | -61272.57 | DOWN | 0.0641 | 20 | Medium | 670609.94 | 0.7 | 7 | 228707.06 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP031 | 2025-12 | 2025-07-27 | 1823192.12 | 1260090 | -563102.12 | 563102.12 | 1 | 2025-12-28 | 1 |  |  |  |  | 154 | Low | 422743.14 | 0.222 | 1 | 837346.86 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP031 | 2025-12 | 2025-08-26 | 1496194.82 | 1260090 | -236104.82 | 236104.82 | 1 | 2025-12-28 | 2 | 1823192.12 | -326997.3 | DOWN | 0.2186 | 124 | Low | 513559.09 | 0.323 | 3 | 746530.91 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP031 | 2025-12 | 2025-09-17 | 1379239.05 | 1260090 | -119149.05 | 119149.05 | 0 | 2025-12-28 | 3 | 1496194.82 | -116955.77 | DOWN | 0.0848 | 102 | Low | 533377.54 | 0.397 | 8 | 726712.46 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP031 | 2025-12 | 2025-11-28 | 1318129.88 | 1260090 | -58039.88 | 58039.88 | 0 | 2025-12-28 | 4 | 1379239.05 | -61109.17 | DOWN | 0.0464 | 30 | Medium | 870676.95 | 0.639 | 6 | 389413.05 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP031 | 2025-12 | 2025-12-07 | 1289621.42 | 1260090 | -29531.42 | 29531.42 | 0 | 2025-12-28 | 5 | 1318129.88 | -28508.46 | DOWN | 0.0221 | 21 | Medium | 882167.83 | 0.669 | 6 | 377922.17 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP031 | 2025-12 | 2025-12-09 | 1271272.48 | 1260090 | -11182.48 | 11182.48 | 0 | 2025-12-28 | 6 | 1289621.42 | -18348.94 | DOWN | 0.0144 | 19 | Medium | 853331.03 | 0.676 | 2 | 406758.97 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP029 | 2025-01 | 2024-11-03 | 2801912.8 | 1727230 | -1074682.8 | 1074682.8 | 1 | 2025-01-28 | 1 |  |  |  |  | 86 | Low | 1215898.06 | 0.426 | 3 | 511331.94 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP029 | 2025-01 | 2024-12-05 | 2246095.21 | 1727230 | -518865.21 | 518865.21 | 1 | 2025-01-28 | 2 | 2801912.8 | -555817.59 | DOWN | 0.2475 | 54 | Low | 1276795.38 | 0.527 | 5 | 450434.62 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP029 | 2025-01 | 2024-12-06 | 1931051.1 | 1727230 | -203821.1 | 203821.1 | 0 | 2025-01-28 | 3 | 2246095.21 | -315044.11 | DOWN | 0.1631 | 53 | Low | 1055845.47 | 0.53 | 4 | 671384.53 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP029 | 2025-01 | 2024-12-23 | 1840835.78 | 1727230 | -113605.78 | 113605.78 | 0 | 2025-01-28 | 4 | 1931051.1 | -90215.32 | DOWN | 0.049 | 36 | Low | 1121455.72 | 0.584 | 8 | 605774.28 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP029 | 2025-01 | 2025-01-13 | 1760793.67 | 1727230 | -33563.67 | 33563.67 | 0 | 2025-01-28 | 5 | 1840835.78 | -80042.11 | DOWN | 0.0455 | 15 | Low | 1063000.84 | 0.651 | 4 | 664229.16 | 19 | 1.97 | 1.9
P001 | Mechanical | SUP029 | 2025-02 | 2024-10-10 | 3538196.5 | 2156037 | -1382159.5 | 1382159.5 | 1 | 2025-02-28 | 1 |  |  |  |  | 141 | Low | 866404.09 | 0.255 | 5 | 1289632.91 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP029 | 2025-02 | 2024-11-21 | 2837978.12 | 2156037 | -681941.12 | 681941.12 | 1 | 2025-02-28 | 2 | 3538196.5 | -700218.38 | DOWN | 0.2467 | 99 | Low | 1090547.28 | 0.391 | 1 | 1065489.72 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP029 | 2025-02 | 2024-12-01 | 2449622.1 | 2156037 | -293585.1 | 293585.1 | 0 | 2025-02-28 | 3 | 2837978.12 | -388356.02 | DOWN | 0.1585 | 89 | Low | 1049308.99 | 0.423 | 1 | 1106728.01 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP029 | 2025-02 | 2025-02-08 | 2278981.02 | 2156037 | -122944.02 | 122944.02 | 0 | 2025-02-28 | 4 | 2449622.1 | -170641.08 | DOWN | 0.0749 | 20 | Medium | 1389171.4 | 0.646 | 2 | 766865.6 | 18 | 1.81 | 1.54
P001 | Materials | SUP029 | 2025-03 | 2024-10-24 | 962453.27 | 657490 | -304963.27 | 304963.27 | 1 | 2025-03-28 | 1 |  |  |  |  | 155 | Low | 221570.92 | 0.23 | 2 | 435919.08 | 20 | 0.93 | 1.57
P001 | Materials | SUP029 | 2025-03 | 2024-11-01 | 791220.81 | 657490 | -133730.81 | 133730.81 | 1 | 2025-03-28 | 2 | 962453.27 | -171232.46 | DOWN | 0.2164 | 147 | Low | 215440.23 | 0.259 | 0 | 442049.77 | 20 | 0.93 | 1.57
P001 | Materials | SUP029 | 2025-03 | 2024-11-06 | 720528.11 | 657490 | -63038.11 | 63038.11 | 0 | 2025-03-28 | 3 | 791220.81 | -70692.7 | DOWN | 0.0981 | 142 | Low | 185486.49 | 0.277 | 0 | 472003.51 | 20 | 0.93 | 1.57
P001 | Materials | SUP029 | 2025-03 | 2024-12-03 | 687369.95 | 657490 | -29879.95 | 29879.95 | 0 | 2025-03-28 | 4 | 720528.11 | -33158.16 | DOWN | 0.0482 | 115 | Low | 264504.03 | 0.372 | 1 | 392985.97 | 20 | 0.93 | 1.57
P001 | Materials | SUP029 | 2025-03 | 2024-12-11 | 669132.79 | 657490 | -11642.79 | 11642.79 | 0 | 2025-03-28 | 5 | 687369.95 | -18237.16 | DOWN | 0.0273 | 107 | Low | 254756.92 | 0.401 | 1 | 402733.08 | 20 | 0.93 | 1.57
P001 | Materials | SUP029 | 2025-03 | 2025-02-07 | 658634.27 | 657490 | -1144.27 | 1144.27 | 0 | 2025-03-28 | 6 | 669132.79 | -10498.52 | DOWN | 0.0159 | 49 | Medium | 427384.67 | 0.606 | 8 | 230105.33 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP029 | 2025-04 | 2024-10-31 | 1328894.38 | 692304 | -636590.38 | 636590.38 | 1 | 2025-04-28 | 1 |  |  |  |  | 179 | Low | 194159.6 | 0.136 | 0 | 498144.4 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP029 | 2025-04 | 2025-01-04 | 1010568.34 | 692304 | -318264.34 | 318264.34 | 1 | 2025-04-28 | 2 | 1328894.38 | -318326.04 | DOWN | 0.315 | 114 | Low | 304907.12 | 0.327 | 2 | 387396.88 | 22 | 2.23 | 1.91
P001 | Mechanical | SUP029 | 2025-04 | 2025-02-15 | 854412.4 | 692304 | -162108.4 | 162108.4 | 1 | 2025-04-28 | 3 | 1010568.34 | -156155.94 | DOWN | 0.1828 | 72 | Low | 407435.07 | 0.457 | 6 | 284868.93 | 22 | 2.23 | 1.91
P001 | Services | SUP029 | 2025-05 | 2024-12-10 | 1986460.81 | 1045686 | -940774.81 | 940774.81 | 1 | 2025-05-28 | 1 |  |  |  |  | 169 | Low | 323956.81 | 0.164 | 3 | 721729.19 | 21 | 1.86 | 0.96
P001 | Services | SUP029 | 2025-05 | 2025-03-05 | 1489609.08 | 1045686 | -443923.08 | 443923.08 | 1 | 2025-05-28 | 2 | 1986460.81 | -496851.73 | DOWN | 0.3335 | 84 | Low | 665793.44 | 0.437 | 4 | 379892.56 | 21 | 1.86 | 0.96
P001 | Services | SUP029 | 2025-05 | 2025-04-07 | 1241733.24 | 1045686 | -196047.24 | 196047.24 | 1 | 2025-05-28 | 3 | 1489609.08 | -247875.84 | DOWN | 0.1996 | 51 | Low | 713770.07 | 0.543 | 2 | 331915.93 | 21 | 1.86 | 0.96
P001 | Mechanical | SUP029 | 2025-06 | 2025-01-10 | 1923045.6 | 1266819 | -656226.6 | 656226.6 | 1 | 2025-06-28 | 1 |  |  |  |  | 169 | Low | 340968.78 | 0.166 | 3 | 925850.22 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP029 | 2025-06 | 2025-01-30 | 1542299.29 | 1266819 | -275480.29 | 275480.29 | 1 | 2025-06-28 | 2 | 1923045.6 | -380746.31 | DOWN | 0.2469 | 149 | Low | 359446.34 | 0.231 | 3 | 907372.66 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP029 | 2025-06 | 2025-02-28 | 1390310.54 | 1266819 | -123491.54 | 123491.54 | 0 | 2025-06-28 | 3 | 1542299.29 | -151988.75 | DOWN | 0.1093 | 120 | Low | 482481.21 | 0.325 | 2 | 784337.79 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP029 | 2025-06 | 2025-03-10 | 1296677.82 | 1266819 | -29858.82 | 29858.82 | 0 | 2025-06-28 | 4 | 1390310.54 | -93632.72 | DOWN | 0.0722 | 110 | Low | 487380.43 | 0.358 | 0 | 779438.57 | 18 | 1.75 | 1.8
P001 | Materials | SUP029 | 2025-07 | 2025-03-28 | 1517511.99 | 897758 | -619753.99 | 619753.99 | 1 | 2025-07-28 | 1 |  |  |  |  | 122 | Low | 547707.66 | 0.337 | 3 | 350050.34 | 17 | 1.27 | 1.46
P001 | Materials | SUP029 | 2025-07 | 2025-04-02 | 1169596.88 | 897758 | -271838.88 | 271838.88 | 1 | 2025-07-28 | 2 | 1517511.99 | -347915.11 | DOWN | 0.2975 | 117 | Low | 409975.2 | 0.354 | 2 | 487782.8 | 17 | 1.27 | 1.46
P001 | Materials | SUP029 | 2025-07 | 2025-04-10 | 1016951.13 | 897758 | -119193.13 | 119193.13 | 0 | 2025-07-28 | 3 | 1169596.88 | -152645.75 | DOWN | 0.1501 | 109 | Low | 365036.81 | 0.381 | 4 | 532721.19 | 17 | 1.27 | 1.46
P001 | Materials | SUP029 | 2025-07 | 2025-04-18 | 946333.98 | 897758 | -48575.98 | 48575.98 | 0 | 2025-07-28 | 4 | 1016951.13 | -70617.15 | DOWN | 0.0746 | 101 | Low | 394007.56 | 0.409 | 1 | 503750.44 | 17 | 1.27 | 1.46
P001 | Materials | SUP029 | 2025-07 | 2025-07-06 | 919835.6 | 897758 | -22077.6 | 22077.6 | 0 | 2025-07-28 | 5 | 946333.98 | -26498.38 | DOWN | 0.0288 | 22 | High | 661797.37 | 0.68 | 5 | 235960.63 | 17 | 1.27 | 1.46
P001 | Software | SUP029 | 2025-08 | 2025-03-26 | 413107.15 | 255036 | -158071.15 | 158071.15 | 1 | 2025-08-28 | 1 |  |  |  |  | 155 | Low | 84066.43 | 0.216 | 2 | 170969.57 | 21 | 1.54 | 1.03
P001 | Software | SUP029 | 2025-08 | 2025-03-27 | 329446.56 | 255036 | -74410.56 | 74410.56 | 1 | 2025-08-28 | 2 | 413107.15 | -83660.59 | DOWN | 0.2539 | 154 | Low | 66816.24 | 0.22 | 1 | 188219.76 | 21 | 1.54 | 1.03
P001 | Software | SUP029 | 2025-08 | 2025-04-07 | 287471.65 | 255036 | -32435.65 | 32435.65 | 0 | 2025-08-28 | 3 | 329446.56 | -41974.91 | DOWN | 0.146 | 143 | Low | 74977.61 | 0.256 | 2 | 180058.39 | 21 | 1.54 | 1.03
P001 | Software | SUP029 | 2025-08 | 2025-05-11 | 268143.71 | 255036 | -13107.71 | 13107.71 | 0 | 2025-08-28 | 4 | 287471.65 | -19327.94 | DOWN | 0.0721 | 109 | Low | 101870.82 | 0.37 | 2 | 153165.18 | 21 | 1.54 | 1.03
P001 | Software | SUP029 | 2025-08 | 2025-07-13 | 255760.3 | 255036 | -724.3 | 724.3 | 0 | 2025-08-28 | 5 | 268143.71 | -12383.41 | DOWN | 0.0484 | 46 | Medium | 143102.61 | 0.579 | 6 | 111933.39 | 21 | 1.54 | 1.03
P001 | Software | SUP029 | 2025-08 | 2025-07-25 | 253514.03 | 255036 | 1521.97 | 1521.97 | 0 | 2025-08-28 | 6 | 255760.3 | -2246.27 | DOWN | 0.0089 | 34 | Medium | 147785.43 | 0.619 | 7 | 107250.57 | 21 | 1.54 | 1.03
P001 | Software | SUP029 | 2025-09 | 2025-04-03 | 5324636.84 | 2570186 | -2754450.84 | 2754450.84 | 1 | 2025-09-28 | 1 |  |  |  |  | 178 | Low | 871315.39 | 0.153 | 1 | 1698870.61 | 15 | 1.16 | 1.5
P001 | Software | SUP029 | 2025-09 | 2025-06-06 | 3744701.19 | 2570186 | -1174515.19 | 1174515.19 | 1 | 2025-09-28 | 2 | 5324636.84 | -1579935.65 | DOWN | 0.4219 | 114 | Low | 1304591.08 | 0.369 | 3 | 1265594.92 | 15 | 1.16 | 1.5
P001 | Software | SUP029 | 2025-09 | 2025-07-09 | 3072973.54 | 2570186 | -502787.54 | 502787.54 | 1 | 2025-09-28 | 3 | 3744701.19 | -671727.65 | DOWN | 0.2186 | 81 | Low | 1596352.98 | 0.484 | 3 | 973833.02 | 15 | 1.16 | 1.5
P001 | Electronics | SUP029 | 2025-10 | 2025-07-23 | 4070889.6 | 1964728 | -2106161.6 | 2106161.6 | 1 | 2025-10-28 | 1 |  |  |  |  | 97 | Low | 1574028.74 | 0.397 | 2 | 390699.26 | 18 | 1.81 | 1.33
P001 | Electronics | SUP029 | 2025-10 | 2025-08-06 | 2838469.4 | 1964728 | -873741.4 | 873741.4 | 1 | 2025-10-28 | 2 | 4070889.6 | -1232420.2 | DOWN | 0.4342 | 83 | Low | 1216352.6 | 0.443 | 2 | 748375.4 | 18 | 1.81 | 1.33
P001 | Electronics | SUP029 | 2025-10 | 2025-08-29 | 2328550.7 | 1964728 | -363822.7 | 363822.7 | 1 | 2025-10-28 | 3 | 2838469.4 | -509918.7 | DOWN | 0.219 | 60 | Low | 1108020.62 | 0.517 | 6 | 856707.38 | 18 | 1.81 | 1.33
P001 | Electronics | SUP029 | 2025-10 | 2025-09-05 | 2123425.42 | 1964728 | -158697.42 | 158697.42 | 0 | 2025-10-28 | 4 | 2328550.7 | -205125.28 | DOWN | 0.0966 | 53 | Medium | 1131132.96 | 0.54 | 4 | 833595.04 | 18 | 1.81 | 1.33
P001 | Services | SUP029 | 2025-11 | 2025-06-01 | 4293263.26 | 2378024 | -1915239.26 | 1915239.26 | 1 | 2025-11-28 | 1 |  |  |  |  | 180 | Low | 650411.68 | 0.154 | 1 | 1727612.32 | 26 | 1.11 | 1.53
P001 | Services | SUP029 | 2025-11 | 2025-08-22 | 3284094.01 | 2378024 | -906070.01 | 906070.01 | 1 | 2025-11-28 | 2 | 4293263.26 | -1009169.25 | DOWN | 0.3073 | 98 | Low | 1476037.22 | 0.427 | 0 | 901986.78 | 26 | 1.11 | 1.53
P001 | Services | SUP029 | 2025-11 | 2025-08-25 | 2784052.25 | 2378024 | -406028.25 | 406028.25 | 0 | 2025-11-28 | 3 | 3284094.01 | -500041.76 | DOWN | 0.1796 | 95 | Low | 1253958.12 | 0.437 | 0 | 1124065.88 | 26 | 1.11 | 1.53
P001 | Services | SUP029 | 2025-11 | 2025-09-30 | 2540088.43 | 2378024 | -162064.43 | 162064.43 | 0 | 2025-11-28 | 4 | 2784052.25 | -243963.82 | DOWN | 0.096 | 59 | Medium | 1328834.36 | 0.563 | 4 | 1049189.64 | 26 | 1.11 | 1.53
P001 | Services | SUP029 | 2025-11 | 2025-10-02 | 2461363.81 | 2378024 | -83339.81 | 83339.81 | 0 | 2025-11-28 | 5 | 2540088.43 | -78724.62 | DOWN | 0.032 | 57 | Medium | 1458762.22 | 0.57 | 4 | 919261.78 | 26 | 1.11 | 1.53
P001 | Services | SUP029 | 2025-11 | 2025-10-05 | 2417264.04 | 2378024 | -39240.04 | 39240.04 | 0 | 2025-11-28 | 6 | 2461363.81 | -44099.77 | DOWN | 0.0182 | 54 | Medium | 1469270.98 | 0.581 | 5 | 908753.02 | 26 | 1.11 | 1.53
P001 | Services | SUP029 | 2025-12 | 2025-11-04 | 2216595.8 | 1266755 | -949840.8 | 949840.8 | 1 | 2025-12-28 | 1 |  |  |  |  | 54 | Medium | 1200906.88 | 0.558 | 8 | 65848.12 | 17 | 1.45 | 1.29
P001 | Services | SUP029 | 2025-12 | 2025-11-15 | 1678305.79 | 1266755 | -411550.79 | 411550.79 | 1 | 2025-12-28 | 2 | 2216595.8 | -538290.01 | DOWN | 0.3207 | 43 | Low | 970242.54 | 0.595 | 5 | 296512.46 | 17 | 1.45 | 1.29
P001 | Services | SUP029 | 2025-12 | 2025-12-02 | 1440456.16 | 1266755 | -173701.16 | 173701.16 | 0 | 2025-12-28 | 3 | 1678305.79 | -237849.63 | DOWN | 0.1651 | 26 | Low | 967147.97 | 0.653 | 6 | 299607.03 | 17 | 1.45 | 1.29
P001 | Logistics | SUP025 | 2025-01 | 2024-08-05 | 3963160.17 | 1705007 | -2258153.17 | 2258153.17 | 1 | 2025-01-28 | 1 |  |  |  |  | 176 | Low | 405807.16 | 0.099 | 0 | 1299199.84 | 19 | 1.97 | 1.9
P001 | Logistics | SUP025 | 2025-01 | 2024-09-11 | 3035073.79 | 1705007 | -1330066.79 | 1330066.79 | 1 | 2025-01-28 | 2 | 3963160.17 | -928086.38 | DOWN | 0.3058 | 139 | Low | 547148.92 | 0.181 | 2 | 1157858.08 | 19 | 1.97 | 1.9
P001 | Logistics | SUP025 | 2025-01 | 2024-09-23 | 2505352.76 | 1705007 | -800345.76 | 800345.76 | 1 | 2025-01-28 | 3 | 3035073.79 | -529721.03 | DOWN | 0.2114 | 127 | Low | 514177.48 | 0.208 | 0 | 1190829.52 | 19 | 1.97 | 1.9
P001 | Materials | SUP025 | 2025-02 | 2024-09-06 | 966433.67 | 498012 | -468421.67 | 468421.67 | 1 | 2025-02-28 | 1 |  |  |  |  | 175 | Low | 93718.21 | 0.103 | 0 | 404293.79 | 18 | 1.81 | 1.54
P001 | Materials | SUP025 | 2025-02 | 2024-09-18 | 780675.74 | 498012 | -282663.74 | 282663.74 | 1 | 2025-02-28 | 2 | 966433.67 | -185757.93 | DOWN | 0.2379 | 163 | Low | 97600.52 | 0.13 | 1 | 400411.48 | 18 | 1.81 | 1.54
P001 | Materials | SUP025 | 2025-02 | 2024-10-10 | 656718.35 | 498012 | -158706.35 | 158706.35 | 1 | 2025-02-28 | 3 | 780675.74 | -123957.39 | DOWN | 0.1888 | 141 | Low | 120956.06 | 0.18 | 4 | 377055.94 | 18 | 1.81 | 1.54
P001 | Materials | SUP025 | 2025-02 | 2024-10-17 | 578296.77 | 498012 | -80284.77 | 80284.77 | 0 | 2025-02-28 | 4 | 656718.35 | -78421.58 | DOWN | 0.1356 | 134 | Low | 114087.18 | 0.196 | 1 | 383924.82 | 18 | 1.81 | 1.54
P001 | Materials | SUP025 | 2025-02 | 2024-11-19 | 550256.13 | 498012 | -52244.13 | 52244.13 | 0 | 2025-02-28 | 5 | 578296.77 | -28040.64 | DOWN | 0.051 | 101 | Low | 149503.4 | 0.271 | 4 | 348508.6 | 18 | 1.81 | 1.54
P001 | Materials | SUP025 | 2025-02 | 2024-12-14 | 522614.76 | 498012 | -24602.76 | 24602.76 | 0 | 2025-02-28 | 6 | 550256.13 | -27641.37 | DOWN | 0.0529 | 76 | Low | 179754.54 | 0.328 | 1 | 318257.46 | 18 | 1.81 | 1.54
P001 | Services | SUP025 | 2025-03 | 2024-12-05 | 3911160.6 | 2019859 | -1891301.6 | 1891301.6 | 1 | 2025-03-28 | 1 |  |  |  |  | 113 | Low | 1087104.2 | 0.268 | 4 | 932754.8 | 20 | 0.93 | 1.57
P001 | Services | SUP025 | 2025-03 | 2024-12-16 | 3127626.3 | 2019859 | -1107767.3 | 1107767.3 | 1 | 2025-03-28 | 2 | 3911160.6 | -783534.3 | DOWN | 0.2505 | 102 | Low | 942608.82 | 0.295 | 5 | 1077250.18 | 20 | 0.93 | 1.57
P001 | Services | SUP025 | 2025-03 | 2025-01-12 | 2696558.49 | 2019859 | -676699.49 | 676699.49 | 1 | 2025-03-28 | 3 | 3127626.3 | -431067.81 | DOWN | 0.1599 | 75 | Low | 980189.73 | 0.363 | 0 | 1039669.27 | 20 | 0.93 | 1.57
P001 | Services | SUP025 | 2025-03 | 2025-01-30 | 2391259.27 | 2019859 | -371400.27 | 371400.27 | 1 | 2025-03-28 | 4 | 2696558.49 | -305299.22 | DOWN | 0.1277 | 57 | Low | 897548.96 | 0.408 | 3 | 1122310.04 | 20 | 0.93 | 1.57
P001 | Services | SUP025 | 2025-03 | 2025-03-01 | 2244995.51 | 2019859 | -225136.51 | 225136.51 | 0 | 2025-03-28 | 5 | 2391259.27 | -146263.76 | DOWN | 0.0652 | 27 | Low | 1025689.85 | 0.483 | 4 | 994169.15 | 20 | 0.93 | 1.57
P001 | Services | SUP025 | 2025-03 | 2025-03-09 | 2149416.52 | 2019859 | -129557.52 | 129557.52 | 0 | 2025-03-28 | 6 | 2244995.51 | -95578.99 | DOWN | 0.0445 | 19 | Low | 1057935.99 | 0.503 | 2 | 961923.01 | 20 | 0.93 | 1.57
P001 | Logistics | SUP025 | 2025-04 | 2024-11-03 | 4246782.89 | 1613230 | -2633552.89 | 2633552.89 | 1 | 2025-04-28 | 1 |  |  |  |  | 176 | Low | 393617.65 | 0.096 | 2 | 1219612.35 | 22 | 2.23 | 1.91
P001 | Logistics | SUP025 | 2025-04 | 2024-11-18 | 3269995.51 | 1613230 | -1656765.51 | 1656765.51 | 1 | 2025-04-28 | 2 | 4246782.89 | -976787.38 | DOWN | 0.2987 | 161 | Low | 453689.19 | 0.129 | 2 | 1159540.81 | 22 | 2.23 | 1.91
P001 | Logistics | SUP025 | 2025-04 | 2025-01-19 | 2646981.96 | 1613230 | -1033751.96 | 1033751.96 | 1 | 2025-04-28 | 3 | 3269995.51 | -623013.55 | DOWN | 0.2354 | 99 | Low | 718082.66 | 0.264 | 1 | 895147.34 | 22 | 2.23 | 1.91
P001 | Logistics | SUP025 | 2025-04 | 2025-01-27 | 2276214.34 | 1613230 | -662984.34 | 662984.34 | 1 | 2025-04-28 | 4 | 2646981.96 | -370767.62 | DOWN | 0.1629 | 91 | Low | 678350.06 | 0.281 | 0 | 934879.94 | 22 | 2.23 | 1.91
P001 | Electronics | SUP025 | 2025-05 | 2025-03-20 | 3601440.34 | 2257121 | -1344319.34 | 1344319.34 | 1 | 2025-05-28 | 1 |  |  |  |  | 69 | Low | 1141844.47 | 0.342 | 4 | 1115276.53 | 21 | 1.86 | 0.96
P001 | Electronics | SUP025 | 2025-05 | 2025-04-08 | 3027249.7 | 2257121 | -770128.7 | 770128.7 | 1 | 2025-05-28 | 2 | 3601440.34 | -574190.64 | DOWN | 0.1897 | 50 | Low | 1162452.43 | 0.385 | 4 | 1094668.57 | 21 | 1.86 | 0.96
P001 | Electronics | SUP025 | 2025-05 | 2025-04-16 | 2700074.03 | 2257121 | -442953.03 | 442953.03 | 1 | 2025-05-28 | 3 | 3027249.7 | -327175.67 | DOWN | 0.1212 | 42 | Low | 1140902.89 | 0.403 | 3 | 1116218.11 | 21 | 1.86 | 0.96
P001 | Services | SUP025 | 2025-06 | 2025-01-04 | 1195914.64 | 596961 | -598953.64 | 598953.64 | 1 | 2025-06-28 | 1 |  |  |  |  | 175 | Low | 122808.51 | 0.103 | 0 | 474152.49 | 18 | 1.75 | 1.8
P001 | Services | SUP025 | 2025-06 | 2025-01-19 | 928450.11 | 596961 | -331489.11 | 331489.11 | 1 | 2025-06-28 | 2 | 1195914.64 | -267464.53 | DOWN | 0.2881 | 160 | Low | 122600.04 | 0.138 | 0 | 474360.96 | 18 | 1.75 | 1.8
P001 | Services | SUP025 | 2025-06 | 2025-04-06 | 799053.04 | 596961 | -202092.04 | 202092.04 | 1 | 2025-06-28 | 3 | 928450.11 | -129397.07 | DOWN | 0.1619 | 83 | Low | 238879.78 | 0.314 | 3 | 358081.22 | 18 | 1.75 | 1.8
P001 | Services | SUP025 | 2025-06 | 2025-05-05 | 714153.68 | 596961 | -117192.68 | 117192.68 | 1 | 2025-06-28 | 4 | 799053.04 | -84899.36 | DOWN | 0.1189 | 54 | Low | 254091.95 | 0.381 | 0 | 342869.05 | 18 | 1.75 | 1.8
P001 | Services | SUP025 | 2025-06 | 2025-05-08 | 670173.53 | 596961 | -73212.53 | 73212.53 | 0 | 2025-06-28 | 5 | 714153.68 | -43980.15 | DOWN | 0.0656 | 51 | Low | 263068.23 | 0.388 | 7 | 333892.77 | 18 | 1.75 | 1.8
P001 | Materials | SUP025 | 2025-07 | 2025-03-06 | 504063.69 | 268781 | -235282.69 | 235282.69 | 1 | 2025-07-28 | 1 |  |  |  |  | 144 | Low | 100069.41 | 0.184 | 2 | 168711.59 | 17 | 1.27 | 1.46
P001 | Materials | SUP025 | 2025-07 | 2025-03-13 | 409139.07 | 268781 | -140358.07 | 140358.07 | 1 | 2025-07-28 | 2 | 504063.69 | -94924.62 | DOWN | 0.232 | 137 | Low | 87808.02 | 0.201 | 0 | 180972.98 | 17 | 1.27 | 1.46
P001 | Materials | SUP025 | 2025-07 | 2025-05-21 | 349319.73 | 268781 | -80538.73 | 80538.73 | 1 | 2025-07-28 | 3 | 409139.07 | -59819.34 | DOWN | 0.1712 | 68 | Low | 135023.94 | 0.368 | 6 | 133757.06 | 17 | 1.27 | 1.46
P001 | Materials | SUP025 | 2025-07 | 2025-06-12 | 313204.57 | 268781 | -44423.57 | 44423.57 | 0 | 2025-07-28 | 4 | 349319.73 | -36115.16 | DOWN | 0.1153 | 46 | Low | 135431.15 | 0.421 | 2 | 133349.85 | 17 | 1.27 | 1.46
P001 | Materials | SUP025 | 2025-07 | 2025-06-28 | 295040.31 | 268781 | -26259.31 | 26259.31 | 0 | 2025-07-28 | 5 | 313204.57 | -18164.26 | DOWN | 0.0616 | 30 | Low | 132230.62 | 0.46 | 2 | 136550.38 | 17 | 1.27 | 1.46
P001 | Logistics | SUP025 | 2025-08 | 2025-03-25 | 2025571.1 | 919763 | -1105808.1 | 1105808.1 | 1 | 2025-08-28 | 1 |  |  |  |  | 156 | Low | 308186.13 | 0.15 | 1 | 611576.87 | 21 | 1.54 | 1.03
P001 | Logistics | SUP025 | 2025-08 | 2025-04-22 | 1630243.09 | 919763 | -710480.09 | 710480.09 | 1 | 2025-08-28 | 2 | 2025571.1 | -395328.01 | DOWN | 0.2425 | 128 | Low | 359257.98 | 0.216 | 3 | 560505.02 | 21 | 1.54 | 1.03
P001 | Logistics | SUP025 | 2025-08 | 2025-05-13 | 1334478.15 | 919763 | -414715.15 | 414715.15 | 1 | 2025-08-28 | 3 | 1630243.09 | -295764.94 | DOWN | 0.2216 | 107 | Low | 358723.4 | 0.265 | 2 | 561039.6 | 21 | 1.54 | 1.03
P001 | Logistics | SUP025 | 2025-08 | 2025-06-07 | 1156557.42 | 919763 | -236794.42 | 236794.42 | 1 | 2025-08-28 | 4 | 1334478.15 | -177920.73 | DOWN | 0.1538 | 82 | Low | 363649.21 | 0.324 | 2 | 556113.79 | 21 | 1.54 | 1.03
P001 | Logistics | SUP025 | 2025-08 | 2025-06-19 | 1068188.41 | 919763 | -148425.41 | 148425.41 | 0 | 2025-08-28 | 5 | 1156557.42 | -88369.01 | DOWN | 0.0827 | 70 | Low | 364094.69 | 0.352 | 3 | 555668.31 | 21 | 1.54 | 1.03
P001 | Logistics | SUP025 | 2025-08 | 2025-06-24 | 987124.03 | 919763 | -67361.03 | 67361.03 | 0 | 2025-08-28 | 6 | 1068188.41 | -81064.38 | DOWN | 0.0821 | 65 | Low | 382280.67 | 0.364 | 3 | 537482.33 | 21 | 1.54 | 1.03
P001 | Software | SUP025 | 2025-09 | 2025-04-18 | 4383407.37 | 2047999 | -2335408.37 | 2335408.37 | 1 | 2025-09-28 | 1 |  |  |  |  | 163 | Low | 613363.13 | 0.14 | 3 | 1434635.87 | 15 | 1.16 | 1.5
P001 | Software | SUP025 | 2025-09 | 2025-05-03 | 3377805.11 | 2047999 | -1329806.11 | 1329806.11 | 1 | 2025-09-28 | 2 | 4383407.37 | -1005602.26 | DOWN | 0.2977 | 148 | Low | 619298.17 | 0.177 | 0 | 1428700.83 | 15 | 1.16 | 1.5
P001 | Software | SUP025 | 2025-09 | 2025-05-04 | 2842669.86 | 2047999 | -794670.86 | 794670.86 | 1 | 2025-09-28 | 3 | 3377805.11 | -535135.25 | DOWN | 0.1883 | 147 | Low | 545084.68 | 0.179 | 0 | 1502914.32 | 15 | 1.16 | 1.5
P001 | Software | SUP025 | 2025-09 | 2025-06-10 | 2498213.9 | 2047999 | -450214.9 | 450214.9 | 1 | 2025-09-28 | 4 | 2842669.86 | -344455.96 | DOWN | 0.1379 | 110 | Low | 626308.23 | 0.27 | 0 | 1421690.77 | 15 | 1.16 | 1.5
P001 | Software | SUP025 | 2025-09 | 2025-08-14 | 2294391.72 | 2047999 | -246392.72 | 246392.72 | 0 | 2025-09-28 | 5 | 2498213.9 | -203822.18 | DOWN | 0.0888 | 45 | Low | 1029743.77 | 0.429 | 3 | 1018255.23 | 15 | 1.16 | 1.5
P001 | Software | SUP025 | 2025-09 | 2025-08-26 | 2201942.9 | 2047999 | -153943.9 | 153943.9 | 0 | 2025-09-28 | 6 | 2294391.72 | -92448.82 | DOWN | 0.042 | 33 | Low | 932727.94 | 0.459 | 4 | 1115271.06 | 15 | 1.16 | 1.5
P001 | Logistics | SUP025 | 2025-10 | 2025-07-25 | 3409019.18 | 1500203 | -1908816.18 | 1908816.18 | 1 | 2025-10-28 | 1 |  |  |  |  | 95 | Low | 898127.85 | 0.285 | 4 | 602075.15 | 18 | 1.81 | 1.33
P001 | Logistics | SUP025 | 2025-10 | 2025-09-26 | 2652244.59 | 1500203 | -1152041.59 | 1152041.59 | 1 | 2025-10-28 | 2 | 3409019.18 | -756774.59 | DOWN | 0.2853 | 32 | Low | 1214625.73 | 0.428 | 3 | 285577.27 | 18 | 1.81 | 1.33
P001 | Logistics | SUP025 | 2025-10 | 2025-10-06 | 2107031.97 | 1500203 | -606828.97 | 606828.97 | 1 | 2025-10-28 | 3 | 2652244.59 | -545212.62 | DOWN | 0.2588 | 22 | Low | 952955.4 | 0.451 | 1 | 547247.6 | 18 | 1.81 | 1.33
P001 | Mechanical | SUP025 | 2025-11 | 2025-06-13 | 3682117.57 | 2385830 | -1296287.57 | 1296287.57 | 1 | 2025-11-28 | 1 |  |  |  |  | 168 | Low | 492576.66 | 0.128 | 5 | 1893253.34 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP025 | 2025-11 | 2025-08-10 | 3190738.74 | 2385830 | -804908.74 | 804908.74 | 1 | 2025-11-28 | 2 | 3682117.57 | -491378.83 | DOWN | 0.154 | 110 | Low | 889252.69 | 0.271 | 0 | 1496577.31 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP025 | 2025-11 | 2025-09-20 | 2855528.87 | 2385830 | -469698.87 | 469698.87 | 1 | 2025-11-28 | 3 | 3190738.74 | -335209.87 | DOWN | 0.1174 | 69 | Low | 1008206.13 | 0.373 | 3 | 1377623.87 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP025 | 2025-11 | 2025-10-05 | 2652198.66 | 2385830 | -266368.66 | 266368.66 | 0 | 2025-11-28 | 4 | 2855528.87 | -203330.21 | DOWN | 0.0767 | 54 | Low | 1162303.22 | 0.41 | 3 | 1223526.78 | 26 | 1.11 | 1.53
P001 | Services | SUP025 | 2025-12 | 2025-08-31 | 4126821.38 | 2084748 | -2042073.38 | 2042073.38 | 1 | 2025-12-28 | 1 |  |  |  |  | 119 | Low | 1037726.45 | 0.24 | 0 | 1047021.55 | 17 | 1.45 | 1.29
P001 | Services | SUP025 | 2025-12 | 2025-09-08 | 3265367.87 | 2084748 | -1180619.87 | 1180619.87 | 1 | 2025-12-28 | 2 | 4126821.38 | -861453.51 | DOWN | 0.2638 | 111 | Low | 831874.7 | 0.259 | 0 | 1252873.3 | 17 | 1.45 | 1.29
P001 | Services | SUP025 | 2025-12 | 2025-11-23 | 2805270.47 | 2084748 | -720522.47 | 720522.47 | 1 | 2025-12-28 | 3 | 3265367.87 | -460097.4 | DOWN | 0.164 | 35 | Low | 1290173.77 | 0.439 | 4 | 794574.23 | 17 | 1.45 | 1.29
P001 | Logistics | SUP023 | 2025-01 | 2024-08-07 | 1728990 | 979910 | -749080 | 749080 | 1 | 2025-01-28 | 1 |  |  |  |  | 174 | Low | 262116.22 | 0.146 | 2 | 717793.78 | 19 | 1.97 | 1.9
P001 | Logistics | SUP023 | 2025-01 | 2024-08-25 | 1330584.11 | 979910 | -350674.11 | 350674.11 | 1 | 2025-01-28 | 2 | 1728990 | -398405.89 | DOWN | 0.2994 | 156 | Low | 264539.97 | 0.203 | 2 | 715370.03 | 19 | 1.97 | 1.9
P001 | Logistics | SUP023 | 2025-01 | 2024-11-02 | 1128437.54 | 979910 | -148527.54 | 148527.54 | 0 | 2025-01-28 | 3 | 1330584.11 | -202146.57 | DOWN | 0.1791 | 87 | Low | 467297.91 | 0.422 | 5 | 512612.09 | 19 | 1.97 | 1.9
P001 | Logistics | SUP023 | 2025-01 | 2024-11-04 | 1048813.69 | 979910 | -68903.69 | 68903.69 | 0 | 2025-01-28 | 4 | 1128437.54 | -79623.85 | DOWN | 0.0759 | 85 | Low | 442591.66 | 0.429 | 4 | 537318.34 | 19 | 1.97 | 1.9
P001 | Logistics | SUP023 | 2025-01 | 2024-11-18 | 1034709.23 | 979910 | -54799.23 | 54799.23 | 0 | 2025-01-28 | 5 | 1048813.69 | -14104.46 | DOWN | 0.0136 | 71 | Low | 472005.17 | 0.473 | 4 | 507904.83 | 19 | 1.97 | 1.9
P001 | Logistics | SUP023 | 2025-02 | 2024-10-04 | 775328.67 | 360007 | -415321.67 | 415321.67 | 1 | 2025-02-28 | 1 |  |  |  |  | 147 | Low | 187128.7 | 0.236 | 2 | 172878.3 | 18 | 1.81 | 1.54
P001 | Logistics | SUP023 | 2025-02 | 2024-11-23 | 528575.9 | 360007 | -168568.9 | 168568.9 | 1 | 2025-02-28 | 2 | 775328.67 | -246752.77 | DOWN | 0.4668 | 97 | Low | 199029.14 | 0.397 | 4 | 160977.86 | 18 | 1.81 | 1.54
P001 | Logistics | SUP023 | 2025-02 | 2025-01-11 | 437480.35 | 360007 | -77473.35 | 77473.35 | 1 | 2025-02-28 | 3 | 528575.9 | -91095.55 | DOWN | 0.2082 | 48 | Low | 234174.56 | 0.556 | 2 | 125832.44 | 18 | 1.81 | 1.54
P001 | Logistics | SUP023 | 2025-02 | 2025-01-28 | 388544.1 | 360007 | -28537.1 | 28537.1 | 0 | 2025-02-28 | 4 | 437480.35 | -48936.25 | DOWN | 0.1259 | 31 | Low | 236757.68 | 0.611 | 2 | 123249.32 | 18 | 1.81 | 1.54
P001 | Electronics | SUP023 | 2025-03 | 2024-10-15 | 1887324.13 | 940332 | -946992.13 | 946992.13 | 1 | 2025-03-28 | 1 |  |  |  |  | 164 | Low | 393074.14 | 0.199 | 0 | 547257.86 | 20 | 0.93 | 1.57
P001 | Electronics | SUP023 | 2025-03 | 2024-10-22 | 1363417.3 | 940332 | -423085.3 | 423085.3 | 1 | 2025-03-28 | 2 | 1887324.13 | -523906.83 | DOWN | 0.3843 | 157 | Low | 299405.3 | 0.223 | 1 | 640926.7 | 20 | 0.93 | 1.57
P001 | Electronics | SUP023 | 2025-03 | 2025-01-27 | 1144915.06 | 940332 | -204583.06 | 204583.06 | 1 | 2025-03-28 | 3 | 1363417.3 | -218502.24 | DOWN | 0.1908 | 60 | Low | 696952.32 | 0.567 | 3 | 243379.68 | 20 | 0.93 | 1.57
P001 | Electronics | SUP023 | 2025-03 | 2025-01-29 | 1038477.43 | 940332 | -98145.43 | 98145.43 | 0 | 2025-03-28 | 4 | 1144915.06 | -106437.63 | DOWN | 0.1025 | 58 | Medium | 620970.89 | 0.574 | 6 | 319361.11 | 20 | 0.93 | 1.57
P001 | Materials | SUP023 | 2025-04 | 2025-02-16 | 1848491.86 | 1081169 | -767322.86 | 767322.86 | 1 | 2025-04-28 | 1 |  |  |  |  | 71 | Low | 888534.24 | 0.46 | 4 | 192634.76 | 22 | 2.23 | 1.91
P001 | Materials | SUP023 | 2025-04 | 2025-03-27 | 1465211.71 | 1081169 | -384042.71 | 384042.71 | 1 | 2025-04-28 | 2 | 1848491.86 | -383280.15 | DOWN | 0.2616 | 32 | Low | 891384.3 | 0.581 | 8 | 189784.7 | 22 | 2.23 | 1.91
P001 | Materials | SUP023 | 2025-04 | 2025-04-06 | 1212123.49 | 1081169 | -130954.49 | 130954.49 | 0 | 2025-04-28 | 3 | 1465211.71 | -253088.22 | DOWN | 0.2088 | 22 | Low | 719259.59 | 0.612 | 6 | 361909.41 | 22 | 2.23 | 1.91
P001 | Software | SUP023 | 2025-05 | 2024-12-02 | 2161974.36 | 980086 | -1181888.36 | 1181888.36 | 1 | 2025-05-28 | 1 |  |  |  |  | 177 | Low | 299420.66 | 0.141 | 2 | 680665.34 | 21 | 1.86 | 0.96
P001 | Software | SUP023 | 2025-05 | 2024-12-06 | 1497035.13 | 980086 | -516949.13 | 516949.13 | 1 | 2025-05-28 | 2 | 2161974.36 | -664939.23 | DOWN | 0.4442 | 173 | Low | 242784.49 | 0.151 | 2 | 737301.51 | 21 | 1.86 | 0.96
P001 | Software | SUP023 | 2025-05 | 2025-03-03 | 1231345.91 | 980086 | -251259.91 | 251259.91 | 1 | 2025-05-28 | 3 | 1497035.13 | -265689.22 | DOWN | 0.2158 | 86 | Low | 564499.67 | 0.431 | 1 | 415586.33 | 21 | 1.86 | 0.96
P001 | Software | SUP023 | 2025-05 | 2025-03-05 | 1113010.91 | 980086 | -132924.91 | 132924.91 | 0 | 2025-05-28 | 4 | 1231345.91 | -118335 | DOWN | 0.1063 | 84 | Low | 514763.93 | 0.437 | 2 | 465322.07 | 21 | 1.86 | 0.96
P001 | Software | SUP023 | 2025-05 | 2025-05-03 | 1069389.85 | 980086 | -89303.85 | 89303.85 | 0 | 2025-05-28 | 5 | 1113010.91 | -43621.06 | DOWN | 0.0408 | 25 | Medium | 685806.02 | 0.627 | 6 | 294279.98 | 21 | 1.86 | 0.96
P001 | Software | SUP023 | 2025-06 | 2025-02-16 | 3273260.41 | 1703660 | -1569600.41 | 1569600.41 | 1 | 2025-06-28 | 1 |  |  |  |  | 132 | Low | 917934.13 | 0.286 | 5 | 785725.87 | 18 | 1.75 | 1.8
P001 | Software | SUP023 | 2025-06 | 2025-05-31 | 2451503.95 | 1703660 | -747843.95 | 747843.95 | 1 | 2025-06-28 | 2 | 3273260.41 | -821756.46 | DOWN | 0.3352 | 28 | Low | 1429185.49 | 0.625 | 5 | 274474.51 | 18 | 1.75 | 1.8
P001 | Software | SUP023 | 2025-06 | 2025-06-02 | 2050991.37 | 1703660 | -347331.37 | 347331.37 | 1 | 2025-06-28 | 3 | 2451503.95 | -400512.58 | DOWN | 0.1953 | 26 | Low | 1377836.64 | 0.631 | 7 | 325823.36 | 18 | 1.75 | 1.8
P001 | Materials | SUP023 | 2025-07 | 2025-02-13 | 2454793.81 | 1600742 | -854051.81 | 854051.81 | 1 | 2025-07-28 | 1 |  |  |  |  | 165 | Low | 454077.26 | 0.189 | 0 | 1146664.74 | 17 | 1.27 | 1.46
P001 | Materials | SUP023 | 2025-07 | 2025-03-29 | 1968640.15 | 1600742 | -367898.15 | 367898.15 | 1 | 2025-07-28 | 2 | 2454793.81 | -486153.66 | DOWN | 0.2469 | 121 | Low | 655247.17 | 0.34 | 6 | 945494.83 | 17 | 1.27 | 1.46
P001 | Materials | SUP023 | 2025-07 | 2025-05-13 | 1746253.11 | 1600742 | -145511.11 | 145511.11 | 0 | 2025-07-28 | 3 | 1968640.15 | -222387.04 | DOWN | 0.1274 | 76 | Low | 910184.49 | 0.495 | 3 | 690557.51 | 17 | 1.27 | 1.46
P001 | Services | SUP023 | 2025-08 | 2025-04-18 | 946125.36 | 564255 | -381870.36 | 381870.36 | 1 | 2025-08-28 | 1 |  |  |  |  | 132 | Low | 297363.99 | 0.293 | 6 | 266891.01 | 21 | 1.54 | 1.03
P001 | Services | SUP023 | 2025-08 | 2025-05-05 | 720243.04 | 564255 | -155988.04 | 155988.04 | 1 | 2025-08-28 | 2 | 946125.36 | -225882.32 | DOWN | 0.3136 | 115 | Low | 267232.7 | 0.35 | 4 | 297022.3 | 21 | 1.54 | 1.03
P001 | Services | SUP023 | 2025-08 | 2025-07-22 | 635546.63 | 564255 | -71291.63 | 71291.63 | 0 | 2025-08-28 | 3 | 720243.04 | -84696.41 | DOWN | 0.1333 | 37 | Low | 369872.23 | 0.609 | 6 | 194382.77 | 21 | 1.54 | 1.03
P001 | Services | SUP023 | 2025-09 | 2025-04-13 | 2145308.65 | 1242392 | -902916.65 | 902916.65 | 1 | 2025-09-28 | 1 |  |  |  |  | 168 | Low | 403613.17 | 0.181 | 2 | 838778.83 | 15 | 1.16 | 1.5
P001 | Services | SUP023 | 2025-09 | 2025-04-13 | 1648003.65 | 1242392 | -405611.65 | 405611.65 | 1 | 2025-09-28 | 2 | 2145308.65 | -497305 | DOWN | 0.3018 | 168 | Low | 293526.88 | 0.181 | 3 | 948865.12 | 15 | 1.16 | 1.5
P001 | Services | SUP023 | 2025-09 | 2025-05-18 | 1430464.19 | 1242392 | -188072.19 | 188072.19 | 0 | 2025-09-28 | 3 | 1648003.65 | -217539.46 | DOWN | 0.1521 | 133 | Low | 440967.29 | 0.303 | 0 | 801424.71 | 15 | 1.16 | 1.5
P001 | Services | SUP023 | 2025-09 | 2025-06-01 | 1333962.85 | 1242392 | -91570.85 | 91570.85 | 0 | 2025-09-28 | 4 | 1430464.19 | -96501.34 | DOWN | 0.0723 | 119 | Low | 469476.17 | 0.351 | 1 | 772915.83 | 15 | 1.16 | 1.5
P001 | Services | SUP023 | 2025-09 | 2025-08-28 | 1271476.13 | 1242392 | -29084.13 | 29084.13 | 0 | 2025-09-28 | 5 | 1333962.85 | -62486.72 | DOWN | 0.0491 | 31 | Medium | 867495.54 | 0.657 | 10 | 374896.46 | 15 | 1.16 | 1.5
P001 | Services | SUP023 | 2025-10 | 2025-05-09 | 3318914.51 | 1889868 | -1429046.51 | 1429046.51 | 1 | 2025-10-28 | 1 |  |  |  |  | 172 | Low | 554082.07 | 0.155 | 0 | 1335785.93 | 18 | 1.81 | 1.33
P001 | Services | SUP023 | 2025-10 | 2025-05-15 | 2501137.15 | 1889868 | -611269.15 | 611269.15 | 1 | 2025-10-28 | 2 | 3318914.51 | -817777.36 | DOWN | 0.327 | 166 | Low | 467344.3 | 0.174 | 0 | 1422523.7 | 18 | 1.81 | 1.33
P001 | Services | SUP023 | 2025-10 | 2025-06-27 | 2183778.73 | 1889868 | -293910.73 | 293910.73 | 0 | 2025-10-28 | 3 | 2501137.15 | -317358.42 | DOWN | 0.1453 | 123 | Low | 718082.11 | 0.313 | 3 | 1171785.89 | 18 | 1.81 | 1.33
P001 | Services | SUP023 | 2025-10 | 2025-06-29 | 1993599.23 | 1889868 | -103731.23 | 103731.23 | 0 | 2025-10-28 | 4 | 2183778.73 | -190179.5 | DOWN | 0.0954 | 121 | Low | 684270.97 | 0.32 | 6 | 1205597.03 | 18 | 1.81 | 1.33
P001 | Services | SUP023 | 2025-10 | 2025-09-07 | 1965537.46 | 1889868 | -75669.46 | 75669.46 | 0 | 2025-10-28 | 5 | 1993599.23 | -28061.77 | DOWN | 0.0143 | 51 | Medium | 1124873.43 | 0.546 | 3 | 764994.57 | 18 | 1.81 | 1.33
P001 | Services | SUP023 | 2025-10 | 2025-09-22 | 1952799.82 | 1889868 | -62931.82 | 62931.82 | 0 | 2025-10-28 | 6 | 1965537.46 | -12737.64 | DOWN | 0.0065 | 36 | Medium | 1111213.26 | 0.595 | 3 | 778654.74 | 18 | 1.81 | 1.33
P001 | Software | SUP023 | 2025-11 | 2025-07-04 | 2169795.98 | 1139916 | -1029879.98 | 1029879.98 | 1 | 2025-11-28 | 1 |  |  |  |  | 147 | Low | 589313.88 | 0.255 | 2 | 550602.12 | 26 | 1.11 | 1.53
P001 | Software | SUP023 | 2025-11 | 2025-10-07 | 1601224.08 | 1139916 | -461308.08 | 461308.08 | 1 | 2025-11-28 | 2 | 2169795.98 | -568571.9 | DOWN | 0.3551 | 52 | Low | 904661.01 | 0.588 | 0 | 235254.99 | 26 | 1.11 | 1.53
P001 | Software | SUP023 | 2025-11 | 2025-10-14 | 1344911.98 | 1139916 | -204995.98 | 204995.98 | 1 | 2025-11-28 | 3 | 1601224.08 | -256312.1 | DOWN | 0.1906 | 45 | Low | 784275.43 | 0.612 | 3 | 355640.57 | 26 | 1.11 | 1.53
P001 | Electronics | SUP023 | 2025-12 | 2025-07-28 | 2854636.32 | 1686522 | -1168114.32 | 1168114.32 | 1 | 2025-12-28 | 1 |  |  |  |  | 153 | Low | 659537.06 | 0.225 | 5 | 1026984.94 | 17 | 1.45 | 1.29
P001 | Electronics | SUP023 | 2025-12 | 2025-09-20 | 2205443.48 | 1686522 | -518921.48 | 518921.48 | 1 | 2025-12-28 | 2 | 2854636.32 | -649192.84 | DOWN | 0.2944 | 99 | Low | 904749.94 | 0.407 | 4 | 781772.06 | 17 | 1.45 | 1.29
P001 | Electronics | SUP023 | 2025-12 | 2025-11-05 | 1926079.39 | 1686522 | -239557.39 | 239557.39 | 0 | 2025-12-28 | 3 | 2205443.48 | -279364.09 | DOWN | 0.145 | 53 | Low | 1021743.83 | 0.562 | 4 | 664778.17 | 17 | 1.45 | 1.29
P001 | Electronics | SUP023 | 2025-12 | 2025-11-07 | 1777568.15 | 1686522 | -91046.15 | 91046.15 | 0 | 2025-12-28 | 4 | 1926079.39 | -148511.24 | DOWN | 0.0835 | 51 | Medium | 1000047.25 | 0.568 | 5 | 686474.75 | 17 | 1.45 | 1.29
P001 | Electronics | SUP023 | 2025-12 | 2025-11-12 | 1753869.99 | 1686522 | -67347.99 | 67347.99 | 0 | 2025-12-28 | 5 | 1777568.15 | -23698.16 | DOWN | 0.0135 | 46 | Medium | 1010952.16 | 0.585 | 1 | 675569.84 | 17 | 1.45 | 1.29
P001 | Materials | SUP032 | 2025-01 | 2024-08-13 | 2022606.79 | 972698 | -1049908.79 | 1049908.79 | 1 | 2025-01-28 | 1 |  |  |  |  | 168 | Low | 217327.72 | 0.106 | 0 | 755370.28 | 19 | 1.97 | 1.9
P001 | Materials | SUP032 | 2025-01 | 2024-10-06 | 1739932.62 | 972698 | -767234.62 | 767234.62 | 1 | 2025-01-28 | 2 | 2022606.79 | -282674.17 | DOWN | 0.1625 | 114 | Low | 387001.91 | 0.216 | 3 | 585696.09 | 19 | 1.97 | 1.9
P001 | Materials | SUP032 | 2025-01 | 2024-10-19 | 1551373.07 | 972698 | -578675.07 | 578675.07 | 1 | 2025-01-28 | 3 | 1739932.62 | -188559.55 | DOWN | 0.1215 | 101 | Low | 367397.83 | 0.242 | 2 | 605300.17 | 19 | 1.97 | 1.9
P001 | Materials | SUP032 | 2025-01 | 2024-10-26 | 1405148.35 | 972698 | -432450.35 | 432450.35 | 1 | 2025-01-28 | 4 | 1551373.07 | -146224.72 | DOWN | 0.1041 | 94 | Low | 374538.86 | 0.257 | 0 | 598159.14 | 19 | 1.97 | 1.9
P001 | Materials | SUP032 | 2025-01 | 2025-01-05 | 1313489.23 | 972698 | -340791.23 | 340791.23 | 1 | 2025-01-28 | 5 | 1405148.35 | -91659.12 | DOWN | 0.0698 | 23 | Low | 495817.19 | 0.401 | 5 | 476880.81 | 19 | 1.97 | 1.9
P001 | Software | SUP032 | 2025-02 | 2024-09-07 | 4224681.33 | 1756038 | -2468643.33 | 2468643.33 | 1 | 2025-02-28 | 1 |  |  |  |  | 174 | Low | 423461.71 | 0.095 | 0 | 1332576.29 | 18 | 1.81 | 1.54
P001 | Software | SUP032 | 2025-02 | 2024-09-22 | 3550078.06 | 1756038 | -1794040.06 | 1794040.06 | 1 | 2025-02-28 | 2 | 4224681.33 | -674603.27 | DOWN | 0.19 | 159 | Low | 453306.61 | 0.126 | 0 | 1302731.39 | 18 | 1.81 | 1.54
P001 | Software | SUP032 | 2025-02 | 2024-09-25 | 3168522.49 | 1756038 | -1412484.49 | 1412484.49 | 1 | 2025-02-28 | 3 | 3550078.06 | -381555.57 | DOWN | 0.1204 | 156 | Low | 434506.86 | 0.133 | 0 | 1321531.14 | 18 | 1.81 | 1.54
P001 | Software | SUP032 | 2025-02 | 2024-10-27 | 2737399.2 | 1756038 | -981361.2 | 981361.2 | 1 | 2025-02-28 | 4 | 3168522.49 | -431123.29 | DOWN | 0.1575 | 124 | Low | 577208.8 | 0.199 | 0 | 1178829.2 | 18 | 1.81 | 1.54
P001 | Software | SUP032 | 2025-02 | 2024-11-28 | 2475371.11 | 1756038 | -719333.11 | 719333.11 | 1 | 2025-02-28 | 5 | 2737399.2 | -262028.09 | DOWN | 0.1059 | 92 | Low | 681346.14 | 0.265 | 4 | 1074691.86 | 18 | 1.81 | 1.54
P001 | Software | SUP032 | 2025-02 | 2025-01-06 | 2301457.73 | 1756038 | -545419.73 | 545419.73 | 1 | 2025-02-28 | 6 | 2475371.11 | -173913.38 | DOWN | 0.0756 | 53 | Low | 786863.61 | 0.346 | 2 | 969174.39 | 18 | 1.81 | 1.54
P001 | Electronics | SUP032 | 2025-03 | 2024-09-29 | 2786906.91 | 1264794 | -1522112.91 | 1522112.91 | 1 | 2025-03-28 | 1 |  |  |  |  | 180 | Low | 279591.23 | 0.1 | 3 | 985202.77 | 20 | 0.93 | 1.57
P001 | Electronics | SUP032 | 2025-03 | 2024-11-04 | 2393140.05 | 1264794 | -1128346.05 | 1128346.05 | 1 | 2025-03-28 | 2 | 2786906.91 | -393766.86 | DOWN | 0.1645 | 144 | Low | 391488.2 | 0.173 | 0 | 873305.8 | 20 | 0.93 | 1.57
P001 | Electronics | SUP032 | 2025-03 | 2025-03-03 | 2119452.91 | 1264794 | -854658.91 | 854658.91 | 1 | 2025-03-28 | 3 | 2393140.05 | -273687.14 | DOWN | 0.1291 | 25 | Low | 925401.19 | 0.443 | 0 | 339392.81 | 20 | 0.93 | 1.57
P001 | Software | SUP032 | 2025-04 | 2024-12-31 | 4023451.42 | 1367595 | -2655856.42 | 2655856.42 | 1 | 2025-04-28 | 1 |  |  |  |  | 118 | Low | 842462.39 | 0.202 | 0 | 525132.61 | 22 | 2.23 | 1.91
P001 | Software | SUP032 | 2025-04 | 2025-02-12 | 3477956.22 | 1367595 | -2110361.22 | 2110361.22 | 1 | 2025-04-28 | 2 | 4023451.42 | -545495.2 | DOWN | 0.1568 | 75 | Low | 1069083.98 | 0.287 | 4 | 298511.02 | 22 | 2.23 | 1.91
P001 | Software | SUP032 | 2025-04 | 2025-02-17 | 2952244.92 | 1367595 | -1584649.92 | 1584649.92 | 1 | 2025-04-28 | 3 | 3477956.22 | -525711.3 | DOWN | 0.1781 | 70 | Low | 927661.2 | 0.297 | 2 | 439933.8 | 22 | 2.23 | 1.91
P001 | Software | SUP032 | 2025-04 | 2025-02-24 | 2506063.14 | 1367595 | -1138468.14 | 1138468.14 | 1 | 2025-04-28 | 4 | 2952244.92 | -446181.78 | DOWN | 0.178 | 63 | Low | 792318.85 | 0.311 | 1 | 575276.15 | 22 | 2.23 | 1.91
P001 | Software | SUP032 | 2025-04 | 2025-04-05 | 2229556.62 | 1367595 | -861961.62 | 861961.62 | 1 | 2025-04-28 | 5 | 2506063.14 | -276506.52 | DOWN | 0.124 | 23 | Low | 871354.94 | 0.39 | 2 | 496240.06 | 22 | 2.23 | 1.91
P001 | Software | SUP032 | 2025-05 | 2025-02-11 | 1937014.84 | 845015 | -1091999.84 | 1091999.84 | 1 | 2025-05-28 | 1 |  |  |  |  | 106 | Low | 487022.87 | 0.235 | 0 | 357992.13 | 21 | 1.86 | 0.96
P001 | Software | SUP032 | 2025-05 | 2025-02-21 | 1643103.53 | 845015 | -798088.53 | 798088.53 | 1 | 2025-05-28 | 2 | 1937014.84 | -293911.31 | DOWN | 0.1789 | 96 | Low | 428009.16 | 0.255 | 2 | 417005.84 | 21 | 1.86 | 0.96
P001 | Software | SUP032 | 2025-05 | 2025-03-09 | 1444477.04 | 845015 | -599462.04 | 599462.04 | 1 | 2025-05-28 | 3 | 1643103.53 | -198626.49 | DOWN | 0.1375 | 80 | Low | 392525.56 | 0.288 | 0 | 452489.44 | 21 | 1.86 | 0.96
P001 | Materials | SUP032 | 2025-06 | 2025-04-16 | 4582774.25 | 2130607 | -2452167.25 | 2452167.25 | 1 | 2025-06-28 | 1 |  |  |  |  | 73 | Low | 1363523.15 | 0.307 | 1 | 767083.85 | 18 | 1.75 | 1.8
P001 | Materials | SUP032 | 2025-06 | 2025-04-18 | 4046424.48 | 2130607 | -1915817.48 | 1915817.48 | 1 | 2025-06-28 | 2 | 4582774.25 | -536349.77 | DOWN | 0.1325 | 71 | Low | 1352278.51 | 0.311 | 1 | 778328.49 | 18 | 1.75 | 1.8
P001 | Materials | SUP032 | 2025-06 | 2025-05-07 | 3569220.43 | 2130607 | -1438613.43 | 1438613.43 | 1 | 2025-06-28 | 3 | 4046424.48 | -477204.05 | DOWN | 0.1337 | 52 | Low | 1327833.94 | 0.35 | 1 | 802773.06 | 18 | 1.75 | 1.8
P001 | Electronics | SUP032 | 2025-07 | 2025-02-06 | 3613969.48 | 1711172 | -1902797.48 | 1902797.48 | 1 | 2025-07-28 | 1 |  |  |  |  | 172 | Low | 358831.66 | 0.106 | 2 | 1352340.34 | 17 | 1.27 | 1.46
P001 | Electronics | SUP032 | 2025-07 | 2025-03-01 | 3145278.38 | 1711172 | -1434106.38 | 1434106.38 | 1 | 2025-07-28 | 2 | 3613969.48 | -468691.1 | DOWN | 0.149 | 149 | Low | 486727.59 | 0.156 | 0 | 1224444.41 | 17 | 1.27 | 1.46
P001 | Electronics | SUP032 | 2025-07 | 2025-04-07 | 2819629.59 | 1711172 | -1108457.59 | 1108457.59 | 1 | 2025-07-28 | 3 | 3145278.38 | -325648.79 | DOWN | 0.1155 | 112 | Low | 687740.87 | 0.238 | 3 | 1023431.13 | 17 | 1.27 | 1.46
P001 | Electronics | SUP032 | 2025-07 | 2025-05-19 | 2503047.65 | 1711172 | -791875.65 | 791875.65 | 1 | 2025-07-28 | 4 | 2819629.59 | -316581.94 | DOWN | 0.1265 | 70 | Low | 857474.63 | 0.33 | 3 | 853697.37 | 17 | 1.27 | 1.46
P001 | Electronics | SUP032 | 2025-07 | 2025-06-22 | 2312162.43 | 1711172 | -600990.43 | 600990.43 | 1 | 2025-07-28 | 5 | 2503047.65 | -190885.22 | DOWN | 0.0826 | 36 | Low | 1002818.66 | 0.405 | 0 | 708353.34 | 17 | 1.27 | 1.46
P001 | Electronics | SUP032 | 2025-07 | 2025-07-02 | 2182936.97 | 1711172 | -471764.97 | 471764.97 | 1 | 2025-07-28 | 6 | 2312162.43 | -129225.46 | DOWN | 0.0592 | 26 | Low | 870319.82 | 0.427 | 5 | 840852.18 | 17 | 1.27 | 1.46
P001 | Logistics | SUP032 | 2025-08 | 2025-04-11 | 1628234.99 | 735391 | -892843.99 | 892843.99 | 1 | 2025-08-28 | 1 |  |  |  |  | 139 | Low | 287642.24 | 0.173 | 0 | 447748.76 | 21 | 1.54 | 1.03
P001 | Logistics | SUP032 | 2025-08 | 2025-04-16 | 1402063.49 | 735391 | -666672.49 | 666672.49 | 1 | 2025-08-28 | 2 | 1628234.99 | -226171.5 | DOWN | 0.1613 | 134 | Low | 244887.37 | 0.184 | 2 | 490503.63 | 21 | 1.54 | 1.03
P001 | Logistics | SUP032 | 2025-08 | 2025-04-27 | 1238916.67 | 735391 | -503525.67 | 503525.67 | 1 | 2025-08-28 | 3 | 1402063.49 | -163146.82 | DOWN | 0.1317 | 123 | Low | 273414.27 | 0.207 | 6 | 461976.73 | 21 | 1.54 | 1.03
P001 | Logistics | SUP032 | 2025-08 | 2025-06-30 | 1129354.47 | 735391 | -393963.47 | 393963.47 | 1 | 2025-08-28 | 4 | 1238916.67 | -109562.2 | DOWN | 0.097 | 59 | Low | 382615.81 | 0.344 | 1 | 352775.19 | 21 | 1.54 | 1.03
P001 | Logistics | SUP032 | 2025-08 | 2025-07-14 | 1047737.25 | 735391 | -312346.25 | 312346.25 | 1 | 2025-08-28 | 5 | 1129354.47 | -81617.22 | DOWN | 0.0779 | 45 | Low | 405559.24 | 0.374 | 3 | 329831.76 | 21 | 1.54 | 1.03
P001 | Electronics | SUP032 | 2025-09 | 2025-05-08 | 1428258.09 | 589209 | -839049.09 | 839049.09 | 1 | 2025-09-28 | 1 |  |  |  |  | 143 | Low | 261841.19 | 0.172 | 2 | 327367.81 | 15 | 1.16 | 1.5
P001 | Electronics | SUP032 | 2025-09 | 2025-06-16 | 1225517.74 | 589209 | -636308.74 | 636308.74 | 1 | 2025-09-28 | 2 | 1428258.09 | -202740.35 | DOWN | 0.1654 | 104 | Low | 324519.44 | 0.259 | 0 | 264689.56 | 15 | 1.16 | 1.5
P001 | Electronics | SUP032 | 2025-09 | 2025-09-05 | 1059242.66 | 589209 | -470033.66 | 470033.66 | 1 | 2025-09-28 | 3 | 1225517.74 | -166275.08 | DOWN | 0.157 | 23 | Low | 491424.18 | 0.439 | 0 | 97784.82 | 15 | 1.16 | 1.5
P001 | Logistics | SUP032 | 2025-10 | 2025-05-21 | 3486643.34 | 1314244 | -2172399.34 | 2172399.34 | 1 | 2025-10-28 | 1 |  |  |  |  | 160 | Low | 437495.96 | 0.124 | 0 | 876748.04 | 18 | 1.81 | 1.33
P001 | Logistics | SUP032 | 2025-10 | 2025-06-30 | 2955889.05 | 1314244 | -1641645.05 | 1641645.05 | 1 | 2025-10-28 | 2 | 3486643.34 | -530754.29 | DOWN | 0.1796 | 120 | Low | 611974.65 | 0.207 | 3 | 702269.35 | 18 | 1.81 | 1.33
P001 | Logistics | SUP032 | 2025-10 | 2025-08-12 | 2478957.48 | 1314244 | -1164713.48 | 1164713.48 | 1 | 2025-10-28 | 3 | 2955889.05 | -476931.57 | DOWN | 0.1924 | 77 | Low | 743422.68 | 0.296 | 2 | 570821.32 | 18 | 1.81 | 1.33
P001 | Logistics | SUP032 | 2025-10 | 2025-08-21 | 2220836.07 | 1314244 | -906592.07 | 906592.07 | 1 | 2025-10-28 | 4 | 2478957.48 | -258121.41 | DOWN | 0.1162 | 68 | Low | 706125.8 | 0.315 | 3 | 608118.2 | 18 | 1.81 | 1.33
P001 | Materials | SUP032 | 2025-11 | 2025-08-13 | 466685.95 | 267125 | -199560.95 | 199560.95 | 1 | 2025-11-28 | 1 |  |  |  |  | 107 | Low | 114410.7 | 0.253 | 1 | 152714.3 | 26 | 1.11 | 1.53
P001 | Materials | SUP032 | 2025-11 | 2025-09-06 | 421113.17 | 267125 | -153988.17 | 153988.17 | 1 | 2025-11-28 | 2 | 466685.95 | -45572.78 | DOWN | 0.1082 | 83 | Low | 137314.36 | 0.307 | 5 | 129810.64 | 26 | 1.11 | 1.53
P001 | Materials | SUP032 | 2025-11 | 2025-10-11 | 386125.8 | 267125 | -119000.8 | 119000.8 | 1 | 2025-11-28 | 3 | 421113.17 | -34987.37 | DOWN | 0.0906 | 48 | Low | 151888.12 | 0.386 | 1 | 115236.88 | 26 | 1.11 | 1.53
P001 | Materials | SUP032 | 2025-11 | 2025-11-09 | 352111.78 | 267125 | -84986.78 | 84986.78 | 1 | 2025-11-28 | 4 | 386125.8 | -34014.02 | DOWN | 0.0966 | 19 | Low | 159113.34 | 0.451 | 1 | 108011.66 | 26 | 1.11 | 1.53
P001 | Materials | SUP032 | 2025-11 | 2025-11-11 | 330281.69 | 267125 | -63156.69 | 63156.69 | 1 | 2025-11-28 | 5 | 352111.78 | -21830.09 | DOWN | 0.0661 | 17 | Low | 157026.11 | 0.455 | 4 | 110098.89 | 26 | 1.11 | 1.53
P001 | Materials | SUP032 | 2025-12 | 2025-07-22 | 4110185.55 | 1740285 | -2369900.55 | 2369900.55 | 1 | 2025-12-28 | 1 |  |  |  |  | 159 | Low | 543579.93 | 0.132 | 2 | 1196705.07 | 17 | 1.45 | 1.29
P001 | Materials | SUP032 | 2025-12 | 2025-08-12 | 3498196.82 | 1740285 | -1757911.82 | 1757911.82 | 1 | 2025-12-28 | 2 | 4110185.55 | -611988.73 | DOWN | 0.1749 | 138 | Low | 569449.78 | 0.177 | 1 | 1170835.22 | 17 | 1.45 | 1.29
P001 | Materials | SUP032 | 2025-12 | 2025-10-04 | 3045215.57 | 1740285 | -1304930.57 | 1304930.57 | 1 | 2025-12-28 | 3 | 3498196.82 | -452981.25 | DOWN | 0.1488 | 85 | Low | 873892.59 | 0.291 | 3 | 866392.41 | 17 | 1.45 | 1.29
P001 | Materials | SUP032 | 2025-12 | 2025-11-01 | 2692646.12 | 1740285 | -952361.12 | 952361.12 | 1 | 2025-12-28 | 4 | 3045215.57 | -352569.45 | DOWN | 0.1309 | 57 | Low | 879068.97 | 0.351 | 0 | 861216.03 | 17 | 1.45 | 1.29
P001 | Materials | SUP032 | 2025-12 | 2025-11-29 | 2423013.79 | 1740285 | -682728.79 | 682728.79 | 1 | 2025-12-28 | 5 | 2692646.12 | -269632.33 | DOWN | 0.1113 | 29 | Low | 1043665.3 | 0.412 | 3 | 696619.7 | 17 | 1.45 | 1.29
P001 | Materials | SUP032 | 2025-12 | 2025-12-18 | 2259101.38 | 1740285 | -518816.38 | 518816.38 | 1 | 2025-12-28 | 6 | 2423013.79 | -163912.41 | DOWN | 0.0726 | 10 | Low | 1078534.22 | 0.451 | 4 | 661750.78 | 17 | 1.45 | 1.29
P001 | Logistics | SUP024 | 2025-01 | 2024-08-18 | 4149394.17 | 1737189 | -2412205.17 | 2412205.17 | 1 | 2025-01-28 | 1 |  |  |  |  | 163 | Low | 627915.71 | 0.151 | 2 | 1109273.29 | 19 | 1.97 | 1.9
P001 | Logistics | SUP024 | 2025-01 | 2024-08-26 | 3128736.19 | 1737189 | -1391547.19 | 1391547.19 | 1 | 2025-01-28 | 2 | 4149394.17 | -1020657.98 | DOWN | 0.3262 | 155 | Low | 538615.47 | 0.172 | 0 | 1198573.53 | 19 | 1.97 | 1.9
P001 | Logistics | SUP024 | 2025-01 | 2024-09-11 | 2612672.48 | 1737189 | -875483.48 | 875483.48 | 1 | 2025-01-28 | 3 | 3128736.19 | -516063.71 | DOWN | 0.1975 | 139 | Low | 548365.34 | 0.214 | 0 | 1188823.66 | 19 | 1.97 | 1.9
P001 | Logistics | SUP024 | 2025-01 | 2024-09-23 | 2272682.91 | 1737189 | -535493.91 | 535493.91 | 1 | 2025-01-28 | 4 | 2612672.48 | -339989.57 | DOWN | 0.1496 | 127 | Low | 527729.4 | 0.246 | 1 | 1209459.6 | 19 | 1.97 | 1.9
P001 | Logistics | SUP024 | 2025-01 | 2024-11-06 | 1974995.05 | 1737189 | -237806.05 | 237806.05 | 0 | 2025-01-28 | 5 | 2272682.91 | -297687.86 | DOWN | 0.1507 | 83 | Low | 746396.3 | 0.363 | 5 | 990792.7 | 19 | 1.97 | 1.9
P001 | Logistics | SUP024 | 2025-01 | 2025-01-04 | 1855769.18 | 1737189 | -118580.18 | 118580.18 | 0 | 2025-01-28 | 6 | 1974995.05 | -119225.87 | DOWN | 0.0642 | 24 | Low | 1035955.43 | 0.519 | 1 | 701233.57 | 19 | 1.97 | 1.9
P001 | Electronics | SUP024 | 2025-02 | 2024-11-22 | 4295410.62 | 2284609 | -2010801.62 | 2010801.62 | 1 | 2025-02-28 | 1 |  |  |  |  | 98 | Low | 1457787.52 | 0.329 | 1 | 826821.48 | 18 | 1.81 | 1.54
P001 | Electronics | SUP024 | 2025-02 | 2024-12-24 | 3366923.17 | 2284609 | -1082314.17 | 1082314.17 | 1 | 2025-02-28 | 2 | 4295410.62 | -928487.45 | DOWN | 0.2758 | 66 | Low | 1325686.83 | 0.415 | 0 | 958922.17 | 18 | 1.81 | 1.54
P001 | Electronics | SUP024 | 2025-02 | 2025-01-01 | 2846717.9 | 2284609 | -562108.9 | 562108.9 | 1 | 2025-02-28 | 3 | 3366923.17 | -520205.27 | DOWN | 0.1827 | 58 | Low | 1330806.95 | 0.436 | 4 | 953802.05 | 18 | 1.81 | 1.54
P001 | Services | SUP024 | 2025-03 | 2024-11-18 | 1111123.79 | 487820 | -623303.79 | 623303.79 | 1 | 2025-03-28 | 1 |  |  |  |  | 130 | Low | 299094.48 | 0.266 | 1 | 188725.52 | 20 | 0.93 | 1.57
P001 | Services | SUP024 | 2025-03 | 2024-12-09 | 823304.43 | 487820 | -335484.43 | 335484.43 | 1 | 2025-03-28 | 2 | 1111123.79 | -287819.36 | DOWN | 0.3496 | 109 | Low | 250872.69 | 0.328 | 2 | 236947.31 | 20 | 0.93 | 1.57
P001 | Services | SUP024 | 2025-03 | 2025-03-12 | 680847.58 | 487820 | -193027.58 | 193027.58 | 1 | 2025-03-28 | 3 | 823304.43 | -142456.85 | DOWN | 0.2092 | 16 | Low | 432592.21 | 0.603 | 2 | 55227.79 | 20 | 0.93 | 1.57
P001 | Services | SUP024 | 2025-03 | 2025-03-17 | 597775.05 | 487820 | -109955.05 | 109955.05 | 1 | 2025-03-28 | 4 | 680847.58 | -83072.53 | DOWN | 0.139 | 11 | Low | 388266.1 | 0.617 | 6 | 99553.9 | 20 | 0.93 | 1.57
P001 | Electronics | SUP024 | 2025-04 | 2024-11-17 | 2058032.93 | 1045092 | -1012940.93 | 1012940.93 | 1 | 2025-04-28 | 1 |  |  |  |  | 162 | Low | 296741.73 | 0.149 | 0 | 748350.27 | 22 | 2.23 | 1.91
P001 | Electronics | SUP024 | 2025-04 | 2025-01-06 | 1619101.64 | 1045092 | -574009.64 | 574009.64 | 1 | 2025-04-28 | 2 | 2058032.93 | -438931.29 | DOWN | 0.2711 | 112 | Low | 450369.64 | 0.278 | 3 | 594722.36 | 22 | 2.23 | 1.91
P001 | Electronics | SUP024 | 2025-04 | 2025-01-07 | 1403894.8 | 1045092 | -358802.8 | 358802.8 | 1 | 2025-04-28 | 3 | 1619101.64 | -215206.84 | DOWN | 0.1533 | 111 | Low | 386609.21 | 0.281 | 4 | 658482.79 | 22 | 2.23 | 1.91
P001 | Electronics | SUP024 | 2025-04 | 2025-02-07 | 1219819.82 | 1045092 | -174727.82 | 174727.82 | 0 | 2025-04-28 | 4 | 1403894.8 | -184074.98 | DOWN | 0.1509 | 80 | Low | 425391.89 | 0.36 | 0 | 619700.11 | 22 | 2.23 | 1.91
P001 | Software | SUP024 | 2025-05 | 2024-12-11 | 3167349.53 | 1481847 | -1685502.53 | 1685502.53 | 1 | 2025-05-28 | 1 |  |  |  |  | 168 | Low | 440415.55 | 0.139 | 1 | 1041431.45 | 21 | 1.86 | 0.96
P001 | Software | SUP024 | 2025-05 | 2025-01-12 | 2397323.51 | 1481847 | -915476.51 | 915476.51 | 1 | 2025-05-28 | 2 | 3167349.53 | -770026.02 | DOWN | 0.3212 | 136 | Low | 514166.26 | 0.225 | 0 | 967680.74 | 21 | 1.86 | 0.96
P001 | Software | SUP024 | 2025-05 | 2025-01-25 | 1954435.4 | 1481847 | -472588.4 | 472588.4 | 1 | 2025-05-28 | 3 | 2397323.51 | -442888.11 | DOWN | 0.2266 | 123 | Low | 494990.82 | 0.26 | 0 | 986856.18 | 21 | 1.86 | 0.96
P001 | Software | SUP024 | 2025-05 | 2025-02-20 | 1760645.19 | 1481847 | -278798.19 | 278798.19 | 1 | 2025-05-28 | 4 | 1954435.4 | -193790.21 | DOWN | 0.1101 | 97 | Low | 620317.04 | 0.329 | 1 | 861529.96 | 21 | 1.86 | 0.96
P001 | Software | SUP024 | 2025-05 | 2025-03-07 | 1614379.79 | 1481847 | -132532.79 | 132532.79 | 0 | 2025-05-28 | 5 | 1760645.19 | -146265.4 | DOWN | 0.0906 | 82 | Low | 630573.97 | 0.37 | 0 | 851273.03 | 21 | 1.86 | 0.96
P001 | Software | SUP024 | 2025-05 | 2025-04-28 | 1540444.71 | 1481847 | -58597.71 | 58597.71 | 0 | 2025-05-28 | 6 | 1614379.79 | -73935.08 | DOWN | 0.048 | 30 | Medium | 803216.85 | 0.509 | 5 | 678630.15 | 21 | 1.86 | 0.96
P001 | Materials | SUP024 | 2025-06 | 2025-01-08 | 3434471.78 | 1633961 | -1800510.78 | 1800510.78 | 1 | 2025-06-28 | 1 |  |  |  |  | 171 | Low | 457471.12 | 0.133 | 1 | 1176489.88 | 18 | 1.75 | 1.8
P001 | Materials | SUP024 | 2025-06 | 2025-02-07 | 2606283.45 | 1633961 | -972322.45 | 972322.45 | 1 | 2025-06-28 | 2 | 3434471.78 | -828188.33 | DOWN | 0.3178 | 141 | Low | 583271.08 | 0.214 | 2 | 1050689.92 | 18 | 1.75 | 1.8
P001 | Materials | SUP024 | 2025-06 | 2025-02-17 | 2186190.75 | 1633961 | -552229.75 | 552229.75 | 1 | 2025-06-28 | 3 | 2606283.45 | -420092.7 | DOWN | 0.1922 | 131 | Low | 558229.84 | 0.241 | 0 | 1075731.16 | 18 | 1.75 | 1.8
P001 | Materials | SUP024 | 2025-06 | 2025-04-03 | 1913872.3 | 1633961 | -279911.3 | 279911.3 | 0 | 2025-06-28 | 4 | 2186190.75 | -272318.45 | DOWN | 0.1423 | 86 | Low | 653828.64 | 0.363 | 1 | 980132.36 | 18 | 1.75 | 1.8
P001 | Materials | SUP024 | 2025-06 | 2025-04-14 | 1782704.11 | 1633961 | -148743.11 | 148743.11 | 0 | 2025-06-28 | 5 | 1913872.3 | -131168.19 | DOWN | 0.0736 | 75 | Low | 696350.59 | 0.393 | 5 | 937610.41 | 18 | 1.75 | 1.8
P001 | Materials | SUP024 | 2025-06 | 2025-04-28 | 1715165.39 | 1633961 | -81204.39 | 81204.39 | 0 | 2025-06-28 | 6 | 1782704.11 | -67538.72 | DOWN | 0.0394 | 61 | Low | 761518.14 | 0.431 | 5 | 872442.86 | 18 | 1.75 | 1.8
P001 | Software | SUP024 | 2025-07 | 2025-02-12 | 3344045.52 | 1623886 | -1720159.52 | 1720159.52 | 1 | 2025-07-28 | 1 |  |  |  |  | 166 | Low | 491902.94 | 0.155 | 1 | 1131983.06 | 17 | 1.27 | 1.46
P001 | Software | SUP024 | 2025-07 | 2025-02-24 | 2560115.33 | 1623886 | -936229.33 | 936229.33 | 1 | 2025-07-28 | 2 | 3344045.52 | -783930.19 | DOWN | 0.3062 | 154 | Low | 500926.86 | 0.189 | 0 | 1122959.14 | 17 | 1.27 | 1.46
P001 | Software | SUP024 | 2025-07 | 2025-06-14 | 2120954.6 | 1623886 | -497068.6 | 497068.6 | 1 | 2025-07-28 | 3 | 2560115.33 | -439160.73 | DOWN | 0.2071 | 44 | Low | 1049172.26 | 0.504 | 4 | 574713.74 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP024 | 2025-08 | 2025-04-14 | 3310210.13 | 1629570 | -1680640.13 | 1680640.13 | 1 | 2025-08-28 | 1 |  |  |  |  | 136 | Low | 778670.78 | 0.233 | 0 | 850899.22 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP024 | 2025-08 | 2025-04-29 | 2555287.7 | 1629570 | -925717.7 | 925717.7 | 1 | 2025-08-28 | 2 | 3310210.13 | -754922.43 | DOWN | 0.2954 | 121 | Low | 711594.39 | 0.275 | 2 | 917975.61 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP024 | 2025-08 | 2025-05-06 | 2166809.02 | 1629570 | -537239.02 | 537239.02 | 1 | 2025-08-28 | 3 | 2555287.7 | -388478.68 | DOWN | 0.1793 | 114 | Low | 614054.09 | 0.294 | 2 | 1015515.91 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP024 | 2025-08 | 2025-07-14 | 1893007.89 | 1629570 | -263437.89 | 263437.89 | 0 | 2025-08-28 | 4 | 2166809.02 | -273801.13 | DOWN | 0.1446 | 45 | Low | 931128.34 | 0.486 | 5 | 698441.66 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP024 | 2025-08 | 2025-08-17 | 1788807.11 | 1629570 | -159237.11 | 159237.11 | 0 | 2025-08-28 | 5 | 1893007.89 | -104200.78 | DOWN | 0.0583 | 11 | Medium | 954631.38 | 0.58 | 4 | 674938.62 | 21 | 1.54 | 1.03
P001 | Software | SUP024 | 2025-09 | 2025-05-02 | 4163276.19 | 1854608 | -2308668.19 | 2308668.19 | 1 | 2025-09-28 | 1 |  |  |  |  | 149 | Low | 852787.62 | 0.206 | 0 | 1001820.38 | 15 | 1.16 | 1.5
P001 | Software | SUP024 | 2025-09 | 2025-06-11 | 3068705.88 | 1854608 | -1214097.88 | 1214097.88 | 1 | 2025-09-28 | 2 | 4163276.19 | -1094570.31 | DOWN | 0.3567 | 109 | Low | 1021375.26 | 0.322 | 4 | 833232.74 | 15 | 1.16 | 1.5
P001 | Software | SUP024 | 2025-09 | 2025-07-25 | 2551265.64 | 1854608 | -696657.64 | 696657.64 | 1 | 2025-09-28 | 3 | 3068705.88 | -517440.24 | DOWN | 0.2028 | 65 | Low | 1230953.26 | 0.449 | 4 | 623654.74 | 15 | 1.16 | 1.5
P001 | Logistics | SUP024 | 2025-10 | 2025-05-13 | 5202864.27 | 2120932 | -3081932.27 | 3081932.27 | 1 | 2025-10-28 | 1 |  |  |  |  | 168 | Low | 773802.28 | 0.14 | 0 | 1347129.72 | 18 | 1.81 | 1.33
P001 | Logistics | SUP024 | 2025-10 | 2025-05-21 | 3722457.88 | 2120932 | -1601525.88 | 1601525.88 | 1 | 2025-10-28 | 2 | 5202864.27 | -1480406.39 | DOWN | 0.3977 | 160 | Low | 562978.1 | 0.162 | 1 | 1557953.9 | 18 | 1.81 | 1.33
P001 | Logistics | SUP024 | 2025-10 | 2025-07-06 | 3007702.53 | 2120932 | -886770.53 | 886770.53 | 1 | 2025-10-28 | 3 | 3722457.88 | -714755.35 | DOWN | 0.2376 | 114 | Low | 900046.62 | 0.285 | 1 | 1220885.38 | 18 | 1.81 | 1.33
P001 | Logistics | SUP024 | 2025-10 | 2025-07-17 | 2575584.83 | 2120932 | -454652.83 | 454652.83 | 1 | 2025-10-28 | 4 | 3007702.53 | -432117.7 | DOWN | 0.1678 | 103 | Low | 874906.79 | 0.315 | 4 | 1246025.21 | 18 | 1.81 | 1.33
P001 | Logistics | SUP024 | 2025-10 | 2025-08-16 | 2418357.28 | 2120932 | -297425.28 | 297425.28 | 0 | 2025-10-28 | 5 | 2575584.83 | -157227.55 | DOWN | 0.065 | 73 | Low | 934304.28 | 0.396 | 3 | 1186627.72 | 18 | 1.81 | 1.33
P001 | Logistics | SUP024 | 2025-10 | 2025-08-21 | 2244394.76 | 2120932 | -123462.76 | 123462.76 | 0 | 2025-10-28 | 6 | 2418357.28 | -173962.52 | DOWN | 0.0775 | 68 | Low | 859973.08 | 0.409 | 0 | 1260958.92 | 18 | 1.81 | 1.33
P001 | Electronics | SUP024 | 2025-11 | 2025-06-19 | 3178951.74 | 1379233 | -1799718.74 | 1799718.74 | 1 | 2025-11-28 | 1 |  |  |  |  | 162 | Low | 519072.15 | 0.169 | 3 | 860160.85 | 26 | 1.11 | 1.53
P001 | Electronics | SUP024 | 2025-11 | 2025-06-27 | 2404288.27 | 1379233 | -1025055.27 | 1025055.27 | 1 | 2025-11-28 | 2 | 3178951.74 | -774663.47 | DOWN | 0.3222 | 154 | Low | 487154.31 | 0.192 | 0 | 892078.69 | 26 | 1.11 | 1.53
P001 | Electronics | SUP024 | 2025-11 | 2025-07-09 | 1930159.67 | 1379233 | -550926.67 | 550926.67 | 1 | 2025-11-28 | 3 | 2404288.27 | -474128.6 | DOWN | 0.2456 | 142 | Low | 460849.22 | 0.227 | 4 | 918383.78 | 26 | 1.11 | 1.53
P001 | Electronics | SUP024 | 2025-11 | 2025-09-06 | 1665033.43 | 1379233 | -285800.43 | 285800.43 | 1 | 2025-11-28 | 4 | 1930159.67 | -265126.24 | DOWN | 0.1592 | 83 | Low | 695196.54 | 0.399 | 4 | 684036.46 | 26 | 1.11 | 1.53
P001 | Electronics | SUP024 | 2025-11 | 2025-09-26 | 1545396.36 | 1379233 | -166163.36 | 166163.36 | 0 | 2025-11-28 | 5 | 1665033.43 | -119637.07 | DOWN | 0.0774 | 63 | Low | 754655.64 | 0.458 | 3 | 624577.36 | 26 | 1.11 | 1.53
P001 | Electronics | SUP024 | 2025-11 | 2025-09-27 | 1456180.95 | 1379233 | -76947.95 | 76947.95 | 0 | 2025-11-28 | 6 | 1545396.36 | -89215.41 | DOWN | 0.0613 | 62 | Low | 619846.94 | 0.461 | 0 | 759386.06 | 26 | 1.11 | 1.53
P001 | Materials | SUP024 | 2025-12 | 2025-08-04 | 2181506.57 | 1008169 | -1173337.57 | 1173337.57 | 1 | 2025-12-28 | 1 |  |  |  |  | 146 | Low | 419352.29 | 0.207 | 0 | 588816.71 | 17 | 1.45 | 1.29
P001 | Materials | SUP024 | 2025-12 | 2025-08-06 | 1637258.22 | 1008169 | -629089.22 | 629089.22 | 1 | 2025-12-28 | 2 | 2181506.57 | -544248.35 | DOWN | 0.3324 | 144 | Low | 376117.12 | 0.213 | 6 | 632051.88 | 17 | 1.45 | 1.29
P001 | Materials | SUP024 | 2025-12 | 2025-09-25 | 1348976.32 | 1008169 | -340807.32 | 340807.32 | 1 | 2025-12-28 | 3 | 1637258.22 | -288281.9 | DOWN | 0.2137 | 94 | Low | 512766.9 | 0.353 | 1 | 495402.1 | 17 | 1.45 | 1.29
P001 | Materials | SUP024 | 2025-12 | 2025-10-12 | 1207143.05 | 1008169 | -198974.05 | 198974.05 | 1 | 2025-12-28 | 4 | 1348976.32 | -141833.27 | DOWN | 0.1175 | 77 | Low | 497671.34 | 0.401 | 3 | 510497.66 | 17 | 1.45 | 1.29
P001 | Materials | SUP024 | 2025-12 | 2025-10-21 | 1124462.85 | 1008169 | -116293.85 | 116293.85 | 0 | 2025-12-28 | 5 | 1207143.05 | -82680.2 | DOWN | 0.0735 | 68 | Low | 476077.92 | 0.426 | 4 | 532091.08 | 17 | 1.45 | 1.29
P001 | Materials | SUP024 | 2025-12 | 2025-12-06 | 1067089.73 | 1008169 | -58920.73 | 58920.73 | 0 | 2025-12-28 | 6 | 1124462.85 | -57373.12 | DOWN | 0.0538 | 22 | Medium | 592524.42 | 0.555 | 4 | 415644.58 | 17 | 1.45 | 1.29
P001 | Materials | SUP008 | 2025-01 | 2024-08-13 | 1975725.18 | 1199526 | -776199.18 | 776199.18 | 1 | 2025-01-28 | 1 |  |  |  |  | 168 | Low | 330781.57 | 0.165 | 3 | 868744.43 | 19 | 1.97 | 1.9
P001 | Materials | SUP008 | 2025-01 | 2024-09-13 | 1524833.02 | 1199526 | -325307.02 | 325307.02 | 1 | 2025-01-28 | 2 | 1975725.18 | -450892.16 | DOWN | 0.2957 | 137 | Low | 405725.33 | 0.264 | 1 | 793800.67 | 19 | 1.97 | 1.9
P001 | Materials | SUP008 | 2025-01 | 2024-10-21 | 1358892.11 | 1199526 | -159366.11 | 159366.11 | 0 | 2025-01-28 | 3 | 1524833.02 | -165940.91 | DOWN | 0.1221 | 99 | Low | 552139.66 | 0.384 | 2 | 647386.34 | 19 | 1.97 | 1.9
P001 | Materials | SUP008 | 2025-01 | 2024-11-17 | 1256605.76 | 1199526 | -57079.76 | 57079.76 | 0 | 2025-01-28 | 4 | 1358892.11 | -102286.35 | DOWN | 0.0814 | 72 | Low | 601690.67 | 0.47 | 4 | 597835.33 | 19 | 1.97 | 1.9
P001 | Materials | SUP008 | 2025-01 | 2024-12-27 | 1248478.17 | 1199526 | -48952.17 | 48952.17 | 0 | 2025-01-28 | 5 | 1256605.76 | -8127.59 | DOWN | 0.0065 | 32 | Low | 793319.61 | 0.597 | 4 | 406206.39 | 19 | 1.97 | 1.9
P001 | Materials | SUP008 | 2025-01 | 2025-01-18 | 1222593.66 | 1199526 | -23067.66 | 23067.66 | 0 | 2025-01-28 | 6 | 1248478.17 | -25884.51 | DOWN | 0.0212 | 10 | Low | 810306.1 | 0.664 | 6 | 389219.9 | 19 | 1.97 | 1.9
P001 | Software | SUP008 | 2025-02 | 2024-10-11 | 1828176.82 | 896609 | -931567.82 | 931567.82 | 1 | 2025-02-28 | 1 |  |  |  |  | 140 | Low | 509372.42 | 0.259 | 1 | 387236.58 | 18 | 1.81 | 1.54
P001 | Software | SUP008 | 2025-02 | 2024-10-26 | 1343133.15 | 896609 | -446524.15 | 446524.15 | 1 | 2025-02-28 | 2 | 1828176.82 | -485043.67 | DOWN | 0.3611 | 125 | Low | 423296.89 | 0.307 | 2 | 473312.11 | 18 | 1.81 | 1.54
P001 | Software | SUP008 | 2025-02 | 2024-10-31 | 1104980.44 | 896609 | -208371.44 | 208371.44 | 1 | 2025-02-28 | 3 | 1343133.15 | -238152.71 | DOWN | 0.2155 | 120 | Low | 371745.08 | 0.323 | 0 | 524863.92 | 18 | 1.81 | 1.54
P001 | Software | SUP008 | 2025-02 | 2024-12-30 | 989860.42 | 896609 | -93251.42 | 93251.42 | 0 | 2025-02-28 | 4 | 1104980.44 | -115120.02 | DOWN | 0.1163 | 60 | Medium | 492804.69 | 0.517 | 2 | 403804.31 | 18 | 1.81 | 1.54
P001 | Materials | SUP008 | 2025-03 | 2024-10-18 | 2382976.22 | 1559437 | -823539.22 | 823539.22 | 1 | 2025-03-28 | 1 |  |  |  |  | 161 | Low | 528273.76 | 0.209 | 2 | 1031163.24 | 20 | 0.93 | 1.57
P001 | Materials | SUP008 | 2025-03 | 2024-11-04 | 1911038.39 | 1559437 | -351601.39 | 351601.39 | 1 | 2025-03-28 | 2 | 2382976.22 | -471937.83 | DOWN | 0.247 | 144 | Low | 538400.05 | 0.269 | 3 | 1021036.95 | 20 | 0.93 | 1.57
P001 | Materials | SUP008 | 2025-03 | 2025-01-24 | 1703897.05 | 1559437 | -144460.05 | 144460.05 | 0 | 2025-03-28 | 3 | 1911038.39 | -207141.34 | DOWN | 0.1216 | 63 | Low | 980284.56 | 0.557 | 3 | 579152.44 | 20 | 0.93 | 1.57
P001 | Materials | SUP008 | 2025-03 | 2025-02-26 | 1631425.4 | 1559437 | -71988.4 | 71988.4 | 0 | 2025-03-28 | 4 | 1703897.05 | -72471.65 | DOWN | 0.0444 | 30 | High | 1102696.8 | 0.674 | 4 | 456740.2 | 20 | 0.93 | 1.57
P001 | Materials | SUP008 | 2025-03 | 2025-03-11 | 1593298.11 | 1559437 | -33861.11 | 33861.11 | 0 | 2025-03-28 | 5 | 1631425.4 | -38127.29 | DOWN | 0.0239 | 17 | High | 1079858.41 | 0.72 | 7 | 479578.59 | 20 | 0.93 | 1.57
P001 | Logistics | SUP008 | 2025-04 | 2024-10-31 | 1331171.1 | 704119 | -627052.1 | 627052.1 | 1 | 2025-04-28 | 1 |  |  |  |  | 179 | Low | 169169.61 | 0.136 | 1 | 534949.39 | 22 | 2.23 | 1.91
P001 | Logistics | SUP008 | 2025-04 | 2024-11-14 | 966783.45 | 704119 | -262664.45 | 262664.45 | 1 | 2025-04-28 | 2 | 1331171.1 | -364387.65 | DOWN | 0.3769 | 165 | Low | 168715.84 | 0.17 | 2 | 535403.16 | 22 | 2.23 | 1.91
P001 | Logistics | SUP008 | 2025-04 | 2024-11-27 | 843497.21 | 704119 | -139378.21 | 139378.21 | 1 | 2025-04-28 | 3 | 966783.45 | -123286.24 | DOWN | 0.1462 | 152 | Low | 173153.73 | 0.21 | 3 | 530965.27 | 22 | 2.23 | 1.91
P001 | Logistics | SUP008 | 2025-04 | 2025-01-23 | 740598.32 | 704119 | -36479.32 | 36479.32 | 0 | 2025-04-28 | 4 | 843497.21 | -102898.89 | DOWN | 0.1389 | 95 | Low | 296326.81 | 0.386 | 4 | 407792.19 | 22 | 2.23 | 1.91
P001 | Logistics | SUP008 | 2025-04 | 2025-04-03 | 717923.67 | 704119 | -13804.67 | 13804.67 | 0 | 2025-04-28 | 5 | 740598.32 | -22674.65 | DOWN | 0.0316 | 25 | Low | 448929.73 | 0.602 | 6 | 255189.27 | 22 | 2.23 | 1.91
P001 | Services | SUP008 | 2025-05 | 2025-01-02 | 3491674.62 | 2117432 | -1374242.62 | 1374242.62 | 1 | 2025-05-28 | 1 |  |  |  |  | 146 | Low | 892764.72 | 0.238 | 3 | 1224667.28 | 21 | 1.86 | 0.96
P001 | Services | SUP008 | 2025-05 | 2025-01-07 | 2746945.62 | 2117432 | -629513.62 | 629513.62 | 1 | 2025-05-28 | 2 | 3491674.62 | -744729 | DOWN | 0.2711 | 141 | Low | 738346.65 | 0.254 | 2 | 1379085.35 | 21 | 1.86 | 0.96
P001 | Services | SUP008 | 2025-05 | 2025-04-01 | 2420128.96 | 2117432 | -302696.96 | 302696.96 | 0 | 2025-05-28 | 3 | 2746945.62 | -326816.66 | DOWN | 0.135 | 57 | Low | 1179279.66 | 0.524 | 2 | 938152.34 | 21 | 1.86 | 0.96
P001 | Services | SUP008 | 2025-06 | 2025-01-02 | 1220933.41 | 641018 | -579915.41 | 579915.41 | 1 | 2025-06-28 | 1 |  |  |  |  | 177 | Low | 185445.64 | 0.143 | 0 | 455572.36 | 18 | 1.75 | 1.8
P001 | Services | SUP008 | 2025-06 | 2025-01-07 | 891006.42 | 641018 | -249988.42 | 249988.42 | 1 | 2025-06-28 | 2 | 1220933.41 | -329926.99 | DOWN | 0.3703 | 172 | Low | 131565.52 | 0.156 | 2 | 509452.48 | 18 | 1.75 | 1.8
P001 | Services | SUP008 | 2025-06 | 2025-01-09 | 756453.79 | 641018 | -115435.79 | 115435.79 | 1 | 2025-06-28 | 3 | 891006.42 | -134552.63 | DOWN | 0.1779 | 170 | Low | 121328.04 | 0.163 | 2 | 519689.96 | 18 | 1.75 | 1.8
P001 | Services | SUP008 | 2025-06 | 2025-02-24 | 699556.99 | 641018 | -58538.99 | 58538.99 | 0 | 2025-06-28 | 4 | 756453.79 | -56896.8 | DOWN | 0.0813 | 124 | Low | 217292.06 | 0.312 | 3 | 423725.94 | 18 | 1.75 | 1.8
P001 | Services | SUP008 | 2025-06 | 2025-05-05 | 672132.16 | 641018 | -31114.16 | 31114.16 | 0 | 2025-06-28 | 5 | 699556.99 | -27424.83 | DOWN | 0.0408 | 54 | Medium | 386839.39 | 0.54 | 4 | 254178.61 | 18 | 1.75 | 1.8
P001 | Services | SUP008 | 2025-06 | 2025-05-10 | 649997.05 | 641018 | -8979.05 | 8979.05 | 0 | 2025-06-28 | 6 | 672132.16 | -22135.11 | DOWN | 0.0341 | 49 | Medium | 367478.44 | 0.556 | 4 | 273539.56 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP008 | 2025-07 | 2025-03-01 | 1023638.97 | 669450 | -354188.97 | 354188.97 | 1 | 2025-07-28 | 1 |  |  |  |  | 149 | Low | 233816.61 | 0.244 | 0 | 435633.39 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP008 | 2025-07 | 2025-03-05 | 822536.72 | 669450 | -153086.72 | 153086.72 | 1 | 2025-07-28 | 2 | 1023638.97 | -201102.25 | DOWN | 0.2445 | 145 | Low | 201273.93 | 0.258 | 4 | 468176.07 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP008 | 2025-07 | 2025-03-14 | 740548.13 | 669450 | -71098.13 | 71098.13 | 0 | 2025-07-28 | 3 | 822536.72 | -81988.59 | DOWN | 0.1107 | 136 | Low | 228883.32 | 0.288 | 0 | 440566.68 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP008 | 2025-07 | 2025-03-18 | 701533.9 | 669450 | -32083.9 | 32083.9 | 0 | 2025-07-28 | 4 | 740548.13 | -39014.23 | DOWN | 0.0556 | 132 | Low | 208890.67 | 0.302 | 1 | 460559.33 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP008 | 2025-07 | 2025-04-20 | 685686.49 | 669450 | -16236.49 | 16236.49 | 0 | 2025-07-28 | 5 | 701533.9 | -15847.41 | DOWN | 0.0231 | 99 | Low | 278113.12 | 0.416 | 3 | 391336.88 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP008 | 2025-07 | 2025-07-05 | 674366.52 | 669450 | -4916.52 | 4916.52 | 0 | 2025-07-28 | 6 | 685686.49 | -11319.97 | DOWN | 0.0168 | 23 | High | 464693.64 | 0.677 | 6 | 204756.36 | 17 | 1.27 | 1.46
P001 | Services | SUP008 | 2025-08 | 2025-03-06 | 3440520.96 | 1971664 | -1468856.96 | 1468856.96 | 1 | 2025-08-28 | 1 |  |  |  |  | 175 | Low | 520931.6 | 0.15 | 2 | 1450732.4 | 21 | 1.54 | 1.03
P001 | Services | SUP008 | 2025-08 | 2025-04-19 | 2653062.96 | 1971664 | -681398.96 | 681398.96 | 1 | 2025-08-28 | 2 | 3440520.96 | -787458 | DOWN | 0.2968 | 131 | Low | 752968.18 | 0.296 | 4 | 1218695.82 | 21 | 1.54 | 1.03
P001 | Services | SUP008 | 2025-08 | 2025-04-26 | 2300395.9 | 1971664 | -328731.9 | 328731.9 | 0 | 2025-08-28 | 3 | 2653062.96 | -352667.06 | DOWN | 0.1533 | 124 | Low | 731236.97 | 0.32 | 2 | 1240427.03 | 21 | 1.54 | 1.03
P001 | Services | SUP008 | 2025-08 | 2025-05-31 | 2115005.31 | 1971664 | -143341.31 | 143341.31 | 0 | 2025-08-28 | 4 | 2300395.9 | -185390.59 | DOWN | 0.0877 | 89 | Low | 931478.67 | 0.436 | 0 | 1040185.33 | 21 | 1.54 | 1.03
P001 | Services | SUP008 | 2025-08 | 2025-08-07 | 2070604.64 | 1971664 | -98940.64 | 98940.64 | 0 | 2025-08-28 | 5 | 2115005.31 | -44400.67 | DOWN | 0.0214 | 21 | Medium | 1312326.63 | 0.663 | 3 | 659337.37 | 21 | 1.54 | 1.03
P001 | Electronics | SUP008 | 2025-09 | 2025-04-27 | 2466271.54 | 1540428 | -925843.54 | 925843.54 | 1 | 2025-09-28 | 1 |  |  |  |  | 154 | Low | 559236.74 | 0.23 | 4 | 981191.26 | 15 | 1.16 | 1.5
P001 | Electronics | SUP008 | 2025-09 | 2025-06-20 | 1965421.99 | 1540428 | -424993.99 | 424993.99 | 1 | 2025-09-28 | 2 | 2466271.54 | -500849.55 | DOWN | 0.2548 | 100 | Low | 801052.7 | 0.417 | 0 | 739375.3 | 15 | 1.16 | 1.5
P001 | Electronics | SUP008 | 2025-09 | 2025-06-29 | 1705375.17 | 1540428 | -164947.17 | 164947.17 | 0 | 2025-09-28 | 3 | 1965421.99 | -260046.82 | DOWN | 0.1525 | 91 | Low | 786239.47 | 0.449 | 2 | 754188.53 | 15 | 1.16 | 1.5
P001 | Electronics | SUP008 | 2025-09 | 2025-08-04 | 1608578.24 | 1540428 | -68150.24 | 68150.24 | 0 | 2025-09-28 | 4 | 1705375.17 | -96796.93 | DOWN | 0.0602 | 55 | Medium | 906029.17 | 0.574 | 5 | 634398.83 | 15 | 1.16 | 1.5
P001 | Electronics | SUP008 | 2025-09 | 2025-09-17 | 1571258.34 | 1540428 | -30830.34 | 30830.34 | 0 | 2025-09-28 | 5 | 1608578.24 | -37319.9 | DOWN | 0.0238 | 11 | High | 1215539.25 | 0.727 | 6 | 324888.75 | 15 | 1.16 | 1.5
P001 | Services | SUP008 | 2025-10 | 2025-06-08 | 1239080.61 | 674692 | -564388.61 | 564388.61 | 1 | 2025-10-28 | 1 |  |  |  |  | 142 | Low | 327342.95 | 0.252 | 0 | 347349.05 | 18 | 1.81 | 1.33
P001 | Services | SUP008 | 2025-10 | 2025-06-23 | 893531.95 | 674692 | -218839.95 | 218839.95 | 1 | 2025-10-28 | 2 | 1239080.61 | -345548.66 | DOWN | 0.3867 | 127 | Low | 280542.05 | 0.301 | 1 | 394149.95 | 18 | 1.81 | 1.33
P001 | Services | SUP008 | 2025-10 | 2025-09-02 | 779583.72 | 674692 | -104891.72 | 104891.72 | 0 | 2025-10-28 | 3 | 893531.95 | -113948.23 | DOWN | 0.1462 | 56 | Low | 387550.82 | 0.53 | 2 | 287141.18 | 18 | 1.81 | 1.33
P001 | Logistics | SUP008 | 2025-11 | 2025-08-07 | 2116675.33 | 1175053 | -941622.33 | 941622.33 | 1 | 2025-11-28 | 1 |  |  |  |  | 113 | Low | 737454.73 | 0.374 | 5 | 437598.27 | 26 | 1.11 | 1.53
P001 | Logistics | SUP008 | 2025-11 | 2025-09-04 | 1624949.04 | 1175053 | -449896.04 | 449896.04 | 1 | 2025-11-28 | 2 | 2116675.33 | -491726.29 | DOWN | 0.3026 | 85 | Low | 741220.92 | 0.472 | 4 | 433832.08 | 26 | 1.11 | 1.53
P001 | Logistics | SUP008 | 2025-11 | 2025-09-25 | 1358729.54 | 1175053 | -183676.54 | 183676.54 | 0 | 2025-11-28 | 3 | 1624949.04 | -266219.5 | DOWN | 0.1959 | 64 | Low | 715526.74 | 0.546 | 4 | 459526.26 | 26 | 1.11 | 1.53
P001 | Logistics | SUP008 | 2025-11 | 2025-10-02 | 1239219.15 | 1175053 | -64166.15 | 64166.15 | 0 | 2025-11-28 | 4 | 1358729.54 | -119510.39 | DOWN | 0.0964 | 57 | Medium | 689993.6 | 0.57 | 3 | 485059.4 | 26 | 1.11 | 1.53
P001 | Materials | SUP008 | 2025-12 | 2025-07-18 | 282644.95 | 146797 | -135847.95 | 135847.95 | 1 | 2025-12-28 | 1 |  |  |  |  | 163 | Low | 58175.95 | 0.192 | 3 | 88621.05 | 17 | 1.45 | 1.29
P001 | Materials | SUP008 | 2025-12 | 2025-07-19 | 206515.59 | 146797 | -59718.59 | 59718.59 | 1 | 2025-12-28 | 2 | 282644.95 | -76129.36 | DOWN | 0.3686 | 162 | Low | 43110.92 | 0.195 | 0 | 103686.08 | 17 | 1.45 | 1.29
P001 | Materials | SUP008 | 2025-12 | 2025-08-25 | 175434.79 | 146797 | -28637.79 | 28637.79 | 1 | 2025-12-28 | 3 | 206515.59 | -31080.8 | DOWN | 0.1772 | 125 | Low | 52653.02 | 0.32 | 1 | 94143.98 | 17 | 1.45 | 1.29
P001 | Materials | SUP008 | 2025-12 | 2025-09-26 | 160084.67 | 146797 | -13287.67 | 13287.67 | 0 | 2025-12-28 | 4 | 175434.79 | -15350.12 | DOWN | 0.0959 | 93 | Low | 69379.68 | 0.427 | 2 | 77417.32 | 17 | 1.45 | 1.29
P001 | Materials | SUP008 | 2025-12 | 2025-11-12 | 152080.21 | 146797 | -5283.21 | 5283.21 | 0 | 2025-12-28 | 5 | 160084.67 | -8004.46 | DOWN | 0.0526 | 46 | Medium | 83632.75 | 0.585 | 3 | 63164.25 | 17 | 1.45 | 1.29
P001 | Materials | SUP008 | 2025-12 | 2025-11-22 | 149151.19 | 146797 | -2354.19 | 2354.19 | 0 | 2025-12-28 | 6 | 152080.21 | -2929.02 | DOWN | 0.0196 | 36 | Medium | 90744.22 | 0.619 | 4 | 56052.78 | 17 | 1.45 | 1.29
P001 | Logistics | SUP036 | 2025-01 | 2024-08-09 | 463250.36 | 230600 | -232650.36 | 232650.36 | 1 | 2025-01-28 | 1 |  |  |  |  | 172 | Low | 46487.65 | 0.107 | 2 | 184112.35 | 19 | 1.97 | 1.9
P001 | Logistics | SUP036 | 2025-01 | 2024-08-14 | 379340.55 | 230600 | -148740.55 | 148740.55 | 1 | 2025-01-28 | 2 | 463250.36 | -83909.81 | DOWN | 0.2212 | 167 | Low | 44992.24 | 0.119 | 0 | 185607.76 | 19 | 1.97 | 1.9
P001 | Logistics | SUP036 | 2025-01 | 2024-08-26 | 326126.04 | 230600 | -95526.04 | 95526.04 | 1 | 2025-01-28 | 3 | 379340.55 | -53214.51 | DOWN | 0.1632 | 155 | Low | 50599.78 | 0.146 | 0 | 180000.22 | 19 | 1.97 | 1.9
P001 | Logistics | SUP036 | 2025-01 | 2024-09-25 | 285759.2 | 230600 | -55159.2 | 55159.2 | 1 | 2025-01-28 | 4 | 326126.04 | -40366.84 | DOWN | 0.1413 | 125 | Low | 57806.21 | 0.213 | 2 | 172793.79 | 19 | 1.97 | 1.9
P001 | Logistics | SUP036 | 2025-01 | 2024-11-16 | 264610.87 | 230600 | -34010.87 | 34010.87 | 0 | 2025-01-28 | 5 | 285759.2 | -21148.33 | DOWN | 0.0799 | 73 | Low | 88853.85 | 0.329 | 0 | 141746.15 | 19 | 1.97 | 1.9
P001 | Services | SUP036 | 2025-02 | 2024-09-10 | 1781895.62 | 829852 | -952043.62 | 952043.62 | 1 | 2025-02-28 | 1 |  |  |  |  | 171 | Low | 199830.64 | 0.112 | 1 | 630021.36 | 18 | 1.81 | 1.54
P001 | Services | SUP036 | 2025-02 | 2024-11-04 | 1398983.26 | 829852 | -569131.26 | 569131.26 | 1 | 2025-02-28 | 2 | 1781895.62 | -382912.36 | DOWN | 0.2737 | 116 | Low | 312427.38 | 0.237 | 1 | 517424.62 | 18 | 1.81 | 1.54
P001 | Services | SUP036 | 2025-02 | 2024-12-19 | 1170222.42 | 829852 | -340370.42 | 340370.42 | 1 | 2025-02-28 | 3 | 1398983.26 | -228760.84 | DOWN | 0.1955 | 71 | Low | 408330.33 | 0.34 | 4 | 421521.67 | 18 | 1.81 | 1.54
P001 | Logistics | SUP036 | 2025-03 | 2024-11-16 | 3506780.91 | 1419259 | -2087521.91 | 2087521.91 | 1 | 2025-03-28 | 1 |  |  |  |  | 132 | Low | 709986.55 | 0.22 | 2 | 709272.45 | 20 | 0.93 | 1.57
P001 | Logistics | SUP036 | 2025-03 | 2024-12-24 | 2702386.66 | 1419259 | -1283127.66 | 1283127.66 | 1 | 2025-03-28 | 2 | 3506780.91 | -804394.25 | DOWN | 0.2977 | 94 | Low | 892707.2 | 0.315 | 0 | 526551.8 | 20 | 0.93 | 1.57
P001 | Logistics | SUP036 | 2025-03 | 2025-01-15 | 2145974.06 | 1419259 | -726715.06 | 726715.06 | 1 | 2025-03-28 | 3 | 2702386.66 | -556412.6 | DOWN | 0.2593 | 72 | Low | 822082.82 | 0.37 | 3 | 597176.18 | 20 | 0.93 | 1.57
P001 | Logistics | SUP036 | 2025-03 | 2025-02-03 | 1894919.72 | 1419259 | -475660.72 | 475660.72 | 1 | 2025-03-28 | 4 | 2145974.06 | -251054.34 | DOWN | 0.1325 | 53 | Low | 757124.82 | 0.417 | 2 | 662134.18 | 20 | 0.93 | 1.57
P001 | Logistics | SUP036 | 2025-03 | 2025-02-21 | 1734896.01 | 1419259 | -315637.01 | 315637.01 | 1 | 2025-03-28 | 5 | 1894919.72 | -160023.71 | DOWN | 0.0922 | 35 | Medium | 767733.8 | 0.463 | 1 | 651525.2 | 20 | 0.93 | 1.57
P001 | Services | SUP036 | 2025-04 | 2024-10-30 | 3006471.74 | 1442549 | -1563922.74 | 1563922.74 | 1 | 2025-04-28 | 1 |  |  |  |  | 180 | Low | 296201.99 | 0.096 | 2 | 1146347.01 | 22 | 2.23 | 1.91
P001 | Services | SUP036 | 2025-04 | 2024-10-31 | 2337346.18 | 1442549 | -894797.18 | 894797.18 | 1 | 2025-04-28 | 2 | 3006471.74 | -669125.56 | DOWN | 0.2863 | 179 | Low | 210863.86 | 0.096 | 0 | 1231685.14 | 22 | 2.23 | 1.91
P001 | Services | SUP036 | 2025-04 | 2024-12-02 | 2045561.6 | 1442549 | -603012.6 | 603012.6 | 1 | 2025-04-28 | 3 | 2337346.18 | -291784.58 | DOWN | 0.1426 | 147 | Low | 301552.5 | 0.159 | 1 | 1140996.5 | 22 | 2.23 | 1.91
P001 | Services | SUP036 | 2025-04 | 2025-01-17 | 1771977.5 | 1442549 | -329428.5 | 329428.5 | 1 | 2025-04-28 | 4 | 2045561.6 | -273584.1 | DOWN | 0.1544 | 101 | Low | 490705.15 | 0.259 | 1 | 951843.85 | 22 | 2.23 | 1.91
P001 | Services | SUP036 | 2025-04 | 2025-04-07 | 1686441.67 | 1442549 | -243892.67 | 243892.67 | 0 | 2025-04-28 | 5 | 1771977.5 | -85535.83 | DOWN | 0.0507 | 21 | Low | 780088.95 | 0.434 | 4 | 662460.05 | 22 | 2.23 | 1.91
P001 | Services | SUP036 | 2025-04 | 2025-04-10 | 1566694.5 | 1442549 | -124145.5 | 124145.5 | 0 | 2025-04-28 | 6 | 1686441.67 | -119747.17 | DOWN | 0.0764 | 18 | Low | 727277.91 | 0.44 | 5 | 715271.09 | 22 | 2.23 | 1.91
P001 | Services | SUP036 | 2025-05 | 2024-12-10 | 6062787.94 | 2468319 | -3594468.94 | 3594468.94 | 1 | 2025-05-28 | 1 |  |  |  |  | 169 | Low | 675543.38 | 0.116 | 0 | 1792775.62 | 21 | 1.86 | 0.96
P001 | Services | SUP036 | 2025-05 | 2024-12-29 | 4465186.75 | 2468319 | -1996867.75 | 1996867.75 | 1 | 2025-05-28 | 2 | 6062787.94 | -1597601.19 | DOWN | 0.3578 | 150 | Low | 686677.86 | 0.159 | 0 | 1781641.14 | 21 | 1.86 | 0.96
P001 | Services | SUP036 | 2025-05 | 2025-02-03 | 3649279.15 | 2468319 | -1180960.15 | 1180960.15 | 1 | 2025-05-28 | 3 | 4465186.75 | -815907.6 | DOWN | 0.2236 | 114 | Low | 882775.55 | 0.24 | 1 | 1585543.45 | 21 | 1.86 | 0.96
P001 | Services | SUP036 | 2025-05 | 2025-03-10 | 3182235.21 | 2468319 | -713916.21 | 713916.21 | 1 | 2025-05-28 | 4 | 3649279.15 | -467043.94 | DOWN | 0.1468 | 79 | Low | 1037872.1 | 0.32 | 2 | 1430446.9 | 21 | 1.86 | 0.96
P001 | Services | SUP036 | 2025-05 | 2025-05-09 | 2962972.74 | 2468319 | -494653.74 | 494653.74 | 1 | 2025-05-28 | 5 | 3182235.21 | -219262.47 | DOWN | 0.074 | 19 | Medium | 1445356.33 | 0.455 | 5 | 1022962.67 | 21 | 1.86 | 0.96
P001 | Services | SUP036 | 2025-06 | 2025-01-24 | 703181.38 | 325043 | -378138.38 | 378138.38 | 1 | 2025-06-28 | 1 |  |  |  |  | 155 | Low | 102390.36 | 0.149 | 0 | 222652.64 | 18 | 1.75 | 1.8
P001 | Services | SUP036 | 2025-06 | 2025-02-16 | 556392.08 | 325043 | -231349.08 | 231349.08 | 1 | 2025-06-28 | 2 | 703181.38 | -146789.3 | DOWN | 0.2638 | 132 | Low | 119452.44 | 0.202 | 3 | 205590.56 | 18 | 1.75 | 1.8
P001 | Services | SUP036 | 2025-06 | 2025-03-06 | 462387.79 | 325043 | -137344.79 | 137344.79 | 1 | 2025-06-28 | 3 | 556392.08 | -94004.29 | DOWN | 0.2033 | 114 | Low | 104974.26 | 0.243 | 0 | 220068.74 | 18 | 1.75 | 1.8
P001 | Services | SUP036 | 2025-06 | 2025-03-09 | 418932.17 | 325043 | -93889.17 | 93889.17 | 1 | 2025-06-28 | 4 | 462387.79 | -43455.62 | DOWN | 0.1037 | 111 | Low | 97723.02 | 0.25 | 1 | 227319.98 | 18 | 1.75 | 1.8
P001 | Services | SUP036 | 2025-07 | 2025-02-15 | 906507.93 | 533519 | -372988.93 | 372988.93 | 1 | 2025-07-28 | 1 |  |  |  |  | 163 | Low | 124381.09 | 0.138 | 1 | 409137.91 | 17 | 1.27 | 1.46
P001 | Services | SUP036 | 2025-07 | 2025-03-15 | 752525.17 | 533519 | -219006.17 | 219006.17 | 1 | 2025-07-28 | 2 | 906507.93 | -153982.76 | DOWN | 0.2046 | 135 | Low | 163502.98 | 0.206 | 1 | 370016.02 | 17 | 1.27 | 1.46
P001 | Services | SUP036 | 2025-07 | 2025-03-16 | 664986.57 | 533519 | -131467.57 | 131467.57 | 1 | 2025-07-28 | 3 | 752525.17 | -87538.6 | DOWN | 0.1316 | 134 | Low | 148807.45 | 0.208 | 2 | 384711.55 | 17 | 1.27 | 1.46
P001 | Services | SUP036 | 2025-07 | 2025-04-15 | 602100.69 | 533519 | -68581.69 | 68581.69 | 0 | 2025-07-28 | 4 | 664986.57 | -62885.88 | DOWN | 0.1044 | 104 | Low | 175894.27 | 0.281 | 1 | 357624.73 | 17 | 1.27 | 1.46
P001 | Services | SUP036 | 2025-07 | 2025-07-02 | 580656.7 | 533519 | -47137.7 | 47137.7 | 0 | 2025-07-28 | 5 | 602100.69 | -21443.99 | DOWN | 0.0369 | 26 | Medium | 260928.05 | 0.47 | 3 | 272590.95 | 17 | 1.27 | 1.46
P001 | Services | SUP036 | 2025-07 | 2025-07-13 | 559670.81 | 533519 | -26151.81 | 26151.81 | 0 | 2025-07-28 | 6 | 580656.7 | -20985.89 | DOWN | 0.0375 | 15 | Medium | 299050.99 | 0.496 | 2 | 234468.01 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP036 | 2025-08 | 2025-04-10 | 781901.43 | 449974 | -331927.43 | 331927.43 | 1 | 2025-08-28 | 1 |  |  |  |  | 140 | Low | 151433.27 | 0.188 | 2 | 298540.73 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP036 | 2025-08 | 2025-05-02 | 646559.73 | 449974 | -196585.73 | 196585.73 | 1 | 2025-08-28 | 2 | 781901.43 | -135341.7 | DOWN | 0.2093 | 118 | Low | 152090.98 | 0.239 | 4 | 297883.02 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP036 | 2025-08 | 2025-05-16 | 561482.5 | 449974 | -111508.5 | 111508.5 | 1 | 2025-08-28 | 3 | 646559.73 | -85077.23 | DOWN | 0.1515 | 104 | Low | 146489.63 | 0.272 | 0 | 303484.37 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP036 | 2025-08 | 2025-05-29 | 511268.85 | 449974 | -61294.85 | 61294.85 | 0 | 2025-08-28 | 4 | 561482.5 | -50213.65 | DOWN | 0.0982 | 91 | Low | 155102.13 | 0.303 | 2 | 294871.87 | 21 | 1.54 | 1.03
P001 | Mechanical | SUP036 | 2025-08 | 2025-06-29 | 485669.85 | 449974 | -35695.85 | 35695.85 | 0 | 2025-08-28 | 5 | 511268.85 | -25599 | DOWN | 0.0527 | 60 | Low | 189021.66 | 0.376 | 0 | 260952.34 | 21 | 1.54 | 1.03
P001 | Materials | SUP036 | 2025-09 | 2025-04-12 | 1092838.28 | 678804 | -414034.28 | 414034.28 | 1 | 2025-09-28 | 1 |  |  |  |  | 169 | Low | 133043.11 | 0.125 | 1 | 545760.89 | 15 | 1.16 | 1.5
P001 | Materials | SUP036 | 2025-09 | 2025-04-13 | 926875.95 | 678804 | -248071.95 | 248071.95 | 1 | 2025-09-28 | 2 | 1092838.28 | -165962.33 | DOWN | 0.1791 | 168 | Low | 123932.75 | 0.128 | 0 | 554871.25 | 15 | 1.16 | 1.5
P001 | Materials | SUP036 | 2025-09 | 2025-07-18 | 836320.94 | 678804 | -157516.94 | 157516.94 | 1 | 2025-09-28 | 3 | 926875.95 | -90555.01 | DOWN | 0.1083 | 72 | Low | 295701.43 | 0.363 | 0 | 383102.57 | 15 | 1.16 | 1.5
P001 | Materials | SUP036 | 2025-09 | 2025-08-06 | 778214.14 | 678804 | -99410.14 | 99410.14 | 0 | 2025-09-28 | 4 | 836320.94 | -58106.8 | DOWN | 0.0747 | 53 | Low | 338194.05 | 0.41 | 1 | 340609.95 | 15 | 1.16 | 1.5
P001 | Logistics | SUP036 | 2025-10 | 2025-06-02 | 1779844.28 | 832663 | -947181.28 | 947181.28 | 1 | 2025-10-28 | 1 |  |  |  |  | 148 | Low | 290230.53 | 0.164 | 3 | 542432.47 | 18 | 1.81 | 1.33
P001 | Logistics | SUP036 | 2025-10 | 2025-06-26 | 1357186.14 | 832663 | -524523.14 | 524523.14 | 1 | 2025-10-28 | 2 | 1779844.28 | -422658.14 | DOWN | 0.3114 | 124 | Low | 304234.43 | 0.219 | 0 | 528428.57 | 18 | 1.81 | 1.33
P001 | Logistics | SUP036 | 2025-10 | 2025-07-12 | 1160455.77 | 832663 | -327792.77 | 327792.77 | 1 | 2025-10-28 | 3 | 1357186.14 | -196730.37 | DOWN | 0.1695 | 108 | Low | 279479.65 | 0.255 | 4 | 553183.35 | 18 | 1.81 | 1.33
P001 | Logistics | SUP036 | 2025-10 | 2025-07-31 | 1047325.36 | 832663 | -214662.36 | 214662.36 | 1 | 2025-10-28 | 4 | 1160455.77 | -113130.41 | DOWN | 0.108 | 89 | Low | 293644.11 | 0.298 | 0 | 539018.89 | 18 | 1.81 | 1.33
P001 | Logistics | SUP036 | 2025-10 | 2025-08-19 | 963261.44 | 832663 | -130598.44 | 130598.44 | 0 | 2025-10-28 | 5 | 1047325.36 | -84063.92 | DOWN | 0.0873 | 70 | Low | 311772.55 | 0.342 | 2 | 520890.45 | 18 | 1.81 | 1.33
P001 | Logistics | SUP036 | 2025-10 | 2025-08-20 | 903123.08 | 832663 | -70460.08 | 70460.08 | 0 | 2025-10-28 | 6 | 963261.44 | -60138.36 | DOWN | 0.0666 | 69 | Low | 305043.89 | 0.344 | 2 | 527619.11 | 18 | 1.81 | 1.33
P001 | Logistics | SUP036 | 2025-11 | 2025-06-30 | 4849474.36 | 2435651 | -2413823.36 | 2413823.36 | 1 | 2025-11-28 | 1 |  |  |  |  | 151 | Low | 885194.08 | 0.17 | 0 | 1550456.92 | 26 | 1.11 | 1.53
P001 | Logistics | SUP036 | 2025-11 | 2025-07-22 | 3867884.72 | 2435651 | -1432233.72 | 1432233.72 | 1 | 2025-11-28 | 2 | 4849474.36 | -981589.64 | DOWN | 0.2538 | 129 | Low | 832414.39 | 0.225 | 1 | 1603236.61 | 26 | 1.11 | 1.53
P001 | Logistics | SUP036 | 2025-11 | 2025-07-23 | 3242876.48 | 2435651 | -807225.48 | 807225.48 | 1 | 2025-11-28 | 3 | 3867884.72 | -625008.24 | DOWN | 0.1927 | 128 | Low | 738373.17 | 0.227 | 2 | 1697277.83 | 26 | 1.11 | 1.53
P001 | Logistics | SUP036 | 2025-11 | 2025-10-02 | 2924672.32 | 2435651 | -489021.32 | 489021.32 | 1 | 2025-11-28 | 4 | 3242876.48 | -318204.16 | DOWN | 0.1088 | 57 | Low | 1157468.97 | 0.402 | 5 | 1278182.03 | 26 | 1.11 | 1.53
P001 | Services | SUP036 | 2025-12 | 2025-07-23 | 4900379.01 | 2446727 | -2453652.01 | 2453652.01 | 1 | 2025-12-28 | 1 |  |  |  |  | 158 | Low | 761104.7 | 0.147 | 2 | 1685622.3 | 17 | 1.45 | 1.29
P001 | Services | SUP036 | 2025-12 | 2025-08-21 | 3897782.83 | 2446727 | -1451055.83 | 1451055.83 | 1 | 2025-12-28 | 2 | 4900379.01 | -1002596.18 | DOWN | 0.2572 | 129 | Low | 783718.46 | 0.216 | 4 | 1663008.54 | 17 | 1.45 | 1.29
P001 | Services | SUP036 | 2025-12 | 2025-09-27 | 3348759.58 | 2446727 | -902032.58 | 902032.58 | 1 | 2025-12-28 | 3 | 3897782.83 | -549023.25 | DOWN | 0.1639 | 92 | Low | 1078546.42 | 0.304 | 0 | 1368180.58 | 17 | 1.45 | 1.29
P001 | Services | SUP036 | 2025-12 | 2025-12-03 | 2952618.49 | 2446727 | -505891.49 | 505891.49 | 1 | 2025-12-28 | 4 | 3348759.58 | -396141.09 | DOWN | 0.1342 | 25 | Low | 1274336.47 | 0.463 | 4 | 1172390.53 | 17 | 1.45 | 1.29
P001 | Electronics | SUP013 | 2025-01 | 2024-08-16 | 1698386.58 | 845046 | -853340.58 | 853340.58 | 1 | 2025-01-28 | 1 |  |  |  |  | 165 | Low | 194974.89 | 0.112 | 1 | 650071.11 | 19 | 1.97 | 1.9
P001 | Electronics | SUP013 | 2025-01 | 2024-09-02 | 1459621.83 | 845046 | -614575.83 | 614575.83 | 1 | 2025-01-28 | 2 | 1698386.58 | -238764.75 | DOWN | 0.1636 | 148 | Low | 201518.65 | 0.147 | 1 | 643527.35 | 19 | 1.97 | 1.9
P001 | Electronics | SUP013 | 2025-01 | 2024-09-15 | 1305094.51 | 845046 | -460048.51 | 460048.51 | 1 | 2025-01-28 | 3 | 1459621.83 | -154527.32 | DOWN | 0.1184 | 135 | Low | 233145.79 | 0.173 | 1 | 611900.21 | 19 | 1.97 | 1.9
P001 | Electronics | SUP013 | 2025-01 | 2024-12-17 | 1197085.01 | 845046 | -352039.01 | 352039.01 | 1 | 2025-01-28 | 4 | 1305094.51 | -108009.5 | DOWN | 0.0902 | 42 | Low | 465135.47 | 0.362 | 3 | 379910.53 | 19 | 1.97 | 1.9
P001 | Electronics | SUP013 | 2025-01 | 2025-01-08 | 1091241.48 | 845046 | -246195.48 | 246195.48 | 1 | 2025-01-28 | 5 | 1197085.01 | -105843.53 | DOWN | 0.097 | 20 | Low | 425245.6 | 0.407 | 5 | 419800.4 | 19 | 1.97 | 1.9
P001 | Services | SUP013 | 2025-02 | 2024-10-15 | 4891708.91 | 1913201 | -2978507.91 | 2978507.91 | 1 | 2025-02-28 | 1 |  |  |  |  | 136 | Low | 869073.86 | 0.174 | 1 | 1044127.14 | 18 | 1.81 | 1.54
P001 | Services | SUP013 | 2025-02 | 2024-11-28 | 4159378.99 | 1913201 | -2246177.99 | 2246177.99 | 1 | 2025-02-28 | 2 | 4891708.91 | -732329.92 | DOWN | 0.1761 | 92 | Low | 1165397.47 | 0.265 | 2 | 747803.53 | 18 | 1.81 | 1.54
P001 | Services | SUP013 | 2025-02 | 2024-12-06 | 3595061.77 | 1913201 | -1681860.77 | 1681860.77 | 1 | 2025-02-28 | 3 | 4159378.99 | -564317.22 | DOWN | 0.157 | 84 | Low | 1010181.18 | 0.282 | 0 | 903019.82 | 18 | 1.81 | 1.54
P001 | Services | SUP013 | 2025-02 | 2025-02-14 | 3139767.79 | 1913201 | -1226566.79 | 1226566.79 | 1 | 2025-02-28 | 4 | 3595061.77 | -455293.98 | DOWN | 0.145 | 14 | Low | 1294388.88 | 0.427 | 3 | 618812.12 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP013 | 2025-03 | 2024-10-08 | 1240528.69 | 756413 | -484115.69 | 484115.69 | 1 | 2025-03-28 | 1 |  |  |  |  | 171 | Low | 135367.36 | 0.111 | 0 | 621045.64 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP013 | 2025-03 | 2024-11-12 | 1119448.55 | 756413 | -363035.55 | 363035.55 | 1 | 2025-03-28 | 2 | 1240528.69 | -121080.14 | DOWN | 0.1082 | 136 | Low | 224735.64 | 0.191 | 0 | 531677.36 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP013 | 2025-03 | 2024-12-14 | 1025082.62 | 756413 | -268669.62 | 268669.62 | 1 | 2025-03-28 | 3 | 1119448.55 | -94365.93 | DOWN | 0.0921 | 104 | Low | 266952.37 | 0.264 | 2 | 489460.63 | 20 | 0.93 | 1.57
P001 | Services | SUP013 | 2025-04 | 2025-01-15 | 4709515.95 | 1834558 | -2874957.95 | 2874957.95 | 1 | 2025-04-28 | 1 |  |  |  |  | 103 | Low | 1097800.46 | 0.232 | 3 | 736757.54 | 22 | 2.23 | 1.91
P001 | Services | SUP013 | 2025-04 | 2025-01-18 | 4044269.85 | 1834558 | -2209711.85 | 2209711.85 | 1 | 2025-04-28 | 2 | 4709515.95 | -665246.1 | DOWN | 0.1645 | 100 | Low | 886076.56 | 0.238 | 0 | 948481.44 | 22 | 2.23 | 1.91
P001 | Services | SUP013 | 2025-04 | 2025-02-12 | 3526910.37 | 1834558 | -1692352.37 | 1692352.37 | 1 | 2025-04-28 | 3 | 4044269.85 | -517359.48 | DOWN | 0.1467 | 75 | Low | 980230.23 | 0.287 | 1 | 854327.77 | 22 | 2.23 | 1.91
P001 | Services | SUP013 | 2025-04 | 2025-03-03 | 3022305.89 | 1834558 | -1187747.89 | 1187747.89 | 1 | 2025-04-28 | 4 | 3526910.37 | -504604.48 | DOWN | 0.167 | 56 | Low | 947673.83 | 0.325 | 2 | 886884.17 | 22 | 2.23 | 1.91
P001 | Materials | SUP013 | 2025-05 | 2024-12-07 | 381431.05 | 163296 | -218135.05 | 218135.05 | 1 | 2025-05-28 | 1 |  |  |  |  | 172 | Low | 38447.5 | 0.099 | 0 | 124848.5 | 21 | 1.86 | 0.96
P001 | Materials | SUP013 | 2025-05 | 2024-12-12 | 336365.59 | 163296 | -173069.59 | 173069.59 | 1 | 2025-05-28 | 2 | 381431.05 | -45065.46 | DOWN | 0.134 | 167 | Low | 37903.63 | 0.109 | 3 | 125392.37 | 21 | 1.86 | 0.96
P001 | Materials | SUP013 | 2025-05 | 2025-01-17 | 290768.21 | 163296 | -127472.21 | 127472.21 | 1 | 2025-05-28 | 3 | 336365.59 | -45597.38 | DOWN | 0.1568 | 131 | Low | 51365.53 | 0.183 | 3 | 111930.47 | 21 | 1.86 | 0.96
P001 | Materials | SUP013 | 2025-05 | 2025-01-24 | 264096.59 | 163296 | -100800.59 | 100800.59 | 1 | 2025-05-28 | 4 | 290768.21 | -26671.62 | DOWN | 0.101 | 124 | Low | 56300.59 | 0.198 | 1 | 106995.41 | 21 | 1.86 | 0.96
P001 | Materials | SUP013 | 2025-05 | 2025-03-25 | 241698.8 | 163296 | -78402.8 | 78402.8 | 1 | 2025-05-28 | 5 | 264096.59 | -22397.79 | DOWN | 0.0927 | 64 | Low | 75782.63 | 0.321 | 3 | 87513.37 | 21 | 1.86 | 0.96
P001 | Materials | SUP013 | 2025-05 | 2025-04-25 | 222046.68 | 163296 | -58750.68 | 58750.68 | 1 | 2025-05-28 | 6 | 241698.8 | -19652.12 | DOWN | 0.0885 | 33 | Low | 89529.69 | 0.385 | 4 | 73766.31 | 21 | 1.86 | 0.96
P001 | Logistics | SUP013 | 2025-06 | 2025-01-14 | 2621099.46 | 1003247 | -1617852.46 | 1617852.46 | 1 | 2025-06-28 | 1 |  |  |  |  | 165 | Low | 312036.98 | 0.115 | 0 | 691210.02 | 18 | 1.75 | 1.8
P001 | Logistics | SUP013 | 2025-06 | 2025-02-27 | 2239590.87 | 1003247 | -1236343.87 | 1236343.87 | 1 | 2025-06-28 | 2 | 2621099.46 | -381508.59 | DOWN | 0.1703 | 121 | Low | 428515.98 | 0.206 | 1 | 574731.02 | 18 | 1.75 | 1.8
P001 | Logistics | SUP013 | 2025-06 | 2025-03-11 | 1991308.05 | 1003247 | -988061.05 | 988061.05 | 1 | 2025-06-28 | 3 | 2239590.87 | -248282.82 | DOWN | 0.1247 | 109 | Low | 474462.52 | 0.231 | 0 | 528784.48 | 18 | 1.75 | 1.8
P001 | Logistics | SUP013 | 2025-06 | 2025-04-29 | 1775754.68 | 1003247 | -772507.68 | 772507.68 | 1 | 2025-06-28 | 4 | 1991308.05 | -215553.37 | DOWN | 0.1214 | 60 | Low | 617834.49 | 0.334 | 1 | 385412.51 | 18 | 1.75 | 1.8
P001 | Logistics | SUP013 | 2025-06 | 2025-05-01 | 1610796.47 | 1003247 | -607549.47 | 607549.47 | 1 | 2025-06-28 | 5 | 1775754.68 | -164958.21 | DOWN | 0.1024 | 58 | Low | 540348.12 | 0.338 | 3 | 462898.88 | 18 | 1.75 | 1.8
P001 | Logistics | SUP013 | 2025-06 | 2025-06-06 | 1463734.41 | 1003247 | -460487.41 | 460487.41 | 1 | 2025-06-28 | 6 | 1610796.47 | -147062.06 | DOWN | 0.1005 | 22 | Low | 587199.42 | 0.413 | 4 | 416047.58 | 18 | 1.75 | 1.8
P001 | Logistics | SUP013 | 2025-07 | 2025-03-23 | 2702441.16 | 1047909 | -1654532.16 | 1654532.16 | 1 | 2025-07-28 | 1 |  |  |  |  | 127 | Low | 587209.65 | 0.205 | 1 | 460699.35 | 17 | 1.27 | 1.46
P001 | Logistics | SUP013 | 2025-07 | 2025-03-29 | 2253362.33 | 1047909 | -1205453.33 | 1205453.33 | 1 | 2025-07-28 | 2 | 2702441.16 | -449078.83 | DOWN | 0.1993 | 121 | Low | 464278.59 | 0.218 | 1 | 583630.41 | 17 | 1.27 | 1.46
P001 | Logistics | SUP013 | 2025-07 | 2025-04-05 | 1907905.04 | 1047909 | -859996.04 | 859996.04 | 1 | 2025-07-28 | 3 | 2253362.33 | -345457.29 | DOWN | 0.1811 | 114 | Low | 441781.73 | 0.233 | 0 | 606127.27 | 17 | 1.27 | 1.46
P001 | Logistics | SUP013 | 2025-07 | 2025-04-17 | 1731318.99 | 1047909 | -683409.99 | 683409.99 | 1 | 2025-07-28 | 4 | 1907905.04 | -176586.05 | DOWN | 0.102 | 102 | Low | 479676 | 0.26 | 2 | 568233 | 17 | 1.27 | 1.46
P001 | Logistics | SUP013 | 2025-07 | 2025-06-03 | 1527406.4 | 1047909 | -479497.4 | 479497.4 | 1 | 2025-07-28 | 5 | 1731318.99 | -203912.59 | DOWN | 0.1335 | 55 | Low | 551511.51 | 0.363 | 5 | 496397.49 | 17 | 1.27 | 1.46
P001 | Logistics | SUP013 | 2025-07 | 2025-06-22 | 1391864.48 | 1047909 | -343955.48 | 343955.48 | 1 | 2025-07-28 | 6 | 1527406.4 | -135541.92 | DOWN | 0.0974 | 36 | Low | 555893.52 | 0.405 | 4 | 492015.48 | 17 | 1.27 | 1.46
P001 | Software | SUP013 | 2025-08 | 2025-03-12 | 3794533.65 | 1739415 | -2055118.65 | 2055118.65 | 1 | 2025-08-28 | 1 |  |  |  |  | 169 | Low | 427921.82 | 0.109 | 0 | 1311493.18 | 21 | 1.54 | 1.03
P001 | Software | SUP013 | 2025-08 | 2025-03-29 | 3299589.75 | 1739415 | -1560174.75 | 1560174.75 | 1 | 2025-08-28 | 2 | 3794533.65 | -494943.9 | DOWN | 0.15 | 152 | Low | 513846.75 | 0.145 | 1 | 1225568.25 | 21 | 1.54 | 1.03
P001 | Software | SUP013 | 2025-08 | 2025-04-05 | 2868157.29 | 1739415 | -1128742.29 | 1128742.29 | 1 | 2025-08-28 | 3 | 3299589.75 | -431432.46 | DOWN | 0.1504 | 145 | Low | 449108.25 | 0.16 | 4 | 1290306.75 | 21 | 1.54 | 1.03
P001 | Software | SUP013 | 2025-08 | 2025-08-05 | 2619783.84 | 1739415 | -880368.84 | 880368.84 | 1 | 2025-08-28 | 4 | 2868157.29 | -248373.45 | DOWN | 0.0948 | 23 | Low | 1189488.18 | 0.42 | 4 | 549926.82 | 21 | 1.54 | 1.03
P001 | Software | SUP013 | 2025-09 | 2025-04-04 | 2207344.53 | 981268 | -1226076.53 | 1226076.53 | 1 | 2025-09-28 | 1 |  |  |  |  | 177 | Low | 200202.44 | 0.098 | 0 | 781065.56 | 15 | 1.16 | 1.5
P001 | Software | SUP013 | 2025-09 | 2025-06-01 | 1930087.31 | 981268 | -948819.31 | 948819.31 | 1 | 2025-09-28 | 2 | 2207344.53 | -277257.22 | DOWN | 0.1437 | 119 | Low | 417537.87 | 0.225 | 2 | 563730.13 | 15 | 1.16 | 1.5
P001 | Software | SUP013 | 2025-09 | 2025-08-26 | 1663352.65 | 981268 | -682084.65 | 682084.65 | 1 | 2025-09-28 | 3 | 1930087.31 | -266734.66 | DOWN | 0.1604 | 33 | Low | 696978.01 | 0.417 | 2 | 284289.99 | 15 | 1.16 | 1.5
P001 | Logistics | SUP013 | 2025-10 | 2025-06-04 | 5573079.06 | 1901586 | -3671493.06 | 3671493.06 | 1 | 2025-10-28 | 1 |  |  |  |  | 146 | Low | 845935.62 | 0.153 | 3 | 1055650.38 | 18 | 1.81 | 1.33
P001 | Logistics | SUP013 | 2025-10 | 2025-06-09 | 4589463.03 | 1901586 | -2687877.03 | 2687877.03 | 1 | 2025-10-28 | 2 | 5573079.06 | -983616.03 | DOWN | 0.2143 | 141 | Low | 700462.61 | 0.164 | 1 | 1201123.39 | 18 | 1.81 | 1.33
P001 | Logistics | SUP013 | 2025-10 | 2025-08-30 | 3811413.38 | 1901586 | -1909827.38 | 1909827.38 | 1 | 2025-10-28 | 3 | 4589463.03 | -778049.65 | DOWN | 0.2041 | 59 | Low | 1180088.22 | 0.333 | 3 | 721497.78 | 18 | 1.81 | 1.33
P001 | Logistics | SUP013 | 2025-10 | 2025-09-06 | 3315369.7 | 1901586 | -1413783.7 | 1413783.7 | 1 | 2025-10-28 | 4 | 3811413.38 | -496043.68 | DOWN | 0.1496 | 52 | Low | 1073350.1 | 0.348 | 0 | 828235.9 | 18 | 1.81 | 1.33
P001 | Logistics | SUP013 | 2025-10 | 2025-10-17 | 2902775.63 | 1901586 | -1001189.63 | 1001189.63 | 1 | 2025-10-28 | 5 | 3315369.7 | -412594.07 | DOWN | 0.1421 | 11 | Low | 1254916.5 | 0.433 | 1 | 646669.5 | 18 | 1.81 | 1.33
P001 | Logistics | SUP013 | 2025-11 | 2025-07-25 | 3028826.83 | 1269521 | -1759305.83 | 1759305.83 | 1 | 2025-11-28 | 1 |  |  |  |  | 126 | Low | 687785.75 | 0.211 | 2 | 581735.25 | 26 | 1.11 | 1.53
P001 | Logistics | SUP013 | 2025-11 | 2025-07-27 | 2569211.1 | 1269521 | -1299690.1 | 1299690.1 | 1 | 2025-11-28 | 2 | 3028826.83 | -459615.73 | DOWN | 0.1789 | 124 | Low | 567690.92 | 0.215 | 0 | 701830.08 | 26 | 1.11 | 1.53
P001 | Logistics | SUP013 | 2025-11 | 2025-09-09 | 2221865.92 | 1269521 | -952344.92 | 952344.92 | 1 | 2025-11-28 | 3 | 2569211.1 | -347345.18 | DOWN | 0.1563 | 80 | Low | 723734.28 | 0.314 | 5 | 545786.72 | 26 | 1.11 | 1.53
P001 | Logistics | SUP013 | 2025-11 | 2025-09-10 | 1946712.92 | 1269521 | -677191.92 | 677191.92 | 1 | 2025-11-28 | 4 | 2221865.92 | -275153 | DOWN | 0.1413 | 79 | Low | 629203.68 | 0.316 | 0 | 640317.32 | 26 | 1.11 | 1.53
P001 | Logistics | SUP013 | 2025-11 | 2025-09-23 | 1751881.84 | 1269521 | -482360.84 | 482360.84 | 1 | 2025-11-28 | 5 | 1946712.92 | -194831.08 | DOWN | 0.1112 | 66 | Low | 620680.46 | 0.345 | 3 | 648840.54 | 26 | 1.11 | 1.53
P001 | Logistics | SUP013 | 2025-11 | 2025-09-29 | 1631925.39 | 1269521 | -362404.39 | 362404.39 | 1 | 2025-11-28 | 6 | 1751881.84 | -119956.45 | DOWN | 0.0735 | 60 | Low | 621671.45 | 0.359 | 2 | 647849.55 | 26 | 1.11 | 1.53
P001 | Services | SUP013 | 2025-12 | 2025-07-01 | 2903515.85 | 1360453 | -1543062.85 | 1543062.85 | 1 | 2025-12-28 | 1 |  |  |  |  | 180 | Low | 294618.64 | 0.095 | 0 | 1065834.36 | 17 | 1.45 | 1.29
P001 | Services | SUP013 | 2025-12 | 2025-07-03 | 2487216.12 | 1360453 | -1126763.12 | 1126763.12 | 1 | 2025-12-28 | 2 | 2903515.85 | -416299.73 | DOWN | 0.1674 | 178 | Low | 230760.89 | 0.095 | 0 | 1129692.11 | 17 | 1.45 | 1.29
P001 | Services | SUP013 | 2025-12 | 2025-07-11 | 2190245.49 | 1360453 | -829792.49 | 829792.49 | 1 | 2025-12-28 | 3 | 2487216.12 | -296970.63 | DOWN | 0.1356 | 170 | Low | 254206.78 | 0.108 | 0 | 1106246.22 | 17 | 1.45 | 1.29
P001 | Electronics | SUP028 | 2025-01 | 2024-08-07 | 3269224.82 | 1693896 | -1575328.82 | 1575328.82 | 1 | 2025-01-28 | 1 |  |  |  |  | 174 | Low | 454984.68 | 0.146 | 2 | 1238911.32 | 19 | 1.97 | 1.9
P001 | Electronics | SUP028 | 2025-01 | 2024-09-06 | 2364567.82 | 1693896 | -670671.82 | 670671.82 | 1 | 2025-01-28 | 2 | 3269224.82 | -904657 | DOWN | 0.3826 | 144 | Low | 571785.91 | 0.241 | 4 | 1122110.09 | 19 | 1.97 | 1.9
P001 | Electronics | SUP028 | 2025-01 | 2024-09-16 | 2042023.48 | 1693896 | -348127.48 | 348127.48 | 1 | 2025-01-28 | 3 | 2364567.82 | -322544.34 | DOWN | 0.158 | 134 | Low | 515884.55 | 0.273 | 5 | 1178011.45 | 19 | 1.97 | 1.9
P001 | Electronics | SUP028 | 2025-01 | 2025-01-14 | 1797819.5 | 1693896 | -103923.5 | 103923.5 | 0 | 2025-01-28 | 4 | 2042023.48 | -244203.98 | DOWN | 0.1358 | 14 | Low | 1086484.44 | 0.654 | 6 | 607411.56 | 19 | 1.97 | 1.9
P001 | Materials | SUP028 | 2025-02 | 2024-09-06 | 3010012.56 | 1624602 | -1385410.56 | 1385410.56 | 1 | 2025-02-28 | 1 |  |  |  |  | 175 | Low | 470853.09 | 0.145 | 0 | 1153748.91 | 18 | 1.81 | 1.54
P001 | Materials | SUP028 | 2025-02 | 2024-10-18 | 2263598.47 | 1624602 | -638996.47 | 638996.47 | 1 | 2025-02-28 | 2 | 3010012.56 | -746414.09 | DOWN | 0.3297 | 133 | Low | 599241.05 | 0.281 | 0 | 1025360.95 | 18 | 1.81 | 1.54
P001 | Materials | SUP028 | 2025-02 | 2024-12-20 | 1939056.46 | 1624602 | -314454.46 | 314454.46 | 1 | 2025-02-28 | 3 | 2263598.47 | -324542.01 | DOWN | 0.1674 | 70 | Low | 973740.46 | 0.485 | 1 | 650861.54 | 18 | 1.81 | 1.54
P001 | Materials | SUP028 | 2025-02 | 2024-12-26 | 1773911.36 | 1624602 | -149309.36 | 149309.36 | 0 | 2025-02-28 | 4 | 1939056.46 | -165145.1 | DOWN | 0.0931 | 64 | Low | 902931.64 | 0.504 | 2 | 721670.36 | 18 | 1.81 | 1.54
P001 | Electronics | SUP028 | 2025-03 | 2024-10-03 | 3268019.86 | 1932690 | -1335329.86 | 1335329.86 | 1 | 2025-03-28 | 1 |  |  |  |  | 176 | Low | 483090.04 | 0.156 | 0 | 1449599.96 | 20 | 0.93 | 1.57
P001 | Electronics | SUP028 | 2025-03 | 2024-12-08 | 2504568.11 | 1932690 | -571878.11 | 571878.11 | 1 | 2025-03-28 | 2 | 3268019.86 | -763451.75 | DOWN | 0.3048 | 110 | Low | 903995.36 | 0.39 | 3 | 1028694.64 | 20 | 0.93 | 1.57
P001 | Electronics | SUP028 | 2025-03 | 2025-01-07 | 2169250.66 | 1932690 | -236560.66 | 236560.66 | 0 | 2025-03-28 | 3 | 2504568.11 | -335317.45 | DOWN | 0.1546 | 80 | Low | 1056994.63 | 0.496 | 3 | 875695.37 | 20 | 0.93 | 1.57
P001 | Electronics | SUP028 | 2025-03 | 2025-01-08 | 2037949.22 | 1932690 | -105259.22 | 105259.22 | 0 | 2025-03-28 | 4 | 2169250.66 | -131301.44 | DOWN | 0.0644 | 79 | Low | 1015840.31 | 0.5 | 7 | 916849.69 | 20 | 0.93 | 1.57
P001 | Services | SUP028 | 2025-04 | 2024-11-20 | 968608.97 | 556635 | -411973.97 | 411973.97 | 1 | 2025-04-28 | 1 |  |  |  |  | 159 | Low | 176560.76 | 0.188 | 0 | 380074.24 | 22 | 2.23 | 1.91
P001 | Services | SUP028 | 2025-04 | 2025-01-09 | 753688.63 | 556635 | -197053.63 | 197053.63 | 1 | 2025-04-28 | 2 | 968608.97 | -214920.34 | DOWN | 0.2852 | 109 | Low | 265632.94 | 0.343 | 4 | 291002.06 | 22 | 2.23 | 1.91
P001 | Services | SUP028 | 2025-04 | 2025-02-11 | 648532.52 | 556635 | -91897.52 | 91897.52 | 0 | 2025-04-28 | 3 | 753688.63 | -105156.11 | DOWN | 0.1621 | 76 | Low | 275836.35 | 0.445 | 1 | 280798.65 | 22 | 2.23 | 1.91
P001 | Services | SUP028 | 2025-04 | 2025-02-19 | 617047.55 | 556635 | -60412.55 | 60412.55 | 0 | 2025-04-28 | 4 | 648532.52 | -31484.97 | DOWN | 0.051 | 68 | Low | 272775.47 | 0.47 | 5 | 283859.53 | 22 | 2.23 | 1.91
P001 | Services | SUP028 | 2025-04 | 2025-03-05 | 586163.1 | 556635 | -29528.1 | 29528.1 | 0 | 2025-04-28 | 5 | 617047.55 | -30884.45 | DOWN | 0.0527 | 54 | Low | 317781.1 | 0.513 | 5 | 238853.9 | 22 | 2.23 | 1.91
P001 | Software | SUP028 | 2025-05 | 2025-02-17 | 3008609.82 | 1709712 | -1298897.82 | 1298897.82 | 1 | 2025-05-28 | 1 |  |  |  |  | 100 | Low | 1136808.7 | 0.386 | 0 | 572903.3 | 21 | 1.86 | 0.96
P001 | Software | SUP028 | 2025-05 | 2025-03-16 | 2350167.58 | 1709712 | -640455.58 | 640455.58 | 1 | 2025-05-28 | 2 | 3008609.82 | -658442.24 | DOWN | 0.2802 | 73 | Low | 1035507.41 | 0.472 | 1 | 674204.59 | 21 | 1.86 | 0.96
P001 | Software | SUP028 | 2025-05 | 2025-05-04 | 1920097.51 | 1709712 | -210385.51 | 210385.51 | 0 | 2025-05-28 | 3 | 2350167.58 | -430070.07 | DOWN | 0.224 | 24 | Low | 1128707.43 | 0.63 | 3 | 581004.57 | 21 | 1.86 | 0.96
P001 | Materials | SUP028 | 2025-06 | 2024-12-30 | 4504120.06 | 2394940 | -2109180.06 | 2109180.06 | 1 | 2025-06-28 | 1 |  |  |  |  | 180 | Low | 598959.59 | 0.143 | 2 | 1795980.41 | 18 | 1.75 | 1.8
P001 | Materials | SUP028 | 2025-06 | 2025-01-27 | 3299688.81 | 2394940 | -904748.81 | 904748.81 | 1 | 2025-06-28 | 2 | 4504120.06 | -1204431.25 | DOWN | 0.365 | 152 | Low | 675579.34 | 0.221 | 0 | 1719360.66 | 18 | 1.75 | 1.8
P001 | Materials | SUP028 | 2025-06 | 2025-03-23 | 2775072.93 | 2394940 | -380132.93 | 380132.93 | 0 | 2025-06-28 | 3 | 3299688.81 | -524615.88 | DOWN | 0.189 | 97 | Low | 1140330.17 | 0.4 | 0 | 1254609.83 | 18 | 1.75 | 1.8
P001 | Materials | SUP028 | 2025-06 | 2025-04-16 | 2559466.03 | 2394940 | -164526.03 | 164526.03 | 0 | 2025-06-28 | 4 | 2775072.93 | -215606.9 | DOWN | 0.0842 | 73 | Low | 1235463.6 | 0.478 | 2 | 1159476.4 | 18 | 1.75 | 1.8
P001 | Materials | SUP028 | 2025-06 | 2025-05-10 | 2441317.73 | 2394940 | -46377.73 | 46377.73 | 0 | 2025-06-28 | 5 | 2559466.03 | -118148.3 | DOWN | 0.0484 | 49 | Medium | 1394263.06 | 0.556 | 2 | 1000676.94 | 18 | 1.75 | 1.8
P001 | Materials | SUP028 | 2025-06 | 2025-05-17 | 2419649.41 | 2394940 | -24709.41 | 24709.41 | 0 | 2025-06-28 | 6 | 2441317.73 | -21668.32 | DOWN | 0.009 | 42 | Medium | 1317293.26 | 0.579 | 0 | 1077646.74 | 18 | 1.75 | 1.8
P001 | Mechanical | SUP028 | 2025-07 | 2025-02-28 | 1891725.95 | 1241769 | -649956.95 | 649956.95 | 1 | 2025-07-28 | 1 |  |  |  |  | 150 | Low | 468622.04 | 0.24 | 2 | 773146.96 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP028 | 2025-07 | 2025-02-28 | 1546138.68 | 1241769 | -304369.68 | 304369.68 | 1 | 2025-07-28 | 2 | 1891725.95 | -345587.27 | DOWN | 0.2235 | 150 | Low | 375791.65 | 0.24 | 3 | 865977.35 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP028 | 2025-07 | 2025-03-14 | 1381113.33 | 1241769 | -139344.33 | 139344.33 | 0 | 2025-07-28 | 3 | 1546138.68 | -165025.35 | DOWN | 0.1195 | 136 | Low | 417727.87 | 0.288 | 0 | 824041.13 | 17 | 1.27 | 1.46
P001 | Mechanical | SUP028 | 2025-07 | 2025-03-19 | 1292165.99 | 1241769 | -50396.99 | 50396.99 | 0 | 2025-07-28 | 4 | 1381113.33 | -88947.34 | DOWN | 0.0688 | 131 | Low | 365185.37 | 0.306 | 3 | 876583.63 | 17 | 1.27 | 1.46
P001 | Logistics | SUP028 | 2025-08 | 2025-03-13 | 421593.77 | 247981 | -173612.77 | 173612.77 | 1 | 2025-08-28 | 1 |  |  |  |  | 168 | Low | 72845.67 | 0.173 | 0 | 175135.33 | 21 | 1.54 | 1.03
P001 | Logistics | SUP028 | 2025-08 | 2025-04-22 | 325044.02 | 247981 | -77063.02 | 77063.02 | 1 | 2025-08-28 | 2 | 421593.77 | -96549.75 | DOWN | 0.297 | 128 | Low | 97077.28 | 0.306 | 3 | 150903.72 | 21 | 1.54 | 1.03
P001 | Logistics | SUP028 | 2025-08 | 2025-05-07 | 278874.25 | 247981 | -30893.25 | 30893.25 | 0 | 2025-08-28 | 3 | 325044.02 | -46169.77 | DOWN | 0.1656 | 113 | Low | 97135.01 | 0.356 | 1 | 150845.99 | 21 | 1.54 | 1.03
P001 | Logistics | SUP028 | 2025-08 | 2025-05-28 | 261041.17 | 247981 | -13060.17 | 13060.17 | 0 | 2025-08-28 | 4 | 278874.25 | -17833.08 | DOWN | 0.0683 | 92 | Low | 102928.36 | 0.426 | 6 | 145052.64 | 21 | 1.54 | 1.03
P001 | Logistics | SUP028 | 2025-08 | 2025-07-20 | 247861.26 | 247981 | 119.74 | 119.74 | 0 | 2025-08-28 | 5 | 261041.17 | -13179.91 | DOWN | 0.0532 | 39 | Medium | 155218.7 | 0.603 | 4 | 92762.3 | 21 | 1.54 | 1.03
P001 | Services | SUP028 | 2025-09 | 2025-04-23 | 508401.46 | 275980 | -232421.46 | 232421.46 | 1 | 2025-09-28 | 1 |  |  |  |  | 158 | Low | 108533.05 | 0.216 | 0 | 167446.95 | 15 | 1.16 | 1.5
P001 | Services | SUP028 | 2025-09 | 2025-05-03 | 373140.06 | 275980 | -97160.06 | 97160.06 | 1 | 2025-09-28 | 2 | 508401.46 | -135261.4 | DOWN | 0.3625 | 148 | Low | 91694.6 | 0.25 | 4 | 184285.4 | 15 | 1.16 | 1.5
P001 | Services | SUP028 | 2025-09 | 2025-07-30 | 322727.71 | 275980 | -46747.71 | 46747.71 | 0 | 2025-09-28 | 3 | 373140.06 | -50412.35 | DOWN | 0.1562 | 60 | Low | 193259.71 | 0.557 | 8 | 82720.29 | 15 | 1.16 | 1.5
P001 | Services | SUP028 | 2025-09 | 2025-08-18 | 295193.34 | 275980 | -19213.34 | 19213.34 | 0 | 2025-09-28 | 4 | 322727.71 | -27534.37 | DOWN | 0.0933 | 41 | Medium | 195254.25 | 0.623 | 5 | 80725.75 | 15 | 1.16 | 1.5
P001 | Electronics | SUP028 | 2025-10 | 2025-05-14 | 2627332.49 | 1496027 | -1131305.49 | 1131305.49 | 1 | 2025-10-28 | 1 |  |  |  |  | 167 | Low | 448006.37 | 0.171 | 4 | 1048020.63 | 18 | 1.81 | 1.33
P001 | Electronics | SUP028 | 2025-10 | 2025-05-19 | 2048241.91 | 1496027 | -552214.91 | 552214.91 | 1 | 2025-10-28 | 2 | 2627332.49 | -579090.58 | DOWN | 0.2827 | 162 | Low | 404372.94 | 0.187 | 2 | 1091654.06 | 18 | 1.81 | 1.33
P001 | Electronics | SUP028 | 2025-10 | 2025-07-04 | 1731850.28 | 1496027 | -235823.28 | 235823.28 | 0 | 2025-10-28 | 3 | 2048241.91 | -316391.63 | DOWN | 0.1827 | 116 | Low | 543802.05 | 0.336 | 2 | 952224.95 | 18 | 1.81 | 1.33
P001 | Electronics | SUP028 | 2025-10 | 2025-08-10 | 1586733.62 | 1496027 | -90706.62 | 90706.62 | 0 | 2025-10-28 | 4 | 1731850.28 | -145116.66 | DOWN | 0.0915 | 79 | Low | 692275.19 | 0.456 | 4 | 803751.81 | 18 | 1.81 | 1.33
P001 | Mechanical | SUP028 | 2025-11 | 2025-06-12 | 602525.61 | 390385 | -212140.61 | 212140.61 | 1 | 2025-11-28 | 1 |  |  |  |  | 169 | Low | 106391.39 | 0.178 | 0 | 283993.61 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP028 | 2025-11 | 2025-06-16 | 488636.91 | 390385 | -98251.91 | 98251.91 | 1 | 2025-11-28 | 2 | 602525.61 | -113888.7 | DOWN | 0.2331 | 165 | Low | 90673.56 | 0.192 | 1 | 299711.44 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP028 | 2025-11 | 2025-07-30 | 435902.41 | 390385 | -45517.41 | 45517.41 | 0 | 2025-11-28 | 3 | 488636.91 | -52734.5 | DOWN | 0.121 | 121 | Low | 149642.92 | 0.346 | 0 | 240742.08 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP028 | 2025-11 | 2025-09-07 | 410690.36 | 390385 | -20305.36 | 20305.36 | 0 | 2025-11-28 | 4 | 435902.41 | -25212.05 | DOWN | 0.0614 | 82 | Low | 199083.11 | 0.483 | 5 | 191301.89 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP028 | 2025-11 | 2025-09-10 | 398332.43 | 390385 | -7947.43 | 7947.43 | 0 | 2025-11-28 | 5 | 410690.36 | -12357.93 | DOWN | 0.031 | 79 | Low | 181816.3 | 0.493 | 2 | 208568.7 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP028 | 2025-11 | 2025-10-02 | 394355.21 | 390385 | -3970.21 | 3970.21 | 0 | 2025-11-28 | 6 | 398332.43 | -3977.22 | DOWN | 0.0101 | 57 | Medium | 238315.06 | 0.57 | 4 | 152069.94 | 26 | 1.11 | 1.53
P001 | Services | SUP028 | 2025-12 | 2025-08-15 | 3201531.18 | 1928982 | -1272549.18 | 1272549.18 | 1 | 2025-12-28 | 1 |  |  |  |  | 135 | Low | 898076.02 | 0.286 | 4 | 1030905.98 | 17 | 1.45 | 1.29
P001 | Services | SUP028 | 2025-12 | 2025-08-29 | 2471902.81 | 1928982 | -542920.81 | 542920.81 | 1 | 2025-12-28 | 2 | 3201531.18 | -729628.37 | DOWN | 0.2952 | 121 | Low | 846147.37 | 0.333 | 0 | 1082834.63 | 17 | 1.45 | 1.29
P001 | Services | SUP028 | 2025-12 | 2025-10-03 | 2165986.67 | 1928982 | -237004.67 | 237004.67 | 0 | 2025-12-28 | 3 | 2471902.81 | -305916.14 | DOWN | 0.1412 | 86 | Low | 1051917.65 | 0.451 | 4 | 877064.35 | 17 | 1.45 | 1.29
P001 | Services | SUP028 | 2025-12 | 2025-10-20 | 2067607.06 | 1928982 | -138625.06 | 138625.06 | 0 | 2025-12-28 | 4 | 2165986.67 | -98379.61 | DOWN | 0.0476 | 69 | Low | 1065920.77 | 0.508 | 0 | 863061.23 | 17 | 1.45 | 1.29
P001 | Logistics | SUP020 | 2025-01 | 2024-08-01 | 4814221.18 | 1946608 | -2867613.18 | 2867613.18 | 1 | 2025-01-28 | 1 |  |  |  |  | 180 | Low | 403473.15 | 0.09 | 1 | 1543134.85 | 19 | 1.97 | 1.9
P001 | Logistics | SUP020 | 2025-01 | 2024-09-29 | 4199520.92 | 1946608 | -2252912.92 | 2252912.92 | 1 | 2025-01-28 | 2 | 4814221.18 | -614700.26 | DOWN | 0.1464 | 121 | Low | 802771.47 | 0.202 | 3 | 1143836.53 | 19 | 1.97 | 1.9
P001 | Logistics | SUP020 | 2025-01 | 2024-10-04 | 3471497.67 | 1946608 | -1524889.67 | 1524889.67 | 1 | 2025-01-28 | 3 | 4199520.92 | -728023.25 | DOWN | 0.2097 | 116 | Low | 697730.88 | 0.212 | 3 | 1248877.12 | 19 | 1.97 | 1.9
P001 | Logistics | SUP020 | 2025-01 | 2024-10-12 | 3054661.29 | 1946608 | -1108053.29 | 1108053.29 | 1 | 2025-01-28 | 4 | 3471497.67 | -416836.38 | DOWN | 0.1365 | 108 | Low | 731573.29 | 0.228 | 2 | 1215034.71 | 19 | 1.97 | 1.9
P001 | Logistics | SUP020 | 2025-01 | 2024-11-09 | 2862835.56 | 1946608 | -916227.56 | 916227.56 | 1 | 2025-01-28 | 5 | 3054661.29 | -191825.73 | DOWN | 0.067 | 80 | Low | 782341.04 | 0.285 | 0 | 1164266.96 | 19 | 1.97 | 1.9
P001 | Logistics | SUP020 | 2025-01 | 2025-01-12 | 2711359.21 | 1946608 | -764751.21 | 764751.21 | 1 | 2025-01-28 | 6 | 2862835.56 | -151476.35 | DOWN | 0.0559 | 16 | Low | 1203588.01 | 0.415 | 0 | 743019.99 | 19 | 1.97 | 1.9
P001 | Software | SUP020 | 2025-02 | 2024-09-04 | 1907677.41 | 807481 | -1100196.41 | 1100196.41 | 1 | 2025-02-28 | 1 |  |  |  |  | 177 | Low | 166047.76 | 0.091 | 0 | 641433.24 | 18 | 1.81 | 1.54
P001 | Software | SUP020 | 2025-02 | 2024-09-21 | 1667573.57 | 807481 | -860092.57 | 860092.57 | 1 | 2025-02-28 | 2 | 1907677.41 | -240103.84 | DOWN | 0.144 | 160 | Low | 223199.67 | 0.124 | 0 | 584281.33 | 18 | 1.81 | 1.54
P001 | Software | SUP020 | 2025-02 | 2024-11-18 | 1453388.85 | 807481 | -645907.85 | 645907.85 | 1 | 2025-02-28 | 3 | 1667573.57 | -214184.72 | DOWN | 0.1474 | 102 | Low | 333166.94 | 0.244 | 0 | 474314.06 | 18 | 1.81 | 1.54
P001 | Software | SUP020 | 2025-02 | 2024-11-22 | 1300094.66 | 807481 | -492613.66 | 492613.66 | 1 | 2025-02-28 | 4 | 1453388.85 | -153294.19 | DOWN | 0.1179 | 98 | Low | 343840.02 | 0.253 | 1 | 463640.98 | 18 | 1.81 | 1.54
P001 | Software | SUP020 | 2025-02 | 2024-12-14 | 1175755.08 | 807481 | -368274.08 | 368274.08 | 1 | 2025-02-28 | 5 | 1300094.66 | -124339.58 | DOWN | 0.1058 | 76 | Low | 351075.6 | 0.298 | 2 | 456405.4 | 18 | 1.81 | 1.54
P001 | Mechanical | SUP020 | 2025-03 | 2024-11-23 | 3141166.8 | 1591933 | -1549233.8 | 1549233.8 | 1 | 2025-03-28 | 1 |  |  |  |  | 125 | Low | 659385.44 | 0.216 | 1 | 932547.56 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP020 | 2025-03 | 2024-12-01 | 2739507.63 | 1591933 | -1147574.63 | 1147574.63 | 1 | 2025-03-28 | 2 | 3141166.8 | -401659.17 | DOWN | 0.1466 | 117 | Low | 626768.32 | 0.234 | 3 | 965164.68 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP020 | 2025-03 | 2024-12-04 | 2439527.58 | 1591933 | -847594.58 | 847594.58 | 1 | 2025-03-28 | 3 | 2739507.63 | -299980.05 | DOWN | 0.123 | 114 | Low | 541573.95 | 0.241 | 0 | 1050359.05 | 20 | 0.93 | 1.57
P001 | Mechanical | SUP020 | 2025-03 | 2025-02-10 | 2218887.67 | 1591933 | -626954.67 | 626954.67 | 1 | 2025-03-28 | 4 | 2439527.58 | -220639.91 | DOWN | 0.0994 | 46 | Low | 849727.12 | 0.395 | 2 | 742205.88 | 20 | 0.93 | 1.57
P001 | Logistics | SUP020 | 2025-04 | 2024-12-14 | 4758849.2 | 1557895 | -3200954.2 | 3200954.2 | 1 | 2025-04-28 | 1 |  |  |  |  | 135 | Low | 787926.83 | 0.168 | 4 | 769968.17 | 22 | 2.23 | 1.91
P001 | Logistics | SUP020 | 2025-04 | 2025-01-03 | 3947001.72 | 1557895 | -2389106.72 | 2389106.72 | 1 | 2025-04-28 | 2 | 4758849.2 | -811847.48 | DOWN | 0.2057 | 115 | Low | 826922.34 | 0.208 | 2 | 730972.66 | 22 | 2.23 | 1.91
P001 | Logistics | SUP020 | 2025-04 | 2025-01-07 | 3277917.3 | 1557895 | -1720022.3 | 1720022.3 | 1 | 2025-04-28 | 3 | 3947001.72 | -669084.42 | DOWN | 0.2041 | 111 | Low | 742584.36 | 0.216 | 0 | 815310.64 | 22 | 2.23 | 1.91
P001 | Logistics | SUP020 | 2025-04 | 2025-02-27 | 2853742.13 | 1557895 | -1295847.13 | 1295847.13 | 1 | 2025-04-28 | 4 | 3277917.3 | -424175.17 | DOWN | 0.1486 | 60 | Low | 916025.13 | 0.317 | 1 | 641869.87 | 22 | 2.23 | 1.91
P001 | Logistics | SUP020 | 2025-04 | 2025-03-11 | 2526260.91 | 1557895 | -968365.91 | 968365.91 | 1 | 2025-04-28 | 5 | 2853742.13 | -327481.22 | DOWN | 0.1296 | 48 | Low | 902272.25 | 0.341 | 3 | 655622.75 | 22 | 2.23 | 1.91
P001 | Logistics | SUP020 | 2025-04 | 2025-04-16 | 2190052.64 | 1557895 | -632157.64 | 632157.64 | 1 | 2025-04-28 | 6 | 2526260.91 | -336208.27 | DOWN | 0.1535 | 12 | Low | 842627.84 | 0.412 | 2 | 715267.16 | 22 | 2.23 | 1.91
P001 | Software | SUP020 | 2025-05 | 2025-01-07 | 1703195.94 | 604557 | -1098638.94 | 1098638.94 | 1 | 2025-05-28 | 1 |  |  |  |  | 141 | Low | 281947.3 | 0.163 | 2 | 322609.7 | 21 | 1.86 | 0.96
P001 | Software | SUP020 | 2025-05 | 2025-02-16 | 1444827.79 | 604557 | -840270.79 | 840270.79 | 1 | 2025-05-28 | 2 | 1703195.94 | -258368.15 | DOWN | 0.1788 | 101 | Low | 349216.44 | 0.245 | 4 | 255340.56 | 21 | 1.86 | 0.96
P001 | Software | SUP020 | 2025-05 | 2025-04-04 | 1275751.11 | 604557 | -671194.11 | 671194.11 | 1 | 2025-05-28 | 3 | 1444827.79 | -169076.68 | DOWN | 0.1325 | 54 | Low | 439257.65 | 0.342 | 4 | 165299.35 | 21 | 1.86 | 0.96
P001 | Software | SUP020 | 2025-05 | 2025-04-08 | 1135376.35 | 604557 | -530819.35 | 530819.35 | 1 | 2025-05-28 | 4 | 1275751.11 | -140374.76 | DOWN | 0.1236 | 50 | Low | 377898.18 | 0.35 | 2 | 226658.82 | 21 | 1.86 | 0.96
P001 | Software | SUP020 | 2025-05 | 2025-05-12 | 1021758.1 | 604557 | -417201.1 | 417201.1 | 1 | 2025-05-28 | 5 | 1135376.35 | -113618.25 | DOWN | 0.1112 | 16 | Low | 426899.51 | 0.42 | 1 | 177657.49 | 21 | 1.86 | 0.96
P001 | Electronics | SUP020 | 2025-06 | 2025-01-28 | 542120.23 | 261764 | -280356.23 | 280356.23 | 1 | 2025-06-28 | 1 |  |  |  |  | 151 | Low | 73754.6 | 0.144 | 0 | 188009.4 | 18 | 1.75 | 1.8
P001 | Electronics | SUP020 | 2025-06 | 2025-03-28 | 476648.9 | 261764 | -214884.9 | 214884.9 | 1 | 2025-06-28 | 2 | 542120.23 | -65471.33 | DOWN | 0.1374 | 92 | Low | 125437.58 | 0.267 | 4 | 136326.42 | 18 | 1.75 | 1.8
P001 | Electronics | SUP020 | 2025-06 | 2025-06-11 | 415521.78 | 261764 | -153757.78 | 153757.78 | 1 | 2025-06-28 | 3 | 476648.9 | -61127.12 | DOWN | 0.1471 | 17 | Low | 185083.46 | 0.423 | 3 | 76680.54 | 18 | 1.75 | 1.8
P001 | Electronics | SUP020 | 2025-06 | 2025-06-13 | 376752.93 | 261764 | -114988.93 | 114988.93 | 1 | 2025-06-28 | 4 | 415521.78 | -38768.85 | DOWN | 0.1029 | 15 | Low | 158143.63 | 0.427 | 4 | 103620.37 | 18 | 1.75 | 1.8
P001 | Electronics | SUP020 | 2025-06 | 2025-06-15 | 343207.69 | 261764 | -81443.69 | 81443.69 | 1 | 2025-06-28 | 5 | 376752.93 | -33545.24 | DOWN | 0.0977 | 13 | Low | 150151.28 | 0.432 | 4 | 111612.72 | 18 | 1.75 | 1.8
P001 | Services | SUP020 | 2025-07 | 2025-03-09 | 2936299.9 | 1379623 | -1556676.9 | 1556676.9 | 1 | 2025-07-28 | 1 |  |  |  |  | 141 | Low | 504968.78 | 0.174 | 0 | 874654.22 | 17 | 1.27 | 1.46
P001 | Services | SUP020 | 2025-07 | 2025-07-08 | 2529450.24 | 1379623 | -1149827.24 | 1149827.24 | 1 | 2025-07-28 | 2 | 2936299.9 | -406849.66 | DOWN | 0.1608 | 20 | Low | 1160423.62 | 0.44 | 0 | 219199.38 | 17 | 1.27 | 1.46
P001 | Services | SUP020 | 2025-07 | 2025-07-12 | 2234116.74 | 1379623 | -854493.74 | 854493.74 | 1 | 2025-07-28 | 3 | 2529450.24 | -295333.5 | DOWN | 0.1322 | 16 | Low | 940143.28 | 0.449 | 2 | 439479.72 | 17 | 1.27 | 1.46
P001 | Electronics | SUP020 | 2025-08 | 2025-03-06 | 4809698.41 | 2145420 | -2664278.41 | 2664278.41 | 1 | 2025-08-28 | 1 |  |  |  |  | 175 | Low | 450444.34 | 0.096 | 2 | 1694975.66 | 21 | 1.54 | 1.03
P001 | Electronics | SUP020 | 2025-08 | 2025-05-18 | 4082127.77 | 2145420 | -1936707.77 | 1936707.77 | 1 | 2025-08-28 | 2 | 4809698.41 | -727570.64 | DOWN | 0.1782 | 102 | Low | 981395.19 | 0.252 | 0 | 1164024.81 | 21 | 1.54 | 1.03
P001 | Electronics | SUP020 | 2025-08 | 2025-05-22 | 3608429.05 | 2145420 | -1463009.05 | 1463009.05 | 1 | 2025-08-28 | 3 | 4082127.77 | -473698.72 | DOWN | 0.1313 | 98 | Low | 876078.64 | 0.26 | 0 | 1269341.36 | 21 | 1.54 | 1.03
P001 | Electronics | SUP020 | 2025-08 | 2025-06-20 | 3278053.49 | 2145420 | -1132633.49 | 1132633.49 | 1 | 2025-08-28 | 4 | 3608429.05 | -330375.56 | DOWN | 0.1008 | 69 | Low | 1038034.68 | 0.322 | 1 | 1107385.32 | 21 | 1.54 | 1.03
P001 | Electronics | SUP020 | 2025-08 | 2025-07-18 | 3012714.69 | 2145420 | -867294.69 | 867294.69 | 1 | 2025-08-28 | 5 | 3278053.49 | -265338.8 | DOWN | 0.0881 | 41 | Low | 1226001.04 | 0.382 | 3 | 919418.96 | 21 | 1.54 | 1.03
P001 | Logistics | SUP020 | 2025-09 | 2025-04-09 | 483877.52 | 189979 | -293898.52 | 293898.52 | 1 | 2025-09-28 | 1 |  |  |  |  | 172 | Low | 55139.46 | 0.107 | 7 | 134839.54 | 15 | 1.16 | 1.5
P001 | Logistics | SUP020 | 2025-09 | 2025-04-28 | 416181.52 | 189979 | -226202.52 | 226202.52 | 1 | 2025-09-28 | 2 | 483877.52 | -67696 | DOWN | 0.1627 | 153 | Low | 64532.14 | 0.149 | 6 | 125446.86 | 15 | 1.16 | 1.5
P001 | Logistics | SUP020 | 2025-09 | 2025-07-18 | 367295.14 | 189979 | -177316.14 | 177316.14 | 1 | 2025-09-28 | 3 | 416181.52 | -48886.38 | DOWN | 0.1331 | 72 | Low | 112512.4 | 0.33 | 0 | 77466.6 | 15 | 1.16 | 1.5
P001 | Logistics | SUP020 | 2025-09 | 2025-08-02 | 323048.38 | 189979 | -133069.38 | 133069.38 | 1 | 2025-09-28 | 4 | 367295.14 | -44246.76 | DOWN | 0.137 | 57 | Low | 112986.97 | 0.363 | 2 | 76992.03 | 15 | 1.16 | 1.5
P001 | Materials | SUP020 | 2025-10 | 2025-07-02 | 858473.49 | 408055 | -450418.49 | 450418.49 | 1 | 2025-10-28 | 1 |  |  |  |  | 118 | Low | 185343.4 | 0.211 | 6 | 222711.6 | 18 | 1.81 | 1.33
P001 | Materials | SUP020 | 2025-10 | 2025-09-23 | 752472.5 | 408055 | -344417.5 | 344417.5 | 1 | 2025-10-28 | 2 | 858473.49 | -106000.99 | DOWN | 0.1409 | 35 | Low | 279178.3 | 0.383 | 2 | 128876.7 | 18 | 1.81 | 1.33
P001 | Materials | SUP020 | 2025-10 | 2025-10-12 | 670742.42 | 408055 | -262687.42 | 262687.42 | 1 | 2025-10-28 | 3 | 752472.5 | -81730.08 | DOWN | 0.1219 | 16 | Low | 277293.17 | 0.423 | 3 | 130761.83 | 18 | 1.81 | 1.33
P001 | Services | SUP020 | 2025-11 | 2025-06-23 | 4224536.56 | 2010422 | -2214114.56 | 2214114.56 | 1 | 2025-11-28 | 1 |  |  |  |  | 158 | Low | 611979.83 | 0.139 | 2 | 1398442.17 | 26 | 1.11 | 1.53
P001 | Services | SUP020 | 2025-11 | 2025-07-13 | 3641339.95 | 2010422 | -1630917.95 | 1630917.95 | 1 | 2025-11-28 | 2 | 4224536.56 | -583196.61 | DOWN | 0.1602 | 138 | Low | 695882.34 | 0.184 | 3 | 1314539.66 | 26 | 1.11 | 1.53
P001 | Services | SUP020 | 2025-11 | 2025-07-22 | 3233312.16 | 2010422 | -1222890.16 | 1222890.16 | 1 | 2025-11-28 | 3 | 3641339.95 | -408027.79 | DOWN | 0.1262 | 129 | Low | 622290.29 | 0.204 | 0 | 1388131.71 | 26 | 1.11 | 1.53
P001 | Services | SUP020 | 2025-11 | 2025-09-30 | 2954147.33 | 2010422 | -943725.33 | 943725.33 | 1 | 2025-11-28 | 4 | 3233312.16 | -279164.83 | DOWN | 0.0945 | 59 | Low | 1096698.87 | 0.361 | 0 | 913723.13 | 26 | 1.11 | 1.53
P001 | Services | SUP020 | 2025-11 | 2025-10-05 | 2686851.74 | 2010422 | -676429.74 | 676429.74 | 1 | 2025-11-28 | 5 | 2954147.33 | -267295.59 | DOWN | 0.0995 | 54 | Low | 932871.49 | 0.372 | 4 | 1077550.51 | 26 | 1.11 | 1.53
P001 | Software | SUP020 | 2025-12 | 2025-08-25 | 5600895.02 | 2305242 | -3295653.02 | 3295653.02 | 1 | 2025-12-28 | 1 |  |  |  |  | 125 | Low | 1101421.85 | 0.205 | 0 | 1203820.15 | 17 | 1.45 | 1.29
P001 | Software | SUP020 | 2025-12 | 2025-09-20 | 4793056.48 | 2305242 | -2487814.48 | 2487814.48 | 1 | 2025-12-28 | 2 | 5600895.02 | -807838.54 | DOWN | 0.1685 | 99 | Low | 1299167.18 | 0.261 | 0 | 1006074.82 | 17 | 1.45 | 1.29
P001 | Software | SUP020 | 2025-12 | 2025-09-20 | 4145974.24 | 2305242 | -1840732.24 | 1840732.24 | 1 | 2025-12-28 | 3 | 4793056.48 | -647082.24 | DOWN | 0.1561 | 99 | Low | 1024880 | 0.261 | 0 | 1280362 | 17 | 1.45 | 1.29
P001 | Software | SUP020 | 2025-12 | 2025-10-30 | 3724026.56 | 2305242 | -1418784.56 | 1418784.56 | 1 | 2025-12-28 | 4 | 4145974.24 | -421947.68 | DOWN | 0.1133 | 59 | Low | 1247137.7 | 0.347 | 4 | 1058104.3 | 17 | 1.45 | 1.29
P001 | Software | SUP020 | 2025-12 | 2025-11-27 | 3312673.89 | 2305242 | -1007431.89 | 1007431.89 | 1 | 2025-12-28 | 5 | 3724026.56 | -411352.67 | DOWN | 0.1242 | 31 | Low | 1386275.23 | 0.408 | 2 | 918966.77 | 17 | 1.45 | 1.29
P001 | Software | SUP020 | 2025-12 | 2025-12-10 | 3010308.88 | 2305242 | -705066.88 | 705066.88 | 1 | 2025-12-28 | 6 | 3312673.89 | -302365.01 | DOWN | 0.1004 | 18 | Low | 1283651.68 | 0.436 | 3 | 1021590.32 | 17 | 1.45 | 1.29
P001 | Services | SUP010 | 2025-01 | 2024-08-08 | 2930864.17 | 1267547 | -1663317.17 | 1663317.17 | 1 | 2025-01-28 | 1 |  |  |  |  | 173 | Low | 389368.72 | 0.124 | 0 | 878178.28 | 19 | 1.97 | 1.9
P001 | Services | SUP010 | 2025-01 | 2024-12-02 | 2142552.23 | 1267547 | -875005.23 | 875005.23 | 1 | 2025-01-28 | 2 | 2930864.17 | -788311.94 | DOWN | 0.3679 | 57 | Low | 953853.88 | 0.431 | 3 | 313693.12 | 19 | 1.97 | 1.9
P001 | Services | SUP010 | 2025-01 | 2024-12-27 | 1693610.82 | 1267547 | -426063.82 | 426063.82 | 1 | 2025-01-28 | 3 | 2142552.23 | -448941.41 | DOWN | 0.2651 | 32 | Low | 879659.49 | 0.498 | 5 | 387887.51 | 19 | 1.97 | 1.9
P001 | Services | SUP010 | 2025-01 | 2025-01-16 | 1488049.15 | 1267547 | -220502.15 | 220502.15 | 0 | 2025-01-28 | 4 | 1693610.82 | -205561.67 | DOWN | 0.1381 | 12 | Low | 759393.8 | 0.55 | 4 | 508153.2 | 19 | 1.97 | 1.9
P001 | Logistics | SUP010 | 2025-02 | 2024-09-26 | 850684.68 | 336100 | -514584.68 | 514584.68 | 1 | 2025-02-28 | 1 |  |  |  |  | 155 | Low | 152751.54 | 0.175 | 1 | 183348.46 | 18 | 1.81 | 1.54
P001 | Logistics | SUP010 | 2025-02 | 2024-09-29 | 614945.37 | 336100 | -278845.37 | 278845.37 | 1 | 2025-02-28 | 2 | 850684.68 | -235739.31 | DOWN | 0.3834 | 152 | Low | 115288.75 | 0.183 | 1 | 220811.25 | 18 | 1.81 | 1.54
P001 | Logistics | SUP010 | 2025-02 | 2025-01-16 | 495914.65 | 336100 | -159814.65 | 159814.65 | 1 | 2025-02-28 | 3 | 614945.37 | -119030.72 | DOWN | 0.24 | 43 | Low | 225034.97 | 0.477 | 2 | 111065.03 | 18 | 1.81 | 1.54
P001 | Software | SUP010 | 2025-03 | 2024-10-10 | 3855445.5 | 1524734 | -2330711.5 | 2330711.5 | 1 | 2025-03-28 | 1 |  |  |  |  | 169 | Low | 575681.14 | 0.151 | 2 | 949052.86 | 20 | 0.93 | 1.57
P001 | Software | SUP010 | 2025-03 | 2024-10-31 | 2800014.41 | 1524734 | -1275280.41 | 1275280.41 | 1 | 2025-03-28 | 2 | 3855445.5 | -1055431.09 | DOWN | 0.3769 | 148 | Low | 601602.72 | 0.213 | 2 | 923131.28 | 20 | 0.93 | 1.57
P001 | Software | SUP010 | 2025-03 | 2024-12-06 | 2252138.98 | 1524734 | -727404.98 | 727404.98 | 1 | 2025-03-28 | 3 | 2800014.41 | -547875.43 | DOWN | 0.2433 | 112 | Low | 682084.29 | 0.319 | 0 | 842649.71 | 20 | 0.93 | 1.57
P001 | Software | SUP010 | 2025-03 | 2025-02-08 | 1935617.81 | 1524734 | -410883.81 | 410883.81 | 1 | 2025-03-28 | 4 | 2252138.98 | -316521.17 | DOWN | 0.1635 | 48 | Low | 1054683.89 | 0.508 | 2 | 470050.11 | 20 | 0.93 | 1.57
P001 | Software | SUP010 | 2025-03 | 2025-03-18 | 1772647.86 | 1524734 | -247913.86 | 247913.86 | 0 | 2025-03-28 | 5 | 1935617.81 | -162969.95 | DOWN | 0.0919 | 10 | Medium | 1087710.13 | 0.617 | 3 | 437023.87 | 20 | 0.93 | 1.57
P001 | Software | SUP010 | 2025-03 | 2025-03-18 | 1632668.57 | 1524734 | -107934.57 | 107934.57 | 0 | 2025-03-28 | 6 | 1772647.86 | -139979.29 | DOWN | 0.0857 | 10 | Medium | 1053995.03 | 0.617 | 7 | 470738.97 | 20 | 0.93 | 1.57
P001 | Electronics | SUP010 | 2025-04 | 2025-01-17 | 4191887.66 | 1780335 | -2411552.66 | 2411552.66 | 1 | 2025-04-28 | 1 |  |  |  |  | 101 | Low | 1383387.59 | 0.306 | 2 | 396947.41 | 22 | 2.23 | 1.91
P001 | Electronics | SUP010 | 2025-04 | 2025-02-20 | 3019723.84 | 1780335 | -1239388.84 | 1239388.84 | 1 | 2025-04-28 | 2 | 4191887.66 | -1172163.82 | DOWN | 0.3882 | 67 | Low | 1172593.66 | 0.394 | 4 | 607741.34 | 22 | 2.23 | 1.91
P001 | Electronics | SUP010 | 2025-04 | 2025-03-03 | 2539492.46 | 1780335 | -759157.46 | 759157.46 | 1 | 2025-04-28 | 3 | 3019723.84 | -480231.38 | DOWN | 0.1891 | 56 | Low | 1052353.21 | 0.422 | 4 | 727981.79 | 22 | 2.23 | 1.91
P001 | Electronics | SUP010 | 2025-04 | 2025-03-30 | 2195544.21 | 1780335 | -415209.21 | 415209.21 | 1 | 2025-04-28 | 4 | 2539492.46 | -343948.25 | DOWN | 0.1567 | 29 | Low | 1083856 | 0.492 | 2 | 696479 | 22 | 2.23 | 1.91
P001 | Services | SUP010 | 2025-05 | 2024-12-06 | 404300.65 | 179534 | -224766.65 | 224766.65 | 1 | 2025-05-28 | 1 |  |  |  |  | 173 | Low | 51421.22 | 0.126 | 0 | 128112.78 | 21 | 1.86 | 0.96
P001 | Services | SUP010 | 2025-05 | 2024-12-18 | 303979.14 | 179534 | -124445.14 | 124445.14 | 1 | 2025-05-28 | 2 | 404300.65 | -100321.51 | DOWN | 0.33 | 161 | Low | 51834.04 | 0.158 | 0 | 127699.96 | 21 | 1.86 | 0.96
P001 | Services | SUP010 | 2025-05 | 2025-01-15 | 242191.49 | 179534 | -62657.49 | 62657.49 | 1 | 2025-05-28 | 3 | 303979.14 | -61787.65 | DOWN | 0.2551 | 133 | Low | 60833.65 | 0.233 | 2 | 118700.35 | 21 | 1.86 | 0.96
P001 | Services | SUP010 | 2025-05 | 2025-01-16 | 213069.29 | 179534 | -33535.29 | 33535.29 | 1 | 2025-05-28 | 4 | 242191.49 | -29122.2 | DOWN | 0.1367 | 132 | Low | 47778.03 | 0.236 | 0 | 131755.97 | 21 | 1.86 | 0.96
P001 | Services | SUP010 | 2025-05 | 2025-02-25 | 199341.9 | 179534 | -19807.9 | 19807.9 | 0 | 2025-05-28 | 5 | 213069.29 | -13727.39 | DOWN | 0.0689 | 92 | Low | 66243.87 | 0.343 | 1 | 113290.13 | 21 | 1.86 | 0.96
P001 | Services | SUP010 | 2025-05 | 2025-04-12 | 188334.22 | 179534 | -8800.22 | 8800.22 | 0 | 2025-05-28 | 6 | 199341.9 | -11007.68 | DOWN | 0.0584 | 46 | Medium | 87231.05 | 0.466 | 4 | 92302.95 | 21 | 1.86 | 0.96
P001 | Materials | SUP010 | 2025-06 | 2025-01-11 | 870440.87 | 485902 | -384538.87 | 384538.87 | 1 | 2025-06-28 | 1 |  |  |  |  | 168 | Low | 126835.5 | 0.141 | 2 | 359066.5 | 18 | 1.75 | 1.8
P001 | Materials | SUP010 | 2025-06 | 2025-01-12 | 689718.24 | 485902 | -203816.24 | 203816.24 | 1 | 2025-06-28 | 2 | 870440.87 | -180722.63 | DOWN | 0.262 | 167 | Low | 103720.8 | 0.144 | 0 | 382181.2 | 18 | 1.75 | 1.8
P001 | Materials | SUP010 | 2025-06 | 2025-04-30 | 601866.39 | 485902 | -115964.39 | 115964.39 | 1 | 2025-06-28 | 3 | 689718.24 | -87851.85 | DOWN | 0.146 | 59 | Low | 277854.98 | 0.436 | 5 | 208047.02 | 18 | 1.75 | 1.8
P001 | Materials | SUP010 | 2025-06 | 2025-05-30 | 552889.6 | 485902 | -66987.6 | 66987.6 | 0 | 2025-06-28 | 4 | 601866.39 | -48976.79 | DOWN | 0.0886 | 29 | Medium | 299212.41 | 0.518 | 3 | 186689.59 | 18 | 1.75 | 1.8
P001 | Electronics | SUP010 | 2025-07 | 2025-03-15 | 883827.54 | 437594 | -446233.54 | 446233.54 | 1 | 2025-07-28 | 1 |  |  |  |  | 135 | Low | 223111.8 | 0.243 | 0 | 214482.2 | 17 | 1.27 | 1.46
P001 | Electronics | SUP010 | 2025-07 | 2025-04-14 | 685053.74 | 437594 | -247459.74 | 247459.74 | 1 | 2025-07-28 | 2 | 883827.54 | -198773.8 | DOWN | 0.2902 | 105 | Low | 212078.55 | 0.329 | 4 | 225515.45 | 17 | 1.27 | 1.46
P001 | Electronics | SUP010 | 2025-07 | 2025-04-14 | 567333.38 | 437594 | -129739.38 | 129739.38 | 1 | 2025-07-28 | 3 | 685053.74 | -117720.36 | DOWN | 0.2075 | 105 | Low | 185709.39 | 0.329 | 0 | 251884.61 | 17 | 1.27 | 1.46
P001 | Electronics | SUP010 | 2025-07 | 2025-04-20 | 505402.49 | 437594 | -67808.49 | 67808.49 | 0 | 2025-07-28 | 4 | 567333.38 | -61930.89 | DOWN | 0.1225 | 99 | Low | 169225.89 | 0.346 | 5 | 268368.11 | 17 | 1.27 | 1.46
P001 | Electronics | SUP010 | 2025-07 | 2025-07-09 | 471150.72 | 437594 | -33556.72 | 33556.72 | 0 | 2025-07-28 | 5 | 505402.49 | -34251.77 | DOWN | 0.0727 | 19 | Medium | 259959.08 | 0.575 | 6 | 177634.92 | 17 | 1.27 | 1.46
P001 | Services | SUP010 | 2025-08 | 2025-03-19 | 904598.63 | 447521 | -457077.63 | 457077.63 | 1 | 2025-08-28 | 1 |  |  |  |  | 162 | Low | 154404.62 | 0.161 | 0 | 293116.38 | 21 | 1.54 | 1.03
P001 | Services | SUP010 | 2025-08 | 2025-06-06 | 702214.26 | 447521 | -254693.26 | 254693.26 | 1 | 2025-08-28 | 2 | 904598.63 | -202384.37 | DOWN | 0.2882 | 83 | Low | 275573.86 | 0.38 | 4 | 171947.14 | 21 | 1.54 | 1.03
P001 | Services | SUP010 | 2025-08 | 2025-06-19 | 600664.77 | 447521 | -153143.77 | 153143.77 | 1 | 2025-08-28 | 3 | 702214.26 | -101549.49 | DOWN | 0.1691 | 70 | Low | 263918.93 | 0.416 | 5 | 183602.07 | 21 | 1.54 | 1.03
P001 | Services | SUP010 | 2025-08 | 2025-07-06 | 533836.9 | 447521 | -86315.9 | 86315.9 | 1 | 2025-08-28 | 4 | 600664.77 | -66827.87 | DOWN | 0.1252 | 53 | Low | 261141.93 | 0.463 | 3 | 186379.07 | 21 | 1.54 | 1.03
P001 | Services | SUP010 | 2025-08 | 2025-08-11 | 497317.04 | 447521 | -49796.04 | 49796.04 | 0 | 2025-08-28 | 5 | 533836.9 | -36519.86 | DOWN | 0.0734 | 17 | Medium | 296490.56 | 0.563 | 4 | 151030.44 | 21 | 1.54 | 1.03
P001 | Electronics | SUP010 | 2025-09 | 2025-04-27 | 3000897.19 | 1515497 | -1485400.19 | 1485400.19 | 1 | 2025-09-28 | 1 |  |  |  |  | 154 | Low | 605267.26 | 0.191 | 2 | 910229.74 | 15 | 1.16 | 1.5
P001 | Electronics | SUP010 | 2025-09 | 2025-05-22 | 2361555.62 | 1515497 | -846058.62 | 846058.62 | 1 | 2025-09-28 | 2 | 3000897.19 | -639341.57 | DOWN | 0.2707 | 129 | Low | 607063.73 | 0.264 | 0 | 908433.27 | 15 | 1.16 | 1.5
P001 | Electronics | SUP010 | 2025-09 | 2025-08-11 | 2003285.52 | 1515497 | -487788.52 | 487788.52 | 1 | 2025-09-28 | 3 | 2361555.62 | -358270.1 | DOWN | 0.1788 | 48 | Low | 1075793.64 | 0.499 | 2 | 439703.36 | 15 | 1.16 | 1.5
P001 | Electronics | SUP010 | 2025-09 | 2025-08-29 | 1782484.67 | 1515497 | -266987.67 | 266987.67 | 0 | 2025-09-28 | 4 | 2003285.52 | -220800.85 | DOWN | 0.1239 | 30 | Low | 955708.36 | 0.551 | 7 | 559788.64 | 15 | 1.16 | 1.5
P001 | Electronics | SUP010 | 2025-09 | 2025-09-03 | 1680828.69 | 1515497 | -165331.69 | 165331.69 | 0 | 2025-09-28 | 5 | 1782484.67 | -101655.98 | DOWN | 0.0605 | 25 | Medium | 964926.98 | 0.565 | 4 | 550570.02 | 15 | 1.16 | 1.5
P001 | Electronics | SUP010 | 2025-09 | 2025-09-13 | 1621475.73 | 1515497 | -105978.73 | 105978.73 | 0 | 2025-09-28 | 6 | 1680828.69 | -59352.96 | DOWN | 0.0366 | 15 | Medium | 1021524.44 | 0.594 | 6 | 493972.56 | 15 | 1.16 | 1.5
P001 | Software | SUP010 | 2025-10 | 2025-05-24 | 4827754.98 | 1826608 | -3001146.98 | 3001146.98 | 1 | 2025-10-28 | 1 |  |  |  |  | 157 | Low | 768355.71 | 0.17 | 0 | 1058252.29 | 18 | 1.81 | 1.33
P001 | Software | SUP010 | 2025-10 | 2025-06-06 | 3502002.42 | 1826608 | -1675394.42 | 1675394.42 | 1 | 2025-10-28 | 2 | 4827754.98 | -1325752.56 | DOWN | 0.3786 | 144 | Low | 761078.55 | 0.205 | 1 | 1065529.45 | 18 | 1.81 | 1.33
P001 | Software | SUP010 | 2025-10 | 2025-07-16 | 2780337.13 | 1826608 | -953729.13 | 953729.13 | 1 | 2025-10-28 | 3 | 3502002.42 | -721665.29 | DOWN | 0.2596 | 104 | Low | 887245.92 | 0.312 | 4 | 939362.08 | 18 | 1.81 | 1.33
P001 | Software | SUP010 | 2025-10 | 2025-07-31 | 2418876.59 | 1826608 | -592268.59 | 592268.59 | 1 | 2025-10-28 | 4 | 2780337.13 | -361460.54 | DOWN | 0.1494 | 89 | Low | 906804.36 | 0.353 | 0 | 919803.64 | 18 | 1.81 | 1.33
P001 | Materials | SUP010 | 2025-11 | 2025-06-09 | 3379325.01 | 1828763 | -1550562.01 | 1550562.01 | 1 | 2025-11-28 | 1 |  |  |  |  | 172 | Low | 504113.64 | 0.14 | 0 | 1324649.36 | 26 | 1.11 | 1.53
P001 | Materials | SUP010 | 2025-11 | 2025-06-15 | 2690690.67 | 1828763 | -861927.67 | 861927.67 | 1 | 2025-11-28 | 2 | 3379325.01 | -688634.34 | DOWN | 0.2559 | 166 | Low | 435311.36 | 0.157 | 0 | 1393451.64 | 26 | 1.11 | 1.53
P001 | Materials | SUP010 | 2025-11 | 2025-08-19 | 2315554.82 | 1828763 | -486791.82 | 486791.82 | 1 | 2025-11-28 | 3 | 2690690.67 | -375135.85 | DOWN | 0.162 | 101 | Low | 774457.93 | 0.347 | 4 | 1054305.07 | 26 | 1.11 | 1.53
P001 | Materials | SUP010 | 2025-11 | 2025-08-23 | 2087604.68 | 1828763 | -258841.68 | 258841.68 | 0 | 2025-11-28 | 4 | 2315554.82 | -227950.14 | DOWN | 0.1092 | 97 | Low | 744029.33 | 0.359 | 4 | 1084733.67 | 26 | 1.11 | 1.53
P001 | Materials | SUP010 | 2025-11 | 2025-10-26 | 1987719.28 | 1828763 | -158956.28 | 158956.28 | 0 | 2025-11-28 | 5 | 2087604.68 | -99885.4 | DOWN | 0.0503 | 33 | Medium | 1046717.5 | 0.545 | 3 | 782045.5 | 26 | 1.11 | 1.53
P001 | Materials | SUP010 | 2025-11 | 2025-11-13 | 1934808.46 | 1828763 | -106045.46 | 106045.46 | 0 | 2025-11-28 | 6 | 1987719.28 | -52910.82 | DOWN | 0.0273 | 15 | Medium | 1125926.4 | 0.598 | 4 | 702836.6 | 26 | 1.11 | 1.53
P001 | Mechanical | SUP010 | 2025-12 | 2025-08-20 | 3458379.78 | 1897677 | -1560702.78 | 1560702.78 | 1 | 2025-12-28 | 1 |  |  |  |  | 130 | Low | 898039.34 | 0.252 | 3 | 999637.66 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP010 | 2025-12 | 2025-10-31 | 2763777.22 | 1897677 | -866100.22 | 866100.22 | 1 | 2025-12-28 | 2 | 3458379.78 | -694602.56 | DOWN | 0.2513 | 58 | Low | 1285305.31 | 0.454 | 4 | 612371.69 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP010 | 2025-12 | 2025-11-17 | 2392999.4 | 1897677 | -495322.4 | 495322.4 | 1 | 2025-12-28 | 3 | 2763777.22 | -370777.82 | DOWN | 0.1549 | 41 | Low | 1131478.64 | 0.502 | 2 | 766198.36 | 17 | 1.45 | 1.29
P001 | Mechanical | SUP010 | 2025-12 | 2025-11-19 | 2170637.5 | 1897677 | -272960.5 | 272960.5 | 0 | 2025-12-28 | 4 | 2392999.4 | -222361.9 | DOWN | 0.1024 | 39 | Medium | 1107784.32 | 0.507 | 5 | 789892.68 | 17 | 1.45 | 1.29
P002 | Services | SUP027 | 2025-01 | 2024-08-27 | 648520.65 | 331609 | -316911.65 | 316911.65 | 1 | 2025-01-28 | 1 |  |  |  |  | 154 | Low | 126481.73 | 0.185 | 0 | 205127.27 | 20 | 1.45 | 1.35
P002 | Services | SUP027 | 2025-01 | 2024-09-12 | 506697.75 | 331609 | -175088.75 | 175088.75 | 1 | 2025-01-28 | 2 | 648520.65 | -141822.9 | DOWN | 0.2799 | 138 | Low | 108172.06 | 0.23 | 2 | 223436.94 | 20 | 1.45 | 1.35
P002 | Services | SUP027 | 2025-01 | 2024-10-13 | 425350.19 | 331609 | -93741.19 | 93741.19 | 1 | 2025-01-28 | 3 | 506697.75 | -81347.56 | DOWN | 0.1912 | 107 | Low | 126579.93 | 0.317 | 4 | 205029.07 | 20 | 1.45 | 1.35
P002 | Services | SUP027 | 2025-01 | 2024-11-25 | 378860.15 | 331609 | -47251.15 | 47251.15 | 0 | 2025-01-28 | 4 | 425350.19 | -46490.04 | DOWN | 0.1227 | 64 | Low | 172127.77 | 0.437 | 0 | 159481.23 | 20 | 1.45 | 1.35
P002 | Services | SUP027 | 2025-01 | 2024-12-21 | 358609.03 | 331609 | -27000.03 | 27000.03 | 0 | 2025-01-28 | 5 | 378860.15 | -20251.12 | DOWN | 0.0565 | 38 | Medium | 194170.13 | 0.51 | 4 | 137438.87 | 20 | 1.45 | 1.35
P002 | Services | SUP027 | 2025-01 | 2025-01-14 | 353000.84 | 331609 | -21391.84 | 21391.84 | 0 | 2025-01-28 | 6 | 358609.03 | -5608.19 | DOWN | 0.0159 | 14 | Medium | 203594.62 | 0.577 | 0 | 128014.38 | 20 | 1.45 | 1.35
P002 | Electronics | SUP027 | 2025-02 | 2024-09-17 | 1389575.57 | 657357 | -732218.57 | 732218.57 | 1 | 2025-02-28 | 1 |  |  |  |  | 164 | Low | 228155.96 | 0.158 | 0 | 429201.04 | 23 | 1.4 | 1.5
P002 | Electronics | SUP027 | 2025-02 | 2024-09-25 | 1063155.65 | 657357 | -405798.65 | 405798.65 | 1 | 2025-02-28 | 2 | 1389575.57 | -326419.92 | DOWN | 0.307 | 156 | Low | 186068.47 | 0.18 | 2 | 471288.53 | 23 | 1.4 | 1.5
P002 | Electronics | SUP027 | 2025-02 | 2024-10-01 | 893547.9 | 657357 | -236190.9 | 236190.9 | 1 | 2025-02-28 | 3 | 1063155.65 | -169607.75 | DOWN | 0.1898 | 150 | Low | 184577.24 | 0.197 | 4 | 472779.76 | 23 | 1.4 | 1.5
P002 | Electronics | SUP027 | 2025-02 | 2024-12-31 | 790416.29 | 657357 | -133059.29 | 133059.29 | 1 | 2025-02-28 | 4 | 893547.9 | -103131.61 | DOWN | 0.1305 | 59 | Low | 338621.2 | 0.454 | 0 | 318735.8 | 23 | 1.4 | 1.5
P002 | Electronics | SUP027 | 2025-03 | 2024-10-04 | 970148.02 | 427154 | -542994.02 | 542994.02 | 1 | 2025-03-28 | 1 |  |  |  |  | 175 | Low | 105645.37 | 0.115 | 2 | 321508.63 | 25 | 2.28 | 1.97
P002 | Electronics | SUP027 | 2025-03 | 2024-11-09 | 744807.77 | 427154 | -317653.77 | 317653.77 | 1 | 2025-03-28 | 2 | 970148.02 | -225340.25 | DOWN | 0.3025 | 139 | Low | 161333.19 | 0.207 | 1 | 265820.81 | 25 | 2.28 | 1.97
P002 | Electronics | SUP027 | 2025-03 | 2025-01-10 | 603361.69 | 427154 | -176207.69 | 176207.69 | 1 | 2025-03-28 | 3 | 744807.77 | -141446.08 | DOWN | 0.2344 | 77 | Low | 234472.61 | 0.366 | 1 | 192681.39 | 25 | 2.28 | 1.97
P002 | Electronics | SUP027 | 2025-03 | 2025-02-07 | 516868.22 | 427154 | -89714.22 | 89714.22 | 1 | 2025-03-28 | 4 | 603361.69 | -86493.47 | DOWN | 0.1673 | 49 | Low | 224681.72 | 0.438 | 5 | 202472.28 | 25 | 2.28 | 1.97
P002 | Electronics | SUP027 | 2025-03 | 2025-02-10 | 481375.93 | 427154 | -54221.93 | 54221.93 | 0 | 2025-03-28 | 5 | 516868.22 | -35492.29 | DOWN | 0.0737 | 46 | Low | 218595.8 | 0.446 | 2 | 208558.2 | 25 | 2.28 | 1.97
P002 | Electronics | SUP027 | 2025-03 | 2025-02-23 | 458254.22 | 427154 | -31100.22 | 31100.22 | 0 | 2025-03-28 | 6 | 481375.93 | -23121.71 | DOWN | 0.0505 | 33 | Low | 215453.95 | 0.479 | 3 | 211700.05 | 25 | 2.28 | 1.97
P002 | Materials | SUP027 | 2025-04 | 2024-11-16 | 997303.13 | 567507 | -429796.13 | 429796.13 | 1 | 2025-04-28 | 1 |  |  |  |  | 163 | Low | 162458.49 | 0.167 | 1 | 405048.51 | 21 | 1.06 | 1.67
P002 | Materials | SUP027 | 2025-04 | 2024-11-19 | 796807.2 | 567507 | -229300.2 | 229300.2 | 1 | 2025-04-28 | 2 | 997303.13 | -200495.93 | DOWN | 0.2516 | 160 | Low | 146494.06 | 0.176 | 3 | 421012.94 | 21 | 1.06 | 1.67
P002 | Materials | SUP027 | 2025-04 | 2024-12-23 | 690211.7 | 567507 | -122704.7 | 122704.7 | 1 | 2025-04-28 | 3 | 796807.2 | -106595.5 | DOWN | 0.1544 | 126 | Low | 187686.33 | 0.276 | 2 | 379820.67 | 21 | 1.06 | 1.67
P002 | Materials | SUP027 | 2025-04 | 2024-12-26 | 629639.11 | 567507 | -62132.11 | 62132.11 | 0 | 2025-04-28 | 4 | 690211.7 | -60572.59 | DOWN | 0.0962 | 123 | Low | 187356.6 | 0.285 | 4 | 380150.4 | 21 | 1.06 | 1.67
P002 | Materials | SUP027 | 2025-04 | 2025-01-11 | 602133.51 | 567507 | -34626.51 | 34626.51 | 0 | 2025-04-28 | 5 | 629639.11 | -27505.6 | DOWN | 0.0457 | 107 | Low | 186434.95 | 0.331 | 2 | 381072.05 | 21 | 1.06 | 1.67
P002 | Materials | SUP027 | 2025-04 | 2025-01-27 | 585029.87 | 567507 | -17522.87 | 17522.87 | 0 | 2025-04-28 | 6 | 602133.51 | -17103.64 | DOWN | 0.0292 | 91 | Low | 236640.85 | 0.378 | 4 | 330866.15 | 21 | 1.06 | 1.67
P002 | Software | SUP027 | 2025-05 | 2025-02-11 | 2910593.38 | 1251024 | -1659569.38 | 1659569.38 | 1 | 2025-05-28 | 1 |  |  |  |  | 106 | Low | 827105.19 | 0.298 | 0 | 423918.81 | 28 | 2.1 | 0.99
P002 | Software | SUP027 | 2025-05 | 2025-02-25 | 2185391.65 | 1251024 | -934367.65 | 934367.65 | 1 | 2025-05-28 | 2 | 2910593.38 | -725201.73 | DOWN | 0.3318 | 92 | Low | 740541.79 | 0.334 | 3 | 510482.21 | 28 | 2.1 | 0.99
P002 | Software | SUP027 | 2025-05 | 2025-05-02 | 1817947.51 | 1251024 | -566923.51 | 566923.51 | 1 | 2025-05-28 | 3 | 2185391.65 | -367444.14 | DOWN | 0.2021 | 26 | Low | 914850.75 | 0.506 | 2 | 336173.25 | 28 | 2.1 | 0.99
P002 | Logistics | SUP027 | 2025-06 | 2025-02-12 | 2446580.55 | 947915 | -1498665.55 | 1498665.55 | 1 | 2025-06-28 | 1 |  |  |  |  | 136 | Low | 597200.34 | 0.24 | 1 | 350714.66 | 17 | 1.27 | 1.62
P002 | Logistics | SUP027 | 2025-06 | 2025-03-03 | 1727868.21 | 947915 | -779953.21 | 779953.21 | 1 | 2025-06-28 | 2 | 2446580.55 | -718712.34 | DOWN | 0.416 | 117 | Low | 519969.43 | 0.295 | 0 | 427945.57 | 17 | 1.27 | 1.62
P002 | Logistics | SUP027 | 2025-06 | 2025-03-26 | 1379927.3 | 947915 | -432012.3 | 432012.3 | 1 | 2025-06-28 | 3 | 1727868.21 | -347940.91 | DOWN | 0.2521 | 94 | Low | 473593.65 | 0.361 | 4 | 474321.35 | 17 | 1.27 | 1.62
P002 | Logistics | SUP027 | 2025-06 | 2025-03-28 | 1202150.44 | 947915 | -254235.44 | 254235.44 | 1 | 2025-06-28 | 4 | 1379927.3 | -177776.86 | DOWN | 0.1479 | 92 | Low | 466372.21 | 0.366 | 4 | 481542.79 | 17 | 1.27 | 1.62
P002 | Logistics | SUP027 | 2025-06 | 2025-05-18 | 1104031.35 | 947915 | -156116.35 | 156116.35 | 0 | 2025-06-28 | 5 | 1202150.44 | -98119.09 | DOWN | 0.0889 | 41 | Medium | 578893.31 | 0.512 | 5 | 369021.69 | 17 | 1.27 | 1.62
P002 | Materials | SUP027 | 2025-07 | 2025-03-26 | 3311607.16 | 1570159 | -1741448.16 | 1741448.16 | 1 | 2025-07-28 | 1 |  |  |  |  | 124 | Low | 936506.66 | 0.268 | 2 | 633652.34 | 24 | 1.49 | 1.96
P002 | Materials | SUP027 | 2025-07 | 2025-04-28 | 2501869.96 | 1570159 | -931710.96 | 931710.96 | 1 | 2025-07-28 | 2 | 3311607.16 | -809737.2 | DOWN | 0.3237 | 91 | Low | 874873.49 | 0.36 | 5 | 695285.51 | 24 | 1.49 | 1.96
P002 | Materials | SUP027 | 2025-07 | 2025-06-19 | 2082410.89 | 1570159 | -512251.89 | 512251.89 | 1 | 2025-07-28 | 3 | 2501869.96 | -419459.07 | DOWN | 0.2014 | 39 | Low | 1108894.05 | 0.505 | 4 | 461264.95 | 24 | 1.49 | 1.96
P002 | Materials | SUP027 | 2025-07 | 2025-06-26 | 1836769.95 | 1570159 | -266610.95 | 266610.95 | 0 | 2025-07-28 | 4 | 2082410.89 | -245640.94 | DOWN | 0.1337 | 32 | Low | 917444.96 | 0.525 | 3 | 652714.04 | 24 | 1.49 | 1.96
P002 | Materials | SUP027 | 2025-08 | 2025-03-22 | 2742279.51 | 1490299 | -1251980.51 | 1251980.51 | 1 | 2025-08-28 | 1 |  |  |  |  | 159 | Low | 450829.49 | 0.174 | 0 | 1039469.51 | 25 | 1.29 | 1.82
P002 | Materials | SUP027 | 2025-08 | 2025-03-31 | 2162021.87 | 1490299 | -671722.87 | 671722.87 | 1 | 2025-08-28 | 2 | 2742279.51 | -580257.64 | DOWN | 0.2684 | 150 | Low | 439119.54 | 0.2 | 1 | 1051179.46 | 25 | 1.29 | 1.82
P002 | Materials | SUP027 | 2025-08 | 2025-04-03 | 1853894.3 | 1490299 | -363595.3 | 363595.3 | 1 | 2025-08-28 | 3 | 2162021.87 | -308127.57 | DOWN | 0.1662 | 147 | Low | 373909.28 | 0.208 | 3 | 1116389.72 | 25 | 1.29 | 1.82
P002 | Materials | SUP027 | 2025-08 | 2025-05-17 | 1677333.9 | 1490299 | -187034.9 | 187034.9 | 0 | 2025-08-28 | 4 | 1853894.3 | -176560.4 | DOWN | 0.1053 | 103 | Low | 532763.61 | 0.334 | 1 | 957535.39 | 25 | 1.29 | 1.82
P002 | Materials | SUP027 | 2025-08 | 2025-06-17 | 1589251.28 | 1490299 | -98952.28 | 98952.28 | 0 | 2025-08-28 | 5 | 1677333.9 | -88082.62 | DOWN | 0.0554 | 72 | Low | 632935 | 0.423 | 0 | 857364 | 25 | 1.29 | 1.82
P002 | Materials | SUP027 | 2025-08 | 2025-06-29 | 1562089.64 | 1490299 | -71790.64 | 71790.64 | 0 | 2025-08-28 | 6 | 1589251.28 | -27161.64 | DOWN | 0.0174 | 60 | Medium | 664772.05 | 0.457 | 2 | 825526.95 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP027 | 2025-09 | 2025-04-13 | 2639577.81 | 1590575 | -1049002.81 | 1049002.81 | 1 | 2025-09-28 | 1 |  |  |  |  | 168 | Low | 394326.24 | 0.147 | 0 | 1196248.76 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP027 | 2025-09 | 2025-06-08 | 2178417.22 | 1590575 | -587842.22 | 587842.22 | 1 | 2025-09-28 | 2 | 2639577.81 | -461160.59 | DOWN | 0.2117 | 112 | Low | 654712.4 | 0.305 | 0 | 935862.6 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP027 | 2025-09 | 2025-06-19 | 1900032.23 | 1590575 | -309457.23 | 309457.23 | 1 | 2025-09-28 | 3 | 2178417.22 | -278384.99 | DOWN | 0.1465 | 101 | Low | 615712.07 | 0.336 | 1 | 974862.93 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP027 | 2025-09 | 2025-07-28 | 1760979.48 | 1590575 | -170404.48 | 170404.48 | 0 | 2025-09-28 | 4 | 1900032.23 | -139052.75 | DOWN | 0.079 | 62 | Low | 815015.58 | 0.446 | 0 | 775559.42 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP027 | 2025-09 | 2025-08-05 | 1694745.34 | 1590575 | -104170.34 | 104170.34 | 0 | 2025-09-28 | 5 | 1760979.48 | -66234.14 | DOWN | 0.0391 | 54 | Medium | 824793.85 | 0.469 | 7 | 765781.15 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP027 | 2025-09 | 2025-09-16 | 1650514.03 | 1590575 | -59939.03 | 59939.03 | 0 | 2025-09-28 | 6 | 1694745.34 | -44231.31 | DOWN | 0.0268 | 12 | Medium | 1036117.24 | 0.588 | 6 | 554457.76 | 25 | 1.38 | 1.58
P002 | Materials | SUP027 | 2025-10 | 2025-07-06 | 2078044.5 | 1101279 | -976765.5 | 976765.5 | 1 | 2025-10-28 | 1 |  |  |  |  | 114 | Low | 635039.56 | 0.287 | 1 | 466239.44 | 21 | 1.76 | 1.29
P002 | Materials | SUP027 | 2025-10 | 2025-07-21 | 1661120.75 | 1101279 | -559841.75 | 559841.75 | 1 | 2025-10-28 | 2 | 2078044.5 | -416923.75 | DOWN | 0.251 | 99 | Low | 586479.65 | 0.328 | 3 | 514799.35 | 21 | 1.76 | 1.29
P002 | Materials | SUP027 | 2025-10 | 2025-08-21 | 1440394.19 | 1101279 | -339115.19 | 339115.19 | 1 | 2025-10-28 | 3 | 1661120.75 | -220726.56 | DOWN | 0.1532 | 68 | Low | 571105.35 | 0.412 | 1 | 530173.65 | 21 | 1.76 | 1.29
P002 | Services | SUP027 | 2025-11 | 2025-07-08 | 3664261.26 | 1577694 | -2086567.26 | 2086567.26 | 1 | 2025-11-28 | 1 |  |  |  |  | 143 | Low | 805296.74 | 0.212 | 0 | 772397.26 | 26 | 1.59 | 1.38
P002 | Services | SUP027 | 2025-11 | 2025-09-30 | 2721563.33 | 1577694 | -1143869.33 | 1143869.33 | 1 | 2025-11-28 | 2 | 3664261.26 | -942697.93 | DOWN | 0.3464 | 59 | Low | 1247246.26 | 0.444 | 3 | 330447.74 | 26 | 1.59 | 1.38
P002 | Services | SUP027 | 2025-11 | 2025-10-23 | 2221089.78 | 1577694 | -643395.78 | 643395.78 | 1 | 2025-11-28 | 3 | 2721563.33 | -500473.55 | DOWN | 0.2253 | 36 | Low | 1105748.45 | 0.508 | 4 | 471945.55 | 26 | 1.59 | 1.38
P002 | Services | SUP027 | 2025-11 | 2025-10-31 | 1939905.8 | 1577694 | -362211.8 | 362211.8 | 1 | 2025-11-28 | 4 | 2221089.78 | -281183.98 | DOWN | 0.1449 | 28 | Low | 974356.77 | 0.53 | 3 | 603337.23 | 26 | 1.59 | 1.38
P002 | Services | SUP027 | 2025-12 | 2025-08-07 | 4463329.51 | 2105088 | -2358241.51 | 2358241.51 | 1 | 2025-12-28 | 1 |  |  |  |  | 143 | Low | 939730.84 | 0.216 | 0 | 1165357.16 | 27 | 1.43 | 1.4
P002 | Services | SUP027 | 2025-12 | 2025-09-17 | 3415749.9 | 2105088 | -1310661.9 | 1310661.9 | 1 | 2025-12-28 | 2 | 4463329.51 | -1047579.61 | DOWN | 0.3067 | 102 | Low | 1200956.97 | 0.332 | 3 | 904131.03 | 27 | 1.43 | 1.4
P002 | Services | SUP027 | 2025-12 | 2025-09-23 | 2779423.85 | 2105088 | -674335.85 | 674335.85 | 1 | 2025-12-28 | 3 | 3415749.9 | -636326.05 | DOWN | 0.2289 | 96 | Low | 930934.92 | 0.348 | 2 | 1174153.08 | 27 | 1.43 | 1.4
P002 | Services | SUP027 | 2025-12 | 2025-10-04 | 2462707.08 | 2105088 | -357619.08 | 357619.08 | 0 | 2025-12-28 | 4 | 2779423.85 | -316716.77 | DOWN | 0.1286 | 85 | Low | 878791.2 | 0.379 | 3 | 1226296.8 | 27 | 1.43 | 1.4
P002 | Services | SUP027 | 2025-12 | 2025-11-25 | 2311059.88 | 2105088 | -205971.88 | 205971.88 | 0 | 2025-12-28 | 5 | 2462707.08 | -151647.2 | DOWN | 0.0656 | 33 | Medium | 1308998.12 | 0.525 | 4 | 796089.88 | 27 | 1.43 | 1.4
P002 | Services | SUP027 | 2025-12 | 2025-12-02 | 2202478.91 | 2105088 | -97390.91 | 97390.91 | 0 | 2025-12-28 | 6 | 2311059.88 | -108580.97 | DOWN | 0.0493 | 26 | Medium | 1241706.61 | 0.545 | 2 | 863381.39 | 27 | 1.43 | 1.4
P002 | Software | SUP050 | 2025-01 | 2024-09-03 | 2834367.92 | 1322845 | -1511522.92 | 1511522.92 | 1 | 2025-01-28 | 1 |  |  |  |  | 147 | Low | 557051.27 | 0.205 | 1 | 765793.73 | 20 | 1.45 | 1.35
P002 | Software | SUP050 | 2025-01 | 2024-09-06 | 2155061.14 | 1322845 | -832216.14 | 832216.14 | 1 | 2025-01-28 | 2 | 2834367.92 | -679306.78 | DOWN | 0.3152 | 144 | Low | 487136.73 | 0.213 | 1 | 835708.27 | 20 | 1.45 | 1.35
P002 | Software | SUP050 | 2025-01 | 2024-10-24 | 1825840.58 | 1322845 | -502995.58 | 502995.58 | 1 | 2025-01-28 | 3 | 2155061.14 | -329220.56 | DOWN | 0.1803 | 96 | Low | 629186.41 | 0.348 | 1 | 693658.59 | 20 | 1.45 | 1.35
P002 | Software | SUP050 | 2025-01 | 2024-10-27 | 1613903.75 | 1322845 | -291058.75 | 291058.75 | 1 | 2025-01-28 | 4 | 1825840.58 | -211936.83 | DOWN | 0.1313 | 93 | Low | 593927.68 | 0.356 | 3 | 728917.32 | 20 | 1.45 | 1.35
P002 | Software | SUP050 | 2025-01 | 2024-12-13 | 1467839.06 | 1322845 | -144994.06 | 144994.06 | 0 | 2025-01-28 | 5 | 1613903.75 | -146064.69 | DOWN | 0.0995 | 46 | Medium | 666785.22 | 0.488 | 4 | 656059.78 | 20 | 1.45 | 1.35
P002 | Logistics | SUP050 | 2025-02 | 2024-10-11 | 1316458.9 | 615286 | -701172.9 | 701172.9 | 1 | 2025-02-28 | 1 |  |  |  |  | 140 | Low | 287618.85 | 0.226 | 1 | 327667.15 | 23 | 1.4 | 1.5
P002 | Logistics | SUP050 | 2025-02 | 2024-12-02 | 974523.15 | 615286 | -359237.15 | 359237.15 | 1 | 2025-02-28 | 2 | 1316458.9 | -341935.75 | DOWN | 0.3509 | 88 | Low | 387220.44 | 0.372 | 0 | 228065.56 | 23 | 1.4 | 1.5
P002 | Logistics | SUP050 | 2025-02 | 2025-01-28 | 809083.47 | 615286 | -193797.47 | 193797.47 | 1 | 2025-02-28 | 3 | 974523.15 | -165439.68 | DOWN | 0.2045 | 31 | Low | 429316.03 | 0.533 | 6 | 185969.97 | 23 | 1.4 | 1.5
P002 | Software | SUP050 | 2025-03 | 2024-10-31 | 4219548.88 | 1954970 | -2264578.88 | 2264578.88 | 1 | 2025-03-28 | 1 |  |  |  |  | 148 | Low | 829971.46 | 0.184 | 0 | 1124998.54 | 25 | 2.28 | 1.97
P002 | Software | SUP050 | 2025-03 | 2024-12-14 | 3149992.74 | 1954970 | -1195022.74 | 1195022.74 | 1 | 2025-03-28 | 2 | 4219548.88 | -1069556.14 | DOWN | 0.3395 | 104 | Low | 918330.55 | 0.297 | 2 | 1036639.45 | 25 | 2.28 | 1.97
P002 | Software | SUP050 | 2025-03 | 2024-12-24 | 2662668.57 | 1954970 | -707698.57 | 707698.57 | 1 | 2025-03-28 | 3 | 3149992.74 | -487324.17 | DOWN | 0.183 | 94 | Low | 838846.78 | 0.323 | 1 | 1116123.22 | 25 | 2.28 | 1.97
P002 | Software | SUP050 | 2025-03 | 2024-12-29 | 2402722.96 | 1954970 | -447752.96 | 447752.96 | 1 | 2025-03-28 | 4 | 2662668.57 | -259945.61 | DOWN | 0.1082 | 89 | Low | 856209.36 | 0.336 | 3 | 1098760.64 | 25 | 2.28 | 1.97
P002 | Software | SUP050 | 2025-03 | 2025-01-11 | 2177005.64 | 1954970 | -222035.64 | 222035.64 | 0 | 2025-03-28 | 5 | 2402722.96 | -225717.32 | DOWN | 0.1037 | 76 | Low | 787673.94 | 0.369 | 2 | 1167296.06 | 25 | 2.28 | 1.97
P002 | Software | SUP050 | 2025-03 | 2025-02-01 | 2145939.18 | 1954970 | -190969.18 | 190969.18 | 0 | 2025-03-28 | 6 | 2177005.64 | -31066.46 | DOWN | 0.0145 | 55 | Low | 834322.72 | 0.423 | 2 | 1120647.28 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP050 | 2025-04 | 2025-03-23 | 1551816.1 | 921686 | -630130.1 | 630130.1 | 1 | 2025-04-28 | 1 |  |  |  |  | 36 | Medium | 811909.5 | 0.54 | 4 | 109776.5 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP050 | 2025-04 | 2025-03-24 | 1277174.84 | 921686 | -355488.84 | 355488.84 | 1 | 2025-04-28 | 2 | 1551816.1 | -274641.26 | DOWN | 0.215 | 35 | Low | 725904.4 | 0.543 | 6 | 195781.6 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP050 | 2025-04 | 2025-04-10 | 1115865.18 | 921686 | -194179.18 | 194179.18 | 1 | 2025-04-28 | 3 | 1277174.84 | -161309.66 | DOWN | 0.1446 | 18 | Low | 627469.79 | 0.593 | 3 | 294216.21 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP050 | 2025-05 | 2025-01-16 | 4282262.67 | 1995901 | -2286361.67 | 2286361.67 | 1 | 2025-05-28 | 1 |  |  |  |  | 132 | Low | 945124.28 | 0.23 | 0 | 1050776.72 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP050 | 2025-05 | 2025-01-18 | 3204894.01 | 1995901 | -1208993.01 | 1208993.01 | 1 | 2025-05-28 | 2 | 4282262.67 | -1077368.66 | DOWN | 0.3362 | 130 | Low | 801082.05 | 0.235 | 2 | 1194818.95 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP050 | 2025-05 | 2025-01-28 | 2661250.72 | 1995901 | -665349.72 | 665349.72 | 1 | 2025-05-28 | 3 | 3204894.01 | -543643.29 | DOWN | 0.2043 | 120 | Low | 694721.69 | 0.261 | 0 | 1301179.31 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP050 | 2025-05 | 2025-04-23 | 2325841.73 | 1995901 | -329940.73 | 329940.73 | 0 | 2025-05-28 | 4 | 2661250.72 | -335408.99 | DOWN | 0.1442 | 35 | Low | 1091565.97 | 0.483 | 4 | 904335.03 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP050 | 2025-05 | 2025-05-05 | 2157875.11 | 1995901 | -161974.11 | 161974.11 | 0 | 2025-05-28 | 5 | 2325841.73 | -167966.62 | DOWN | 0.0778 | 23 | Low | 1130887.02 | 0.514 | 2 | 865013.98 | 28 | 2.1 | 0.99
P002 | Software | SUP050 | 2025-06 | 2025-03-14 | 4608272.96 | 2022704 | -2585568.96 | 2585568.96 | 1 | 2025-06-28 | 1 |  |  |  |  | 106 | Low | 1437282.92 | 0.326 | 0 | 585421.08 | 17 | 1.27 | 1.62
P002 | Software | SUP050 | 2025-06 | 2025-03-25 | 3378427.85 | 2022704 | -1355723.85 | 1355723.85 | 1 | 2025-06-28 | 2 | 4608272.96 | -1229845.11 | DOWN | 0.364 | 95 | Low | 1254047.15 | 0.358 | 2 | 768656.85 | 17 | 1.27 | 1.62
P002 | Software | SUP050 | 2025-06 | 2025-04-05 | 2792706.45 | 2022704 | -770002.45 | 770002.45 | 1 | 2025-06-28 | 3 | 3378427.85 | -585721.4 | DOWN | 0.2097 | 84 | Low | 1017962.78 | 0.389 | 2 | 1004741.22 | 17 | 1.27 | 1.62
P002 | Software | SUP050 | 2025-06 | 2025-04-30 | 2487916.21 | 2022704 | -465212.21 | 465212.21 | 1 | 2025-06-28 | 4 | 2792706.45 | -304790.24 | DOWN | 0.1225 | 59 | Low | 1134619.21 | 0.461 | 3 | 888084.79 | 17 | 1.27 | 1.62
P002 | Software | SUP050 | 2025-06 | 2025-06-12 | 2247879.66 | 2022704 | -225175.66 | 225175.66 | 0 | 2025-06-28 | 5 | 2487916.21 | -240036.55 | DOWN | 0.1068 | 16 | Medium | 1282241.55 | 0.584 | 2 | 740462.45 | 17 | 1.27 | 1.62
P002 | Software | SUP050 | 2025-06 | 2025-06-16 | 2174508.47 | 2022704 | -151804.47 | 151804.47 | 0 | 2025-06-28 | 6 | 2247879.66 | -73371.19 | DOWN | 0.0337 | 12 | Medium | 1233542.49 | 0.595 | 2 | 789161.51 | 17 | 1.27 | 1.62
P002 | Software | SUP050 | 2025-07 | 2025-02-15 | 663107.71 | 308007 | -355100.71 | 355100.71 | 1 | 2025-07-28 | 1 |  |  |  |  | 163 | Low | 98072.04 | 0.159 | 1 | 209934.96 | 24 | 1.49 | 1.96
P002 | Software | SUP050 | 2025-07 | 2025-02-21 | 511107.97 | 308007 | -203100.97 | 203100.97 | 1 | 2025-07-28 | 2 | 663107.71 | -151999.74 | DOWN | 0.2974 | 157 | Low | 83931.4 | 0.176 | 3 | 224075.6 | 24 | 1.49 | 1.96
P002 | Software | SUP050 | 2025-07 | 2025-02-28 | 414519.16 | 308007 | -106512.16 | 106512.16 | 1 | 2025-07-28 | 3 | 511107.97 | -96588.81 | DOWN | 0.233 | 150 | Low | 77107.72 | 0.195 | 1 | 230899.28 | 24 | 1.49 | 1.96
P002 | Software | SUP050 | 2025-07 | 2025-03-20 | 364150.08 | 308007 | -56143.08 | 56143.08 | 1 | 2025-07-28 | 4 | 414519.16 | -50369.08 | DOWN | 0.1383 | 130 | Low | 87044.81 | 0.251 | 0 | 220962.19 | 24 | 1.49 | 1.96
P002 | Software | SUP050 | 2025-07 | 2025-03-23 | 337278.28 | 308007 | -29271.28 | 29271.28 | 0 | 2025-07-28 | 5 | 364150.08 | -26871.8 | DOWN | 0.0797 | 127 | Low | 90534.35 | 0.26 | 5 | 217472.65 | 24 | 1.49 | 1.96
P002 | Software | SUP050 | 2025-08 | 2025-05-27 | 4617921.29 | 1983348 | -2634573.29 | 2634573.29 | 1 | 2025-08-28 | 1 |  |  |  |  | 93 | Low | 1617699.25 | 0.363 | 1 | 365648.75 | 25 | 1.29 | 1.82
P002 | Software | SUP050 | 2025-08 | 2025-06-10 | 3385066.54 | 1983348 | -1401718.54 | 1401718.54 | 1 | 2025-08-28 | 2 | 4617921.29 | -1232854.75 | DOWN | 0.3642 | 79 | Low | 1271666.32 | 0.403 | 6 | 711681.68 | 25 | 1.29 | 1.82
P002 | Software | SUP050 | 2025-08 | 2025-06-23 | 2767412.73 | 1983348 | -784064.73 | 784064.73 | 1 | 2025-08-28 | 3 | 3385066.54 | -617653.81 | DOWN | 0.2232 | 66 | Low | 1133899.16 | 0.44 | 4 | 849448.84 | 25 | 1.29 | 1.82
P002 | Software | SUP050 | 2025-08 | 2025-08-10 | 2392180.13 | 1983348 | -408832.13 | 408832.13 | 1 | 2025-08-28 | 4 | 2767412.73 | -375232.6 | DOWN | 0.1569 | 18 | Low | 1360783.99 | 0.577 | 4 | 622564.01 | 25 | 1.29 | 1.82
P002 | Software | SUP050 | 2025-09 | 2025-04-04 | 3022923.71 | 1319869 | -1703054.71 | 1703054.71 | 1 | 2025-09-28 | 1 |  |  |  |  | 177 | Low | 380796.43 | 0.124 | 1 | 939072.57 | 25 | 1.38 | 1.58
P002 | Software | SUP050 | 2025-09 | 2025-04-22 | 2301307.23 | 1319869 | -981438.23 | 981438.23 | 1 | 2025-09-28 | 2 | 3022923.71 | -721616.48 | DOWN | 0.3136 | 159 | Low | 428306.37 | 0.172 | 2 | 891562.63 | 25 | 1.38 | 1.58
P002 | Software | SUP050 | 2025-09 | 2025-05-08 | 1817073.45 | 1319869 | -497204.45 | 497204.45 | 1 | 2025-09-28 | 3 | 2301307.23 | -484233.78 | DOWN | 0.2665 | 143 | Low | 375590.92 | 0.218 | 6 | 944278.08 | 25 | 1.38 | 1.58
P002 | Software | SUP050 | 2025-09 | 2025-06-05 | 1586683.27 | 1319869 | -266814.27 | 266814.27 | 1 | 2025-09-28 | 4 | 1817073.45 | -230390.18 | DOWN | 0.1452 | 115 | Low | 445833.41 | 0.297 | 2 | 874035.59 | 25 | 1.38 | 1.58
P002 | Software | SUP050 | 2025-09 | 2025-06-07 | 1473883.86 | 1319869 | -154014.86 | 154014.86 | 0 | 2025-09-28 | 5 | 1586683.27 | -112799.41 | DOWN | 0.0765 | 113 | Low | 472311.71 | 0.302 | 2 | 847557.29 | 25 | 1.38 | 1.58
P002 | Services | SUP050 | 2025-10 | 2025-05-19 | 3039215.7 | 1272220 | -1766995.7 | 1766995.7 | 1 | 2025-10-28 | 1 |  |  |  |  | 162 | Low | 442374.58 | 0.157 | 3 | 829845.42 | 21 | 1.76 | 1.29
P002 | Services | SUP050 | 2025-10 | 2025-08-10 | 2191072.4 | 1272220 | -918852.4 | 918852.4 | 1 | 2025-10-28 | 2 | 3039215.7 | -848143.3 | DOWN | 0.3871 | 79 | Low | 852973.6 | 0.382 | 3 | 419246.4 | 21 | 1.76 | 1.29
P002 | Services | SUP050 | 2025-10 | 2025-10-11 | 1772277.45 | 1272220 | -500057.45 | 500057.45 | 1 | 2025-10-28 | 3 | 2191072.4 | -418794.95 | DOWN | 0.2363 | 17 | Low | 958068.63 | 0.55 | 5 | 314151.37 | 21 | 1.76 | 1.29
P002 | Electronics | SUP050 | 2025-11 | 2025-06-15 | 3435918.29 | 1657205 | -1778713.29 | 1778713.29 | 1 | 2025-11-28 | 1 |  |  |  |  | 166 | Low | 510760.77 | 0.149 | 0 | 1146444.23 | 26 | 1.59 | 1.38
P002 | Electronics | SUP050 | 2025-11 | 2025-06-28 | 2713639.94 | 1657205 | -1056434.94 | 1056434.94 | 1 | 2025-11-28 | 2 | 3435918.29 | -722278.35 | DOWN | 0.2662 | 153 | Low | 521931.79 | 0.185 | 1 | 1135273.21 | 26 | 1.59 | 1.38
P002 | Electronics | SUP050 | 2025-11 | 2025-08-28 | 2217986.37 | 1657205 | -560781.37 | 560781.37 | 1 | 2025-11-28 | 3 | 2713639.94 | -495653.57 | DOWN | 0.2235 | 92 | Low | 749261.07 | 0.353 | 3 | 907943.93 | 26 | 1.59 | 1.38
P002 | Electronics | SUP050 | 2025-11 | 2025-08-31 | 2003353.12 | 1657205 | -346148.12 | 346148.12 | 1 | 2025-11-28 | 4 | 2217986.37 | -214633.25 | DOWN | 0.1071 | 89 | Low | 728562.38 | 0.361 | 2 | 928642.62 | 26 | 1.59 | 1.38
P002 | Software | SUP050 | 2025-12 | 2025-07-22 | 6694155.54 | 2763917 | -3930238.54 | 3930238.54 | 1 | 2025-12-28 | 1 |  |  |  |  | 159 | Low | 1190040.82 | 0.171 | 2 | 1573876.18 | 27 | 1.43 | 1.4
P002 | Software | SUP050 | 2025-12 | 2025-07-22 | 5050978.01 | 2763917 | -2287061.01 | 2287061.01 | 1 | 2025-12-28 | 2 | 6694155.54 | -1643177.53 | DOWN | 0.3253 | 159 | Low | 818268.05 | 0.171 | 0 | 1945648.95 | 27 | 1.43 | 1.4
P002 | Software | SUP050 | 2025-12 | 2025-10-10 | 3970380.48 | 2763917 | -1206463.48 | 1206463.48 | 1 | 2025-12-28 | 3 | 5050978.01 | -1080597.53 | DOWN | 0.2722 | 79 | Low | 1580230.98 | 0.396 | 2 | 1183686.02 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP028 | 2025-01 | 2024-08-29 | 2831991.32 | 1814023 | -1017968.32 | 1017968.32 | 1 | 2025-01-28 | 1 |  |  |  |  | 152 | Low | 659137.1 | 0.229 | 0 | 1154885.9 | 20 | 1.45 | 1.35
P002 | Mechanical | SUP028 | 2025-01 | 2024-10-20 | 2274075.48 | 1814023 | -460052.48 | 460052.48 | 1 | 2025-01-28 | 2 | 2831991.32 | -557915.84 | DOWN | 0.2453 | 100 | Low | 955294.68 | 0.404 | 1 | 858728.32 | 20 | 1.45 | 1.35
P002 | Mechanical | SUP028 | 2025-01 | 2025-01-06 | 2012181.27 | 1814023 | -198158.27 | 198158.27 | 0 | 2025-01-28 | 3 | 2274075.48 | -261894.21 | DOWN | 0.1302 | 22 | Low | 1410169.39 | 0.666 | 3 | 403853.61 | 20 | 1.45 | 1.35
P002 | Materials | SUP028 | 2025-02 | 2024-11-12 | 961282.15 | 583763 | -377519.15 | 377519.15 | 1 | 2025-02-28 | 1 |  |  |  |  | 108 | Low | 368179.48 | 0.379 | 0 | 215583.52 | 23 | 1.4 | 1.5
P002 | Materials | SUP028 | 2025-02 | 2024-12-13 | 765065.73 | 583763 | -181302.73 | 181302.73 | 1 | 2025-02-28 | 2 | 961282.15 | -196216.42 | DOWN | 0.2565 | 77 | Low | 341202.44 | 0.484 | 5 | 242560.56 | 23 | 1.4 | 1.5
P002 | Materials | SUP028 | 2025-02 | 2024-12-25 | 670498.14 | 583763 | -86735.14 | 86735.14 | 0 | 2025-02-28 | 3 | 765065.73 | -94567.59 | DOWN | 0.141 | 65 | Low | 330693.51 | 0.524 | 4 | 253069.49 | 23 | 1.4 | 1.5
P002 | Materials | SUP028 | 2025-02 | 2024-12-27 | 617962.6 | 583763 | -34199.6 | 34199.6 | 0 | 2025-02-28 | 4 | 670498.14 | -52535.54 | DOWN | 0.085 | 63 | Low | 313476.08 | 0.531 | 3 | 270286.92 | 23 | 1.4 | 1.5
P002 | Materials | SUP028 | 2025-02 | 2025-01-05 | 593818.5 | 583763 | -10055.5 | 10055.5 | 0 | 2025-02-28 | 5 | 617962.6 | -24144.1 | DOWN | 0.0407 | 54 | Medium | 310200 | 0.562 | 5 | 273563 | 23 | 1.4 | 1.5
P002 | Materials | SUP028 | 2025-02 | 2025-02-10 | 587240.07 | 583763 | -3477.07 | 3477.07 | 0 | 2025-02-28 | 6 | 593818.5 | -6578.43 | DOWN | 0.0112 | 18 | High | 377635.73 | 0.683 | 6 | 206127.27 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP028 | 2025-03 | 2024-12-01 | 541992.58 | 283841 | -258151.58 | 258151.58 | 1 | 2025-03-28 | 1 |  |  |  |  | 117 | Low | 175387.55 | 0.317 | 0 | 108453.45 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP028 | 2025-03 | 2025-01-16 | 403000.77 | 283841 | -119159.77 | 119159.77 | 1 | 2025-03-28 | 2 | 541992.58 | -138991.81 | DOWN | 0.3449 | 71 | Low | 176155.85 | 0.458 | 4 | 107685.15 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP028 | 2025-03 | 2025-01-26 | 345040.5 | 283841 | -61199.5 | 61199.5 | 1 | 2025-03-28 | 3 | 403000.77 | -57960.27 | DOWN | 0.168 | 61 | Low | 160941.3 | 0.489 | 4 | 122899.7 | 25 | 2.28 | 1.97
P002 | Software | SUP028 | 2025-04 | 2025-01-22 | 4840349.7 | 2585049 | -2255300.7 | 2255300.7 | 1 | 2025-04-28 | 1 |  |  |  |  | 96 | Low | 2263640.17 | 0.436 | 4 | 321408.83 | 21 | 1.06 | 1.67
P002 | Software | SUP028 | 2025-04 | 2025-02-28 | 3587663.88 | 2585049 | -1002614.88 | 1002614.88 | 1 | 2025-04-28 | 2 | 4840349.7 | -1252685.82 | DOWN | 0.3492 | 59 | Low | 1912679.93 | 0.567 | 4 | 672369.07 | 21 | 1.06 | 1.67
P002 | Software | SUP028 | 2025-04 | 2025-03-19 | 3022347.13 | 2585049 | -437298.13 | 437298.13 | 0 | 2025-04-28 | 3 | 3587663.88 | -565316.75 | DOWN | 0.187 | 40 | Low | 1946470.37 | 0.634 | 5 | 638578.63 | 21 | 1.06 | 1.67
P002 | Software | SUP028 | 2025-04 | 2025-04-01 | 2836117.55 | 2585049 | -251068.55 | 251068.55 | 0 | 2025-04-28 | 4 | 3022347.13 | -186229.58 | DOWN | 0.0657 | 27 | Medium | 1835485.85 | 0.679 | 7 | 749563.15 | 21 | 1.06 | 1.67
P002 | Software | SUP028 | 2025-05 | 2025-02-15 | 1451164.12 | 821517 | -629647.12 | 629647.12 | 1 | 2025-05-28 | 1 |  |  |  |  | 102 | Low | 526148.3 | 0.37 | 5 | 295368.7 | 28 | 2.1 | 0.99
P002 | Software | SUP028 | 2025-05 | 2025-04-01 | 1077124.73 | 821517 | -255607.73 | 255607.73 | 1 | 2025-05-28 | 2 | 1451164.12 | -374039.39 | DOWN | 0.3473 | 57 | Low | 571655.63 | 0.511 | 3 | 249861.37 | 28 | 2.1 | 0.99
P002 | Software | SUP028 | 2025-05 | 2025-04-14 | 963535.7 | 821517 | -142018.7 | 142018.7 | 0 | 2025-05-28 | 3 | 1077124.73 | -113589.03 | DOWN | 0.1179 | 44 | Low | 515364.23 | 0.551 | 6 | 306152.77 | 28 | 2.1 | 0.99
P002 | Software | SUP028 | 2025-05 | 2025-04-17 | 877552.77 | 821517 | -56035.77 | 56035.77 | 0 | 2025-05-28 | 4 | 963535.7 | -85982.93 | DOWN | 0.098 | 41 | Low | 469154.23 | 0.561 | 5 | 352362.77 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP028 | 2025-06 | 2025-02-06 | 1850290.1 | 1300873 | -549417.1 | 549417.1 | 1 | 2025-06-28 | 1 |  |  |  |  | 142 | Low | 500788.36 | 0.268 | 2 | 800084.64 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP028 | 2025-06 | 2025-02-07 | 1546931.06 | 1300873 | -246058.06 | 246058.06 | 1 | 2025-06-28 | 2 | 1850290.1 | -303359.04 | DOWN | 0.1961 | 141 | Low | 428151.29 | 0.271 | 3 | 872721.71 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP028 | 2025-06 | 2025-04-17 | 1410258.62 | 1300873 | -109385.62 | 109385.62 | 0 | 2025-06-28 | 3 | 1546931.06 | -136672.44 | DOWN | 0.0969 | 72 | Low | 669396.7 | 0.508 | 4 | 631476.3 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP028 | 2025-06 | 2025-04-30 | 1345014.87 | 1300873 | -44141.87 | 44141.87 | 0 | 2025-06-28 | 4 | 1410258.62 | -65243.75 | DOWN | 0.0485 | 59 | Medium | 746092.18 | 0.553 | 2 | 554780.82 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP028 | 2025-06 | 2025-06-05 | 1315928.19 | 1300873 | -15055.19 | 15055.19 | 0 | 2025-06-28 | 5 | 1345014.87 | -29086.68 | DOWN | 0.0221 | 23 | High | 961310.63 | 0.677 | 7 | 339562.37 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP028 | 2025-06 | 2025-06-14 | 1317181.72 | 1300873 | -16308.72 | 16308.72 | 0 | 2025-06-28 | 6 | 1315928.19 | 1253.53 | UP | 0.001 | 14 | High | 882773.04 | 0.707 | 7 | 418099.96 | 17 | 1.27 | 1.62
P002 | Services | SUP028 | 2025-07 | 2025-03-08 | 2215628.27 | 1232360 | -983268.27 | 983268.27 | 1 | 2025-07-28 | 1 |  |  |  |  | 142 | Low | 558563.17 | 0.261 | 0 | 673796.83 | 24 | 1.49 | 1.96
P002 | Services | SUP028 | 2025-07 | 2025-03-09 | 1648767.64 | 1232360 | -416407.64 | 416407.64 | 1 | 2025-07-28 | 2 | 2215628.27 | -566860.63 | DOWN | 0.3438 | 141 | Low | 422037.94 | 0.265 | 0 | 810322.06 | 24 | 1.49 | 1.96
P002 | Services | SUP028 | 2025-07 | 2025-04-17 | 1424121.28 | 1232360 | -191761.28 | 191761.28 | 0 | 2025-07-28 | 3 | 1648767.64 | -224646.36 | DOWN | 0.1577 | 102 | Low | 562420.1 | 0.395 | 2 | 669939.9 | 24 | 1.49 | 1.96
P002 | Services | SUP028 | 2025-07 | 2025-06-04 | 1324825.17 | 1232360 | -92465.17 | 92465.17 | 0 | 2025-07-28 | 4 | 1424121.28 | -99296.11 | DOWN | 0.075 | 54 | Medium | 700514.08 | 0.556 | 5 | 531845.92 | 24 | 1.49 | 1.96
P002 | Services | SUP028 | 2025-07 | 2025-07-08 | 1285007.78 | 1232360 | -52647.78 | 52647.78 | 0 | 2025-07-28 | 5 | 1324825.17 | -39817.39 | DOWN | 0.031 | 20 | Medium | 867076.09 | 0.67 | 8 | 365283.91 | 24 | 1.49 | 1.96
P002 | Services | SUP028 | 2025-07 | 2025-07-16 | 1237299.93 | 1232360 | -4939.93 | 4939.93 | 0 | 2025-07-28 | 6 | 1285007.78 | -47707.85 | DOWN | 0.0386 | 12 | Medium | 869797.05 | 0.697 | 3 | 362562.95 | 24 | 1.49 | 1.96
P002 | Electronics | SUP028 | 2025-08 | 2025-03-17 | 2981910.08 | 1726077 | -1255833.08 | 1255833.08 | 1 | 2025-08-28 | 1 |  |  |  |  | 164 | Low | 616125.22 | 0.192 | 0 | 1109951.78 | 25 | 1.29 | 1.82
P002 | Electronics | SUP028 | 2025-08 | 2025-03-26 | 2272884.6 | 1726077 | -546807.6 | 546807.6 | 1 | 2025-08-28 | 2 | 2981910.08 | -709025.48 | DOWN | 0.3119 | 155 | Low | 475827.72 | 0.223 | 1 | 1250249.28 | 25 | 1.29 | 1.82
P002 | Electronics | SUP028 | 2025-08 | 2025-04-05 | 1952552.84 | 1726077 | -226475.84 | 226475.84 | 0 | 2025-08-28 | 3 | 2272884.6 | -320331.76 | DOWN | 0.1641 | 145 | Low | 472195.33 | 0.257 | 4 | 1253881.67 | 25 | 1.29 | 1.82
P002 | Electronics | SUP028 | 2025-08 | 2025-05-21 | 1849905.29 | 1726077 | -123828.29 | 123828.29 | 0 | 2025-08-28 | 4 | 1952552.84 | -102647.55 | DOWN | 0.0555 | 99 | Low | 755896.99 | 0.415 | 5 | 970180.01 | 25 | 1.29 | 1.82
P002 | Electronics | SUP028 | 2025-08 | 2025-06-16 | 1780583.37 | 1726077 | -54506.37 | 54506.37 | 0 | 2025-08-28 | 5 | 1849905.29 | -69321.92 | DOWN | 0.0389 | 73 | Low | 964363.79 | 0.504 | 0 | 761713.21 | 25 | 1.29 | 1.82
P002 | Electronics | SUP028 | 2025-08 | 2025-07-16 | 1726274.27 | 1726077 | -197.27 | 197.27 | 0 | 2025-08-28 | 6 | 1780583.37 | -54309.1 | DOWN | 0.0315 | 43 | Medium | 1022999.11 | 0.606 | 5 | 703077.89 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP028 | 2025-09 | 2025-04-16 | 2114204.29 | 1283528 | -830676.29 | 830676.29 | 1 | 2025-09-28 | 1 |  |  |  |  | 165 | Low | 383406 | 0.186 | 1 | 900122 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP028 | 2025-09 | 2025-06-11 | 1642514.29 | 1283528 | -358986.29 | 358986.29 | 1 | 2025-09-28 | 2 | 2114204.29 | -471690 | DOWN | 0.2872 | 109 | Low | 605227.13 | 0.376 | 0 | 678300.87 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP028 | 2025-09 | 2025-06-14 | 1463627.93 | 1283528 | -180099.93 | 180099.93 | 0 | 2025-09-28 | 3 | 1642514.29 | -178886.36 | DOWN | 0.1222 | 106 | Low | 593096.37 | 0.387 | 2 | 690431.63 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP028 | 2025-09 | 2025-07-19 | 1379846.86 | 1283528 | -96318.86 | 96318.86 | 0 | 2025-09-28 | 4 | 1463627.93 | -83781.07 | DOWN | 0.0607 | 71 | Low | 736652.25 | 0.505 | 4 | 546875.75 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP028 | 2025-09 | 2025-07-27 | 1327409.13 | 1283528 | -43881.13 | 43881.13 | 0 | 2025-09-28 | 5 | 1379846.86 | -52437.73 | DOWN | 0.0395 | 63 | Low | 670826.39 | 0.532 | 0 | 612701.61 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP028 | 2025-09 | 2025-08-28 | 1308472.44 | 1283528 | -24944.44 | 24944.44 | 0 | 2025-09-28 | 6 | 1327409.13 | -18936.69 | DOWN | 0.0145 | 31 | Medium | 808820.1 | 0.641 | 3 | 474707.9 | 25 | 1.38 | 1.58
P002 | Materials | SUP028 | 2025-10 | 2025-05-03 | 4657106.89 | 2539334 | -2117772.89 | 2117772.89 | 1 | 2025-10-28 | 1 |  |  |  |  | 178 | Low | 633061.2 | 0.143 | 1 | 1906272.8 | 21 | 1.76 | 1.29
P002 | Materials | SUP028 | 2025-10 | 2025-06-03 | 3476835.7 | 2539334 | -937501.7 | 937501.7 | 1 | 2025-10-28 | 2 | 4657106.89 | -1180271.19 | DOWN | 0.3395 | 147 | Low | 885619.48 | 0.237 | 1 | 1653714.52 | 21 | 1.76 | 1.29
P002 | Materials | SUP028 | 2025-10 | 2025-08-11 | 2958491.93 | 2539334 | -419157.93 | 419157.93 | 0 | 2025-10-28 | 3 | 3476835.7 | -518343.77 | DOWN | 0.1752 | 78 | Low | 1366678.91 | 0.461 | 1 | 1172655.09 | 21 | 1.76 | 1.29
P002 | Materials | SUP028 | 2025-10 | 2025-09-23 | 2764168.09 | 2539334 | -224834.09 | 224834.09 | 0 | 2025-10-28 | 4 | 2958491.93 | -194323.84 | DOWN | 0.0703 | 35 | Medium | 1739416.37 | 0.601 | 5 | 799917.63 | 21 | 1.76 | 1.29
P002 | Materials | SUP028 | 2025-10 | 2025-10-11 | 2624754.02 | 2539334 | -85420.02 | 85420.02 | 0 | 2025-10-28 | 5 | 2764168.09 | -139414.07 | DOWN | 0.0531 | 17 | Medium | 1717732.15 | 0.66 | 6 | 821601.85 | 21 | 1.76 | 1.29
P002 | Materials | SUP028 | 2025-10 | 2025-10-12 | 2537231.22 | 2539334 | 2102.78 | 2102.78 | 0 | 2025-10-28 | 6 | 2624754.02 | -87522.8 | DOWN | 0.0345 | 16 | Medium | 1638946.31 | 0.663 | 3 | 900387.69 | 21 | 1.76 | 1.29
P002 | Electronics | SUP028 | 2025-11 | 2025-06-30 | 889159.33 | 561538 | -327621.33 | 327621.33 | 1 | 2025-11-28 | 1 |  |  |  |  | 151 | Low | 210577.69 | 0.228 | 6 | 350960.31 | 26 | 1.59 | 1.38
P002 | Electronics | SUP028 | 2025-11 | 2025-07-25 | 700895.55 | 561538 | -139357.55 | 139357.55 | 1 | 2025-11-28 | 2 | 889159.33 | -188263.78 | DOWN | 0.2686 | 126 | Low | 202615.89 | 0.311 | 2 | 358922.11 | 26 | 1.59 | 1.38
P002 | Electronics | SUP028 | 2025-11 | 2025-09-16 | 628368.93 | 561538 | -66830.93 | 66830.93 | 0 | 2025-11-28 | 3 | 700895.55 | -72526.62 | DOWN | 0.1154 | 73 | Low | 285801.29 | 0.487 | 3 | 275736.71 | 26 | 1.59 | 1.38
P002 | Electronics | SUP028 | 2025-11 | 2025-09-22 | 595075.14 | 561538 | -33537.14 | 33537.14 | 0 | 2025-11-28 | 4 | 628368.93 | -33293.79 | DOWN | 0.0559 | 67 | Low | 324037.04 | 0.507 | 4 | 237500.96 | 26 | 1.59 | 1.38
P002 | Electronics | SUP028 | 2025-11 | 2025-09-28 | 577291.51 | 561538 | -15753.51 | 15753.51 | 0 | 2025-11-28 | 5 | 595075.14 | -17783.63 | DOWN | 0.0308 | 61 | Low | 326398.5 | 0.526 | 4 | 235139.5 | 26 | 1.59 | 1.38
P002 | Electronics | SUP028 | 2025-11 | 2025-11-17 | 575399.1 | 561538 | -13861.1 | 13861.1 | 0 | 2025-11-28 | 6 | 577291.51 | -1892.41 | DOWN | 0.0033 | 11 | Medium | 378877.02 | 0.692 | 6 | 182660.98 | 26 | 1.59 | 1.38
P002 | Logistics | SUP028 | 2025-12 | 2025-09-05 | 5767932.15 | 2779417 | -2988515.15 | 2988515.15 | 1 | 2025-12-28 | 1 |  |  |  |  | 114 | Low | 2112319.31 | 0.357 | 1 | 667097.69 | 27 | 1.43 | 1.4
P002 | Logistics | SUP028 | 2025-12 | 2025-11-07 | 4154320.3 | 2779417 | -1374903.3 | 1374903.3 | 1 | 2025-12-28 | 2 | 5767932.15 | -1613611.85 | DOWN | 0.3884 | 51 | Low | 2328549.68 | 0.57 | 6 | 450867.32 | 27 | 1.43 | 1.4
P002 | Logistics | SUP028 | 2025-12 | 2025-11-28 | 3444869.09 | 2779417 | -665452.09 | 665452.09 | 1 | 2025-12-28 | 3 | 4154320.3 | -709451.21 | DOWN | 0.2059 | 30 | Low | 2115099.47 | 0.641 | 0 | 664317.53 | 27 | 1.43 | 1.4
P002 | Electronics | SUP045 | 2025-01 | 2024-09-06 | 2249059.14 | 1507368 | -741691.14 | 741691.14 | 1 | 2025-01-28 | 1 |  |  |  |  | 144 | Low | 539858.29 | 0.256 | 1 | 967509.71 | 20 | 1.45 | 1.35
P002 | Electronics | SUP045 | 2025-01 | 2024-11-25 | 1824186.14 | 1507368 | -316818.14 | 316818.14 | 1 | 2025-01-28 | 2 | 2249059.14 | -424873 | DOWN | 0.2329 | 64 | Low | 976702.96 | 0.525 | 6 | 530665.04 | 20 | 1.45 | 1.35
P002 | Electronics | SUP045 | 2025-01 | 2025-01-14 | 1651275.59 | 1507368 | -143907.59 | 143907.59 | 0 | 2025-01-28 | 3 | 1824186.14 | -172910.55 | DOWN | 0.1047 | 14 | Medium | 1134304.37 | 0.693 | 7 | 373063.63 | 20 | 1.45 | 1.35
P002 | Logistics | SUP045 | 2025-02 | 2024-09-12 | 6389372.58 | 3012251 | -3377121.58 | 3377121.58 | 1 | 2025-02-28 | 1 |  |  |  |  | 169 | Low | 1102072.7 | 0.173 | 0 | 1910178.3 | 23 | 1.4 | 1.5
P002 | Logistics | SUP045 | 2025-02 | 2024-11-19 | 4632215.95 | 3012251 | -1619964.95 | 1619964.95 | 1 | 2025-02-28 | 2 | 6389372.58 | -1757156.63 | DOWN | 0.3793 | 101 | Low | 1982089.09 | 0.403 | 5 | 1030161.91 | 23 | 1.4 | 1.5
P002 | Logistics | SUP045 | 2025-02 | 2024-12-23 | 3794477.9 | 3012251 | -782226.9 | 782226.9 | 1 | 2025-02-28 | 3 | 4632215.95 | -837738.05 | DOWN | 0.2208 | 67 | Low | 2103801 | 0.518 | 4 | 908450 | 23 | 1.4 | 1.5
P002 | Logistics | SUP045 | 2025-02 | 2025-01-17 | 3412064.78 | 3012251 | -399813.78 | 399813.78 | 0 | 2025-02-28 | 4 | 3794477.9 | -382413.12 | DOWN | 0.1121 | 42 | Medium | 2191637.67 | 0.602 | 3 | 820613.33 | 23 | 1.4 | 1.5
P002 | Logistics | SUP045 | 2025-03 | 2024-10-11 | 4320037.52 | 2292754 | -2027283.52 | 2027283.52 | 1 | 2025-03-28 | 1 |  |  |  |  | 168 | Low | 733871.84 | 0.16 | 0 | 1558882.16 | 25 | 2.28 | 1.97
P002 | Logistics | SUP045 | 2025-03 | 2024-11-13 | 3335024.69 | 2292754 | -1042270.69 | 1042270.69 | 1 | 2025-03-28 | 2 | 4320037.52 | -985012.83 | DOWN | 0.2954 | 135 | Low | 935675.62 | 0.261 | 3 | 1357078.38 | 25 | 2.28 | 1.97
P002 | Logistics | SUP045 | 2025-03 | 2025-02-08 | 2761343.9 | 2292754 | -468589.9 | 468589.9 | 1 | 2025-03-28 | 3 | 3335024.69 | -573680.79 | DOWN | 0.2078 | 48 | Low | 1385480.04 | 0.529 | 5 | 907273.96 | 25 | 2.28 | 1.97
P002 | Logistics | SUP045 | 2025-03 | 2025-03-11 | 2446421.83 | 2292754 | -153667.83 | 153667.83 | 0 | 2025-03-28 | 4 | 2761343.9 | -314922.07 | DOWN | 0.1287 | 17 | Low | 1446651.39 | 0.624 | 4 | 846102.61 | 25 | 2.28 | 1.97
P002 | Software | SUP045 | 2025-04 | 2024-11-29 | 4751293.3 | 2502275 | -2249018.3 | 2249018.3 | 1 | 2025-04-28 | 1 |  |  |  |  | 150 | Low | 1109732.35 | 0.246 | 4 | 1392542.65 | 21 | 1.06 | 1.67
P002 | Software | SUP045 | 2025-04 | 2025-01-16 | 3427365.98 | 2502275 | -925090.98 | 925090.98 | 1 | 2025-04-28 | 2 | 4751293.3 | -1323927.32 | DOWN | 0.3863 | 102 | Low | 1517717.52 | 0.415 | 0 | 984557.48 | 21 | 1.06 | 1.67
P002 | Software | SUP045 | 2025-04 | 2025-01-30 | 2951937.18 | 2502275 | -449662.18 | 449662.18 | 1 | 2025-04-28 | 3 | 3427365.98 | -475428.8 | DOWN | 0.1611 | 88 | Low | 1365428.95 | 0.465 | 2 | 1136846.05 | 21 | 1.06 | 1.67
P002 | Software | SUP045 | 2025-04 | 2025-03-23 | 2733220.59 | 2502275 | -230945.59 | 230945.59 | 0 | 2025-04-28 | 4 | 2951937.18 | -218716.59 | DOWN | 0.08 | 36 | Medium | 1670854.12 | 0.648 | 4 | 831420.88 | 21 | 1.06 | 1.67
P002 | Software | SUP045 | 2025-04 | 2025-04-06 | 2644130.94 | 2502275 | -141855.94 | 141855.94 | 0 | 2025-04-28 | 5 | 2733220.59 | -89089.65 | DOWN | 0.0337 | 22 | High | 1757656.5 | 0.697 | 5 | 744618.5 | 21 | 1.06 | 1.67
P002 | Software | SUP045 | 2025-05 | 2024-12-09 | 402318.87 | 200228 | -202090.87 | 202090.87 | 1 | 2025-05-28 | 1 |  |  |  |  | 170 | Low | 67006.47 | 0.157 | 0 | 133221.53 | 28 | 2.1 | 0.99
P002 | Software | SUP045 | 2025-05 | 2025-01-01 | 290959.47 | 200228 | -90731.47 | 90731.47 | 1 | 2025-05-28 | 2 | 402318.87 | -111359.4 | DOWN | 0.3827 | 147 | Low | 65758.84 | 0.229 | 4 | 134469.16 | 28 | 2.1 | 0.99
P002 | Software | SUP045 | 2025-05 | 2025-01-09 | 241048.62 | 200228 | -40820.62 | 40820.62 | 1 | 2025-05-28 | 3 | 290959.47 | -49910.85 | DOWN | 0.2071 | 139 | Low | 57944.1 | 0.254 | 2 | 142283.9 | 28 | 2.1 | 0.99
P002 | Software | SUP045 | 2025-05 | 2025-04-01 | 219814.73 | 200228 | -19586.73 | 19586.73 | 0 | 2025-05-28 | 4 | 241048.62 | -21233.89 | DOWN | 0.0966 | 57 | Low | 111420.35 | 0.511 | 5 | 88807.65 | 28 | 2.1 | 0.99
P002 | Software | SUP045 | 2025-05 | 2025-04-24 | 210285.88 | 200228 | -10057.88 | 10057.88 | 0 | 2025-05-28 | 5 | 219814.73 | -9528.85 | DOWN | 0.0453 | 34 | Low | 112882.36 | 0.583 | 6 | 87345.64 | 28 | 2.1 | 0.99
P002 | Materials | SUP045 | 2025-06 | 2025-01-05 | 4157923.27 | 2446253 | -1711670.27 | 1711670.27 | 1 | 2025-06-28 | 1 |  |  |  |  | 174 | Low | 680818.29 | 0.158 | 2 | 1765434.71 | 17 | 1.27 | 1.62
P002 | Materials | SUP045 | 2025-06 | 2025-01-06 | 3230140.53 | 2446253 | -783887.53 | 783887.53 | 1 | 2025-06-28 | 2 | 4157923.27 | -927782.74 | DOWN | 0.2872 | 173 | Low | 522144.3 | 0.161 | 3 | 1924108.7 | 17 | 1.27 | 1.62
P002 | Materials | SUP045 | 2025-06 | 2025-03-11 | 2766714.87 | 2446253 | -320461.87 | 320461.87 | 0 | 2025-06-28 | 3 | 3230140.53 | -463425.66 | DOWN | 0.1675 | 109 | Low | 1106114.66 | 0.381 | 6 | 1340138.34 | 17 | 1.27 | 1.62
P002 | Materials | SUP045 | 2025-06 | 2025-05-22 | 2610185.5 | 2446253 | -163932.5 | 163932.5 | 0 | 2025-06-28 | 4 | 2766714.87 | -156529.37 | DOWN | 0.06 | 37 | Medium | 1531371.53 | 0.628 | 3 | 914881.47 | 17 | 1.27 | 1.62
P002 | Materials | SUP045 | 2025-06 | 2025-06-10 | 2521860.5 | 2446253 | -75607.5 | 75607.5 | 0 | 2025-06-28 | 5 | 2610185.5 | -88325 | DOWN | 0.035 | 18 | High | 1738381.01 | 0.694 | 4 | 707871.99 | 17 | 1.27 | 1.62
P002 | Services | SUP045 | 2025-07 | 2025-02-27 | 4920724.54 | 3060120 | -1860604.54 | 1860604.54 | 1 | 2025-07-28 | 1 |  |  |  |  | 151 | Low | 1164097.74 | 0.231 | 3 | 1896022.26 | 24 | 1.49 | 1.96
P002 | Services | SUP045 | 2025-07 | 2025-03-18 | 3993936.7 | 3060120 | -933816.7 | 933816.7 | 1 | 2025-07-28 | 2 | 4920724.54 | -926787.84 | DOWN | 0.232 | 132 | Low | 1091070.08 | 0.295 | 2 | 1969049.92 | 24 | 1.49 | 1.96
P002 | Services | SUP045 | 2025-07 | 2025-04-15 | 3504237.13 | 3060120 | -444117.13 | 444117.13 | 0 | 2025-07-28 | 3 | 3993936.7 | -489699.57 | DOWN | 0.1397 | 104 | Low | 1252841.56 | 0.388 | 3 | 1807278.44 | 24 | 1.49 | 1.96
P002 | Services | SUP045 | 2025-07 | 2025-05-29 | 3191316.01 | 3060120 | -131196.01 | 131196.01 | 0 | 2025-07-28 | 4 | 3504237.13 | -312921.12 | DOWN | 0.0981 | 60 | Medium | 1715087.23 | 0.536 | 4 | 1345032.77 | 24 | 1.49 | 1.96
P002 | Services | SUP045 | 2025-07 | 2025-06-27 | 3170641.57 | 3060120 | -110521.57 | 110521.57 | 0 | 2025-07-28 | 5 | 3191316.01 | -20674.44 | DOWN | 0.0065 | 31 | Medium | 1929357.86 | 0.633 | 5 | 1130762.14 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP045 | 2025-08 | 2025-03-20 | 5367812.75 | 3139767 | -2228045.75 | 2228045.75 | 1 | 2025-08-28 | 1 |  |  |  |  | 161 | Low | 1020931.81 | 0.202 | 6 | 2118835.19 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP045 | 2025-08 | 2025-08-03 | 4136886.71 | 3139767 | -997119.71 | 997119.71 | 1 | 2025-08-28 | 2 | 5367812.75 | -1230926.04 | DOWN | 0.2975 | 25 | Low | 2748002 | 0.668 | 6 | 391765 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP045 | 2025-08 | 2025-08-10 | 3586138.08 | 3139767 | -446371.08 | 446371.08 | 0 | 2025-08-28 | 3 | 4136886.71 | -550748.63 | DOWN | 0.1536 | 18 | Low | 2423317.76 | 0.692 | 0 | 716449.24 | 25 | 1.29 | 1.82
P002 | Services | SUP045 | 2025-09 | 2025-04-23 | 2072279.35 | 1035583 | -1036696.35 | 1036696.35 | 1 | 2025-09-28 | 1 |  |  |  |  | 158 | Low | 444250.77 | 0.21 | 0 | 591332.23 | 25 | 1.38 | 1.58
P002 | Services | SUP045 | 2025-09 | 2025-06-01 | 1505111.31 | 1035583 | -469528.31 | 469528.31 | 1 | 2025-09-28 | 2 | 2072279.35 | -567168.04 | DOWN | 0.3768 | 119 | Low | 499768.88 | 0.342 | 2 | 535814.12 | 25 | 1.38 | 1.58
P002 | Services | SUP045 | 2025-09 | 2025-06-12 | 1237858.84 | 1035583 | -202275.84 | 202275.84 | 1 | 2025-09-28 | 3 | 1505111.31 | -267252.47 | DOWN | 0.2159 | 108 | Low | 445258.69 | 0.38 | 4 | 590324.31 | 25 | 1.38 | 1.58
P002 | Services | SUP045 | 2025-09 | 2025-06-21 | 1117071.73 | 1035583 | -81488.73 | 81488.73 | 0 | 2025-09-28 | 4 | 1237858.84 | -120787.11 | DOWN | 0.1081 | 99 | Low | 477829.56 | 0.41 | 2 | 557753.44 | 25 | 1.38 | 1.58
P002 | Services | SUP045 | 2025-09 | 2025-08-15 | 1061718.69 | 1035583 | -26135.69 | 26135.69 | 0 | 2025-09-28 | 5 | 1117071.73 | -55353.04 | DOWN | 0.0521 | 44 | Medium | 662282.28 | 0.597 | 6 | 373300.72 | 25 | 1.38 | 1.58
P002 | Services | SUP045 | 2025-09 | 2025-09-06 | 1038919.3 | 1035583 | -3336.3 | 3336.3 | 0 | 2025-09-28 | 6 | 1061718.69 | -22799.39 | DOWN | 0.0219 | 22 | High | 684069.91 | 0.671 | 9 | 351513.09 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP045 | 2025-10 | 2025-05-24 | 3898656.82 | 2239689 | -1658967.82 | 1658967.82 | 1 | 2025-10-28 | 1 |  |  |  |  | 157 | Low | 858996.99 | 0.205 | 3 | 1380692.01 | 21 | 1.76 | 1.29
P002 | Mechanical | SUP045 | 2025-10 | 2025-06-09 | 3038661.06 | 2239689 | -798972.06 | 798972.06 | 1 | 2025-10-28 | 2 | 3898656.82 | -859995.76 | DOWN | 0.283 | 141 | Low | 813392.86 | 0.257 | 4 | 1426296.14 | 21 | 1.76 | 1.29
P002 | Mechanical | SUP045 | 2025-10 | 2025-09-10 | 2580577.87 | 2239689 | -340888.87 | 340888.87 | 0 | 2025-10-28 | 3 | 3038661.06 | -458083.19 | DOWN | 0.1775 | 48 | Low | 1408472.51 | 0.559 | 2 | 831216.49 | 21 | 1.76 | 1.29
P002 | Materials | SUP045 | 2025-11 | 2025-06-01 | 2061109.17 | 1280847 | -780262.17 | 780262.17 | 1 | 2025-11-28 | 1 |  |  |  |  | 180 | Low | 305260.56 | 0.146 | 0 | 975586.44 | 26 | 1.59 | 1.38
P002 | Materials | SUP045 | 2025-11 | 2025-07-07 | 1631790 | 1280847 | -350943 | 350943 | 1 | 2025-11-28 | 2 | 2061109.17 | -429319.17 | DOWN | 0.2631 | 144 | Low | 425692.3 | 0.252 | 1 | 855154.7 | 26 | 1.59 | 1.38
P002 | Materials | SUP045 | 2025-11 | 2025-10-16 | 1416382.08 | 1280847 | -135535.08 | 135535.08 | 0 | 2025-11-28 | 3 | 1631790 | -215407.92 | DOWN | 0.1521 | 43 | Low | 861670.78 | 0.586 | 5 | 419176.22 | 26 | 1.59 | 1.38
P002 | Materials | SUP045 | 2025-11 | 2025-11-10 | 1326157.1 | 1280847 | -45310.1 | 45310.1 | 0 | 2025-11-28 | 4 | 1416382.08 | -90224.98 | DOWN | 0.068 | 18 | Medium | 825597.41 | 0.669 | 4 | 455249.59 | 26 | 1.59 | 1.38
P002 | Services | SUP045 | 2025-12 | 2025-07-05 | 4946297.94 | 2726833 | -2219464.94 | 2219464.94 | 1 | 2025-12-28 | 1 |  |  |  |  | 176 | Low | 745454.84 | 0.148 | 1 | 1981378.16 | 27 | 1.43 | 1.4
P002 | Services | SUP045 | 2025-12 | 2025-08-18 | 3694171.31 | 2726833 | -967338.31 | 967338.31 | 1 | 2025-12-28 | 2 | 4946297.94 | -1252126.63 | DOWN | 0.3389 | 132 | Low | 1035005.53 | 0.297 | 6 | 1691827.47 | 27 | 1.43 | 1.4
P002 | Services | SUP045 | 2025-12 | 2025-09-10 | 3172845.29 | 2726833 | -446012.29 | 446012.29 | 0 | 2025-12-28 | 3 | 3694171.31 | -521326.02 | DOWN | 0.1643 | 109 | Low | 1215813.29 | 0.374 | 6 | 1511019.71 | 27 | 1.43 | 1.4
P002 | Services | SUP045 | 2025-12 | 2025-11-29 | 2894268.52 | 2726833 | -167435.52 | 167435.52 | 0 | 2025-12-28 | 4 | 3172845.29 | -278576.77 | DOWN | 0.0963 | 29 | Medium | 2004723.86 | 0.644 | 5 | 722109.14 | 27 | 1.43 | 1.4
P002 | Services | SUP047 | 2025-01 | 2024-08-28 | 401502.81 | 226249 | -175253.81 | 175253.81 | 1 | 2025-01-28 | 1 |  |  |  |  | 153 | Low | 95187.33 | 0.225 | 2 | 131061.67 | 20 | 1.45 | 1.35
P002 | Services | SUP047 | 2025-01 | 2024-10-16 | 311099.55 | 226249 | -84850.55 | 84850.55 | 1 | 2025-01-28 | 2 | 401502.81 | -90403.26 | DOWN | 0.2906 | 104 | Low | 119974.51 | 0.39 | 4 | 106274.49 | 20 | 1.45 | 1.35
P002 | Services | SUP047 | 2025-01 | 2024-10-29 | 267319.8 | 226249 | -41070.8 | 41070.8 | 1 | 2025-01-28 | 3 | 311099.55 | -43779.75 | DOWN | 0.1638 | 91 | Low | 124142.26 | 0.434 | 5 | 102106.74 | 20 | 1.45 | 1.35
P002 | Services | SUP047 | 2025-01 | 2024-10-31 | 246402.6 | 226249 | -20153.6 | 20153.6 | 0 | 2025-01-28 | 4 | 267319.8 | -20917.2 | DOWN | 0.0849 | 89 | Low | 111381.16 | 0.441 | 1 | 114867.84 | 20 | 1.45 | 1.35
P002 | Services | SUP047 | 2025-01 | 2025-01-16 | 232890.99 | 226249 | -6641.99 | 6641.99 | 0 | 2025-01-28 | 5 | 246402.6 | -13511.61 | DOWN | 0.058 | 12 | Medium | 171528.41 | 0.7 | 5 | 54720.59 | 20 | 1.45 | 1.35
P002 | Electronics | SUP047 | 2025-02 | 2024-09-11 | 4457003.54 | 2521246 | -1935757.54 | 1935757.54 | 1 | 2025-02-28 | 1 |  |  |  |  | 170 | Low | 750691.04 | 0.169 | 0 | 1770554.96 | 23 | 1.4 | 1.5
P002 | Electronics | SUP047 | 2025-02 | 2024-11-25 | 3440161.79 | 2521246 | -918915.79 | 918915.79 | 1 | 2025-02-28 | 2 | 4457003.54 | -1016841.75 | DOWN | 0.2956 | 95 | Low | 1445004.06 | 0.423 | 2 | 1076241.94 | 23 | 1.4 | 1.5
P002 | Electronics | SUP047 | 2025-02 | 2025-01-28 | 2914931.85 | 2521246 | -393685.85 | 393685.85 | 0 | 2025-02-28 | 3 | 3440161.79 | -525229.94 | DOWN | 0.1802 | 31 | Low | 1733405.94 | 0.639 | 3 | 787840.06 | 23 | 1.4 | 1.5
P002 | Services | SUP047 | 2025-03 | 2024-10-21 | 2400555.9 | 1067919 | -1332636.9 | 1332636.9 | 1 | 2025-03-28 | 1 |  |  |  |  | 158 | Low | 485831.54 | 0.191 | 0 | 582087.46 | 25 | 2.28 | 1.97
P002 | Services | SUP047 | 2025-03 | 2024-12-29 | 1680169.01 | 1067919 | -612250.01 | 612250.01 | 1 | 2025-03-28 | 2 | 2400555.9 | -720386.89 | DOWN | 0.4288 | 89 | Low | 676284.15 | 0.403 | 3 | 391634.85 | 25 | 2.28 | 1.97
P002 | Services | SUP047 | 2025-03 | 2025-02-10 | 1376018.09 | 1067919 | -308099.09 | 308099.09 | 1 | 2025-03-28 | 3 | 1680169.01 | -304150.92 | DOWN | 0.221 | 46 | Low | 706926.12 | 0.535 | 5 | 360992.88 | 25 | 2.28 | 1.97
P002 | Services | SUP047 | 2025-03 | 2025-03-03 | 1244508.83 | 1067919 | -176589.83 | 176589.83 | 0 | 2025-03-28 | 4 | 1376018.09 | -131509.26 | DOWN | 0.1057 | 25 | Low | 775906.21 | 0.599 | 5 | 292012.79 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP047 | 2025-04 | 2024-11-02 | 862510.88 | 621889 | -240621.88 | 240621.88 | 1 | 2025-04-28 | 1 |  |  |  |  | 177 | Low | 124020.85 | 0.155 | 0 | 497868.15 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP047 | 2025-04 | 2024-11-27 | 734107.74 | 621889 | -112218.74 | 112218.74 | 1 | 2025-04-28 | 2 | 862510.88 | -128403.14 | DOWN | 0.1749 | 152 | Low | 166956.33 | 0.239 | 3 | 454932.67 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP047 | 2025-04 | 2025-01-19 | 671190.56 | 621889 | -49301.56 | 49301.56 | 0 | 2025-04-28 | 3 | 734107.74 | -62917.18 | DOWN | 0.0937 | 99 | Low | 308365.36 | 0.426 | 1 | 313523.64 | 21 | 1.06 | 1.67
P002 | Services | SUP047 | 2025-05 | 2025-01-09 | 1625108.61 | 788769 | -836339.61 | 836339.61 | 1 | 2025-05-28 | 1 |  |  |  |  | 139 | Low | 404874.93 | 0.254 | 1 | 383894.07 | 28 | 2.1 | 0.99
P002 | Services | SUP047 | 2025-05 | 2025-01-26 | 1156376.2 | 788769 | -367607.2 | 367607.2 | 1 | 2025-05-28 | 2 | 1625108.61 | -468732.41 | DOWN | 0.4053 | 122 | Low | 356199.79 | 0.307 | 4 | 432569.21 | 28 | 2.1 | 0.99
P002 | Services | SUP047 | 2025-05 | 2025-02-23 | 936154.96 | 788769 | -147385.96 | 147385.96 | 1 | 2025-05-28 | 3 | 1156376.2 | -220221.24 | DOWN | 0.2352 | 94 | Low | 397854.45 | 0.395 | 2 | 390914.55 | 28 | 2.1 | 0.99
P002 | Services | SUP047 | 2025-05 | 2025-03-06 | 856721.6 | 788769 | -67952.6 | 67952.6 | 0 | 2025-05-28 | 4 | 936154.96 | -79433.36 | DOWN | 0.0927 | 83 | Low | 395132.03 | 0.429 | 2 | 393636.97 | 28 | 2.1 | 0.99
P002 | Services | SUP047 | 2025-05 | 2025-03-10 | 798276.89 | 788769 | -9507.89 | 9507.89 | 0 | 2025-05-28 | 5 | 856721.6 | -58444.71 | DOWN | 0.0732 | 79 | Low | 361477.92 | 0.442 | 0 | 427291.08 | 28 | 2.1 | 0.99
P002 | Materials | SUP047 | 2025-06 | 2025-03-11 | 3115473.18 | 1679421 | -1436052.18 | 1436052.18 | 1 | 2025-06-28 | 1 |  |  |  |  | 109 | Low | 1130312.25 | 0.381 | 0 | 549108.75 | 17 | 1.27 | 1.62
P002 | Materials | SUP047 | 2025-06 | 2025-04-28 | 2345937.92 | 1679421 | -666516.92 | 666516.92 | 1 | 2025-06-28 | 2 | 3115473.18 | -769535.26 | DOWN | 0.328 | 61 | Low | 1339935.78 | 0.546 | 3 | 339485.22 | 17 | 1.27 | 1.62
P002 | Materials | SUP047 | 2025-06 | 2025-06-06 | 1981578.85 | 1679421 | -302157.85 | 302157.85 | 1 | 2025-06-28 | 3 | 2345937.92 | -364359.07 | DOWN | 0.1839 | 22 | Low | 1352184.62 | 0.68 | 5 | 327236.38 | 17 | 1.27 | 1.62
P002 | Materials | SUP047 | 2025-06 | 2025-06-09 | 1809469.95 | 1679421 | -130048.95 | 130048.95 | 0 | 2025-06-28 | 4 | 1981578.85 | -172108.9 | DOWN | 0.0951 | 19 | Medium | 1207124.4 | 0.69 | 7 | 472296.6 | 17 | 1.27 | 1.62
P002 | Materials | SUP047 | 2025-06 | 2025-06-15 | 1726659.16 | 1679421 | -47238.16 | 47238.16 | 0 | 2025-06-28 | 5 | 1809469.95 | -82810.79 | DOWN | 0.048 | 13 | High | 1140276.58 | 0.711 | 8 | 539144.42 | 17 | 1.27 | 1.62
P002 | Logistics | SUP047 | 2025-07 | 2025-03-03 | 2301234.29 | 1216360 | -1084874.29 | 1084874.29 | 1 | 2025-07-28 | 1 |  |  |  |  | 147 | Low | 557993.97 | 0.244 | 1 | 658366.03 | 24 | 1.49 | 1.96
P002 | Logistics | SUP047 | 2025-07 | 2025-04-27 | 1747095.81 | 1216360 | -530735.81 | 530735.81 | 1 | 2025-07-28 | 2 | 2301234.29 | -554138.48 | DOWN | 0.3172 | 92 | Low | 721082.65 | 0.429 | 7 | 495277.35 | 24 | 1.49 | 1.96
P002 | Logistics | SUP047 | 2025-07 | 2025-06-27 | 1480305.44 | 1216360 | -263945.44 | 263945.44 | 1 | 2025-07-28 | 3 | 1747095.81 | -266790.37 | DOWN | 0.1802 | 31 | Low | 925651.4 | 0.633 | 6 | 290708.6 | 24 | 1.49 | 1.96
P002 | Logistics | SUP047 | 2025-07 | 2025-07-04 | 1320497.34 | 1216360 | -104137.34 | 104137.34 | 0 | 2025-07-28 | 4 | 1480305.44 | -159808.1 | DOWN | 0.121 | 24 | Low | 818763.62 | 0.656 | 4 | 397596.38 | 24 | 1.49 | 1.96
P002 | Logistics | SUP047 | 2025-07 | 2025-07-05 | 1291731.92 | 1216360 | -75371.92 | 75371.92 | 0 | 2025-07-28 | 5 | 1320497.34 | -28765.42 | DOWN | 0.0223 | 23 | Medium | 899046.46 | 0.66 | 5 | 317313.54 | 24 | 1.49 | 1.96
P002 | Software | SUP047 | 2025-08 | 2025-03-19 | 1167707.01 | 672093 | -495614.01 | 495614.01 | 1 | 2025-08-28 | 1 |  |  |  |  | 162 | Low | 242006.32 | 0.199 | 1 | 430086.68 | 25 | 1.29 | 1.82
P002 | Software | SUP047 | 2025-08 | 2025-04-28 | 902961.58 | 672093 | -230868.58 | 230868.58 | 1 | 2025-08-28 | 2 | 1167707.01 | -264745.43 | DOWN | 0.2932 | 122 | Low | 283408.81 | 0.336 | 0 | 388684.19 | 25 | 1.29 | 1.82
P002 | Software | SUP047 | 2025-08 | 2025-05-03 | 781362.16 | 672093 | -109269.16 | 109269.16 | 0 | 2025-08-28 | 3 | 902961.58 | -121599.42 | DOWN | 0.1556 | 117 | Low | 287586.23 | 0.353 | 3 | 384506.77 | 25 | 1.29 | 1.82
P002 | Software | SUP047 | 2025-08 | 2025-05-15 | 714960.82 | 672093 | -42867.82 | 42867.82 | 0 | 2025-08-28 | 4 | 781362.16 | -66401.34 | DOWN | 0.0929 | 105 | Low | 267147.54 | 0.394 | 0 | 404945.46 | 25 | 1.29 | 1.82
P002 | Software | SUP047 | 2025-08 | 2025-08-02 | 694711.73 | 672093 | -22618.73 | 22618.73 | 0 | 2025-08-28 | 5 | 714960.82 | -20249.09 | DOWN | 0.0291 | 26 | High | 465456.48 | 0.665 | 2 | 206636.52 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP047 | 2025-09 | 2025-04-18 | 2885619.24 | 1887921 | -997698.24 | 997698.24 | 1 | 2025-09-28 | 1 |  |  |  |  | 163 | Low | 533673.76 | 0.193 | 0 | 1354247.24 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP047 | 2025-09 | 2025-04-28 | 2359361.75 | 1887921 | -471440.75 | 471440.75 | 1 | 2025-09-28 | 2 | 2885619.24 | -526257.49 | DOWN | 0.2231 | 153 | Low | 500569.08 | 0.227 | 3 | 1387351.92 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP047 | 2025-09 | 2025-05-01 | 2107376.38 | 1887921 | -219455.38 | 219455.38 | 0 | 2025-09-28 | 3 | 2359361.75 | -251985.37 | DOWN | 0.1196 | 150 | Low | 515776.88 | 0.237 | 4 | 1372144.12 | 25 | 1.38 | 1.58
P002 | Materials | SUP047 | 2025-10 | 2025-06-14 | 4168167.7 | 2504502 | -1663665.7 | 1663665.7 | 1 | 2025-10-28 | 1 |  |  |  |  | 136 | Low | 1220512.4 | 0.273 | 3 | 1283989.6 | 21 | 1.76 | 1.29
P002 | Materials | SUP047 | 2025-10 | 2025-07-31 | 3292164.01 | 2504502 | -787662.01 | 787662.01 | 1 | 2025-10-28 | 2 | 4168167.7 | -876003.69 | DOWN | 0.2661 | 89 | Low | 1386514.37 | 0.426 | 3 | 1117987.63 | 21 | 1.76 | 1.29
P002 | Materials | SUP047 | 2025-10 | 2025-08-13 | 2850379.56 | 2504502 | -345877.56 | 345877.56 | 0 | 2025-10-28 | 3 | 3292164.01 | -441784.45 | DOWN | 0.155 | 76 | Low | 1375891.3 | 0.468 | 1 | 1128610.7 | 21 | 1.76 | 1.29
P002 | Materials | SUP047 | 2025-10 | 2025-09-11 | 2675056.74 | 2504502 | -170554.74 | 170554.74 | 0 | 2025-10-28 | 4 | 2850379.56 | -175322.82 | DOWN | 0.0655 | 47 | Medium | 1540499.27 | 0.562 | 7 | 964002.73 | 21 | 1.76 | 1.29
P002 | Materials | SUP047 | 2025-10 | 2025-10-12 | 2534968.26 | 2504502 | -30466.26 | 30466.26 | 0 | 2025-10-28 | 5 | 2675056.74 | -140088.48 | DOWN | 0.0553 | 16 | Medium | 1814090.82 | 0.663 | 5 | 690411.18 | 21 | 1.76 | 1.29
P002 | Mechanical | SUP047 | 2025-11 | 2025-08-15 | 1534677.24 | 1055644 | -479033.24 | 479033.24 | 1 | 2025-11-28 | 1 |  |  |  |  | 105 | Low | 550689.82 | 0.381 | 2 | 504954.18 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP047 | 2025-11 | 2025-08-20 | 1275339 | 1055644 | -219695 | 219695 | 1 | 2025-11-28 | 2 | 1534677.24 | -259338.24 | DOWN | 0.2033 | 100 | Low | 467923.08 | 0.397 | 1 | 587720.92 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP047 | 2025-11 | 2025-10-01 | 1170622.99 | 1055644 | -114978.99 | 114978.99 | 0 | 2025-11-28 | 3 | 1275339 | -104716.01 | DOWN | 0.0895 | 58 | Medium | 622780.87 | 0.536 | 2 | 432863.13 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP047 | 2025-11 | 2025-10-26 | 1107069.65 | 1055644 | -51425.65 | 51425.65 | 0 | 2025-11-28 | 4 | 1170622.99 | -63553.34 | DOWN | 0.0574 | 33 | Medium | 710203.22 | 0.619 | 6 | 345440.78 | 26 | 1.59 | 1.38
P002 | Electronics | SUP047 | 2025-12 | 2025-07-28 | 1151818.26 | 665645 | -486173.26 | 486173.26 | 1 | 2025-12-28 | 1 |  |  |  |  | 153 | Low | 245747.55 | 0.226 | 1 | 419897.45 | 27 | 1.43 | 1.4
P002 | Electronics | SUP047 | 2025-12 | 2025-08-07 | 881872.64 | 665645 | -216227.64 | 216227.64 | 1 | 2025-12-28 | 2 | 1151818.26 | -269945.62 | DOWN | 0.3061 | 143 | Low | 235044.39 | 0.26 | 0 | 430600.61 | 27 | 1.43 | 1.4
P002 | Electronics | SUP047 | 2025-12 | 2025-08-19 | 764535.24 | 665645 | -98890.24 | 98890.24 | 0 | 2025-12-28 | 3 | 881872.64 | -117337.4 | DOWN | 0.1535 | 131 | Low | 242320.71 | 0.3 | 4 | 423324.29 | 27 | 1.43 | 1.4
P002 | Electronics | SUP047 | 2025-12 | 2025-08-20 | 717177.41 | 665645 | -51532.41 | 51532.41 | 0 | 2025-12-28 | 4 | 764535.24 | -47357.83 | DOWN | 0.066 | 130 | Low | 211794.1 | 0.303 | 1 | 453850.9 | 27 | 1.43 | 1.4
P002 | Electronics | SUP047 | 2025-12 | 2025-08-21 | 689716.66 | 665645 | -24071.66 | 24071.66 | 0 | 2025-12-28 | 5 | 717177.41 | -27460.75 | DOWN | 0.0398 | 129 | Low | 210878.88 | 0.307 | 3 | 454766.12 | 27 | 1.43 | 1.4
P002 | Electronics | SUP047 | 2025-12 | 2025-11-15 | 681403.01 | 665645 | -15758.01 | 15758.01 | 0 | 2025-12-28 | 6 | 689716.66 | -8313.65 | DOWN | 0.0122 | 43 | Medium | 380225.85 | 0.597 | 5 | 285419.15 | 27 | 1.43 | 1.4
P002 | Electronics | SUP022 | 2025-01 | 2024-10-13 | 737033.29 | 371117 | -365916.29 | 365916.29 | 1 | 2025-01-28 | 1 |  |  |  |  | 107 | Low | 207501.48 | 0.268 | 0 | 163615.52 | 20 | 1.45 | 1.35
P002 | Electronics | SUP022 | 2025-01 | 2024-11-16 | 580598.26 | 371117 | -209481.26 | 209481.26 | 1 | 2025-01-28 | 2 | 737033.29 | -156435.03 | DOWN | 0.2694 | 73 | Low | 212344.98 | 0.349 | 3 | 158772.02 | 20 | 1.45 | 1.35
P002 | Electronics | SUP022 | 2025-01 | 2024-12-17 | 497964.01 | 371117 | -126847.01 | 126847.01 | 1 | 2025-01-28 | 3 | 580598.26 | -82634.25 | DOWN | 0.1659 | 42 | Low | 225312.51 | 0.422 | 4 | 145804.49 | 20 | 1.45 | 1.35
P002 | Electronics | SUP022 | 2025-01 | 2025-01-08 | 443334.59 | 371117 | -72217.59 | 72217.59 | 1 | 2025-01-28 | 4 | 497964.01 | -54629.42 | DOWN | 0.1232 | 20 | Low | 213720.71 | 0.474 | 4 | 157396.29 | 20 | 1.45 | 1.35
P002 | Software | SUP022 | 2025-02 | 2024-11-26 | 3554271.65 | 1948860 | -1605411.65 | 1605411.65 | 1 | 2025-02-28 | 1 |  |  |  |  | 94 | Low | 1092269.72 | 0.301 | 2 | 856590.28 | 23 | 1.4 | 1.5
P002 | Software | SUP022 | 2025-02 | 2024-12-10 | 2917527.49 | 1948860 | -968667.49 | 968667.49 | 1 | 2025-02-28 | 2 | 3554271.65 | -636744.16 | DOWN | 0.2182 | 80 | Low | 917213.01 | 0.334 | 3 | 1031646.99 | 23 | 1.4 | 1.5
P002 | Software | SUP022 | 2025-02 | 2025-02-16 | 2547681.93 | 1948860 | -598821.93 | 598821.93 | 1 | 2025-02-28 | 3 | 2917527.49 | -369845.56 | DOWN | 0.1452 | 12 | Low | 1240926.08 | 0.496 | 3 | 707933.92 | 23 | 1.4 | 1.5
P002 | Software | SUP022 | 2025-03 | 2024-10-08 | 4199832.28 | 2386686 | -1813146.28 | 1813146.28 | 1 | 2025-03-28 | 1 |  |  |  |  | 171 | Low | 479205.38 | 0.106 | 1 | 1907480.62 | 25 | 2.28 | 1.97
P002 | Software | SUP022 | 2025-03 | 2024-10-10 | 3421674.42 | 2386686 | -1034988.42 | 1034988.42 | 1 | 2025-03-28 | 2 | 4199832.28 | -778157.86 | DOWN | 0.2274 | 169 | Low | 353863.37 | 0.111 | 0 | 2032822.63 | 25 | 2.28 | 1.97
P002 | Software | SUP022 | 2025-03 | 2024-10-29 | 3113328.17 | 2386686 | -726642.17 | 726642.17 | 1 | 2025-03-28 | 3 | 3421674.42 | -308346.25 | DOWN | 0.099 | 150 | Low | 442034.51 | 0.152 | 0 | 1944651.49 | 25 | 2.28 | 1.97
P002 | Software | SUP022 | 2025-03 | 2025-02-26 | 2914059.52 | 2386686 | -527373.52 | 527373.52 | 1 | 2025-03-28 | 4 | 3113328.17 | -199268.65 | DOWN | 0.0684 | 30 | Low | 1279270.89 | 0.412 | 0 | 1107415.11 | 25 | 2.28 | 1.97
P002 | Services | SUP022 | 2025-04 | 2024-11-08 | 3704595.61 | 1742892 | -1961703.61 | 1961703.61 | 1 | 2025-04-28 | 1 |  |  |  |  | 171 | Low | 430519.96 | 0.122 | 0 | 1312372.04 | 21 | 1.06 | 1.67
P002 | Services | SUP022 | 2025-04 | 2024-11-29 | 2932103.85 | 1742892 | -1189211.85 | 1189211.85 | 1 | 2025-04-28 | 2 | 3704595.61 | -772491.76 | DOWN | 0.2635 | 150 | Low | 492384.14 | 0.174 | 0 | 1250507.86 | 21 | 1.06 | 1.67
P002 | Services | SUP022 | 2025-04 | 2024-12-21 | 2422530.68 | 1742892 | -679638.68 | 679638.68 | 1 | 2025-04-28 | 3 | 2932103.85 | -509573.17 | DOWN | 0.2103 | 128 | Low | 532553.08 | 0.228 | 3 | 1210338.92 | 21 | 1.06 | 1.67
P002 | Services | SUP022 | 2025-04 | 2025-01-10 | 2158670.47 | 1742892 | -415778.47 | 415778.47 | 1 | 2025-04-28 | 4 | 2422530.68 | -263860.21 | DOWN | 0.1222 | 108 | Low | 565151.4 | 0.278 | 2 | 1177740.6 | 21 | 1.06 | 1.67
P002 | Services | SUP022 | 2025-04 | 2025-02-19 | 1989210.52 | 1742892 | -246318.52 | 246318.52 | 0 | 2025-04-28 | 5 | 2158670.47 | -169459.95 | DOWN | 0.0852 | 68 | Low | 797346.85 | 0.377 | 4 | 945545.15 | 21 | 1.06 | 1.67
P002 | Services | SUP022 | 2025-04 | 2025-02-24 | 1899733.59 | 1742892 | -156841.59 | 156841.59 | 0 | 2025-04-28 | 6 | 1989210.52 | -89476.93 | DOWN | 0.0471 | 63 | Low | 696759.22 | 0.39 | 3 | 1046132.78 | 21 | 1.06 | 1.67
P002 | Materials | SUP022 | 2025-05 | 2024-12-29 | 4248149.04 | 2366683 | -1881466.04 | 1881466.04 | 1 | 2025-05-28 | 1 |  |  |  |  | 150 | Low | 632446.95 | 0.155 | 0 | 1734236.05 | 28 | 2.1 | 0.99
P002 | Materials | SUP022 | 2025-05 | 2025-01-24 | 3584858.25 | 2366683 | -1218175.25 | 1218175.25 | 1 | 2025-05-28 | 2 | 4248149.04 | -663290.79 | DOWN | 0.185 | 124 | Low | 742305.05 | 0.212 | 0 | 1624377.95 | 28 | 2.1 | 0.99
P002 | Materials | SUP022 | 2025-05 | 2025-01-29 | 3072211.41 | 2366683 | -705528.41 | 705528.41 | 1 | 2025-05-28 | 3 | 3584858.25 | -512646.84 | DOWN | 0.1669 | 119 | Low | 668863.95 | 0.223 | 4 | 1697819.05 | 28 | 2.1 | 0.99
P002 | Services | SUP022 | 2025-06 | 2025-01-18 | 3178907.82 | 1699156 | -1479751.82 | 1479751.82 | 1 | 2025-06-28 | 1 |  |  |  |  | 161 | Low | 445573.98 | 0.143 | 0 | 1253582.02 | 17 | 1.27 | 1.62
P002 | Services | SUP022 | 2025-06 | 2025-01-19 | 2592927.59 | 1699156 | -893771.59 | 893771.59 | 1 | 2025-06-28 | 2 | 3178907.82 | -585980.23 | DOWN | 0.226 | 160 | Low | 373418.68 | 0.145 | 1 | 1325737.32 | 17 | 1.27 | 1.62
P002 | Services | SUP022 | 2025-06 | 2025-03-05 | 2277583.51 | 1699156 | -578427.51 | 578427.51 | 1 | 2025-06-28 | 3 | 2592927.59 | -315344.08 | DOWN | 0.1385 | 115 | Low | 579375.49 | 0.254 | 2 | 1119780.51 | 17 | 1.27 | 1.62
P002 | Services | SUP022 | 2025-06 | 2025-03-26 | 2058577.4 | 1699156 | -359421.4 | 359421.4 | 1 | 2025-06-28 | 4 | 2277583.51 | -219006.11 | DOWN | 0.1064 | 94 | Low | 661654.27 | 0.305 | 4 | 1037501.73 | 17 | 1.27 | 1.62
P002 | Services | SUP022 | 2025-06 | 2025-04-17 | 1932570.65 | 1699156 | -233414.65 | 233414.65 | 0 | 2025-06-28 | 5 | 2058577.4 | -126006.75 | DOWN | 0.0652 | 72 | Low | 744772.97 | 0.358 | 4 | 954383.03 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP022 | 2025-07 | 2025-02-10 | 3110675.47 | 1955215 | -1155460.47 | 1155460.47 | 1 | 2025-07-28 | 1 |  |  |  |  | 168 | Low | 378464.11 | 0.123 | 0 | 1576750.89 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP022 | 2025-07 | 2025-03-07 | 2626235.39 | 1955215 | -671020.39 | 671020.39 | 1 | 2025-07-28 | 2 | 3110675.47 | -484440.08 | DOWN | 0.1845 | 143 | Low | 465089.94 | 0.182 | 2 | 1490125.06 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP022 | 2025-07 | 2025-03-20 | 2332983.25 | 1955215 | -377768.25 | 377768.25 | 1 | 2025-07-28 | 3 | 2626235.39 | -293252.14 | DOWN | 0.1257 | 130 | Low | 490854.92 | 0.213 | 1 | 1464360.08 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP022 | 2025-07 | 2025-03-31 | 2202085.83 | 1955215 | -246870.83 | 246870.83 | 0 | 2025-07-28 | 4 | 2332983.25 | -130897.42 | DOWN | 0.0594 | 119 | Low | 503523.38 | 0.238 | 1 | 1451691.62 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP022 | 2025-07 | 2025-07-05 | 2083768.07 | 1955215 | -128553.07 | 128553.07 | 0 | 2025-07-28 | 5 | 2202085.83 | -118317.76 | DOWN | 0.0568 | 23 | Medium | 964077.95 | 0.465 | 3 | 991137.05 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP022 | 2025-07 | 2025-07-08 | 2052613.81 | 1955215 | -97398.81 | 97398.81 | 0 | 2025-07-28 | 6 | 2083768.07 | -31154.26 | DOWN | 0.0152 | 20 | Medium | 910416.74 | 0.472 | 4 | 1044798.26 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP022 | 2025-08 | 2025-05-03 | 922469.15 | 488997 | -433472.15 | 433472.15 | 1 | 2025-08-28 | 1 |  |  |  |  | 117 | Low | 235046.39 | 0.249 | 1 | 253950.61 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP022 | 2025-08 | 2025-07-28 | 751013.23 | 488997 | -262016.23 | 262016.23 | 1 | 2025-08-28 | 2 | 922469.15 | -171455.92 | DOWN | 0.2283 | 31 | Low | 366735.32 | 0.457 | 3 | 122261.68 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP022 | 2025-08 | 2025-08-07 | 642913.1 | 488997 | -153916.1 | 153916.1 | 1 | 2025-08-28 | 3 | 751013.23 | -108100.13 | DOWN | 0.1681 | 21 | Low | 311489.27 | 0.481 | 4 | 177507.73 | 25 | 1.29 | 1.82
P002 | Software | SUP022 | 2025-09 | 2025-04-07 | 2864023.55 | 1365194 | -1498829.55 | 1498829.55 | 1 | 2025-09-28 | 1 |  |  |  |  | 174 | Low | 338601.35 | 0.11 | 2 | 1026592.65 | 25 | 1.38 | 1.58
P002 | Software | SUP022 | 2025-09 | 2025-04-30 | 2320426.14 | 1365194 | -955232.14 | 955232.14 | 1 | 2025-09-28 | 2 | 2864023.55 | -543597.41 | DOWN | 0.2343 | 151 | Low | 352939.22 | 0.165 | 2 | 1012254.78 | 25 | 1.38 | 1.58
P002 | Software | SUP022 | 2025-09 | 2025-06-14 | 1885116.53 | 1365194 | -519922.53 | 519922.53 | 1 | 2025-09-28 | 3 | 2320426.14 | -435309.61 | DOWN | 0.2309 | 106 | Low | 531886.59 | 0.273 | 0 | 833307.41 | 25 | 1.38 | 1.58
P002 | Software | SUP022 | 2025-09 | 2025-07-11 | 1669227.35 | 1365194 | -304033.35 | 304033.35 | 1 | 2025-09-28 | 4 | 1885116.53 | -215889.18 | DOWN | 0.1293 | 79 | Low | 554869.01 | 0.337 | 3 | 810324.99 | 25 | 1.38 | 1.58
P002 | Software | SUP022 | 2025-09 | 2025-07-23 | 1566841.18 | 1365194 | -201647.18 | 201647.18 | 0 | 2025-09-28 | 5 | 1669227.35 | -102386.17 | DOWN | 0.0653 | 67 | Low | 559047.79 | 0.366 | 3 | 806146.21 | 25 | 1.38 | 1.58
P002 | Services | SUP022 | 2025-10 | 2025-05-24 | 1011953.15 | 505631 | -506322.15 | 506322.15 | 1 | 2025-10-28 | 1 |  |  |  |  | 157 | Low | 150564.63 | 0.144 | 0 | 355066.37 | 21 | 1.76 | 1.29
P002 | Services | SUP022 | 2025-10 | 2025-05-29 | 787113.62 | 505631 | -281482.62 | 281482.62 | 1 | 2025-10-28 | 2 | 1011953.15 | -224839.53 | DOWN | 0.2857 | 152 | Low | 130166.17 | 0.156 | 0 | 375464.83 | 21 | 1.76 | 1.29
P002 | Services | SUP022 | 2025-10 | 2025-06-09 | 667579.02 | 505631 | -161948.02 | 161948.02 | 1 | 2025-10-28 | 3 | 787113.62 | -119534.6 | DOWN | 0.1791 | 141 | Low | 130110.5 | 0.181 | 3 | 375520.5 | 21 | 1.76 | 1.29
P002 | Services | SUP022 | 2025-10 | 2025-09-29 | 599574.23 | 505631 | -93943.23 | 93943.23 | 1 | 2025-10-28 | 4 | 667579.02 | -68004.79 | DOWN | 0.1134 | 29 | Low | 281838.5 | 0.438 | 0 | 223792.5 | 21 | 1.76 | 1.29
P002 | Services | SUP022 | 2025-10 | 2025-10-12 | 574886.46 | 505631 | -69255.46 | 69255.46 | 0 | 2025-10-28 | 5 | 599574.23 | -24687.77 | DOWN | 0.0429 | 16 | Medium | 270073.78 | 0.467 | 4 | 235557.22 | 21 | 1.76 | 1.29
P002 | Software | SUP022 | 2025-11 | 2025-07-17 | 1469100.48 | 673461 | -795639.48 | 795639.48 | 1 | 2025-11-28 | 1 |  |  |  |  | 134 | Low | 313000.24 | 0.201 | 2 | 360460.76 | 26 | 1.59 | 1.38
P002 | Software | SUP022 | 2025-11 | 2025-07-19 | 1175522.01 | 673461 | -502061.01 | 502061.01 | 1 | 2025-11-28 | 2 | 1469100.48 | -293578.47 | DOWN | 0.2497 | 132 | Low | 228802.73 | 0.205 | 2 | 444658.27 | 26 | 1.59 | 1.38
P002 | Software | SUP022 | 2025-11 | 2025-07-19 | 977656.43 | 673461 | -304195.43 | 304195.43 | 1 | 2025-11-28 | 3 | 1175522.01 | -197865.58 | DOWN | 0.2024 | 132 | Low | 211991.46 | 0.205 | 0 | 461469.54 | 26 | 1.59 | 1.38
P002 | Software | SUP022 | 2025-11 | 2025-10-25 | 871611.8 | 673461 | -198150.8 | 198150.8 | 1 | 2025-11-28 | 4 | 977656.43 | -106044.63 | DOWN | 0.1217 | 34 | Low | 401987.77 | 0.434 | 1 | 271473.23 | 26 | 1.59 | 1.38
P002 | Materials | SUP022 | 2025-12 | 2025-07-04 | 4213219.19 | 2016024 | -2197195.19 | 2197195.19 | 1 | 2025-12-28 | 1 |  |  |  |  | 177 | Low | 469085.99 | 0.105 | 0 | 1546938.01 | 27 | 1.43 | 1.4
P002 | Materials | SUP022 | 2025-12 | 2025-10-22 | 3347917.66 | 2016024 | -1331893.66 | 1331893.66 | 1 | 2025-12-28 | 2 | 4213219.19 | -865301.53 | DOWN | 0.2585 | 67 | Low | 1236625.97 | 0.364 | 0 | 779398.03 | 27 | 1.43 | 1.4
P002 | Materials | SUP022 | 2025-12 | 2025-10-27 | 2852464.76 | 2016024 | -836440.76 | 836440.76 | 1 | 2025-12-28 | 3 | 3347917.66 | -495452.9 | DOWN | 0.1737 | 62 | Low | 993057.24 | 0.376 | 1 | 1022966.76 | 27 | 1.43 | 1.4
P002 | Materials | SUP022 | 2025-12 | 2025-10-30 | 2508928.62 | 2016024 | -492904.62 | 492904.62 | 1 | 2025-12-28 | 4 | 2852464.76 | -343536.14 | DOWN | 0.1369 | 59 | Low | 1028643.87 | 0.383 | 3 | 987380.13 | 27 | 1.43 | 1.4
P002 | Software | SUP002 | 2025-01 | 2024-09-22 | 3925492.98 | 1950260 | -1975232.98 | 1975232.98 | 1 | 2025-01-28 | 1 |  |  |  |  | 128 | Low | 1253258.83 | 0.309 | 3 | 697001.17 | 20 | 1.45 | 1.35
P002 | Software | SUP002 | 2025-01 | 2024-10-21 | 2864050.13 | 1950260 | -913790.13 | 913790.13 | 1 | 2025-01-28 | 2 | 3925492.98 | -1061442.85 | DOWN | 0.3706 | 99 | Low | 1118318.63 | 0.407 | 4 | 831941.37 | 20 | 1.45 | 1.35
P002 | Software | SUP002 | 2025-01 | 2024-12-10 | 2354118.21 | 1950260 | -403858.21 | 403858.21 | 1 | 2025-01-28 | 3 | 2864050.13 | -509931.92 | DOWN | 0.2166 | 49 | Low | 1432335.49 | 0.575 | 1 | 517924.51 | 20 | 1.45 | 1.35
P002 | Software | SUP002 | 2025-01 | 2024-12-27 | 2100447.96 | 1950260 | -150187.96 | 150187.96 | 0 | 2025-01-28 | 4 | 2354118.21 | -253670.25 | DOWN | 0.1208 | 32 | Low | 1321979.96 | 0.632 | 5 | 628280.04 | 20 | 1.45 | 1.35
P002 | Materials | SUP002 | 2025-02 | 2024-09-25 | 2126698.69 | 1397815 | -728883.69 | 728883.69 | 1 | 2025-02-28 | 1 |  |  |  |  | 156 | Low | 478837.3 | 0.217 | 2 | 918977.7 | 23 | 1.4 | 1.5
P002 | Materials | SUP002 | 2025-02 | 2025-01-13 | 1727229.46 | 1397815 | -329414.46 | 329414.46 | 1 | 2025-02-28 | 2 | 2126698.69 | -399469.23 | DOWN | 0.2313 | 46 | Low | 1015528.73 | 0.589 | 4 | 382286.27 | 23 | 1.4 | 1.5
P002 | Materials | SUP002 | 2025-02 | 2025-01-20 | 1546123.33 | 1397815 | -148308.33 | 148308.33 | 0 | 2025-02-28 | 3 | 1727229.46 | -181106.13 | DOWN | 0.1171 | 39 | Medium | 940529.03 | 0.612 | 2 | 457285.97 | 23 | 1.4 | 1.5
P002 | Materials | SUP002 | 2025-02 | 2025-01-20 | 1464070.6 | 1397815 | -66255.6 | 66255.6 | 0 | 2025-02-28 | 4 | 1546123.33 | -82052.73 | DOWN | 0.056 | 39 | Medium | 902423.53 | 0.612 | 3 | 495391.47 | 23 | 1.4 | 1.5
P002 | Materials | SUP002 | 2025-02 | 2025-02-08 | 1423629.71 | 1397815 | -25814.71 | 25814.71 | 0 | 2025-02-28 | 5 | 1464070.6 | -40440.89 | DOWN | 0.0284 | 20 | High | 930303.72 | 0.677 | 4 | 467511.28 | 23 | 1.4 | 1.5
P002 | Materials | SUP002 | 2025-02 | 2025-02-09 | 1401868.21 | 1397815 | -4053.21 | 4053.21 | 0 | 2025-02-28 | 6 | 1423629.71 | -21761.5 | DOWN | 0.0155 | 19 | High | 925983.51 | 0.68 | 4 | 471831.49 | 23 | 1.4 | 1.5
P002 | Logistics | SUP002 | 2025-03 | 2024-11-01 | 306757.46 | 169110 | -137647.46 | 137647.46 | 1 | 2025-03-28 | 1 |  |  |  |  | 147 | Low | 68959.98 | 0.224 | 0 | 100150.02 | 25 | 2.28 | 1.97
P002 | Logistics | SUP002 | 2025-03 | 2024-11-30 | 230200.82 | 169110 | -61090.82 | 61090.82 | 1 | 2025-03-28 | 2 | 306757.46 | -76556.64 | DOWN | 0.3326 | 118 | Low | 69844.1 | 0.313 | 3 | 99265.9 | 25 | 2.28 | 1.97
P002 | Logistics | SUP002 | 2025-03 | 2024-12-25 | 192723.6 | 169110 | -23613.6 | 23613.6 | 0 | 2025-03-28 | 3 | 230200.82 | -37477.22 | DOWN | 0.1945 | 93 | Low | 79591.53 | 0.39 | 2 | 89518.47 | 25 | 2.28 | 1.97
P002 | Logistics | SUP002 | 2025-03 | 2025-02-15 | 179064.59 | 169110 | -9954.59 | 9954.59 | 0 | 2025-03-28 | 4 | 192723.6 | -13659.01 | DOWN | 0.0763 | 41 | Low | 94372.09 | 0.55 | 9 | 74737.91 | 25 | 2.28 | 1.97
P002 | Logistics | SUP002 | 2025-03 | 2025-02-20 | 180661.02 | 169110 | -11551.02 | 11551.02 | 0 | 2025-03-28 | 5 | 179064.59 | 1596.43 | UP | 0.0088 | 36 | Low | 102671.4 | 0.566 | 2 | 66438.6 | 25 | 2.28 | 1.97
P002 | Logistics | SUP002 | 2025-03 | 2025-03-05 | 170315.33 | 169110 | -1205.33 | 1205.33 | 0 | 2025-03-28 | 6 | 180661.02 | -10345.69 | DOWN | 0.0607 | 23 | Low | 105314.47 | 0.605 | 2 | 63795.53 | 25 | 2.28 | 1.97
P002 | Logistics | SUP002 | 2025-04 | 2024-12-22 | 4526908.11 | 2423151 | -2103757.11 | 2103757.11 | 1 | 2025-04-28 | 1 |  |  |  |  | 127 | Low | 1403599.44 | 0.327 | 1 | 1019551.56 | 21 | 1.06 | 1.67
P002 | Logistics | SUP002 | 2025-04 | 2025-02-09 | 3450202.55 | 2423151 | -1027051.55 | 1027051.55 | 1 | 2025-04-28 | 2 | 4526908.11 | -1076705.56 | DOWN | 0.3121 | 78 | Low | 1860416 | 0.5 | 1 | 562735 | 21 | 1.06 | 1.67
P002 | Logistics | SUP002 | 2025-04 | 2025-03-30 | 2831348.15 | 2423151 | -408197.15 | 408197.15 | 0 | 2025-04-28 | 3 | 3450202.55 | -618854.4 | DOWN | 0.2186 | 29 | Low | 1820214.7 | 0.672 | 7 | 602936.3 | 21 | 1.06 | 1.67
P002 | Electronics | SUP002 | 2025-05 | 2024-12-02 | 1353668.05 | 725080 | -628588.05 | 628588.05 | 1 | 2025-05-28 | 1 |  |  |  |  | 177 | Low | 181366.61 | 0.138 | 0 | 543713.39 | 28 | 2.1 | 0.99
P002 | Electronics | SUP002 | 2025-05 | 2024-12-24 | 1000517.15 | 725080 | -275437.15 | 275437.15 | 1 | 2025-05-28 | 2 | 1353668.05 | -353150.9 | DOWN | 0.353 | 155 | Low | 213155.28 | 0.204 | 0 | 511924.72 | 28 | 2.1 | 0.99
P002 | Electronics | SUP002 | 2025-05 | 2025-01-15 | 825014.08 | 725080 | -99934.08 | 99934.08 | 0 | 2025-05-28 | 3 | 1000517.15 | -175503.07 | DOWN | 0.2127 | 133 | Low | 237029.18 | 0.272 | 3 | 488050.82 | 28 | 2.1 | 0.99
P002 | Electronics | SUP002 | 2025-05 | 2025-03-04 | 774036.74 | 725080 | -48956.74 | 48956.74 | 0 | 2025-05-28 | 4 | 825014.08 | -50977.34 | DOWN | 0.0659 | 85 | Low | 330753.1 | 0.423 | 6 | 394326.9 | 28 | 2.1 | 0.99
P002 | Electronics | SUP002 | 2025-05 | 2025-03-12 | 738015.24 | 725080 | -12935.24 | 12935.24 | 0 | 2025-05-28 | 5 | 774036.74 | -36021.5 | DOWN | 0.0488 | 77 | Low | 352270.59 | 0.448 | 2 | 372809.41 | 28 | 2.1 | 0.99
P002 | Electronics | SUP002 | 2025-05 | 2025-04-25 | 736258.55 | 725080 | -11178.55 | 11178.55 | 0 | 2025-05-28 | 6 | 738015.24 | -1756.69 | DOWN | 0.0024 | 33 | Low | 427813.41 | 0.586 | 4 | 297266.59 | 28 | 2.1 | 0.99
P002 | Materials | SUP002 | 2025-06 | 2025-02-27 | 2420223.05 | 1439837 | -980386.05 | 980386.05 | 1 | 2025-06-28 | 1 |  |  |  |  | 121 | Low | 793962.04 | 0.34 | 0 | 645874.96 | 17 | 1.27 | 1.62
P002 | Materials | SUP002 | 2025-06 | 2025-03-16 | 1864038.77 | 1439837 | -424201.77 | 424201.77 | 1 | 2025-06-28 | 2 | 2420223.05 | -556184.28 | DOWN | 0.2984 | 104 | Low | 695076.2 | 0.398 | 0 | 744760.8 | 17 | 1.27 | 1.62
P002 | Materials | SUP002 | 2025-06 | 2025-03-20 | 1639742.28 | 1439837 | -199905.28 | 199905.28 | 0 | 2025-06-28 | 3 | 1864038.77 | -224296.49 | DOWN | 0.1368 | 100 | Low | 720896 | 0.412 | 0 | 718941 | 17 | 1.27 | 1.62
P002 | Materials | SUP002 | 2025-07 | 2025-03-02 | 3921310.61 | 2193214 | -1728096.61 | 1728096.61 | 1 | 2025-07-28 | 1 |  |  |  |  | 148 | Low | 901233.76 | 0.241 | 4 | 1291980.24 | 24 | 1.49 | 1.96
P002 | Materials | SUP002 | 2025-07 | 2025-05-08 | 2984843.92 | 2193214 | -791629.92 | 791629.92 | 1 | 2025-07-28 | 2 | 3921310.61 | -936466.69 | DOWN | 0.3137 | 81 | Low | 1346227.06 | 0.465 | 3 | 846986.94 | 24 | 1.49 | 1.96
P002 | Materials | SUP002 | 2025-07 | 2025-05-25 | 2516160.66 | 2193214 | -322946.66 | 322946.66 | 0 | 2025-07-28 | 3 | 2984843.92 | -468683.26 | DOWN | 0.1863 | 64 | Low | 1212748.14 | 0.522 | 3 | 980465.86 | 24 | 1.49 | 1.96
P002 | Materials | SUP002 | 2025-07 | 2025-07-07 | 2355321.76 | 2193214 | -162107.76 | 162107.76 | 0 | 2025-07-28 | 4 | 2516160.66 | -160838.9 | DOWN | 0.0683 | 21 | Medium | 1689831.42 | 0.666 | 5 | 503382.58 | 24 | 1.49 | 1.96
P002 | Materials | SUP002 | 2025-07 | 2025-07-18 | 2246204.38 | 2193214 | -52990.38 | 52990.38 | 0 | 2025-07-28 | 5 | 2355321.76 | -109117.38 | DOWN | 0.0486 | 10 | Medium | 1664516.17 | 0.7 | 7 | 528697.83 | 24 | 1.49 | 1.96
P002 | Logistics | SUP002 | 2025-08 | 2025-04-11 | 1317035.1 | 635200 | -681835.1 | 681835.1 | 1 | 2025-08-28 | 1 |  |  |  |  | 139 | Low | 344966.58 | 0.278 | 3 | 290233.42 | 25 | 1.29 | 1.82
P002 | Logistics | SUP002 | 2025-08 | 2025-04-23 | 952825.73 | 635200 | -317625.73 | 317625.73 | 1 | 2025-08-28 | 2 | 1317035.1 | -364209.37 | DOWN | 0.3822 | 127 | Low | 321275.43 | 0.319 | 2 | 313924.57 | 25 | 1.29 | 1.82
P002 | Logistics | SUP002 | 2025-08 | 2025-04-26 | 763907.21 | 635200 | -128707.21 | 128707.21 | 1 | 2025-08-28 | 3 | 952825.73 | -188918.52 | DOWN | 0.2473 | 124 | Low | 268855.22 | 0.329 | 3 | 366344.78 | 25 | 1.29 | 1.82
P002 | Logistics | SUP002 | 2025-08 | 2025-08-04 | 690240.93 | 635200 | -55040.93 | 55040.93 | 0 | 2025-08-28 | 4 | 763907.21 | -73666.28 | DOWN | 0.1067 | 24 | Medium | 434856.16 | 0.672 | 5 | 200343.84 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP002 | 2025-09 | 2025-04-19 | 571415.46 | 365096 | -206319.46 | 206319.46 | 1 | 2025-09-28 | 1 |  |  |  |  | 162 | Low | 118272.96 | 0.197 | 0 | 246823.04 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP002 | 2025-09 | 2025-08-17 | 456948.67 | 365096 | -91852.67 | 91852.67 | 1 | 2025-09-28 | 2 | 571415.46 | -114466.79 | DOWN | 0.2505 | 42 | Low | 285467.32 | 0.604 | 5 | 79628.68 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP002 | 2025-09 | 2025-08-19 | 406041.49 | 365096 | -40945.49 | 40945.49 | 0 | 2025-09-28 | 3 | 456948.67 | -50907.18 | DOWN | 0.1254 | 40 | Low | 262510.25 | 0.61 | 2 | 102585.75 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP002 | 2025-09 | 2025-09-05 | 380234.25 | 365096 | -15138.25 | 15138.25 | 0 | 2025-09-28 | 4 | 406041.49 | -25807.24 | DOWN | 0.0679 | 23 | Medium | 272405.76 | 0.668 | 7 | 92690.24 | 25 | 1.38 | 1.58
P002 | Logistics | SUP002 | 2025-10 | 2025-05-31 | 1181845.79 | 618166 | -563679.79 | 563679.79 | 1 | 2025-10-28 | 1 |  |  |  |  | 150 | Low | 283102.76 | 0.227 | 0 | 335063.24 | 21 | 1.76 | 1.29
P002 | Logistics | SUP002 | 2025-10 | 2025-06-26 | 866344.9 | 618166 | -248178.9 | 248178.9 | 1 | 2025-10-28 | 2 | 1181845.79 | -315500.89 | DOWN | 0.3642 | 124 | Low | 267781.81 | 0.312 | 0 | 350384.19 | 21 | 1.76 | 1.29
P002 | Logistics | SUP002 | 2025-10 | 2025-09-07 | 713365.63 | 618166 | -95199.63 | 95199.63 | 0 | 2025-10-28 | 3 | 866344.9 | -152979.27 | DOWN | 0.2144 | 51 | Low | 388663.36 | 0.549 | 4 | 229502.64 | 21 | 1.76 | 1.29
P002 | Logistics | SUP002 | 2025-10 | 2025-09-22 | 654679.97 | 618166 | -36513.97 | 36513.97 | 0 | 2025-10-28 | 4 | 713365.63 | -58685.66 | DOWN | 0.0896 | 36 | Medium | 360576.67 | 0.598 | 3 | 257589.33 | 21 | 1.76 | 1.29
P002 | Logistics | SUP002 | 2025-10 | 2025-09-29 | 621888.31 | 618166 | -3722.31 | 3722.31 | 0 | 2025-10-28 | 5 | 654679.97 | -32791.66 | DOWN | 0.0527 | 29 | Medium | 403797.92 | 0.621 | 5 | 214368.08 | 21 | 1.76 | 1.29
P002 | Logistics | SUP002 | 2025-10 | 2025-10-17 | 618801.15 | 618166 | -635.15 | 635.15 | 0 | 2025-10-28 | 6 | 621888.31 | -3087.16 | DOWN | 0.005 | 11 | Medium | 406538.47 | 0.679 | 4 | 211627.53 | 21 | 1.76 | 1.29
P002 | Logistics | SUP002 | 2025-11 | 2025-07-15 | 2830628.97 | 1430513 | -1400115.97 | 1400115.97 | 1 | 2025-11-28 | 1 |  |  |  |  | 136 | Low | 775730.63 | 0.278 | 0 | 654782.37 | 26 | 1.59 | 1.38
P002 | Logistics | SUP002 | 2025-11 | 2025-08-28 | 2131329.48 | 1430513 | -700816.48 | 700816.48 | 1 | 2025-11-28 | 2 | 2830628.97 | -699299.49 | DOWN | 0.3281 | 92 | Low | 864163.67 | 0.424 | 5 | 566349.33 | 26 | 1.59 | 1.38
P002 | Logistics | SUP002 | 2025-11 | 2025-08-30 | 1766122.69 | 1430513 | -335609.69 | 335609.69 | 1 | 2025-11-28 | 3 | 2131329.48 | -365206.79 | DOWN | 0.2068 | 90 | Low | 754837.01 | 0.43 | 4 | 675675.99 | 26 | 1.59 | 1.38
P002 | Logistics | SUP002 | 2025-11 | 2025-09-11 | 1616329.99 | 1430513 | -185816.99 | 185816.99 | 0 | 2025-11-28 | 4 | 1766122.69 | -149792.7 | DOWN | 0.0927 | 78 | Low | 723580.83 | 0.47 | 3 | 706932.17 | 26 | 1.59 | 1.38
P002 | Logistics | SUP002 | 2025-11 | 2025-09-12 | 1526037.47 | 1430513 | -95524.47 | 95524.47 | 0 | 2025-11-28 | 5 | 1616329.99 | -90292.52 | DOWN | 0.0592 | 77 | Low | 758235.41 | 0.473 | 3 | 672277.59 | 26 | 1.59 | 1.38
P002 | Electronics | SUP002 | 2025-12 | 2025-07-12 | 5006969.54 | 3010964 | -1996005.54 | 1996005.54 | 1 | 2025-12-28 | 1 |  |  |  |  | 169 | Low | 911822.94 | 0.172 | 5 | 2099141.06 | 27 | 1.43 | 1.4
P002 | Electronics | SUP002 | 2025-12 | 2025-09-19 | 3858551.09 | 3010964 | -847587.09 | 847587.09 | 1 | 2025-12-28 | 2 | 5006969.54 | -1148418.45 | DOWN | 0.2976 | 100 | Low | 1492285.21 | 0.405 | 6 | 1518678.79 | 27 | 1.43 | 1.4
P002 | Electronics | SUP002 | 2025-12 | 2025-11-29 | 3452985.14 | 3010964 | -442021.14 | 442021.14 | 0 | 2025-12-28 | 3 | 3858551.09 | -405565.95 | DOWN | 0.1175 | 29 | Medium | 2055398.23 | 0.644 | 2 | 955565.77 | 27 | 1.43 | 1.4
P002 | Electronics | SUP002 | 2025-12 | 2025-12-06 | 3210002.66 | 3010964 | -199038.66 | 199038.66 | 0 | 2025-12-28 | 4 | 3452985.14 | -242982.48 | DOWN | 0.0757 | 22 | Medium | 2192554.88 | 0.668 | 0 | 818409.12 | 27 | 1.43 | 1.4
P002 | Services | SUP008 | 2025-01 | 2024-10-21 | 3633512.31 | 2193043 | -1440469.31 | 1440469.31 | 1 | 2025-01-28 | 1 |  |  |  |  | 99 | Low | 1405678.27 | 0.407 | 3 | 787364.73 | 20 | 1.45 | 1.35
P002 | Services | SUP008 | 2025-01 | 2024-11-27 | 2817358.87 | 2193043 | -624315.87 | 624315.87 | 1 | 2025-01-28 | 2 | 3633512.31 | -816153.44 | DOWN | 0.2897 | 62 | Low | 1546836.09 | 0.531 | 4 | 646206.91 | 20 | 1.45 | 1.35
P002 | Services | SUP008 | 2025-01 | 2024-12-02 | 2419743.2 | 2193043 | -226700.2 | 226700.2 | 0 | 2025-01-28 | 3 | 2817358.87 | -397615.67 | DOWN | 0.1643 | 57 | Low | 1320480.26 | 0.548 | 4 | 872562.74 | 20 | 1.45 | 1.35
P002 | Services | SUP008 | 2025-01 | 2024-12-03 | 2278805.17 | 2193043 | -85762.17 | 85762.17 | 0 | 2025-01-28 | 4 | 2419743.2 | -140938.03 | DOWN | 0.0618 | 56 | Medium | 1354522.21 | 0.552 | 2 | 838520.79 | 20 | 1.45 | 1.35
P002 | Services | SUP008 | 2025-01 | 2024-12-28 | 2219568.19 | 2193043 | -26525.19 | 26525.19 | 0 | 2025-01-28 | 5 | 2278805.17 | -59236.98 | DOWN | 0.0267 | 31 | Medium | 1473131.65 | 0.636 | 5 | 719911.35 | 20 | 1.45 | 1.35
P002 | Services | SUP008 | 2025-01 | 2025-01-06 | 2181873.06 | 2193043 | 11169.94 | 11169.94 | 0 | 2025-01-28 | 6 | 2219568.19 | -37695.13 | DOWN | 0.0173 | 22 | Medium | 1518312.04 | 0.666 | 0 | 674730.96 | 20 | 1.45 | 1.35
P002 | Services | SUP008 | 2025-02 | 2024-09-27 | 2721112.87 | 1423123 | -1297989.87 | 1297989.87 | 1 | 2025-02-28 | 1 |  |  |  |  | 154 | Low | 588583 | 0.223 | 0 | 834540 | 23 | 1.4 | 1.5
P002 | Services | SUP008 | 2025-02 | 2024-12-03 | 2024848.23 | 1423123 | -601725.23 | 601725.23 | 1 | 2025-02-28 | 2 | 2721112.87 | -696264.64 | DOWN | 0.3439 | 87 | Low | 909418.46 | 0.45 | 0 | 513704.54 | 23 | 1.4 | 1.5
P002 | Services | SUP008 | 2025-02 | 2024-12-17 | 1682553.83 | 1423123 | -259430.83 | 259430.83 | 1 | 2025-02-28 | 3 | 2024848.23 | -342294.4 | DOWN | 0.2034 | 73 | Low | 898986.53 | 0.497 | 8 | 524136.47 | 23 | 1.4 | 1.5
P002 | Services | SUP008 | 2025-02 | 2024-12-27 | 1547312.21 | 1423123 | -124189.21 | 124189.21 | 0 | 2025-02-28 | 4 | 1682553.83 | -135241.62 | DOWN | 0.0874 | 63 | Low | 769137.28 | 0.531 | 4 | 653985.72 | 23 | 1.4 | 1.5
P002 | Services | SUP008 | 2025-02 | 2025-01-25 | 1455743.92 | 1423123 | -32620.92 | 32620.92 | 0 | 2025-02-28 | 5 | 1547312.21 | -91568.29 | DOWN | 0.0629 | 34 | Medium | 985940.41 | 0.629 | 5 | 437182.59 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP008 | 2025-03 | 2024-10-28 | 2755822.77 | 1689282 | -1066540.77 | 1066540.77 | 1 | 2025-03-28 | 1 |  |  |  |  | 151 | Low | 600569.69 | 0.212 | 0 | 1088712.31 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP008 | 2025-03 | 2024-12-31 | 2217452.78 | 1689282 | -528170.78 | 528170.78 | 1 | 2025-03-28 | 2 | 2755822.77 | -538369.99 | DOWN | 0.2428 | 87 | Low | 935037.99 | 0.409 | 2 | 754244.01 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP008 | 2025-03 | 2025-02-15 | 1918534.18 | 1689282 | -229252.18 | 229252.18 | 0 | 2025-03-28 | 3 | 2217452.78 | -298918.6 | DOWN | 0.1558 | 41 | Low | 1027279.89 | 0.55 | 7 | 662002.11 | 25 | 2.28 | 1.97
P002 | Software | SUP008 | 2025-04 | 2024-11-15 | 1552610.87 | 820406 | -732204.87 | 732204.87 | 1 | 2025-04-28 | 1 |  |  |  |  | 164 | Low | 324545.9 | 0.197 | 5 | 495860.1 | 21 | 1.06 | 1.67
P002 | Software | SUP008 | 2025-04 | 2024-11-25 | 1165891.44 | 820406 | -345485.44 | 345485.44 | 1 | 2025-04-28 | 2 | 1552610.87 | -386719.43 | DOWN | 0.3317 | 154 | Low | 270658.67 | 0.232 | 5 | 549747.33 | 21 | 1.06 | 1.67
P002 | Software | SUP008 | 2025-04 | 2025-01-24 | 960890.76 | 820406 | -140484.76 | 140484.76 | 0 | 2025-04-28 | 3 | 1165891.44 | -205000.68 | DOWN | 0.2133 | 94 | Low | 445469.75 | 0.444 | 4 | 374936.25 | 21 | 1.06 | 1.67
P002 | Materials | SUP008 | 2025-05 | 2024-11-29 | 1250889.52 | 620886 | -630003.52 | 630003.52 | 1 | 2025-05-28 | 1 |  |  |  |  | 180 | Low | 165825.15 | 0.138 | 2 | 455060.85 | 28 | 2.1 | 0.99
P002 | Materials | SUP008 | 2025-05 | 2024-12-26 | 892553.5 | 620886 | -271667.5 | 271667.5 | 1 | 2025-05-28 | 2 | 1250889.52 | -358336.02 | DOWN | 0.4015 | 153 | Low | 182269.3 | 0.21 | 2 | 438616.7 | 28 | 2.1 | 0.99
P002 | Materials | SUP008 | 2025-05 | 2025-02-11 | 749401.8 | 620886 | -128515.8 | 128515.8 | 1 | 2025-05-28 | 3 | 892553.5 | -143151.7 | DOWN | 0.191 | 106 | Low | 261825.88 | 0.357 | 0 | 359060.12 | 28 | 2.1 | 0.99
P002 | Materials | SUP008 | 2025-05 | 2025-03-20 | 674340.98 | 620886 | -53454.98 | 53454.98 | 0 | 2025-05-28 | 4 | 749401.8 | -75060.82 | DOWN | 0.1113 | 69 | Low | 298891.35 | 0.473 | 2 | 321994.65 | 28 | 2.1 | 0.99
P002 | Materials | SUP008 | 2025-05 | 2025-03-21 | 650619.93 | 620886 | -29733.93 | 29733.93 | 0 | 2025-05-28 | 5 | 674340.98 | -23721.05 | DOWN | 0.0365 | 68 | Low | 320553.64 | 0.476 | 0 | 300332.36 | 28 | 2.1 | 0.99
P002 | Materials | SUP008 | 2025-05 | 2025-05-17 | 650188.28 | 620886 | -29302.28 | 29302.28 | 0 | 2025-05-28 | 6 | 650619.93 | -431.65 | DOWN | 0.0007 | 11 | Low | 451472.05 | 0.655 | 9 | 169413.95 | 28 | 2.1 | 0.99
P002 | Software | SUP008 | 2025-06 | 2025-01-30 | 4676095.08 | 2604567 | -2071528.08 | 2071528.08 | 1 | 2025-06-28 | 1 |  |  |  |  | 149 | Low | 1173963.6 | 0.244 | 0 | 1430603.4 | 17 | 1.27 | 1.62
P002 | Software | SUP008 | 2025-06 | 2025-02-16 | 3448624.06 | 2604567 | -844057.06 | 844057.06 | 1 | 2025-06-28 | 2 | 4676095.08 | -1227471.02 | DOWN | 0.3559 | 132 | Low | 988649.48 | 0.302 | 1 | 1615917.52 | 17 | 1.27 | 1.62
P002 | Software | SUP008 | 2025-06 | 2025-03-31 | 3033288.22 | 2604567 | -428721.22 | 428721.22 | 0 | 2025-06-28 | 3 | 3448624.06 | -415335.84 | DOWN | 0.1369 | 89 | Low | 1331788.99 | 0.45 | 3 | 1272778.01 | 17 | 1.27 | 1.62
P002 | Software | SUP008 | 2025-06 | 2025-04-16 | 2791788.31 | 2604567 | -187221.31 | 187221.31 | 0 | 2025-06-28 | 4 | 3033288.22 | -241499.91 | DOWN | 0.0865 | 73 | Low | 1330196.96 | 0.505 | 2 | 1274370.04 | 17 | 1.27 | 1.62
P002 | Services | SUP008 | 2025-07 | 2025-02-08 | 4918809.47 | 2492804 | -2426005.47 | 2426005.47 | 1 | 2025-07-28 | 1 |  |  |  |  | 170 | Low | 780457.17 | 0.167 | 2 | 1712346.83 | 24 | 1.49 | 1.96
P002 | Services | SUP008 | 2025-07 | 2025-03-26 | 3604623.08 | 2492804 | -1111819.08 | 1111819.08 | 1 | 2025-07-28 | 2 | 4918809.47 | -1314186.39 | DOWN | 0.3646 | 124 | Low | 1138533.57 | 0.321 | 3 | 1354270.43 | 24 | 1.49 | 1.96
P002 | Services | SUP008 | 2025-07 | 2025-04-07 | 3004225.03 | 2492804 | -511421.03 | 511421.03 | 1 | 2025-07-28 | 3 | 3604623.08 | -600398.05 | DOWN | 0.1999 | 112 | Low | 1152729.67 | 0.362 | 1 | 1340074.33 | 24 | 1.49 | 1.96
P002 | Services | SUP008 | 2025-07 | 2025-04-24 | 2688725.71 | 2492804 | -195921.71 | 195921.71 | 0 | 2025-07-28 | 4 | 3004225.03 | -315499.32 | DOWN | 0.1173 | 95 | Low | 1110176.76 | 0.419 | 4 | 1382627.24 | 24 | 1.49 | 1.96
P002 | Logistics | SUP008 | 2025-08 | 2025-03-03 | 843065.27 | 492442 | -350623.27 | 350623.27 | 1 | 2025-08-28 | 1 |  |  |  |  | 178 | Low | 123278.9 | 0.151 | 1 | 369163.1 | 25 | 1.29 | 1.82
P002 | Logistics | SUP008 | 2025-08 | 2025-05-09 | 659999.15 | 492442 | -167557.15 | 167557.15 | 1 | 2025-08-28 | 2 | 843065.27 | -183066.12 | DOWN | 0.2774 | 111 | Low | 229409.28 | 0.373 | 0 | 263032.72 | 25 | 1.29 | 1.82
P002 | Logistics | SUP008 | 2025-08 | 2025-05-10 | 573022.9 | 492442 | -80580.9 | 80580.9 | 0 | 2025-08-28 | 3 | 659999.15 | -86976.25 | DOWN | 0.1518 | 110 | Low | 199825.8 | 0.377 | 3 | 292616.2 | 25 | 1.29 | 1.82
P002 | Logistics | SUP008 | 2025-08 | 2025-05-13 | 540812.76 | 492442 | -48370.76 | 48370.76 | 0 | 2025-08-28 | 4 | 573022.9 | -32210.14 | DOWN | 0.0596 | 107 | Low | 210766.58 | 0.387 | 3 | 281675.42 | 25 | 1.29 | 1.82
P002 | Logistics | SUP008 | 2025-08 | 2025-08-01 | 518648.85 | 492442 | -26206.85 | 26206.85 | 0 | 2025-08-28 | 5 | 540812.76 | -22163.91 | DOWN | 0.0427 | 27 | High | 368952.82 | 0.661 | 6 | 123489.18 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP008 | 2025-09 | 2025-04-12 | 1760790.3 | 1157893 | -602897.3 | 602897.3 | 1 | 2025-09-28 | 1 |  |  |  |  | 169 | Low | 302473.7 | 0.173 | 0 | 855419.3 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP008 | 2025-09 | 2025-05-10 | 1422329.28 | 1157893 | -264436.28 | 264436.28 | 1 | 2025-09-28 | 2 | 1760790.3 | -338461.02 | DOWN | 0.238 | 141 | Low | 377795.5 | 0.268 | 2 | 780097.5 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP008 | 2025-09 | 2025-05-26 | 1281489.25 | 1157893 | -123596.25 | 123596.25 | 0 | 2025-09-28 | 3 | 1422329.28 | -140840.03 | DOWN | 0.1099 | 125 | Low | 413816.88 | 0.322 | 1 | 744076.12 | 25 | 1.38 | 1.58
P002 | Mechanical | SUP008 | 2025-09 | 2025-07-24 | 1208533.77 | 1157893 | -50640.77 | 50640.77 | 0 | 2025-09-28 | 4 | 1281489.25 | -72955.48 | DOWN | 0.0604 | 66 | Low | 632228.37 | 0.522 | 5 | 525664.63 | 25 | 1.38 | 1.58
P002 | Electronics | SUP008 | 2025-10 | 2025-05-26 | 2174046.71 | 1329184 | -844862.71 | 844862.71 | 1 | 2025-10-28 | 1 |  |  |  |  | 155 | Low | 465191.68 | 0.211 | 3 | 863992.32 | 21 | 1.76 | 1.29
P002 | Electronics | SUP008 | 2025-10 | 2025-06-04 | 1709470.06 | 1329184 | -380286.06 | 380286.06 | 1 | 2025-10-28 | 2 | 2174046.71 | -464576.65 | DOWN | 0.2718 | 146 | Low | 439529.25 | 0.24 | 2 | 889654.75 | 21 | 1.76 | 1.29
P002 | Electronics | SUP008 | 2025-10 | 2025-06-16 | 1479793.11 | 1329184 | -150609.11 | 150609.11 | 0 | 2025-10-28 | 3 | 1709470.06 | -229676.95 | DOWN | 0.1552 | 134 | Low | 425607.76 | 0.279 | 0 | 903576.24 | 21 | 1.76 | 1.29
P002 | Electronics | SUP008 | 2025-10 | 2025-06-21 | 1409852.39 | 1329184 | -80668.39 | 80668.39 | 0 | 2025-10-28 | 4 | 1479793.11 | -69940.72 | DOWN | 0.0496 | 129 | Low | 437349.57 | 0.296 | 1 | 891834.43 | 21 | 1.76 | 1.29
P002 | Electronics | SUP008 | 2025-10 | 2025-08-03 | 1345263.07 | 1329184 | -16079.07 | 16079.07 | 0 | 2025-10-28 | 5 | 1409852.39 | -64589.32 | DOWN | 0.048 | 86 | Low | 625699.88 | 0.435 | 0 | 703484.12 | 21 | 1.76 | 1.29
P002 | Software | SUP008 | 2025-11 | 2025-06-04 | 4565461.4 | 2275312 | -2290149.4 | 2290149.4 | 1 | 2025-11-28 | 1 |  |  |  |  | 177 | Low | 702137.35 | 0.146 | 3 | 1573174.65 | 26 | 1.59 | 1.38
P002 | Software | SUP008 | 2025-11 | 2025-07-08 | 3387442.94 | 2275312 | -1112130.94 | 1112130.94 | 1 | 2025-11-28 | 2 | 4565461.4 | -1178018.46 | DOWN | 0.3478 | 143 | Low | 907607.82 | 0.255 | 4 | 1367704.18 | 26 | 1.59 | 1.38
P002 | Software | SUP008 | 2025-11 | 2025-08-11 | 2742922.5 | 2275312 | -467610.5 | 467610.5 | 1 | 2025-11-28 | 3 | 3387442.94 | -644520.44 | DOWN | 0.235 | 109 | Low | 950130.41 | 0.368 | 2 | 1325181.59 | 26 | 1.59 | 1.38
P002 | Software | SUP008 | 2025-11 | 2025-08-20 | 2413303.99 | 2275312 | -137991.99 | 137991.99 | 0 | 2025-11-28 | 4 | 2742922.5 | -329618.51 | DOWN | 0.1366 | 100 | Low | 976450.3 | 0.397 | 1 | 1298861.7 | 26 | 1.59 | 1.38
P002 | Electronics | SUP008 | 2025-12 | 2025-07-26 | 2433649.66 | 1251732 | -1181917.66 | 1181917.66 | 1 | 2025-12-28 | 1 |  |  |  |  | 155 | Low | 549429.97 | 0.219 | 3 | 702302.03 | 27 | 1.43 | 1.4
P002 | Electronics | SUP008 | 2025-12 | 2025-08-21 | 1757095.95 | 1251732 | -505363.95 | 505363.95 | 1 | 2025-12-28 | 2 | 2433649.66 | -676553.71 | DOWN | 0.385 | 129 | Low | 550820.89 | 0.307 | 0 | 700911.11 | 27 | 1.43 | 1.4
P002 | Electronics | SUP008 | 2025-12 | 2025-09-17 | 1473685.28 | 1251732 | -221953.28 | 221953.28 | 1 | 2025-12-28 | 3 | 1757095.95 | -283410.67 | DOWN | 0.1923 | 102 | Low | 578298.45 | 0.398 | 6 | 673433.55 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP048 | 2025-01 | 2024-08-05 | 2394188.43 | 1155210 | -1238978.43 | 1238978.43 | 1 | 2025-01-28 | 1 |  |  |  |  | 176 | Low | 217840.2 | 0.095 | 0 | 937369.8 | 20 | 1.45 | 1.35
P002 | Mechanical | SUP048 | 2025-01 | 2024-11-05 | 2096129.92 | 1155210 | -940919.92 | 940919.92 | 1 | 2025-01-28 | 2 | 2394188.43 | -298058.51 | DOWN | 0.1422 | 84 | Low | 576696.43 | 0.293 | 6 | 578513.57 | 20 | 1.45 | 1.35
P002 | Mechanical | SUP048 | 2025-01 | 2024-12-26 | 1863241.71 | 1155210 | -708031.71 | 708031.71 | 1 | 2025-01-28 | 3 | 2096129.92 | -232888.21 | DOWN | 0.125 | 33 | Low | 707242.75 | 0.403 | 1 | 447967.25 | 20 | 1.45 | 1.35
P002 | Services | SUP048 | 2025-02 | 2024-09-03 | 2493568.46 | 1006197 | -1487371.46 | 1487371.46 | 1 | 2025-02-28 | 1 |  |  |  |  | 178 | Low | 255524.44 | 0.095 | 4 | 750672.56 | 23 | 1.4 | 1.5
P002 | Services | SUP048 | 2025-02 | 2024-11-09 | 2162474.3 | 1006197 | -1156277.3 | 1156277.3 | 1 | 2025-02-28 | 2 | 2493568.46 | -331094.16 | DOWN | 0.1531 | 111 | Low | 518592.56 | 0.236 | 3 | 487604.44 | 23 | 1.4 | 1.5
P002 | Services | SUP048 | 2025-02 | 2025-02-02 | 1874890.35 | 1006197 | -868693.35 | 868693.35 | 1 | 2025-02-28 | 3 | 2162474.3 | -287583.95 | DOWN | 0.1534 | 26 | Low | 749518.67 | 0.421 | 0 | 256678.33 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP048 | 2025-03 | 2024-11-05 | 3471984.84 | 1731352 | -1740632.84 | 1740632.84 | 1 | 2025-03-28 | 1 |  |  |  |  | 143 | Low | 499136.72 | 0.152 | 1 | 1232215.28 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP048 | 2025-03 | 2024-11-14 | 2992690.26 | 1731352 | -1261338.26 | 1261338.26 | 1 | 2025-03-28 | 2 | 3471984.84 | -479294.58 | DOWN | 0.1602 | 134 | Low | 496308.64 | 0.169 | 0 | 1235043.36 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP048 | 2025-03 | 2025-01-13 | 2648024.18 | 1731352 | -916672.18 | 916672.18 | 1 | 2025-03-28 | 3 | 2992690.26 | -344666.08 | DOWN | 0.1302 | 74 | Low | 767759.97 | 0.288 | 0 | 963592.03 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP048 | 2025-03 | 2025-02-25 | 2390177.36 | 1731352 | -658825.36 | 658825.36 | 1 | 2025-03-28 | 4 | 2648024.18 | -257846.82 | DOWN | 0.1079 | 31 | Low | 927513.88 | 0.372 | 1 | 803838.12 | 25 | 2.28 | 1.97
P002 | Services | SUP048 | 2025-04 | 2024-11-09 | 5907773.2 | 2246051 | -3661722.2 | 3661722.2 | 1 | 2025-04-28 | 1 |  |  |  |  | 170 | Low | 631229.14 | 0.113 | 2 | 1614821.86 | 21 | 1.06 | 1.67
P002 | Services | SUP048 | 2025-04 | 2025-01-26 | 5070824.15 | 2246051 | -2824773.15 | 2824773.15 | 1 | 2025-04-28 | 2 | 5907773.2 | -836949.05 | DOWN | 0.1651 | 92 | Low | 1543660.94 | 0.289 | 4 | 702390.06 | 21 | 1.06 | 1.67
P002 | Services | SUP048 | 2025-04 | 2025-02-25 | 4382779.66 | 2246051 | -2136728.66 | 2136728.66 | 1 | 2025-04-28 | 3 | 5070824.15 | -688044.49 | DOWN | 0.157 | 62 | Low | 1525203.21 | 0.357 | 4 | 720847.79 | 21 | 1.06 | 1.67
P002 | Materials | SUP048 | 2025-05 | 2024-12-30 | 2206378.53 | 1071318 | -1135060.53 | 1135060.53 | 1 | 2025-05-28 | 1 |  |  |  |  | 149 | Low | 299592.26 | 0.143 | 1 | 771725.74 | 28 | 2.1 | 0.99
P002 | Materials | SUP048 | 2025-05 | 2025-02-16 | 1937523.33 | 1071318 | -866205.33 | 866205.33 | 1 | 2025-05-28 | 2 | 2206378.53 | -268855.2 | DOWN | 0.1388 | 101 | Low | 496904.37 | 0.239 | 6 | 574413.63 | 28 | 2.1 | 0.99
P002 | Materials | SUP048 | 2025-05 | 2025-03-05 | 1675209.53 | 1071318 | -603891.53 | 603891.53 | 1 | 2025-05-28 | 3 | 1937523.33 | -262313.8 | DOWN | 0.1566 | 84 | Low | 471738.88 | 0.273 | 0 | 599579.12 | 28 | 2.1 | 0.99
P002 | Materials | SUP048 | 2025-05 | 2025-05-04 | 1531301.17 | 1071318 | -459983.17 | 459983.17 | 1 | 2025-05-28 | 4 | 1675209.53 | -143908.36 | DOWN | 0.094 | 24 | Low | 601709 | 0.394 | 2 | 469609 | 28 | 2.1 | 0.99
P002 | Logistics | SUP048 | 2025-06 | 2025-01-04 | 5218336.86 | 2146211 | -3072125.86 | 3072125.86 | 1 | 2025-06-28 | 1 |  |  |  |  | 175 | Low | 536522.79 | 0.099 | 3 | 1609688.21 | 17 | 1.27 | 1.62
P002 | Logistics | SUP048 | 2025-06 | 2025-01-09 | 4405235.6 | 2146211 | -2259024.6 | 2259024.6 | 1 | 2025-06-28 | 2 | 5218336.86 | -813101.26 | DOWN | 0.1846 | 170 | Low | 515980 | 0.11 | 1 | 1630231 | 17 | 1.27 | 1.62
P002 | Logistics | SUP048 | 2025-06 | 2025-01-13 | 3893342.38 | 2146211 | -1747131.38 | 1747131.38 | 1 | 2025-06-28 | 3 | 4405235.6 | -511893.22 | DOWN | 0.1315 | 166 | Low | 490643.8 | 0.119 | 0 | 1655567.2 | 17 | 1.27 | 1.62
P002 | Logistics | SUP048 | 2025-06 | 2025-04-27 | 3439455.98 | 2146211 | -1293244.98 | 1293244.98 | 1 | 2025-06-28 | 4 | 3893342.38 | -453886.4 | DOWN | 0.132 | 62 | Low | 1227207.16 | 0.348 | 0 | 919003.84 | 17 | 1.27 | 1.62
P002 | Logistics | SUP048 | 2025-06 | 2025-05-04 | 3161547.8 | 2146211 | -1015336.8 | 1015336.8 | 1 | 2025-06-28 | 5 | 3439455.98 | -277908.18 | DOWN | 0.0879 | 55 | Low | 1239410.85 | 0.363 | 1 | 906800.15 | 17 | 1.27 | 1.62
P002 | Logistics | SUP048 | 2025-06 | 2025-05-04 | 2894398.57 | 2146211 | -748187.57 | 748187.57 | 1 | 2025-06-28 | 6 | 3161547.8 | -267149.23 | DOWN | 0.0923 | 55 | Low | 1080023.41 | 0.363 | 2 | 1066187.59 | 17 | 1.27 | 1.62
P002 | Services | SUP048 | 2025-07 | 2025-04-03 | 2104997.93 | 782849 | -1322148.93 | 1322148.93 | 1 | 2025-07-28 | 1 |  |  |  |  | 116 | Low | 448503.62 | 0.223 | 1 | 334345.38 | 24 | 1.49 | 1.96
P002 | Services | SUP048 | 2025-07 | 2025-05-25 | 1777577.98 | 782849 | -994728.98 | 994728.98 | 1 | 2025-07-28 | 2 | 2104997.93 | -327419.95 | DOWN | 0.1842 | 64 | Low | 572746.37 | 0.335 | 1 | 210102.63 | 24 | 1.49 | 1.96
P002 | Services | SUP048 | 2025-07 | 2025-06-28 | 1543079.3 | 782849 | -760230.3 | 760230.3 | 1 | 2025-07-28 | 3 | 1777577.98 | -234498.68 | DOWN | 0.152 | 30 | Low | 582226.14 | 0.408 | 4 | 200622.86 | 24 | 1.49 | 1.96
P002 | Services | SUP048 | 2025-07 | 2025-07-02 | 1317186.41 | 782849 | -534337.41 | 534337.41 | 1 | 2025-07-28 | 4 | 1543079.3 | -225892.89 | DOWN | 0.1715 | 26 | Low | 538215.29 | 0.416 | 1 | 244633.71 | 24 | 1.49 | 1.96
P002 | Services | SUP048 | 2025-08 | 2025-03-03 | 2788166.95 | 1305089 | -1483077.95 | 1483077.95 | 1 | 2025-08-28 | 1 |  |  |  |  | 178 | Low | 280425.91 | 0.097 | 2 | 1024663.09 | 25 | 1.29 | 1.82
P002 | Services | SUP048 | 2025-08 | 2025-05-28 | 2446284.22 | 1305089 | -1141195.22 | 1141195.22 | 1 | 2025-08-28 | 2 | 2788166.95 | -341882.73 | DOWN | 0.1398 | 92 | Low | 675868.37 | 0.281 | 2 | 629220.63 | 25 | 1.29 | 1.82
P002 | Services | SUP048 | 2025-08 | 2025-06-15 | 2136540.17 | 1305089 | -831451.17 | 831451.17 | 1 | 2025-08-28 | 3 | 2446284.22 | -309744.05 | DOWN | 0.145 | 74 | Low | 704044.64 | 0.321 | 1 | 601044.36 | 25 | 1.29 | 1.82
P002 | Services | SUP048 | 2025-08 | 2025-08-05 | 1947455.15 | 1305089 | -642366.15 | 642366.15 | 1 | 2025-08-28 | 4 | 2136540.17 | -189085.02 | DOWN | 0.0971 | 23 | Low | 807511.54 | 0.433 | 2 | 497577.46 | 25 | 1.29 | 1.82
P002 | Services | SUP048 | 2025-08 | 2025-08-17 | 1764642.78 | 1305089 | -459553.78 | 459553.78 | 1 | 2025-08-28 | 5 | 1947455.15 | -182812.37 | DOWN | 0.1036 | 11 | Medium | 748615.4 | 0.459 | 4 | 556473.6 | 25 | 1.29 | 1.82
P002 | Services | SUP048 | 2025-09 | 2025-04-17 | 2293503.4 | 1005812 | -1287691.4 | 1287691.4 | 1 | 2025-09-28 | 1 |  |  |  |  | 164 | Low | 283053 | 0.122 | 0 | 722759 | 25 | 1.38 | 1.58
P002 | Services | SUP048 | 2025-09 | 2025-06-14 | 1935912.85 | 1005812 | -930100.85 | 930100.85 | 1 | 2025-09-28 | 2 | 2293503.4 | -357590.55 | DOWN | 0.1847 | 106 | Low | 450831.5 | 0.248 | 0 | 554980.5 | 25 | 1.38 | 1.58
P002 | Services | SUP048 | 2025-09 | 2025-07-02 | 1701778.73 | 1005812 | -695966.73 | 695966.73 | 1 | 2025-09-28 | 3 | 1935912.85 | -234134.12 | DOWN | 0.1376 | 88 | Low | 452777.43 | 0.287 | 2 | 553034.57 | 25 | 1.38 | 1.58
P002 | Services | SUP048 | 2025-09 | 2025-08-17 | 1546867.02 | 1005812 | -541055.02 | 541055.02 | 1 | 2025-09-28 | 4 | 1701778.73 | -154911.71 | DOWN | 0.1001 | 42 | Low | 605581.38 | 0.387 | 5 | 400230.62 | 25 | 1.38 | 1.58
P002 | Materials | SUP048 | 2025-10 | 2025-05-17 | 4453764.82 | 2210291 | -2243473.82 | 2243473.82 | 1 | 2025-10-28 | 1 |  |  |  |  | 164 | Low | 486836.88 | 0.117 | 6 | 1723454.12 | 21 | 1.76 | 1.29
P002 | Materials | SUP048 | 2025-10 | 2025-08-10 | 3882987.72 | 2210291 | -1672696.72 | 1672696.72 | 1 | 2025-10-28 | 2 | 4453764.82 | -570777.1 | DOWN | 0.147 | 79 | Low | 1136315.21 | 0.294 | 1 | 1073975.79 | 21 | 1.76 | 1.29
P002 | Materials | SUP048 | 2025-10 | 2025-09-04 | 3462544.61 | 2210291 | -1252253.61 | 1252253.61 | 1 | 2025-10-28 | 3 | 3882987.72 | -420443.11 | DOWN | 0.1214 | 54 | Low | 1261018.47 | 0.346 | 0 | 949272.53 | 21 | 1.76 | 1.29
P002 | Materials | SUP048 | 2025-10 | 2025-09-25 | 3148959.99 | 2210291 | -938668.99 | 938668.99 | 1 | 2025-10-28 | 4 | 3462544.61 | -313584.62 | DOWN | 0.0996 | 33 | Low | 1240379.75 | 0.389 | 1 | 969911.25 | 21 | 1.76 | 1.29
P002 | Materials | SUP048 | 2025-10 | 2025-09-28 | 2944334.48 | 2210291 | -734043.48 | 734043.48 | 1 | 2025-10-28 | 5 | 3148959.99 | -204625.51 | DOWN | 0.0695 | 30 | Low | 1087861.46 | 0.396 | 1 | 1122429.54 | 21 | 1.76 | 1.29
P002 | Materials | SUP048 | 2025-10 | 2025-10-02 | 2793813.01 | 2210291 | -583522.01 | 583522.01 | 1 | 2025-10-28 | 6 | 2944334.48 | -150521.47 | DOWN | 0.0539 | 26 | Low | 1132531.79 | 0.404 | 0 | 1077759.21 | 21 | 1.76 | 1.29
P002 | Materials | SUP048 | 2025-11 | 2025-06-01 | 3166588.77 | 1429024 | -1737564.77 | 1737564.77 | 1 | 2025-11-28 | 1 |  |  |  |  | 180 | Low | 311734.2 | 0.093 | 0 | 1117289.8 | 26 | 1.59 | 1.38
P002 | Materials | SUP048 | 2025-11 | 2025-06-05 | 2682035.87 | 1429024 | -1253011.87 | 1253011.87 | 1 | 2025-11-28 | 2 | 3166588.77 | -484552.9 | DOWN | 0.1807 | 176 | Low | 240011.81 | 0.093 | 0 | 1189012.19 | 26 | 1.59 | 1.38
P002 | Materials | SUP048 | 2025-11 | 2025-06-26 | 2365360.41 | 1429024 | -936336.41 | 936336.41 | 1 | 2025-11-28 | 3 | 2682035.87 | -316675.46 | DOWN | 0.1339 | 155 | Low | 330853.95 | 0.138 | 2 | 1098170.05 | 26 | 1.59 | 1.38
P002 | Materials | SUP048 | 2025-11 | 2025-10-01 | 2106160.74 | 1429024 | -677136.74 | 677136.74 | 1 | 2025-11-28 | 4 | 2365360.41 | -259199.67 | DOWN | 0.1231 | 58 | Low | 688869.48 | 0.344 | 0 | 740154.52 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP048 | 2025-12 | 2025-07-08 | 3339884.96 | 1389738 | -1950146.96 | 1950146.96 | 1 | 2025-12-28 | 1 |  |  |  |  | 173 | Low | 363387.36 | 0.102 | 0 | 1026350.64 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP048 | 2025-12 | 2025-08-21 | 2876114.2 | 1389738 | -1486376.2 | 1486376.2 | 1 | 2025-12-28 | 2 | 3339884.96 | -463770.76 | DOWN | 0.1612 | 129 | Low | 568956.64 | 0.197 | 0 | 820781.36 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP048 | 2025-12 | 2025-09-24 | 2500268.58 | 1389738 | -1110530.58 | 1110530.58 | 1 | 2025-12-28 | 3 | 2876114.2 | -375845.62 | DOWN | 0.1503 | 95 | Low | 657952.36 | 0.27 | 2 | 731785.64 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP048 | 2025-12 | 2025-10-27 | 2229737.14 | 1389738 | -839999.14 | 839999.14 | 1 | 2025-12-28 | 4 | 2500268.58 | -270531.44 | DOWN | 0.1213 | 62 | Low | 782206.54 | 0.341 | 3 | 607531.46 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP048 | 2025-12 | 2025-12-07 | 2028908.44 | 1389738 | -639170.44 | 639170.44 | 1 | 2025-12-28 | 5 | 2229737.14 | -200828.7 | DOWN | 0.099 | 21 | Low | 899923.18 | 0.43 | 4 | 489814.82 | 27 | 1.43 | 1.4
P002 | Software | SUP046 | 2025-01 | 2024-08-01 | 1512176.37 | 768085 | -744091.37 | 744091.37 | 1 | 2025-01-28 | 1 |  |  |  |  | 180 | Low | 211503.2 | 0.148 | 0 | 556581.8 | 20 | 1.45 | 1.35
P002 | Software | SUP046 | 2025-01 | 2024-09-19 | 1088466.93 | 768085 | -320381.93 | 320381.93 | 1 | 2025-01-28 | 2 | 1512176.37 | -423709.44 | DOWN | 0.3893 | 131 | Low | 301214.04 | 0.299 | 0 | 466870.96 | 20 | 1.45 | 1.35
P002 | Software | SUP046 | 2025-01 | 2024-09-24 | 931784.6 | 768085 | -163699.6 | 163699.6 | 1 | 2025-01-28 | 3 | 1088466.93 | -156682.33 | DOWN | 0.1682 | 126 | Low | 296645.74 | 0.316 | 0 | 471439.26 | 20 | 1.45 | 1.35
P002 | Software | SUP046 | 2025-01 | 2024-10-22 | 854726.03 | 768085 | -86641.03 | 86641.03 | 0 | 2025-01-28 | 4 | 931784.6 | -77058.57 | DOWN | 0.0902 | 98 | Low | 364091.77 | 0.41 | 4 | 403993.23 | 20 | 1.45 | 1.35
P002 | Software | SUP046 | 2025-01 | 2024-11-06 | 801694.94 | 768085 | -33609.94 | 33609.94 | 0 | 2025-01-28 | 5 | 854726.03 | -53031.09 | DOWN | 0.0661 | 83 | Low | 368194.94 | 0.461 | 4 | 399890.06 | 20 | 1.45 | 1.35
P002 | Mechanical | SUP046 | 2025-02 | 2024-10-24 | 4804167.6 | 2794999 | -2009168.6 | 2009168.6 | 1 | 2025-02-28 | 1 |  |  |  |  | 127 | Low | 1433113.69 | 0.315 | 0 | 1361885.31 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP046 | 2025-02 | 2024-11-23 | 3717949.36 | 2794999 | -922950.36 | 922950.36 | 1 | 2025-02-28 | 2 | 4804167.6 | -1086218.24 | DOWN | 0.2922 | 97 | Low | 1494276.55 | 0.416 | 2 | 1300722.45 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP046 | 2025-02 | 2024-12-16 | 3220691.73 | 2794999 | -425692.73 | 425692.73 | 0 | 2025-02-28 | 3 | 3717949.36 | -497257.63 | DOWN | 0.1544 | 74 | Low | 1697750.12 | 0.494 | 5 | 1097248.88 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP046 | 2025-02 | 2025-01-08 | 2952298.45 | 2794999 | -157299.45 | 157299.45 | 0 | 2025-02-28 | 4 | 3220691.73 | -268393.28 | DOWN | 0.0909 | 51 | Medium | 1720647.5 | 0.572 | 3 | 1074351.5 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP046 | 2025-02 | 2025-02-01 | 2846571.6 | 2794999 | -51572.6 | 51572.6 | 0 | 2025-02-28 | 5 | 2952298.45 | -105726.85 | DOWN | 0.0371 | 27 | High | 1882418.52 | 0.653 | 8 | 912580.48 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP046 | 2025-02 | 2025-02-14 | 2804336.45 | 2794999 | -9337.45 | 9337.45 | 0 | 2025-02-28 | 6 | 2846571.6 | -42235.15 | DOWN | 0.0151 | 14 | High | 1831633.22 | 0.697 | 5 | 963365.78 | 23 | 1.4 | 1.5
P002 | Materials | SUP046 | 2025-03 | 2024-10-08 | 4590736.88 | 2247564 | -2343172.88 | 2343172.88 | 1 | 2025-03-28 | 1 |  |  |  |  | 171 | Low | 692124.88 | 0.151 | 1 | 1555439.12 | 25 | 2.28 | 1.97
P002 | Materials | SUP046 | 2025-03 | 2024-12-15 | 3278619.36 | 2247564 | -1031055.36 | 1031055.36 | 1 | 2025-03-28 | 2 | 4590736.88 | -1312117.52 | DOWN | 0.4002 | 103 | Low | 1142714.17 | 0.36 | 2 | 1104849.83 | 25 | 2.28 | 1.97
P002 | Materials | SUP046 | 2025-03 | 2024-12-25 | 2621389.91 | 2247564 | -373825.91 | 373825.91 | 0 | 2025-03-28 | 3 | 3278619.36 | -657229.45 | DOWN | 0.2507 | 93 | Low | 1017310.31 | 0.39 | 3 | 1230253.69 | 25 | 2.28 | 1.97
P002 | Materials | SUP046 | 2025-03 | 2025-01-13 | 2452697.79 | 2247564 | -205133.79 | 205133.79 | 0 | 2025-03-28 | 4 | 2621389.91 | -168692.12 | DOWN | 0.0688 | 74 | Low | 1158699.81 | 0.449 | 4 | 1088864.19 | 25 | 2.28 | 1.97
P002 | Services | SUP046 | 2025-04 | 2024-11-06 | 4418428.48 | 2433097 | -1985331.48 | 1985331.48 | 1 | 2025-04-28 | 1 |  |  |  |  | 173 | Low | 742218.85 | 0.165 | 0 | 1690878.15 | 21 | 1.06 | 1.67
P002 | Services | SUP046 | 2025-04 | 2025-04-05 | 3258033.05 | 2433097 | -824936.05 | 824936.05 | 1 | 2025-04-28 | 2 | 4418428.48 | -1160395.43 | DOWN | 0.3562 | 23 | Low | 2259227.51 | 0.693 | 7 | 173869.49 | 21 | 1.06 | 1.67
P002 | Services | SUP046 | 2025-04 | 2025-04-08 | 2778920.44 | 2433097 | -345823.44 | 345823.44 | 0 | 2025-04-28 | 3 | 3258033.05 | -479112.61 | DOWN | 0.1724 | 20 | Low | 1973613.42 | 0.704 | 7 | 459483.58 | 21 | 1.06 | 1.67
P002 | Logistics | SUP046 | 2025-05 | 2025-01-11 | 2420162.13 | 1119558 | -1300604.13 | 1300604.13 | 1 | 2025-05-28 | 1 |  |  |  |  | 137 | Low | 601538.15 | 0.26 | 0 | 518019.85 | 28 | 2.1 | 0.99
P002 | Logistics | SUP046 | 2025-05 | 2025-02-26 | 1672929.21 | 1119558 | -553371.21 | 553371.21 | 1 | 2025-05-28 | 2 | 2420162.13 | -747232.92 | DOWN | 0.4467 | 91 | Low | 681603.74 | 0.404 | 6 | 437954.26 | 28 | 2.1 | 0.99
P002 | Logistics | SUP046 | 2025-05 | 2025-03-02 | 1344657.93 | 1119558 | -225099.93 | 225099.93 | 1 | 2025-05-28 | 3 | 1672929.21 | -328271.28 | DOWN | 0.2441 | 87 | Low | 592540.83 | 0.417 | 9 | 527017.17 | 28 | 2.1 | 0.99
P002 | Logistics | SUP046 | 2025-05 | 2025-03-17 | 1209973.77 | 1119558 | -90415.77 | 90415.77 | 0 | 2025-05-28 | 4 | 1344657.93 | -134684.16 | DOWN | 0.1113 | 72 | Low | 570529.52 | 0.464 | 4 | 549028.48 | 28 | 2.1 | 0.99
P002 | Logistics | SUP046 | 2025-05 | 2025-03-25 | 1176246.15 | 1119558 | -56688.15 | 56688.15 | 0 | 2025-05-28 | 5 | 1209973.77 | -33727.62 | DOWN | 0.0287 | 64 | Low | 533260.03 | 0.489 | 4 | 586297.97 | 28 | 2.1 | 0.99
P002 | Software | SUP046 | 2025-06 | 2025-01-24 | 4604033.59 | 2499925 | -2104108.59 | 2104108.59 | 1 | 2025-06-28 | 1 |  |  |  |  | 155 | Low | 1098857.61 | 0.223 | 3 | 1401067.39 | 17 | 1.27 | 1.62
P002 | Software | SUP046 | 2025-06 | 2025-03-09 | 3436926.16 | 2499925 | -937001.16 | 937001.16 | 1 | 2025-06-28 | 2 | 4604033.59 | -1167107.43 | DOWN | 0.3396 | 111 | Low | 1317265.03 | 0.374 | 3 | 1182659.97 | 17 | 1.27 | 1.62
P002 | Software | SUP046 | 2025-06 | 2025-04-05 | 2883474.19 | 2499925 | -383549.19 | 383549.19 | 0 | 2025-06-28 | 3 | 3436926.16 | -553451.97 | DOWN | 0.1919 | 84 | Low | 1260029.65 | 0.467 | 2 | 1239895.35 | 17 | 1.27 | 1.62
P002 | Software | SUP046 | 2025-06 | 2025-05-31 | 2696111.01 | 2499925 | -196186.01 | 196186.01 | 0 | 2025-06-28 | 4 | 2883474.19 | -187363.18 | DOWN | 0.0695 | 28 | Medium | 1872894.08 | 0.659 | 2 | 627030.92 | 17 | 1.27 | 1.62
P002 | Software | SUP046 | 2025-06 | 2025-06-16 | 2554117.64 | 2499925 | -54192.64 | 54192.64 | 0 | 2025-06-28 | 5 | 2696111.01 | -141993.37 | DOWN | 0.0556 | 12 | High | 1868494.7 | 0.714 | 5 | 631430.3 | 17 | 1.27 | 1.62
P002 | Logistics | SUP046 | 2025-07 | 2025-03-07 | 6388251.98 | 2818061 | -3570190.98 | 3570190.98 | 1 | 2025-07-28 | 1 |  |  |  |  | 143 | Low | 1699122.11 | 0.258 | 0 | 1118938.89 | 24 | 1.49 | 1.96
P002 | Logistics | SUP046 | 2025-07 | 2025-03-14 | 4259288.57 | 2818061 | -1441227.57 | 1441227.57 | 1 | 2025-07-28 | 2 | 6388251.98 | -2128963.41 | DOWN | 0.4998 | 136 | Low | 1269282.78 | 0.281 | 3 | 1548778.22 | 24 | 1.49 | 1.96
P002 | Logistics | SUP046 | 2025-07 | 2025-05-12 | 3367026.66 | 2818061 | -548965.66 | 548965.66 | 1 | 2025-07-28 | 3 | 4259288.57 | -892261.91 | DOWN | 0.265 | 77 | Low | 1565841.59 | 0.479 | 4 | 1252219.41 | 24 | 1.49 | 1.96
P002 | Logistics | SUP046 | 2025-07 | 2025-05-13 | 2971403.58 | 2818061 | -153342.58 | 153342.58 | 0 | 2025-07-28 | 4 | 3367026.66 | -395623.08 | DOWN | 0.1331 | 76 | Low | 1456093.2 | 0.482 | 4 | 1361967.8 | 24 | 1.49 | 1.96
P002 | Logistics | SUP046 | 2025-07 | 2025-06-19 | 2894982.52 | 2818061 | -76921.52 | 76921.52 | 0 | 2025-07-28 | 5 | 2971403.58 | -76421.06 | DOWN | 0.0264 | 39 | Medium | 1807120.38 | 0.606 | 3 | 1010940.62 | 24 | 1.49 | 1.96
P002 | Logistics | SUP046 | 2025-07 | 2025-07-02 | 2848470 | 2818061 | -30409 | 30409 | 0 | 2025-07-28 | 6 | 2894982.52 | -46512.52 | DOWN | 0.0163 | 26 | Medium | 1920180.99 | 0.65 | 3 | 897880.01 | 24 | 1.49 | 1.96
P002 | Logistics | SUP046 | 2025-08 | 2025-03-21 | 4154397.23 | 2321059 | -1833338.23 | 1833338.23 | 1 | 2025-08-28 | 1 |  |  |  |  | 160 | Low | 843003.64 | 0.206 | 1 | 1478055.36 | 25 | 1.29 | 1.82
P002 | Logistics | SUP046 | 2025-08 | 2025-03-26 | 3090969.13 | 2321059 | -769910.13 | 769910.13 | 1 | 2025-08-28 | 2 | 4154397.23 | -1063428.1 | DOWN | 0.344 | 155 | Low | 648148.33 | 0.223 | 0 | 1672910.67 | 25 | 1.29 | 1.82
P002 | Logistics | SUP046 | 2025-08 | 2025-03-28 | 2651507.32 | 2321059 | -330448.32 | 330448.32 | 0 | 2025-08-28 | 3 | 3090969.13 | -439461.81 | DOWN | 0.1657 | 153 | Low | 624096.15 | 0.23 | 0 | 1696962.85 | 25 | 1.29 | 1.82
P002 | Logistics | SUP046 | 2025-08 | 2025-04-30 | 2440049.94 | 2321059 | -118990.94 | 118990.94 | 0 | 2025-08-28 | 4 | 2651507.32 | -211457.38 | DOWN | 0.0867 | 120 | Low | 848530.92 | 0.343 | 4 | 1472528.08 | 25 | 1.29 | 1.82
P002 | Logistics | SUP046 | 2025-08 | 2025-06-06 | 2411342.63 | 2321059 | -90283.63 | 90283.63 | 0 | 2025-08-28 | 5 | 2440049.94 | -28707.31 | DOWN | 0.0119 | 83 | Low | 1182627.09 | 0.469 | 4 | 1138431.91 | 25 | 1.29 | 1.82
P002 | Logistics | SUP046 | 2025-08 | 2025-07-29 | 2335171.61 | 2321059 | -14112.61 | 14112.61 | 0 | 2025-08-28 | 6 | 2411342.63 | -76171.02 | DOWN | 0.0326 | 30 | High | 1518460.72 | 0.651 | 3 | 802598.28 | 25 | 1.29 | 1.82
P002 | Services | SUP046 | 2025-09 | 2025-05-01 | 1749741.94 | 907601 | -842140.94 | 842140.94 | 1 | 2025-09-28 | 1 |  |  |  |  | 150 | Low | 384673.5 | 0.237 | 1 | 522927.5 | 25 | 1.38 | 1.58
P002 | Services | SUP046 | 2025-09 | 2025-05-08 | 1283532.59 | 907601 | -375931.59 | 375931.59 | 1 | 2025-09-28 | 2 | 1749741.94 | -466209.35 | DOWN | 0.3632 | 143 | Low | 358718.01 | 0.261 | 4 | 548882.99 | 25 | 1.38 | 1.58
P002 | Services | SUP046 | 2025-09 | 2025-06-08 | 1074790.04 | 907601 | -167189.04 | 167189.04 | 1 | 2025-09-28 | 3 | 1283532.59 | -208742.55 | DOWN | 0.1942 | 112 | Low | 387732.6 | 0.366 | 0 | 519868.4 | 25 | 1.38 | 1.58
P002 | Services | SUP046 | 2025-09 | 2025-08-02 | 985999.68 | 907601 | -78398.68 | 78398.68 | 0 | 2025-09-28 | 4 | 1074790.04 | -88790.36 | DOWN | 0.0901 | 57 | Medium | 581579.36 | 0.553 | 6 | 326021.64 | 25 | 1.38 | 1.58
P002 | Services | SUP046 | 2025-09 | 2025-09-06 | 933739.24 | 907601 | -26138.24 | 26138.24 | 0 | 2025-09-28 | 5 | 985999.68 | -52260.44 | DOWN | 0.056 | 22 | High | 615426.01 | 0.671 | 3 | 292174.99 | 25 | 1.38 | 1.58
P002 | Materials | SUP046 | 2025-10 | 2025-07-17 | 2233527.07 | 1298317 | -935210.07 | 935210.07 | 1 | 2025-10-28 | 1 |  |  |  |  | 103 | Low | 834103.62 | 0.38 | 4 | 464213.38 | 21 | 1.76 | 1.29
P002 | Materials | SUP046 | 2025-10 | 2025-07-21 | 1729826.39 | 1298317 | -431509.39 | 431509.39 | 1 | 2025-10-28 | 2 | 2233527.07 | -503700.68 | DOWN | 0.2912 | 99 | Low | 664833.75 | 0.393 | 3 | 633483.25 | 21 | 1.76 | 1.29
P002 | Materials | SUP046 | 2025-10 | 2025-09-05 | 1525878.47 | 1298317 | -227561.47 | 227561.47 | 0 | 2025-10-28 | 3 | 1729826.39 | -203947.92 | DOWN | 0.1337 | 53 | Low | 879816.15 | 0.543 | 0 | 418500.85 | 21 | 1.76 | 1.29
P002 | Materials | SUP046 | 2025-10 | 2025-10-04 | 1402943.75 | 1298317 | -104626.75 | 104626.75 | 0 | 2025-10-28 | 4 | 1525878.47 | -122934.72 | DOWN | 0.0876 | 24 | Medium | 916327.38 | 0.637 | 4 | 381989.62 | 21 | 1.76 | 1.29
P002 | Materials | SUP046 | 2025-11 | 2025-06-21 | 1332138.44 | 822254 | -509884.44 | 509884.44 | 1 | 2025-11-28 | 1 |  |  |  |  | 160 | Low | 253562 | 0.199 | 2 | 568692 | 26 | 1.59 | 1.38
P002 | Materials | SUP046 | 2025-11 | 2025-08-03 | 1063541.81 | 822254 | -241287.81 | 241287.81 | 1 | 2025-11-28 | 2 | 1332138.44 | -268596.63 | DOWN | 0.2525 | 117 | Low | 338229.13 | 0.341 | 0 | 484024.87 | 26 | 1.59 | 1.38
P002 | Materials | SUP046 | 2025-11 | 2025-08-05 | 937035.37 | 822254 | -114781.37 | 114781.37 | 0 | 2025-11-28 | 3 | 1063541.81 | -126506.44 | DOWN | 0.135 | 115 | Low | 327335.5 | 0.348 | 5 | 494918.5 | 26 | 1.59 | 1.38
P002 | Materials | SUP046 | 2025-11 | 2025-10-01 | 869804.49 | 822254 | -47550.49 | 47550.49 | 0 | 2025-11-28 | 4 | 937035.37 | -67230.88 | DOWN | 0.0773 | 58 | Medium | 498310.13 | 0.536 | 2 | 323943.87 | 26 | 1.59 | 1.38
P002 | Services | SUP046 | 2025-12 | 2025-07-11 | 4251097.08 | 2517696 | -1733401.08 | 1733401.08 | 1 | 2025-12-28 | 1 |  |  |  |  | 170 | Low | 744692.68 | 0.169 | 0 | 1773003.32 | 27 | 1.43 | 1.4
P002 | Services | SUP046 | 2025-12 | 2025-09-23 | 3326879.18 | 2517696 | -809183.18 | 809183.18 | 1 | 2025-12-28 | 2 | 4251097.08 | -924217.9 | DOWN | 0.2778 | 96 | Low | 1386690.67 | 0.418 | 5 | 1131005.33 | 27 | 1.43 | 1.4
P002 | Services | SUP046 | 2025-12 | 2025-10-09 | 2905726.14 | 2517696 | -388030.14 | 388030.14 | 0 | 2025-12-28 | 3 | 3326879.18 | -421153.04 | DOWN | 0.1449 | 80 | Low | 1468126.81 | 0.472 | 8 | 1049569.19 | 27 | 1.43 | 1.4
P002 | Logistics | SUP041 | 2025-01 | 2024-08-14 | 1542261 | 626961 | -915300 | 915300 | 1 | 2025-01-28 | 1 |  |  |  |  | 167 | Low | 206960.24 | 0.126 | 1 | 420000.76 | 20 | 1.45 | 1.35
P002 | Logistics | SUP041 | 2025-01 | 2024-11-08 | 1169796.76 | 626961 | -542835.76 | 542835.76 | 1 | 2025-01-28 | 2 | 1542261 | -372464.24 | DOWN | 0.3184 | 81 | Low | 364650.56 | 0.33 | 0 | 262310.44 | 20 | 1.45 | 1.35
P002 | Logistics | SUP041 | 2025-01 | 2024-12-05 | 970920.61 | 626961 | -343959.61 | 343959.61 | 1 | 2025-01-28 | 3 | 1169796.76 | -198876.15 | DOWN | 0.2048 | 54 | Low | 355116.68 | 0.394 | 5 | 271844.32 | 20 | 1.45 | 1.35
P002 | Logistics | SUP041 | 2025-01 | 2024-12-15 | 853594.33 | 626961 | -226633.33 | 226633.33 | 1 | 2025-01-28 | 4 | 970920.61 | -117326.28 | DOWN | 0.1374 | 44 | Low | 355520.19 | 0.417 | 5 | 271440.81 | 20 | 1.45 | 1.35
P002 | Logistics | SUP041 | 2025-02 | 2024-11-09 | 3207672.98 | 1234500 | -1973172.98 | 1973172.98 | 1 | 2025-02-28 | 1 |  |  |  |  | 111 | Low | 839192.75 | 0.26 | 0 | 395307.25 | 23 | 1.4 | 1.5
P002 | Logistics | SUP041 | 2025-02 | 2024-11-15 | 2457663.57 | 1234500 | -1223163.57 | 1223163.57 | 1 | 2025-02-28 | 2 | 3207672.98 | -750009.41 | DOWN | 0.3052 | 105 | Low | 693921.05 | 0.274 | 1 | 540578.95 | 23 | 1.4 | 1.5
P002 | Logistics | SUP041 | 2025-02 | 2024-12-15 | 1985009.74 | 1234500 | -750509.74 | 750509.74 | 1 | 2025-02-28 | 3 | 2457663.57 | -472653.83 | DOWN | 0.2381 | 75 | Low | 676899.4 | 0.346 | 0 | 557600.6 | 23 | 1.4 | 1.5
P002 | Logistics | SUP041 | 2025-02 | 2024-12-17 | 1714856.09 | 1234500 | -480356.09 | 480356.09 | 1 | 2025-02-28 | 4 | 1985009.74 | -270153.65 | DOWN | 0.1575 | 73 | Low | 607376.35 | 0.351 | 3 | 627123.65 | 23 | 1.4 | 1.5
P002 | Logistics | SUP041 | 2025-02 | 2025-01-05 | 1508129.44 | 1234500 | -273629.44 | 273629.44 | 1 | 2025-02-28 | 5 | 1714856.09 | -206726.65 | DOWN | 0.1371 | 54 | Low | 629854.28 | 0.396 | 5 | 604645.72 | 23 | 1.4 | 1.5
P002 | Software | SUP041 | 2025-03 | 2025-01-15 | 1050870.51 | 505657 | -545213.51 | 545213.51 | 1 | 2025-03-28 | 1 |  |  |  |  | 72 | Low | 333597.74 | 0.321 | 5 | 172059.26 | 25 | 2.28 | 1.97
P002 | Software | SUP041 | 2025-03 | 2025-01-16 | 801958.32 | 505657 | -296301.32 | 296301.32 | 1 | 2025-03-28 | 2 | 1050870.51 | -248912.19 | DOWN | 0.3104 | 71 | Low | 254056.72 | 0.323 | 5 | 251600.28 | 25 | 2.28 | 1.97
P002 | Software | SUP041 | 2025-03 | 2025-01-17 | 674112.89 | 505657 | -168455.89 | 168455.89 | 1 | 2025-03-28 | 3 | 801958.32 | -127845.43 | DOWN | 0.1896 | 70 | Low | 226862.17 | 0.325 | 5 | 278794.83 | 25 | 2.28 | 1.97
P002 | Electronics | SUP041 | 2025-04 | 2024-12-23 | 1094279.65 | 595786 | -498493.65 | 498493.65 | 1 | 2025-04-28 | 1 |  |  |  |  | 126 | Low | 250705.3 | 0.233 | 0 | 345080.7 | 21 | 1.06 | 1.67
P002 | Electronics | SUP041 | 2025-04 | 2024-12-31 | 884685.04 | 595786 | -288899.04 | 288899.04 | 1 | 2025-04-28 | 2 | 1094279.65 | -209594.61 | DOWN | 0.2369 | 118 | Low | 239179.21 | 0.253 | 0 | 356606.79 | 21 | 1.06 | 1.67
P002 | Electronics | SUP041 | 2025-04 | 2025-01-16 | 759437.5 | 595786 | -163651.5 | 163651.5 | 1 | 2025-04-28 | 3 | 884685.04 | -125247.54 | DOWN | 0.1649 | 102 | Low | 219292.99 | 0.293 | 0 | 376493.01 | 21 | 1.06 | 1.67
P002 | Electronics | SUP041 | 2025-04 | 2025-03-25 | 694208.98 | 595786 | -98422.98 | 98422.98 | 0 | 2025-04-28 | 4 | 759437.5 | -65228.52 | DOWN | 0.094 | 34 | Medium | 321413.24 | 0.462 | 6 | 274372.76 | 21 | 1.06 | 1.67
P002 | Electronics | SUP041 | 2025-04 | 2025-04-10 | 653293.1 | 595786 | -57507.1 | 57507.1 | 0 | 2025-04-28 | 5 | 694208.98 | -40915.88 | DOWN | 0.0626 | 18 | Medium | 309834.28 | 0.501 | 5 | 285951.72 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP041 | 2025-05 | 2025-01-06 | 2739791.08 | 1484012 | -1255779.08 | 1255779.08 | 1 | 2025-05-28 | 1 |  |  |  |  | 142 | Low | 499099.38 | 0.172 | 0 | 984912.62 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP041 | 2025-05 | 2025-02-24 | 2245358.37 | 1484012 | -761346.37 | 761346.37 | 1 | 2025-05-28 | 2 | 2739791.08 | -494432.71 | DOWN | 0.2202 | 93 | Low | 662378.7 | 0.28 | 4 | 821633.3 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP041 | 2025-05 | 2025-03-04 | 1942785.59 | 1484012 | -458773.59 | 458773.59 | 1 | 2025-05-28 | 3 | 2245358.37 | -302572.78 | DOWN | 0.1557 | 85 | Low | 602955.8 | 0.298 | 1 | 881056.2 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP041 | 2025-05 | 2025-04-16 | 1789646.48 | 1484012 | -305634.48 | 305634.48 | 1 | 2025-05-28 | 4 | 1942785.59 | -153139.11 | DOWN | 0.0856 | 42 | Low | 647562.96 | 0.393 | 4 | 836449.04 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP041 | 2025-05 | 2025-04-17 | 1688056.38 | 1484012 | -204044.38 | 204044.38 | 0 | 2025-05-28 | 5 | 1789646.48 | -101590.1 | DOWN | 0.0602 | 41 | Low | 626344.36 | 0.395 | 1 | 857667.64 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP041 | 2025-05 | 2025-05-17 | 1622698.6 | 1484012 | -138686.6 | 138686.6 | 0 | 2025-05-28 | 6 | 1688056.38 | -65357.78 | DOWN | 0.0403 | 11 | Low | 798763.01 | 0.462 | 2 | 685248.99 | 28 | 2.1 | 0.99
P002 | Logistics | SUP041 | 2025-06 | 2025-01-08 | 2235971.7 | 855024 | -1380947.7 | 1380947.7 | 1 | 2025-06-28 | 1 |  |  |  |  | 171 | Low | 257670.74 | 0.119 | 0 | 597353.26 | 17 | 1.27 | 1.62
P002 | Logistics | SUP041 | 2025-06 | 2025-01-21 | 1679414.26 | 855024 | -824390.26 | 824390.26 | 1 | 2025-06-28 | 2 | 2235971.7 | -556557.44 | DOWN | 0.3314 | 158 | Low | 270328.01 | 0.15 | 2 | 584695.99 | 17 | 1.27 | 1.62
P002 | Logistics | SUP041 | 2025-06 | 2025-05-28 | 1375973.15 | 855024 | -520949.15 | 520949.15 | 1 | 2025-06-28 | 3 | 1679414.26 | -303441.11 | DOWN | 0.2205 | 31 | Low | 630887.25 | 0.458 | 2 | 224136.75 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP041 | 2025-07 | 2025-03-27 | 1510066.98 | 748371 | -761695.98 | 761695.98 | 1 | 2025-07-28 | 1 |  |  |  |  | 123 | Low | 369800.69 | 0.229 | 2 | 378570.31 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP041 | 2025-07 | 2025-04-12 | 1191573.87 | 748371 | -443202.87 | 443202.87 | 1 | 2025-07-28 | 2 | 1510066.98 | -318493.11 | DOWN | 0.2673 | 107 | Low | 303107.79 | 0.267 | 2 | 445263.21 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP041 | 2025-07 | 2025-04-20 | 1015937.69 | 748371 | -267566.69 | 267566.69 | 1 | 2025-07-28 | 3 | 1191573.87 | -175636.18 | DOWN | 0.1729 | 99 | Low | 296736.04 | 0.286 | 1 | 451634.96 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP041 | 2025-07 | 2025-06-18 | 908747.11 | 748371 | -160376.11 | 160376.11 | 1 | 2025-07-28 | 4 | 1015937.69 | -107190.58 | DOWN | 0.118 | 40 | Low | 412076.69 | 0.425 | 4 | 336294.31 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP041 | 2025-07 | 2025-07-16 | 840189.42 | 748371 | -91818.42 | 91818.42 | 0 | 2025-07-28 | 5 | 908747.11 | -68557.69 | DOWN | 0.0816 | 12 | Medium | 417622.4 | 0.491 | 3 | 330748.6 | 24 | 1.49 | 1.96
P002 | Logistics | SUP041 | 2025-08 | 2025-03-31 | 5194315.05 | 2053677 | -3140638.05 | 3140638.05 | 1 | 2025-08-28 | 1 |  |  |  |  | 150 | Low | 843262.13 | 0.169 | 0 | 1210414.87 | 25 | 1.29 | 1.82
P002 | Logistics | SUP041 | 2025-08 | 2025-04-04 | 4050407.03 | 2053677 | -1996730.03 | 1996730.03 | 1 | 2025-08-28 | 2 | 5194315.05 | -1143908.02 | DOWN | 0.2824 | 146 | Low | 702806.49 | 0.179 | 1 | 1350870.51 | 25 | 1.29 | 1.82
P002 | Logistics | SUP041 | 2025-08 | 2025-05-14 | 3321462.76 | 2053677 | -1267785.76 | 1267785.76 | 1 | 2025-08-28 | 3 | 4050407.03 | -728944.27 | DOWN | 0.2195 | 106 | Low | 916090.43 | 0.275 | 0 | 1137586.57 | 25 | 1.29 | 1.82
P002 | Logistics | SUP041 | 2025-08 | 2025-05-28 | 2853536.36 | 2053677 | -799859.36 | 799859.36 | 1 | 2025-08-28 | 4 | 3321462.76 | -467926.4 | DOWN | 0.164 | 92 | Low | 937628.13 | 0.309 | 0 | 1116048.87 | 25 | 1.29 | 1.82
P002 | Logistics | SUP041 | 2025-08 | 2025-06-03 | 2533204.28 | 2053677 | -479527.28 | 479527.28 | 1 | 2025-08-28 | 5 | 2853536.36 | -320332.08 | DOWN | 0.1265 | 86 | Low | 772222.95 | 0.324 | 2 | 1281454.05 | 25 | 1.29 | 1.82
P002 | Logistics | SUP041 | 2025-08 | 2025-07-26 | 2379182.83 | 2053677 | -325505.83 | 325505.83 | 0 | 2025-08-28 | 6 | 2533204.28 | -154021.45 | DOWN | 0.0647 | 33 | Medium | 1026897.58 | 0.452 | 6 | 1026779.42 | 25 | 1.29 | 1.82
P002 | Services | SUP041 | 2025-09 | 2025-05-06 | 3863140.36 | 1740375 | -2122765.36 | 2122765.36 | 1 | 2025-09-28 | 1 |  |  |  |  | 145 | Low | 648422.8 | 0.179 | 1 | 1091952.2 | 25 | 1.38 | 1.58
P002 | Services | SUP041 | 2025-09 | 2025-05-09 | 3042788.51 | 1740375 | -1302413.51 | 1302413.51 | 1 | 2025-09-28 | 2 | 3863140.36 | -820351.85 | DOWN | 0.2696 | 142 | Low | 599552.82 | 0.186 | 2 | 1140822.18 | 25 | 1.38 | 1.58
P002 | Services | SUP041 | 2025-09 | 2025-05-28 | 2538956.04 | 1740375 | -798581.04 | 798581.04 | 1 | 2025-09-28 | 3 | 3042788.51 | -503832.47 | DOWN | 0.1984 | 123 | Low | 600999.25 | 0.232 | 3 | 1139375.75 | 25 | 1.38 | 1.58
P002 | Services | SUP041 | 2025-09 | 2025-08-07 | 2236460.26 | 1740375 | -496085.26 | 496085.26 | 1 | 2025-09-28 | 4 | 2538956.04 | -302495.78 | DOWN | 0.1353 | 52 | Low | 845204.51 | 0.402 | 5 | 895170.49 | 25 | 1.38 | 1.58
P002 | Services | SUP041 | 2025-09 | 2025-09-04 | 2030653.99 | 1740375 | -290278.99 | 290278.99 | 0 | 2025-09-28 | 5 | 2236460.26 | -205806.27 | DOWN | 0.1013 | 24 | Medium | 982732.17 | 0.469 | 4 | 757642.83 | 25 | 1.38 | 1.58
P002 | Services | SUP041 | 2025-10 | 2025-07-07 | 1549202.14 | 848337 | -700865.14 | 700865.14 | 1 | 2025-10-28 | 1 |  |  |  |  | 113 | Low | 389605.44 | 0.245 | 2 | 458731.56 | 21 | 1.76 | 1.29
P002 | Services | SUP041 | 2025-10 | 2025-09-04 | 1288083.53 | 848337 | -439746.53 | 439746.53 | 1 | 2025-10-28 | 2 | 1549202.14 | -261118.61 | DOWN | 0.2027 | 54 | Low | 477659.21 | 0.38 | 3 | 370677.79 | 21 | 1.76 | 1.29
P002 | Services | SUP041 | 2025-10 | 2025-10-15 | 1122448.96 | 848337 | -274111.96 | 274111.96 | 1 | 2025-10-28 | 3 | 1288083.53 | -165634.57 | DOWN | 0.1476 | 13 | Low | 525238.2 | 0.474 | 2 | 323098.8 | 21 | 1.76 | 1.29
P002 | Electronics | SUP041 | 2025-11 | 2025-06-04 | 3379623.95 | 1998279 | -1381344.95 | 1381344.95 | 1 | 2025-11-28 | 1 |  |  |  |  | 177 | Low | 354191.71 | 0.103 | 5 | 1644087.29 | 26 | 1.59 | 1.38
P002 | Electronics | SUP041 | 2025-11 | 2025-09-12 | 2763256.06 | 1998279 | -764977.06 | 764977.06 | 1 | 2025-11-28 | 2 | 3379623.95 | -616367.89 | DOWN | 0.2231 | 77 | Low | 942554.65 | 0.334 | 3 | 1055724.35 | 26 | 1.59 | 1.38
P002 | Electronics | SUP041 | 2025-11 | 2025-10-05 | 2456726.48 | 1998279 | -458447.48 | 458447.48 | 1 | 2025-11-28 | 3 | 2763256.06 | -306529.58 | DOWN | 0.1248 | 54 | Low | 976362.19 | 0.388 | 0 | 1021916.81 | 26 | 1.59 | 1.38
P002 | Electronics | SUP041 | 2025-11 | 2025-10-06 | 2252026.34 | 1998279 | -253747.34 | 253747.34 | 0 | 2025-11-28 | 4 | 2456726.48 | -204700.14 | DOWN | 0.0909 | 53 | Low | 845880.64 | 0.39 | 3 | 1152398.36 | 26 | 1.59 | 1.38
P002 | Electronics | SUP041 | 2025-12 | 2025-07-01 | 1412497.47 | 899800 | -512697.47 | 512697.47 | 1 | 2025-12-28 | 1 |  |  |  |  | 180 | Low | 143927.75 | 0.105 | 3 | 755872.25 | 27 | 1.43 | 1.4
P002 | Electronics | SUP041 | 2025-12 | 2025-07-09 | 1194114.36 | 899800 | -294314.36 | 294314.36 | 1 | 2025-12-28 | 2 | 1412497.47 | -218383.11 | DOWN | 0.1829 | 172 | Low | 125510.72 | 0.114 | 2 | 774289.28 | 27 | 1.43 | 1.4
P002 | Electronics | SUP041 | 2025-12 | 2025-08-07 | 1088316.49 | 899800 | -188516.49 | 188516.49 | 1 | 2025-12-28 | 3 | 1194114.36 | -105797.87 | DOWN | 0.0972 | 143 | Low | 191279.13 | 0.183 | 1 | 708520.87 | 27 | 1.43 | 1.4
P002 | Electronics | SUP041 | 2025-12 | 2025-10-28 | 1012716.84 | 899800 | -112916.84 | 112916.84 | 0 | 2025-12-28 | 4 | 1088316.49 | -75599.65 | DOWN | 0.0747 | 61 | Low | 357097.13 | 0.378 | 1 | 542702.87 | 27 | 1.43 | 1.4
P002 | Materials | SUP015 | 2025-01 | 2024-10-06 | 3923689.9 | 2322349 | -1601340.9 | 1601340.9 | 1 | 2025-01-28 | 1 |  |  |  |  | 114 | Low | 1501658.84 | 0.357 | 2 | 820690.16 | 20 | 1.45 | 1.35
P002 | Materials | SUP015 | 2025-01 | 2024-10-22 | 3090193.84 | 2322349 | -767844.84 | 767844.84 | 1 | 2025-01-28 | 2 | 3923689.9 | -833496.06 | DOWN | 0.2697 | 98 | Low | 1336503.77 | 0.41 | 4 | 985845.23 | 20 | 1.45 | 1.35
P002 | Materials | SUP015 | 2025-01 | 2024-11-19 | 2646346.38 | 2322349 | -323997.38 | 323997.38 | 0 | 2025-01-28 | 3 | 3090193.84 | -443847.46 | DOWN | 0.1677 | 70 | Low | 1321421.21 | 0.505 | 3 | 1000927.79 | 20 | 1.45 | 1.35
P002 | Materials | SUP015 | 2025-01 | 2024-12-01 | 2478601.16 | 2322349 | -156252.16 | 156252.16 | 0 | 2025-01-28 | 4 | 2646346.38 | -167745.22 | DOWN | 0.0677 | 58 | Medium | 1452930.21 | 0.545 | 5 | 869418.79 | 20 | 1.45 | 1.35
P002 | Materials | SUP015 | 2025-01 | 2025-01-15 | 2435171.72 | 2322349 | -112822.72 | 112822.72 | 0 | 2025-01-28 | 5 | 2478601.16 | -43429.44 | DOWN | 0.0178 | 13 | Medium | 1662570.9 | 0.696 | 4 | 659778.1 | 20 | 1.45 | 1.35
P002 | Materials | SUP015 | 2025-02 | 2024-09-14 | 5154604.51 | 3010761 | -2143843.51 | 2143843.51 | 1 | 2025-02-28 | 1 |  |  |  |  | 167 | Low | 866340.02 | 0.179 | 0 | 2144420.98 | 23 | 1.4 | 1.5
P002 | Materials | SUP015 | 2025-02 | 2024-09-16 | 3930357.32 | 3010761 | -919596.32 | 919596.32 | 1 | 2025-02-28 | 2 | 5154604.51 | -1224247.19 | DOWN | 0.3115 | 165 | Low | 675252.91 | 0.186 | 1 | 2335508.09 | 23 | 1.4 | 1.5
P002 | Materials | SUP015 | 2025-02 | 2024-11-09 | 3424637.22 | 3010761 | -413876.22 | 413876.22 | 0 | 2025-02-28 | 3 | 3930357.32 | -505720.1 | DOWN | 0.1477 | 111 | Low | 1293454.75 | 0.369 | 3 | 1717306.25 | 23 | 1.4 | 1.5
P002 | Materials | SUP015 | 2025-02 | 2025-01-04 | 3164853.1 | 3010761 | -154092.1 | 154092.1 | 0 | 2025-02-28 | 4 | 3424637.22 | -259784.12 | DOWN | 0.0821 | 55 | Medium | 1805774.33 | 0.558 | 1 | 1204986.67 | 23 | 1.4 | 1.5
P002 | Software | SUP015 | 2025-03 | 2024-10-16 | 3927007.38 | 2284464 | -1642543.38 | 1642543.38 | 1 | 2025-03-28 | 1 |  |  |  |  | 163 | Low | 642688.63 | 0.175 | 3 | 1641775.37 | 25 | 2.28 | 1.97
P002 | Software | SUP015 | 2025-03 | 2024-10-17 | 2961376.54 | 2284464 | -676912.54 | 676912.54 | 1 | 2025-03-28 | 2 | 3927007.38 | -965630.84 | DOWN | 0.3261 | 162 | Low | 497781.37 | 0.178 | 4 | 1786682.63 | 25 | 2.28 | 1.97
P002 | Software | SUP015 | 2025-03 | 2024-11-17 | 2598101.97 | 2284464 | -313637.97 | 313637.97 | 0 | 2025-03-28 | 3 | 2961376.54 | -363274.57 | DOWN | 0.1398 | 131 | Low | 657306.11 | 0.274 | 4 | 1627157.89 | 25 | 2.28 | 1.97
P002 | Software | SUP015 | 2025-03 | 2024-11-27 | 2390500.77 | 2284464 | -106036.77 | 106036.77 | 0 | 2025-03-28 | 4 | 2598101.97 | -207601.2 | DOWN | 0.0868 | 121 | Low | 670379.02 | 0.304 | 6 | 1614084.98 | 25 | 2.28 | 1.97
P002 | Software | SUP015 | 2025-03 | 2024-12-28 | 2314468.23 | 2284464 | -30004.23 | 30004.23 | 0 | 2025-03-28 | 5 | 2390500.77 | -76032.54 | DOWN | 0.0329 | 90 | Low | 995040.12 | 0.4 | 2 | 1289423.88 | 25 | 2.28 | 1.97
P002 | Software | SUP015 | 2025-03 | 2025-03-09 | 2319723.98 | 2284464 | -35259.98 | 35259.98 | 0 | 2025-03-28 | 6 | 2314468.23 | 5255.75 | UP | 0.0023 | 19 | Low | 1326648.28 | 0.618 | 8 | 957815.72 | 25 | 2.28 | 1.97
P002 | Materials | SUP015 | 2025-04 | 2024-12-15 | 1352971.97 | 805087 | -547884.97 | 547884.97 | 1 | 2025-04-28 | 1 |  |  |  |  | 134 | Low | 391426.08 | 0.303 | 1 | 413660.92 | 21 | 1.06 | 1.67
P002 | Materials | SUP015 | 2025-04 | 2025-02-10 | 1054051.97 | 805087 | -248964.97 | 248964.97 | 1 | 2025-04-28 | 2 | 1352971.97 | -298920 | DOWN | 0.2836 | 77 | Low | 569233.48 | 0.503 | 3 | 235853.52 | 21 | 1.06 | 1.67
P002 | Materials | SUP015 | 2025-04 | 2025-03-11 | 917283.29 | 805087 | -112196.29 | 112196.29 | 0 | 2025-04-28 | 3 | 1054051.97 | -136768.68 | DOWN | 0.1491 | 48 | Low | 592021.94 | 0.605 | 6 | 213065.06 | 21 | 1.06 | 1.67
P002 | Materials | SUP015 | 2025-04 | 2025-03-13 | 849347.64 | 805087 | -44260.64 | 44260.64 | 0 | 2025-04-28 | 4 | 917283.29 | -67935.65 | DOWN | 0.08 | 46 | Medium | 558821.9 | 0.612 | 2 | 246265.1 | 21 | 1.06 | 1.67
P002 | Materials | SUP015 | 2025-04 | 2025-04-14 | 828466.79 | 805087 | -23379.79 | 23379.79 | 0 | 2025-04-28 | 5 | 849347.64 | -20880.85 | DOWN | 0.0252 | 14 | High | 636725.68 | 0.725 | 4 | 168361.32 | 21 | 1.06 | 1.67
P002 | Software | SUP015 | 2025-05 | 2024-11-30 | 1589376.4 | 814618 | -774758.4 | 774758.4 | 1 | 2025-05-28 | 1 |  |  |  |  | 179 | Low | 211387.23 | 0.138 | 1 | 603230.77 | 28 | 2.1 | 0.99
P002 | Software | SUP015 | 2025-05 | 2024-12-12 | 1125512.6 | 814618 | -310894.6 | 310894.6 | 1 | 2025-05-28 | 2 | 1589376.4 | -463863.8 | DOWN | 0.4121 | 167 | Low | 189412.97 | 0.166 | 2 | 625205.03 | 28 | 2.1 | 0.99
P002 | Software | SUP015 | 2025-05 | 2025-01-15 | 971951.25 | 814618 | -157333.25 | 157333.25 | 1 | 2025-05-28 | 3 | 1125512.6 | -153561.35 | DOWN | 0.158 | 133 | Low | 276668.22 | 0.272 | 1 | 537949.78 | 28 | 2.1 | 0.99
P002 | Software | SUP015 | 2025-05 | 2025-02-20 | 889968.49 | 814618 | -75350.49 | 75350.49 | 0 | 2025-05-28 | 4 | 971951.25 | -81982.76 | DOWN | 0.0921 | 97 | Low | 346671.9 | 0.385 | 2 | 467946.1 | 28 | 2.1 | 0.99
P002 | Software | SUP015 | 2025-05 | 2025-04-22 | 832549.13 | 814618 | -17931.13 | 17931.13 | 0 | 2025-05-28 | 5 | 889968.49 | -57419.36 | DOWN | 0.069 | 36 | Low | 447994.93 | 0.576 | 5 | 366623.07 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP015 | 2025-06 | 2025-02-23 | 1250271.26 | 797442 | -452829.26 | 452829.26 | 1 | 2025-06-28 | 1 |  |  |  |  | 125 | Low | 420824.71 | 0.326 | 0 | 376617.29 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP015 | 2025-06 | 2025-03-18 | 1006039.82 | 797442 | -208597.82 | 208597.82 | 1 | 2025-06-28 | 2 | 1250271.26 | -244231.44 | DOWN | 0.2428 | 102 | Low | 398179.53 | 0.405 | 2 | 399262.47 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP015 | 2025-06 | 2025-03-28 | 889960.51 | 797442 | -92518.51 | 92518.51 | 0 | 2025-06-28 | 3 | 1006039.82 | -116079.31 | DOWN | 0.1304 | 92 | Low | 397397.26 | 0.44 | 4 | 400044.74 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP015 | 2025-06 | 2025-04-24 | 842888.3 | 797442 | -45446.3 | 45446.3 | 0 | 2025-06-28 | 4 | 889960.51 | -47072.21 | DOWN | 0.0558 | 65 | Low | 437320.8 | 0.532 | 5 | 360121.2 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP015 | 2025-06 | 2025-05-05 | 817887.56 | 797442 | -20445.56 | 20445.56 | 0 | 2025-06-28 | 5 | 842888.3 | -25000.74 | DOWN | 0.0306 | 54 | Medium | 440152.9 | 0.57 | 2 | 357289.1 | 17 | 1.27 | 1.62
P002 | Materials | SUP015 | 2025-07 | 2025-02-26 | 2926365.49 | 1722870 | -1203495.49 | 1203495.49 | 1 | 2025-07-28 | 1 |  |  |  |  | 152 | Low | 675943.12 | 0.228 | 3 | 1046926.88 | 24 | 1.49 | 1.96
P002 | Materials | SUP015 | 2025-07 | 2025-04-07 | 2245176.08 | 1722870 | -522306.08 | 522306.08 | 1 | 2025-07-28 | 2 | 2926365.49 | -681189.41 | DOWN | 0.3034 | 112 | Low | 750917.63 | 0.362 | 3 | 971952.37 | 24 | 1.49 | 1.96
P002 | Materials | SUP015 | 2025-07 | 2025-05-16 | 1991418.47 | 1722870 | -268548.47 | 268548.47 | 0 | 2025-07-28 | 3 | 2245176.08 | -253757.61 | DOWN | 0.1274 | 73 | Low | 990791.47 | 0.492 | 3 | 732078.53 | 24 | 1.49 | 1.96
P002 | Materials | SUP015 | 2025-07 | 2025-07-09 | 1852751.74 | 1722870 | -129881.74 | 129881.74 | 0 | 2025-07-28 | 4 | 1991418.47 | -138666.73 | DOWN | 0.0748 | 19 | Medium | 1236964.57 | 0.673 | 4 | 485905.43 | 24 | 1.49 | 1.96
P002 | Services | SUP015 | 2025-08 | 2025-03-09 | 550950.63 | 298435 | -252515.63 | 252515.63 | 1 | 2025-08-28 | 1 |  |  |  |  | 172 | Low | 90923.18 | 0.164 | 0 | 207511.82 | 25 | 1.29 | 1.82
P002 | Services | SUP015 | 2025-08 | 2025-04-25 | 414357.92 | 298435 | -115922.92 | 115922.92 | 1 | 2025-08-28 | 2 | 550950.63 | -136592.71 | DOWN | 0.3296 | 125 | Low | 128166.11 | 0.325 | 3 | 170268.89 | 25 | 1.29 | 1.82
P002 | Services | SUP015 | 2025-08 | 2025-04-27 | 344751.57 | 298435 | -46316.57 | 46316.57 | 0 | 2025-08-28 | 3 | 414357.92 | -69606.35 | DOWN | 0.2019 | 123 | Low | 113408.03 | 0.332 | 4 | 185026.97 | 25 | 1.29 | 1.82
P002 | Services | SUP015 | 2025-08 | 2025-05-09 | 322175.24 | 298435 | -23740.24 | 23740.24 | 0 | 2025-08-28 | 4 | 344751.57 | -22576.33 | DOWN | 0.0701 | 111 | Low | 129909.65 | 0.373 | 4 | 168525.35 | 25 | 1.29 | 1.82
P002 | Software | SUP015 | 2025-09 | 2025-04-03 | 791915.17 | 426831 | -365084.17 | 365084.17 | 1 | 2025-09-28 | 1 |  |  |  |  | 178 | Low | 113122.07 | 0.149 | 1 | 313708.93 | 25 | 1.38 | 1.58
P002 | Software | SUP015 | 2025-09 | 2025-06-11 | 606527.46 | 426831 | -179696.46 | 179696.46 | 1 | 2025-09-28 | 2 | 791915.17 | -185387.71 | DOWN | 0.3057 | 109 | Low | 234443.79 | 0.376 | 3 | 192387.21 | 25 | 1.38 | 1.58
P002 | Software | SUP015 | 2025-09 | 2025-09-13 | 511046.62 | 426831 | -84215.62 | 84215.62 | 1 | 2025-09-28 | 3 | 606527.46 | -95480.84 | DOWN | 0.1868 | 15 | Low | 356016.15 | 0.695 | 4 | 70814.85 | 25 | 1.38 | 1.58
P002 | Electronics | SUP015 | 2025-10 | 2025-07-01 | 596128.91 | 361775 | -234353.91 | 234353.91 | 1 | 2025-10-28 | 1 |  |  |  |  | 119 | Low | 192610.89 | 0.328 | 1 | 169164.11 | 21 | 1.76 | 1.29
P002 | Electronics | SUP015 | 2025-10 | 2025-07-10 | 462790.82 | 361775 | -101015.82 | 101015.82 | 1 | 2025-10-28 | 2 | 596128.91 | -133338.09 | DOWN | 0.2881 | 110 | Low | 164558.83 | 0.357 | 2 | 197216.17 | 21 | 1.76 | 1.29
P002 | Electronics | SUP015 | 2025-10 | 2025-08-17 | 411207.69 | 361775 | -49432.69 | 49432.69 | 0 | 2025-10-28 | 3 | 462790.82 | -51583.13 | DOWN | 0.1254 | 72 | Low | 192626.85 | 0.481 | 4 | 169148.15 | 21 | 1.76 | 1.29
P002 | Electronics | SUP015 | 2025-10 | 2025-10-03 | 384958.78 | 361775 | -23183.78 | 23183.78 | 0 | 2025-10-28 | 4 | 411207.69 | -26248.91 | DOWN | 0.0682 | 25 | Medium | 239649.42 | 0.634 | 7 | 122125.58 | 21 | 1.76 | 1.29
P002 | Mechanical | SUP015 | 2025-11 | 2025-06-27 | 2454414.54 | 1316362 | -1138052.54 | 1138052.54 | 1 | 2025-11-28 | 1 |  |  |  |  | 154 | Low | 505109.92 | 0.219 | 0 | 811252.08 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP015 | 2025-11 | 2025-08-10 | 1863821.14 | 1316362 | -547459.14 | 547459.14 | 1 | 2025-11-28 | 2 | 2454414.54 | -590593.4 | DOWN | 0.3169 | 110 | Low | 703943.98 | 0.364 | 3 | 612418.02 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP015 | 2025-11 | 2025-10-18 | 1543132.66 | 1316362 | -226770.66 | 226770.66 | 0 | 2025-11-28 | 3 | 1863821.14 | -320688.48 | DOWN | 0.2078 | 41 | Low | 943267.57 | 0.593 | 5 | 373094.43 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP015 | 2025-11 | 2025-11-14 | 1438556.62 | 1316362 | -122194.62 | 122194.62 | 0 | 2025-11-28 | 4 | 1543132.66 | -104576.04 | DOWN | 0.0727 | 14 | Medium | 994771.44 | 0.682 | 4 | 321590.56 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP015 | 2025-12 | 2025-08-22 | 919493.96 | 558809 | -360684.96 | 360684.96 | 1 | 2025-12-28 | 1 |  |  |  |  | 128 | Low | 262507.77 | 0.31 | 1 | 296301.23 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP015 | 2025-12 | 2025-11-05 | 732055.73 | 558809 | -173246.73 | 173246.73 | 1 | 2025-12-28 | 2 | 919493.96 | -187438.23 | DOWN | 0.256 | 53 | Low | 423303.79 | 0.563 | 4 | 135505.21 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP015 | 2025-12 | 2025-11-13 | 631240.49 | 558809 | -72431.49 | 72431.49 | 0 | 2025-12-28 | 3 | 732055.73 | -100815.24 | DOWN | 0.1597 | 45 | Low | 362697.76 | 0.59 | 7 | 196111.24 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP015 | 2025-12 | 2025-12-15 | 595420.31 | 558809 | -36611.31 | 36611.31 | 0 | 2025-12-28 | 4 | 631240.49 | -35820.18 | DOWN | 0.0602 | 13 | Medium | 409641.78 | 0.698 | 4 | 149167.22 | 27 | 1.43 | 1.4
P002 | Services | SUP001 | 2025-01 | 2024-08-11 | 3561201.61 | 1852590 | -1708611.61 | 1708611.61 | 1 | 2025-01-28 | 1 |  |  |  |  | 170 | Low | 633608.72 | 0.168 | 0 | 1218981.28 | 20 | 1.45 | 1.35
P002 | Services | SUP001 | 2025-01 | 2024-09-23 | 2629373.02 | 1852590 | -776783.02 | 776783.02 | 1 | 2025-01-28 | 2 | 3561201.61 | -931828.59 | DOWN | 0.3544 | 127 | Low | 884423.68 | 0.313 | 2 | 968166.32 | 20 | 1.45 | 1.35
P002 | Services | SUP001 | 2025-01 | 2024-11-24 | 2204026.48 | 1852590 | -351436.48 | 351436.48 | 1 | 2025-01-28 | 3 | 2629373.02 | -425346.54 | DOWN | 0.193 | 65 | Low | 1229536.6 | 0.521 | 4 | 623053.4 | 20 | 1.45 | 1.35
P002 | Services | SUP001 | 2025-01 | 2024-11-25 | 2008292.18 | 1852590 | -155702.18 | 155702.18 | 0 | 2025-01-28 | 4 | 2204026.48 | -195734.3 | DOWN | 0.0975 | 64 | Low | 1014370.77 | 0.525 | 2 | 838219.23 | 20 | 1.45 | 1.35
P002 | Services | SUP001 | 2025-02 | 2024-09-30 | 2192807.33 | 1197128 | -995679.33 | 995679.33 | 1 | 2025-02-28 | 1 |  |  |  |  | 151 | Low | 476554 | 0.233 | 0 | 720574 | 23 | 1.4 | 1.5
P002 | Services | SUP001 | 2025-02 | 2024-10-22 | 1664720.11 | 1197128 | -467592.11 | 467592.11 | 1 | 2025-02-28 | 2 | 2192807.33 | -528087.22 | DOWN | 0.3172 | 129 | Low | 525789.78 | 0.308 | 1 | 671338.22 | 23 | 1.4 | 1.5
P002 | Services | SUP001 | 2025-02 | 2024-11-15 | 1379019.5 | 1197128 | -181891.5 | 181891.5 | 0 | 2025-02-28 | 3 | 1664720.11 | -285700.61 | DOWN | 0.2072 | 105 | Low | 551596.44 | 0.389 | 7 | 645531.56 | 23 | 1.4 | 1.5
P002 | Services | SUP001 | 2025-02 | 2025-01-18 | 1268390.29 | 1197128 | -71262.29 | 71262.29 | 0 | 2025-02-28 | 4 | 1379019.5 | -110629.21 | DOWN | 0.0872 | 41 | Medium | 727870.94 | 0.606 | 1 | 469257.06 | 23 | 1.4 | 1.5
P002 | Services | SUP001 | 2025-02 | 2025-02-17 | 1235843.42 | 1197128 | -38715.42 | 38715.42 | 0 | 2025-02-28 | 5 | 1268390.29 | -32546.87 | DOWN | 0.0263 | 11 | High | 871846.4 | 0.707 | 5 | 325281.6 | 23 | 1.4 | 1.5
P002 | Logistics | SUP001 | 2025-03 | 2024-10-22 | 1512002.57 | 677347 | -834655.57 | 834655.57 | 1 | 2025-03-28 | 1 |  |  |  |  | 157 | Low | 282768 | 0.194 | 2 | 394579 | 25 | 2.28 | 1.97
P002 | Logistics | SUP001 | 2025-03 | 2024-12-16 | 1061454.49 | 677347 | -384107.49 | 384107.49 | 1 | 2025-03-28 | 2 | 1512002.57 | -450548.08 | DOWN | 0.4245 | 102 | Low | 387183.99 | 0.363 | 5 | 290163.01 | 25 | 2.28 | 1.97
P002 | Logistics | SUP001 | 2025-03 | 2024-12-22 | 815123.03 | 677347 | -137776.03 | 137776.03 | 1 | 2025-03-28 | 3 | 1061454.49 | -246331.46 | DOWN | 0.3022 | 96 | Low | 319677.67 | 0.381 | 2 | 357669.33 | 25 | 2.28 | 1.97
P002 | Logistics | SUP001 | 2025-03 | 2025-01-07 | 716289.52 | 677347 | -38942.52 | 38942.52 | 0 | 2025-03-28 | 4 | 815123.03 | -98833.51 | DOWN | 0.138 | 80 | Low | 312492.2 | 0.43 | 6 | 364854.8 | 25 | 2.28 | 1.97
P002 | Logistics | SUP001 | 2025-03 | 2025-03-09 | 707542.47 | 677347 | -30195.47 | 30195.47 | 0 | 2025-03-28 | 5 | 716289.52 | -8747.05 | DOWN | 0.0124 | 19 | Low | 453778.94 | 0.618 | 5 | 223568.06 | 25 | 2.28 | 1.97
P002 | Electronics | SUP001 | 2025-04 | 2025-01-20 | 751748.61 | 454468 | -297280.61 | 297280.61 | 1 | 2025-04-28 | 1 |  |  |  |  | 98 | Low | 343637.16 | 0.429 | 4 | 110830.84 | 21 | 1.06 | 1.67
P002 | Electronics | SUP001 | 2025-04 | 2025-02-23 | 580009.76 | 454468 | -125541.76 | 125541.76 | 1 | 2025-04-28 | 2 | 751748.61 | -171738.85 | DOWN | 0.2961 | 64 | Low | 337038.57 | 0.549 | 6 | 117429.43 | 21 | 1.06 | 1.67
P002 | Electronics | SUP001 | 2025-04 | 2025-02-27 | 509929.11 | 454468 | -55461.11 | 55461.11 | 0 | 2025-04-28 | 3 | 580009.76 | -70080.65 | DOWN | 0.1374 | 60 | Low | 298435.19 | 0.563 | 6 | 156032.81 | 21 | 1.06 | 1.67
P002 | Electronics | SUP001 | 2025-04 | 2025-03-04 | 479402.2 | 454468 | -24934.2 | 24934.2 | 0 | 2025-04-28 | 4 | 509929.11 | -30526.91 | DOWN | 0.0637 | 55 | Medium | 267112.59 | 0.581 | 3 | 187355.41 | 21 | 1.06 | 1.67
P002 | Electronics | SUP001 | 2025-04 | 2025-03-31 | 459687.52 | 454468 | -5219.52 | 5219.52 | 0 | 2025-04-28 | 5 | 479402.2 | -19714.68 | DOWN | 0.0429 | 28 | High | 322952.15 | 0.676 | 7 | 131515.85 | 21 | 1.06 | 1.67
P002 | Electronics | SUP001 | 2025-04 | 2025-04-07 | 458848.22 | 454468 | -4380.22 | 4380.22 | 0 | 2025-04-28 | 6 | 459687.52 | -839.3 | DOWN | 0.0018 | 21 | High | 300234.8 | 0.701 | 2 | 154233.2 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP001 | 2025-05 | 2025-01-16 | 1735599.53 | 1232442 | -503157.53 | 503157.53 | 1 | 2025-05-28 | 1 |  |  |  |  | 132 | Low | 474822.26 | 0.276 | 2 | 757619.74 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP001 | 2025-05 | 2025-02-17 | 1479707.2 | 1232442 | -247265.2 | 247265.2 | 1 | 2025-05-28 | 2 | 1735599.53 | -255892.33 | DOWN | 0.1729 | 100 | Low | 525062.95 | 0.376 | 3 | 707379.05 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP001 | 2025-05 | 2025-03-23 | 1355880 | 1232442 | -123438 | 123438 | 0 | 2025-05-28 | 3 | 1479707.2 | -123827.2 | DOWN | 0.0913 | 66 | Low | 612394.71 | 0.482 | 1 | 620047.29 | 28 | 2.1 | 0.99
P002 | Services | SUP001 | 2025-06 | 2025-01-20 | 5063095.75 | 2461926 | -2601169.75 | 2601169.75 | 1 | 2025-06-28 | 1 |  |  |  |  | 159 | Low | 988537.3 | 0.209 | 5 | 1473388.7 | 17 | 1.27 | 1.62
P002 | Services | SUP001 | 2025-06 | 2025-01-22 | 3644137.07 | 2461926 | -1182211.07 | 1182211.07 | 1 | 2025-06-28 | 2 | 5063095.75 | -1418958.68 | DOWN | 0.3894 | 157 | Low | 773926.21 | 0.216 | 2 | 1687999.79 | 17 | 1.27 | 1.62
P002 | Services | SUP001 | 2025-06 | 2025-02-15 | 3054354.79 | 2461926 | -592428.79 | 592428.79 | 1 | 2025-06-28 | 3 | 3644137.07 | -589782.28 | DOWN | 0.1931 | 133 | Low | 906175.73 | 0.299 | 1 | 1555750.27 | 17 | 1.27 | 1.62
P002 | Services | SUP001 | 2025-06 | 2025-03-07 | 2744728.87 | 2461926 | -282802.87 | 282802.87 | 0 | 2025-06-28 | 4 | 3054354.79 | -309625.92 | DOWN | 0.1128 | 113 | Low | 963686.91 | 0.367 | 0 | 1498239.09 | 17 | 1.27 | 1.62
P002 | Services | SUP001 | 2025-06 | 2025-04-11 | 2620108.23 | 2461926 | -158182.23 | 158182.23 | 0 | 2025-06-28 | 5 | 2744728.87 | -124620.64 | DOWN | 0.0476 | 78 | Low | 1193205.3 | 0.488 | 2 | 1268720.7 | 17 | 1.27 | 1.62
P002 | Services | SUP001 | 2025-06 | 2025-06-18 | 2496654.54 | 2461926 | -34728.54 | 34728.54 | 0 | 2025-06-28 | 6 | 2620108.23 | -123453.69 | DOWN | 0.0494 | 10 | High | 1926260.67 | 0.718 | 2 | 535665.33 | 17 | 1.27 | 1.62
P002 | Services | SUP001 | 2025-07 | 2025-03-12 | 1824952.09 | 1054412 | -770540.09 | 770540.09 | 1 | 2025-07-28 | 1 |  |  |  |  | 138 | Low | 496415.77 | 0.275 | 4 | 557996.23 | 24 | 1.49 | 1.96
P002 | Services | SUP001 | 2025-07 | 2025-04-25 | 1416190.81 | 1054412 | -361778.81 | 361778.81 | 1 | 2025-07-28 | 2 | 1824952.09 | -408761.28 | DOWN | 0.2886 | 94 | Low | 636954.64 | 0.422 | 3 | 417457.36 | 24 | 1.49 | 1.96
P002 | Services | SUP001 | 2025-07 | 2025-06-25 | 1234076.7 | 1054412 | -179664.7 | 179664.7 | 0 | 2025-07-28 | 3 | 1416190.81 | -182114.11 | DOWN | 0.1476 | 33 | Low | 762891.51 | 0.626 | 7 | 291520.49 | 24 | 1.49 | 1.96
P002 | Services | SUP001 | 2025-08 | 2025-05-04 | 1103486.47 | 557918 | -545568.47 | 545568.47 | 1 | 2025-08-28 | 1 |  |  |  |  | 116 | Low | 419482.96 | 0.356 | 1 | 138435.04 | 25 | 1.29 | 1.82
P002 | Services | SUP001 | 2025-08 | 2025-05-21 | 799683.84 | 557918 | -241765.84 | 241765.84 | 1 | 2025-08-28 | 2 | 1103486.47 | -303802.63 | DOWN | 0.3799 | 99 | Low | 340859.15 | 0.415 | 2 | 217058.85 | 25 | 1.29 | 1.82
P002 | Services | SUP001 | 2025-08 | 2025-07-12 | 664776.95 | 557918 | -106858.95 | 106858.95 | 1 | 2025-08-28 | 3 | 799683.84 | -134906.89 | DOWN | 0.2029 | 47 | Low | 400951.18 | 0.593 | 5 | 156966.82 | 25 | 1.29 | 1.82
P002 | Services | SUP001 | 2025-08 | 2025-07-23 | 601498.31 | 557918 | -43580.31 | 43580.31 | 0 | 2025-08-28 | 4 | 664776.95 | -63278.64 | DOWN | 0.1052 | 36 | Medium | 349395.28 | 0.63 | 6 | 208522.72 | 25 | 1.29 | 1.82
P002 | Services | SUP001 | 2025-08 | 2025-07-25 | 585534.86 | 557918 | -27616.86 | 27616.86 | 0 | 2025-08-28 | 5 | 601498.31 | -15963.45 | DOWN | 0.0273 | 34 | Medium | 395824.97 | 0.637 | 7 | 162093.03 | 25 | 1.29 | 1.82
P002 | Logistics | SUP001 | 2025-09 | 2025-05-11 | 3760178.43 | 2028584 | -1731594.43 | 1731594.43 | 1 | 2025-09-28 | 1 |  |  |  |  | 140 | Low | 1051229.19 | 0.271 | 0 | 977354.81 | 25 | 1.38 | 1.58
P002 | Logistics | SUP001 | 2025-09 | 2025-05-22 | 2836402.13 | 2028584 | -807818.13 | 807818.13 | 1 | 2025-09-28 | 2 | 3760178.43 | -923776.3 | DOWN | 0.3257 | 129 | Low | 911737.55 | 0.309 | 1 | 1116846.45 | 25 | 1.38 | 1.58
P002 | Logistics | SUP001 | 2025-09 | 2025-05-30 | 2349616.36 | 2028584 | -321032.36 | 321032.36 | 0 | 2025-09-28 | 3 | 2836402.13 | -486785.77 | DOWN | 0.2072 | 121 | Low | 753520.32 | 0.336 | 0 | 1275063.68 | 25 | 1.38 | 1.58
P002 | Logistics | SUP001 | 2025-09 | 2025-08-15 | 2196786.97 | 2028584 | -168202.97 | 168202.97 | 0 | 2025-09-28 | 4 | 2349616.36 | -152829.39 | DOWN | 0.0696 | 44 | Medium | 1294003.89 | 0.597 | 0 | 734580.11 | 25 | 1.38 | 1.58
P002 | Logistics | SUP001 | 2025-09 | 2025-09-01 | 2069219.13 | 2028584 | -40635.13 | 40635.13 | 0 | 2025-09-28 | 5 | 2196786.97 | -127567.84 | DOWN | 0.0617 | 27 | Medium | 1298980.9 | 0.654 | 1 | 729603.1 | 25 | 1.38 | 1.58
P002 | Materials | SUP001 | 2025-10 | 2025-06-01 | 443420.9 | 268911 | -174509.9 | 174509.9 | 1 | 2025-10-28 | 1 |  |  |  |  | 149 | Low | 100576.14 | 0.231 | 3 | 168334.86 | 21 | 1.76 | 1.29
P002 | Materials | SUP001 | 2025-10 | 2025-08-08 | 350691.44 | 268911 | -81780.44 | 81780.44 | 1 | 2025-10-28 | 2 | 443420.9 | -92729.46 | DOWN | 0.2644 | 81 | Low | 166627.84 | 0.452 | 4 | 102283.16 | 21 | 1.76 | 1.29
P002 | Materials | SUP001 | 2025-10 | 2025-10-08 | 300218.43 | 268911 | -31307.43 | 31307.43 | 0 | 2025-10-28 | 3 | 350691.44 | -50473.01 | DOWN | 0.1681 | 20 | Low | 183691.09 | 0.65 | 4 | 85219.91 | 21 | 1.76 | 1.29
P002 | Services | SUP001 | 2025-11 | 2025-06-09 | 2650299.02 | 1538021 | -1112278.02 | 1112278.02 | 1 | 2025-11-28 | 1 |  |  |  |  | 172 | Low | 396099.92 | 0.159 | 0 | 1141921.08 | 26 | 1.59 | 1.38
P002 | Services | SUP001 | 2025-11 | 2025-06-09 | 2073372.96 | 1538021 | -535351.96 | 535351.96 | 1 | 2025-11-28 | 2 | 2650299.02 | -576926.06 | DOWN | 0.2783 | 172 | Low | 305618.18 | 0.159 | 1 | 1232402.82 | 26 | 1.59 | 1.38
P002 | Services | SUP001 | 2025-11 | 2025-07-25 | 1764499.58 | 1538021 | -226478.58 | 226478.58 | 0 | 2025-11-28 | 3 | 2073372.96 | -308873.38 | DOWN | 0.175 | 126 | Low | 538088.18 | 0.311 | 2 | 999932.82 | 26 | 1.59 | 1.38
P002 | Services | SUP001 | 2025-11 | 2025-10-20 | 1634923.71 | 1538021 | -96902.71 | 96902.71 | 0 | 2025-11-28 | 4 | 1764499.58 | -129575.87 | DOWN | 0.0793 | 39 | Medium | 1043401.59 | 0.599 | 5 | 494619.41 | 26 | 1.59 | 1.38
P002 | Services | SUP001 | 2025-11 | 2025-10-21 | 1607969.61 | 1538021 | -69948.61 | 69948.61 | 0 | 2025-11-28 | 5 | 1634923.71 | -26954.1 | DOWN | 0.0168 | 38 | Medium | 905863.07 | 0.603 | 7 | 632157.93 | 26 | 1.59 | 1.38
P002 | Services | SUP001 | 2025-11 | 2025-10-22 | 1552065.9 | 1538021 | -14044.9 | 14044.9 | 0 | 2025-11-28 | 6 | 1607969.61 | -55903.71 | DOWN | 0.036 | 37 | Medium | 919246.36 | 0.606 | 3 | 618774.64 | 26 | 1.59 | 1.38
P002 | Materials | SUP001 | 2025-12 | 2025-07-24 | 4993984.97 | 2698797 | -2295187.97 | 2295187.97 | 1 | 2025-12-28 | 1 |  |  |  |  | 157 | Low | 976487.03 | 0.212 | 6 | 1722309.97 | 27 | 1.43 | 1.4
P002 | Materials | SUP001 | 2025-12 | 2025-07-27 | 3770146.22 | 2698797 | -1071349.22 | 1071349.22 | 1 | 2025-12-28 | 2 | 4993984.97 | -1223838.75 | DOWN | 0.3246 | 154 | Low | 807591.99 | 0.223 | 2 | 1891205.01 | 27 | 1.43 | 1.4
P002 | Materials | SUP001 | 2025-12 | 2025-10-24 | 3178611.95 | 2698797 | -479814.95 | 479814.95 | 1 | 2025-12-28 | 3 | 3770146.22 | -591534.27 | DOWN | 0.1861 | 65 | Low | 1562148.33 | 0.523 | 6 | 1136648.67 | 27 | 1.43 | 1.4
P002 | Software | SUP029 | 2025-01 | 2024-09-22 | 3555339.83 | 2205204 | -1350135.83 | 1350135.83 | 1 | 2025-01-28 | 1 |  |  |  |  | 128 | Low | 1098655.97 | 0.309 | 2 | 1106548.03 | 20 | 1.45 | 1.35
P002 | Software | SUP029 | 2025-01 | 2024-12-03 | 2880682.96 | 2205204 | -675478.96 | 675478.96 | 1 | 2025-01-28 | 2 | 3555339.83 | -674656.87 | DOWN | 0.2342 | 56 | Low | 1586173.98 | 0.552 | 2 | 619030.02 | 20 | 1.45 | 1.35
P002 | Software | SUP029 | 2025-01 | 2024-12-15 | 2512728.77 | 2205204 | -307524.77 | 307524.77 | 0 | 2025-01-28 | 3 | 2880682.96 | -367954.19 | DOWN | 0.1464 | 44 | Low | 1452476.05 | 0.592 | 6 | 752727.95 | 20 | 1.45 | 1.35
P002 | Software | SUP029 | 2025-01 | 2024-12-17 | 2307480.03 | 2205204 | -102276.03 | 102276.03 | 0 | 2025-01-28 | 4 | 2512728.77 | -205248.74 | DOWN | 0.0889 | 42 | Medium | 1369700.6 | 0.599 | 3 | 835503.4 | 20 | 1.45 | 1.35
P002 | Software | SUP029 | 2025-01 | 2025-01-14 | 2244803.06 | 2205204 | -39599.06 | 39599.06 | 0 | 2025-01-28 | 5 | 2307480.03 | -62676.97 | DOWN | 0.0279 | 14 | Medium | 1673858.1 | 0.693 | 2 | 531345.9 | 20 | 1.45 | 1.35
P002 | Software | SUP029 | 2025-01 | 2025-01-18 | 2229207.03 | 2205204 | -24003.03 | 24003.03 | 0 | 2025-01-28 | 6 | 2244803.06 | -15596.03 | DOWN | 0.007 | 10 | Medium | 1615286.68 | 0.703 | 3 | 589917.32 | 20 | 1.45 | 1.35
P002 | Software | SUP029 | 2025-02 | 2024-10-27 | 3837197.29 | 2124308 | -1712889.29 | 1712889.29 | 1 | 2025-02-28 | 1 |  |  |  |  | 124 | Low | 1342674.05 | 0.325 | 2 | 781633.95 | 23 | 1.4 | 1.5
P002 | Software | SUP029 | 2025-02 | 2024-11-15 | 2962258.76 | 2124308 | -837950.76 | 837950.76 | 1 | 2025-02-28 | 2 | 3837197.29 | -874938.53 | DOWN | 0.2954 | 105 | Low | 1171909.2 | 0.389 | 2 | 952398.8 | 23 | 1.4 | 1.5
P002 | Software | SUP029 | 2025-02 | 2025-01-04 | 2533428.95 | 2124308 | -409120.95 | 409120.95 | 1 | 2025-02-28 | 3 | 2962258.76 | -428829.81 | DOWN | 0.1693 | 55 | Low | 1521320.54 | 0.558 | 6 | 602987.46 | 23 | 1.4 | 1.5
P002 | Logistics | SUP029 | 2025-03 | 2024-10-02 | 2011395.39 | 995501 | -1015894.39 | 1015894.39 | 1 | 2025-03-28 | 1 |  |  |  |  | 177 | Low | 278595.79 | 0.135 | 1 | 716905.21 | 25 | 2.28 | 1.97
P002 | Logistics | SUP029 | 2025-03 | 2024-12-25 | 1502562.75 | 995501 | -507061.75 | 507061.75 | 1 | 2025-03-28 | 2 | 2011395.39 | -508832.64 | DOWN | 0.3386 | 93 | Low | 631586.19 | 0.39 | 7 | 363914.81 | 25 | 2.28 | 1.97
P002 | Logistics | SUP029 | 2025-03 | 2024-12-28 | 1214008.3 | 995501 | -218507.3 | 218507.3 | 1 | 2025-03-28 | 3 | 1502562.75 | -288554.45 | DOWN | 0.2377 | 90 | Low | 449226.2 | 0.4 | 3 | 546274.8 | 25 | 2.28 | 1.97
P002 | Logistics | SUP029 | 2025-03 | 2025-02-17 | 1125544 | 995501 | -130043 | 130043 | 0 | 2025-03-28 | 4 | 1214008.3 | -88464.3 | DOWN | 0.0786 | 39 | Low | 673182.16 | 0.556 | 5 | 322318.84 | 25 | 2.28 | 1.97
P002 | Logistics | SUP029 | 2025-03 | 2025-02-22 | 1021468.8 | 995501 | -25967.8 | 25967.8 | 0 | 2025-03-28 | 5 | 1125544 | -104075.2 | DOWN | 0.1019 | 34 | Low | 572429.04 | 0.572 | 2 | 423071.96 | 25 | 2.28 | 1.97
P002 | Logistics | SUP029 | 2025-03 | 2025-02-26 | 1017721.84 | 995501 | -22220.84 | 22220.84 | 0 | 2025-03-28 | 6 | 1021468.8 | -3746.96 | DOWN | 0.0037 | 30 | Low | 635826.31 | 0.584 | 6 | 359674.69 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP029 | 2025-04 | 2024-11-17 | 3487737.21 | 2287385 | -1200352.21 | 1200352.21 | 1 | 2025-04-28 | 1 |  |  |  |  | 162 | Low | 726715.3 | 0.204 | 0 | 1560669.7 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP029 | 2025-04 | 2024-11-25 | 2828208.55 | 2287385 | -540823.55 | 540823.55 | 1 | 2025-04-28 | 2 | 3487737.21 | -659528.66 | DOWN | 0.2332 | 154 | Low | 700146.59 | 0.232 | 0 | 1587238.41 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP029 | 2025-04 | 2025-01-11 | 2527042.87 | 2287385 | -239657.87 | 239657.87 | 0 | 2025-04-28 | 3 | 2828208.55 | -301165.68 | DOWN | 0.1192 | 107 | Low | 980559.94 | 0.398 | 3 | 1306825.06 | 21 | 1.06 | 1.67
P002 | Mechanical | SUP029 | 2025-04 | 2025-03-04 | 2408065.94 | 2287385 | -120680.94 | 120680.94 | 0 | 2025-04-28 | 4 | 2527042.87 | -118976.93 | DOWN | 0.0494 | 55 | Medium | 1508676.01 | 0.581 | 3 | 778708.99 | 21 | 1.06 | 1.67
P002 | Electronics | SUP029 | 2025-05 | 2025-01-20 | 1103638.41 | 586476 | -517162.41 | 517162.41 | 1 | 2025-05-28 | 1 |  |  |  |  | 128 | Low | 320710.06 | 0.288 | 0 | 265765.94 | 28 | 2.1 | 0.99
P002 | Electronics | SUP029 | 2025-05 | 2025-03-12 | 803836.63 | 586476 | -217360.63 | 217360.63 | 1 | 2025-05-28 | 2 | 1103638.41 | -299801.78 | DOWN | 0.373 | 77 | Low | 387555.13 | 0.448 | 3 | 198920.87 | 28 | 2.1 | 0.99
P002 | Electronics | SUP029 | 2025-05 | 2025-03-30 | 676999.47 | 586476 | -90523.47 | 90523.47 | 0 | 2025-05-28 | 3 | 803836.63 | -126837.16 | DOWN | 0.1874 | 59 | Low | 327866.28 | 0.504 | 2 | 258609.72 | 28 | 2.1 | 0.99
P002 | Electronics | SUP029 | 2025-05 | 2025-05-07 | 623159.67 | 586476 | -36683.67 | 36683.67 | 0 | 2025-05-28 | 4 | 676999.47 | -53839.8 | DOWN | 0.0864 | 21 | Low | 407529.64 | 0.623 | 3 | 178946.36 | 28 | 2.1 | 0.99
P002 | Electronics | SUP029 | 2025-05 | 2025-05-13 | 598731.56 | 586476 | -12255.56 | 12255.56 | 0 | 2025-05-28 | 5 | 623159.67 | -24428.11 | DOWN | 0.0408 | 15 | Low | 383780.5 | 0.642 | 6 | 202695.5 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP029 | 2025-06 | 2025-01-20 | 3451621.62 | 2266806 | -1184815.62 | 1184815.62 | 1 | 2025-06-28 | 1 |  |  |  |  | 159 | Low | 704825.64 | 0.209 | 0 | 1561980.36 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP029 | 2025-06 | 2025-03-24 | 2780243.77 | 2266806 | -513437.77 | 513437.77 | 1 | 2025-06-28 | 2 | 3451621.62 | -671377.85 | DOWN | 0.2415 | 96 | Low | 1200263.26 | 0.426 | 5 | 1066542.74 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP029 | 2025-06 | 2025-04-12 | 2491578.49 | 2266806 | -224772.49 | 224772.49 | 0 | 2025-06-28 | 3 | 2780243.77 | -288665.28 | DOWN | 0.1159 | 77 | Low | 1197225.43 | 0.491 | 3 | 1069580.57 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP029 | 2025-06 | 2025-05-04 | 2388958.35 | 2266806 | -122152.35 | 122152.35 | 0 | 2025-06-28 | 4 | 2491578.49 | -102620.14 | DOWN | 0.043 | 55 | Medium | 1286353.8 | 0.567 | 0 | 980452.2 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP029 | 2025-06 | 2025-05-18 | 2308985.08 | 2266806 | -42179.08 | 42179.08 | 0 | 2025-06-28 | 5 | 2388958.35 | -79973.27 | DOWN | 0.0346 | 41 | Medium | 1367668.32 | 0.615 | 5 | 899137.68 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP029 | 2025-06 | 2025-05-20 | 2297672.32 | 2266806 | -30866.32 | 30866.32 | 0 | 2025-06-28 | 6 | 2308985.08 | -11312.76 | DOWN | 0.0049 | 39 | Medium | 1449827.77 | 0.622 | 9 | 816978.23 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP029 | 2025-07 | 2025-03-20 | 506139.54 | 275939 | -230200.54 | 230200.54 | 1 | 2025-07-28 | 1 |  |  |  |  | 130 | Low | 148287.55 | 0.301 | 0 | 127651.45 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP029 | 2025-07 | 2025-04-10 | 375072.43 | 275939 | -99133.43 | 99133.43 | 1 | 2025-07-28 | 2 | 506139.54 | -131067.11 | DOWN | 0.3494 | 109 | Low | 138449.27 | 0.372 | 3 | 137489.73 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP029 | 2025-07 | 2025-06-25 | 325264.15 | 275939 | -49325.15 | 49325.15 | 1 | 2025-07-28 | 3 | 375072.43 | -49808.28 | DOWN | 0.1531 | 33 | Low | 195937.93 | 0.626 | 3 | 80001.07 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP029 | 2025-07 | 2025-06-28 | 293220.8 | 275939 | -17281.8 | 17281.8 | 0 | 2025-07-28 | 4 | 325264.15 | -32043.35 | DOWN | 0.1093 | 30 | Medium | 185696.64 | 0.636 | 4 | 90242.36 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP029 | 2025-07 | 2025-07-06 | 283212.56 | 275939 | -7273.56 | 7273.56 | 0 | 2025-07-28 | 5 | 293220.8 | -10008.24 | DOWN | 0.0353 | 22 | Medium | 187265.44 | 0.663 | 3 | 88673.56 | 24 | 1.49 | 1.96
P002 | Materials | SUP029 | 2025-08 | 2025-03-16 | 2487517.82 | 1385467 | -1102050.82 | 1102050.82 | 1 | 2025-08-28 | 1 |  |  |  |  | 165 | Low | 469397.01 | 0.188 | 0 | 916069.99 | 25 | 1.29 | 1.82
P002 | Materials | SUP029 | 2025-08 | 2025-04-06 | 1909412.38 | 1385467 | -523945.38 | 523945.38 | 1 | 2025-08-28 | 2 | 2487517.82 | -578105.44 | DOWN | 0.3028 | 144 | Low | 470749.02 | 0.26 | 0 | 914717.98 | 25 | 1.29 | 1.82
P002 | Materials | SUP029 | 2025-08 | 2025-07-04 | 1608039.13 | 1385467 | -222572.13 | 222572.13 | 0 | 2025-08-28 | 3 | 1909412.38 | -301373.25 | DOWN | 0.1874 | 55 | Low | 921026.13 | 0.565 | 2 | 464440.87 | 25 | 1.29 | 1.82
P002 | Materials | SUP029 | 2025-08 | 2025-07-29 | 1486769.01 | 1385467 | -101302.01 | 101302.01 | 0 | 2025-08-28 | 4 | 1608039.13 | -121270.12 | DOWN | 0.0816 | 30 | Medium | 1044753.94 | 0.651 | 2 | 340713.06 | 25 | 1.29 | 1.82
P002 | Logistics | SUP029 | 2025-09 | 2025-07-28 | 3315528.49 | 1634582 | -1680946.49 | 1680946.49 | 1 | 2025-09-28 | 1 |  |  |  |  | 62 | Low | 1661069.1 | 0.536 | 3 | -26487.1 | 25 | 1.38 | 1.58
P002 | Logistics | SUP029 | 2025-09 | 2025-08-02 | 2458077.75 | 1634582 | -823495.75 | 823495.75 | 1 | 2025-09-28 | 2 | 3315528.49 | -857450.74 | DOWN | 0.3488 | 57 | Low | 1268732.05 | 0.553 | 5 | 365849.95 | 25 | 1.38 | 1.58
P002 | Logistics | SUP029 | 2025-09 | 2025-08-19 | 1993107.48 | 1634582 | -358525.48 | 358525.48 | 1 | 2025-09-28 | 3 | 2458077.75 | -464970.27 | DOWN | 0.2333 | 40 | Low | 1243791.98 | 0.61 | 3 | 390790.02 | 25 | 1.38 | 1.58
P002 | Services | SUP029 | 2025-10 | 2025-05-10 | 5138763.74 | 2483846 | -2654917.74 | 2654917.74 | 1 | 2025-10-28 | 1 |  |  |  |  | 171 | Low | 811414.85 | 0.159 | 3 | 1672431.15 | 21 | 1.76 | 1.29
P002 | Services | SUP029 | 2025-10 | 2025-07-28 | 3689721.87 | 2483846 | -1205875.87 | 1205875.87 | 1 | 2025-10-28 | 2 | 5138763.74 | -1449041.87 | DOWN | 0.3927 | 92 | Low | 1511010.65 | 0.416 | 3 | 972835.35 | 21 | 1.76 | 1.29
P002 | Services | SUP029 | 2025-10 | 2025-08-19 | 3048036.7 | 2483846 | -564190.7 | 564190.7 | 1 | 2025-10-28 | 3 | 3689721.87 | -641685.17 | DOWN | 0.2105 | 70 | Low | 1518480.61 | 0.487 | 4 | 965365.39 | 21 | 1.76 | 1.29
P002 | Services | SUP029 | 2025-10 | 2025-08-29 | 2764802.77 | 2483846 | -280956.77 | 280956.77 | 0 | 2025-10-28 | 4 | 3048036.7 | -283233.93 | DOWN | 0.1024 | 60 | Medium | 1460348.9 | 0.52 | 3 | 1023497.1 | 21 | 1.76 | 1.29
P002 | Services | SUP029 | 2025-10 | 2025-09-13 | 2590984.19 | 2483846 | -107138.19 | 107138.19 | 0 | 2025-10-28 | 5 | 2764802.77 | -173818.58 | DOWN | 0.0671 | 45 | Medium | 1452701.66 | 0.569 | 6 | 1031144.34 | 21 | 1.76 | 1.29
P002 | Software | SUP029 | 2025-11 | 2025-08-08 | 4352681.64 | 2271450 | -2081231.64 | 2081231.64 | 1 | 2025-11-28 | 1 |  |  |  |  | 112 | Low | 1452377.44 | 0.358 | 5 | 819072.56 | 26 | 1.59 | 1.38
P002 | Software | SUP029 | 2025-11 | 2025-09-27 | 3259506.69 | 2271450 | -988056.69 | 988056.69 | 1 | 2025-11-28 | 2 | 4352681.64 | -1093174.95 | DOWN | 0.3354 | 62 | Low | 1681928.63 | 0.523 | 3 | 589521.37 | 26 | 1.59 | 1.38
P002 | Software | SUP029 | 2025-11 | 2025-10-22 | 2694605.31 | 2271450 | -423155.31 | 423155.31 | 1 | 2025-11-28 | 3 | 3259506.69 | -564901.38 | DOWN | 0.2096 | 37 | Low | 1576770.49 | 0.606 | 4 | 694679.51 | 26 | 1.59 | 1.38
P002 | Electronics | SUP029 | 2025-12 | 2025-08-05 | 5078432.21 | 2871316 | -2207116.21 | 2207116.21 | 1 | 2025-12-28 | 1 |  |  |  |  | 145 | Low | 1221738.09 | 0.253 | 0 | 1649577.91 | 27 | 1.43 | 1.4
P002 | Electronics | SUP029 | 2025-12 | 2025-10-19 | 3866782.36 | 2871316 | -995466.36 | 995466.36 | 1 | 2025-12-28 | 2 | 5078432.21 | -1211649.85 | DOWN | 0.3133 | 70 | Low | 2055007.31 | 0.506 | 0 | 816308.69 | 27 | 1.43 | 1.4
P002 | Electronics | SUP029 | 2025-12 | 2025-11-03 | 3317328.96 | 2871316 | -446012.96 | 446012.96 | 0 | 2025-12-28 | 3 | 3866782.36 | -549453.4 | DOWN | 0.1656 | 55 | Low | 1756510.98 | 0.556 | 3 | 1114805.02 | 27 | 1.43 | 1.4
P002 | Electronics | SUP029 | 2025-12 | 2025-11-04 | 3074808.48 | 2871316 | -203492.48 | 203492.48 | 0 | 2025-12-28 | 4 | 3317328.96 | -242520.48 | DOWN | 0.0789 | 54 | Medium | 1839386.24 | 0.56 | 2 | 1031929.76 | 27 | 1.43 | 1.4
P002 | Services | SUP044 | 2025-01 | 2024-10-10 | 3136386.42 | 1730884 | -1405502.42 | 1405502.42 | 1 | 2025-01-28 | 1 |  |  |  |  | 110 | Low | 1084251.03 | 0.37 | 4 | 646632.97 | 20 | 1.45 | 1.35
P002 | Services | SUP044 | 2025-01 | 2024-10-18 | 2314949.83 | 1730884 | -584065.83 | 584065.83 | 1 | 2025-01-28 | 2 | 3136386.42 | -821436.59 | DOWN | 0.3548 | 102 | Low | 902362.87 | 0.397 | 5 | 828521.13 | 20 | 1.45 | 1.35
P002 | Services | SUP044 | 2025-01 | 2025-01-05 | 2004057.15 | 1730884 | -273173.15 | 273173.15 | 0 | 2025-01-28 | 3 | 2314949.83 | -310892.68 | DOWN | 0.1551 | 23 | Low | 1309619.18 | 0.663 | 7 | 421264.82 | 20 | 1.45 | 1.35
P002 | Logistics | SUP044 | 2025-02 | 2024-12-08 | 1545215.57 | 794320 | -750895.57 | 750895.57 | 1 | 2025-02-28 | 1 |  |  |  |  | 82 | Low | 673127.71 | 0.467 | 5 | 121192.29 | 23 | 1.4 | 1.5
P002 | Logistics | SUP044 | 2025-02 | 2025-01-21 | 1145818.01 | 794320 | -351498.01 | 351498.01 | 1 | 2025-02-28 | 2 | 1545215.57 | -399397.56 | DOWN | 0.3486 | 38 | Low | 728061.92 | 0.616 | 3 | 66258.08 | 23 | 1.4 | 1.5
P002 | Logistics | SUP044 | 2025-02 | 2025-01-22 | 964508.67 | 794320 | -170188.67 | 170188.67 | 1 | 2025-02-28 | 3 | 1145818.01 | -181309.34 | DOWN | 0.188 | 37 | Low | 594081.27 | 0.619 | 2 | 200238.73 | 23 | 1.4 | 1.5
P002 | Logistics | SUP044 | 2025-02 | 2025-02-02 | 892310.44 | 794320 | -97990.44 | 97990.44 | 0 | 2025-02-28 | 4 | 964508.67 | -72198.23 | DOWN | 0.0809 | 26 | Medium | 584457.82 | 0.656 | 1 | 209862.18 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP044 | 2025-03 | 2024-10-14 | 448091.32 | 276304 | -171787.32 | 171787.32 | 1 | 2025-03-28 | 1 |  |  |  |  | 165 | Low | 78041.01 | 0.169 | 0 | 198262.99 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP044 | 2025-03 | 2024-12-04 | 358010.7 | 276304 | -81706.7 | 81706.7 | 1 | 2025-03-28 | 2 | 448091.32 | -90080.62 | DOWN | 0.2516 | 114 | Low | 113210.25 | 0.326 | 0 | 163093.75 | 25 | 2.28 | 1.97
P002 | Mechanical | SUP044 | 2025-03 | 2024-12-25 | 317686.24 | 276304 | -41382.24 | 41382.24 | 0 | 2025-03-28 | 3 | 358010.7 | -40324.46 | DOWN | 0.1269 | 93 | Low | 122424.96 | 0.39 | 6 | 153879.04 | 25 | 2.28 | 1.97
P002 | Logistics | SUP044 | 2025-04 | 2025-01-05 | 1999129.35 | 918278 | -1080851.35 | 1080851.35 | 1 | 2025-04-28 | 1 |  |  |  |  | 113 | Low | 737598.68 | 0.377 | 4 | 180679.32 | 21 | 1.06 | 1.67
P002 | Logistics | SUP044 | 2025-04 | 2025-02-25 | 1425118.02 | 918278 | -506840.02 | 506840.02 | 1 | 2025-04-28 | 2 | 1999129.35 | -574011.33 | DOWN | 0.4028 | 62 | Low | 812421.2 | 0.556 | 2 | 105856.8 | 21 | 1.06 | 1.67
P002 | Logistics | SUP044 | 2025-04 | 2025-03-12 | 1159751.9 | 918278 | -241473.9 | 241473.9 | 1 | 2025-04-28 | 3 | 1425118.02 | -265366.12 | DOWN | 0.2288 | 47 | Low | 711842.74 | 0.609 | 7 | 206435.26 | 21 | 1.06 | 1.67
P002 | Logistics | SUP044 | 2025-04 | 2025-03-22 | 1037303.42 | 918278 | -119025.42 | 119025.42 | 0 | 2025-04-28 | 4 | 1159751.9 | -122448.48 | DOWN | 0.118 | 37 | Medium | 620378.53 | 0.644 | 2 | 297899.47 | 21 | 1.06 | 1.67
P002 | Logistics | SUP044 | 2025-04 | 2025-04-09 | 962680.04 | 918278 | -44402.04 | 44402.04 | 0 | 2025-04-28 | 5 | 1037303.42 | -74623.38 | DOWN | 0.0775 | 19 | Medium | 652327.65 | 0.708 | 7 | 265950.35 | 21 | 1.06 | 1.67
P002 | Logistics | SUP044 | 2025-04 | 2025-04-12 | 952998.1 | 918278 | -34720.1 | 34720.1 | 0 | 2025-04-28 | 6 | 962680.04 | -9681.94 | DOWN | 0.0102 | 16 | High | 713535.9 | 0.718 | 5 | 204742.1 | 21 | 1.06 | 1.67
P002 | Logistics | SUP044 | 2025-05 | 2025-03-01 | 3198069.63 | 1820232 | -1377837.63 | 1377837.63 | 1 | 2025-05-28 | 1 |  |  |  |  | 88 | Low | 1337272.52 | 0.413 | 4 | 482959.48 | 28 | 2.1 | 0.99
P002 | Logistics | SUP044 | 2025-05 | 2025-04-03 | 2441273.54 | 1820232 | -621041.54 | 621041.54 | 1 | 2025-05-28 | 2 | 3198069.63 | -756796.09 | DOWN | 0.31 | 55 | Low | 1301572.56 | 0.517 | 5 | 518659.44 | 28 | 2.1 | 0.99
P002 | Logistics | SUP044 | 2025-05 | 2025-05-02 | 2088008.89 | 1820232 | -267776.89 | 267776.89 | 0 | 2025-05-28 | 3 | 2441273.54 | -353264.65 | DOWN | 0.1692 | 26 | Low | 1231381.83 | 0.608 | 8 | 588850.17 | 28 | 2.1 | 0.99
P002 | Materials | SUP044 | 2025-06 | 2025-01-15 | 2751728.13 | 1750099 | -1001629.13 | 1001629.13 | 1 | 2025-06-28 | 1 |  |  |  |  | 164 | Low | 512529.59 | 0.192 | 0 | 1237569.41 | 17 | 1.27 | 1.62
P002 | Materials | SUP044 | 2025-06 | 2025-01-23 | 2206121.87 | 1750099 | -456022.87 | 456022.87 | 1 | 2025-06-28 | 2 | 2751728.13 | -545606.26 | DOWN | 0.2473 | 156 | Low | 450355.5 | 0.22 | 3 | 1299743.5 | 17 | 1.27 | 1.62
P002 | Materials | SUP044 | 2025-06 | 2025-02-21 | 1968054.1 | 1750099 | -217955.1 | 217955.1 | 0 | 2025-06-28 | 3 | 2206121.87 | -238067.77 | DOWN | 0.121 | 127 | Low | 666189.43 | 0.319 | 0 | 1083909.57 | 17 | 1.27 | 1.62
P002 | Materials | SUP044 | 2025-06 | 2025-05-05 | 1844286.78 | 1750099 | -94187.78 | 94187.78 | 0 | 2025-06-28 | 4 | 1968054.1 | -123767.32 | DOWN | 0.0671 | 54 | Medium | 1102584.74 | 0.57 | 3 | 647514.26 | 17 | 1.27 | 1.62
P002 | Materials | SUP044 | 2025-06 | 2025-05-27 | 1796729.78 | 1750099 | -46630.78 | 46630.78 | 0 | 2025-06-28 | 5 | 1844286.78 | -47557 | DOWN | 0.0265 | 32 | Medium | 1103753.96 | 0.646 | 4 | 646345.04 | 17 | 1.27 | 1.62
P002 | Materials | SUP044 | 2025-06 | 2025-06-01 | 1762822.49 | 1750099 | -12723.49 | 12723.49 | 0 | 2025-06-28 | 6 | 1796729.78 | -33907.29 | DOWN | 0.0192 | 27 | High | 1192175.45 | 0.663 | 5 | 557923.55 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP044 | 2025-07 | 2025-03-31 | 3260774.93 | 1919311 | -1341463.93 | 1341463.93 | 1 | 2025-07-28 | 1 |  |  |  |  | 119 | Low | 1073492.06 | 0.338 | 3 | 845818.94 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP044 | 2025-07 | 2025-04-05 | 2560297.31 | 1919311 | -640986.31 | 640986.31 | 1 | 2025-07-28 | 2 | 3260774.93 | -700477.62 | DOWN | 0.2736 | 114 | Low | 855306.96 | 0.355 | 0 | 1064004.04 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP044 | 2025-07 | 2025-04-05 | 2191224.33 | 1919311 | -271913.33 | 271913.33 | 0 | 2025-07-28 | 3 | 2560297.31 | -369072.98 | DOWN | 0.1684 | 114 | Low | 780587.28 | 0.355 | 1 | 1138723.72 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP044 | 2025-07 | 2025-07-03 | 2021447.65 | 1919311 | -102136.65 | 102136.65 | 0 | 2025-07-28 | 4 | 2191224.33 | -169776.68 | DOWN | 0.084 | 25 | Medium | 1380991.27 | 0.653 | 0 | 538319.73 | 24 | 1.49 | 1.96
P002 | Logistics | SUP044 | 2025-08 | 2025-03-02 | 2183890.96 | 1101569 | -1082321.96 | 1082321.96 | 1 | 2025-08-28 | 1 |  |  |  |  | 179 | Low | 318562.57 | 0.151 | 1 | 783006.43 | 25 | 1.29 | 1.82
P002 | Logistics | SUP044 | 2025-08 | 2025-03-23 | 1594716.74 | 1101569 | -493147.74 | 493147.74 | 1 | 2025-08-28 | 2 | 2183890.96 | -589174.22 | DOWN | 0.3695 | 158 | Low | 319364.34 | 0.212 | 0 | 782204.66 | 25 | 1.29 | 1.82
P002 | Logistics | SUP044 | 2025-08 | 2025-04-24 | 1321025.88 | 1101569 | -219456.88 | 219456.88 | 1 | 2025-08-28 | 3 | 1594716.74 | -273690.86 | DOWN | 0.2072 | 126 | Low | 391987.33 | 0.322 | 3 | 709581.67 | 25 | 1.29 | 1.82
P002 | Logistics | SUP044 | 2025-08 | 2025-05-21 | 1201042.25 | 1101569 | -99473.25 | 99473.25 | 0 | 2025-08-28 | 4 | 1321025.88 | -119983.63 | DOWN | 0.0999 | 99 | Low | 501440.83 | 0.415 | 4 | 600128.17 | 25 | 1.29 | 1.82
P002 | Logistics | SUP044 | 2025-08 | 2025-08-05 | 1170042.61 | 1101569 | -68473.61 | 68473.61 | 0 | 2025-08-28 | 5 | 1201042.25 | -30999.64 | DOWN | 0.0265 | 23 | High | 758214.91 | 0.675 | 3 | 343354.09 | 25 | 1.29 | 1.82
P002 | Electronics | SUP044 | 2025-09 | 2025-07-08 | 2050733.07 | 1072874 | -977859.07 | 977859.07 | 1 | 2025-09-28 | 1 |  |  |  |  | 82 | Low | 921188.45 | 0.468 | 5 | 151685.55 | 25 | 1.38 | 1.58
P002 | Electronics | SUP044 | 2025-09 | 2025-08-06 | 1491567.41 | 1072874 | -418693.41 | 418693.41 | 1 | 2025-09-28 | 2 | 2050733.07 | -559165.66 | DOWN | 0.3749 | 53 | Low | 791095.11 | 0.566 | 6 | 281778.89 | 25 | 1.38 | 1.58
P002 | Electronics | SUP044 | 2025-09 | 2025-08-13 | 1280471.15 | 1072874 | -207597.15 | 207597.15 | 1 | 2025-09-28 | 3 | 1491567.41 | -211096.26 | DOWN | 0.1649 | 46 | Low | 724041.96 | 0.59 | 3 | 348832.04 | 25 | 1.38 | 1.58
P002 | Electronics | SUP044 | 2025-09 | 2025-09-08 | 1169316.69 | 1072874 | -96442.69 | 96442.69 | 0 | 2025-09-28 | 4 | 1280471.15 | -111154.46 | DOWN | 0.0951 | 20 | Medium | 802351.57 | 0.678 | 3 | 270522.43 | 25 | 1.38 | 1.58
P002 | Electronics | SUP044 | 2025-09 | 2025-09-12 | 1128272.51 | 1072874 | -55398.51 | 55398.51 | 0 | 2025-09-28 | 5 | 1169316.69 | -41044.18 | DOWN | 0.0364 | 16 | High | 809361.21 | 0.692 | 7 | 263512.79 | 25 | 1.38 | 1.58
P002 | Software | SUP044 | 2025-10 | 2025-06-28 | 2620982.86 | 1389006 | -1231976.86 | 1231976.86 | 1 | 2025-10-28 | 1 |  |  |  |  | 122 | Low | 850270.67 | 0.318 | 3 | 538735.33 | 21 | 1.76 | 1.29
P002 | Software | SUP044 | 2025-10 | 2025-08-17 | 1956273.77 | 1389006 | -567267.77 | 567267.77 | 1 | 2025-10-28 | 2 | 2620982.86 | -664709.09 | DOWN | 0.3398 | 72 | Low | 958304.73 | 0.481 | 2 | 430701.27 | 21 | 1.76 | 1.29
P002 | Software | SUP044 | 2025-10 | 2025-09-05 | 1641017.46 | 1389006 | -252011.46 | 252011.46 | 1 | 2025-10-28 | 3 | 1956273.77 | -315256.31 | DOWN | 0.1921 | 53 | Low | 883194.04 | 0.543 | 4 | 505811.96 | 21 | 1.76 | 1.29
P002 | Software | SUP044 | 2025-10 | 2025-10-02 | 1527343.36 | 1389006 | -138337.36 | 138337.36 | 0 | 2025-10-28 | 4 | 1641017.46 | -113674.1 | DOWN | 0.0744 | 26 | Medium | 892106.76 | 0.63 | 3 | 496899.24 | 21 | 1.76 | 1.29
P002 | Services | SUP044 | 2025-11 | 2025-06-03 | 3769209.11 | 2062347 | -1706862.11 | 1706862.11 | 1 | 2025-11-28 | 1 |  |  |  |  | 178 | Low | 557082.9 | 0.146 | 2 | 1505264.1 | 26 | 1.59 | 1.38
P002 | Services | SUP044 | 2025-11 | 2025-07-20 | 2785208.89 | 2062347 | -722861.89 | 722861.89 | 1 | 2025-11-28 | 2 | 3769209.11 | -984000.22 | DOWN | 0.3533 | 131 | Low | 755549.16 | 0.295 | 2 | 1306797.84 | 26 | 1.59 | 1.38
P002 | Services | SUP044 | 2025-11 | 2025-08-17 | 2403190.2 | 2062347 | -340843.2 | 340843.2 | 0 | 2025-11-28 | 3 | 2785208.89 | -382018.69 | DOWN | 0.159 | 103 | Low | 949158.04 | 0.387 | 1 | 1113188.96 | 26 | 1.59 | 1.38
P002 | Services | SUP044 | 2025-11 | 2025-08-21 | 2184960.29 | 2062347 | -122613.29 | 122613.29 | 0 | 2025-11-28 | 4 | 2403190.2 | -218229.91 | DOWN | 0.0999 | 99 | Low | 906238.52 | 0.401 | 4 | 1156108.48 | 26 | 1.59 | 1.38
P002 | Services | SUP044 | 2025-11 | 2025-09-03 | 2119208.74 | 2062347 | -56861.74 | 56861.74 | 0 | 2025-11-28 | 5 | 2184960.29 | -65751.55 | DOWN | 0.031 | 86 | Low | 889888.76 | 0.444 | 4 | 1172458.24 | 26 | 1.59 | 1.38
P002 | Services | SUP044 | 2025-11 | 2025-11-09 | 2094385.8 | 2062347 | -32038.8 | 32038.8 | 0 | 2025-11-28 | 6 | 2119208.74 | -24822.94 | DOWN | 0.0119 | 19 | Medium | 1420103.72 | 0.666 | 3 | 642243.28 | 26 | 1.59 | 1.38
P002 | Software | SUP044 | 2025-12 | 2025-07-08 | 2471721.79 | 1335364 | -1136357.79 | 1136357.79 | 1 | 2025-12-28 | 1 |  |  |  |  | 173 | Low | 399173.34 | 0.158 | 1 | 936190.66 | 27 | 1.43 | 1.4
P002 | Software | SUP044 | 2025-12 | 2025-07-17 | 1800174.91 | 1335364 | -464810.91 | 464810.91 | 1 | 2025-12-28 | 2 | 2471721.79 | -671546.88 | DOWN | 0.373 | 164 | Low | 357859.74 | 0.189 | 0 | 977504.26 | 27 | 1.43 | 1.4
P002 | Software | SUP044 | 2025-12 | 2025-08-15 | 1557734.74 | 1335364 | -222370.74 | 222370.74 | 0 | 2025-12-28 | 3 | 1800174.91 | -242440.17 | DOWN | 0.1556 | 135 | Low | 438225.61 | 0.287 | 1 | 897138.39 | 27 | 1.43 | 1.4
P002 | Software | SUP044 | 2025-12 | 2025-10-14 | 1400708.15 | 1335364 | -65344.15 | 65344.15 | 0 | 2025-12-28 | 4 | 1557734.74 | -157026.59 | DOWN | 0.1121 | 75 | Low | 665404.24 | 0.489 | 3 | 669959.76 | 27 | 1.43 | 1.4
P002 | Software | SUP044 | 2025-12 | 2025-10-20 | 1376552.65 | 1335364 | -41188.65 | 41188.65 | 0 | 2025-12-28 | 5 | 1400708.15 | -24155.5 | DOWN | 0.0175 | 69 | Low | 715646.6 | 0.509 | 0 | 619717.4 | 27 | 1.43 | 1.4
P002 | Materials | SUP025 | 2025-01 | 2024-08-17 | 5371643.91 | 2845584 | -2526059.91 | 2526059.91 | 1 | 2025-01-28 | 1 |  |  |  |  | 164 | Low | 706519.65 | 0.133 | 1 | 2139064.35 | 20 | 1.45 | 1.35
P002 | Materials | SUP025 | 2025-01 | 2024-08-18 | 4314374.87 | 2845584 | -1468790.87 | 1468790.87 | 1 | 2025-01-28 | 2 | 5371643.91 | -1057269.04 | DOWN | 0.2451 | 163 | Low | 549027.31 | 0.135 | 0 | 2296556.69 | 20 | 1.45 | 1.35
P002 | Materials | SUP025 | 2025-01 | 2024-09-23 | 3771161 | 2845584 | -925577 | 925577 | 1 | 2025-01-28 | 3 | 4314374.87 | -543213.87 | DOWN | 0.144 | 127 | Low | 825439.59 | 0.221 | 2 | 2020144.41 | 20 | 1.45 | 1.35
P002 | Electronics | SUP025 | 2025-02 | 2024-09-06 | 4160776.78 | 2108265 | -2052511.78 | 2052511.78 | 1 | 2025-02-28 | 1 |  |  |  |  | 175 | Low | 460577.56 | 0.107 | 5 | 1647687.44 | 23 | 1.4 | 1.5
P002 | Electronics | SUP025 | 2025-02 | 2024-09-06 | 3363042.09 | 2108265 | -1254777.09 | 1254777.09 | 1 | 2025-02-28 | 2 | 4160776.78 | -797734.69 | DOWN | 0.2372 | 175 | Low | 366516.38 | 0.107 | 1 | 1741748.62 | 23 | 1.4 | 1.5
P002 | Electronics | SUP025 | 2025-02 | 2024-09-22 | 2802582.82 | 2108265 | -694317.82 | 694317.82 | 1 | 2025-02-28 | 3 | 3363042.09 | -560459.27 | DOWN | 0.2 | 159 | Low | 433348.17 | 0.146 | 1 | 1674916.83 | 23 | 1.4 | 1.5
P002 | Electronics | SUP025 | 2025-02 | 2024-12-29 | 2506839.23 | 2108265 | -398574.23 | 398574.23 | 1 | 2025-02-28 | 4 | 2802582.82 | -295743.59 | DOWN | 0.118 | 61 | Low | 1020003.06 | 0.379 | 0 | 1088261.94 | 23 | 1.4 | 1.5
P002 | Electronics | SUP025 | 2025-02 | 2025-01-31 | 2322389.35 | 2108265 | -214124.35 | 214124.35 | 0 | 2025-02-28 | 5 | 2506839.23 | -184449.88 | DOWN | 0.0794 | 28 | Low | 1010667.08 | 0.458 | 7 | 1097597.92 | 23 | 1.4 | 1.5
P002 | Electronics | SUP025 | 2025-02 | 2025-02-14 | 2222002.92 | 2108265 | -113737.92 | 113737.92 | 0 | 2025-02-28 | 6 | 2322389.35 | -100386.43 | DOWN | 0.0452 | 14 | Low | 1052323.08 | 0.491 | 2 | 1055941.92 | 23 | 1.4 | 1.5
P002 | Software | SUP025 | 2025-03 | 2024-12-30 | 5323063.6 | 2088954 | -3234109.6 | 3234109.6 | 1 | 2025-03-28 | 1 |  |  |  |  | 88 | Low | 1473065.17 | 0.286 | 0 | 615888.83 | 25 | 2.28 | 1.97
P002 | Software | SUP025 | 2025-03 | 2025-02-03 | 3963178.01 | 2088954 | -1874224.01 | 1874224.01 | 1 | 2025-03-28 | 2 | 5323063.6 | -1359885.59 | DOWN | 0.3431 | 53 | Low | 1490492.5 | 0.362 | 5 | 598461.5 | 25 | 2.28 | 1.97
P002 | Software | SUP025 | 2025-03 | 2025-02-19 | 3238710.61 | 2088954 | -1149756.61 | 1149756.61 | 1 | 2025-03-28 | 3 | 3963178.01 | -724467.4 | DOWN | 0.2237 | 37 | Low | 1225264.12 | 0.397 | 5 | 863689.88 | 25 | 2.28 | 1.97
P002 | Electronics | SUP025 | 2025-04 | 2024-11-24 | 368253.15 | 194604 | -173649.15 | 173649.15 | 1 | 2025-04-28 | 1 |  |  |  |  | 155 | Low | 59010.74 | 0.161 | 2 | 135593.26 | 21 | 1.06 | 1.67
P002 | Electronics | SUP025 | 2025-04 | 2025-02-05 | 299342.47 | 194604 | -104738.47 | 104738.47 | 1 | 2025-04-28 | 2 | 368253.15 | -68910.68 | DOWN | 0.2302 | 82 | Low | 106927.22 | 0.343 | 3 | 87676.78 | 21 | 1.06 | 1.67
P002 | Electronics | SUP025 | 2025-04 | 2025-02-20 | 256642.7 | 194604 | -62038.7 | 62038.7 | 1 | 2025-04-28 | 3 | 299342.47 | -42699.77 | DOWN | 0.1664 | 67 | Low | 90812.64 | 0.38 | 2 | 103791.36 | 21 | 1.06 | 1.67
P002 | Logistics | SUP025 | 2025-05 | 2025-01-16 | 6045906.93 | 2733771 | -3312135.93 | 3312135.93 | 1 | 2025-05-28 | 1 |  |  |  |  | 132 | Low | 1162595.33 | 0.194 | 0 | 1571175.67 | 28 | 2.1 | 0.99
P002 | Logistics | SUP025 | 2025-05 | 2025-03-20 | 4561325.81 | 2733771 | -1827554.81 | 1827554.81 | 1 | 2025-05-28 | 2 | 6045906.93 | -1484581.12 | DOWN | 0.3255 | 69 | Low | 1464455.24 | 0.333 | 4 | 1269315.76 | 28 | 2.1 | 0.99
P002 | Logistics | SUP025 | 2025-05 | 2025-03-23 | 3909451.54 | 2733771 | -1175680.54 | 1175680.54 | 1 | 2025-05-28 | 3 | 4561325.81 | -651874.27 | DOWN | 0.1667 | 66 | Low | 1340110.94 | 0.34 | 4 | 1393660.06 | 28 | 2.1 | 0.99
P002 | Logistics | SUP025 | 2025-05 | 2025-04-21 | 3575832.85 | 2733771 | -842061.85 | 842061.85 | 1 | 2025-05-28 | 4 | 3909451.54 | -333618.69 | DOWN | 0.0933 | 37 | Low | 1384889.9 | 0.404 | 5 | 1348881.1 | 28 | 2.1 | 0.99
P002 | Logistics | SUP025 | 2025-05 | 2025-05-06 | 3282080.59 | 2733771 | -548309.59 | 548309.59 | 1 | 2025-05-28 | 5 | 3575832.85 | -293752.26 | DOWN | 0.0895 | 22 | Low | 1521204.95 | 0.437 | 0 | 1212566.05 | 28 | 2.1 | 0.99
P002 | Materials | SUP025 | 2025-06 | 2025-01-21 | 992523.61 | 486061 | -506462.61 | 506462.61 | 1 | 2025-06-28 | 1 |  |  |  |  | 158 | Low | 139373.97 | 0.15 | 2 | 346687.03 | 17 | 1.27 | 1.62
P002 | Materials | SUP025 | 2025-06 | 2025-03-18 | 791228.04 | 486061 | -305167.04 | 305167.04 | 1 | 2025-06-28 | 2 | 992523.61 | -201295.57 | DOWN | 0.2544 | 102 | Low | 238010.32 | 0.286 | 0 | 248050.68 | 17 | 1.27 | 1.62
P002 | Materials | SUP025 | 2025-06 | 2025-04-20 | 671535.79 | 486061 | -185474.79 | 185474.79 | 1 | 2025-06-28 | 3 | 791228.04 | -119692.25 | DOWN | 0.1782 | 69 | Low | 235782.61 | 0.366 | 0 | 250278.39 | 17 | 1.27 | 1.62
P002 | Logistics | SUP025 | 2025-07 | 2025-02-09 | 5664948.81 | 2730205 | -2934743.81 | 2934743.81 | 1 | 2025-07-28 | 1 |  |  |  |  | 169 | Low | 735873.32 | 0.12 | 0 | 1994331.68 | 24 | 1.49 | 1.96
P002 | Logistics | SUP025 | 2025-07 | 2025-04-01 | 4448787.65 | 2730205 | -1718582.65 | 1718582.65 | 1 | 2025-07-28 | 2 | 5664948.81 | -1216161.16 | DOWN | 0.2734 | 118 | Low | 1122381.14 | 0.241 | 0 | 1607823.86 | 24 | 1.49 | 1.96
P002 | Logistics | SUP025 | 2025-07 | 2025-04-08 | 3699806.73 | 2730205 | -969601.73 | 969601.73 | 1 | 2025-07-28 | 3 | 4448787.65 | -748980.92 | DOWN | 0.2024 | 111 | Low | 1008501.05 | 0.257 | 3 | 1721703.95 | 24 | 1.49 | 1.96
P002 | Logistics | SUP025 | 2025-07 | 2025-04-17 | 3275767.56 | 2730205 | -545562.56 | 545562.56 | 1 | 2025-07-28 | 4 | 3699806.73 | -424039.17 | DOWN | 0.1294 | 102 | Low | 855391.64 | 0.279 | 6 | 1874813.36 | 24 | 1.49 | 1.96
P002 | Logistics | SUP025 | 2025-07 | 2025-07-05 | 3106747.9 | 2730205 | -376542.9 | 376542.9 | 0 | 2025-07-28 | 5 | 3275767.56 | -169019.66 | DOWN | 0.0544 | 23 | Low | 1399424.53 | 0.465 | 1 | 1330780.47 | 24 | 1.49 | 1.96
P002 | Logistics | SUP025 | 2025-07 | 2025-07-11 | 2954792.88 | 2730205 | -224587.88 | 224587.88 | 0 | 2025-07-28 | 6 | 3106747.9 | -151955.02 | DOWN | 0.0514 | 17 | Low | 1381935.43 | 0.479 | 4 | 1348269.57 | 24 | 1.49 | 1.96
P002 | Logistics | SUP025 | 2025-08 | 2025-04-03 | 1722379.19 | 877141 | -845238.19 | 845238.19 | 1 | 2025-08-28 | 1 |  |  |  |  | 147 | Low | 295631.44 | 0.176 | 2 | 581509.56 | 25 | 1.29 | 1.82
P002 | Logistics | SUP025 | 2025-08 | 2025-04-13 | 1382072.49 | 877141 | -504931.49 | 504931.49 | 1 | 2025-08-28 | 2 | 1722379.19 | -340306.7 | DOWN | 0.2462 | 137 | Low | 295830.03 | 0.201 | 3 | 581310.97 | 25 | 1.29 | 1.82
P002 | Logistics | SUP025 | 2025-08 | 2025-04-27 | 1146319.98 | 877141 | -269178.98 | 269178.98 | 1 | 2025-08-28 | 3 | 1382072.49 | -235752.51 | DOWN | 0.2057 | 123 | Low | 272914.43 | 0.234 | 0 | 604226.57 | 25 | 1.29 | 1.82
P002 | Logistics | SUP025 | 2025-08 | 2025-06-04 | 1052678.91 | 877141 | -175537.91 | 175537.91 | 1 | 2025-08-28 | 4 | 1146319.98 | -93641.07 | DOWN | 0.089 | 85 | Low | 330078.77 | 0.326 | 1 | 547062.23 | 25 | 1.29 | 1.82
P002 | Logistics | SUP025 | 2025-08 | 2025-06-07 | 967491.98 | 877141 | -90350.98 | 90350.98 | 0 | 2025-08-28 | 5 | 1052678.91 | -85186.93 | DOWN | 0.088 | 82 | Low | 321440.73 | 0.333 | 4 | 555700.27 | 25 | 1.29 | 1.82
P002 | Logistics | SUP025 | 2025-08 | 2025-06-29 | 929904.96 | 877141 | -52763.96 | 52763.96 | 0 | 2025-08-28 | 6 | 967491.98 | -37587.02 | DOWN | 0.0404 | 60 | Low | 373061.39 | 0.387 | 1 | 504079.61 | 25 | 1.29 | 1.82
P002 | Software | SUP025 | 2025-09 | 2025-05-19 | 1349029.9 | 631127 | -717902.9 | 717902.9 | 1 | 2025-09-28 | 1 |  |  |  |  | 132 | Low | 303734 | 0.21 | 5 | 327393 | 25 | 1.38 | 1.58
P002 | Software | SUP025 | 2025-09 | 2025-06-14 | 1067047.11 | 631127 | -435920.11 | 435920.11 | 1 | 2025-09-28 | 2 | 1349029.9 | -281982.79 | DOWN | 0.2643 | 106 | Low | 298223.29 | 0.273 | 3 | 332903.71 | 25 | 1.38 | 1.58
P002 | Software | SUP025 | 2025-09 | 2025-08-04 | 914959.47 | 631127 | -283832.47 | 283832.47 | 1 | 2025-09-28 | 3 | 1067047.11 | -152087.64 | DOWN | 0.1662 | 55 | Low | 352663.32 | 0.395 | 1 | 278463.68 | 25 | 1.38 | 1.58
P002 | Software | SUP025 | 2025-09 | 2025-08-25 | 801786.54 | 631127 | -170659.54 | 170659.54 | 1 | 2025-09-28 | 4 | 914959.47 | -113172.93 | DOWN | 0.1412 | 34 | Low | 375483.48 | 0.445 | 4 | 255643.52 | 25 | 1.38 | 1.58
P002 | Services | SUP025 | 2025-10 | 2025-07-01 | 5176015.42 | 2252241 | -2923774.42 | 2923774.42 | 1 | 2025-10-28 | 1 |  |  |  |  | 119 | Low | 1281867.94 | 0.231 | 5 | 970373.06 | 21 | 1.76 | 1.29
P002 | Services | SUP025 | 2025-10 | 2025-07-10 | 4001273.39 | 2252241 | -1749032.39 | 1749032.39 | 1 | 2025-10-28 | 2 | 5176015.42 | -1174742.03 | DOWN | 0.2936 | 110 | Low | 1019949.56 | 0.252 | 2 | 1232291.44 | 21 | 1.76 | 1.29
P002 | Services | SUP025 | 2025-10 | 2025-08-29 | 3226543.31 | 2252241 | -974302.31 | 974302.31 | 1 | 2025-10-28 | 3 | 4001273.39 | -774730.08 | DOWN | 0.2401 | 60 | Low | 1257146.46 | 0.367 | 4 | 995094.54 | 21 | 1.76 | 1.29
P002 | Services | SUP025 | 2025-10 | 2025-09-08 | 2868805.67 | 2252241 | -616564.67 | 616564.67 | 1 | 2025-10-28 | 4 | 3226543.31 | -357737.64 | DOWN | 0.1247 | 50 | Low | 1169953.08 | 0.389 | 4 | 1082287.92 | 21 | 1.76 | 1.29
P002 | Electronics | SUP025 | 2025-11 | 2025-06-13 | 1901270.76 | 1017352 | -883918.76 | 883918.76 | 1 | 2025-11-28 | 1 |  |  |  |  | 168 | Low | 243580.02 | 0.121 | 2 | 773771.98 | 26 | 1.59 | 1.38
P002 | Electronics | SUP025 | 2025-11 | 2025-09-18 | 1529919.04 | 1017352 | -512567.04 | 512567.04 | 1 | 2025-11-28 | 2 | 1901270.76 | -371351.72 | DOWN | 0.2427 | 71 | Low | 508456.48 | 0.348 | 0 | 508895.52 | 26 | 1.59 | 1.38
P002 | Electronics | SUP025 | 2025-11 | 2025-10-03 | 1312629.36 | 1017352 | -295277.36 | 295277.36 | 1 | 2025-11-28 | 3 | 1529919.04 | -217289.68 | DOWN | 0.1655 | 56 | Low | 531602.09 | 0.383 | 2 | 485749.91 | 26 | 1.59 | 1.38
P002 | Logistics | SUP025 | 2025-12 | 2025-08-08 | 980129.5 | 447101 | -533028.5 | 533028.5 | 1 | 2025-12-28 | 1 |  |  |  |  | 142 | Low | 192557.99 | 0.185 | 2 | 254543.01 | 27 | 1.43 | 1.4
P002 | Logistics | SUP025 | 2025-12 | 2025-11-03 | 767752.85 | 447101 | -320651.85 | 320651.85 | 1 | 2025-12-28 | 2 | 980129.5 | -212376.65 | DOWN | 0.2766 | 55 | Low | 280555.93 | 0.392 | 3 | 166545.07 | 27 | 1.43 | 1.4
P002 | Logistics | SUP025 | 2025-12 | 2025-11-27 | 648175.78 | 447101 | -201074.78 | 201074.78 | 1 | 2025-12-28 | 3 | 767752.85 | -119577.07 | DOWN | 0.1845 | 31 | Low | 300986.54 | 0.449 | 6 | 146114.46 | 27 | 1.43 | 1.4
P002 | Logistics | SUP042 | 2025-01 | 2024-08-03 | 519267.07 | 270399 | -248868.07 | 248868.07 | 1 | 2025-01-28 | 1 |  |  |  |  | 178 | Low | 75593.46 | 0.148 | 0 | 194805.54 | 20 | 1.45 | 1.35
P002 | Logistics | SUP042 | 2025-01 | 2024-09-24 | 384645.4 | 270399 | -114246.4 | 114246.4 | 1 | 2025-01-28 | 2 | 519267.07 | -134621.67 | DOWN | 0.35 | 126 | Low | 117956.28 | 0.316 | 2 | 152442.72 | 20 | 1.45 | 1.35
P002 | Logistics | SUP042 | 2025-01 | 2024-11-04 | 320399.57 | 270399 | -50000.57 | 50000.57 | 1 | 2025-01-28 | 3 | 384645.4 | -64245.83 | DOWN | 0.2005 | 85 | Low | 144323.52 | 0.454 | 0 | 126075.48 | 20 | 1.45 | 1.35
P002 | Electronics | SUP042 | 2025-02 | 2024-09-05 | 2854166.63 | 1659343 | -1194823.63 | 1194823.63 | 1 | 2025-02-28 | 1 |  |  |  |  | 176 | Low | 431297.8 | 0.149 | 0 | 1228045.2 | 23 | 1.4 | 1.5
P002 | Electronics | SUP042 | 2025-02 | 2024-10-24 | 2201354.43 | 1659343 | -542011.43 | 542011.43 | 1 | 2025-02-28 | 2 | 2854166.63 | -652812.2 | DOWN | 0.2966 | 127 | Low | 663812.48 | 0.315 | 2 | 995530.52 | 23 | 1.4 | 1.5
P002 | Electronics | SUP042 | 2025-02 | 2024-11-21 | 1882050.41 | 1659343 | -222707.41 | 222707.41 | 0 | 2025-02-28 | 3 | 2201354.43 | -319304.02 | DOWN | 0.1697 | 99 | Low | 825012.43 | 0.409 | 1 | 834330.57 | 23 | 1.4 | 1.5
P002 | Electronics | SUP042 | 2025-02 | 2025-02-13 | 1742761.33 | 1659343 | -83418.33 | 83418.33 | 0 | 2025-02-28 | 4 | 1882050.41 | -139289.08 | DOWN | 0.0799 | 15 | Medium | 1256043.79 | 0.694 | 5 | 403299.21 | 23 | 1.4 | 1.5
P002 | Electronics | SUP042 | 2025-02 | 2025-02-15 | 1705627.66 | 1659343 | -46284.66 | 46284.66 | 0 | 2025-02-28 | 5 | 1742761.33 | -37133.67 | DOWN | 0.0218 | 13 | High | 1157203.07 | 0.7 | 0 | 502139.93 | 23 | 1.4 | 1.5
P002 | Logistics | SUP042 | 2025-03 | 2024-10-31 | 3891795.54 | 1815485 | -2076310.54 | 2076310.54 | 1 | 2025-03-28 | 1 |  |  |  |  | 148 | Low | 841800.25 | 0.221 | 5 | 973684.75 | 25 | 2.28 | 1.97
P002 | Logistics | SUP042 | 2025-03 | 2024-11-12 | 2596198.15 | 1815485 | -780713.15 | 780713.15 | 1 | 2025-03-28 | 2 | 3891795.54 | -1295597.39 | DOWN | 0.499 | 136 | Low | 628376.35 | 0.258 | 0 | 1187108.65 | 25 | 2.28 | 1.97
P002 | Logistics | SUP042 | 2025-03 | 2024-11-25 | 2087511.73 | 1815485 | -272026.73 | 272026.73 | 0 | 2025-03-28 | 3 | 2596198.15 | -508686.42 | DOWN | 0.2437 | 123 | Low | 665556.46 | 0.298 | 6 | 1149928.54 | 25 | 2.28 | 1.97
P002 | Logistics | SUP042 | 2025-03 | 2024-11-26 | 1962357.54 | 1815485 | -146872.54 | 146872.54 | 0 | 2025-03-28 | 4 | 2087511.73 | -125154.19 | DOWN | 0.0638 | 122 | Low | 566207.96 | 0.301 | 2 | 1249277.04 | 25 | 2.28 | 1.97
P002 | Logistics | SUP042 | 2025-03 | 2025-02-23 | 1957650.67 | 1815485 | -142165.67 | 142165.67 | 0 | 2025-03-28 | 5 | 1962357.54 | -4706.87 | DOWN | 0.0024 | 33 | Low | 1165832.68 | 0.575 | 2 | 649652.32 | 25 | 2.28 | 1.97
P002 | Logistics | SUP042 | 2025-03 | 2025-03-06 | 1790640.66 | 1815485 | 24844.34 | 24844.34 | 0 | 2025-03-28 | 6 | 1957650.67 | -167010.01 | DOWN | 0.0933 | 22 | Low | 1038689.93 | 0.609 | 4 | 776795.07 | 25 | 2.28 | 1.97
P002 | Materials | SUP042 | 2025-04 | 2024-11-10 | 353198.19 | 227652 | -125546.19 | 125546.19 | 1 | 2025-04-28 | 1 |  |  |  |  | 169 | Low | 59913.41 | 0.18 | 1 | 167738.59 | 21 | 1.06 | 1.67
P002 | Materials | SUP042 | 2025-04 | 2025-01-09 | 281524.3 | 227652 | -53872.3 | 53872.3 | 1 | 2025-04-28 | 2 | 353198.19 | -71673.89 | DOWN | 0.2546 | 109 | Low | 103815.38 | 0.391 | 4 | 123836.62 | 21 | 1.06 | 1.67
P002 | Materials | SUP042 | 2025-04 | 2025-01-19 | 253849.61 | 227652 | -26197.61 | 26197.61 | 0 | 2025-04-28 | 3 | 281524.3 | -27674.69 | DOWN | 0.109 | 99 | Low | 108683.27 | 0.426 | 1 | 118968.73 | 21 | 1.06 | 1.67
P002 | Materials | SUP042 | 2025-04 | 2025-03-23 | 240159.05 | 227652 | -12507.05 | 12507.05 | 0 | 2025-04-28 | 4 | 253849.61 | -13690.56 | DOWN | 0.057 | 36 | Medium | 145277.55 | 0.648 | 7 | 82374.45 | 21 | 1.06 | 1.67
P002 | Materials | SUP042 | 2025-04 | 2025-03-31 | 234463.07 | 227652 | -6811.07 | 6811.07 | 0 | 2025-04-28 | 5 | 240159.05 | -5695.98 | DOWN | 0.0243 | 28 | High | 156952.62 | 0.676 | 3 | 70699.38 | 21 | 1.06 | 1.67
P002 | Services | SUP042 | 2025-05 | 2025-01-26 | 3673388.26 | 1641970 | -2031418.26 | 2031418.26 | 1 | 2025-05-28 | 1 |  |  |  |  | 122 | Low | 1125506.05 | 0.307 | 2 | 516463.95 | 28 | 2.1 | 0.99
P002 | Services | SUP042 | 2025-05 | 2025-02-09 | 2550272.8 | 1641970 | -908302.8 | 908302.8 | 1 | 2025-05-28 | 2 | 3673388.26 | -1123115.46 | DOWN | 0.4404 | 108 | Low | 937218.2 | 0.351 | 0 | 704751.8 | 28 | 2.1 | 0.99
P002 | Services | SUP042 | 2025-05 | 2025-02-14 | 2077220.66 | 1641970 | -435250.66 | 435250.66 | 1 | 2025-05-28 | 3 | 2550272.8 | -473052.14 | DOWN | 0.2277 | 103 | Low | 730590.59 | 0.366 | 2 | 911379.41 | 28 | 2.1 | 0.99
P002 | Services | SUP042 | 2025-05 | 2025-03-13 | 1864322.88 | 1641970 | -222352.88 | 222352.88 | 0 | 2025-05-28 | 4 | 2077220.66 | -212897.78 | DOWN | 0.1142 | 76 | Low | 811166.03 | 0.451 | 1 | 830803.97 | 28 | 2.1 | 0.99
P002 | Services | SUP042 | 2025-06 | 2025-01-12 | 1044083.22 | 526165 | -517918.22 | 517918.22 | 1 | 2025-06-28 | 1 |  |  |  |  | 167 | Low | 199633.11 | 0.182 | 4 | 326531.89 | 17 | 1.27 | 1.62
P002 | Services | SUP042 | 2025-06 | 2025-02-11 | 753713.1 | 526165 | -227548.1 | 227548.1 | 1 | 2025-06-28 | 2 | 1044083.22 | -290370.12 | DOWN | 0.3853 | 137 | Low | 201775.39 | 0.285 | 3 | 324389.61 | 17 | 1.27 | 1.62
P002 | Services | SUP042 | 2025-06 | 2025-02-12 | 626633.26 | 526165 | -100468.26 | 100468.26 | 1 | 2025-06-28 | 3 | 753713.1 | -127079.84 | DOWN | 0.2028 | 136 | Low | 168162.15 | 0.288 | 5 | 358002.85 | 17 | 1.27 | 1.62
P002 | Services | SUP042 | 2025-06 | 2025-03-23 | 572168.78 | 526165 | -46003.78 | 46003.78 | 0 | 2025-06-28 | 4 | 626633.26 | -54464.48 | DOWN | 0.0952 | 97 | Low | 251539.48 | 0.422 | 2 | 274625.52 | 17 | 1.27 | 1.62
P002 | Services | SUP042 | 2025-06 | 2025-05-25 | 549185.72 | 526165 | -23020.72 | 23020.72 | 0 | 2025-06-28 | 5 | 572168.78 | -22983.06 | DOWN | 0.0418 | 34 | Medium | 330531.56 | 0.639 | 4 | 195633.44 | 17 | 1.27 | 1.62
P002 | Services | SUP042 | 2025-06 | 2025-05-30 | 539108.09 | 526165 | -12943.09 | 12943.09 | 0 | 2025-06-28 | 6 | 549185.72 | -10077.63 | DOWN | 0.0187 | 29 | High | 363615.45 | 0.656 | 9 | 162549.55 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP042 | 2025-07 | 2025-06-06 | 773208.12 | 522239 | -250969.12 | 250969.12 | 1 | 2025-07-28 | 1 |  |  |  |  | 52 | Medium | 456861.38 | 0.563 | 5 | 65377.62 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP042 | 2025-07 | 2025-07-06 | 634207.94 | 522239 | -111968.94 | 111968.94 | 1 | 2025-07-28 | 2 | 773208.12 | -139000.18 | DOWN | 0.2192 | 22 | Low | 430940.3 | 0.663 | 8 | 91298.7 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP042 | 2025-07 | 2025-07-12 | 572964.71 | 522239 | -50725.71 | 50725.71 | 0 | 2025-07-28 | 3 | 634207.94 | -61243.23 | DOWN | 0.1069 | 16 | Medium | 414288.62 | 0.683 | 7 | 107950.38 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP042 | 2025-08 | 2025-03-03 | 1362774.43 | 890030 | -472744.43 | 472744.43 | 1 | 2025-08-28 | 1 |  |  |  |  | 178 | Low | 214226.8 | 0.151 | 0 | 675803.2 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP042 | 2025-08 | 2025-04-13 | 1095800.9 | 890030 | -205770.9 | 205770.9 | 1 | 2025-08-28 | 2 | 1362774.43 | -266973.53 | DOWN | 0.2436 | 137 | Low | 316648.4 | 0.284 | 2 | 573381.6 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP042 | 2025-08 | 2025-06-17 | 982192.82 | 890030 | -92162.82 | 92162.82 | 0 | 2025-08-28 | 3 | 1095800.9 | -113608.08 | DOWN | 0.1157 | 72 | Low | 512041.17 | 0.507 | 2 | 377988.83 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP042 | 2025-08 | 2025-07-06 | 935249.52 | 890030 | -45219.52 | 45219.52 | 0 | 2025-08-28 | 4 | 982192.82 | -46943.3 | DOWN | 0.0502 | 53 | Medium | 538723.25 | 0.572 | 3 | 351306.75 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP042 | 2025-08 | 2025-08-11 | 899517.81 | 890030 | -9487.81 | 9487.81 | 0 | 2025-08-28 | 5 | 935249.52 | -35731.71 | DOWN | 0.0397 | 17 | High | 597536.58 | 0.696 | 6 | 292493.42 | 25 | 1.29 | 1.82
P002 | Software | SUP042 | 2025-09 | 2025-04-24 | 955459.87 | 509907 | -445552.87 | 445552.87 | 1 | 2025-09-28 | 1 |  |  |  |  | 157 | Low | 207847.53 | 0.214 | 3 | 302059.47 | 25 | 1.38 | 1.58
P002 | Software | SUP042 | 2025-09 | 2025-05-28 | 696498.81 | 509907 | -186591.81 | 186591.81 | 1 | 2025-09-28 | 2 | 955459.87 | -258961.06 | DOWN | 0.3718 | 123 | Low | 226967.41 | 0.329 | 2 | 282939.59 | 25 | 1.38 | 1.58
P002 | Software | SUP042 | 2025-09 | 2025-06-06 | 596683.79 | 509907 | -86776.79 | 86776.79 | 0 | 2025-09-28 | 3 | 696498.81 | -99815.02 | DOWN | 0.1673 | 114 | Low | 213668.82 | 0.359 | 2 | 296238.18 | 25 | 1.38 | 1.58
P002 | Software | SUP042 | 2025-09 | 2025-07-26 | 547008.88 | 509907 | -37101.88 | 37101.88 | 0 | 2025-09-28 | 4 | 596683.79 | -49674.91 | DOWN | 0.0908 | 64 | Low | 308568.92 | 0.529 | 3 | 201338.08 | 25 | 1.38 | 1.58
P002 | Software | SUP042 | 2025-09 | 2025-08-15 | 527351.28 | 509907 | -17444.28 | 17444.28 | 0 | 2025-09-28 | 5 | 547008.88 | -19657.6 | DOWN | 0.0373 | 44 | Medium | 320370.09 | 0.597 | 2 | 189536.91 | 25 | 1.38 | 1.58
P002 | Software | SUP042 | 2025-09 | 2025-09-12 | 521944.75 | 509907 | -12037.75 | 12037.75 | 0 | 2025-09-28 | 6 | 527351.28 | -5406.53 | DOWN | 0.0104 | 16 | High | 365116.91 | 0.692 | 9 | 144790.09 | 25 | 1.38 | 1.58
P002 | Electronics | SUP042 | 2025-10 | 2025-07-10 | 1647280.94 | 919791 | -727489.94 | 727489.94 | 1 | 2025-10-28 | 1 |  |  |  |  | 110 | Low | 590981.69 | 0.357 | 0 | 328809.31 | 21 | 1.76 | 1.29
P002 | Electronics | SUP042 | 2025-10 | 2025-08-02 | 1228008.97 | 919791 | -308217.97 | 308217.97 | 1 | 2025-10-28 | 2 | 1647280.94 | -419271.97 | DOWN | 0.3414 | 87 | Low | 508401.56 | 0.432 | 4 | 411389.44 | 21 | 1.76 | 1.29
P002 | Electronics | SUP042 | 2025-10 | 2025-08-09 | 1054206.85 | 919791 | -134415.85 | 134415.85 | 0 | 2025-10-28 | 3 | 1228008.97 | -173802.12 | DOWN | 0.1649 | 80 | Low | 507926.92 | 0.455 | 0 | 411864.08 | 21 | 1.76 | 1.29
P002 | Electronics | SUP042 | 2025-10 | 2025-09-12 | 970778.75 | 919791 | -50987.75 | 50987.75 | 0 | 2025-10-28 | 4 | 1054206.85 | -83428.1 | DOWN | 0.0859 | 46 | Medium | 528985.99 | 0.565 | 3 | 390805.01 | 21 | 1.76 | 1.29
P002 | Electronics | SUP042 | 2025-10 | 2025-10-01 | 936051.74 | 919791 | -16260.74 | 16260.74 | 0 | 2025-10-28 | 5 | 970778.75 | -34727.01 | DOWN | 0.0371 | 27 | Medium | 551027.56 | 0.627 | 2 | 368763.44 | 21 | 1.76 | 1.29
P002 | Electronics | SUP042 | 2025-10 | 2025-10-08 | 917475.12 | 919791 | 2315.88 | 2315.88 | 0 | 2025-10-28 | 6 | 936051.74 | -18576.62 | DOWN | 0.0202 | 20 | Medium | 614206.48 | 0.65 | 6 | 305584.52 | 21 | 1.76 | 1.29
P002 | Logistics | SUP042 | 2025-11 | 2025-06-01 | 3822550.7 | 2179479 | -1643071.7 | 1643071.7 | 1 | 2025-11-28 | 1 |  |  |  |  | 180 | Low | 600042.4 | 0.146 | 0 | 1579436.6 | 26 | 1.59 | 1.38
P002 | Logistics | SUP042 | 2025-11 | 2025-07-02 | 2940749.72 | 2179479 | -761270.72 | 761270.72 | 1 | 2025-11-28 | 2 | 3822550.7 | -881800.98 | DOWN | 0.2999 | 149 | Low | 690855.59 | 0.235 | 2 | 1488623.41 | 26 | 1.59 | 1.38
P002 | Logistics | SUP042 | 2025-11 | 2025-07-21 | 2563327.54 | 2179479 | -383848.54 | 383848.54 | 0 | 2025-11-28 | 3 | 2940749.72 | -377422.18 | DOWN | 0.1472 | 130 | Low | 703421.39 | 0.298 | 3 | 1476057.61 | 26 | 1.59 | 1.38
P002 | Logistics | SUP042 | 2025-11 | 2025-08-11 | 2385904.84 | 2179479 | -206425.84 | 206425.84 | 0 | 2025-11-28 | 4 | 2563327.54 | -177422.7 | DOWN | 0.0744 | 109 | Low | 922792.21 | 0.368 | 4 | 1256686.79 | 26 | 1.59 | 1.38
P002 | Logistics | SUP042 | 2025-11 | 2025-08-21 | 2289423.15 | 2179479 | -109944.15 | 109944.15 | 0 | 2025-11-28 | 5 | 2385904.84 | -96481.69 | DOWN | 0.0421 | 99 | Low | 961792.38 | 0.401 | 6 | 1217686.62 | 26 | 1.59 | 1.38
P002 | Logistics | SUP042 | 2025-11 | 2025-09-21 | 2207985.26 | 2179479 | -28506.26 | 28506.26 | 0 | 2025-11-28 | 6 | 2289423.15 | -81437.89 | DOWN | 0.0369 | 68 | Low | 1163921.33 | 0.503 | 7 | 1015557.67 | 26 | 1.59 | 1.38
P002 | Mechanical | SUP042 | 2025-12 | 2025-08-08 | 2188014.9 | 1532314 | -655700.9 | 655700.9 | 1 | 2025-12-28 | 1 |  |  |  |  | 142 | Low | 538864.15 | 0.263 | 5 | 993449.85 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP042 | 2025-12 | 2025-08-11 | 1843357.02 | 1532314 | -311043.02 | 311043.02 | 1 | 2025-12-28 | 2 | 2188014.9 | -344657.88 | DOWN | 0.187 | 139 | Low | 496042.37 | 0.273 | 3 | 1036271.63 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP042 | 2025-12 | 2025-08-28 | 1660270.2 | 1532314 | -127956.2 | 127956.2 | 0 | 2025-12-28 | 3 | 1843357.02 | -183086.82 | DOWN | 0.1103 | 122 | Low | 532036.74 | 0.33 | 0 | 1000277.26 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP042 | 2025-12 | 2025-09-24 | 1597389.57 | 1532314 | -65075.57 | 65075.57 | 0 | 2025-12-28 | 4 | 1660270.2 | -62880.63 | DOWN | 0.0394 | 95 | Low | 669068.17 | 0.421 | 5 | 863245.83 | 27 | 1.43 | 1.4
P002 | Mechanical | SUP042 | 2025-12 | 2025-11-25 | 1560361.93 | 1532314 | -28047.93 | 28047.93 | 0 | 2025-12-28 | 5 | 1597389.57 | -37027.64 | DOWN | 0.0237 | 33 | Medium | 956235.85 | 0.63 | 8 | 576078.15 | 27 | 1.43 | 1.4
P002 | Services | SUP037 | 2025-01 | 2024-08-11 | 4762371.14 | 2563373 | -2198998.14 | 2198998.14 | 1 | 2025-01-28 | 1 |  |  |  |  | 170 | Low | 788616.04 | 0.168 | 1 | 1774756.96 | 20 | 1.45 | 1.35
P002 | Services | SUP037 | 2025-01 | 2024-11-17 | 3510365.1 | 2563373 | -946992.1 | 946992.1 | 1 | 2025-01-28 | 2 | 4762371.14 | -1252006.04 | DOWN | 0.3567 | 72 | Low | 1719245.97 | 0.498 | 4 | 844127.03 | 20 | 1.45 | 1.35
P002 | Services | SUP037 | 2025-01 | 2024-12-11 | 2990376.2 | 2563373 | -427003.2 | 427003.2 | 0 | 2025-01-28 | 3 | 3510365.1 | -519988.9 | DOWN | 0.1739 | 48 | Low | 1799853.57 | 0.579 | 4 | 763519.43 | 20 | 1.45 | 1.35
P002 | Services | SUP037 | 2025-01 | 2024-12-18 | 2781350.23 | 2563373 | -217977.23 | 217977.23 | 0 | 2025-01-28 | 4 | 2990376.2 | -209025.97 | DOWN | 0.0752 | 41 | Medium | 1547491.45 | 0.602 | 0 | 1015881.55 | 20 | 1.45 | 1.35
P002 | Services | SUP037 | 2025-01 | 2025-01-05 | 2656458.17 | 2563373 | -93085.17 | 93085.17 | 0 | 2025-01-28 | 5 | 2781350.23 | -124892.06 | DOWN | 0.047 | 23 | Medium | 1830735.83 | 0.663 | 5 | 732637.17 | 20 | 1.45 | 1.35
P002 | Materials | SUP037 | 2025-02 | 2024-10-15 | 1358091.78 | 789771 | -568320.78 | 568320.78 | 1 | 2025-02-28 | 1 |  |  |  |  | 136 | Low | 406847.23 | 0.284 | 1 | 382923.77 | 23 | 1.4 | 1.5
P002 | Materials | SUP037 | 2025-02 | 2024-10-17 | 1045445.86 | 789771 | -255674.86 | 255674.86 | 1 | 2025-02-28 | 2 | 1358091.78 | -312645.92 | DOWN | 0.2991 | 134 | Low | 307098.12 | 0.291 | 4 | 482672.88 | 23 | 1.4 | 1.5
P002 | Materials | SUP037 | 2025-02 | 2024-10-20 | 902482.62 | 789771 | -112711.62 | 112711.62 | 0 | 2025-02-28 | 3 | 1045445.86 | -142963.24 | DOWN | 0.1584 | 131 | Low | 292666.95 | 0.301 | 4 | 497104.05 | 23 | 1.4 | 1.5
P002 | Materials | SUP037 | 2025-02 | 2024-12-29 | 839249.71 | 789771 | -49478.71 | 49478.71 | 0 | 2025-02-28 | 4 | 902482.62 | -63232.91 | DOWN | 0.0753 | 61 | Low | 468299.61 | 0.538 | 4 | 321471.39 | 23 | 1.4 | 1.5
P002 | Materials | SUP037 | 2025-02 | 2025-01-09 | 817096.13 | 789771 | -27325.13 | 27325.13 | 0 | 2025-02-28 | 5 | 839249.71 | -22153.58 | DOWN | 0.0271 | 50 | Medium | 455531.24 | 0.575 | 5 | 334239.76 | 23 | 1.4 | 1.5
P002 | Services | SUP037 | 2025-03 | 2024-10-15 | 896788.39 | 467752 | -429036.39 | 429036.39 | 1 | 2025-03-28 | 1 |  |  |  |  | 164 | Low | 161376.68 | 0.172 | 0 | 306375.32 | 25 | 2.28 | 1.97
P002 | Services | SUP037 | 2025-03 | 2024-10-19 | 637516.99 | 467752 | -169764.99 | 169764.99 | 1 | 2025-03-28 | 2 | 896788.39 | -259271.4 | DOWN | 0.4067 | 160 | Low | 114989.89 | 0.184 | 1 | 352762.11 | 25 | 2.28 | 1.97
P002 | Services | SUP037 | 2025-03 | 2025-02-08 | 540328.86 | 467752 | -72576.86 | 72576.86 | 0 | 2025-03-28 | 3 | 637516.99 | -97188.13 | DOWN | 0.1799 | 48 | Low | 282653.47 | 0.529 | 3 | 185098.53 | 25 | 2.28 | 1.97
P002 | Services | SUP037 | 2025-03 | 2025-02-10 | 517813.18 | 467752 | -50061.18 | 50061.18 | 0 | 2025-03-28 | 4 | 540328.86 | -22515.68 | DOWN | 0.0435 | 46 | Low | 288215.98 | 0.535 | 5 | 179536.02 | 25 | 2.28 | 1.97
P002 | Logistics | SUP037 | 2025-04 | 2024-12-03 | 5997551.51 | 2852443 | -3145108.51 | 3145108.51 | 1 | 2025-04-28 | 1 |  |  |  |  | 146 | Low | 1580985.88 | 0.26 | 2 | 1271457.12 | 21 | 1.06 | 1.67
P002 | Logistics | SUP037 | 2025-04 | 2024-12-13 | 4311336.96 | 2852443 | -1458893.96 | 1458893.96 | 1 | 2025-04-28 | 2 | 5997551.51 | -1686214.55 | DOWN | 0.3911 | 136 | Low | 1304671.72 | 0.296 | 6 | 1547771.28 | 21 | 1.06 | 1.67
P002 | Logistics | SUP037 | 2025-04 | 2025-02-12 | 3481756.86 | 2852443 | -629313.86 | 629313.86 | 1 | 2025-04-28 | 3 | 4311336.96 | -829580.1 | DOWN | 0.2383 | 75 | Low | 1750793.04 | 0.51 | 1 | 1101649.96 | 21 | 1.06 | 1.67
P002 | Logistics | SUP037 | 2025-04 | 2025-03-26 | 3100247.18 | 2852443 | -247804.18 | 247804.18 | 0 | 2025-04-28 | 4 | 3481756.86 | -381509.68 | DOWN | 0.1231 | 33 | Low | 2093335.07 | 0.658 | 6 | 759107.93 | 21 | 1.06 | 1.67
P002 | Logistics | SUP037 | 2025-04 | 2025-04-12 | 2897185.46 | 2852443 | -44742.46 | 44742.46 | 0 | 2025-04-28 | 5 | 3100247.18 | -203061.72 | DOWN | 0.0701 | 16 | Medium | 2130327.14 | 0.718 | 4 | 722115.86 | 21 | 1.06 | 1.67
P002 | Software | SUP037 | 2025-05 | 2025-01-11 | 1736382.32 | 775223 | -961159.32 | 961159.32 | 1 | 2025-05-28 | 1 |  |  |  |  | 137 | Low | 465850.78 | 0.26 | 4 | 309372.22 | 28 | 2.1 | 0.99
P002 | Software | SUP037 | 2025-05 | 2025-01-17 | 1243316.02 | 775223 | -468093.02 | 468093.02 | 1 | 2025-05-28 | 2 | 1736382.32 | -493066.3 | DOWN | 0.3966 | 131 | Low | 359504.56 | 0.279 | 4 | 415718.44 | 28 | 2.1 | 0.99
P002 | Software | SUP037 | 2025-05 | 2025-03-25 | 966383.41 | 775223 | -191160.41 | 191160.41 | 1 | 2025-05-28 | 3 | 1243316.02 | -276932.61 | DOWN | 0.2866 | 64 | Low | 463068.04 | 0.489 | 3 | 312154.96 | 28 | 2.1 | 0.99
P002 | Software | SUP037 | 2025-05 | 2025-04-23 | 861933.83 | 775223 | -86710.83 | 86710.83 | 0 | 2025-05-28 | 4 | 966383.41 | -104449.58 | DOWN | 0.1212 | 35 | Low | 510119.15 | 0.579 | 7 | 265103.85 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP037 | 2025-06 | 2025-03-18 | 455622.79 | 320345 | -135277.79 | 135277.79 | 1 | 2025-06-28 | 1 |  |  |  |  | 102 | Low | 187031.24 | 0.405 | 2 | 133313.76 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP037 | 2025-06 | 2025-04-04 | 377529.34 | 320345 | -57184.34 | 57184.34 | 1 | 2025-06-28 | 2 | 455622.79 | -78093.45 | DOWN | 0.2069 | 85 | Low | 183733.12 | 0.464 | 5 | 136611.88 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP037 | 2025-06 | 2025-04-21 | 345447.61 | 320345 | -25102.61 | 25102.61 | 0 | 2025-06-28 | 3 | 377529.34 | -32081.73 | DOWN | 0.0929 | 68 | Low | 190678.67 | 0.522 | 3 | 129666.33 | 17 | 1.27 | 1.62
P002 | Electronics | SUP037 | 2025-07 | 2025-03-23 | 601865.16 | 318684 | -283181.16 | 283181.16 | 1 | 2025-07-28 | 1 |  |  |  |  | 127 | Low | 196672.89 | 0.311 | 0 | 122011.11 | 24 | 1.49 | 1.96
P002 | Electronics | SUP037 | 2025-07 | 2025-04-24 | 447603.18 | 318684 | -128919.18 | 128919.18 | 1 | 2025-07-28 | 2 | 601865.16 | -154261.98 | DOWN | 0.3446 | 95 | Low | 181914.73 | 0.419 | 5 | 136769.27 | 24 | 1.49 | 1.96
P002 | Electronics | SUP037 | 2025-07 | 2025-05-23 | 377630.46 | 318684 | -58946.46 | 58946.46 | 1 | 2025-07-28 | 3 | 447603.18 | -69972.72 | DOWN | 0.1853 | 66 | Low | 185473.39 | 0.516 | 6 | 133210.61 | 24 | 1.49 | 1.96
P002 | Electronics | SUP037 | 2025-07 | 2025-05-27 | 340977.72 | 318684 | -22293.72 | 22293.72 | 0 | 2025-07-28 | 4 | 377630.46 | -36652.74 | DOWN | 0.1075 | 62 | Low | 180068.14 | 0.529 | 4 | 138615.86 | 24 | 1.49 | 1.96
P002 | Electronics | SUP037 | 2025-07 | 2025-06-26 | 323792.18 | 318684 | -5108.18 | 5108.18 | 0 | 2025-07-28 | 5 | 340977.72 | -17185.54 | DOWN | 0.0531 | 32 | Medium | 191304.12 | 0.63 | 5 | 127379.88 | 24 | 1.49 | 1.96
P002 | Mechanical | SUP037 | 2025-08 | 2025-03-18 | 3755033.06 | 2525270 | -1229763.06 | 1229763.06 | 1 | 2025-08-28 | 1 |  |  |  |  | 163 | Low | 790063.68 | 0.195 | 0 | 1735206.32 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP037 | 2025-08 | 2025-05-21 | 3055346.55 | 2525270 | -530076.55 | 530076.55 | 1 | 2025-08-28 | 2 | 3755033.06 | -699686.51 | DOWN | 0.229 | 99 | Low | 1291511.56 | 0.415 | 0 | 1233758.44 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP037 | 2025-08 | 2025-05-30 | 2743604.15 | 2525270 | -218334.15 | 218334.15 | 0 | 2025-08-28 | 3 | 3055346.55 | -311742.4 | DOWN | 0.1136 | 90 | Low | 1225491.82 | 0.445 | 7 | 1299778.18 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP037 | 2025-08 | 2025-06-22 | 2641906.98 | 2525270 | -116636.98 | 116636.98 | 0 | 2025-08-28 | 4 | 2743604.15 | -101697.17 | DOWN | 0.0385 | 67 | Low | 1436322.52 | 0.524 | 5 | 1088947.48 | 25 | 1.29 | 1.82
P002 | Mechanical | SUP037 | 2025-08 | 2025-06-23 | 2558130.1 | 2525270 | -32860.1 | 32860.1 | 0 | 2025-08-28 | 5 | 2641906.98 | -83776.88 | DOWN | 0.0327 | 66 | Low | 1358657.9 | 0.528 | 3 | 1166612.1 | 25 | 1.29 | 1.82
P002 | Electronics | SUP037 | 2025-09 | 2025-05-04 | 2205930.2 | 1131309 | -1074621.2 | 1074621.2 | 1 | 2025-09-28 | 1 |  |  |  |  | 147 | Low | 535897.65 | 0.248 | 2 | 595411.35 | 25 | 1.38 | 1.58
P002 | Electronics | SUP037 | 2025-09 | 2025-06-26 | 1598563.63 | 1131309 | -467254.63 | 467254.63 | 1 | 2025-09-28 | 2 | 2205930.2 | -607366.57 | DOWN | 0.3799 | 94 | Low | 669467.17 | 0.427 | 4 | 461841.83 | 25 | 1.38 | 1.58
P002 | Electronics | SUP037 | 2025-09 | 2025-08-24 | 1338925.37 | 1131309 | -207616.37 | 207616.37 | 1 | 2025-09-28 | 3 | 1598563.63 | -259638.26 | DOWN | 0.1939 | 35 | Low | 785913.5 | 0.627 | 5 | 345395.5 | 25 | 1.38 | 1.58
P002 | Electronics | SUP037 | 2025-10 | 2025-05-07 | 3522082.33 | 2285076 | -1237006.33 | 1237006.33 | 1 | 2025-10-28 | 1 |  |  |  |  | 174 | Low | 496156.03 | 0.149 | 1 | 1788919.97 | 21 | 1.76 | 1.29
P002 | Electronics | SUP037 | 2025-10 | 2025-07-24 | 2829644.93 | 2285076 | -544568.93 | 544568.93 | 1 | 2025-10-28 | 2 | 3522082.33 | -692437.4 | DOWN | 0.2447 | 96 | Low | 1143264.89 | 0.403 | 2 | 1141811.11 | 21 | 1.76 | 1.29
P002 | Electronics | SUP037 | 2025-10 | 2025-09-12 | 2579911.29 | 2285076 | -294835.29 | 294835.29 | 0 | 2025-10-28 | 3 | 2829644.93 | -249733.64 | DOWN | 0.0968 | 46 | Medium | 1522483.2 | 0.565 | 4 | 762592.8 | 21 | 1.76 | 1.29
P002 | Electronics | SUP037 | 2025-10 | 2025-09-24 | 2399590.82 | 2285076 | -114514.82 | 114514.82 | 0 | 2025-10-28 | 4 | 2579911.29 | -180320.47 | DOWN | 0.0751 | 34 | Medium | 1397032.09 | 0.604 | 0 | 888043.91 | 21 | 1.76 | 1.29
P002 | Logistics | SUP037 | 2025-11 | 2025-07-09 | 1883868.79 | 1009553 | -874315.79 | 874315.79 | 1 | 2025-11-28 | 1 |  |  |  |  | 142 | Low | 453985.64 | 0.258 | 4 | 555567.36 | 26 | 1.59 | 1.38
P002 | Logistics | SUP037 | 2025-11 | 2025-08-25 | 1405920.23 | 1009553 | -396367.23 | 396367.23 | 1 | 2025-11-28 | 2 | 1883868.79 | -477948.56 | DOWN | 0.34 | 95 | Low | 578691.25 | 0.414 | 3 | 430861.75 | 26 | 1.59 | 1.38
P002 | Logistics | SUP037 | 2025-11 | 2025-08-30 | 1195059.15 | 1009553 | -185506.15 | 185506.15 | 1 | 2025-11-28 | 3 | 1405920.23 | -210861.08 | DOWN | 0.1764 | 90 | Low | 548655.3 | 0.43 | 3 | 460897.7 | 26 | 1.59 | 1.38
P002 | Logistics | SUP037 | 2025-11 | 2025-10-30 | 1100933.41 | 1009553 | -91380.41 | 91380.41 | 0 | 2025-11-28 | 4 | 1195059.15 | -94125.74 | DOWN | 0.0855 | 29 | Medium | 665118.06 | 0.632 | 8 | 344434.94 | 26 | 1.59 | 1.38
P002 | Logistics | SUP037 | 2025-11 | 2025-11-06 | 1029227.2 | 1009553 | -19674.2 | 19674.2 | 0 | 2025-11-28 | 5 | 1100933.41 | -71706.21 | DOWN | 0.0697 | 22 | Medium | 647388.71 | 0.656 | 3 | 362164.29 | 26 | 1.59 | 1.38
P002 | Logistics | SUP037 | 2025-11 | 2025-11-14 | 1009870.67 | 1009553 | -317.67 | 317.67 | 0 | 2025-11-28 | 6 | 1029227.2 | -19356.53 | DOWN | 0.0192 | 14 | Medium | 655735.89 | 0.682 | 3 | 353817.11 | 26 | 1.59 | 1.38
P002 | Services | SUP037 | 2025-12 | 2025-07-07 | 2444052.24 | 1480247 | -963805.24 | 963805.24 | 1 | 2025-12-28 | 1 |  |  |  |  | 174 | Low | 355712.38 | 0.155 | 0 | 1124534.62 | 27 | 1.43 | 1.4
P002 | Services | SUP037 | 2025-12 | 2025-09-20 | 1897299.39 | 1480247 | -417052.39 | 417052.39 | 1 | 2025-12-28 | 2 | 2444052.24 | -546752.85 | DOWN | 0.2882 | 99 | Low | 745298.62 | 0.408 | 3 | 734948.38 | 27 | 1.43 | 1.4
P002 | Services | SUP037 | 2025-12 | 2025-11-26 | 1678098.55 | 1480247 | -197851.55 | 197851.55 | 0 | 2025-12-28 | 3 | 1897299.39 | -219200.84 | DOWN | 0.1306 | 32 | Low | 1058571.2 | 0.634 | 6 | 421675.8 | 27 | 1.43 | 1.4
P002 | Services | SUP035 | 2025-01 | 2024-08-06 | 2266861.2 | 1058481 | -1208380.2 | 1208380.2 | 1 | 2025-01-28 | 1 |  |  |  |  | 175 | Low | 291008.93 | 0.126 | 0 | 767472.07 | 20 | 1.45 | 1.35
P002 | Services | SUP035 | 2025-01 | 2024-08-27 | 1713087.05 | 1058481 | -654606.05 | 654606.05 | 1 | 2025-01-28 | 2 | 2266861.2 | -553774.15 | DOWN | 0.3233 | 154 | Low | 334977.68 | 0.185 | 2 | 723503.32 | 20 | 1.45 | 1.35
P002 | Services | SUP035 | 2025-01 | 2024-09-12 | 1406846.8 | 1058481 | -348365.8 | 348365.8 | 1 | 2025-01-28 | 3 | 1713087.05 | -306240.25 | DOWN | 0.2177 | 138 | Low | 303866.45 | 0.23 | 3 | 754614.55 | 20 | 1.45 | 1.35
P002 | Services | SUP035 | 2025-01 | 2024-11-12 | 1243457.81 | 1058481 | -184976.81 | 184976.81 | 0 | 2025-01-28 | 4 | 1406846.8 | -163388.99 | DOWN | 0.1314 | 77 | Low | 515310.3 | 0.401 | 3 | 543170.7 | 20 | 1.45 | 1.35
P002 | Services | SUP035 | 2025-01 | 2024-11-14 | 1169940.58 | 1058481 | -111459.58 | 111459.58 | 0 | 2025-01-28 | 5 | 1243457.81 | -73517.23 | DOWN | 0.0628 | 75 | Low | 503593.75 | 0.406 | 0 | 554887.25 | 20 | 1.45 | 1.35
P002 | Services | SUP035 | 2025-01 | 2024-12-16 | 1122265.15 | 1058481 | -63784.15 | 63784.15 | 0 | 2025-01-28 | 6 | 1169940.58 | -47675.43 | DOWN | 0.0425 | 43 | Medium | 600212.75 | 0.496 | 3 | 458268.25 | 20 | 1.45 | 1.35
P002 | Mechanical | SUP035 | 2025-02 | 2024-11-13 | 4484834.36 | 2756533 | -1728301.36 | 1728301.36 | 1 | 2025-02-28 | 1 |  |  |  |  | 107 | Low | 1430945.37 | 0.319 | 7 | 1325587.63 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP035 | 2025-02 | 2024-11-22 | 3694584.33 | 2756533 | -938051.33 | 938051.33 | 1 | 2025-02-28 | 2 | 4484834.36 | -790250.03 | DOWN | 0.2139 | 98 | Low | 1346655.42 | 0.344 | 0 | 1409877.58 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP035 | 2025-02 | 2025-01-10 | 3290702.36 | 2756533 | -534169.36 | 534169.36 | 1 | 2025-02-28 | 3 | 3694584.33 | -403881.97 | DOWN | 0.1227 | 49 | Low | 1470110.16 | 0.482 | 5 | 1286422.84 | 23 | 1.4 | 1.5
P002 | Mechanical | SUP035 | 2025-02 | 2025-01-17 | 3046374.76 | 2756533 | -289841.76 | 289841.76 | 0 | 2025-02-28 | 4 | 3290702.36 | -244327.6 | DOWN | 0.0802 | 42 | Medium | 1505132.06 | 0.502 | 5 | 1251400.94 | 23 | 1.4 | 1.5
P002 | Software | SUP035 | 2025-03 | 2024-11-25 | 588820.92 | 276307 | -312513.92 | 312513.92 | 1 | 2025-03-28 | 1 |  |  |  |  | 123 | Low | 156663.33 | 0.248 | 5 | 119643.67 | 25 | 2.28 | 1.97
P002 | Software | SUP035 | 2025-03 | 2025-02-14 | 458951.52 | 276307 | -182644.52 | 182644.52 | 1 | 2025-03-28 | 2 | 588820.92 | -129869.4 | DOWN | 0.283 | 42 | Low | 224216.89 | 0.456 | 5 | 52090.11 | 25 | 2.28 | 1.97
P002 | Software | SUP035 | 2025-03 | 2025-02-17 | 379256.6 | 276307 | -102949.6 | 102949.6 | 1 | 2025-03-28 | 3 | 458951.52 | -79694.92 | DOWN | 0.2101 | 39 | Low | 164064.28 | 0.464 | 2 | 112242.72 | 25 | 2.28 | 1.97
P002 | Software | SUP035 | 2025-04 | 2024-12-05 | 4762161.02 | 2036850 | -2725311.02 | 2725311.02 | 1 | 2025-04-28 | 1 |  |  |  |  | 144 | Low | 1091297.42 | 0.223 | 2 | 945552.58 | 21 | 1.06 | 1.67
P002 | Software | SUP035 | 2025-04 | 2024-12-21 | 3596040.13 | 2036850 | -1559190.13 | 1559190.13 | 1 | 2025-04-28 | 2 | 4762161.02 | -1166120.89 | DOWN | 0.3243 | 128 | Low | 964750.48 | 0.27 | 4 | 1072099.52 | 21 | 1.06 | 1.67
P002 | Software | SUP035 | 2025-04 | 2025-01-28 | 2937144.25 | 2036850 | -900294.25 | 900294.25 | 1 | 2025-04-28 | 3 | 3596040.13 | -658895.88 | DOWN | 0.2243 | 90 | Low | 1143288 | 0.381 | 4 | 893562 | 21 | 1.06 | 1.67
P002 | Software | SUP035 | 2025-04 | 2025-02-14 | 2503428.61 | 2036850 | -466578.61 | 466578.61 | 1 | 2025-04-28 | 4 | 2937144.25 | -433715.64 | DOWN | 0.1732 | 73 | Low | 1164737.09 | 0.431 | 2 | 872112.91 | 21 | 1.06 | 1.67
P002 | Software | SUP035 | 2025-04 | 2025-02-19 | 2273537.72 | 2036850 | -236687.72 | 236687.72 | 0 | 2025-04-28 | 5 | 2503428.61 | -229890.89 | DOWN | 0.1011 | 68 | Low | 1050014.13 | 0.446 | 2 | 986835.87 | 21 | 1.06 | 1.67
P002 | Software | SUP035 | 2025-04 | 2025-04-02 | 2204890.98 | 2036850 | -168040.98 | 168040.98 | 0 | 2025-04-28 | 6 | 2273537.72 | -68646.74 | DOWN | 0.0311 | 26 | Medium | 1169419.81 | 0.569 | 8 | 867430.19 | 21 | 1.06 | 1.67
P002 | Materials | SUP035 | 2025-05 | 2025-01-09 | 2606890.08 | 1154548 | -1452342.08 | 1452342.08 | 1 | 2025-05-28 | 1 |  |  |  |  | 139 | Low | 531365.29 | 0.211 | 4 | 623182.71 | 28 | 2.1 | 0.99
P002 | Materials | SUP035 | 2025-05 | 2025-02-04 | 1978005.29 | 1154548 | -823457.29 | 823457.29 | 1 | 2025-05-28 | 2 | 2606890.08 | -628884.79 | DOWN | 0.3179 | 113 | Low | 536096.9 | 0.279 | 1 | 618451.1 | 28 | 2.1 | 0.99
P002 | Materials | SUP035 | 2025-05 | 2025-04-02 | 1634730.38 | 1154548 | -480182.38 | 480182.38 | 1 | 2025-05-28 | 3 | 1978005.29 | -343274.91 | DOWN | 0.21 | 56 | Low | 717489.85 | 0.428 | 4 | 437058.15 | 28 | 2.1 | 0.99
P002 | Materials | SUP035 | 2025-05 | 2025-05-08 | 1395731.19 | 1154548 | -241183.19 | 241183.19 | 1 | 2025-05-28 | 4 | 1634730.38 | -238999.19 | DOWN | 0.1712 | 20 | Low | 774974.05 | 0.522 | 1 | 379573.95 | 28 | 2.1 | 0.99
P002 | Mechanical | SUP035 | 2025-06 | 2024-12-31 | 2990159.54 | 1587953 | -1402206.54 | 1402206.54 | 1 | 2025-06-28 | 1 |  |  |  |  | 179 | Low | 400889.7 | 0.126 | 4 | 1187063.3 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP035 | 2025-06 | 2025-01-09 | 2360365.31 | 1587953 | -772412.31 | 772412.31 | 1 | 2025-06-28 | 2 | 2990159.54 | -629794.23 | DOWN | 0.2668 | 170 | Low | 350394.73 | 0.143 | 0 | 1237558.27 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP035 | 2025-06 | 2025-03-15 | 1993497.72 | 1587953 | -405544.72 | 405544.72 | 1 | 2025-06-28 | 3 | 2360365.31 | -366867.59 | DOWN | 0.184 | 105 | Low | 684158.48 | 0.329 | 3 | 903794.52 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP035 | 2025-06 | 2025-03-29 | 1801675.54 | 1587953 | -213722.54 | 213722.54 | 0 | 2025-06-28 | 4 | 1993497.72 | -191822.18 | DOWN | 0.1065 | 91 | Low | 677487.83 | 0.369 | 3 | 910465.17 | 17 | 1.27 | 1.62
P002 | Mechanical | SUP035 | 2025-06 | 2025-06-11 | 1716128.74 | 1587953 | -128175.74 | 128175.74 | 0 | 2025-06-28 | 5 | 1801675.54 | -85546.8 | DOWN | 0.0498 | 17 | Medium | 947505.71 | 0.581 | 5 | 640447.29 | 17 | 1.27 | 1.62
P002 | Electronics | SUP035 | 2025-07 | 2025-01-30 | 3559914.28 | 1544259 | -2015655.28 | 2015655.28 | 1 | 2025-07-28 | 1 |  |  |  |  | 179 | Low | 452460.37 | 0.123 | 2 | 1091798.63 | 24 | 1.49 | 1.96
P002 | Electronics | SUP035 | 2025-07 | 2025-04-10 | 2658139.95 | 1544259 | -1113880.95 | 1113880.95 | 1 | 2025-07-28 | 2 | 3559914.28 | -901774.33 | DOWN | 0.3393 | 109 | Low | 844201.71 | 0.31 | 2 | 700057.29 | 24 | 1.49 | 1.96
P002 | Electronics | SUP035 | 2025-07 | 2025-06-08 | 2178302.77 | 1544259 | -634043.77 | 634043.77 | 1 | 2025-07-28 | 3 | 2658139.95 | -479837.18 | DOWN | 0.2203 | 50 | Low | 1000945.4 | 0.474 | 5 | 543313.6 | 24 | 1.49 | 1.96
P002 | Electronics | SUP035 | 2025-07 | 2025-06-27 | 1900399.1 | 1544259 | -356140.1 | 356140.1 | 1 | 2025-07-28 | 4 | 2178302.77 | -277903.67 | DOWN | 0.1462 | 31 | Low | 1036382.08 | 0.527 | 4 | 507876.92 | 24 | 1.49 | 1.96
P002 | Electronics | SUP035 | 2025-07 | 2025-07-10 | 1765047.96 | 1544259 | -220788.96 | 220788.96 | 0 | 2025-07-28 | 5 | 1900399.1 | -135351.14 | DOWN | 0.0767 | 18 | Medium | 1049007.51 | 0.564 | 4 | 495251.49 | 24 | 1.49 | 1.96
P002 | Services | SUP035 | 2025-08 | 2025-03-10 | 699934.52 | 353958 | -345976.52 | 345976.52 | 1 | 2025-08-28 | 1 |  |  |  |  | 171 | Low | 90927.27 | 0.14 | 1 | 263030.73 | 25 | 1.29 | 1.82
P002 | Services | SUP035 | 2025-08 | 2025-03-19 | 544576.55 | 353958 | -190618.55 | 190618.55 | 1 | 2025-08-28 | 2 | 699934.52 | -155357.97 | DOWN | 0.2853 | 162 | Low | 90005.96 | 0.166 | 2 | 263952.04 | 25 | 1.29 | 1.82
P002 | Services | SUP035 | 2025-08 | 2025-04-16 | 467235.75 | 353958 | -113277.75 | 113277.75 | 1 | 2025-08-28 | 3 | 544576.55 | -77340.8 | DOWN | 0.1655 | 134 | Low | 108480.78 | 0.246 | 0 | 245477.22 | 25 | 1.29 | 1.82
P002 | Services | SUP035 | 2025-08 | 2025-05-28 | 415898.15 | 353958 | -61940.15 | 61940.15 | 0 | 2025-08-28 | 4 | 467235.75 | -51337.6 | DOWN | 0.1234 | 92 | Low | 147291.87 | 0.365 | 3 | 206666.13 | 25 | 1.29 | 1.82
P002 | Services | SUP035 | 2025-08 | 2025-06-14 | 382637.55 | 353958 | -28679.55 | 28679.55 | 0 | 2025-08-28 | 5 | 415898.15 | -33260.6 | DOWN | 0.0869 | 75 | Low | 148734.96 | 0.414 | 8 | 205223.04 | 25 | 1.29 | 1.82
P002 | Services | SUP035 | 2025-08 | 2025-07-20 | 374965.81 | 353958 | -21007.81 | 21007.81 | 0 | 2025-08-28 | 6 | 382637.55 | -7671.74 | DOWN | 0.0205 | 39 | Medium | 196704.1 | 0.517 | 4 | 157253.9 | 25 | 1.29 | 1.82
P002 | Materials | SUP035 | 2025-09 | 2025-04-04 | 2244073.51 | 1100614 | -1143459.51 | 1143459.51 | 1 | 2025-09-28 | 1 |  |  |  |  | 177 | Low | 294424.12 | 0.124 | 2 | 806189.88 | 25 | 1.38 | 1.58
P002 | Materials | SUP035 | 2025-09 | 2025-04-09 | 1732602.05 | 1100614 | -631988.05 | 631988.05 | 1 | 2025-09-28 | 2 | 2244073.51 | -511471.46 | DOWN | 0.2952 | 172 | Low | 232293.93 | 0.136 | 0 | 868320.07 | 25 | 1.38 | 1.58
P002 | Materials | SUP035 | 2025-09 | 2025-05-10 | 1450062.99 | 1100614 | -349448.99 | 349448.99 | 1 | 2025-09-28 | 3 | 1732602.05 | -282539.06 | DOWN | 0.1948 | 141 | Low | 326963.48 | 0.223 | 5 | 773650.52 | 25 | 1.38 | 1.58
P002 | Services | SUP035 | 2025-10 | 2025-05-24 | 3895857.28 | 1530890 | -2364967.28 | 2364967.28 | 1 | 2025-10-28 | 1 |  |  |  |  | 157 | Low | 684477.6 | 0.171 | 0 | 846412.4 | 21 | 1.76 | 1.29
P002 | Services | SUP035 | 2025-10 | 2025-06-05 | 2765344.59 | 1530890 | -1234454.59 | 1234454.59 | 1 | 2025-10-28 | 2 | 3895857.28 | -1130512.69 | DOWN | 0.4088 | 145 | Low | 561692.34 | 0.203 | 2 | 969197.66 | 21 | 1.76 | 1.29
P002 | Services | SUP035 | 2025-10 | 2025-06-17 | 2163134.44 | 1530890 | -632244.44 | 632244.44 | 1 | 2025-10-28 | 3 | 2765344.59 | -602210.15 | DOWN | 0.2784 | 133 | Low | 549566.24 | 0.236 | 1 | 981323.76 | 21 | 1.76 | 1.29
P002 | Services | SUP035 | 2025-10 | 2025-07-13 | 1898547.24 | 1530890 | -367657.24 | 367657.24 | 1 | 2025-10-28 | 4 | 2163134.44 | -264587.2 | DOWN | 0.1394 | 107 | Low | 539278.77 | 0.306 | 4 | 991611.23 | 21 | 1.76 | 1.29
P002 | Services | SUP035 | 2025-11 | 2025-06-21 | 2676611.04 | 1044325 | -1632286.04 | 1632286.04 | 1 | 2025-11-28 | 1 |  |  |  |  | 160 | Low | 471322.35 | 0.166 | 0 | 573002.65 | 26 | 1.59 | 1.38
P002 | Services | SUP035 | 2025-11 | 2025-07-14 | 1942399.19 | 1044325 | -898074.19 | 898074.19 | 1 | 2025-11-28 | 2 | 2676611.04 | -734211.85 | DOWN | 0.378 | 137 | Low | 433675.01 | 0.229 | 4 | 610649.99 | 26 | 1.59 | 1.38
P002 | Services | SUP035 | 2025-11 | 2025-11-04 | 1538907.05 | 1044325 | -494582.05 | 494582.05 | 1 | 2025-11-28 | 3 | 1942399.19 | -403492.14 | DOWN | 0.2622 | 24 | Low | 816437.19 | 0.541 | 4 | 227887.81 | 26 | 1.59 | 1.38
P002 | Services | SUP035 | 2025-11 | 2025-11-11 | 1305351.7 | 1044325 | -261026.7 | 261026.7 | 1 | 2025-11-28 | 4 | 1538907.05 | -233555.35 | DOWN | 0.1789 | 17 | Low | 737637.29 | 0.56 | 5 | 306687.71 | 26 | 1.59 | 1.38
P002 | Software | SUP035 | 2025-12 | 2025-07-15 | 5266211.9 | 2228467 | -3037744.9 | 3037744.9 | 1 | 2025-12-28 | 1 |  |  |  |  | 166 | Low | 803619.61 | 0.152 | 0 | 1424847.39 | 27 | 1.43 | 1.4
P002 | Software | SUP035 | 2025-12 | 2025-09-08 | 3842364.91 | 2228467 | -1613897.91 | 1613897.91 | 1 | 2025-12-28 | 2 | 5266211.9 | -1423846.99 | DOWN | 0.3706 | 111 | Low | 1176600.19 | 0.306 | 5 | 1051866.81 | 27 | 1.43 | 1.4
P002 | Software | SUP035 | 2025-12 | 2025-09-29 | 3150793.24 | 2228467 | -922326.24 | 922326.24 | 1 | 2025-12-28 | 3 | 3842364.91 | -691571.67 | DOWN | 0.2195 | 90 | Low | 1148404.04 | 0.365 | 5 | 1080062.96 | 27 | 1.43 | 1.4
P002 | Software | SUP035 | 2025-12 | 2025-10-14 | 2806567.75 | 2228467 | -578100.75 | 578100.75 | 1 | 2025-12-28 | 4 | 3150793.24 | -344225.49 | DOWN | 0.1226 | 75 | Low | 1159210.4 | 0.407 | 2 | 1069256.6 | 27 | 1.43 | 1.4
P002 | Software | SUP035 | 2025-12 | 2025-11-02 | 2578203.42 | 2228467 | -349736.42 | 349736.42 | 0 | 2025-12-28 | 5 | 2806567.75 | -228364.33 | DOWN | 0.0886 | 56 | Medium | 1120150.99 | 0.461 | 7 | 1108316.01 | 27 | 1.43 | 1.4
P002 | Software | SUP035 | 2025-12 | 2025-11-20 | 2474163.14 | 2228467 | -245696.14 | 245696.14 | 0 | 2025-12-28 | 6 | 2578203.42 | -104040.28 | DOWN | 0.0421 | 38 | Medium | 1296904.16 | 0.511 | 6 | 931562.84 | 27 | 1.43 | 1.4
P003 | Electronics | SUP010 | 2025-01 | 2024-12-23 | 4189330.99 | 2192656 | -1996674.99 | 1996674.99 | 1 | 2025-01-28 | 1 |  |  |  |  | 36 | Medium | 2130839.07 | 0.493 | 1 | 61816.93 | 17 | 1.86 | 1.34
P003 | Electronics | SUP010 | 2025-01 | 2024-12-25 | 3318288.41 | 2192656 | -1125632.41 | 1125632.41 | 1 | 2025-01-28 | 2 | 4189330.99 | -871042.58 | DOWN | 0.2625 | 34 | Low | 1765279.16 | 0.498 | 5 | 427376.84 | 17 | 1.86 | 1.34
P003 | Electronics | SUP010 | 2025-01 | 2025-01-02 | 2741194.65 | 2192656 | -548538.65 | 548538.65 | 1 | 2025-01-28 | 3 | 3318288.41 | -577093.76 | DOWN | 0.2105 | 26 | Low | 1358740.64 | 0.52 | 5 | 833915.36 | 17 | 1.86 | 1.34
P003 | Electronics | SUP010 | 2025-01 | 2025-01-06 | 2464210.68 | 2192656 | -271554.68 | 271554.68 | 0 | 2025-01-28 | 4 | 2741194.65 | -276983.97 | DOWN | 0.1124 | 22 | Medium | 1313924.96 | 0.53 | 4 | 878731.04 | 17 | 1.86 | 1.34
P003 | Electronics | SUP010 | 2025-01 | 2025-01-07 | 2353112.72 | 2192656 | -160456.72 | 160456.72 | 0 | 2025-01-28 | 5 | 2464210.68 | -111097.96 | DOWN | 0.0472 | 21 | Medium | 1342255.45 | 0.533 | 2 | 850400.55 | 17 | 1.86 | 1.34
P003 | Software | SUP010 | 2025-02 | 2024-09-09 | 1847115.14 | 1061378 | -785737.14 | 785737.14 | 1 | 2025-02-28 | 1 |  |  |  |  | 172 | Low | 228510.34 | 0.125 | 2 | 832867.66 | 17 | 2.1 | 1.03
P003 | Software | SUP010 | 2025-02 | 2024-09-16 | 1519005.15 | 1061378 | -457627.15 | 457627.15 | 1 | 2025-02-28 | 2 | 1847115.14 | -328109.99 | DOWN | 0.216 | 165 | Low | 221573.22 | 0.144 | 0 | 839804.78 | 17 | 2.1 | 1.03
P003 | Software | SUP010 | 2025-02 | 2024-12-14 | 1332484 | 1061378 | -271106 | 271106 | 1 | 2025-02-28 | 3 | 1519005.15 | -186521.15 | DOWN | 0.14 | 76 | Low | 471181.73 | 0.376 | 0 | 590196.27 | 17 | 2.1 | 1.03
P003 | Software | SUP010 | 2025-02 | 2024-12-31 | 1220301.07 | 1061378 | -158923.07 | 158923.07 | 0 | 2025-02-28 | 4 | 1332484 | -112182.93 | DOWN | 0.0919 | 59 | Low | 530466.37 | 0.42 | 2 | 530911.63 | 17 | 2.1 | 1.03
P003 | Software | SUP010 | 2025-02 | 2025-02-12 | 1121250.42 | 1061378 | -59872.42 | 59872.42 | 0 | 2025-02-28 | 5 | 1220301.07 | -99050.65 | DOWN | 0.0883 | 16 | Low | 571241.11 | 0.532 | 4 | 490136.89 | 17 | 2.1 | 1.03
P003 | Materials | SUP010 | 2025-03 | 2024-10-13 | 2404408.38 | 1359706 | -1044702.38 | 1044702.38 | 1 | 2025-03-28 | 1 |  |  |  |  | 166 | Low | 370472.39 | 0.157 | 0 | 989233.61 | 13 | 1.13 | 1.73
P003 | Materials | SUP010 | 2025-03 | 2024-11-07 | 1947849.68 | 1359706 | -588143.68 | 588143.68 | 1 | 2025-03-28 | 2 | 2404408.38 | -456558.7 | DOWN | 0.2344 | 141 | Low | 459285.78 | 0.23 | 3 | 900420.22 | 13 | 1.13 | 1.73
P003 | Materials | SUP010 | 2025-03 | 2024-11-13 | 1678840.62 | 1359706 | -319134.62 | 319134.62 | 1 | 2025-03-28 | 3 | 1947849.68 | -269009.06 | DOWN | 0.1602 | 135 | Low | 404792.65 | 0.247 | 5 | 954913.35 | 13 | 1.13 | 1.73
P003 | Materials | SUP010 | 2025-03 | 2024-11-25 | 1524743.16 | 1359706 | -165037.16 | 165037.16 | 0 | 2025-03-28 | 4 | 1678840.62 | -154097.46 | DOWN | 0.1011 | 123 | Low | 459584.41 | 0.282 | 1 | 900121.59 | 13 | 1.13 | 1.73
P003 | Software | SUP010 | 2025-04 | 2025-02-07 | 703041.55 | 434317 | -268724.55 | 268724.55 | 1 | 2025-04-28 | 1 |  |  |  |  | 80 | Low | 287479.07 | 0.403 | 3 | 146837.93 | 13 | 1.21 | 1.27
P003 | Software | SUP010 | 2025-04 | 2025-04-03 | 586093.18 | 434317 | -151776.18 | 151776.18 | 1 | 2025-04-28 | 2 | 703041.55 | -116948.37 | DOWN | 0.1995 | 25 | Low | 337775.25 | 0.562 | 7 | 96541.75 | 13 | 1.21 | 1.27
P003 | Software | SUP010 | 2025-04 | 2025-04-14 | 509000.33 | 434317 | -74683.33 | 74683.33 | 0 | 2025-04-28 | 3 | 586093.18 | -77092.85 | DOWN | 0.1515 | 14 | Low | 304327.02 | 0.594 | 2 | 129989.98 | 13 | 1.21 | 1.27
P003 | Materials | SUP010 | 2025-05 | 2024-12-21 | 3799801.19 | 2181339 | -1618462.19 | 1618462.19 | 1 | 2025-05-28 | 1 |  |  |  |  | 158 | Low | 624158.87 | 0.176 | 0 | 1557180.13 | 14 | 1.36 | 1.73
P003 | Materials | SUP010 | 2025-05 | 2025-01-23 | 3025269.7 | 2181339 | -843930.7 | 843930.7 | 1 | 2025-05-28 | 2 | 3799801.19 | -774531.49 | DOWN | 0.256 | 125 | Low | 863577.4 | 0.269 | 0 | 1317761.6 | 14 | 1.36 | 1.73
P003 | Materials | SUP010 | 2025-05 | 2025-03-01 | 2648763.79 | 2181339 | -467424.79 | 467424.79 | 1 | 2025-05-28 | 3 | 3025269.7 | -376505.91 | DOWN | 0.1421 | 88 | Low | 931820.77 | 0.374 | 1 | 1249518.23 | 14 | 1.36 | 1.73
P003 | Materials | SUP010 | 2025-05 | 2025-04-11 | 2454966.92 | 2181339 | -273627.92 | 273627.92 | 0 | 2025-05-28 | 4 | 2648763.79 | -193796.87 | DOWN | 0.0789 | 47 | Medium | 1121211.33 | 0.49 | 4 | 1060127.67 | 14 | 1.36 | 1.73
P003 | Materials | SUP010 | 2025-05 | 2025-04-24 | 2316583.38 | 2181339 | -135244.38 | 135244.38 | 0 | 2025-05-28 | 5 | 2454966.92 | -138383.54 | DOWN | 0.0597 | 34 | Medium | 1213019.88 | 0.527 | 4 | 968319.12 | 14 | 1.36 | 1.73
P003 | Materials | SUP010 | 2025-05 | 2025-05-02 | 2269086.07 | 2181339 | -87747.07 | 87747.07 | 0 | 2025-05-28 | 6 | 2316583.38 | -47497.31 | DOWN | 0.0209 | 26 | Medium | 1242734.81 | 0.549 | 2 | 938604.19 | 14 | 1.36 | 1.73
P003 | Services | SUP010 | 2025-06 | 2025-01-05 | 2203226.74 | 1206203 | -997023.74 | 997023.74 | 1 | 2025-06-28 | 1 |  |  |  |  | 174 | Low | 289658.54 | 0.129 | 0 | 916544.46 | 22 | 1.47 | 1.51
P003 | Services | SUP010 | 2025-06 | 2025-01-13 | 1753511.41 | 1206203 | -547308.41 | 547308.41 | 1 | 2025-06-28 | 2 | 2203226.74 | -449715.33 | DOWN | 0.2565 | 166 | Low | 280625.11 | 0.151 | 0 | 925577.89 | 22 | 1.47 | 1.51
P003 | Services | SUP010 | 2025-06 | 2025-03-24 | 1477488.77 | 1206203 | -271285.77 | 271285.77 | 1 | 2025-06-28 | 3 | 1753511.41 | -276022.64 | DOWN | 0.1868 | 96 | Low | 507099.44 | 0.347 | 5 | 699103.56 | 22 | 1.47 | 1.51
P003 | Services | SUP010 | 2025-06 | 2025-04-16 | 1349527.87 | 1206203 | -143324.87 | 143324.87 | 0 | 2025-06-28 | 4 | 1477488.77 | -127960.9 | DOWN | 0.0948 | 73 | Low | 526817.36 | 0.411 | 1 | 679385.64 | 22 | 1.47 | 1.51
P003 | Services | SUP010 | 2025-06 | 2025-06-03 | 1302284.43 | 1206203 | -96081.43 | 96081.43 | 0 | 2025-06-28 | 5 | 1349527.87 | -47243.44 | DOWN | 0.0363 | 25 | Medium | 682542.12 | 0.545 | 1 | 523660.88 | 22 | 1.47 | 1.51
P003 | Services | SUP010 | 2025-06 | 2025-06-11 | 1250934.61 | 1206203 | -44731.61 | 44731.61 | 0 | 2025-06-28 | 6 | 1302284.43 | -51349.82 | DOWN | 0.041 | 17 | Medium | 680163.42 | 0.568 | 7 | 526039.58 | 22 | 1.47 | 1.51
P003 | Electronics | SUP010 | 2025-07 | 2025-04-23 | 561372.59 | 340881 | -220491.59 | 220491.59 | 1 | 2025-07-28 | 1 |  |  |  |  | 96 | Low | 207554.93 | 0.366 | 6 | 133326.07 | 13 | 0.8 | 1.22
P003 | Electronics | SUP010 | 2025-07 | 2025-05-02 | 463506.6 | 340881 | -122625.6 | 122625.6 | 1 | 2025-07-28 | 2 | 561372.59 | -97865.99 | DOWN | 0.2111 | 87 | Low | 170222.94 | 0.393 | 1 | 170658.06 | 13 | 0.8 | 1.22
P003 | Electronics | SUP010 | 2025-07 | 2025-06-23 | 410517.72 | 340881 | -69636.72 | 69636.72 | 1 | 2025-07-28 | 3 | 463506.6 | -52988.88 | DOWN | 0.1291 | 35 | Low | 238491.84 | 0.547 | 4 | 102389.16 | 13 | 0.8 | 1.22
P003 | Electronics | SUP010 | 2025-07 | 2025-07-08 | 376337.73 | 340881 | -35456.73 | 35456.73 | 0 | 2025-07-28 | 4 | 410517.72 | -34179.99 | DOWN | 0.0908 | 20 | Medium | 239219.51 | 0.591 | 6 | 101661.49 | 13 | 0.8 | 1.22
P003 | Electronics | SUP010 | 2025-07 | 2025-07-18 | 364646.71 | 340881 | -23765.71 | 23765.71 | 0 | 2025-07-28 | 5 | 376337.73 | -11691.02 | DOWN | 0.0321 | 10 | Medium | 220128.47 | 0.617 | 5 | 120752.53 | 13 | 0.8 | 1.22
P003 | Logistics | SUP010 | 2025-08 | 2025-04-21 | 495533.01 | 252790 | -242743.01 | 242743.01 | 1 | 2025-08-28 | 1 |  |  |  |  | 129 | Low | 119421.02 | 0.257 | 0 | 133368.98 | 7 | 1.37 | 1.47
P003 | Logistics | SUP010 | 2025-08 | 2025-05-04 | 380627.49 | 252790 | -127837.49 | 127837.49 | 1 | 2025-08-28 | 2 | 495533.01 | -114905.52 | DOWN | 0.3019 | 116 | Low | 114810.14 | 0.294 | 7 | 137979.86 | 7 | 1.37 | 1.47
P003 | Logistics | SUP010 | 2025-08 | 2025-05-21 | 328106.53 | 252790 | -75316.53 | 75316.53 | 1 | 2025-08-28 | 3 | 380627.49 | -52520.96 | DOWN | 0.1601 | 99 | Low | 113930.72 | 0.342 | 4 | 138859.28 | 7 | 1.37 | 1.47
P003 | Logistics | SUP010 | 2025-08 | 2025-07-09 | 303113.92 | 252790 | -50323.92 | 50323.92 | 1 | 2025-08-28 | 4 | 328106.53 | -24992.61 | DOWN | 0.0825 | 50 | Medium | 148625.92 | 0.481 | 4 | 104164.08 | 7 | 1.37 | 1.47
P003 | Software | SUP010 | 2025-09 | 2025-05-06 | 3598706.6 | 1747363 | -1851343.6 | 1851343.6 | 1 | 2025-09-28 | 1 |  |  |  |  | 145 | Low | 809208.84 | 0.222 | 1 | 938154.16 | 10 | 0.71 | 1.27
P003 | Software | SUP010 | 2025-09 | 2025-05-28 | 2786346.78 | 1747363 | -1038983.78 | 1038983.78 | 1 | 2025-09-28 | 2 | 3598706.6 | -812359.82 | DOWN | 0.2916 | 123 | Low | 830119.52 | 0.287 | 0 | 917243.48 | 10 | 0.71 | 1.27
P003 | Software | SUP010 | 2025-09 | 2025-08-13 | 2337517.58 | 1747363 | -590154.58 | 590154.58 | 1 | 2025-09-28 | 3 | 2786346.78 | -448829.2 | DOWN | 0.192 | 46 | Low | 1253812.96 | 0.514 | 0 | 493550.04 | 10 | 0.71 | 1.27
P003 | Logistics | SUP010 | 2025-10 | 2025-06-14 | 4508753 | 2061597 | -2447156 | 2447156 | 1 | 2025-10-28 | 1 |  |  |  |  | 136 | Low | 1062652.56 | 0.248 | 5 | 998944.44 | 19 | 0.95 | 0.98
P003 | Logistics | SUP010 | 2025-10 | 2025-06-26 | 3440640.86 | 2061597 | -1379043.86 | 1379043.86 | 1 | 2025-10-28 | 2 | 4508753 | -1068112.14 | DOWN | 0.3104 | 124 | Low | 1011995.92 | 0.284 | 2 | 1049601.08 | 19 | 0.95 | 0.98
P003 | Logistics | SUP010 | 2025-10 | 2025-08-05 | 2819197.27 | 2061597 | -757600.27 | 757600.27 | 1 | 2025-10-28 | 3 | 3440640.86 | -621443.59 | DOWN | 0.2204 | 84 | Low | 1078927.65 | 0.402 | 2 | 982669.35 | 19 | 0.95 | 0.98
P003 | Logistics | SUP010 | 2025-10 | 2025-08-21 | 2430736.11 | 2061597 | -369139.11 | 369139.11 | 1 | 2025-10-28 | 4 | 2819197.27 | -388461.16 | DOWN | 0.1598 | 68 | Low | 1019061.59 | 0.449 | 4 | 1042535.41 | 19 | 0.95 | 0.98
P003 | Electronics | SUP010 | 2025-11 | 2025-06-17 | 1629355.39 | 838246 | -791109.39 | 791109.39 | 1 | 2025-11-28 | 1 |  |  |  |  | 164 | Low | 259946.56 | 0.15 | 5 | 578299.44 | 11 | 1.85 | 1.52
P003 | Electronics | SUP010 | 2025-11 | 2025-06-22 | 1304408.68 | 838246 | -466162.68 | 466162.68 | 1 | 2025-11-28 | 2 | 1629355.39 | -324946.71 | DOWN | 0.2491 | 159 | Low | 222627.4 | 0.164 | 6 | 615618.6 | 11 | 1.85 | 1.52
P003 | Electronics | SUP010 | 2025-11 | 2025-09-02 | 1077175.48 | 838246 | -238929.48 | 238929.48 | 1 | 2025-11-28 | 3 | 1304408.68 | -227233.2 | DOWN | 0.211 | 87 | Low | 411995.78 | 0.357 | 5 | 426250.22 | 11 | 1.85 | 1.52
P003 | Logistics | SUP010 | 2025-12 | 2025-08-31 | 1037417.76 | 479242 | -558175.76 | 558175.76 | 1 | 2025-12-28 | 1 |  |  |  |  | 119 | Low | 321377.01 | 0.296 | 4 | 157864.99 | 10 | 1.08 | 1.22
P003 | Logistics | SUP010 | 2025-12 | 2025-09-09 | 776152.37 | 479242 | -296910.37 | 296910.37 | 1 | 2025-12-28 | 2 | 1037417.76 | -261265.39 | DOWN | 0.3366 | 110 | Low | 258949.05 | 0.322 | 2 | 220292.95 | 10 | 1.08 | 1.22
P003 | Logistics | SUP010 | 2025-12 | 2025-09-12 | 633959.69 | 479242 | -154717.69 | 154717.69 | 1 | 2025-12-28 | 3 | 776152.37 | -142192.68 | DOWN | 0.2243 | 107 | Low | 217467.11 | 0.331 | 2 | 261774.89 | 10 | 1.08 | 1.22
P003 | Materials | SUP039 | 2025-01 | 2024-08-26 | 2201427.82 | 1380858 | -820569.82 | 820569.82 | 1 | 2025-01-28 | 1 |  |  |  |  | 155 | Low | 394357.07 | 0.174 | 0 | 986500.93 | 17 | 1.86 | 1.34
P003 | Materials | SUP039 | 2025-01 | 2024-10-30 | 1844758.15 | 1380858 | -463900.15 | 463900.15 | 1 | 2025-01-28 | 2 | 2201427.82 | -356669.67 | DOWN | 0.1933 | 90 | Low | 597069.36 | 0.348 | 0 | 783788.64 | 17 | 1.86 | 1.34
P003 | Materials | SUP039 | 2025-01 | 2024-10-31 | 1598286.42 | 1380858 | -217428.42 | 217428.42 | 0 | 2025-01-28 | 3 | 1844758.15 | -246471.73 | DOWN | 0.1542 | 89 | Low | 557720.72 | 0.351 | 5 | 823137.28 | 17 | 1.86 | 1.34
P003 | Materials | SUP039 | 2025-01 | 2024-12-18 | 1473728.17 | 1380858 | -92870.17 | 92870.17 | 0 | 2025-01-28 | 4 | 1598286.42 | -124558.25 | DOWN | 0.0845 | 41 | Medium | 732786.28 | 0.479 | 3 | 648071.72 | 17 | 1.86 | 1.34
P003 | Materials | SUP039 | 2025-01 | 2025-01-02 | 1451144.4 | 1380858 | -70286.4 | 70286.4 | 0 | 2025-01-28 | 5 | 1473728.17 | -22583.77 | DOWN | 0.0156 | 26 | Medium | 712112.13 | 0.52 | 3 | 668745.87 | 17 | 1.86 | 1.34
P003 | Logistics | SUP039 | 2025-02 | 2024-09-10 | 1100966.12 | 555265 | -545701.12 | 545701.12 | 1 | 2025-02-28 | 1 |  |  |  |  | 171 | Low | 135029.09 | 0.128 | 4 | 420235.91 | 17 | 2.1 | 1.03
P003 | Logistics | SUP039 | 2025-02 | 2024-11-30 | 817232.07 | 555265 | -261967.07 | 261967.07 | 1 | 2025-02-28 | 2 | 1100966.12 | -283734.05 | DOWN | 0.3472 | 90 | Low | 293337.45 | 0.339 | 2 | 261927.55 | 17 | 2.1 | 1.03
P003 | Logistics | SUP039 | 2025-02 | 2025-01-24 | 685967.65 | 555265 | -130702.65 | 130702.65 | 1 | 2025-02-28 | 3 | 817232.07 | -131264.42 | DOWN | 0.1914 | 35 | Low | 352965.07 | 0.483 | 1 | 202299.93 | 17 | 2.1 | 1.03
P003 | Materials | SUP039 | 2025-03 | 2024-11-13 | 1440707.83 | 819322 | -621385.83 | 621385.83 | 1 | 2025-03-28 | 1 |  |  |  |  | 135 | Low | 331023.59 | 0.247 | 3 | 488298.41 | 13 | 1.13 | 1.73
P003 | Materials | SUP039 | 2025-03 | 2024-11-18 | 1146301.25 | 819322 | -326979.25 | 326979.25 | 1 | 2025-03-28 | 2 | 1440707.83 | -294406.58 | DOWN | 0.2568 | 130 | Low | 319546.11 | 0.262 | 3 | 499775.89 | 13 | 1.13 | 1.73
P003 | Materials | SUP039 | 2025-03 | 2025-01-14 | 994535.83 | 819322 | -175213.83 | 175213.83 | 1 | 2025-03-28 | 3 | 1146301.25 | -151765.42 | DOWN | 0.1526 | 73 | Low | 459190.34 | 0.428 | 3 | 360131.66 | 13 | 1.13 | 1.73
P003 | Services | SUP039 | 2025-04 | 2024-11-14 | 2735329.95 | 1650563 | -1084766.95 | 1084766.95 | 1 | 2025-04-28 | 1 |  |  |  |  | 165 | Low | 431761.12 | 0.159 | 1 | 1218801.88 | 13 | 1.21 | 1.27
P003 | Services | SUP039 | 2025-04 | 2025-02-11 | 2250145.44 | 1650563 | -599582.44 | 599582.44 | 1 | 2025-04-28 | 2 | 2735329.95 | -485184.51 | DOWN | 0.2156 | 76 | Low | 927459.32 | 0.415 | 6 | 723103.68 | 13 | 1.21 | 1.27
P003 | Services | SUP039 | 2025-04 | 2025-04-15 | 1978104.84 | 1650563 | -327541.84 | 327541.84 | 1 | 2025-04-28 | 3 | 2250145.44 | -272040.6 | DOWN | 0.1375 | 13 | Low | 1106843.23 | 0.597 | 5 | 543719.77 | 13 | 1.21 | 1.27
P003 | Logistics | SUP039 | 2025-05 | 2024-12-24 | 4687902.99 | 2362742 | -2325160.99 | 2325160.99 | 1 | 2025-05-28 | 1 |  |  |  |  | 155 | Low | 844166.09 | 0.184 | 2 | 1518575.91 | 14 | 1.36 | 1.73
P003 | Logistics | SUP039 | 2025-05 | 2025-01-07 | 3580931.78 | 2362742 | -1218189.78 | 1218189.78 | 1 | 2025-05-28 | 2 | 4687902.99 | -1106971.21 | DOWN | 0.3091 | 141 | Low | 807513.15 | 0.224 | 1 | 1555228.85 | 14 | 1.36 | 1.73
P003 | Logistics | SUP039 | 2025-05 | 2025-02-27 | 2997074.62 | 2362742 | -634332.62 | 634332.62 | 1 | 2025-05-28 | 3 | 3580931.78 | -583857.16 | DOWN | 0.1948 | 90 | Low | 1153544.2 | 0.368 | 0 | 1209197.8 | 14 | 1.36 | 1.73
P003 | Electronics | SUP039 | 2025-06 | 2025-02-20 | 2239406.54 | 1387527 | -851879.54 | 851879.54 | 1 | 2025-06-28 | 1 |  |  |  |  | 128 | Low | 590009.42 | 0.257 | 3 | 797517.58 | 22 | 1.47 | 1.51
P003 | Electronics | SUP039 | 2025-06 | 2025-02-21 | 1880050.92 | 1387527 | -492523.92 | 492523.92 | 1 | 2025-06-28 | 2 | 2239406.54 | -359355.62 | DOWN | 0.1911 | 127 | Low | 467161.94 | 0.26 | 0 | 920365.06 | 22 | 1.47 | 1.51
P003 | Electronics | SUP039 | 2025-06 | 2025-03-07 | 1625588.37 | 1387527 | -238061.37 | 238061.37 | 0 | 2025-06-28 | 3 | 1880050.92 | -254462.55 | DOWN | 0.1565 | 113 | Low | 519190.36 | 0.299 | 0 | 868336.64 | 22 | 1.47 | 1.51
P003 | Electronics | SUP039 | 2025-06 | 2025-04-27 | 1519694.08 | 1387527 | -132167.08 | 132167.08 | 0 | 2025-06-28 | 4 | 1625588.37 | -105894.29 | DOWN | 0.0697 | 62 | Low | 704716.52 | 0.442 | 3 | 682810.48 | 22 | 1.47 | 1.51
P003 | Software | SUP039 | 2025-07 | 2025-02-28 | 1615304.31 | 899502 | -715802.31 | 715802.31 | 1 | 2025-07-28 | 1 |  |  |  |  | 150 | Low | 311066.66 | 0.207 | 0 | 588435.34 | 13 | 0.8 | 1.22
P003 | Software | SUP039 | 2025-07 | 2025-04-09 | 1290591.04 | 899502 | -391089.04 | 391089.04 | 1 | 2025-07-28 | 2 | 1615304.31 | -324713.27 | DOWN | 0.2516 | 110 | Low | 421482.98 | 0.325 | 3 | 478019.02 | 13 | 0.8 | 1.22
P003 | Software | SUP039 | 2025-07 | 2025-05-18 | 1128335.95 | 899502 | -228833.95 | 228833.95 | 1 | 2025-07-28 | 3 | 1290591.04 | -162255.09 | DOWN | 0.1438 | 71 | Low | 515782.71 | 0.44 | 5 | 383719.29 | 13 | 0.8 | 1.22
P003 | Software | SUP039 | 2025-07 | 2025-05-27 | 1041059.41 | 899502 | -141557.41 | 141557.41 | 0 | 2025-07-28 | 4 | 1128335.95 | -87276.54 | DOWN | 0.0838 | 62 | Low | 449576.41 | 0.467 | 4 | 449925.59 | 13 | 0.8 | 1.22
P003 | Software | SUP039 | 2025-07 | 2025-06-06 | 988570.49 | 899502 | -89068.49 | 89068.49 | 0 | 2025-07-28 | 5 | 1041059.41 | -52488.92 | DOWN | 0.0531 | 52 | Medium | 452452.21 | 0.496 | 2 | 447049.79 | 13 | 0.8 | 1.22
P003 | Software | SUP039 | 2025-07 | 2025-06-12 | 957589.76 | 899502 | -58087.76 | 58087.76 | 0 | 2025-07-28 | 6 | 988570.49 | -30980.73 | DOWN | 0.0324 | 46 | Medium | 476982.96 | 0.514 | 2 | 422519.04 | 13 | 0.8 | 1.22
P003 | Services | SUP039 | 2025-08 | 2025-04-11 | 2037569.51 | 970778 | -1066791.51 | 1066791.51 | 1 | 2025-08-28 | 1 |  |  |  |  | 139 | Low | 491356.25 | 0.229 | 2 | 479421.75 | 7 | 1.37 | 1.47
P003 | Services | SUP039 | 2025-08 | 2025-04-15 | 1538963.97 | 970778 | -568185.97 | 568185.97 | 1 | 2025-08-28 | 2 | 2037569.51 | -498605.54 | DOWN | 0.324 | 135 | Low | 340857.66 | 0.24 | 2 | 629920.34 | 7 | 1.37 | 1.47
P003 | Services | SUP039 | 2025-08 | 2025-05-28 | 1269634.89 | 970778 | -298856.89 | 298856.89 | 1 | 2025-08-28 | 3 | 1538963.97 | -269329.08 | DOWN | 0.2121 | 92 | Low | 457311.12 | 0.362 | 2 | 513466.88 | 7 | 1.37 | 1.47
P003 | Logistics | SUP039 | 2025-09 | 2025-05-14 | 826831.89 | 386588 | -440243.89 | 440243.89 | 1 | 2025-09-28 | 1 |  |  |  |  | 137 | Low | 187079.8 | 0.245 | 0 | 199508.2 | 10 | 0.71 | 1.27
P003 | Logistics | SUP039 | 2025-09 | 2025-06-17 | 619211.09 | 386588 | -232623.09 | 232623.09 | 1 | 2025-09-28 | 2 | 826831.89 | -207620.8 | DOWN | 0.3353 | 103 | Low | 210749.16 | 0.346 | 1 | 175838.84 | 10 | 0.71 | 1.27
P003 | Logistics | SUP039 | 2025-09 | 2025-08-12 | 502560.16 | 386588 | -115972.16 | 115972.16 | 1 | 2025-09-28 | 3 | 619211.09 | -116650.93 | DOWN | 0.2321 | 47 | Low | 261023.41 | 0.511 | 2 | 125564.59 | 10 | 0.71 | 1.27
P003 | Logistics | SUP039 | 2025-09 | 2025-09-06 | 459330.31 | 386588 | -72742.31 | 72742.31 | 1 | 2025-09-28 | 4 | 502560.16 | -43229.85 | DOWN | 0.0941 | 22 | Medium | 262417.03 | 0.585 | 4 | 124170.97 | 10 | 0.71 | 1.27
P003 | Software | SUP039 | 2025-10 | 2025-05-04 | 1135211.48 | 612251 | -522960.48 | 522960.48 | 1 | 2025-10-28 | 1 |  |  |  |  | 177 | Low | 148698.17 | 0.13 | 2 | 463552.83 | 19 | 0.95 | 0.98
P003 | Software | SUP039 | 2025-10 | 2025-06-20 | 916451.03 | 612251 | -304200.03 | 304200.03 | 1 | 2025-10-28 | 2 | 1135211.48 | -218760.45 | DOWN | 0.2387 | 130 | Low | 227252.27 | 0.266 | 0 | 384998.73 | 19 | 0.95 | 0.98
P003 | Software | SUP039 | 2025-10 | 2025-08-09 | 786359.68 | 612251 | -174108.68 | 174108.68 | 1 | 2025-10-28 | 3 | 916451.03 | -130091.35 | DOWN | 0.1654 | 80 | Low | 307290.7 | 0.414 | 2 | 304960.3 | 19 | 0.95 | 0.98
P003 | Software | SUP039 | 2025-10 | 2025-10-04 | 698866.93 | 612251 | -86615.93 | 86615.93 | 0 | 2025-10-28 | 4 | 786359.68 | -87492.75 | DOWN | 0.1252 | 24 | Low | 381992.56 | 0.579 | 2 | 230258.44 | 19 | 0.95 | 0.98
P003 | Logistics | SUP039 | 2025-11 | 2025-08-08 | 1205026.93 | 612955 | -592071.93 | 592071.93 | 1 | 2025-11-28 | 1 |  |  |  |  | 112 | Low | 354590.63 | 0.29 | 3 | 258364.37 | 11 | 1.85 | 1.52
P003 | Logistics | SUP039 | 2025-11 | 2025-08-23 | 939216.53 | 612955 | -326261.53 | 326261.53 | 1 | 2025-11-28 | 2 | 1205026.93 | -265810.4 | DOWN | 0.283 | 97 | Low | 330697.08 | 0.33 | 1 | 282257.92 | 11 | 1.85 | 1.52
P003 | Logistics | SUP039 | 2025-11 | 2025-10-29 | 784719.01 | 612955 | -171764.01 | 171764.01 | 1 | 2025-11-28 | 3 | 939216.53 | -154497.52 | DOWN | 0.1969 | 30 | Low | 428060.4 | 0.509 | 4 | 184894.6 | 11 | 1.85 | 1.52
P003 | Logistics | SUP039 | 2025-11 | 2025-11-09 | 697256.08 | 612955 | -84301.08 | 84301.08 | 0 | 2025-11-28 | 4 | 784719.01 | -87462.93 | DOWN | 0.1254 | 19 | Low | 373573.66 | 0.539 | 0 | 239381.34 | 11 | 1.85 | 1.52
P003 | Logistics | SUP039 | 2025-11 | 2025-11-13 | 648571.63 | 612955 | -35616.63 | 35616.63 | 0 | 2025-11-28 | 5 | 697256.08 | -48684.45 | DOWN | 0.0751 | 15 | Medium | 366484.89 | 0.55 | 5 | 246470.11 | 11 | 1.85 | 1.52
P003 | Electronics | SUP039 | 2025-12 | 2025-08-14 | 1374684.08 | 772836 | -601848.08 | 601848.08 | 1 | 2025-12-28 | 1 |  |  |  |  | 136 | Low | 342169.34 | 0.246 | 4 | 430666.66 | 10 | 1.08 | 1.22
P003 | Electronics | SUP039 | 2025-12 | 2025-10-23 | 1113324.72 | 772836 | -340488.72 | 340488.72 | 1 | 2025-12-28 | 2 | 1374684.08 | -261359.36 | DOWN | 0.2348 | 66 | Low | 469078.3 | 0.451 | 5 | 303757.7 | 10 | 1.08 | 1.22
P003 | Electronics | SUP039 | 2025-12 | 2025-11-03 | 956732.75 | 772836 | -183896.75 | 183896.75 | 1 | 2025-12-28 | 3 | 1113324.72 | -156591.97 | DOWN | 0.1637 | 55 | Low | 485958.82 | 0.483 | 5 | 286877.18 | 10 | 1.08 | 1.22
P003 | Logistics | SUP036 | 2025-01 | 2024-08-20 | 1950846.57 | 1212712 | -738134.57 | 738134.57 | 1 | 2025-01-28 | 1 |  |  |  |  | 161 | Low | 276625.9 | 0.134 | 1 | 936086.1 | 17 | 1.86 | 1.34
P003 | Logistics | SUP036 | 2025-01 | 2024-09-04 | 1628146.28 | 1212712 | -415434.28 | 415434.28 | 1 | 2025-01-28 | 2 | 1950846.57 | -322700.29 | DOWN | 0.1982 | 146 | Low | 261179.83 | 0.168 | 4 | 951532.17 | 17 | 1.86 | 1.34
P003 | Logistics | SUP036 | 2025-01 | 2024-09-05 | 1410139.04 | 1212712 | -197427.04 | 197427.04 | 0 | 2025-01-28 | 3 | 1628146.28 | -218007.24 | DOWN | 0.1546 | 145 | Low | 240871 | 0.17 | 1 | 971841 | 17 | 1.86 | 1.34
P003 | Logistics | SUP036 | 2025-01 | 2024-10-12 | 1329491.77 | 1212712 | -116779.77 | 116779.77 | 0 | 2025-01-28 | 4 | 1410139.04 | -80647.27 | DOWN | 0.0607 | 108 | Low | 360911.36 | 0.254 | 1 | 851800.64 | 17 | 1.86 | 1.34
P003 | Logistics | SUP036 | 2025-01 | 2024-11-04 | 1284265.69 | 1212712 | -71553.69 | 71553.69 | 0 | 2025-01-28 | 5 | 1329491.77 | -45226.08 | DOWN | 0.0352 | 85 | Low | 361473.83 | 0.306 | 2 | 851238.17 | 17 | 1.86 | 1.34
P003 | Logistics | SUP036 | 2025-01 | 2025-01-12 | 1263094.55 | 1212712 | -50382.55 | 50382.55 | 0 | 2025-01-28 | 6 | 1284265.69 | -21171.14 | DOWN | 0.0168 | 16 | Medium | 599978.67 | 0.462 | 4 | 612733.33 | 17 | 1.86 | 1.34
P003 | Electronics | SUP036 | 2025-02 | 2024-09-22 | 2665951.53 | 1525288 | -1140663.53 | 1140663.53 | 1 | 2025-02-28 | 1 |  |  |  |  | 159 | Low | 333373.23 | 0.135 | 3 | 1191914.77 | 17 | 2.1 | 1.03
P003 | Electronics | SUP036 | 2025-02 | 2024-09-28 | 2220742.99 | 1525288 | -695454.99 | 695454.99 | 1 | 2025-02-28 | 2 | 2665951.53 | -445208.54 | DOWN | 0.2005 | 153 | Low | 334372.95 | 0.148 | 0 | 1190915.05 | 17 | 2.1 | 1.03
P003 | Electronics | SUP036 | 2025-02 | 2024-10-25 | 1949674.71 | 1525288 | -424386.71 | 424386.71 | 1 | 2025-02-28 | 3 | 2220742.99 | -271068.28 | DOWN | 0.139 | 126 | Low | 426178.03 | 0.208 | 2 | 1099109.97 | 17 | 2.1 | 1.03
P003 | Electronics | SUP036 | 2025-02 | 2024-11-07 | 1745237.05 | 1525288 | -219949.05 | 219949.05 | 0 | 2025-02-28 | 4 | 1949674.71 | -204437.66 | DOWN | 0.1171 | 113 | Low | 381894.24 | 0.236 | 1 | 1143393.76 | 17 | 2.1 | 1.03
P003 | Electronics | SUP036 | 2025-02 | 2024-11-20 | 1691404.95 | 1525288 | -166116.95 | 166116.95 | 0 | 2025-02-28 | 5 | 1745237.05 | -53832.1 | DOWN | 0.0318 | 100 | Low | 460873.51 | 0.265 | 3 | 1064414.49 | 17 | 2.1 | 1.03
P003 | Logistics | SUP036 | 2025-03 | 2024-10-30 | 2308197.09 | 1220660 | -1087537.09 | 1087537.09 | 1 | 2025-03-28 | 1 |  |  |  |  | 149 | Low | 412939.34 | 0.175 | 2 | 807720.66 | 13 | 1.13 | 1.73
P003 | Logistics | SUP036 | 2025-03 | 2024-12-25 | 1868540.75 | 1220660 | -647880.75 | 647880.75 | 1 | 2025-03-28 | 2 | 2308197.09 | -439656.34 | DOWN | 0.2353 | 93 | Low | 596667.52 | 0.313 | 3 | 623992.48 | 13 | 1.13 | 1.73
P003 | Logistics | SUP036 | 2025-03 | 2025-02-23 | 1639830.79 | 1220660 | -419170.79 | 419170.79 | 1 | 2025-03-28 | 3 | 1868540.75 | -228709.96 | DOWN | 0.1395 | 33 | Low | 696521.19 | 0.46 | 3 | 524138.81 | 13 | 1.13 | 1.73
P003 | Services | SUP036 | 2025-04 | 2024-10-31 | 935426.25 | 567960 | -367466.25 | 367466.25 | 1 | 2025-04-28 | 1 |  |  |  |  | 179 | Low | 103801.69 | 0.107 | 0 | 464158.31 | 13 | 1.21 | 1.27
P003 | Services | SUP036 | 2025-04 | 2024-10-31 | 796278.75 | 567960 | -228318.75 | 228318.75 | 1 | 2025-04-28 | 2 | 935426.25 | -139147.5 | DOWN | 0.1747 | 179 | Low | 89318.26 | 0.107 | 2 | 478641.74 | 13 | 1.21 | 1.27
P003 | Services | SUP036 | 2025-04 | 2024-11-30 | 698919.19 | 567960 | -130959.19 | 130959.19 | 1 | 2025-04-28 | 3 | 796278.75 | -97359.56 | DOWN | 0.1393 | 149 | Low | 126979.6 | 0.173 | 0 | 440980.4 | 13 | 1.21 | 1.27
P003 | Services | SUP036 | 2025-04 | 2025-02-16 | 634860.81 | 567960 | -66900.81 | 66900.81 | 0 | 2025-04-28 | 4 | 698919.19 | -64058.38 | DOWN | 0.1009 | 71 | Low | 225018.92 | 0.363 | 3 | 342941.08 | 13 | 1.21 | 1.27
P003 | Services | SUP036 | 2025-04 | 2025-02-20 | 612617.18 | 567960 | -44657.18 | 44657.18 | 0 | 2025-04-28 | 5 | 634860.81 | -22243.63 | DOWN | 0.0363 | 67 | Low | 232669.4 | 0.373 | 1 | 335290.6 | 13 | 1.21 | 1.27
P003 | Logistics | SUP036 | 2025-05 | 2024-12-29 | 3833931.09 | 2321488 | -1512443.09 | 1512443.09 | 1 | 2025-05-28 | 1 |  |  |  |  | 150 | Low | 614882.07 | 0.168 | 0 | 1706605.93 | 14 | 1.36 | 1.73
P003 | Logistics | SUP036 | 2025-05 | 2025-01-09 | 3169593.17 | 2321488 | -848105.17 | 848105.17 | 1 | 2025-05-28 | 2 | 3833931.09 | -664337.92 | DOWN | 0.2096 | 139 | Low | 638532.46 | 0.194 | 0 | 1682955.54 | 14 | 1.36 | 1.73
P003 | Logistics | SUP036 | 2025-05 | 2025-04-14 | 2841087.17 | 2321488 | -519599.17 | 519599.17 | 1 | 2025-05-28 | 3 | 3169593.17 | -328506 | DOWN | 0.1156 | 44 | Low | 1193598.85 | 0.422 | 2 | 1127889.15 | 14 | 1.36 | 1.73
P003 | Logistics | SUP036 | 2025-06 | 2025-02-23 | 2021627.57 | 971745 | -1049882.57 | 1049882.57 | 1 | 2025-06-28 | 1 |  |  |  |  | 125 | Low | 435641.75 | 0.225 | 3 | 536103.25 | 22 | 1.47 | 1.51
P003 | Logistics | SUP036 | 2025-06 | 2025-04-01 | 1606446.28 | 971745 | -634701.28 | 634701.28 | 1 | 2025-06-28 | 2 | 2021627.57 | -415181.29 | DOWN | 0.2584 | 88 | Low | 493408.17 | 0.312 | 2 | 478336.83 | 22 | 1.47 | 1.51
P003 | Logistics | SUP036 | 2025-06 | 2025-04-28 | 1330112.85 | 971745 | -358367.85 | 358367.85 | 1 | 2025-06-28 | 3 | 1606446.28 | -276333.43 | DOWN | 0.2078 | 61 | Low | 518779.12 | 0.376 | 5 | 452965.88 | 22 | 1.47 | 1.51
P003 | Logistics | SUP036 | 2025-06 | 2025-05-07 | 1202169.95 | 971745 | -230424.95 | 230424.95 | 1 | 2025-06-28 | 4 | 1330112.85 | -127942.9 | DOWN | 0.1064 | 52 | Low | 460042.34 | 0.398 | 3 | 511702.66 | 22 | 1.47 | 1.51
P003 | Logistics | SUP036 | 2025-06 | 2025-05-16 | 1116717.41 | 971745 | -144972.41 | 144972.41 | 0 | 2025-06-28 | 5 | 1202169.95 | -85452.54 | DOWN | 0.0765 | 43 | Low | 435126.19 | 0.419 | 2 | 536618.81 | 22 | 1.47 | 1.51
P003 | Services | SUP036 | 2025-07 | 2025-03-02 | 369124.02 | 190980 | -178144.02 | 178144.02 | 1 | 2025-07-28 | 1 |  |  |  |  | 148 | Low | 71286.97 | 0.18 | 4 | 119693.03 | 13 | 0.8 | 1.22
P003 | Services | SUP036 | 2025-07 | 2025-03-21 | 296223.26 | 190980 | -105243.26 | 105243.26 | 1 | 2025-07-28 | 2 | 369124.02 | -72900.76 | DOWN | 0.2461 | 129 | Low | 67036.2 | 0.228 | 1 | 123943.8 | 13 | 0.8 | 1.22
P003 | Services | SUP036 | 2025-07 | 2025-04-03 | 255647.97 | 190980 | -64667.97 | 64667.97 | 1 | 2025-07-28 | 3 | 296223.26 | -40575.29 | DOWN | 0.1587 | 116 | Low | 71355.06 | 0.26 | 0 | 119624.94 | 13 | 0.8 | 1.22
P003 | Services | SUP036 | 2025-07 | 2025-06-08 | 230125 | 190980 | -39145 | 39145 | 1 | 2025-07-28 | 4 | 255647.97 | -25522.97 | DOWN | 0.1109 | 50 | Low | 96021.19 | 0.425 | 5 | 94958.81 | 13 | 0.8 | 1.22
P003 | Services | SUP036 | 2025-07 | 2025-06-16 | 212405.26 | 190980 | -21425.26 | 21425.26 | 0 | 2025-07-28 | 5 | 230125 | -17719.74 | DOWN | 0.0834 | 42 | Low | 87873.67 | 0.445 | 6 | 103106.33 | 13 | 0.8 | 1.22
P003 | Services | SUP036 | 2025-07 | 2025-07-13 | 204222.99 | 190980 | -13242.99 | 13242.99 | 0 | 2025-07-28 | 6 | 212405.26 | -8182.27 | DOWN | 0.0401 | 15 | Medium | 111921.35 | 0.513 | 6 | 79058.65 | 13 | 0.8 | 1.22
P003 | Software | SUP036 | 2025-08 | 2025-03-16 | 2065400.2 | 1289393 | -776007.2 | 776007.2 | 1 | 2025-08-28 | 1 |  |  |  |  | 165 | Low | 271143.13 | 0.132 | 1 | 1018249.87 | 7 | 1.37 | 1.47
P003 | Software | SUP036 | 2025-08 | 2025-04-23 | 1725567.24 | 1289393 | -436174.24 | 436174.24 | 1 | 2025-08-28 | 2 | 2065400.2 | -339832.96 | DOWN | 0.1969 | 127 | Low | 406224.27 | 0.223 | 0 | 883168.73 | 7 | 1.37 | 1.47
P003 | Software | SUP036 | 2025-08 | 2025-06-20 | 1563685.44 | 1289393 | -274292.44 | 274292.44 | 1 | 2025-08-28 | 3 | 1725567.24 | -161881.8 | DOWN | 0.1035 | 69 | Low | 538535.87 | 0.361 | 5 | 750857.13 | 7 | 1.37 | 1.47
P003 | Software | SUP036 | 2025-08 | 2025-07-15 | 1428310.76 | 1289393 | -138917.76 | 138917.76 | 0 | 2025-08-28 | 4 | 1563685.44 | -135374.68 | DOWN | 0.0948 | 44 | Low | 596751.5 | 0.421 | 1 | 692641.5 | 7 | 1.37 | 1.47
P003 | Software | SUP036 | 2025-08 | 2025-07-29 | 1373834.93 | 1289393 | -84441.93 | 84441.93 | 0 | 2025-08-28 | 5 | 1428310.76 | -54475.83 | DOWN | 0.0397 | 30 | Medium | 662692.18 | 0.455 | 2 | 626700.82 | 7 | 1.37 | 1.47
P003 | Software | SUP036 | 2025-08 | 2025-08-11 | 1337067.12 | 1289393 | -47674.12 | 47674.12 | 0 | 2025-08-28 | 6 | 1373834.93 | -36767.81 | DOWN | 0.0275 | 17 | Medium | 688655.84 | 0.486 | 1 | 600737.16 | 7 | 1.37 | 1.47
P003 | Electronics | SUP036 | 2025-09 | 2025-05-01 | 2212086.4 | 1261345 | -950741.4 | 950741.4 | 1 | 2025-09-28 | 1 |  |  |  |  | 150 | Low | 371126.81 | 0.175 | 0 | 890218.19 | 10 | 0.71 | 1.27
P003 | Electronics | SUP036 | 2025-09 | 2025-05-06 | 1838068.93 | 1261345 | -576723.93 | 576723.93 | 1 | 2025-09-28 | 2 | 2212086.4 | -374017.47 | DOWN | 0.2035 | 145 | Low | 357879.13 | 0.188 | 1 | 903465.87 | 10 | 0.71 | 1.27
P003 | Electronics | SUP036 | 2025-09 | 2025-05-27 | 1587451.63 | 1261345 | -326106.63 | 326106.63 | 1 | 2025-09-28 | 3 | 1838068.93 | -250617.3 | DOWN | 0.1579 | 124 | Low | 374784.04 | 0.24 | 2 | 886560.96 | 10 | 0.71 | 1.27
P003 | Electronics | SUP036 | 2025-09 | 2025-05-28 | 1465924.04 | 1261345 | -204579.04 | 204579.04 | 0 | 2025-09-28 | 4 | 1587451.63 | -121527.59 | DOWN | 0.0829 | 123 | Low | 383000.2 | 0.243 | 0 | 878344.8 | 10 | 0.71 | 1.27
P003 | Electronics | SUP036 | 2025-09 | 2025-07-04 | 1369608.39 | 1261345 | -108263.39 | 108263.39 | 0 | 2025-09-28 | 5 | 1465924.04 | -96315.65 | DOWN | 0.0703 | 86 | Low | 469805.63 | 0.335 | 6 | 791539.37 | 10 | 0.71 | 1.27
P003 | Mechanical | SUP036 | 2025-10 | 2025-06-01 | 511835.48 | 348444 | -163391.48 | 163391.48 | 1 | 2025-10-28 | 1 |  |  |  |  | 149 | Low | 96656.06 | 0.178 | 1 | 251787.94 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP036 | 2025-10 | 2025-06-10 | 446722.84 | 348444 | -98278.84 | 98278.84 | 1 | 2025-10-28 | 2 | 511835.48 | -65112.64 | DOWN | 0.1458 | 140 | Low | 85155.68 | 0.2 | 2 | 263288.32 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP036 | 2025-10 | 2025-07-24 | 408536.27 | 348444 | -60092.27 | 60092.27 | 0 | 2025-10-28 | 3 | 446722.84 | -38186.57 | DOWN | 0.0935 | 96 | Low | 124155.89 | 0.31 | 2 | 224288.11 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP036 | 2025-10 | 2025-08-27 | 383702.38 | 348444 | -35258.38 | 35258.38 | 0 | 2025-10-28 | 4 | 408536.27 | -24833.89 | DOWN | 0.0647 | 62 | Low | 160142.66 | 0.395 | 5 | 188301.34 | 19 | 0.95 | 0.98
P003 | Electronics | SUP036 | 2025-11 | 2025-06-21 | 2862751.81 | 1744827 | -1117924.81 | 1117924.81 | 1 | 2025-11-28 | 1 |  |  |  |  | 160 | Low | 399382.94 | 0.136 | 3 | 1345444.06 | 11 | 1.85 | 1.52
P003 | Electronics | SUP036 | 2025-11 | 2025-08-01 | 2359260.1 | 1744827 | -614433.1 | 614433.1 | 1 | 2025-11-28 | 2 | 2862751.81 | -503491.71 | DOWN | 0.2134 | 119 | Low | 555793.69 | 0.229 | 0 | 1189033.31 | 11 | 1.85 | 1.52
P003 | Electronics | SUP036 | 2025-11 | 2025-08-22 | 2152509.35 | 1744827 | -407682.35 | 407682.35 | 1 | 2025-11-28 | 3 | 2359260.1 | -206750.75 | DOWN | 0.0961 | 98 | Low | 588262.8 | 0.277 | 3 | 1156564.2 | 11 | 1.85 | 1.52
P003 | Electronics | SUP036 | 2025-11 | 2025-09-28 | 2022580.51 | 1744827 | -277753.51 | 277753.51 | 0 | 2025-11-28 | 4 | 2152509.35 | -129928.84 | DOWN | 0.0642 | 61 | Low | 688614.1 | 0.361 | 3 | 1056212.9 | 11 | 1.85 | 1.52
P003 | Electronics | SUP036 | 2025-11 | 2025-10-22 | 1902852.67 | 1744827 | -158025.67 | 158025.67 | 0 | 2025-11-28 | 5 | 2022580.51 | -119727.84 | DOWN | 0.0629 | 37 | Low | 796191.72 | 0.415 | 6 | 948635.28 | 11 | 1.85 | 1.52
P003 | Electronics | SUP036 | 2025-11 | 2025-11-10 | 1819567.07 | 1744827 | -74740.07 | 74740.07 | 0 | 2025-11-28 | 6 | 1902852.67 | -83285.6 | DOWN | 0.0458 | 18 | Medium | 802001.78 | 0.458 | 3 | 942825.22 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP036 | 2025-12 | 2025-08-06 | 3470261.99 | 2401657 | -1068604.99 | 1068604.99 | 1 | 2025-12-28 | 1 |  |  |  |  | 144 | Low | 630897.7 | 0.188 | 1 | 1770759.3 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP036 | 2025-12 | 2025-08-18 | 3041846.82 | 2401657 | -640189.82 | 640189.82 | 1 | 2025-12-28 | 2 | 3470261.99 | -428415.17 | DOWN | 0.1408 | 132 | Low | 679793.97 | 0.218 | 4 | 1721863.03 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP036 | 2025-12 | 2025-11-27 | 2778586.83 | 2401657 | -376929.83 | 376929.83 | 0 | 2025-12-28 | 3 | 3041846.82 | -263259.99 | DOWN | 0.0947 | 31 | Medium | 1301736.74 | 0.468 | 3 | 1099920.26 | 10 | 1.08 | 1.22
P003 | Logistics | SUP031 | 2025-01 | 2024-08-07 | 4562486.71 | 2345618 | -2216868.71 | 2216868.71 | 1 | 2025-01-28 | 1 |  |  |  |  | 174 | Low | 628121.43 | 0.148 | 0 | 1717496.57 | 17 | 1.86 | 1.34
P003 | Logistics | SUP031 | 2025-01 | 2024-09-26 | 3253371.09 | 2345618 | -907753.09 | 907753.09 | 1 | 2025-01-28 | 2 | 4562486.71 | -1309115.62 | DOWN | 0.4024 | 124 | Low | 1037880.75 | 0.309 | 3 | 1307737.25 | 17 | 1.86 | 1.34
P003 | Logistics | SUP031 | 2025-01 | 2024-11-27 | 2769052.12 | 2345618 | -423434.12 | 423434.12 | 1 | 2025-01-28 | 3 | 3253371.09 | -484318.97 | DOWN | 0.1749 | 62 | Low | 1345119.3 | 0.508 | 4 | 1000498.7 | 17 | 1.86 | 1.34
P003 | Logistics | SUP031 | 2025-01 | 2024-12-19 | 2568183.1 | 2345618 | -222565.1 | 222565.1 | 0 | 2025-01-28 | 4 | 2769052.12 | -200869.02 | DOWN | 0.0782 | 40 | Medium | 1525999.02 | 0.578 | 6 | 819618.98 | 17 | 1.86 | 1.34
P003 | Software | SUP031 | 2025-02 | 2024-09-11 | 807995.76 | 471807 | -336188.76 | 336188.76 | 1 | 2025-02-28 | 1 |  |  |  |  | 170 | Low | 118557.84 | 0.157 | 1 | 353249.16 | 17 | 2.1 | 1.03
P003 | Software | SUP031 | 2025-02 | 2024-10-18 | 613666.51 | 471807 | -141859.51 | 141859.51 | 1 | 2025-02-28 | 2 | 807995.76 | -194329.25 | DOWN | 0.3167 | 133 | Low | 164850.28 | 0.272 | 1 | 306956.72 | 17 | 2.1 | 1.03
P003 | Software | SUP031 | 2025-02 | 2024-11-16 | 553582.02 | 471807 | -81775.02 | 81775.02 | 0 | 2025-02-28 | 3 | 613666.51 | -60084.49 | DOWN | 0.1085 | 104 | Low | 199103.44 | 0.363 | 0 | 272703.56 | 17 | 2.1 | 1.03
P003 | Software | SUP031 | 2025-02 | 2024-11-26 | 497939.17 | 471807 | -26132.17 | 26132.17 | 0 | 2025-02-28 | 4 | 553582.02 | -55642.85 | DOWN | 0.1117 | 94 | Low | 188084.32 | 0.395 | 3 | 283722.68 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP031 | 2025-03 | 2024-10-12 | 1132611.33 | 893460 | -239151.33 | 239151.33 | 1 | 2025-03-28 | 1 |  |  |  |  | 167 | Low | 210640.21 | 0.185 | 1 | 682819.79 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP031 | 2025-03 | 2024-10-16 | 1001221.33 | 893460 | -107761.33 | 107761.33 | 0 | 2025-03-28 | 2 | 1132611.33 | -131390 | DOWN | 0.1312 | 163 | Low | 185834.77 | 0.199 | 3 | 707625.23 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP031 | 2025-03 | 2025-02-23 | 945871.03 | 893460 | -52411.03 | 52411.03 | 0 | 2025-03-28 | 3 | 1001221.33 | -55350.3 | DOWN | 0.0585 | 33 | Medium | 641091.91 | 0.653 | 2 | 252368.09 | 13 | 1.13 | 1.73
P003 | Materials | SUP031 | 2025-04 | 2025-01-03 | 2289762.02 | 1801081 | -488681.02 | 488681.02 | 1 | 2025-04-28 | 1 |  |  |  |  | 115 | Low | 775112.47 | 0.363 | 4 | 1025968.53 | 13 | 1.21 | 1.27
P003 | Materials | SUP031 | 2025-04 | 2025-02-07 | 2029121.49 | 1801081 | -228040.49 | 228040.49 | 0 | 2025-04-28 | 2 | 2289762.02 | -260640.53 | DOWN | 0.1284 | 80 | Low | 1029828.97 | 0.484 | 0 | 771252.03 | 13 | 1.21 | 1.27
P003 | Materials | SUP031 | 2025-04 | 2025-03-28 | 1895695.66 | 1801081 | -94614.66 | 94614.66 | 0 | 2025-04-28 | 3 | 2029121.49 | -133425.83 | DOWN | 0.0704 | 31 | Medium | 1168038.28 | 0.654 | 6 | 633042.72 | 13 | 1.21 | 1.27
P003 | Materials | SUP031 | 2025-04 | 2025-03-28 | 1827305.81 | 1801081 | -26224.81 | 26224.81 | 0 | 2025-04-28 | 4 | 1895695.66 | -68389.85 | DOWN | 0.0374 | 31 | Medium | 1140670.25 | 0.654 | 8 | 660410.75 | 13 | 1.21 | 1.27
P003 | Materials | SUP031 | 2025-04 | 2025-04-15 | 1792183.4 | 1801081 | 8897.6 | 8897.6 | 0 | 2025-04-28 | 5 | 1827305.81 | -35122.41 | DOWN | 0.0196 | 13 | High | 1362300 | 0.716 | 8 | 438781 | 13 | 1.21 | 1.27
P003 | Materials | SUP031 | 2025-05 | 2024-12-08 | 4022535.6 | 2441254 | -1581281.6 | 1581281.6 | 1 | 2025-05-28 | 1 |  |  |  |  | 171 | Low | 665018.15 | 0.167 | 0 | 1776235.85 | 14 | 1.36 | 1.73
P003 | Materials | SUP031 | 2025-05 | 2025-01-23 | 3148432.45 | 2441254 | -707178.45 | 707178.45 | 1 | 2025-05-28 | 2 | 4022535.6 | -874103.15 | DOWN | 0.2776 | 125 | Low | 1092062.88 | 0.323 | 4 | 1349191.12 | 14 | 1.36 | 1.73
P003 | Materials | SUP031 | 2025-05 | 2025-02-11 | 2738640.15 | 2441254 | -297386.15 | 297386.15 | 0 | 2025-05-28 | 3 | 3148432.45 | -409792.3 | DOWN | 0.1496 | 106 | Low | 1014833.83 | 0.387 | 2 | 1426420.17 | 14 | 1.36 | 1.73
P003 | Materials | SUP031 | 2025-05 | 2025-03-26 | 2546454.33 | 2441254 | -105200.33 | 105200.33 | 0 | 2025-05-28 | 4 | 2738640.15 | -192185.82 | DOWN | 0.0755 | 63 | Low | 1342080.49 | 0.534 | 4 | 1099173.51 | 14 | 1.36 | 1.73
P003 | Materials | SUP031 | 2025-05 | 2025-05-04 | 2501552.62 | 2441254 | -60298.62 | 60298.62 | 0 | 2025-05-28 | 5 | 2546454.33 | -44901.71 | DOWN | 0.0179 | 24 | High | 1764783.97 | 0.666 | 7 | 676470.03 | 14 | 1.36 | 1.73
P003 | Materials | SUP031 | 2025-05 | 2025-05-04 | 2491385.18 | 2441254 | -50131.18 | 50131.18 | 0 | 2025-05-28 | 6 | 2501552.62 | -10167.44 | DOWN | 0.0041 | 24 | High | 1753068.45 | 0.666 | 7 | 688185.55 | 14 | 1.36 | 1.73
P003 | Materials | SUP031 | 2025-06 | 2025-02-08 | 539220.24 | 367794 | -171426.24 | 171426.24 | 1 | 2025-06-28 | 1 |  |  |  |  | 140 | Low | 151338.99 | 0.268 | 6 | 216455.01 | 22 | 1.47 | 1.51
P003 | Materials | SUP031 | 2025-06 | 2025-04-06 | 440910.7 | 367794 | -73116.7 | 73116.7 | 1 | 2025-06-28 | 2 | 539220.24 | -98309.54 | DOWN | 0.223 | 83 | Low | 209238.98 | 0.46 | 4 | 158555.02 | 22 | 1.47 | 1.51
P003 | Materials | SUP031 | 2025-06 | 2025-05-19 | 398644.45 | 367794 | -30850.45 | 30850.45 | 0 | 2025-06-28 | 3 | 440910.7 | -42266.25 | DOWN | 0.106 | 40 | Medium | 245272.84 | 0.604 | 6 | 122521.16 | 22 | 1.47 | 1.51
P003 | Logistics | SUP031 | 2025-07 | 2025-02-12 | 889478.89 | 485562 | -403916.89 | 403916.89 | 1 | 2025-07-28 | 1 |  |  |  |  | 166 | Low | 161775.02 | 0.191 | 1 | 323786.98 | 13 | 0.8 | 1.22
P003 | Logistics | SUP031 | 2025-07 | 2025-03-06 | 685902.41 | 485562 | -200340.41 | 200340.41 | 1 | 2025-07-28 | 2 | 889478.89 | -203576.48 | DOWN | 0.2968 | 144 | Low | 190077.13 | 0.269 | 4 | 295484.87 | 13 | 0.8 | 1.22
P003 | Logistics | SUP031 | 2025-07 | 2025-05-25 | 576885.65 | 485562 | -91323.65 | 91323.65 | 1 | 2025-07-28 | 3 | 685902.41 | -109016.76 | DOWN | 0.189 | 64 | Low | 325170.13 | 0.553 | 4 | 160391.87 | 13 | 0.8 | 1.22
P003 | Logistics | SUP031 | 2025-07 | 2025-06-19 | 523834.51 | 485562 | -38272.51 | 38272.51 | 0 | 2025-07-28 | 4 | 576885.65 | -53051.14 | DOWN | 0.1013 | 39 | Medium | 338914.58 | 0.642 | 4 | 146647.42 | 13 | 0.8 | 1.22
P003 | Logistics | SUP031 | 2025-07 | 2025-06-22 | 499168.3 | 485562 | -13606.3 | 13606.3 | 0 | 2025-07-28 | 5 | 523834.51 | -24666.21 | DOWN | 0.0494 | 36 | Medium | 330374.51 | 0.652 | 2 | 155187.49 | 13 | 0.8 | 1.22
P003 | Logistics | SUP031 | 2025-08 | 2025-03-07 | 1384737.53 | 801563 | -583174.53 | 583174.53 | 1 | 2025-08-28 | 1 |  |  |  |  | 174 | Low | 205373.01 | 0.156 | 1 | 596189.99 | 7 | 1.37 | 1.47
P003 | Logistics | SUP031 | 2025-08 | 2025-05-08 | 1064481.96 | 801563 | -262918.96 | 262918.96 | 1 | 2025-08-28 | 2 | 1384737.53 | -320255.57 | DOWN | 0.3009 | 112 | Low | 375852.03 | 0.367 | 7 | 425710.97 | 7 | 1.37 | 1.47
P003 | Logistics | SUP031 | 2025-08 | 2025-05-20 | 932297.25 | 801563 | -130734.25 | 130734.25 | 0 | 2025-08-28 | 3 | 1064481.96 | -132184.71 | DOWN | 0.1418 | 100 | Low | 361239.53 | 0.407 | 2 | 440323.47 | 7 | 1.37 | 1.47
P003 | Logistics | SUP031 | 2025-08 | 2025-05-27 | 856171.86 | 801563 | -54608.86 | 54608.86 | 0 | 2025-08-28 | 4 | 932297.25 | -76125.39 | DOWN | 0.0889 | 93 | Low | 371904.24 | 0.431 | 6 | 429658.76 | 7 | 1.37 | 1.47
P003 | Logistics | SUP031 | 2025-08 | 2025-07-09 | 816299.08 | 801563 | -14736.08 | 14736.08 | 0 | 2025-08-28 | 5 | 856171.86 | -39872.78 | DOWN | 0.0488 | 50 | Medium | 485549.59 | 0.577 | 3 | 316013.41 | 7 | 1.37 | 1.47
P003 | Logistics | SUP031 | 2025-08 | 2025-07-10 | 798386.06 | 801563 | 3176.94 | 3176.94 | 0 | 2025-08-28 | 6 | 816299.08 | -17913.02 | DOWN | 0.0224 | 49 | Medium | 448895.06 | 0.58 | 4 | 352667.94 | 7 | 1.37 | 1.47
P003 | Materials | SUP031 | 2025-09 | 2025-08-12 | 2430042.24 | 1568163 | -861879.24 | 861879.24 | 1 | 2025-09-28 | 1 |  |  |  |  | 47 | Medium | 1435250.71 | 0.613 | 3 | 132912.29 | 10 | 0.71 | 1.27
P003 | Materials | SUP031 | 2025-09 | 2025-08-19 | 1943660.81 | 1568163 | -375497.81 | 375497.81 | 1 | 2025-09-28 | 2 | 2430042.24 | -486381.43 | DOWN | 0.2502 | 40 | Low | 1330242.39 | 0.638 | 1 | 237920.61 | 10 | 0.71 | 1.27
P003 | Materials | SUP031 | 2025-09 | 2025-09-15 | 1723870.14 | 1568163 | -155707.14 | 155707.14 | 0 | 2025-09-28 | 3 | 1943660.81 | -219790.67 | DOWN | 0.1275 | 13 | Low | 1194869.4 | 0.734 | 6 | 373293.6 | 10 | 0.71 | 1.27
P003 | Materials | SUP031 | 2025-10 | 2025-06-06 | 1042444.58 | 697580 | -344864.58 | 344864.58 | 1 | 2025-10-28 | 1 |  |  |  |  | 144 | Low | 272435.16 | 0.269 | 0 | 425144.84 | 19 | 0.95 | 0.98
P003 | Materials | SUP031 | 2025-10 | 2025-07-16 | 846794.37 | 697580 | -149214.37 | 149214.37 | 1 | 2025-10-28 | 2 | 1042444.58 | -195650.21 | DOWN | 0.231 | 104 | Low | 357950.24 | 0.411 | 3 | 339629.76 | 19 | 0.95 | 0.98
P003 | Materials | SUP031 | 2025-10 | 2025-09-06 | 762416.83 | 697580 | -64836.83 | 64836.83 | 0 | 2025-10-28 | 3 | 846794.37 | -84377.54 | DOWN | 0.1107 | 52 | Medium | 472328.18 | 0.596 | 6 | 225251.82 | 19 | 0.95 | 0.98
P003 | Materials | SUP031 | 2025-10 | 2025-09-09 | 725291.74 | 697580 | -27711.74 | 27711.74 | 0 | 2025-10-28 | 4 | 762416.83 | -37125.09 | DOWN | 0.0512 | 49 | Medium | 409960.69 | 0.606 | 5 | 287619.31 | 19 | 0.95 | 0.98
P003 | Electronics | SUP031 | 2025-11 | 2025-06-06 | 822466.79 | 578881 | -243585.79 | 243585.79 | 1 | 2025-11-28 | 1 |  |  |  |  | 175 | Low | 110208.03 | 0.145 | 0 | 468672.97 | 11 | 1.85 | 1.52
P003 | Electronics | SUP031 | 2025-11 | 2025-07-15 | 701638.09 | 578881 | -122757.09 | 122757.09 | 1 | 2025-11-28 | 2 | 822466.79 | -120828.7 | DOWN | 0.1722 | 136 | Low | 200975.8 | 0.27 | 0 | 377905.2 | 11 | 1.85 | 1.52
P003 | Electronics | SUP031 | 2025-11 | 2025-10-21 | 649773.95 | 578881 | -70892.95 | 70892.95 | 0 | 2025-11-28 | 3 | 701638.09 | -51864.14 | DOWN | 0.0798 | 38 | Medium | 360396.05 | 0.586 | 0 | 218484.95 | 11 | 1.85 | 1.52
P003 | Electronics | SUP031 | 2025-11 | 2025-10-29 | 617802.5 | 578881 | -38921.5 | 38921.5 | 0 | 2025-11-28 | 4 | 649773.95 | -31971.45 | DOWN | 0.0518 | 30 | Medium | 384737.03 | 0.611 | 3 | 194143.97 | 11 | 1.85 | 1.52
P003 | Electronics | SUP031 | 2025-11 | 2025-11-04 | 594225.34 | 578881 | -15344.34 | 15344.34 | 0 | 2025-11-28 | 5 | 617802.5 | -23577.16 | DOWN | 0.0397 | 24 | Medium | 383128.6 | 0.631 | 1 | 195752.4 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP031 | 2025-12 | 2025-07-23 | 3197081.96 | 2216351 | -980730.96 | 980730.96 | 1 | 2025-12-28 | 1 |  |  |  |  | 158 | Low | 691866.38 | 0.218 | 4 | 1524484.62 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP031 | 2025-12 | 2025-08-02 | 2673816.09 | 2216351 | -457465.09 | 457465.09 | 1 | 2025-12-28 | 2 | 3197081.96 | -523265.87 | DOWN | 0.1957 | 148 | Low | 634035.45 | 0.253 | 4 | 1582315.55 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP031 | 2025-12 | 2025-09-19 | 2417729.92 | 2216351 | -201378.92 | 201378.92 | 0 | 2025-12-28 | 3 | 2673816.09 | -256086.17 | DOWN | 0.1059 | 100 | Low | 1024039.3 | 0.421 | 5 | 1192311.7 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP031 | 2025-12 | 2025-12-08 | 2320508.27 | 2216351 | -104157.27 | 104157.27 | 0 | 2025-12-28 | 4 | 2417729.92 | -97221.65 | DOWN | 0.0419 | 20 | High | 1753103.51 | 0.702 | 6 | 463247.49 | 10 | 1.08 | 1.22
P003 | Electronics | SUP013 | 2025-01 | 2024-08-13 | 4352994.58 | 2258772 | -2094222.58 | 2094222.58 | 1 | 2025-01-28 | 1 |  |  |  |  | 168 | Low | 435224.55 | 0.107 | 0 | 1823547.45 | 17 | 1.86 | 1.34
P003 | Electronics | SUP013 | 2025-01 | 2024-11-28 | 3786252.61 | 2258772 | -1527480.61 | 1527480.61 | 1 | 2025-01-28 | 2 | 4352994.58 | -566741.97 | DOWN | 0.1497 | 61 | Low | 1233581.25 | 0.328 | 3 | 1025190.75 | 17 | 1.86 | 1.34
P003 | Electronics | SUP013 | 2025-01 | 2024-11-29 | 3421431.09 | 2258772 | -1162659.09 | 1162659.09 | 1 | 2025-01-28 | 3 | 3786252.61 | -364821.52 | DOWN | 0.1066 | 60 | Low | 1157051.47 | 0.33 | 4 | 1101720.53 | 17 | 1.86 | 1.34
P003 | Electronics | SUP013 | 2025-01 | 2025-01-10 | 3222082.9 | 2258772 | -963310.9 | 963310.9 | 1 | 2025-01-28 | 4 | 3421431.09 | -199348.19 | DOWN | 0.0619 | 18 | Low | 1372635.95 | 0.416 | 4 | 886136.05 | 17 | 1.86 | 1.34
P003 | Electronics | SUP013 | 2025-01 | 2025-01-18 | 2912397.04 | 2258772 | -653625.04 | 653625.04 | 1 | 2025-01-28 | 5 | 3222082.9 | -309685.86 | DOWN | 0.1063 | 10 | Low | 1231083.19 | 0.431 | 3 | 1027688.81 | 17 | 1.86 | 1.34
P003 | Electronics | SUP013 | 2025-02 | 2024-09-13 | 2366284.66 | 1162182 | -1204102.66 | 1204102.66 | 1 | 2025-02-28 | 1 |  |  |  |  | 168 | Low | 251608.65 | 0.104 | 0 | 910573.35 | 17 | 2.1 | 1.03
P003 | Electronics | SUP013 | 2025-02 | 2024-09-27 | 2054731.65 | 1162182 | -892549.65 | 892549.65 | 1 | 2025-02-28 | 2 | 2366284.66 | -311553.01 | DOWN | 0.1516 | 154 | Low | 262278.26 | 0.133 | 1 | 899903.74 | 17 | 2.1 | 1.03
P003 | Electronics | SUP013 | 2025-02 | 2025-01-27 | 1874511.85 | 1162182 | -712329.85 | 712329.85 | 1 | 2025-02-28 | 3 | 2054731.65 | -180219.8 | DOWN | 0.0961 | 32 | Low | 690944.88 | 0.377 | 1 | 471237.12 | 17 | 2.1 | 1.03
P003 | Electronics | SUP013 | 2025-02 | 2025-02-10 | 1664963.05 | 1162182 | -502781.05 | 502781.05 | 1 | 2025-02-28 | 4 | 1874511.85 | -209548.8 | DOWN | 0.1259 | 18 | Low | 718871.19 | 0.406 | 4 | 443310.81 | 17 | 2.1 | 1.03
P003 | Electronics | SUP013 | 2025-03 | 2024-10-05 | 325032.81 | 164329 | -160703.81 | 160703.81 | 1 | 2025-03-28 | 1 |  |  |  |  | 174 | Low | 32616.02 | 0.103 | 0 | 131712.98 | 13 | 1.13 | 1.73
P003 | Electronics | SUP013 | 2025-03 | 2024-12-03 | 282342.04 | 164329 | -118013.04 | 118013.04 | 1 | 2025-03-28 | 2 | 325032.81 | -42690.77 | DOWN | 0.1512 | 115 | Low | 64489.7 | 0.235 | 0 | 99839.3 | 13 | 1.13 | 1.73
P003 | Electronics | SUP013 | 2025-03 | 2025-03-14 | 253676.64 | 164329 | -89347.64 | 89347.64 | 1 | 2025-03-28 | 3 | 282342.04 | -28665.4 | DOWN | 0.113 | 14 | Medium | 114770.57 | 0.461 | 6 | 49558.43 | 13 | 1.13 | 1.73
P003 | Materials | SUP013 | 2025-04 | 2024-11-13 | 3766064.95 | 2163445 | -1602619.95 | 1602619.95 | 1 | 2025-04-28 | 1 |  |  |  |  | 166 | Low | 433924.9 | 0.12 | 1 | 1729520.1 | 13 | 1.21 | 1.27
P003 | Materials | SUP013 | 2025-04 | 2024-12-18 | 3375548.24 | 2163445 | -1212103.24 | 1212103.24 | 1 | 2025-04-28 | 2 | 3766064.95 | -390516.71 | DOWN | 0.1157 | 131 | Low | 660268.29 | 0.197 | 1 | 1503176.71 | 13 | 1.21 | 1.27
P003 | Materials | SUP013 | 2025-04 | 2025-02-10 | 3058610.73 | 2163445 | -895165.73 | 895165.73 | 1 | 2025-04-28 | 3 | 3375548.24 | -316937.51 | DOWN | 0.1036 | 77 | Low | 1037040.28 | 0.317 | 4 | 1126404.72 | 13 | 1.21 | 1.27
P003 | Materials | SUP013 | 2025-04 | 2025-02-21 | 2807968.86 | 2163445 | -644523.86 | 644523.86 | 1 | 2025-04-28 | 4 | 3058610.73 | -250641.87 | DOWN | 0.0893 | 66 | Low | 1011651.63 | 0.341 | 5 | 1151793.37 | 13 | 1.21 | 1.27
P003 | Materials | SUP013 | 2025-04 | 2025-03-18 | 2639356.52 | 2163445 | -475911.52 | 475911.52 | 1 | 2025-04-28 | 5 | 2807968.86 | -168612.34 | DOWN | 0.0639 | 41 | Low | 1124315.08 | 0.397 | 5 | 1039129.92 | 13 | 1.21 | 1.27
P003 | Materials | SUP013 | 2025-04 | 2025-03-29 | 2536708.46 | 2163445 | -373263.46 | 373263.46 | 0 | 2025-04-28 | 6 | 2639356.52 | -102648.06 | DOWN | 0.0405 | 30 | Low | 1113372.48 | 0.421 | 9 | 1050072.52 | 13 | 1.21 | 1.27
P003 | Materials | SUP013 | 2025-05 | 2024-12-30 | 3311123.35 | 2081718 | -1229405.35 | 1229405.35 | 1 | 2025-05-28 | 1 |  |  |  |  | 149 | Low | 546961.48 | 0.155 | 0 | 1534756.52 | 14 | 1.36 | 1.73
P003 | Materials | SUP013 | 2025-05 | 2025-03-24 | 3026291.96 | 2081718 | -944573.96 | 944573.96 | 1 | 2025-05-28 | 2 | 3311123.35 | -284831.39 | DOWN | 0.0941 | 65 | Low | 1009834.69 | 0.338 | 0 | 1071883.31 | 14 | 1.36 | 1.73
P003 | Materials | SUP013 | 2025-05 | 2025-05-01 | 2809024.25 | 2081718 | -727306.25 | 727306.25 | 1 | 2025-05-28 | 3 | 3026291.96 | -217267.71 | DOWN | 0.0773 | 27 | Low | 1240551.67 | 0.42 | 2 | 841166.33 | 14 | 1.36 | 1.73
P003 | Materials | SUP013 | 2025-06 | 2025-02-15 | 1555679.74 | 811587 | -744092.74 | 744092.74 | 1 | 2025-06-28 | 1 |  |  |  |  | 133 | Low | 284907.27 | 0.187 | 0 | 526679.73 | 22 | 1.47 | 1.51
P003 | Materials | SUP013 | 2025-06 | 2025-02-21 | 1367688.32 | 811587 | -556101.32 | 556101.32 | 1 | 2025-06-28 | 2 | 1555679.74 | -187991.42 | DOWN | 0.1375 | 127 | Low | 275724.88 | 0.2 | 0 | 535862.12 | 22 | 1.47 | 1.51
P003 | Materials | SUP013 | 2025-06 | 2025-02-28 | 1230918.75 | 811587 | -419331.75 | 419331.75 | 1 | 2025-06-28 | 3 | 1367688.32 | -136769.57 | DOWN | 0.1111 | 120 | Low | 256899.65 | 0.215 | 5 | 554687.35 | 22 | 1.47 | 1.51
P003 | Materials | SUP013 | 2025-06 | 2025-05-20 | 1121470.71 | 811587 | -309883.71 | 309883.71 | 1 | 2025-06-28 | 4 | 1230918.75 | -109448.04 | DOWN | 0.0976 | 39 | Low | 461126.58 | 0.389 | 2 | 350460.42 | 22 | 1.47 | 1.51
P003 | Software | SUP013 | 2025-07 | 2025-02-24 | 4865360.05 | 2379541 | -2485819.05 | 2485819.05 | 1 | 2025-07-28 | 1 |  |  |  |  | 154 | Low | 774979.64 | 0.15 | 0 | 1604561.36 | 13 | 0.8 | 1.22
P003 | Software | SUP013 | 2025-07 | 2025-02-26 | 4230998.34 | 2379541 | -1851457.34 | 1851457.34 | 1 | 2025-07-28 | 2 | 4865360.05 | -634361.71 | DOWN | 0.1499 | 152 | Low | 663061.91 | 0.155 | 3 | 1716479.09 | 13 | 0.8 | 1.22
P003 | Software | SUP013 | 2025-07 | 2025-04-06 | 3699217.09 | 2379541 | -1319676.09 | 1319676.09 | 1 | 2025-07-28 | 3 | 4230998.34 | -531781.25 | DOWN | 0.1438 | 113 | Low | 886222.94 | 0.243 | 0 | 1493318.06 | 13 | 0.8 | 1.22
P003 | Software | SUP013 | 2025-07 | 2025-06-12 | 3379484.9 | 2379541 | -999943.9 | 999943.9 | 1 | 2025-07-28 | 4 | 3699217.09 | -319732.19 | DOWN | 0.0946 | 46 | Low | 1338964.63 | 0.395 | 4 | 1040576.37 | 13 | 0.8 | 1.22
P003 | Software | SUP013 | 2025-07 | 2025-07-05 | 3082179.12 | 2379541 | -702638.12 | 702638.12 | 1 | 2025-07-28 | 5 | 3379484.9 | -297305.78 | DOWN | 0.0965 | 23 | Low | 1415866.21 | 0.448 | 0 | 963674.79 | 13 | 0.8 | 1.22
P003 | Electronics | SUP013 | 2025-08 | 2025-03-10 | 3390984.81 | 1718323 | -1672661.81 | 1672661.81 | 1 | 2025-08-28 | 1 |  |  |  |  | 171 | Low | 376435.6 | 0.107 | 3 | 1341887.4 | 7 | 1.37 | 1.47
P003 | Electronics | SUP013 | 2025-08 | 2025-04-26 | 2987972.9 | 1718323 | -1269649.9 | 1269649.9 | 1 | 2025-08-28 | 2 | 3390984.81 | -403011.91 | DOWN | 0.1349 | 124 | Low | 655396.81 | 0.209 | 2 | 1062926.19 | 7 | 1.37 | 1.47
P003 | Electronics | SUP013 | 2025-08 | 2025-05-21 | 2643038.25 | 1718323 | -924715.25 | 924715.25 | 1 | 2025-08-28 | 3 | 2987972.9 | -344934.65 | DOWN | 0.1305 | 99 | Low | 687603.66 | 0.263 | 0 | 1030719.34 | 7 | 1.37 | 1.47
P003 | Electronics | SUP013 | 2025-08 | 2025-05-24 | 2440597.73 | 1718323 | -722274.73 | 722274.73 | 1 | 2025-08-28 | 4 | 2643038.25 | -202440.52 | DOWN | 0.0829 | 96 | Low | 646241.94 | 0.27 | 0 | 1072081.06 | 7 | 1.37 | 1.47
P003 | Electronics | SUP013 | 2025-08 | 2025-06-01 | 2276828.37 | 1718323 | -558505.37 | 558505.37 | 1 | 2025-08-28 | 5 | 2440597.73 | -163769.36 | DOWN | 0.0719 | 88 | Low | 673317.27 | 0.287 | 2 | 1045005.73 | 7 | 1.37 | 1.47
P003 | Electronics | SUP013 | 2025-08 | 2025-08-17 | 2107692.25 | 1718323 | -389369.25 | 389369.25 | 1 | 2025-08-28 | 6 | 2276828.37 | -169136.12 | DOWN | 0.0802 | 11 | Medium | 1029243.92 | 0.455 | 2 | 689079.08 | 7 | 1.37 | 1.47
P003 | Electronics | SUP013 | 2025-09 | 2025-05-25 | 1356343.21 | 699577 | -656766.21 | 656766.21 | 1 | 2025-09-28 | 1 |  |  |  |  | 126 | Low | 279900.62 | 0.214 | 2 | 419676.38 | 10 | 0.71 | 1.27
P003 | Electronics | SUP013 | 2025-09 | 2025-07-16 | 1181773.19 | 699577 | -482196.19 | 482196.19 | 1 | 2025-09-28 | 2 | 1356343.21 | -174570.02 | DOWN | 0.1477 | 74 | Low | 419971.73 | 0.332 | 5 | 279605.27 | 10 | 0.71 | 1.27
P003 | Electronics | SUP013 | 2025-09 | 2025-09-09 | 1051957.82 | 699577 | -352380.82 | 352380.82 | 1 | 2025-09-28 | 3 | 1181773.19 | -129815.37 | DOWN | 0.1234 | 19 | Low | 494589.24 | 0.457 | 7 | 204987.76 | 10 | 0.71 | 1.27
P003 | Electronics | SUP013 | 2025-10 | 2025-06-19 | 2823831.84 | 1404502 | -1419329.84 | 1419329.84 | 1 | 2025-10-28 | 1 |  |  |  |  | 131 | Low | 595975.61 | 0.202 | 1 | 808526.39 | 19 | 0.95 | 0.98
P003 | Electronics | SUP013 | 2025-10 | 2025-07-14 | 2470973.65 | 1404502 | -1066471.65 | 1066471.65 | 1 | 2025-10-28 | 2 | 2823831.84 | -352858.19 | DOWN | 0.1428 | 106 | Low | 664230.29 | 0.259 | 0 | 740271.71 | 19 | 0.95 | 0.98
P003 | Electronics | SUP013 | 2025-10 | 2025-07-29 | 2221562.51 | 1404502 | -817060.51 | 817060.51 | 1 | 2025-10-28 | 3 | 2470973.65 | -249411.14 | DOWN | 0.1123 | 91 | Low | 675938.96 | 0.293 | 0 | 728563.04 | 19 | 0.95 | 0.98
P003 | Electronics | SUP013 | 2025-10 | 2025-08-14 | 2020125.11 | 1404502 | -615623.11 | 615623.11 | 1 | 2025-10-28 | 4 | 2221562.51 | -201437.4 | DOWN | 0.0997 | 75 | Low | 670973.45 | 0.33 | 1 | 733528.55 | 19 | 0.95 | 0.98
P003 | Electronics | SUP013 | 2025-10 | 2025-08-29 | 1871309.42 | 1404502 | -466807.42 | 466807.42 | 1 | 2025-10-28 | 5 | 2020125.11 | -148815.69 | DOWN | 0.0795 | 60 | Low | 662434.17 | 0.364 | 5 | 742067.83 | 19 | 0.95 | 0.98
P003 | Electronics | SUP013 | 2025-10 | 2025-10-09 | 1759598.65 | 1404502 | -355096.65 | 355096.65 | 1 | 2025-10-28 | 6 | 1871309.42 | -111710.77 | DOWN | 0.0635 | 19 | Medium | 770746.85 | 0.457 | 3 | 633755.15 | 19 | 0.95 | 0.98
P003 | Software | SUP013 | 2025-11 | 2025-07-15 | 1267625.15 | 551481 | -716144.15 | 716144.15 | 1 | 2025-11-28 | 1 |  |  |  |  | 136 | Low | 204726.01 | 0.173 | 0 | 346754.99 | 11 | 1.85 | 1.52
P003 | Software | SUP013 | 2025-11 | 2025-08-28 | 1081990.63 | 551481 | -530509.63 | 530509.63 | 1 | 2025-11-28 | 2 | 1267625.15 | -185634.52 | DOWN | 0.1716 | 92 | Low | 281858.13 | 0.264 | 4 | 269622.87 | 11 | 1.85 | 1.52
P003 | Software | SUP013 | 2025-11 | 2025-09-14 | 966307.71 | 551481 | -414826.71 | 414826.71 | 1 | 2025-11-28 | 3 | 1081990.63 | -115682.92 | DOWN | 0.1197 | 75 | Low | 267818.47 | 0.299 | 0 | 283662.53 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP013 | 2025-12 | 2025-07-05 | 3308887.56 | 2309164 | -999723.56 | 999723.56 | 1 | 2025-12-28 | 1 |  |  |  |  | 176 | Low | 304510.31 | 0.099 | 2 | 2004653.69 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP013 | 2025-12 | 2025-08-30 | 3044924.41 | 2309164 | -735760.41 | 735760.41 | 1 | 2025-12-28 | 2 | 3308887.56 | -263963.15 | DOWN | 0.0867 | 120 | Low | 703183.11 | 0.225 | 2 | 1605980.89 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP013 | 2025-12 | 2025-09-16 | 2856795.88 | 2309164 | -547631.88 | 547631.88 | 1 | 2025-12-28 | 3 | 3044924.41 | -188128.53 | DOWN | 0.0659 | 103 | Low | 707611.78 | 0.263 | 0 | 1601552.22 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP013 | 2025-12 | 2025-10-12 | 2730122.91 | 2309164 | -420958.91 | 420958.91 | 1 | 2025-12-28 | 4 | 2856795.88 | -126672.97 | DOWN | 0.0464 | 77 | Low | 820624.52 | 0.322 | 0 | 1488539.48 | 10 | 1.08 | 1.22
P003 | Software | SUP045 | 2025-01 | 2024-08-02 | 2733972.36 | 1825826 | -908146.36 | 908146.36 | 1 | 2025-01-28 | 1 |  |  |  |  | 179 | Low | 359759.72 | 0.141 | 0 | 1466066.28 | 17 | 1.86 | 1.34
P003 | Software | SUP045 | 2025-01 | 2024-09-05 | 2242016.87 | 1825826 | -416190.87 | 416190.87 | 1 | 2025-01-28 | 2 | 2733972.36 | -491955.49 | DOWN | 0.2194 | 145 | Low | 547069.45 | 0.241 | 0 | 1278756.55 | 17 | 1.86 | 1.34
P003 | Software | SUP045 | 2025-01 | 2024-09-21 | 2025783.41 | 1825826 | -199957.41 | 199957.41 | 0 | 2025-01-28 | 3 | 2242016.87 | -216233.46 | DOWN | 0.1067 | 129 | Low | 625795.76 | 0.292 | 0 | 1200030.24 | 17 | 1.86 | 1.34
P003 | Software | SUP045 | 2025-01 | 2024-09-29 | 1963732.84 | 1825826 | -137906.84 | 137906.84 | 0 | 2025-01-28 | 4 | 2025783.41 | -62050.57 | DOWN | 0.0316 | 121 | Low | 622577.27 | 0.318 | 6 | 1203248.73 | 17 | 1.86 | 1.34
P003 | Software | SUP045 | 2025-01 | 2024-12-21 | 1885202.21 | 1825826 | -59376.21 | 59376.21 | 0 | 2025-01-28 | 5 | 1963732.84 | -78530.63 | DOWN | 0.0417 | 38 | Medium | 1031466.07 | 0.585 | 0 | 794359.93 | 17 | 1.86 | 1.34
P003 | Logistics | SUP045 | 2025-02 | 2024-09-08 | 4993402.37 | 2491871 | -2501531.37 | 2501531.37 | 1 | 2025-02-28 | 1 |  |  |  |  | 173 | Low | 728696.99 | 0.147 | 1 | 1763174.01 | 17 | 2.1 | 1.03
P003 | Logistics | SUP045 | 2025-02 | 2024-10-10 | 3493865.55 | 2491871 | -1001994.55 | 1001994.55 | 1 | 2025-02-28 | 2 | 4993402.37 | -1499536.82 | DOWN | 0.4292 | 141 | Low | 881839.73 | 0.247 | 3 | 1610031.27 | 17 | 2.1 | 1.03
P003 | Logistics | SUP045 | 2025-02 | 2024-11-12 | 2928091.42 | 2491871 | -436220.42 | 436220.42 | 0 | 2025-02-28 | 3 | 3493865.55 | -565774.13 | DOWN | 0.1932 | 108 | Low | 1024758.1 | 0.351 | 1 | 1467112.9 | 17 | 2.1 | 1.03
P003 | Logistics | SUP045 | 2025-02 | 2024-11-24 | 2761647.64 | 2491871 | -269776.64 | 269776.64 | 0 | 2025-02-28 | 4 | 2928091.42 | -166443.78 | DOWN | 0.0603 | 96 | Low | 1136435.29 | 0.388 | 7 | 1355435.71 | 17 | 2.1 | 1.03
P003 | Logistics | SUP045 | 2025-02 | 2024-11-29 | 2661292.28 | 2491871 | -169421.28 | 169421.28 | 0 | 2025-02-28 | 5 | 2761647.64 | -100355.36 | DOWN | 0.0377 | 91 | Low | 993215.27 | 0.404 | 5 | 1498655.73 | 17 | 2.1 | 1.03
P003 | Electronics | SUP045 | 2025-03 | 2024-10-17 | 1945525.58 | 1343918 | -601607.58 | 601607.58 | 1 | 2025-03-28 | 1 |  |  |  |  | 162 | Low | 391945.29 | 0.202 | 0 | 951972.71 | 13 | 1.13 | 1.73
P003 | Electronics | SUP045 | 2025-03 | 2024-12-12 | 1609854.7 | 1343918 | -265936.7 | 265936.7 | 1 | 2025-03-28 | 2 | 1945525.58 | -335670.88 | DOWN | 0.2085 | 106 | Low | 627922.4 | 0.398 | 2 | 715995.6 | 13 | 1.13 | 1.73
P003 | Electronics | SUP045 | 2025-03 | 2025-03-02 | 1469256.6 | 1343918 | -125338.6 | 125338.6 | 0 | 2025-03-28 | 3 | 1609854.7 | -140598.1 | DOWN | 0.0957 | 26 | Medium | 1014878.39 | 0.677 | 3 | 329039.61 | 13 | 1.13 | 1.73
P003 | Electronics | SUP045 | 2025-03 | 2025-03-04 | 1397221.55 | 1343918 | -53303.55 | 53303.55 | 0 | 2025-03-28 | 4 | 1469256.6 | -72035.05 | DOWN | 0.0516 | 24 | High | 1000663.96 | 0.684 | 5 | 343254.04 | 13 | 1.13 | 1.73
P003 | Logistics | SUP045 | 2025-04 | 2024-12-01 | 320525.03 | 199541 | -120984.03 | 120984.03 | 1 | 2025-04-28 | 1 |  |  |  |  | 148 | Low | 81878.11 | 0.249 | 2 | 117662.89 | 13 | 1.21 | 1.27
P003 | Logistics | SUP045 | 2025-04 | 2025-02-08 | 257685.02 | 199541 | -58144.02 | 58144.02 | 1 | 2025-04-28 | 2 | 320525.03 | -62840.01 | DOWN | 0.2439 | 79 | Low | 129153.69 | 0.488 | 3 | 70387.31 | 13 | 1.21 | 1.27
P003 | Logistics | SUP045 | 2025-04 | 2025-03-16 | 224136.96 | 199541 | -24595.96 | 24595.96 | 0 | 2025-04-28 | 3 | 257685.02 | -33548.06 | DOWN | 0.1497 | 43 | Low | 126904.73 | 0.612 | 8 | 72636.27 | 13 | 1.21 | 1.27
P003 | Electronics | SUP045 | 2025-05 | 2025-02-14 | 1746981.99 | 1280442 | -466539.99 | 466539.99 | 1 | 2025-05-28 | 1 |  |  |  |  | 103 | Low | 714261.46 | 0.398 | 5 | 566180.54 | 14 | 1.36 | 1.73
P003 | Electronics | SUP045 | 2025-05 | 2025-02-19 | 1498222.48 | 1280442 | -217780.48 | 217780.48 | 0 | 2025-05-28 | 2 | 1746981.99 | -248759.51 | DOWN | 0.166 | 98 | Low | 580708.13 | 0.415 | 2 | 699733.87 | 14 | 1.36 | 1.73
P003 | Electronics | SUP045 | 2025-05 | 2025-03-27 | 1382595.59 | 1280442 | -102153.59 | 102153.59 | 0 | 2025-05-28 | 3 | 1498222.48 | -115626.89 | DOWN | 0.0836 | 62 | Low | 723117.98 | 0.537 | 2 | 557324.02 | 14 | 1.36 | 1.73
P003 | Logistics | SUP045 | 2025-06 | 2025-01-29 | 3618272.15 | 2125807 | -1492465.15 | 1492465.15 | 1 | 2025-06-28 | 1 |  |  |  |  | 150 | Low | 865301.19 | 0.235 | 4 | 1260505.81 | 22 | 1.47 | 1.51
P003 | Logistics | SUP045 | 2025-06 | 2025-02-01 | 2883278.79 | 2125807 | -757471.79 | 757471.79 | 1 | 2025-06-28 | 2 | 3618272.15 | -734993.36 | DOWN | 0.2549 | 147 | Low | 750477.83 | 0.245 | 0 | 1375329.17 | 22 | 1.47 | 1.51
P003 | Logistics | SUP045 | 2025-06 | 2025-05-02 | 2445391.03 | 2125807 | -319584.03 | 319584.03 | 0 | 2025-06-28 | 3 | 2883278.79 | -437887.76 | DOWN | 0.1791 | 57 | Low | 1302374.98 | 0.547 | 3 | 823432.02 | 22 | 1.47 | 1.51
P003 | Logistics | SUP045 | 2025-06 | 2025-05-19 | 2231157.7 | 2125807 | -105350.7 | 105350.7 | 0 | 2025-06-28 | 4 | 2445391.03 | -214233.33 | DOWN | 0.096 | 40 | Medium | 1357067.9 | 0.604 | 2 | 768739.1 | 22 | 1.47 | 1.51
P003 | Logistics | SUP045 | 2025-06 | 2025-05-30 | 2173659.12 | 2125807 | -47852.12 | 47852.12 | 0 | 2025-06-28 | 5 | 2231157.7 | -57498.58 | DOWN | 0.0265 | 29 | Medium | 1330866.38 | 0.641 | 3 | 794940.62 | 22 | 1.47 | 1.51
P003 | Services | SUP045 | 2025-07 | 2025-02-03 | 1929614.52 | 1346464 | -583150.52 | 583150.52 | 1 | 2025-07-28 | 1 |  |  |  |  | 175 | Low | 329353.96 | 0.16 | 2 | 1017110.04 | 13 | 0.8 | 1.22
P003 | Services | SUP045 | 2025-07 | 2025-05-25 | 1624803.8 | 1346464 | -278339.8 | 278339.8 | 1 | 2025-07-28 | 2 | 1929614.52 | -304810.72 | DOWN | 0.1876 | 64 | Low | 938955.99 | 0.553 | 1 | 407508.01 | 13 | 0.8 | 1.22
P003 | Services | SUP045 | 2025-07 | 2025-06-13 | 1483442.78 | 1346464 | -136978.78 | 136978.78 | 0 | 2025-07-28 | 3 | 1624803.8 | -141361.02 | DOWN | 0.0953 | 45 | Medium | 902569.22 | 0.62 | 7 | 443894.78 | 13 | 0.8 | 1.22
P003 | Services | SUP045 | 2025-07 | 2025-06-18 | 1422372.98 | 1346464 | -75908.98 | 75908.98 | 0 | 2025-07-28 | 4 | 1483442.78 | -61069.8 | DOWN | 0.0429 | 40 | Medium | 835542.53 | 0.638 | 6 | 510921.47 | 13 | 0.8 | 1.22
P003 | Services | SUP045 | 2025-07 | 2025-07-01 | 1375363.36 | 1346464 | -28899.36 | 28899.36 | 0 | 2025-07-28 | 5 | 1422372.98 | -47009.62 | DOWN | 0.0342 | 27 | High | 927699.62 | 0.684 | 7 | 418764.38 | 13 | 0.8 | 1.22
P003 | Logistics | SUP045 | 2025-08 | 2025-04-19 | 3359267.57 | 1950066 | -1409201.57 | 1409201.57 | 1 | 2025-08-28 | 1 |  |  |  |  | 131 | Low | 1045366.05 | 0.302 | 0 | 904699.95 | 7 | 1.37 | 1.47
P003 | Logistics | SUP045 | 2025-08 | 2025-05-19 | 2660964.31 | 1950066 | -710898.31 | 710898.31 | 1 | 2025-08-28 | 2 | 3359267.57 | -698303.26 | DOWN | 0.2624 | 101 | Low | 1159323.24 | 0.404 | 7 | 790742.76 | 7 | 1.37 | 1.47
P003 | Logistics | SUP045 | 2025-08 | 2025-06-23 | 2298697.52 | 1950066 | -348631.52 | 348631.52 | 1 | 2025-08-28 | 3 | 2660964.31 | -362266.79 | DOWN | 0.1576 | 66 | Low | 1214695.68 | 0.523 | 0 | 735370.32 | 7 | 1.37 | 1.47
P003 | Logistics | SUP045 | 2025-08 | 2025-06-23 | 2116120.86 | 1950066 | -166054.86 | 166054.86 | 0 | 2025-08-28 | 4 | 2298697.52 | -182576.66 | DOWN | 0.0863 | 66 | Low | 1130152.06 | 0.523 | 8 | 819913.94 | 7 | 1.37 | 1.47
P003 | Logistics | SUP045 | 2025-08 | 2025-07-27 | 2016076.84 | 1950066 | -66010.84 | 66010.84 | 0 | 2025-08-28 | 5 | 2116120.86 | -100044.02 | DOWN | 0.0496 | 32 | Medium | 1276276.12 | 0.638 | 5 | 673789.88 | 7 | 1.37 | 1.47
P003 | Materials | SUP045 | 2025-09 | 2025-07-17 | 2961450.87 | 2104773 | -856677.87 | 856677.87 | 1 | 2025-09-28 | 1 |  |  |  |  | 73 | Low | 1475048.58 | 0.521 | 4 | 629724.42 | 10 | 0.71 | 1.27
P003 | Materials | SUP045 | 2025-09 | 2025-07-18 | 2472746.44 | 2104773 | -367973.44 | 367973.44 | 0 | 2025-09-28 | 2 | 2961450.87 | -488704.43 | DOWN | 0.1976 | 72 | Low | 1317767.97 | 0.525 | 4 | 787005.03 | 10 | 0.71 | 1.27
P003 | Materials | SUP045 | 2025-09 | 2025-08-29 | 2289884.23 | 2104773 | -185111.23 | 185111.23 | 0 | 2025-09-28 | 3 | 2472746.44 | -182862.21 | DOWN | 0.0799 | 30 | Medium | 1594469.13 | 0.674 | 6 | 510303.87 | 10 | 0.71 | 1.27
P003 | Materials | SUP045 | 2025-09 | 2025-08-29 | 2184221.39 | 2104773 | -79448.39 | 79448.39 | 0 | 2025-09-28 | 4 | 2289884.23 | -105662.84 | DOWN | 0.0484 | 30 | High | 1380461.47 | 0.674 | 8 | 724311.53 | 10 | 0.71 | 1.27
P003 | Electronics | SUP045 | 2025-10 | 2025-05-22 | 2378433.01 | 1871908 | -506525.01 | 506525.01 | 1 | 2025-10-28 | 1 |  |  |  |  | 159 | Low | 527914.66 | 0.216 | 0 | 1343993.34 | 19 | 0.95 | 0.98
P003 | Electronics | SUP045 | 2025-10 | 2025-06-30 | 2099497.93 | 1871908 | -227589.93 | 227589.93 | 0 | 2025-10-28 | 2 | 2378433.01 | -278935.08 | DOWN | 0.1329 | 120 | Low | 774104.08 | 0.355 | 4 | 1097803.92 | 19 | 0.95 | 0.98
P003 | Electronics | SUP045 | 2025-10 | 2025-08-05 | 1964150.76 | 1871908 | -92242.76 | 92242.76 | 0 | 2025-10-28 | 3 | 2099497.93 | -135347.17 | DOWN | 0.0689 | 84 | Low | 918205.24 | 0.482 | 2 | 953702.76 | 19 | 0.95 | 0.98
P003 | Electronics | SUP045 | 2025-10 | 2025-08-13 | 1935085.15 | 1871908 | -63177.15 | 63177.15 | 0 | 2025-10-28 | 4 | 1964150.76 | -29065.61 | DOWN | 0.015 | 76 | Low | 1042356.86 | 0.511 | 5 | 829551.14 | 19 | 0.95 | 0.98
P003 | Electronics | SUP045 | 2025-10 | 2025-09-29 | 1888162.16 | 1871908 | -16254.16 | 16254.16 | 0 | 2025-10-28 | 5 | 1935085.15 | -46922.99 | DOWN | 0.0249 | 29 | High | 1178592.9 | 0.677 | 8 | 693315.1 | 19 | 0.95 | 0.98
P003 | Software | SUP045 | 2025-11 | 2025-08-13 | 2073577.09 | 1349154 | -724423.09 | 724423.09 | 1 | 2025-11-28 | 1 |  |  |  |  | 107 | Low | 808110.2 | 0.364 | 5 | 541043.8 | 11 | 1.85 | 1.52
P003 | Software | SUP045 | 2025-11 | 2025-09-05 | 1681015.76 | 1349154 | -331861.76 | 331861.76 | 1 | 2025-11-28 | 2 | 2073577.09 | -392561.33 | DOWN | 0.2335 | 84 | Low | 691029.61 | 0.438 | 5 | 658124.39 | 11 | 1.85 | 1.52
P003 | Software | SUP045 | 2025-11 | 2025-09-10 | 1526028.34 | 1349154 | -176874.34 | 176874.34 | 0 | 2025-11-28 | 3 | 1681015.76 | -154987.42 | DOWN | 0.1016 | 79 | Low | 661055.03 | 0.454 | 4 | 688098.97 | 11 | 1.85 | 1.52
P003 | Software | SUP045 | 2025-11 | 2025-11-10 | 1449882.57 | 1349154 | -100728.57 | 100728.57 | 0 | 2025-11-28 | 4 | 1526028.34 | -76145.77 | DOWN | 0.0525 | 18 | Medium | 974482.39 | 0.65 | 4 | 374671.61 | 11 | 1.85 | 1.52
P003 | Software | SUP045 | 2025-11 | 2025-11-12 | 1372062.87 | 1349154 | -22908.87 | 22908.87 | 0 | 2025-11-28 | 5 | 1449882.57 | -77819.7 | DOWN | 0.0567 | 16 | Medium | 931000.42 | 0.656 | 2 | 418153.58 | 11 | 1.85 | 1.52
P003 | Logistics | SUP045 | 2025-12 | 2025-09-10 | 3511815.52 | 2142397 | -1369418.52 | 1369418.52 | 1 | 2025-12-28 | 1 |  |  |  |  | 109 | Low | 1376172.98 | 0.39 | 5 | 766224.02 | 10 | 1.08 | 1.22
P003 | Logistics | SUP045 | 2025-12 | 2025-10-01 | 2696219.75 | 2142397 | -553822.75 | 553822.75 | 1 | 2025-12-28 | 2 | 3511815.52 | -815595.77 | DOWN | 0.3025 | 88 | Low | 1339691.78 | 0.464 | 3 | 802705.22 | 10 | 1.08 | 1.22
P003 | Logistics | SUP045 | 2025-12 | 2025-10-04 | 2402228.01 | 2142397 | -259831.01 | 259831.01 | 0 | 2025-12-28 | 3 | 2696219.75 | -293991.74 | DOWN | 0.1224 | 85 | Low | 1202349.53 | 0.474 | 1 | 940047.47 | 10 | 1.08 | 1.22
P003 | Logistics | SUP045 | 2025-12 | 2025-10-08 | 2297526.57 | 2142397 | -155129.57 | 155129.57 | 0 | 2025-12-28 | 4 | 2402228.01 | -104701.44 | DOWN | 0.0456 | 81 | Low | 1126076.32 | 0.488 | 5 | 1016320.68 | 10 | 1.08 | 1.22
P003 | Logistics | SUP045 | 2025-12 | 2025-10-08 | 2255153.96 | 2142397 | -112756.96 | 112756.96 | 0 | 2025-12-28 | 5 | 2297526.57 | -42372.61 | DOWN | 0.0188 | 81 | Low | 1055189.53 | 0.488 | 5 | 1087207.47 | 10 | 1.08 | 1.22
P003 | Logistics | SUP045 | 2025-12 | 2025-11-19 | 2160261.66 | 2142397 | -17864.66 | 17864.66 | 0 | 2025-12-28 | 6 | 2255153.96 | -94892.3 | DOWN | 0.0439 | 39 | Medium | 1409214.43 | 0.636 | 5 | 733182.57 | 10 | 1.08 | 1.22
P003 | Electronics | SUP034 | 2025-01 | 2024-08-05 | 2547602.62 | 1597979 | -949623.62 | 949623.62 | 1 | 2025-01-28 | 1 |  |  |  |  | 176 | Low | 369862.72 | 0.141 | 0 | 1228116.28 | 17 | 1.86 | 1.34
P003 | Electronics | SUP034 | 2025-01 | 2024-09-22 | 2079112.84 | 1597979 | -481133.84 | 481133.84 | 1 | 2025-01-28 | 2 | 2547602.62 | -468489.78 | DOWN | 0.2253 | 128 | Low | 589296.17 | 0.296 | 0 | 1008682.83 | 17 | 1.86 | 1.34
P003 | Electronics | SUP034 | 2025-01 | 2024-10-08 | 1855724.71 | 1597979 | -257745.71 | 257745.71 | 0 | 2025-01-28 | 3 | 2079112.84 | -223388.13 | DOWN | 0.1204 | 112 | Low | 610803.8 | 0.347 | 1 | 987175.2 | 17 | 1.86 | 1.34
P003 | Electronics | SUP034 | 2025-01 | 2024-11-15 | 1747877.35 | 1597979 | -149898.35 | 149898.35 | 0 | 2025-01-28 | 4 | 1855724.71 | -107847.36 | DOWN | 0.0617 | 74 | Low | 770168.71 | 0.469 | 2 | 827810.29 | 17 | 1.86 | 1.34
P003 | Electronics | SUP034 | 2025-01 | 2025-01-14 | 1657611.63 | 1597979 | -59632.63 | 59632.63 | 0 | 2025-01-28 | 5 | 1747877.35 | -90265.72 | DOWN | 0.0545 | 14 | Medium | 1112675.61 | 0.662 | 4 | 485303.39 | 17 | 1.86 | 1.34
P003 | Electronics | SUP034 | 2025-02 | 2024-09-25 | 2779688.44 | 1772048 | -1007640.44 | 1007640.44 | 1 | 2025-02-28 | 1 |  |  |  |  | 156 | Low | 564661.22 | 0.2 | 2 | 1207386.78 | 17 | 2.1 | 1.03
P003 | Electronics | SUP034 | 2025-02 | 2024-10-02 | 2278073.02 | 1772048 | -506025.02 | 506025.02 | 1 | 2025-02-28 | 2 | 2779688.44 | -501615.42 | DOWN | 0.2202 | 149 | Low | 532244.77 | 0.222 | 4 | 1239803.23 | 17 | 2.1 | 1.03
P003 | Electronics | SUP034 | 2025-02 | 2024-10-06 | 1969670.69 | 1772048 | -197622.69 | 197622.69 | 0 | 2025-02-28 | 3 | 2278073.02 | -308402.33 | DOWN | 0.1566 | 145 | Low | 441301.49 | 0.235 | 0 | 1330746.51 | 17 | 2.1 | 1.03
P003 | Electronics | SUP034 | 2025-02 | 2024-11-10 | 1888782.66 | 1772048 | -116734.66 | 116734.66 | 0 | 2025-02-28 | 4 | 1969670.69 | -80888.03 | DOWN | 0.0428 | 110 | Low | 684015.14 | 0.345 | 0 | 1088032.86 | 17 | 2.1 | 1.03
P003 | Electronics | SUP034 | 2025-02 | 2024-12-31 | 1847699.81 | 1772048 | -75651.81 | 75651.81 | 0 | 2025-02-28 | 5 | 1888782.66 | -41082.85 | DOWN | 0.0222 | 59 | Low | 889840.87 | 0.504 | 6 | 882207.13 | 17 | 2.1 | 1.03
P003 | Electronics | SUP034 | 2025-02 | 2025-01-27 | 1797329.17 | 1772048 | -25281.17 | 25281.17 | 0 | 2025-02-28 | 6 | 1847699.81 | -50370.64 | DOWN | 0.028 | 32 | Low | 1053911.47 | 0.589 | 7 | 718136.53 | 17 | 2.1 | 1.03
P003 | Logistics | SUP034 | 2025-03 | 2024-12-15 | 5069782.46 | 2918053 | -2151729.46 | 2151729.46 | 1 | 2025-03-28 | 1 |  |  |  |  | 103 | Low | 2086408.2 | 0.408 | 2 | 831644.8 | 13 | 1.13 | 1.73
P003 | Logistics | SUP034 | 2025-03 | 2025-03-04 | 3942851.27 | 2918053 | -1024798.27 | 1024798.27 | 1 | 2025-03-28 | 2 | 5069782.46 | -1126931.19 | DOWN | 0.2858 | 24 | Low | 2644466.31 | 0.684 | 9 | 273586.69 | 13 | 1.13 | 1.73
P003 | Logistics | SUP034 | 2025-03 | 2025-03-16 | 3452180.15 | 2918053 | -534127.15 | 534127.15 | 1 | 2025-03-28 | 3 | 3942851.27 | -490671.12 | DOWN | 0.1421 | 12 | Low | 2597244.91 | 0.726 | 4 | 320808.09 | 13 | 1.13 | 1.73
P003 | Services | SUP034 | 2025-04 | 2024-11-02 | 707227.72 | 439084 | -268143.72 | 268143.72 | 1 | 2025-04-28 | 1 |  |  |  |  | 177 | Low | 103031.58 | 0.152 | 1 | 336052.42 | 13 | 1.21 | 1.27
P003 | Services | SUP034 | 2025-04 | 2025-01-23 | 569049.66 | 439084 | -129965.66 | 129965.66 | 1 | 2025-04-28 | 2 | 707227.72 | -138178.06 | DOWN | 0.2428 | 95 | Low | 234217.75 | 0.432 | 0 | 204866.25 | 13 | 1.21 | 1.27
P003 | Services | SUP034 | 2025-04 | 2025-02-01 | 495520.56 | 439084 | -56436.56 | 56436.56 | 0 | 2025-04-28 | 3 | 569049.66 | -73529.1 | DOWN | 0.1484 | 86 | Low | 212570.47 | 0.463 | 5 | 226513.53 | 13 | 1.21 | 1.27
P003 | Services | SUP034 | 2025-04 | 2025-02-03 | 471385.91 | 439084 | -32301.91 | 32301.91 | 0 | 2025-04-28 | 4 | 495520.56 | -24134.65 | DOWN | 0.0512 | 84 | Low | 214459.97 | 0.47 | 2 | 224624.03 | 13 | 1.21 | 1.27
P003 | Services | SUP034 | 2025-04 | 2025-02-15 | 448886.39 | 439084 | -9802.39 | 9802.39 | 0 | 2025-04-28 | 5 | 471385.91 | -22499.52 | DOWN | 0.0501 | 72 | Low | 246352.25 | 0.512 | 5 | 192731.75 | 13 | 1.21 | 1.27
P003 | Electronics | SUP034 | 2025-05 | 2025-02-09 | 904239.8 | 579991 | -324248.8 | 324248.8 | 1 | 2025-05-28 | 1 |  |  |  |  | 108 | Low | 343298.66 | 0.381 | 5 | 236692.34 | 14 | 1.36 | 1.73
P003 | Electronics | SUP034 | 2025-05 | 2025-02-24 | 730122.45 | 579991 | -150131.45 | 150131.45 | 1 | 2025-05-28 | 2 | 904239.8 | -174117.35 | DOWN | 0.2385 | 93 | Low | 339289.77 | 0.432 | 6 | 240701.23 | 14 | 1.36 | 1.73
P003 | Electronics | SUP034 | 2025-05 | 2025-04-06 | 650248.95 | 579991 | -70257.95 | 70257.95 | 0 | 2025-05-28 | 3 | 730122.45 | -79873.5 | DOWN | 0.1228 | 52 | Low | 379322.12 | 0.571 | 4 | 200668.88 | 14 | 1.36 | 1.73
P003 | Electronics | SUP034 | 2025-05 | 2025-05-09 | 611663.83 | 579991 | -31672.83 | 31672.83 | 0 | 2025-05-28 | 4 | 650248.95 | -38585.12 | DOWN | 0.0631 | 19 | Medium | 429865.21 | 0.683 | 6 | 150125.79 | 14 | 1.36 | 1.73
P003 | Electronics | SUP034 | 2025-05 | 2025-05-09 | 596343.13 | 579991 | -16352.13 | 16352.13 | 0 | 2025-05-28 | 5 | 611663.83 | -15320.7 | DOWN | 0.0257 | 19 | High | 401513.68 | 0.683 | 5 | 178477.32 | 14 | 1.36 | 1.73
P003 | Materials | SUP034 | 2025-06 | 2025-02-22 | 1374275.26 | 904376 | -469899.26 | 469899.26 | 1 | 2025-06-28 | 1 |  |  |  |  | 126 | Low | 402760.69 | 0.315 | 2 | 501615.31 | 22 | 1.47 | 1.51
P003 | Materials | SUP034 | 2025-06 | 2025-02-24 | 1116723.71 | 904376 | -212347.71 | 212347.71 | 1 | 2025-06-28 | 2 | 1374275.26 | -257551.55 | DOWN | 0.2306 | 124 | Low | 346878.16 | 0.322 | 0 | 557497.84 | 22 | 1.47 | 1.51
P003 | Materials | SUP034 | 2025-06 | 2025-03-12 | 1012688.26 | 904376 | -108312.26 | 108312.26 | 0 | 2025-06-28 | 3 | 1116723.71 | -104035.45 | DOWN | 0.1027 | 108 | Low | 388150.48 | 0.376 | 0 | 516225.52 | 22 | 1.47 | 1.51
P003 | Materials | SUP034 | 2025-06 | 2025-05-10 | 951221.55 | 904376 | -46845.55 | 46845.55 | 0 | 2025-06-28 | 4 | 1012688.26 | -61466.71 | DOWN | 0.0646 | 49 | Medium | 541270.7 | 0.574 | 3 | 363105.3 | 22 | 1.47 | 1.51
P003 | Logistics | SUP034 | 2025-07 | 2025-01-31 | 4901386.55 | 3089482 | -1811904.55 | 1811904.55 | 1 | 2025-07-28 | 1 |  |  |  |  | 178 | Low | 746535.81 | 0.156 | 0 | 2342946.19 | 13 | 0.8 | 1.22
P003 | Logistics | SUP034 | 2025-07 | 2025-03-12 | 3878155.03 | 3089482 | -788673.03 | 788673.03 | 1 | 2025-07-28 | 2 | 4901386.55 | -1023231.52 | DOWN | 0.2638 | 138 | Low | 1206953.91 | 0.291 | 5 | 1882528.09 | 13 | 0.8 | 1.22
P003 | Logistics | SUP034 | 2025-07 | 2025-04-08 | 3376929.59 | 3089482 | -287447.59 | 287447.59 | 0 | 2025-07-28 | 3 | 3878155.03 | -501225.44 | DOWN | 0.1484 | 111 | Low | 1359107.49 | 0.386 | 3 | 1730374.51 | 13 | 0.8 | 1.22
P003 | Logistics | SUP034 | 2025-07 | 2025-04-28 | 3255780.11 | 3089482 | -166298.11 | 166298.11 | 0 | 2025-07-28 | 4 | 3376929.59 | -121149.48 | DOWN | 0.0372 | 91 | Low | 1537434.65 | 0.457 | 5 | 1552047.35 | 13 | 0.8 | 1.22
P003 | Logistics | SUP034 | 2025-07 | 2025-05-09 | 3105461.27 | 3089482 | -15979.27 | 15979.27 | 0 | 2025-07-28 | 5 | 3255780.11 | -150318.84 | DOWN | 0.0484 | 80 | Low | 1427274.11 | 0.496 | 5 | 1662207.89 | 13 | 0.8 | 1.22
P003 | Logistics | SUP034 | 2025-07 | 2025-07-13 | 3124995.24 | 3089482 | -35513.24 | 35513.24 | 0 | 2025-07-28 | 6 | 3105461.27 | 19533.97 | UP | 0.0063 | 15 | High | 2117139.15 | 0.727 | 3 | 972342.85 | 13 | 0.8 | 1.22
P003 | Materials | SUP034 | 2025-08 | 2025-03-06 | 2385416.28 | 1808262 | -577154.28 | 577154.28 | 1 | 2025-08-28 | 1 |  |  |  |  | 175 | Low | 381445.12 | 0.153 | 0 | 1426816.88 | 7 | 1.37 | 1.47
P003 | Materials | SUP034 | 2025-08 | 2025-06-17 | 2067749.09 | 1808262 | -259487.09 | 259487.09 | 0 | 2025-08-28 | 2 | 2385416.28 | -317667.19 | DOWN | 0.1536 | 72 | Low | 1092462.89 | 0.502 | 5 | 715799.11 | 7 | 1.37 | 1.47
P003 | Materials | SUP034 | 2025-08 | 2025-06-25 | 1944099.26 | 1808262 | -135837.26 | 135837.26 | 0 | 2025-08-28 | 3 | 2067749.09 | -123649.83 | DOWN | 0.0636 | 64 | Low | 958906.58 | 0.53 | 4 | 849355.42 | 7 | 1.37 | 1.47
P003 | Materials | SUP034 | 2025-08 | 2025-07-08 | 1870935.4 | 1808262 | -62673.4 | 62673.4 | 0 | 2025-08-28 | 4 | 1944099.26 | -73163.86 | DOWN | 0.0391 | 51 | Medium | 1120859.8 | 0.574 | 6 | 687402.2 | 7 | 1.37 | 1.47
P003 | Software | SUP034 | 2025-09 | 2025-05-27 | 1818636.04 | 1201844 | -616792.04 | 616792.04 | 1 | 2025-09-28 | 1 |  |  |  |  | 124 | Low | 602053.85 | 0.34 | 3 | 599790.15 | 10 | 0.71 | 1.27
P003 | Software | SUP034 | 2025-09 | 2025-06-07 | 1476397.54 | 1201844 | -274553.54 | 274553.54 | 1 | 2025-09-28 | 2 | 1818636.04 | -342238.5 | DOWN | 0.2318 | 113 | Low | 578347.58 | 0.379 | 5 | 623496.42 | 10 | 0.71 | 1.27
P003 | Software | SUP034 | 2025-09 | 2025-06-11 | 1304672.21 | 1201844 | -102828.21 | 102828.21 | 0 | 2025-09-28 | 3 | 1476397.54 | -171725.33 | DOWN | 0.1316 | 109 | Low | 473016.42 | 0.394 | 2 | 728827.58 | 10 | 0.71 | 1.27
P003 | Software | SUP034 | 2025-09 | 2025-08-24 | 1226912.53 | 1201844 | -25068.53 | 25068.53 | 0 | 2025-09-28 | 4 | 1304672.21 | -77759.68 | DOWN | 0.0634 | 35 | Medium | 805755.39 | 0.656 | 5 | 396088.61 | 10 | 0.71 | 1.27
P003 | Software | SUP034 | 2025-09 | 2025-09-12 | 1215273.35 | 1201844 | -13429.35 | 13429.35 | 0 | 2025-09-28 | 5 | 1226912.53 | -11639.18 | DOWN | 0.0096 | 16 | High | 830848.6 | 0.723 | 6 | 370995.4 | 10 | 0.71 | 1.27
P003 | Logistics | SUP034 | 2025-10 | 2025-05-15 | 1517182.49 | 942775 | -574407.49 | 574407.49 | 1 | 2025-10-28 | 1 |  |  |  |  | 166 | Low | 309571.2 | 0.191 | 2 | 633203.8 | 19 | 0.95 | 0.98
P003 | Logistics | SUP034 | 2025-10 | 2025-05-27 | 1187937.02 | 942775 | -245162.02 | 245162.02 | 1 | 2025-10-28 | 2 | 1517182.49 | -329245.47 | DOWN | 0.2772 | 154 | Low | 271450.01 | 0.234 | 2 | 671324.99 | 19 | 0.95 | 0.98
P003 | Logistics | SUP034 | 2025-10 | 2025-06-11 | 1063358.55 | 942775 | -120583.55 | 120583.55 | 0 | 2025-10-28 | 3 | 1187937.02 | -124578.47 | DOWN | 0.1172 | 139 | Low | 324036.06 | 0.287 | 3 | 618738.94 | 19 | 0.95 | 0.98
P003 | Logistics | SUP034 | 2025-10 | 2025-07-21 | 994309.09 | 942775 | -51534.09 | 51534.09 | 0 | 2025-10-28 | 4 | 1063358.55 | -69049.46 | DOWN | 0.0694 | 99 | Low | 431334.03 | 0.429 | 4 | 511440.97 | 19 | 0.95 | 0.98
P003 | Logistics | SUP034 | 2025-10 | 2025-09-18 | 949562.67 | 942775 | -6787.67 | 6787.67 | 0 | 2025-10-28 | 5 | 994309.09 | -44746.42 | DOWN | 0.0471 | 40 | Medium | 566602.36 | 0.638 | 3 | 376172.64 | 19 | 0.95 | 0.98
P003 | Logistics | SUP034 | 2025-10 | 2025-09-26 | 957176.08 | 942775 | -14401.08 | 14401.08 | 0 | 2025-10-28 | 6 | 949562.67 | 7613.41 | UP | 0.008 | 32 | Medium | 668108.83 | 0.667 | 6 | 274666.17 | 19 | 0.95 | 0.98
P003 | Software | SUP034 | 2025-11 | 2025-06-24 | 774563.57 | 407621 | -366942.57 | 366942.57 | 1 | 2025-11-28 | 1 |  |  |  |  | 157 | Low | 165288.08 | 0.203 | 1 | 242332.92 | 11 | 1.85 | 1.52
P003 | Software | SUP034 | 2025-11 | 2025-07-23 | 573616.08 | 407621 | -165995.08 | 165995.08 | 1 | 2025-11-28 | 2 | 774563.57 | -200947.49 | DOWN | 0.3503 | 128 | Low | 159268.25 | 0.296 | 1 | 248352.75 | 11 | 1.85 | 1.52
P003 | Software | SUP034 | 2025-11 | 2025-09-06 | 479362.95 | 407621 | -71741.95 | 71741.95 | 0 | 2025-11-28 | 3 | 573616.08 | -94253.13 | DOWN | 0.1966 | 83 | Low | 223990.9 | 0.441 | 1 | 183630.1 | 11 | 1.85 | 1.52
P003 | Software | SUP034 | 2025-11 | 2025-11-07 | 432503.61 | 407621 | -24882.61 | 24882.61 | 0 | 2025-11-28 | 4 | 479362.95 | -46859.34 | DOWN | 0.1083 | 21 | Medium | 255319.53 | 0.64 | 3 | 152301.47 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP034 | 2025-12 | 2025-07-03 | 1195257.35 | 916350 | -278907.35 | 278907.35 | 1 | 2025-12-28 | 1 |  |  |  |  | 178 | Low | 173871.27 | 0.155 | 1 | 742478.73 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP034 | 2025-12 | 2025-07-23 | 1044095.63 | 916350 | -127745.63 | 127745.63 | 0 | 2025-12-28 | 2 | 1195257.35 | -151161.72 | DOWN | 0.1448 | 158 | Low | 210040.18 | 0.218 | 1 | 706309.82 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP034 | 2025-12 | 2025-09-20 | 971669.97 | 916350 | -55319.97 | 55319.97 | 0 | 2025-12-28 | 3 | 1044095.63 | -72425.66 | DOWN | 0.0745 | 99 | Low | 420257.27 | 0.425 | 3 | 496092.73 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP034 | 2025-12 | 2025-10-03 | 937081.23 | 916350 | -20731.23 | 20731.23 | 0 | 2025-12-28 | 4 | 971669.97 | -34588.74 | DOWN | 0.0369 | 86 | Low | 409097.78 | 0.471 | 4 | 507252.22 | 10 | 1.08 | 1.22
P003 | Services | SUP044 | 2025-01 | 2024-09-28 | 292472.18 | 177418 | -115054.18 | 115054.18 | 1 | 2025-01-28 | 1 |  |  |  |  | 122 | Low | 87323.24 | 0.315 | 0 | 90094.76 | 17 | 1.86 | 1.34
P003 | Services | SUP044 | 2025-01 | 2024-12-01 | 224570.91 | 177418 | -47152.91 | 47152.91 | 1 | 2025-01-28 | 2 | 292472.18 | -67901.27 | DOWN | 0.3024 | 58 | Low | 111070.69 | 0.521 | 4 | 66347.31 | 17 | 1.86 | 1.34
P003 | Services | SUP044 | 2025-01 | 2025-01-06 | 198415.26 | 177418 | -20997.26 | 20997.26 | 0 | 2025-01-28 | 3 | 224570.91 | -26155.65 | DOWN | 0.1318 | 22 | Low | 121379.12 | 0.636 | 4 | 56038.88 | 17 | 1.86 | 1.34
P003 | Logistics | SUP044 | 2025-02 | 2024-09-02 | 2453647.16 | 1319701 | -1133946.16 | 1133946.16 | 1 | 2025-02-28 | 1 |  |  |  |  | 179 | Low | 332179.87 | 0.138 | 0 | 987521.13 | 17 | 2.1 | 1.03
P003 | Logistics | SUP044 | 2025-02 | 2024-11-20 | 1807116.13 | 1319701 | -487415.13 | 487415.13 | 1 | 2025-02-28 | 2 | 2453647.16 | -646531.03 | DOWN | 0.3578 | 100 | Low | 702168.12 | 0.376 | 3 | 617532.88 | 17 | 2.1 | 1.03
P003 | Logistics | SUP044 | 2025-02 | 2024-11-30 | 1530552.45 | 1319701 | -210851.45 | 210851.45 | 0 | 2025-02-28 | 3 | 1807116.13 | -276563.68 | DOWN | 0.1807 | 90 | Low | 663010.02 | 0.407 | 2 | 656690.98 | 17 | 2.1 | 1.03
P003 | Logistics | SUP044 | 2025-02 | 2025-01-28 | 1389333.85 | 1319701 | -69632.85 | 69632.85 | 0 | 2025-02-28 | 4 | 1530552.45 | -141218.6 | DOWN | 0.1016 | 31 | Low | 823381.58 | 0.592 | 6 | 496319.42 | 17 | 2.1 | 1.03
P003 | Logistics | SUP044 | 2025-02 | 2025-02-14 | 1305515.24 | 1319701 | 14185.76 | 14185.76 | 0 | 2025-02-28 | 5 | 1389333.85 | -83818.61 | DOWN | 0.0642 | 14 | Low | 864703.1 | 0.645 | 2 | 454997.9 | 17 | 2.1 | 1.03
P003 | Materials | SUP044 | 2025-03 | 2025-01-04 | 352096.93 | 277108 | -74988.93 | 74988.93 | 1 | 2025-03-28 | 1 |  |  |  |  | 83 | Low | 179822.85 | 0.478 | 3 | 97285.15 | 13 | 1.13 | 1.73
P003 | Materials | SUP044 | 2025-03 | 2025-01-17 | 308975.23 | 277108 | -31867.23 | 31867.23 | 0 | 2025-03-28 | 2 | 352096.93 | -43121.7 | DOWN | 0.1396 | 70 | Low | 160526.31 | 0.524 | 6 | 116581.69 | 13 | 1.13 | 1.73
P003 | Materials | SUP044 | 2025-03 | 2025-02-04 | 292178.76 | 277108 | -15070.76 | 15070.76 | 0 | 2025-03-28 | 3 | 308975.23 | -16796.47 | DOWN | 0.0575 | 52 | Medium | 176188.2 | 0.586 | 3 | 100919.8 | 13 | 1.13 | 1.73
P003 | Materials | SUP044 | 2025-03 | 2025-02-19 | 286931.31 | 277108 | -9823.31 | 9823.31 | 0 | 2025-03-28 | 4 | 292178.76 | -5247.45 | DOWN | 0.0183 | 37 | Medium | 196093.65 | 0.639 | 3 | 81014.35 | 13 | 1.13 | 1.73
P003 | Materials | SUP044 | 2025-03 | 2025-02-24 | 283497.13 | 277108 | -6389.13 | 6389.13 | 0 | 2025-03-28 | 5 | 286931.31 | -3434.18 | DOWN | 0.0121 | 32 | Medium | 190946.53 | 0.656 | 3 | 86161.47 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP044 | 2025-04 | 2024-11-06 | 2736999.88 | 2036490 | -700509.88 | 700509.88 | 1 | 2025-04-28 | 1 |  |  |  |  | 173 | Low | 452239.41 | 0.163 | 1 | 1584250.59 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP044 | 2025-04 | 2024-11-17 | 2360348.35 | 2036490 | -323858.35 | 323858.35 | 0 | 2025-04-28 | 2 | 2736999.88 | -376651.53 | DOWN | 0.1596 | 162 | Low | 481119.31 | 0.201 | 4 | 1555370.69 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP044 | 2025-04 | 2024-12-03 | 2177628.28 | 2036490 | -141138.28 | 141138.28 | 0 | 2025-04-28 | 3 | 2360348.35 | -182720.07 | DOWN | 0.0839 | 146 | Low | 588152.83 | 0.256 | 0 | 1448337.17 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP044 | 2025-04 | 2025-01-31 | 2093394.76 | 2036490 | -56904.76 | 56904.76 | 0 | 2025-04-28 | 4 | 2177628.28 | -84233.52 | DOWN | 0.0402 | 87 | Low | 929759.71 | 0.46 | 1 | 1106730.29 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP044 | 2025-04 | 2025-02-11 | 2052701.48 | 2036490 | -16211.48 | 16211.48 | 0 | 2025-04-28 | 5 | 2093394.76 | -40693.28 | DOWN | 0.0198 | 76 | Low | 1097079.24 | 0.498 | 2 | 939410.76 | 13 | 1.21 | 1.27
P003 | Materials | SUP044 | 2025-05 | 2024-12-05 | 1803097.87 | 1252542 | -550555.87 | 550555.87 | 1 | 2025-05-28 | 1 |  |  |  |  | 174 | Low | 275459.66 | 0.156 | 4 | 977082.34 | 14 | 1.36 | 1.73
P003 | Materials | SUP044 | 2025-05 | 2024-12-30 | 1493624.03 | 1252542 | -241082.03 | 241082.03 | 1 | 2025-05-28 | 2 | 1803097.87 | -309473.84 | DOWN | 0.2072 | 149 | Low | 358386.54 | 0.241 | 4 | 894155.46 | 14 | 1.36 | 1.73
P003 | Materials | SUP044 | 2025-05 | 2025-03-06 | 1340891.59 | 1252542 | -88349.59 | 88349.59 | 0 | 2025-05-28 | 3 | 1493624.03 | -152732.44 | DOWN | 0.1139 | 83 | Low | 655087.39 | 0.466 | 1 | 597454.61 | 14 | 1.36 | 1.73
P003 | Materials | SUP044 | 2025-05 | 2025-03-22 | 1292554.22 | 1252542 | -40012.22 | 40012.22 | 0 | 2025-05-28 | 4 | 1340891.59 | -48337.37 | DOWN | 0.0374 | 67 | Low | 706295.58 | 0.52 | 3 | 546246.42 | 14 | 1.36 | 1.73
P003 | Materials | SUP044 | 2025-05 | 2025-04-10 | 1271689.27 | 1252542 | -19147.27 | 19147.27 | 0 | 2025-05-28 | 5 | 1292554.22 | -20864.95 | DOWN | 0.0164 | 48 | Medium | 765739.12 | 0.585 | 4 | 486802.88 | 14 | 1.36 | 1.73
P003 | Materials | SUP044 | 2025-05 | 2025-04-18 | 1255766.19 | 1252542 | -3224.19 | 3224.19 | 0 | 2025-05-28 | 6 | 1271689.27 | -15923.08 | DOWN | 0.0127 | 40 | Medium | 711621.14 | 0.612 | 0 | 540920.86 | 14 | 1.36 | 1.73
P003 | Electronics | SUP044 | 2025-06 | 2025-01-19 | 2854116.74 | 1955054 | -899062.74 | 899062.74 | 1 | 2025-06-28 | 1 |  |  |  |  | 160 | Low | 559296.16 | 0.201 | 1 | 1395757.84 | 22 | 1.47 | 1.51
P003 | Electronics | SUP044 | 2025-06 | 2025-03-26 | 2385525.98 | 1955054 | -430471.98 | 430471.98 | 1 | 2025-06-28 | 2 | 2854116.74 | -468590.76 | DOWN | 0.1964 | 94 | Low | 980645.49 | 0.423 | 2 | 974408.51 | 22 | 1.47 | 1.51
P003 | Electronics | SUP044 | 2025-06 | 2025-03-27 | 2180515.65 | 1955054 | -225461.65 | 225461.65 | 0 | 2025-06-28 | 3 | 2385525.98 | -205010.33 | DOWN | 0.094 | 93 | Low | 856926.06 | 0.426 | 1 | 1098127.94 | 22 | 1.47 | 1.51
P003 | Electronics | SUP044 | 2025-06 | 2025-05-15 | 2078369.61 | 1955054 | -123315.61 | 123315.61 | 0 | 2025-06-28 | 4 | 2180515.65 | -102146.04 | DOWN | 0.0491 | 44 | Medium | 1258027.01 | 0.591 | 1 | 697026.99 | 22 | 1.47 | 1.51
P003 | Electronics | SUP044 | 2025-06 | 2025-06-09 | 2048448.35 | 1955054 | -93394.35 | 93394.35 | 0 | 2025-06-28 | 5 | 2078369.61 | -29921.26 | DOWN | 0.0146 | 19 | Medium | 1378151.3 | 0.675 | 6 | 576902.7 | 22 | 1.47 | 1.51
P003 | Services | SUP044 | 2025-07 | 2025-02-13 | 694842.25 | 509815 | -185027.25 | 185027.25 | 1 | 2025-07-28 | 1 |  |  |  |  | 165 | Low | 144281.24 | 0.195 | 2 | 365533.76 | 13 | 0.8 | 1.22
P003 | Services | SUP044 | 2025-07 | 2025-03-30 | 601915.84 | 509815 | -92100.84 | 92100.84 | 1 | 2025-07-28 | 2 | 694842.25 | -92926.41 | DOWN | 0.1544 | 120 | Low | 213360.27 | 0.355 | 1 | 296454.73 | 13 | 0.8 | 1.22
P003 | Services | SUP044 | 2025-07 | 2025-04-07 | 547529.01 | 509815 | -37714.01 | 37714.01 | 0 | 2025-07-28 | 3 | 601915.84 | -54386.83 | DOWN | 0.0993 | 112 | Low | 204590.23 | 0.383 | 2 | 305224.77 | 13 | 0.8 | 1.22
P003 | Services | SUP044 | 2025-07 | 2025-07-05 | 533872.8 | 509815 | -24057.8 | 24057.8 | 0 | 2025-07-28 | 4 | 547529.01 | -13656.21 | DOWN | 0.0256 | 23 | High | 388820.47 | 0.698 | 7 | 120994.53 | 13 | 0.8 | 1.22
P003 | Materials | SUP044 | 2025-08 | 2025-03-02 | 3971708.05 | 2535336 | -1436372.05 | 1436372.05 | 1 | 2025-08-28 | 1 |  |  |  |  | 179 | Low | 604616 | 0.149 | 2 | 1930720 | 7 | 1.37 | 1.47
P003 | Materials | SUP044 | 2025-08 | 2025-03-16 | 3161178.88 | 2535336 | -625842.88 | 625842.88 | 1 | 2025-08-28 | 2 | 3971708.05 | -810529.17 | DOWN | 0.2564 | 165 | Low | 557932.56 | 0.187 | 0 | 1977403.44 | 7 | 1.37 | 1.47
P003 | Materials | SUP044 | 2025-08 | 2025-05-24 | 2814028.05 | 2535336 | -278692.05 | 278692.05 | 0 | 2025-08-28 | 3 | 3161178.88 | -347150.83 | DOWN | 0.1234 | 96 | Low | 1223756.58 | 0.421 | 4 | 1311579.42 | 7 | 1.37 | 1.47
P003 | Materials | SUP044 | 2025-08 | 2025-05-28 | 2679234.76 | 2535336 | -143898.76 | 143898.76 | 0 | 2025-08-28 | 4 | 2814028.05 | -134793.29 | DOWN | 0.0503 | 92 | Low | 1071757.03 | 0.435 | 3 | 1463578.97 | 7 | 1.37 | 1.47
P003 | Materials | SUP044 | 2025-08 | 2025-06-24 | 2572762.2 | 2535336 | -37426.2 | 37426.2 | 0 | 2025-08-28 | 5 | 2679234.76 | -106472.56 | DOWN | 0.0414 | 65 | Low | 1413204.4 | 0.526 | 0 | 1122131.6 | 7 | 1.37 | 1.47
P003 | Materials | SUP044 | 2025-08 | 2025-08-10 | 2551872.99 | 2535336 | -16536.99 | 16536.99 | 0 | 2025-08-28 | 6 | 2572762.2 | -20889.21 | DOWN | 0.0082 | 18 | High | 1821125.24 | 0.686 | 6 | 714210.76 | 7 | 1.37 | 1.47
P003 | Software | SUP044 | 2025-09 | 2025-05-13 | 1133613.43 | 777211 | -356402.43 | 356402.43 | 1 | 2025-09-28 | 1 |  |  |  |  | 138 | Low | 308413.89 | 0.291 | 0 | 468797.11 | 10 | 0.71 | 1.27
P003 | Software | SUP044 | 2025-09 | 2025-06-14 | 955579.88 | 777211 | -178368.88 | 178368.88 | 1 | 2025-09-28 | 2 | 1133613.43 | -178033.55 | DOWN | 0.1863 | 106 | Low | 381554.75 | 0.404 | 1 | 395656.25 | 10 | 0.71 | 1.27
P003 | Software | SUP044 | 2025-09 | 2025-07-23 | 858002.91 | 777211 | -80791.91 | 80791.91 | 0 | 2025-09-28 | 3 | 955579.88 | -97576.97 | DOWN | 0.1137 | 67 | Low | 465620.55 | 0.542 | 6 | 311590.45 | 10 | 0.71 | 1.27
P003 | Software | SUP044 | 2025-09 | 2025-08-13 | 802906.81 | 777211 | -25695.81 | 25695.81 | 0 | 2025-09-28 | 4 | 858002.91 | -55096.1 | DOWN | 0.0686 | 46 | Medium | 459379.85 | 0.617 | 6 | 317831.15 | 10 | 0.71 | 1.27
P003 | Software | SUP044 | 2025-10 | 2025-06-27 | 2338419.52 | 1483007 | -855412.52 | 855412.52 | 1 | 2025-10-28 | 1 |  |  |  |  | 123 | Low | 856821.48 | 0.344 | 2 | 626185.52 | 19 | 0.95 | 0.98
P003 | Software | SUP044 | 2025-10 | 2025-06-27 | 1829775.59 | 1483007 | -346768.59 | 346768.59 | 1 | 2025-10-28 | 2 | 2338419.52 | -508643.93 | DOWN | 0.278 | 123 | Low | 676081.68 | 0.344 | 4 | 806925.32 | 19 | 0.95 | 0.98
P003 | Software | SUP044 | 2025-10 | 2025-07-15 | 1608431.5 | 1483007 | -125424.5 | 125424.5 | 0 | 2025-10-28 | 3 | 1829775.59 | -221344.09 | DOWN | 0.1376 | 105 | Low | 614099.15 | 0.408 | 2 | 868907.85 | 19 | 0.95 | 0.98
P003 | Software | SUP044 | 2025-10 | 2025-07-28 | 1555881.11 | 1483007 | -72874.11 | 72874.11 | 0 | 2025-10-28 | 4 | 1608431.5 | -52550.39 | DOWN | 0.0338 | 92 | Low | 757153.4 | 0.454 | 4 | 725853.6 | 19 | 0.95 | 0.98
P003 | Software | SUP044 | 2025-10 | 2025-09-09 | 1520184.64 | 1483007 | -37177.64 | 37177.64 | 0 | 2025-10-28 | 5 | 1555881.11 | -35696.47 | DOWN | 0.0235 | 49 | Medium | 938794.28 | 0.606 | 8 | 544212.72 | 19 | 0.95 | 0.98
P003 | Software | SUP044 | 2025-10 | 2025-09-16 | 1480247.6 | 1483007 | 2759.4 | 2759.4 | 0 | 2025-10-28 | 6 | 1520184.64 | -39937.04 | DOWN | 0.027 | 42 | Medium | 928000.13 | 0.631 | 5 | 555006.87 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP044 | 2025-11 | 2025-06-24 | 2996065.51 | 2129390 | -866675.51 | 866675.51 | 1 | 2025-11-28 | 1 |  |  |  |  | 157 | Low | 626722.56 | 0.203 | 0 | 1502667.44 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP044 | 2025-11 | 2025-07-04 | 2471436.46 | 2129390 | -342046.46 | 342046.46 | 0 | 2025-11-28 | 2 | 2996065.51 | -524629.05 | DOWN | 0.2123 | 147 | Low | 569036.47 | 0.235 | 0 | 1560353.53 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP044 | 2025-11 | 2025-08-03 | 2274217.76 | 2129390 | -144827.76 | 144827.76 | 0 | 2025-11-28 | 3 | 2471436.46 | -197218.7 | DOWN | 0.0867 | 117 | Low | 700966.34 | 0.331 | 3 | 1428423.66 | 11 | 1.85 | 1.52
P003 | Electronics | SUP044 | 2025-12 | 2025-07-08 | 1210663.86 | 872103 | -338560.86 | 338560.86 | 1 | 2025-12-28 | 1 |  |  |  |  | 173 | Low | 185130.72 | 0.165 | 0 | 686972.28 | 10 | 1.08 | 1.22
P003 | Electronics | SUP044 | 2025-12 | 2025-08-20 | 1036224.78 | 872103 | -164121.78 | 164121.78 | 1 | 2025-12-28 | 2 | 1210663.86 | -174439.08 | DOWN | 0.1683 | 130 | Low | 344162.45 | 0.316 | 0 | 527940.55 | 10 | 1.08 | 1.22
P003 | Electronics | SUP044 | 2025-12 | 2025-08-21 | 955231.39 | 872103 | -83128.39 | 83128.39 | 0 | 2025-12-28 | 3 | 1036224.78 | -80993.39 | DOWN | 0.0848 | 129 | Low | 304917.72 | 0.32 | 0 | 567185.28 | 10 | 1.08 | 1.22
P003 | Electronics | SUP044 | 2025-12 | 2025-10-09 | 903274.53 | 872103 | -31171.53 | 31171.53 | 0 | 2025-12-28 | 4 | 955231.39 | -51956.86 | DOWN | 0.0575 | 80 | Low | 444514.73 | 0.492 | 4 | 427588.27 | 10 | 1.08 | 1.22
P003 | Electronics | SUP044 | 2025-12 | 2025-10-21 | 893653.66 | 872103 | -21550.66 | 21550.66 | 0 | 2025-12-28 | 5 | 903274.53 | -9620.87 | DOWN | 0.0108 | 68 | Low | 497362.64 | 0.534 | 4 | 374740.36 | 10 | 1.08 | 1.22
P003 | Services | SUP050 | 2025-01 | 2024-10-07 | 1631534.1 | 880034 | -751500.1 | 751500.1 | 1 | 2025-01-28 | 1 |  |  |  |  | 113 | Low | 482645.99 | 0.287 | 2 | 397388.01 | 17 | 1.86 | 1.34
P003 | Services | SUP050 | 2025-01 | 2024-10-09 | 1335517.49 | 880034 | -455483.49 | 455483.49 | 1 | 2025-01-28 | 2 | 1631534.1 | -296016.61 | DOWN | 0.2216 | 111 | Low | 405114.2 | 0.292 | 0 | 474919.8 | 17 | 1.86 | 1.34
P003 | Services | SUP050 | 2025-01 | 2024-10-15 | 1120702.76 | 880034 | -240668.76 | 240668.76 | 1 | 2025-01-28 | 3 | 1335517.49 | -214814.73 | DOWN | 0.1917 | 105 | Low | 333692.49 | 0.308 | 1 | 546341.51 | 17 | 1.86 | 1.34
P003 | Services | SUP050 | 2025-01 | 2024-11-18 | 1026422.86 | 880034 | -146388.86 | 146388.86 | 0 | 2025-01-28 | 4 | 1120702.76 | -94279.9 | DOWN | 0.0919 | 71 | Low | 395189.16 | 0.399 | 3 | 484844.84 | 17 | 1.86 | 1.34
P003 | Services | SUP050 | 2025-01 | 2024-11-29 | 945372.82 | 880034 | -65338.82 | 65338.82 | 0 | 2025-01-28 | 5 | 1026422.86 | -81050.04 | DOWN | 0.0857 | 60 | Low | 374484.95 | 0.429 | 4 | 505549.05 | 17 | 1.86 | 1.34
P003 | Services | SUP050 | 2025-01 | 2024-12-02 | 910105.13 | 880034 | -30071.13 | 30071.13 | 0 | 2025-01-28 | 6 | 945372.82 | -35267.69 | DOWN | 0.0388 | 57 | Low | 392015.91 | 0.437 | 1 | 488018.09 | 17 | 1.86 | 1.34
P003 | Logistics | SUP050 | 2025-02 | 2024-11-14 | 1801090.97 | 844549 | -956541.97 | 956541.97 | 1 | 2025-02-28 | 1 |  |  |  |  | 106 | Low | 577768.65 | 0.298 | 3 | 266780.35 | 17 | 2.1 | 1.03
P003 | Logistics | SUP050 | 2025-02 | 2024-11-25 | 1369803.25 | 844549 | -525254.25 | 525254.25 | 1 | 2025-02-28 | 2 | 1801090.97 | -431287.72 | DOWN | 0.3149 | 95 | Low | 425095.18 | 0.326 | 0 | 419453.82 | 17 | 2.1 | 1.03
P003 | Logistics | SUP050 | 2025-02 | 2024-12-08 | 1148049.73 | 844549 | -303500.73 | 303500.73 | 1 | 2025-02-28 | 3 | 1369803.25 | -221753.52 | DOWN | 0.1932 | 82 | Low | 443574.58 | 0.36 | 1 | 400974.42 | 17 | 2.1 | 1.03
P003 | Logistics | SUP050 | 2025-02 | 2025-02-04 | 1033019.84 | 844549 | -188470.84 | 188470.84 | 1 | 2025-02-28 | 4 | 1148049.73 | -115029.89 | DOWN | 0.1114 | 24 | Low | 512850.9 | 0.512 | 2 | 331698.1 | 17 | 2.1 | 1.03
P003 | Services | SUP050 | 2025-03 | 2025-01-09 | 1520255.55 | 866593 | -653662.55 | 653662.55 | 1 | 2025-03-28 | 1 |  |  |  |  | 78 | Low | 620343.64 | 0.413 | 0 | 246249.36 | 13 | 1.13 | 1.73
P003 | Services | SUP050 | 2025-03 | 2025-01-30 | 1217195.92 | 866593 | -350602.92 | 350602.92 | 1 | 2025-03-28 | 2 | 1520255.55 | -303059.63 | DOWN | 0.249 | 57 | Low | 591800.6 | 0.474 | 2 | 274792.4 | 13 | 1.13 | 1.73
P003 | Services | SUP050 | 2025-03 | 2025-03-15 | 1054124.37 | 866593 | -187531.37 | 187531.37 | 1 | 2025-03-28 | 3 | 1217195.92 | -163071.55 | DOWN | 0.1547 | 13 | Low | 625304.52 | 0.602 | 2 | 241288.48 | 13 | 1.13 | 1.73
P003 | Services | SUP050 | 2025-03 | 2025-03-18 | 970496.89 | 866593 | -103903.89 | 103903.89 | 0 | 2025-03-28 | 4 | 1054124.37 | -83627.48 | DOWN | 0.0862 | 10 | Medium | 565663.72 | 0.608 | 6 | 300929.28 | 13 | 1.13 | 1.73
P003 | Electronics | SUP050 | 2025-04 | 2024-12-15 | 254037.94 | 154552 | -99485.94 | 99485.94 | 1 | 2025-04-28 | 1 |  |  |  |  | 134 | Low | 64414.81 | 0.248 | 2 | 90137.19 | 13 | 1.21 | 1.27
P003 | Electronics | SUP050 | 2025-04 | 2025-02-18 | 210868.48 | 154552 | -56316.48 | 56316.48 | 1 | 2025-04-28 | 2 | 254037.94 | -43169.46 | DOWN | 0.2047 | 69 | Low | 91699.17 | 0.435 | 5 | 62852.83 | 13 | 1.21 | 1.27
P003 | Electronics | SUP050 | 2025-04 | 2025-04-02 | 186952.18 | 154552 | -32400.18 | 32400.18 | 1 | 2025-04-28 | 3 | 210868.48 | -23916.3 | DOWN | 0.1279 | 26 | Low | 97068.24 | 0.559 | 3 | 57483.76 | 13 | 1.21 | 1.27
P003 | Materials | SUP050 | 2025-05 | 2025-02-18 | 261312.37 | 162785 | -98527.37 | 98527.37 | 1 | 2025-05-28 | 1 |  |  |  |  | 99 | Low | 95136.86 | 0.343 | 1 | 67648.14 | 14 | 1.36 | 1.73
P003 | Materials | SUP050 | 2025-05 | 2025-03-06 | 214542.77 | 162785 | -51757.77 | 51757.77 | 1 | 2025-05-28 | 2 | 261312.37 | -46769.6 | DOWN | 0.218 | 83 | Low | 84149.95 | 0.388 | 6 | 78635.05 | 14 | 1.36 | 1.73
P003 | Materials | SUP050 | 2025-05 | 2025-04-28 | 189005.31 | 162785 | -26220.31 | 26220.31 | 0 | 2025-05-28 | 3 | 214542.77 | -25537.46 | DOWN | 0.1351 | 30 | Low | 104979.65 | 0.538 | 7 | 57805.35 | 14 | 1.36 | 1.73
P003 | Materials | SUP050 | 2025-05 | 2025-05-10 | 178212.49 | 162785 | -15427.49 | 15427.49 | 0 | 2025-05-28 | 4 | 189005.31 | -10792.82 | DOWN | 0.0606 | 18 | Medium | 95572.72 | 0.572 | 4 | 67212.28 | 14 | 1.36 | 1.73
P003 | Materials | SUP050 | 2025-05 | 2025-05-16 | 170215.88 | 162785 | -7430.88 | 7430.88 | 0 | 2025-05-28 | 5 | 178212.49 | -7996.61 | DOWN | 0.047 | 12 | Medium | 101087.02 | 0.589 | 4 | 61697.98 | 14 | 1.36 | 1.73
P003 | Materials | SUP050 | 2025-05 | 2025-05-16 | 167492.99 | 162785 | -4707.99 | 4707.99 | 0 | 2025-05-28 | 6 | 170215.88 | -2722.89 | DOWN | 0.0163 | 12 | Medium | 92905.3 | 0.589 | 3 | 69879.7 | 14 | 1.36 | 1.73
P003 | Materials | SUP050 | 2025-06 | 2025-01-01 | 1566113.86 | 976364 | -589749.86 | 589749.86 | 1 | 2025-06-28 | 1 |  |  |  |  | 178 | Low | 203106.89 | 0.123 | 0 | 773257.11 | 22 | 1.47 | 1.51
P003 | Materials | SUP050 | 2025-06 | 2025-02-01 | 1307084.23 | 976364 | -330720.23 | 330720.23 | 1 | 2025-06-28 | 2 | 1566113.86 | -259029.63 | DOWN | 0.1982 | 147 | Low | 287416.78 | 0.204 | 1 | 688947.22 | 22 | 1.47 | 1.51
P003 | Materials | SUP050 | 2025-06 | 2025-02-01 | 1158456.16 | 976364 | -182092.16 | 182092.16 | 1 | 2025-06-28 | 3 | 1307084.23 | -148628.07 | DOWN | 0.1283 | 147 | Low | 225561.61 | 0.204 | 1 | 750802.39 | 22 | 1.47 | 1.51
P003 | Software | SUP050 | 2025-07 | 2025-03-16 | 3369371.83 | 1843842 | -1525529.83 | 1525529.83 | 1 | 2025-07-28 | 1 |  |  |  |  | 134 | Low | 897358.06 | 0.254 | 2 | 946483.94 | 13 | 0.8 | 1.22
P003 | Software | SUP050 | 2025-07 | 2025-04-11 | 2643557.4 | 1843842 | -799715.4 | 799715.4 | 1 | 2025-07-28 | 2 | 3369371.83 | -725814.43 | DOWN | 0.2746 | 108 | Low | 914177.15 | 0.331 | 3 | 929664.85 | 13 | 0.8 | 1.22
P003 | Software | SUP050 | 2025-07 | 2025-05-07 | 2308302.32 | 1843842 | -464460.32 | 464460.32 | 1 | 2025-07-28 | 3 | 2643557.4 | -335255.08 | DOWN | 0.1452 | 82 | Low | 979871.96 | 0.408 | 5 | 863970.04 | 13 | 0.8 | 1.22
P003 | Software | SUP050 | 2025-07 | 2025-06-16 | 2084841.47 | 1843842 | -240999.47 | 240999.47 | 0 | 2025-07-28 | 4 | 2308302.32 | -223460.85 | DOWN | 0.1072 | 42 | Medium | 1141990.75 | 0.526 | 3 | 701851.25 | 13 | 0.8 | 1.22
P003 | Logistics | SUP050 | 2025-08 | 2025-03-19 | 3736947.89 | 1893384 | -1843563.89 | 1843563.89 | 1 | 2025-08-28 | 1 |  |  |  |  | 162 | Low | 590081.93 | 0.164 | 0 | 1303302.07 | 7 | 1.37 | 1.47
P003 | Logistics | SUP050 | 2025-08 | 2025-03-27 | 2855203.65 | 1893384 | -961819.65 | 961819.65 | 1 | 2025-08-28 | 2 | 3736947.89 | -881744.24 | DOWN | 0.3088 | 154 | Low | 543616.09 | 0.187 | 3 | 1349767.91 | 7 | 1.37 | 1.47
P003 | Logistics | SUP050 | 2025-08 | 2025-04-08 | 2403266.15 | 1893384 | -509882.15 | 509882.15 | 1 | 2025-08-28 | 3 | 2855203.65 | -451937.5 | DOWN | 0.1881 | 142 | Low | 540434.86 | 0.221 | 0 | 1352949.14 | 7 | 1.37 | 1.47
P003 | Logistics | SUP050 | 2025-08 | 2025-04-19 | 2206329.98 | 1893384 | -312945.98 | 312945.98 | 0 | 2025-08-28 | 4 | 2403266.15 | -196936.17 | DOWN | 0.0893 | 131 | Low | 582196.06 | 0.252 | 4 | 1311187.94 | 7 | 1.37 | 1.47
P003 | Logistics | SUP050 | 2025-08 | 2025-05-23 | 2056185.78 | 1893384 | -162801.78 | 162801.78 | 0 | 2025-08-28 | 5 | 2206329.98 | -150144.2 | DOWN | 0.073 | 97 | Low | 713491.33 | 0.348 | 3 | 1179892.67 | 7 | 1.37 | 1.47
P003 | Logistics | SUP050 | 2025-08 | 2025-07-15 | 2010835.8 | 1893384 | -117451.8 | 117451.8 | 0 | 2025-08-28 | 6 | 2056185.78 | -45349.98 | DOWN | 0.0226 | 44 | Medium | 1053347.13 | 0.498 | 3 | 840036.87 | 7 | 1.37 | 1.47
P003 | Services | SUP050 | 2025-09 | 2025-04-23 | 3489669.17 | 1870811 | -1618858.17 | 1618858.17 | 1 | 2025-09-28 | 1 |  |  |  |  | 158 | Low | 677114.79 | 0.183 | 8 | 1193696.21 | 10 | 0.71 | 1.27
P003 | Services | SUP050 | 2025-09 | 2025-05-09 | 2745200.39 | 1870811 | -874389.39 | 874389.39 | 1 | 2025-09-28 | 2 | 3489669.17 | -744468.78 | DOWN | 0.2712 | 142 | Low | 681576.46 | 0.23 | 3 | 1189234.54 | 10 | 0.71 | 1.27
P003 | Services | SUP050 | 2025-09 | 2025-06-03 | 2348299.93 | 1870811 | -477488.93 | 477488.93 | 1 | 2025-09-28 | 3 | 2745200.39 | -396900.46 | DOWN | 0.169 | 117 | Low | 673212.45 | 0.304 | 0 | 1197598.55 | 10 | 0.71 | 1.27
P003 | Services | SUP050 | 2025-09 | 2025-06-11 | 2143100.85 | 1870811 | -272289.85 | 272289.85 | 0 | 2025-09-28 | 4 | 2348299.93 | -205199.08 | DOWN | 0.0957 | 109 | Low | 740032.36 | 0.328 | 1 | 1130778.64 | 10 | 0.71 | 1.27
P003 | Services | SUP050 | 2025-09 | 2025-06-22 | 2037611.22 | 1870811 | -166800.22 | 166800.22 | 0 | 2025-09-28 | 5 | 2143100.85 | -105489.63 | DOWN | 0.0518 | 98 | Low | 686697.21 | 0.36 | 3 | 1184113.79 | 10 | 0.71 | 1.27
P003 | Services | SUP050 | 2025-09 | 2025-09-08 | 1953580.34 | 1870811 | -82769.34 | 82769.34 | 0 | 2025-09-28 | 6 | 2037611.22 | -84030.88 | DOWN | 0.043 | 20 | Medium | 1115387.46 | 0.591 | 3 | 755423.54 | 10 | 0.71 | 1.27
P003 | Services | SUP050 | 2025-10 | 2025-05-10 | 1491708.14 | 828026 | -663682.14 | 663682.14 | 1 | 2025-10-28 | 1 |  |  |  |  | 171 | Low | 227811.13 | 0.145 | 1 | 600214.87 | 19 | 0.95 | 0.98
P003 | Services | SUP050 | 2025-10 | 2025-05-21 | 1192496.97 | 828026 | -364470.97 | 364470.97 | 1 | 2025-10-28 | 2 | 1491708.14 | -299211.17 | DOWN | 0.2509 | 160 | Low | 202865.46 | 0.177 | 0 | 625160.54 | 19 | 0.95 | 0.98
P003 | Services | SUP050 | 2025-10 | 2025-06-20 | 1022693.4 | 828026 | -194667.4 | 194667.4 | 1 | 2025-10-28 | 3 | 1192496.97 | -169803.57 | DOWN | 0.166 | 130 | Low | 274674.32 | 0.266 | 1 | 553351.68 | 19 | 0.95 | 0.98
P003 | Services | SUP050 | 2025-10 | 2025-10-17 | 927075 | 828026 | -99049 | 99049 | 0 | 2025-10-28 | 4 | 1022693.4 | -95618.4 | DOWN | 0.1031 | 11 | Medium | 548449.35 | 0.617 | 4 | 279576.65 | 19 | 0.95 | 0.98
P003 | Materials | SUP050 | 2025-11 | 2025-08-11 | 2070360.98 | 1442000 | -628360.98 | 628360.98 | 1 | 2025-11-28 | 1 |  |  |  |  | 109 | Low | 615852.78 | 0.298 | 1 | 826147.22 | 11 | 1.85 | 1.52
P003 | Materials | SUP050 | 2025-11 | 2025-08-17 | 1783803.31 | 1442000 | -341803.31 | 341803.31 | 1 | 2025-11-28 | 2 | 2070360.98 | -286557.67 | DOWN | 0.1606 | 103 | Low | 557360.56 | 0.314 | 2 | 884639.44 | 11 | 1.85 | 1.52
P003 | Materials | SUP050 | 2025-11 | 2025-08-27 | 1630014.25 | 1442000 | -188014.25 | 188014.25 | 0 | 2025-11-28 | 3 | 1783803.31 | -153789.06 | DOWN | 0.0943 | 93 | Low | 532257.16 | 0.34 | 0 | 909742.84 | 11 | 1.85 | 1.52
P003 | Materials | SUP050 | 2025-12 | 2025-07-09 | 711620.97 | 402487 | -309133.97 | 309133.97 | 1 | 2025-12-28 | 1 |  |  |  |  | 172 | Low | 105781.09 | 0.14 | 0 | 296705.91 | 10 | 1.08 | 1.22
P003 | Materials | SUP050 | 2025-12 | 2025-09-01 | 575746.39 | 402487 | -173259.39 | 173259.39 | 1 | 2025-12-28 | 2 | 711620.97 | -135874.58 | DOWN | 0.236 | 118 | Low | 174991 | 0.298 | 0 | 227496 | 10 | 1.08 | 1.22
P003 | Materials | SUP050 | 2025-12 | 2025-10-17 | 500635.22 | 402487 | -98148.22 | 98148.22 | 1 | 2025-12-28 | 3 | 575746.39 | -75111.17 | DOWN | 0.15 | 72 | Low | 231406.88 | 0.433 | 1 | 171080.12 | 10 | 1.08 | 1.22
P003 | Materials | SUP050 | 2025-12 | 2025-12-13 | 455788.51 | 402487 | -53301.51 | 53301.51 | 0 | 2025-12-28 | 4 | 500635.22 | -44846.71 | DOWN | 0.0984 | 15 | Medium | 262744.27 | 0.6 | 7 | 139742.73 | 10 | 1.08 | 1.22
P003 | Materials | SUP050 | 2025-12 | 2025-12-14 | 435125.31 | 402487 | -32638.31 | 32638.31 | 0 | 2025-12-28 | 5 | 455788.51 | -20663.2 | DOWN | 0.0475 | 14 | Medium | 265347.05 | 0.603 | 4 | 137139.95 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP007 | 2025-01 | 2024-08-16 | 2482570.8 | 1441651 | -1040919.8 | 1040919.8 | 1 | 2025-01-28 | 1 |  |  |  |  | 165 | Low | 315553.65 | 0.136 | 1 | 1126097.35 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP007 | 2025-01 | 2024-09-21 | 2121645.19 | 1441651 | -679994.19 | 679994.19 | 1 | 2025-01-28 | 2 | 2482570.8 | -360925.61 | DOWN | 0.1701 | 129 | Low | 491041.57 | 0.225 | 4 | 950609.43 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP007 | 2025-01 | 2024-12-08 | 1876693.85 | 1441651 | -435042.85 | 435042.85 | 1 | 2025-01-28 | 3 | 2121645.19 | -244951.34 | DOWN | 0.1305 | 51 | Low | 735651.5 | 0.418 | 3 | 705999.5 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP007 | 2025-01 | 2024-12-25 | 1722078.69 | 1441651 | -280427.69 | 280427.69 | 1 | 2025-01-28 | 4 | 1876693.85 | -154615.16 | DOWN | 0.0898 | 34 | Medium | 826099.45 | 0.46 | 0 | 615551.55 | 17 | 1.86 | 1.34
P003 | Electronics | SUP007 | 2025-02 | 2024-09-16 | 1875594.96 | 985672 | -889922.96 | 889922.96 | 1 | 2025-02-28 | 1 |  |  |  |  | 165 | Low | 231676.26 | 0.133 | 0 | 753995.74 | 17 | 2.1 | 1.03
P003 | Electronics | SUP007 | 2025-02 | 2024-09-29 | 1559757.93 | 985672 | -574085.93 | 574085.93 | 1 | 2025-02-28 | 2 | 1875594.96 | -315837.03 | DOWN | 0.2025 | 152 | Low | 248490.89 | 0.164 | 3 | 737181.11 | 17 | 2.1 | 1.03
P003 | Electronics | SUP007 | 2025-02 | 2024-12-17 | 1363075.36 | 985672 | -377403.36 | 377403.36 | 1 | 2025-02-28 | 3 | 1559757.93 | -196682.57 | DOWN | 0.1443 | 73 | Low | 469601.87 | 0.354 | 6 | 516070.13 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP007 | 2025-03 | 2024-10-10 | 1152835.76 | 823854 | -328981.76 | 328981.76 | 1 | 2025-03-28 | 1 |  |  |  |  | 169 | Low | 146266.56 | 0.137 | 2 | 677587.44 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP007 | 2025-03 | 2024-11-23 | 1034248.34 | 823854 | -210394.34 | 210394.34 | 1 | 2025-03-28 | 2 | 1152835.76 | -118587.42 | DOWN | 0.1147 | 125 | Low | 251536.4 | 0.255 | 0 | 572317.6 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP007 | 2025-03 | 2024-11-29 | 965613.63 | 823854 | -141759.63 | 141759.63 | 0 | 2025-03-28 | 3 | 1034248.34 | -68634.71 | DOWN | 0.0711 | 119 | Low | 265457.36 | 0.271 | 4 | 558396.64 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP007 | 2025-03 | 2024-12-06 | 914239.15 | 823854 | -90385.15 | 90385.15 | 0 | 2025-03-28 | 4 | 965613.63 | -51374.48 | DOWN | 0.0562 | 112 | Low | 286033.69 | 0.29 | 5 | 537820.31 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP007 | 2025-03 | 2025-02-06 | 885612.06 | 823854 | -61758.06 | 61758.06 | 0 | 2025-03-28 | 5 | 914239.15 | -28627.09 | DOWN | 0.0323 | 50 | Medium | 399856.45 | 0.457 | 7 | 423997.55 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP007 | 2025-03 | 2025-03-06 | 861705.14 | 823854 | -37851.14 | 37851.14 | 0 | 2025-03-28 | 6 | 885612.06 | -23906.92 | DOWN | 0.0277 | 22 | Medium | 479962.43 | 0.532 | 2 | 343891.57 | 13 | 1.13 | 1.73
P003 | Software | SUP007 | 2025-04 | 2024-11-16 | 1543702.73 | 965199 | -578503.73 | 578503.73 | 1 | 2025-04-28 | 1 |  |  |  |  | 163 | Low | 249081.25 | 0.152 | 1 | 716117.75 | 13 | 1.21 | 1.27
P003 | Software | SUP007 | 2025-04 | 2024-12-07 | 1342198.15 | 965199 | -376999.15 | 376999.15 | 1 | 2025-04-28 | 2 | 1543702.73 | -201504.58 | DOWN | 0.1501 | 142 | Low | 278670.49 | 0.207 | 2 | 686528.51 | 13 | 1.21 | 1.27
P003 | Software | SUP007 | 2025-04 | 2025-01-17 | 1199773.7 | 965199 | -234574.7 | 234574.7 | 1 | 2025-04-28 | 3 | 1342198.15 | -142424.45 | DOWN | 0.1187 | 101 | Low | 359113.81 | 0.317 | 2 | 606085.19 | 13 | 1.21 | 1.27
P003 | Software | SUP007 | 2025-04 | 2025-01-30 | 1095046.03 | 965199 | -129847.03 | 129847.03 | 0 | 2025-04-28 | 4 | 1199773.7 | -104727.67 | DOWN | 0.0956 | 88 | Low | 378094.28 | 0.351 | 5 | 587104.72 | 13 | 1.21 | 1.27
P003 | Software | SUP007 | 2025-04 | 2025-03-05 | 1063111.43 | 965199 | -97912.43 | 97912.43 | 0 | 2025-04-28 | 5 | 1095046.03 | -31934.6 | DOWN | 0.03 | 54 | Low | 452669.82 | 0.442 | 1 | 512529.18 | 13 | 1.21 | 1.27
P003 | Software | SUP007 | 2025-04 | 2025-03-13 | 1028480.01 | 965199 | -63281.01 | 63281.01 | 0 | 2025-04-28 | 6 | 1063111.43 | -34631.42 | DOWN | 0.0337 | 46 | Medium | 466380.22 | 0.463 | 7 | 498818.78 | 13 | 1.21 | 1.27
P003 | Logistics | SUP007 | 2025-05 | 2024-12-30 | 3592911.39 | 1702973 | -1889938.39 | 1889938.39 | 1 | 2025-05-28 | 1 |  |  |  |  | 149 | Low | 706136.95 | 0.186 | 3 | 996836.05 | 14 | 1.36 | 1.73
P003 | Logistics | SUP007 | 2025-05 | 2025-03-01 | 2898076.26 | 1702973 | -1195103.26 | 1195103.26 | 1 | 2025-05-28 | 2 | 3592911.39 | -694835.13 | DOWN | 0.2398 | 88 | Low | 974601.85 | 0.345 | 0 | 728371.15 | 14 | 1.36 | 1.73
P003 | Logistics | SUP007 | 2025-05 | 2025-03-02 | 2497797.92 | 1702973 | -794824.92 | 794824.92 | 1 | 2025-05-28 | 3 | 2898076.26 | -400278.34 | DOWN | 0.1603 | 87 | Low | 889295.55 | 0.348 | 1 | 813677.45 | 14 | 1.36 | 1.73
P003 | Logistics | SUP007 | 2025-05 | 2025-03-12 | 2225121.52 | 1702973 | -522148.52 | 522148.52 | 1 | 2025-05-28 | 4 | 2497797.92 | -272676.4 | DOWN | 0.1225 | 77 | Low | 867486.11 | 0.374 | 4 | 835486.89 | 14 | 1.36 | 1.73
P003 | Logistics | SUP007 | 2025-05 | 2025-04-16 | 2062304.89 | 1702973 | -359331.89 | 359331.89 | 1 | 2025-05-28 | 5 | 2225121.52 | -162816.63 | DOWN | 0.0789 | 42 | Medium | 1021340.48 | 0.465 | 4 | 681632.52 | 14 | 1.36 | 1.73
P003 | Logistics | SUP007 | 2025-06 | 2025-01-15 | 2283213.68 | 1035147 | -1248066.68 | 1248066.68 | 1 | 2025-06-28 | 1 |  |  |  |  | 164 | Low | 327142.86 | 0.145 | 3 | 708004.14 | 22 | 1.47 | 1.51
P003 | Logistics | SUP007 | 2025-06 | 2025-01-25 | 1904048.52 | 1035147 | -868901.52 | 868901.52 | 1 | 2025-06-28 | 2 | 2283213.68 | -379165.16 | DOWN | 0.1991 | 154 | Low | 326749.14 | 0.17 | 4 | 708397.86 | 22 | 1.47 | 1.51
P003 | Logistics | SUP007 | 2025-06 | 2025-01-27 | 1583780.16 | 1035147 | -548633.16 | 548633.16 | 1 | 2025-06-28 | 3 | 1904048.52 | -320268.36 | DOWN | 0.2022 | 152 | Low | 298010.31 | 0.176 | 3 | 737136.69 | 22 | 1.47 | 1.51
P003 | Logistics | SUP007 | 2025-06 | 2025-05-10 | 1407631.86 | 1035147 | -372484.86 | 372484.86 | 1 | 2025-06-28 | 4 | 1583780.16 | -176148.3 | DOWN | 0.1251 | 49 | Low | 573266.6 | 0.441 | 5 | 461880.4 | 22 | 1.47 | 1.51
P003 | Logistics | SUP007 | 2025-06 | 2025-05-20 | 1307520.85 | 1035147 | -272373.85 | 272373.85 | 1 | 2025-06-28 | 5 | 1407631.86 | -100111.01 | DOWN | 0.0766 | 39 | Medium | 652422.47 | 0.467 | 2 | 382724.53 | 22 | 1.47 | 1.51
P003 | Services | SUP007 | 2025-07 | 2025-02-16 | 4610334.96 | 2322163 | -2288171.96 | 2288171.96 | 1 | 2025-07-28 | 1 |  |  |  |  | 162 | Low | 761699.93 | 0.158 | 0 | 1560463.07 | 13 | 0.8 | 1.22
P003 | Services | SUP007 | 2025-07 | 2025-03-19 | 3829587.73 | 2322163 | -1507424.73 | 1507424.73 | 1 | 2025-07-28 | 2 | 4610334.96 | -780747.23 | DOWN | 0.2039 | 131 | Low | 889525.25 | 0.243 | 0 | 1432637.75 | 13 | 0.8 | 1.22
P003 | Services | SUP007 | 2025-07 | 2025-05-27 | 3310872.41 | 2322163 | -988709.41 | 988709.41 | 1 | 2025-07-28 | 3 | 3829587.73 | -518715.32 | DOWN | 0.1567 | 62 | Low | 1486163.8 | 0.431 | 3 | 835999.2 | 13 | 0.8 | 1.22
P003 | Services | SUP007 | 2025-07 | 2025-05-27 | 3007600.7 | 2322163 | -685437.7 | 685437.7 | 1 | 2025-07-28 | 4 | 3310872.41 | -303271.71 | DOWN | 0.1008 | 62 | Low | 1349227.18 | 0.431 | 4 | 972935.82 | 13 | 0.8 | 1.22
P003 | Electronics | SUP007 | 2025-08 | 2025-04-26 | 348115 | 189793 | -158322 | 158322 | 1 | 2025-08-28 | 1 |  |  |  |  | 124 | Low | 91438.51 | 0.251 | 0 | 98354.49 | 7 | 1.37 | 1.47
P003 | Electronics | SUP007 | 2025-08 | 2025-05-18 | 287436.8 | 189793 | -97643.8 | 97643.8 | 1 | 2025-08-28 | 2 | 348115 | -60678.2 | DOWN | 0.2111 | 102 | Low | 87066.92 | 0.308 | 2 | 102726.08 | 7 | 1.37 | 1.47
P003 | Electronics | SUP007 | 2025-08 | 2025-07-23 | 251077.95 | 189793 | -61284.95 | 61284.95 | 1 | 2025-08-28 | 3 | 287436.8 | -36358.85 | DOWN | 0.1448 | 36 | Low | 124385.97 | 0.48 | 3 | 65407.03 | 7 | 1.37 | 1.47
P003 | Services | SUP007 | 2025-09 | 2025-04-29 | 3241190.66 | 1757786 | -1483404.66 | 1483404.66 | 1 | 2025-09-28 | 1 |  |  |  |  | 152 | Low | 561875.79 | 0.185 | 0 | 1195910.21 | 10 | 0.71 | 1.27
P003 | Services | SUP007 | 2025-09 | 2025-09-07 | 2695970.24 | 1757786 | -938184.24 | 938184.24 | 1 | 2025-09-28 | 2 | 3241190.66 | -545220.42 | DOWN | 0.2022 | 21 | Low | 1367524.15 | 0.543 | 5 | 390261.85 | 10 | 0.71 | 1.27
P003 | Services | SUP007 | 2025-09 | 2025-09-09 | 2330987.05 | 1757786 | -573201.05 | 573201.05 | 1 | 2025-09-28 | 3 | 2695970.24 | -364983.19 | DOWN | 0.1566 | 19 | Low | 1305352.45 | 0.548 | 6 | 452433.55 | 10 | 0.71 | 1.27
P003 | Logistics | SUP007 | 2025-10 | 2025-09-25 | 2942346.35 | 1665874 | -1276472.35 | 1276472.35 | 1 | 2025-10-28 | 1 |  |  |  |  | 33 | Medium | 1394850.22 | 0.51 | 3 | 271023.78 | 19 | 0.95 | 0.98
P003 | Logistics | SUP007 | 2025-10 | 2025-09-27 | 2507131.28 | 1665874 | -841257.28 | 841257.28 | 1 | 2025-10-28 | 2 | 2942346.35 | -435215.07 | DOWN | 0.1736 | 31 | Low | 1230426.73 | 0.515 | 4 | 435447.27 | 19 | 0.95 | 0.98
P003 | Logistics | SUP007 | 2025-10 | 2025-09-30 | 2214543.84 | 1665874 | -548669.84 | 548669.84 | 1 | 2025-10-28 | 3 | 2507131.28 | -292587.44 | DOWN | 0.1321 | 28 | Low | 1230519.97 | 0.524 | 2 | 435354.03 | 19 | 0.95 | 0.98
P003 | Logistics | SUP007 | 2025-10 | 2025-10-06 | 1983592.06 | 1665874 | -317718.06 | 317718.06 | 1 | 2025-10-28 | 4 | 2214543.84 | -230951.78 | DOWN | 0.1164 | 22 | Medium | 1046302.89 | 0.54 | 5 | 619571.11 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP007 | 2025-11 | 2025-08-05 | 2297619.9 | 1679901 | -617718.9 | 617718.9 | 1 | 2025-11-28 | 1 |  |  |  |  | 115 | Low | 552964.02 | 0.26 | 3 | 1126936.98 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP007 | 2025-11 | 2025-08-13 | 2117167.66 | 1679901 | -437266.66 | 437266.66 | 1 | 2025-11-28 | 2 | 2297619.9 | -180452.24 | DOWN | 0.0852 | 107 | Low | 637321.73 | 0.28 | 5 | 1042579.27 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP007 | 2025-11 | 2025-09-10 | 1931642.05 | 1679901 | -251741.05 | 251741.05 | 0 | 2025-11-28 | 3 | 2117167.66 | -185525.61 | DOWN | 0.096 | 79 | Low | 622537.12 | 0.349 | 6 | 1057363.88 | 11 | 1.85 | 1.52
P003 | Logistics | SUP007 | 2025-12 | 2025-08-05 | 3360359.4 | 1661908 | -1698451.4 | 1698451.4 | 1 | 2025-12-28 | 1 |  |  |  |  | 145 | Low | 640725.19 | 0.203 | 4 | 1021182.81 | 10 | 1.08 | 1.22
P003 | Logistics | SUP007 | 2025-12 | 2025-09-02 | 2786604.31 | 1661908 | -1124696.31 | 1124696.31 | 1 | 2025-12-28 | 2 | 3360359.4 | -573755.09 | DOWN | 0.2059 | 117 | Low | 721156.76 | 0.278 | 3 | 940751.24 | 10 | 1.08 | 1.22
P003 | Logistics | SUP007 | 2025-12 | 2025-09-29 | 2405737.1 | 1661908 | -743829.1 | 743829.1 | 1 | 2025-12-28 | 3 | 2786604.31 | -380867.21 | DOWN | 0.1583 | 90 | Low | 860658.33 | 0.351 | 0 | 801249.67 | 10 | 1.08 | 1.22
P003 | Logistics | SUP007 | 2025-12 | 2025-10-08 | 2162144.81 | 1661908 | -500236.81 | 500236.81 | 1 | 2025-12-28 | 4 | 2405737.1 | -243592.29 | DOWN | 0.1127 | 81 | Low | 839236.87 | 0.375 | 1 | 822671.13 | 10 | 1.08 | 1.22
P003 | Logistics | SUP007 | 2025-12 | 2025-12-02 | 1967752.74 | 1661908 | -305844.74 | 305844.74 | 1 | 2025-12-28 | 5 | 2162144.81 | -194392.07 | DOWN | 0.0988 | 26 | Medium | 1066838.92 | 0.524 | 5 | 595069.08 | 10 | 1.08 | 1.22
P003 | Services | SUP037 | 2025-01 | 2024-09-08 | 560716.91 | 341988 | -218728.91 | 218728.91 | 1 | 2025-01-28 | 1 |  |  |  |  | 142 | Low | 134313.17 | 0.251 | 0 | 207674.83 | 17 | 1.86 | 1.34
P003 | Services | SUP037 | 2025-01 | 2024-10-19 | 446063.12 | 341988 | -104075.12 | 104075.12 | 1 | 2025-01-28 | 2 | 560716.91 | -114653.79 | DOWN | 0.257 | 101 | Low | 173090.89 | 0.382 | 4 | 168897.11 | 17 | 1.86 | 1.34
P003 | Services | SUP037 | 2025-01 | 2024-10-26 | 392454.34 | 341988 | -50466.34 | 50466.34 | 0 | 2025-01-28 | 3 | 446063.12 | -53608.78 | DOWN | 0.1366 | 94 | Low | 158352.88 | 0.405 | 1 | 183635.12 | 17 | 1.86 | 1.34
P003 | Services | SUP037 | 2025-01 | 2024-11-25 | 357410.61 | 341988 | -15422.61 | 15422.61 | 0 | 2025-01-28 | 4 | 392454.34 | -35043.73 | DOWN | 0.098 | 64 | Low | 177179.85 | 0.501 | 7 | 164808.15 | 17 | 1.86 | 1.34
P003 | Services | SUP037 | 2025-01 | 2025-01-03 | 354401.24 | 341988 | -12413.24 | 12413.24 | 0 | 2025-01-28 | 5 | 357410.61 | -3009.37 | DOWN | 0.0085 | 25 | Medium | 223434.91 | 0.627 | 4 | 118553.09 | 17 | 1.86 | 1.34
P003 | Materials | SUP037 | 2025-02 | 2024-11-09 | 2315442.85 | 1468508 | -846934.85 | 846934.85 | 1 | 2025-02-28 | 1 |  |  |  |  | 111 | Low | 757997.64 | 0.341 | 3 | 710510.36 | 17 | 2.1 | 1.03
P003 | Materials | SUP037 | 2025-02 | 2024-12-20 | 1861696.09 | 1468508 | -393188.09 | 393188.09 | 1 | 2025-02-28 | 2 | 2315442.85 | -453746.76 | DOWN | 0.2437 | 70 | Low | 916389.85 | 0.47 | 3 | 552118.15 | 17 | 2.1 | 1.03
P003 | Materials | SUP037 | 2025-02 | 2024-12-22 | 1622968.89 | 1468508 | -154460.89 | 154460.89 | 0 | 2025-02-28 | 3 | 1861696.09 | -238727.2 | DOWN | 0.1471 | 68 | Low | 720524.65 | 0.476 | 4 | 747983.35 | 17 | 2.1 | 1.03
P003 | Materials | SUP037 | 2025-02 | 2025-02-18 | 1574304.02 | 1468508 | -105796.02 | 105796.02 | 0 | 2025-02-28 | 4 | 1622968.89 | -48664.87 | DOWN | 0.0309 | 10 | Low | 1022900.8 | 0.655 | 5 | 445607.2 | 17 | 2.1 | 1.03
P003 | Services | SUP037 | 2025-03 | 2024-10-17 | 668280.15 | 405750 | -262530.15 | 262530.15 | 1 | 2025-03-28 | 1 |  |  |  |  | 162 | Low | 132470.16 | 0.202 | 3 | 273279.84 | 13 | 1.13 | 1.73
P003 | Services | SUP037 | 2025-03 | 2024-10-19 | 527179.55 | 405750 | -121429.55 | 121429.55 | 1 | 2025-03-28 | 2 | 668280.15 | -141100.6 | DOWN | 0.2677 | 160 | Low | 102212.28 | 0.209 | 3 | 303537.72 | 13 | 1.13 | 1.73
P003 | Services | SUP037 | 2025-03 | 2024-10-20 | 454582.77 | 405750 | -48832.77 | 48832.77 | 0 | 2025-03-28 | 3 | 527179.55 | -72596.78 | DOWN | 0.1597 | 159 | Low | 98389.2 | 0.213 | 0 | 307360.8 | 13 | 1.13 | 1.73
P003 | Services | SUP037 | 2025-03 | 2025-02-08 | 433647.73 | 405750 | -27897.73 | 27897.73 | 0 | 2025-03-28 | 4 | 454582.77 | -20935.04 | DOWN | 0.0483 | 48 | Medium | 256765.17 | 0.6 | 3 | 148984.83 | 13 | 1.13 | 1.73
P003 | Materials | SUP037 | 2025-04 | 2025-01-15 | 1584203.16 | 1303615 | -280588.16 | 280588.16 | 1 | 2025-04-28 | 1 |  |  |  |  | 103 | Low | 632187.89 | 0.405 | 5 | 671427.11 | 13 | 1.21 | 1.27
P003 | Materials | SUP037 | 2025-04 | 2025-01-22 | 1440982.64 | 1303615 | -137367.64 | 137367.64 | 0 | 2025-04-28 | 2 | 1584203.16 | -143220.52 | DOWN | 0.0994 | 96 | Low | 656555.46 | 0.429 | 5 | 647059.54 | 13 | 1.21 | 1.27
P003 | Materials | SUP037 | 2025-04 | 2025-02-24 | 1365428.14 | 1303615 | -61813.14 | 61813.14 | 0 | 2025-04-28 | 3 | 1440982.64 | -75554.5 | DOWN | 0.0553 | 63 | Low | 767147.51 | 0.543 | 2 | 536467.49 | 13 | 1.21 | 1.27
P003 | Materials | SUP037 | 2025-04 | 2025-03-06 | 1319170.14 | 1303615 | -15555.14 | 15555.14 | 0 | 2025-04-28 | 4 | 1365428.14 | -46258 | DOWN | 0.0351 | 53 | Medium | 777697.49 | 0.578 | 7 | 525917.51 | 13 | 1.21 | 1.27
P003 | Services | SUP037 | 2025-05 | 2025-03-05 | 3447646.79 | 2294802 | -1152844.79 | 1152844.79 | 1 | 2025-05-28 | 1 |  |  |  |  | 84 | Low | 1513807.44 | 0.462 | 1 | 780994.56 | 14 | 1.36 | 1.73
P003 | Services | SUP037 | 2025-05 | 2025-03-14 | 2863565.77 | 2294802 | -568763.77 | 568763.77 | 1 | 2025-05-28 | 2 | 3447646.79 | -584081.02 | DOWN | 0.204 | 75 | Low | 1408237.26 | 0.493 | 8 | 886564.74 | 14 | 1.36 | 1.73
P003 | Services | SUP037 | 2025-05 | 2025-05-17 | 2591385.97 | 2294802 | -296583.97 | 296583.97 | 0 | 2025-05-28 | 3 | 2863565.77 | -272179.8 | DOWN | 0.105 | 11 | Medium | 1784919.96 | 0.71 | 6 | 509882.04 | 14 | 1.36 | 1.73
P003 | Logistics | SUP037 | 2025-06 | 2025-03-20 | 4238206.8 | 2728693 | -1509513.8 | 1509513.8 | 1 | 2025-06-28 | 1 |  |  |  |  | 100 | Low | 1688669.16 | 0.403 | 5 | 1040023.84 | 22 | 1.47 | 1.51
P003 | Logistics | SUP037 | 2025-06 | 2025-03-26 | 3429239.52 | 2728693 | -700546.52 | 700546.52 | 1 | 2025-06-28 | 2 | 4238206.8 | -808967.28 | DOWN | 0.2359 | 94 | Low | 1534865.67 | 0.423 | 3 | 1193827.33 | 22 | 1.47 | 1.51
P003 | Logistics | SUP037 | 2025-06 | 2025-04-01 | 3079528.64 | 2728693 | -350835.64 | 350835.64 | 0 | 2025-06-28 | 3 | 3429239.52 | -349710.88 | DOWN | 0.1136 | 88 | Low | 1309372.01 | 0.443 | 5 | 1419320.99 | 22 | 1.47 | 1.51
P003 | Logistics | SUP037 | 2025-06 | 2025-04-06 | 2894092.45 | 2728693 | -165399.45 | 165399.45 | 0 | 2025-06-28 | 4 | 3079528.64 | -185436.19 | DOWN | 0.0641 | 83 | Low | 1273641.07 | 0.46 | 6 | 1455051.93 | 22 | 1.47 | 1.51
P003 | Services | SUP037 | 2025-07 | 2025-04-03 | 3377460.68 | 2466818 | -910642.68 | 910642.68 | 1 | 2025-07-28 | 1 |  |  |  |  | 116 | Low | 1333922.91 | 0.369 | 0 | 1132895.09 | 13 | 0.8 | 1.22
P003 | Services | SUP037 | 2025-07 | 2025-04-28 | 2831202.29 | 2466818 | -364384.29 | 364384.29 | 0 | 2025-07-28 | 2 | 3377460.68 | -546258.39 | DOWN | 0.1929 | 91 | Low | 1325943.7 | 0.457 | 1 | 1140874.3 | 13 | 0.8 | 1.22
P003 | Services | SUP037 | 2025-07 | 2025-05-06 | 2657968.16 | 2466818 | -191150.16 | 191150.16 | 0 | 2025-07-28 | 3 | 2831202.29 | -173234.13 | DOWN | 0.0652 | 83 | Low | 1192966.62 | 0.486 | 0 | 1273851.38 | 13 | 0.8 | 1.22
P003 | Logistics | SUP037 | 2025-08 | 2025-03-26 | 1815044.71 | 1117815 | -697229.71 | 697229.71 | 1 | 2025-08-28 | 1 |  |  |  |  | 155 | Low | 421141.76 | 0.221 | 1 | 696673.24 | 7 | 1.37 | 1.47
P003 | Logistics | SUP037 | 2025-08 | 2025-04-05 | 1428274.42 | 1117815 | -310459.42 | 310459.42 | 1 | 2025-08-28 | 2 | 1815044.71 | -386770.29 | DOWN | 0.2708 | 145 | Low | 383290.8 | 0.255 | 1 | 734524.2 | 7 | 1.37 | 1.47
P003 | Logistics | SUP037 | 2025-08 | 2025-05-05 | 1245417.62 | 1117815 | -127602.62 | 127602.62 | 0 | 2025-08-28 | 3 | 1428274.42 | -182856.8 | DOWN | 0.1468 | 115 | Low | 435248.43 | 0.356 | 2 | 682566.57 | 7 | 1.37 | 1.47
P003 | Logistics | SUP037 | 2025-08 | 2025-06-29 | 1172944.78 | 1117815 | -55129.78 | 55129.78 | 0 | 2025-08-28 | 4 | 1245417.62 | -72472.84 | DOWN | 0.0618 | 60 | Medium | 653103.03 | 0.543 | 2 | 464711.97 | 7 | 1.37 | 1.47
P003 | Materials | SUP037 | 2025-09 | 2025-05-26 | 1208773.69 | 884501 | -324272.69 | 324272.69 | 1 | 2025-09-28 | 1 |  |  |  |  | 125 | Low | 386814.21 | 0.337 | 0 | 497686.79 | 10 | 0.71 | 1.27
P003 | Materials | SUP037 | 2025-09 | 2025-06-10 | 1025168.51 | 884501 | -140667.51 | 140667.51 | 0 | 2025-09-28 | 2 | 1208773.69 | -183605.18 | DOWN | 0.1791 | 110 | Low | 408631.32 | 0.39 | 2 | 475869.68 | 10 | 0.71 | 1.27
P003 | Materials | SUP037 | 2025-09 | 2025-07-18 | 951738.07 | 884501 | -67237.07 | 67237.07 | 0 | 2025-09-28 | 3 | 1025168.51 | -73430.44 | DOWN | 0.0772 | 72 | Low | 534533.87 | 0.525 | 1 | 349967.13 | 10 | 0.71 | 1.27
P003 | Materials | SUP037 | 2025-09 | 2025-08-22 | 913886.03 | 884501 | -29385.03 | 29385.03 | 0 | 2025-09-28 | 4 | 951738.07 | -37852.04 | DOWN | 0.0414 | 37 | Medium | 584484.53 | 0.649 | 6 | 300016.47 | 10 | 0.71 | 1.27
P003 | Materials | SUP037 | 2025-09 | 2025-08-30 | 903825.61 | 884501 | -19324.61 | 19324.61 | 0 | 2025-09-28 | 5 | 913886.03 | -10060.42 | DOWN | 0.0111 | 29 | High | 593290.03 | 0.677 | 6 | 291210.97 | 10 | 0.71 | 1.27
P003 | Materials | SUP037 | 2025-09 | 2025-09-05 | 893835.98 | 884501 | -9334.98 | 9334.98 | 0 | 2025-09-28 | 6 | 903825.61 | -9989.63 | DOWN | 0.0112 | 23 | High | 666623.32 | 0.698 | 5 | 217877.68 | 10 | 0.71 | 1.27
P003 | Electronics | SUP037 | 2025-10 | 2025-05-15 | 4169467.15 | 2921392 | -1248075.15 | 1248075.15 | 1 | 2025-10-28 | 1 |  |  |  |  | 166 | Low | 847405.16 | 0.191 | 4 | 2073986.84 | 19 | 0.95 | 0.98
P003 | Electronics | SUP037 | 2025-10 | 2025-05-27 | 3442982.23 | 2921392 | -521590.23 | 521590.23 | 1 | 2025-10-28 | 2 | 4169467.15 | -726484.92 | DOWN | 0.211 | 154 | Low | 770333.97 | 0.234 | 0 | 2151058.03 | 19 | 0.95 | 0.98
P003 | Electronics | SUP037 | 2025-10 | 2025-06-03 | 3140221.04 | 2921392 | -218829.04 | 218829.04 | 0 | 2025-10-28 | 3 | 3442982.23 | -302761.19 | DOWN | 0.0964 | 147 | Low | 819852.83 | 0.259 | 0 | 2101539.17 | 19 | 0.95 | 0.98
P003 | Electronics | SUP037 | 2025-10 | 2025-06-09 | 3034802.38 | 2921392 | -113410.38 | 113410.38 | 0 | 2025-10-28 | 4 | 3140221.04 | -105418.66 | DOWN | 0.0347 | 141 | Low | 872993.38 | 0.28 | 8 | 2048398.62 | 19 | 0.95 | 0.98
P003 | Electronics | SUP037 | 2025-10 | 2025-07-20 | 2949579.95 | 2921392 | -28187.95 | 28187.95 | 0 | 2025-10-28 | 5 | 3034802.38 | -85222.43 | DOWN | 0.0289 | 100 | Low | 1224098.2 | 0.425 | 3 | 1697293.8 | 19 | 0.95 | 0.98
P003 | Services | SUP037 | 2025-11 | 2025-06-28 | 936991.89 | 577573 | -359418.89 | 359418.89 | 1 | 2025-11-28 | 1 |  |  |  |  | 153 | Low | 208541.81 | 0.216 | 0 | 369031.19 | 11 | 1.85 | 1.52
P003 | Services | SUP037 | 2025-11 | 2025-07-15 | 723938.34 | 577573 | -146365.34 | 146365.34 | 1 | 2025-11-28 | 2 | 936991.89 | -213053.55 | DOWN | 0.2943 | 136 | Low | 209209.34 | 0.27 | 4 | 368363.66 | 11 | 1.85 | 1.52
P003 | Services | SUP037 | 2025-11 | 2025-07-23 | 635308.67 | 577573 | -57735.67 | 57735.67 | 0 | 2025-11-28 | 3 | 723938.34 | -88629.67 | DOWN | 0.1395 | 128 | Low | 187618.37 | 0.296 | 3 | 389954.63 | 11 | 1.85 | 1.52
P003 | Services | SUP037 | 2025-11 | 2025-08-31 | 588867.61 | 577573 | -11294.61 | 11294.61 | 0 | 2025-11-28 | 4 | 635308.67 | -46441.06 | DOWN | 0.0789 | 89 | Low | 233482.11 | 0.421 | 2 | 344090.89 | 11 | 1.85 | 1.52
P003 | Services | SUP037 | 2025-11 | 2025-10-09 | 589307.77 | 577573 | -11734.77 | 11734.77 | 0 | 2025-11-28 | 5 | 588867.61 | 440.16 | UP | 0.0007 | 50 | Medium | 311673.61 | 0.547 | 7 | 265899.39 | 11 | 1.85 | 1.52
P003 | Services | SUP037 | 2025-11 | 2025-10-19 | 581615.53 | 577573 | -4042.53 | 4042.53 | 0 | 2025-11-28 | 6 | 589307.77 | -7692.24 | DOWN | 0.0132 | 40 | Medium | 327070.66 | 0.579 | 2 | 250502.34 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP037 | 2025-12 | 2025-07-15 | 1217834.18 | 826719 | -391115.18 | 391115.18 | 1 | 2025-12-28 | 1 |  |  |  |  | 166 | Low | 225581.54 | 0.19 | 0 | 601137.46 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP037 | 2025-12 | 2025-07-18 | 1005704.58 | 826719 | -178985.58 | 178985.58 | 1 | 2025-12-28 | 2 | 1217834.18 | -212129.6 | DOWN | 0.2109 | 163 | Low | 207780.02 | 0.2 | 0 | 618938.98 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP037 | 2025-12 | 2025-09-08 | 907554.26 | 826719 | -80835.26 | 80835.26 | 0 | 2025-12-28 | 3 | 1005704.58 | -98150.32 | DOWN | 0.1081 | 111 | Low | 320325.77 | 0.383 | 4 | 506393.23 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP037 | 2025-12 | 2025-11-23 | 866104.16 | 826719 | -39385.16 | 39385.16 | 0 | 2025-12-28 | 4 | 907554.26 | -41450.1 | DOWN | 0.0479 | 35 | Medium | 592968.81 | 0.65 | 11 | 233750.19 | 10 | 1.08 | 1.22
P003 | Logistics | SUP025 | 2025-01 | 2024-09-04 | 3603672.03 | 1955590 | -1648082.03 | 1648082.03 | 1 | 2025-01-28 | 1 |  |  |  |  | 146 | Low | 556992.97 | 0.168 | 0 | 1398597.03 | 17 | 1.86 | 1.34
P003 | Logistics | SUP025 | 2025-01 | 2024-10-08 | 3007381.88 | 1955590 | -1051791.88 | 1051791.88 | 1 | 2025-01-28 | 2 | 3603672.03 | -596290.15 | DOWN | 0.1983 | 112 | Low | 755589.66 | 0.245 | 2 | 1200000.34 | 17 | 1.86 | 1.34
P003 | Logistics | SUP025 | 2025-01 | 2024-12-03 | 2554138.11 | 1955590 | -598548.11 | 598548.11 | 1 | 2025-01-28 | 3 | 3007381.88 | -453243.77 | DOWN | 0.1775 | 56 | Low | 913169.36 | 0.372 | 5 | 1042420.64 | 17 | 1.86 | 1.34
P003 | Logistics | SUP025 | 2025-01 | 2024-12-17 | 2378830.48 | 1955590 | -423240.48 | 423240.48 | 1 | 2025-01-28 | 4 | 2554138.11 | -175307.63 | DOWN | 0.0737 | 42 | Low | 994383.05 | 0.403 | 3 | 961206.95 | 17 | 1.86 | 1.34
P003 | Logistics | SUP025 | 2025-02 | 2024-09-20 | 2362133.17 | 1338110 | -1024023.17 | 1024023.17 | 1 | 2025-02-28 | 1 |  |  |  |  | 161 | Low | 291367.01 | 0.13 | 1 | 1046742.99 | 17 | 2.1 | 1.03
P003 | Logistics | SUP025 | 2025-02 | 2024-09-26 | 1939456.87 | 1338110 | -601346.87 | 601346.87 | 1 | 2025-02-28 | 2 | 2362133.17 | -422676.3 | DOWN | 0.2179 | 155 | Low | 261700.61 | 0.144 | 1 | 1076409.39 | 17 | 2.1 | 1.03
P003 | Logistics | SUP025 | 2025-02 | 2024-12-31 | 1697429.95 | 1338110 | -359319.95 | 359319.95 | 1 | 2025-02-28 | 3 | 1939456.87 | -242026.92 | DOWN | 0.1426 | 59 | Low | 613957.74 | 0.356 | 0 | 724152.26 | 17 | 2.1 | 1.03
P003 | Logistics | SUP025 | 2025-02 | 2025-02-04 | 1560477.78 | 1338110 | -222367.78 | 222367.78 | 0 | 2025-02-28 | 4 | 1697429.95 | -136952.17 | DOWN | 0.0878 | 24 | Low | 685620.67 | 0.433 | 6 | 652489.33 | 17 | 2.1 | 1.03
P003 | Materials | SUP025 | 2025-03 | 2024-10-06 | 399644.59 | 246107 | -153537.59 | 153537.59 | 1 | 2025-03-28 | 1 |  |  |  |  | 173 | Low | 44648.06 | 0.116 | 2 | 201458.94 | 13 | 1.13 | 1.73
P003 | Materials | SUP025 | 2025-03 | 2024-10-29 | 337099.37 | 246107 | -90992.37 | 90992.37 | 1 | 2025-03-28 | 2 | 399644.59 | -62545.22 | DOWN | 0.1855 | 150 | Low | 59594.67 | 0.172 | 1 | 186512.33 | 13 | 1.13 | 1.73
P003 | Materials | SUP025 | 2025-03 | 2024-12-13 | 302796.66 | 246107 | -56689.66 | 56689.66 | 1 | 2025-03-28 | 3 | 337099.37 | -34302.71 | DOWN | 0.1133 | 105 | Low | 87288.04 | 0.283 | 1 | 158818.96 | 13 | 1.13 | 1.73
P003 | Materials | SUP025 | 2025-03 | 2024-12-28 | 278525.25 | 246107 | -32418.25 | 32418.25 | 0 | 2025-03-28 | 4 | 302796.66 | -24271.41 | DOWN | 0.0871 | 90 | Low | 89835.22 | 0.32 | 1 | 156271.78 | 13 | 1.13 | 1.73
P003 | Materials | SUP025 | 2025-03 | 2025-01-05 | 265360.81 | 246107 | -19253.81 | 19253.81 | 0 | 2025-03-28 | 5 | 278525.25 | -13164.44 | DOWN | 0.0496 | 82 | Low | 89248.76 | 0.34 | 0 | 156858.24 | 13 | 1.13 | 1.73
P003 | Materials | SUP025 | 2025-03 | 2025-03-04 | 257344.4 | 246107 | -11237.4 | 11237.4 | 0 | 2025-03-28 | 6 | 265360.81 | -8016.41 | DOWN | 0.0312 | 24 | Low | 129096.72 | 0.482 | 6 | 117010.28 | 13 | 1.13 | 1.73
P003 | Software | SUP025 | 2025-04 | 2024-12-29 | 1944373.07 | 1301012 | -643361.07 | 643361.07 | 1 | 2025-04-28 | 1 |  |  |  |  | 120 | Low | 505763.81 | 0.244 | 3 | 795248.19 | 13 | 1.21 | 1.27
P003 | Software | SUP025 | 2025-04 | 2025-02-11 | 1727539.59 | 1301012 | -426527.59 | 426527.59 | 1 | 2025-04-28 | 2 | 1944373.07 | -216833.48 | DOWN | 0.1255 | 76 | Low | 560492.85 | 0.351 | 4 | 740519.15 | 13 | 1.21 | 1.27
P003 | Software | SUP025 | 2025-04 | 2025-02-21 | 1558840.25 | 1301012 | -257828.25 | 257828.25 | 1 | 2025-04-28 | 3 | 1727539.59 | -168699.34 | DOWN | 0.1082 | 66 | Low | 596688.64 | 0.376 | 1 | 704323.36 | 13 | 1.21 | 1.27
P003 | Software | SUP025 | 2025-04 | 2025-03-12 | 1453039.16 | 1301012 | -152027.16 | 152027.16 | 0 | 2025-04-28 | 4 | 1558840.25 | -105801.09 | DOWN | 0.0728 | 47 | Low | 616963.94 | 0.422 | 3 | 684048.06 | 13 | 1.21 | 1.27
P003 | Software | SUP025 | 2025-04 | 2025-03-14 | 1398171.13 | 1301012 | -97159.13 | 97159.13 | 0 | 2025-04-28 | 5 | 1453039.16 | -54868.03 | DOWN | 0.0392 | 45 | Low | 572036.46 | 0.427 | 3 | 728975.54 | 13 | 1.21 | 1.27
P003 | Logistics | SUP025 | 2025-05 | 2025-03-08 | 429758.64 | 252046 | -177712.64 | 177712.64 | 1 | 2025-05-28 | 1 |  |  |  |  | 81 | Low | 144321.34 | 0.333 | 1 | 107724.66 | 14 | 1.36 | 1.73
P003 | Logistics | SUP025 | 2025-05 | 2025-03-22 | 363809.03 | 252046 | -111763.03 | 111763.03 | 1 | 2025-05-28 | 2 | 429758.64 | -65949.61 | DOWN | 0.1813 | 67 | Low | 137842.57 | 0.367 | 5 | 114203.43 | 14 | 1.36 | 1.73
P003 | Logistics | SUP025 | 2025-05 | 2025-04-19 | 313830.96 | 252046 | -61784.96 | 61784.96 | 1 | 2025-05-28 | 3 | 363809.03 | -49978.07 | DOWN | 0.1593 | 39 | Low | 138253.82 | 0.434 | 5 | 113792.18 | 14 | 1.36 | 1.73
P003 | Logistics | SUP025 | 2025-05 | 2025-05-03 | 287514.97 | 252046 | -35468.97 | 35468.97 | 0 | 2025-05-28 | 4 | 313830.96 | -26315.99 | DOWN | 0.0915 | 25 | Low | 133941.84 | 0.467 | 3 | 118104.16 | 14 | 1.36 | 1.73
P003 | Logistics | SUP025 | 2025-05 | 2025-05-16 | 267587.04 | 252046 | -15541.04 | 15541.04 | 0 | 2025-05-28 | 5 | 287514.97 | -19927.93 | DOWN | 0.0745 | 12 | Low | 131974.97 | 0.498 | 1 | 120071.03 | 14 | 1.36 | 1.73
P003 | Logistics | SUP025 | 2025-06 | 2025-02-02 | 3065246.68 | 1610575 | -1454671.68 | 1454671.68 | 1 | 2025-06-28 | 1 |  |  |  |  | 146 | Low | 523044.13 | 0.175 | 4 | 1087530.87 | 22 | 1.47 | 1.51
P003 | Logistics | SUP025 | 2025-06 | 2025-03-05 | 2483738.16 | 1610575 | -873163.16 | 873163.16 | 1 | 2025-06-28 | 2 | 3065246.68 | -581508.52 | DOWN | 0.2341 | 115 | Low | 590951.13 | 0.248 | 4 | 1019623.87 | 22 | 1.47 | 1.51
P003 | Logistics | SUP025 | 2025-06 | 2025-03-25 | 2107702.21 | 1610575 | -497127.21 | 497127.21 | 1 | 2025-06-28 | 3 | 2483738.16 | -376035.95 | DOWN | 0.1784 | 95 | Low | 621384.95 | 0.296 | 0 | 989190.05 | 22 | 1.47 | 1.51
P003 | Logistics | SUP025 | 2025-06 | 2025-05-10 | 1890157.1 | 1610575 | -279582.1 | 279582.1 | 0 | 2025-06-28 | 4 | 2107702.21 | -217545.11 | DOWN | 0.1151 | 49 | Low | 778929.49 | 0.405 | 6 | 831645.51 | 22 | 1.47 | 1.51
P003 | Logistics | SUP025 | 2025-07 | 2025-02-10 | 707657.2 | 385940 | -321717.2 | 321717.2 | 1 | 2025-07-28 | 1 |  |  |  |  | 168 | Low | 97762.58 | 0.13 | 1 | 288177.42 | 13 | 0.8 | 1.22
P003 | Logistics | SUP025 | 2025-07 | 2025-03-11 | 568761.89 | 385940 | -182821.89 | 182821.89 | 1 | 2025-07-28 | 2 | 707657.2 | -138895.31 | DOWN | 0.2442 | 139 | Low | 111320.46 | 0.203 | 0 | 274619.54 | 13 | 0.8 | 1.22
P003 | Logistics | SUP025 | 2025-07 | 2025-03-30 | 501168.78 | 385940 | -115228.78 | 115228.78 | 1 | 2025-07-28 | 3 | 568761.89 | -67593.11 | DOWN | 0.1349 | 120 | Low | 127996.42 | 0.25 | 0 | 257943.58 | 13 | 0.8 | 1.22
P003 | Logistics | SUP025 | 2025-07 | 2025-07-13 | 444970.94 | 385940 | -59030.94 | 59030.94 | 0 | 2025-07-28 | 4 | 501168.78 | -56197.84 | DOWN | 0.1263 | 15 | Low | 221258.98 | 0.513 | 3 | 164681.02 | 13 | 0.8 | 1.22
P003 | Logistics | SUP025 | 2025-07 | 2025-07-15 | 426271.71 | 385940 | -40331.71 | 40331.71 | 0 | 2025-07-28 | 5 | 444970.94 | -18699.23 | DOWN | 0.0439 | 13 | Low | 213395.58 | 0.518 | 4 | 172544.42 | 13 | 0.8 | 1.22
P003 | Materials | SUP025 | 2025-08 | 2025-03-01 | 949775.44 | 572839 | -376936.44 | 376936.44 | 1 | 2025-08-28 | 1 |  |  |  |  | 180 | Low | 103996.38 | 0.105 | 0 | 468842.62 | 7 | 1.37 | 1.47
P003 | Materials | SUP025 | 2025-08 | 2025-04-22 | 790814.68 | 572839 | -217975.68 | 217975.68 | 1 | 2025-08-28 | 2 | 949775.44 | -158960.76 | DOWN | 0.201 | 128 | Low | 161960.75 | 0.22 | 0 | 410878.25 | 7 | 1.37 | 1.47
P003 | Materials | SUP025 | 2025-08 | 2025-04-28 | 713357.3 | 572839 | -140518.3 | 140518.3 | 1 | 2025-08-28 | 3 | 790814.68 | -77457.38 | DOWN | 0.1086 | 122 | Low | 156725.6 | 0.235 | 0 | 416113.4 | 7 | 1.37 | 1.47
P003 | Materials | SUP025 | 2025-08 | 2025-06-07 | 652203.6 | 572839 | -79364.6 | 79364.6 | 0 | 2025-08-28 | 4 | 713357.3 | -61153.7 | DOWN | 0.0938 | 82 | Low | 225461.51 | 0.33 | 4 | 347377.49 | 7 | 1.37 | 1.47
P003 | Materials | SUP025 | 2025-08 | 2025-06-17 | 616937.84 | 572839 | -44098.84 | 44098.84 | 0 | 2025-08-28 | 5 | 652203.6 | -35265.76 | DOWN | 0.0572 | 72 | Low | 233369.83 | 0.354 | 7 | 339469.17 | 7 | 1.37 | 1.47
P003 | Logistics | SUP025 | 2025-09 | 2025-04-23 | 2144877.02 | 1430044 | -714833.02 | 714833.02 | 1 | 2025-09-28 | 1 |  |  |  |  | 158 | Low | 357049.28 | 0.155 | 0 | 1072994.72 | 10 | 0.71 | 1.27
P003 | Logistics | SUP025 | 2025-09 | 2025-04-28 | 1879964.51 | 1430044 | -449920.51 | 449920.51 | 1 | 2025-09-28 | 2 | 2144877.02 | -264912.51 | DOWN | 0.1409 | 153 | Low | 332756.96 | 0.168 | 1 | 1097287.04 | 10 | 0.71 | 1.27
P003 | Logistics | SUP025 | 2025-09 | 2025-05-17 | 1684583.82 | 1430044 | -254539.82 | 254539.82 | 1 | 2025-09-28 | 3 | 1879964.51 | -195380.69 | DOWN | 0.116 | 134 | Low | 386927.03 | 0.215 | 2 | 1043116.97 | 10 | 0.71 | 1.27
P003 | Logistics | SUP025 | 2025-09 | 2025-07-23 | 1559773.65 | 1430044 | -129729.65 | 129729.65 | 0 | 2025-09-28 | 4 | 1684583.82 | -124810.17 | DOWN | 0.08 | 67 | Low | 589246.41 | 0.383 | 2 | 840797.59 | 10 | 0.71 | 1.27
P003 | Logistics | SUP025 | 2025-10 | 2025-06-08 | 3562775.67 | 2186799 | -1375976.67 | 1375976.67 | 1 | 2025-10-28 | 1 |  |  |  |  | 142 | Low | 644137.79 | 0.195 | 5 | 1542661.21 | 19 | 0.95 | 0.98
P003 | Logistics | SUP025 | 2025-10 | 2025-07-29 | 3074764.92 | 2186799 | -887965.92 | 887965.92 | 1 | 2025-10-28 | 2 | 3562775.67 | -488010.75 | DOWN | 0.1587 | 91 | Low | 934387.51 | 0.323 | 2 | 1252411.49 | 19 | 0.95 | 0.98
P003 | Logistics | SUP025 | 2025-10 | 2025-08-13 | 2776397.15 | 2186799 | -589598.15 | 589598.15 | 1 | 2025-10-28 | 3 | 3074764.92 | -298367.77 | DOWN | 0.1075 | 76 | Low | 990034.41 | 0.36 | 3 | 1196764.59 | 19 | 0.95 | 0.98
P003 | Logistics | SUP025 | 2025-10 | 2025-09-28 | 2501251.22 | 2186799 | -314452.22 | 314452.22 | 0 | 2025-10-28 | 4 | 2776397.15 | -275145.93 | DOWN | 0.11 | 30 | Low | 1262727.96 | 0.475 | 2 | 924071.04 | 19 | 0.95 | 0.98
P003 | Electronics | SUP025 | 2025-11 | 2025-06-06 | 2075018.67 | 1064997 | -1010021.67 | 1010021.67 | 1 | 2025-11-28 | 1 |  |  |  |  | 175 | Low | 202001.19 | 0.102 | 0 | 862995.81 | 11 | 1.85 | 1.52
P003 | Electronics | SUP025 | 2025-11 | 2025-06-29 | 1699706.78 | 1064997 | -634709.78 | 634709.78 | 1 | 2025-11-28 | 2 | 2075018.67 | -375311.89 | DOWN | 0.2208 | 152 | Low | 264649.78 | 0.154 | 3 | 800347.22 | 11 | 1.85 | 1.52
P003 | Electronics | SUP025 | 2025-11 | 2025-07-03 | 1406959.11 | 1064997 | -341962.11 | 341962.11 | 1 | 2025-11-28 | 3 | 1699706.78 | -292747.67 | DOWN | 0.2081 | 148 | Low | 225940.41 | 0.163 | 1 | 839056.59 | 11 | 1.85 | 1.52
P003 | Electronics | SUP025 | 2025-11 | 2025-08-17 | 1299852.33 | 1064997 | -234855.33 | 234855.33 | 1 | 2025-11-28 | 4 | 1406959.11 | -107106.78 | DOWN | 0.0824 | 103 | Low | 321132.05 | 0.265 | 6 | 743864.95 | 11 | 1.85 | 1.52
P003 | Electronics | SUP025 | 2025-11 | 2025-10-10 | 1213367.98 | 1064997 | -148370.98 | 148370.98 | 0 | 2025-11-28 | 5 | 1299852.33 | -86484.35 | DOWN | 0.0713 | 49 | Low | 465329.07 | 0.388 | 3 | 599667.93 | 11 | 1.85 | 1.52
P003 | Services | SUP025 | 2025-12 | 2025-08-28 | 1569777.05 | 854640 | -715137.05 | 715137.05 | 1 | 2025-12-28 | 1 |  |  |  |  | 122 | Low | 391985.72 | 0.243 | 1 | 462654.28 | 10 | 1.08 | 1.22
P003 | Services | SUP025 | 2025-12 | 2025-09-05 | 1267812.66 | 854640 | -413172.66 | 413172.66 | 1 | 2025-12-28 | 2 | 1569777.05 | -301964.39 | DOWN | 0.2382 | 114 | Low | 323683.2 | 0.262 | 4 | 530956.8 | 10 | 1.08 | 1.22
P003 | Services | SUP025 | 2025-12 | 2025-09-09 | 1100543.06 | 854640 | -245903.06 | 245903.06 | 1 | 2025-12-28 | 3 | 1267812.66 | -167269.6 | DOWN | 0.152 | 110 | Low | 291802.9 | 0.272 | 3 | 562837.1 | 10 | 1.08 | 1.22
P003 | Logistics | SUP043 | 2025-01 | 2024-10-12 | 5015367.16 | 2379330 | -2636037.16 | 2636037.16 | 1 | 2025-01-28 | 1 |  |  |  |  | 108 | Low | 1421919.17 | 0.3 | 3 | 957410.83 | 17 | 1.86 | 1.34
P003 | Logistics | SUP043 | 2025-01 | 2024-10-22 | 3752917.52 | 2379330 | -1373587.52 | 1373587.52 | 1 | 2025-01-28 | 2 | 5015367.16 | -1262449.64 | DOWN | 0.3364 | 98 | Low | 1244128.6 | 0.327 | 3 | 1135201.4 | 17 | 1.86 | 1.34
P003 | Logistics | SUP043 | 2025-01 | 2024-11-14 | 3224561.21 | 2379330 | -845231.21 | 845231.21 | 1 | 2025-01-28 | 3 | 3752917.52 | -528356.31 | DOWN | 0.1639 | 75 | Low | 1346025.32 | 0.388 | 3 | 1033304.68 | 17 | 1.86 | 1.34
P003 | Logistics | SUP043 | 2025-01 | 2024-11-14 | 2843589.56 | 2379330 | -464259.56 | 464259.56 | 1 | 2025-01-28 | 4 | 3224561.21 | -380971.65 | DOWN | 0.134 | 75 | Low | 1061070.49 | 0.388 | 3 | 1318259.51 | 17 | 1.86 | 1.34
P003 | Logistics | SUP043 | 2025-01 | 2024-12-26 | 2582152.21 | 2379330 | -202822.21 | 202822.21 | 0 | 2025-01-28 | 5 | 2843589.56 | -261437.35 | DOWN | 0.1012 | 33 | Medium | 1321569.54 | 0.501 | 0 | 1057760.46 | 17 | 1.86 | 1.34
P003 | Logistics | SUP043 | 2025-02 | 2024-09-19 | 2058450.01 | 965827 | -1092623.01 | 1092623.01 | 1 | 2025-02-28 | 1 |  |  |  |  | 162 | Low | 318830.47 | 0.151 | 3 | 646996.53 | 17 | 2.1 | 1.03
P003 | Logistics | SUP043 | 2025-02 | 2024-09-24 | 1559898.6 | 965827 | -594071.6 | 594071.6 | 1 | 2025-02-28 | 2 | 2058450.01 | -498551.41 | DOWN | 0.3196 | 157 | Low | 239723.8 | 0.164 | 0 | 726103.2 | 17 | 2.1 | 1.03
P003 | Logistics | SUP043 | 2025-02 | 2024-10-16 | 1269611.09 | 965827 | -303784.09 | 303784.09 | 1 | 2025-02-28 | 3 | 1559898.6 | -290287.51 | DOWN | 0.2286 | 135 | Low | 263654.27 | 0.222 | 3 | 702172.73 | 17 | 2.1 | 1.03
P003 | Logistics | SUP043 | 2025-02 | 2024-11-02 | 1093164.42 | 965827 | -127337.42 | 127337.42 | 0 | 2025-02-28 | 4 | 1269611.09 | -176446.67 | DOWN | 0.1614 | 118 | Low | 304120.93 | 0.266 | 0 | 661706.07 | 17 | 2.1 | 1.03
P003 | Logistics | SUP043 | 2025-02 | 2025-02-09 | 1061842.64 | 965827 | -96015.64 | 96015.64 | 0 | 2025-02-28 | 5 | 1093164.42 | -31321.78 | DOWN | 0.0295 | 19 | Low | 513843.87 | 0.525 | 5 | 451983.13 | 17 | 2.1 | 1.03
P003 | Logistics | SUP043 | 2025-03 | 2024-12-10 | 2987593.51 | 1378952 | -1608641.51 | 1608641.51 | 1 | 2025-03-28 | 1 |  |  |  |  | 108 | Low | 941987.11 | 0.326 | 5 | 436964.89 | 13 | 1.13 | 1.73
P003 | Logistics | SUP043 | 2025-03 | 2025-01-19 | 2268147.82 | 1378952 | -889195.82 | 889195.82 | 1 | 2025-03-28 | 2 | 2987593.51 | -719445.69 | DOWN | 0.3172 | 68 | Low | 1043625.59 | 0.442 | 5 | 335326.41 | 13 | 1.13 | 1.73
P003 | Logistics | SUP043 | 2025-03 | 2025-02-18 | 1858163.73 | 1378952 | -479211.73 | 479211.73 | 1 | 2025-03-28 | 3 | 2268147.82 | -409984.09 | DOWN | 0.2206 | 38 | Low | 915586.94 | 0.529 | 2 | 463365.06 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP043 | 2025-04 | 2024-11-05 | 2402731.33 | 1390140 | -1012591.33 | 1012591.33 | 1 | 2025-04-28 | 1 |  |  |  |  | 174 | Low | 296175.49 | 0.133 | 3 | 1093964.51 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP043 | 2025-04 | 2024-11-14 | 1952546.83 | 1390140 | -562406.83 | 562406.83 | 1 | 2025-04-28 | 2 | 2402731.33 | -450184.5 | DOWN | 0.2306 | 165 | Low | 332217.46 | 0.159 | 4 | 1057922.54 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP043 | 2025-04 | 2024-11-28 | 1705143.66 | 1390140 | -315003.66 | 315003.66 | 1 | 2025-04-28 | 3 | 1952546.83 | -247403.17 | DOWN | 0.1451 | 151 | Low | 360619.73 | 0.199 | 1 | 1029520.27 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP043 | 2025-04 | 2024-12-05 | 1558449.32 | 1390140 | -168309.32 | 168309.32 | 0 | 2025-04-28 | 4 | 1705143.66 | -146694.34 | DOWN | 0.0941 | 144 | Low | 345649.54 | 0.219 | 0 | 1044490.46 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP043 | 2025-04 | 2024-12-24 | 1485141.56 | 1390140 | -95001.56 | 95001.56 | 0 | 2025-04-28 | 5 | 1558449.32 | -73307.76 | DOWN | 0.0494 | 125 | Low | 428823.44 | 0.274 | 1 | 961316.56 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP043 | 2025-04 | 2025-02-08 | 1440900.34 | 1390140 | -50760.34 | 50760.34 | 0 | 2025-04-28 | 6 | 1485141.56 | -44241.22 | DOWN | 0.0307 | 79 | Low | 600215.2 | 0.406 | 3 | 789924.8 | 13 | 1.21 | 1.27
P003 | Services | SUP043 | 2025-05 | 2025-01-01 | 810163.53 | 465588 | -344575.53 | 344575.53 | 1 | 2025-05-28 | 1 |  |  |  |  | 147 | Low | 163833.99 | 0.207 | 0 | 301754.01 | 14 | 1.36 | 1.73
P003 | Services | SUP043 | 2025-05 | 2025-02-28 | 652251.66 | 465588 | -186663.66 | 186663.66 | 1 | 2025-05-28 | 2 | 810163.53 | -157911.87 | DOWN | 0.2421 | 89 | Low | 240674.69 | 0.371 | 0 | 224913.31 | 14 | 1.36 | 1.73
P003 | Services | SUP043 | 2025-05 | 2025-04-21 | 562926.96 | 465588 | -97338.96 | 97338.96 | 1 | 2025-05-28 | 3 | 652251.66 | -89324.7 | DOWN | 0.1587 | 37 | Low | 298809.62 | 0.518 | 5 | 166778.38 | 14 | 1.36 | 1.73
P003 | Services | SUP043 | 2025-05 | 2025-04-26 | 517321.12 | 465588 | -51733.12 | 51733.12 | 0 | 2025-05-28 | 4 | 562926.96 | -45605.84 | DOWN | 0.0882 | 32 | Medium | 257385.77 | 0.532 | 5 | 208202.23 | 14 | 1.36 | 1.73
P003 | Services | SUP043 | 2025-05 | 2025-05-14 | 486114.9 | 465588 | -20526.9 | 20526.9 | 0 | 2025-05-28 | 5 | 517321.12 | -31206.22 | DOWN | 0.0642 | 14 | Medium | 298120.99 | 0.583 | 5 | 167467.01 | 14 | 1.36 | 1.73
P003 | Services | SUP043 | 2025-06 | 2025-03-11 | 512741.12 | 289477 | -223264.12 | 223264.12 | 1 | 2025-06-28 | 1 |  |  |  |  | 109 | Low | 157704.27 | 0.31 | 0 | 131772.73 | 22 | 1.47 | 1.51
P003 | Services | SUP043 | 2025-06 | 2025-03-24 | 416563.01 | 289477 | -127086.01 | 127086.01 | 1 | 2025-06-28 | 2 | 512741.12 | -96178.11 | DOWN | 0.2309 | 96 | Low | 136707.06 | 0.347 | 3 | 152769.94 | 22 | 1.47 | 1.51
P003 | Services | SUP043 | 2025-06 | 2025-04-24 | 359436.52 | 289477 | -69959.52 | 69959.52 | 1 | 2025-06-28 | 3 | 416563.01 | -57126.49 | DOWN | 0.1589 | 65 | Low | 155290.32 | 0.434 | 3 | 134186.68 | 22 | 1.47 | 1.51
P003 | Services | SUP043 | 2025-06 | 2025-05-06 | 326082.15 | 289477 | -36605.15 | 36605.15 | 0 | 2025-06-28 | 4 | 359436.52 | -33354.37 | DOWN | 0.1023 | 53 | Medium | 145968.18 | 0.467 | 2 | 143508.82 | 22 | 1.47 | 1.51
P003 | Electronics | SUP043 | 2025-07 | 2025-05-09 | 4234986.89 | 2347991 | -1886995.89 | 1886995.89 | 1 | 2025-07-28 | 1 |  |  |  |  | 80 | Low | 1731719.44 | 0.414 | 2 | 616271.56 | 13 | 0.8 | 1.22
P003 | Electronics | SUP043 | 2025-07 | 2025-05-12 | 3428512.91 | 2347991 | -1080521.91 | 1080521.91 | 1 | 2025-07-28 | 2 | 4234986.89 | -806473.98 | DOWN | 0.2352 | 77 | Low | 1336898.33 | 0.423 | 4 | 1011092.67 | 13 | 0.8 | 1.22
P003 | Electronics | SUP043 | 2025-07 | 2025-05-29 | 2909355.02 | 2347991 | -561364.02 | 561364.02 | 1 | 2025-07-28 | 3 | 3428512.91 | -519157.89 | DOWN | 0.1784 | 60 | Low | 1320658.87 | 0.473 | 5 | 1027332.13 | 13 | 0.8 | 1.22
P003 | Logistics | SUP043 | 2025-08 | 2025-03-08 | 4829438.98 | 2526614 | -2302824.98 | 2302824.98 | 1 | 2025-08-28 | 1 |  |  |  |  | 173 | Low | 659632.87 | 0.133 | 1 | 1866981.13 | 7 | 1.37 | 1.47
P003 | Logistics | SUP043 | 2025-08 | 2025-04-26 | 3836732.38 | 2526614 | -1310118.38 | 1310118.38 | 1 | 2025-08-28 | 2 | 4829438.98 | -992706.6 | DOWN | 0.2587 | 124 | Low | 1010055.37 | 0.272 | 0 | 1516558.63 | 7 | 1.37 | 1.47
P003 | Logistics | SUP043 | 2025-08 | 2025-05-05 | 3326238.37 | 2526614 | -799624.37 | 799624.37 | 1 | 2025-08-28 | 3 | 3836732.38 | -510494.01 | DOWN | 0.1535 | 115 | Low | 978543.73 | 0.297 | 3 | 1548070.27 | 7 | 1.37 | 1.47
P003 | Logistics | SUP043 | 2025-08 | 2025-05-14 | 2967269.43 | 2526614 | -440655.43 | 440655.43 | 0 | 2025-08-28 | 4 | 3326238.37 | -358968.94 | DOWN | 0.121 | 106 | Low | 922163.15 | 0.322 | 1 | 1604450.85 | 7 | 1.37 | 1.47
P003 | Logistics | SUP043 | 2025-08 | 2025-06-27 | 2774097.83 | 2526614 | -247483.83 | 247483.83 | 0 | 2025-08-28 | 5 | 2967269.43 | -193171.6 | DOWN | 0.0696 | 62 | Low | 1141487.11 | 0.447 | 2 | 1385126.89 | 7 | 1.37 | 1.47
P003 | Software | SUP043 | 2025-09 | 2025-04-17 | 711667.32 | 350372 | -361295.32 | 361295.32 | 1 | 2025-09-28 | 1 |  |  |  |  | 164 | Low | 109742.4 | 0.165 | 0 | 240629.6 | 10 | 0.71 | 1.27
P003 | Software | SUP043 | 2025-09 | 2025-04-17 | 543174.37 | 350372 | -192802.37 | 192802.37 | 1 | 2025-09-28 | 2 | 711667.32 | -168492.95 | DOWN | 0.3102 | 164 | Low | 85437.43 | 0.165 | 2 | 264934.57 | 10 | 0.71 | 1.27
P003 | Software | SUP043 | 2025-09 | 2025-04-26 | 446735.81 | 350372 | -96363.81 | 96363.81 | 1 | 2025-09-28 | 3 | 543174.37 | -96438.56 | DOWN | 0.2159 | 155 | Low | 90689.02 | 0.192 | 2 | 259682.98 | 10 | 0.71 | 1.27
P003 | Software | SUP043 | 2025-09 | 2025-06-12 | 409666.44 | 350372 | -59294.44 | 59294.44 | 0 | 2025-09-28 | 4 | 446735.81 | -37069.37 | DOWN | 0.0905 | 108 | Low | 142593.05 | 0.331 | 2 | 207778.95 | 10 | 0.71 | 1.27
P003 | Software | SUP043 | 2025-09 | 2025-07-04 | 381267.46 | 350372 | -30895.46 | 30895.46 | 0 | 2025-09-28 | 5 | 409666.44 | -28398.98 | DOWN | 0.0745 | 86 | Low | 149708.24 | 0.396 | 5 | 200663.76 | 10 | 0.71 | 1.27
P003 | Software | SUP043 | 2025-09 | 2025-07-21 | 374109.42 | 350372 | -23737.42 | 23737.42 | 0 | 2025-09-28 | 6 | 381267.46 | -7158.04 | DOWN | 0.0191 | 69 | Low | 154490.2 | 0.446 | 4 | 195881.8 | 10 | 0.71 | 1.27
P003 | Electronics | SUP043 | 2025-10 | 2025-05-09 | 1616016.13 | 1015415 | -600601.13 | 600601.13 | 1 | 2025-10-28 | 1 |  |  |  |  | 172 | Low | 217823.65 | 0.142 | 1 | 797591.35 | 19 | 0.95 | 0.98
P003 | Electronics | SUP043 | 2025-10 | 2025-05-19 | 1350833.04 | 1015415 | -335418.04 | 335418.04 | 1 | 2025-10-28 | 2 | 1616016.13 | -265183.09 | DOWN | 0.1963 | 162 | Low | 232047.42 | 0.171 | 2 | 783367.58 | 19 | 0.95 | 0.98
P003 | Electronics | SUP043 | 2025-10 | 2025-07-02 | 1205424.81 | 1015415 | -190009.81 | 190009.81 | 1 | 2025-10-28 | 3 | 1350833.04 | -145408.23 | DOWN | 0.1206 | 118 | Low | 390993.2 | 0.301 | 6 | 624421.8 | 19 | 0.95 | 0.98
P003 | Electronics | SUP043 | 2025-10 | 2025-07-25 | 1130884 | 1015415 | -115469 | 115469 | 0 | 2025-10-28 | 4 | 1205424.81 | -74540.81 | DOWN | 0.0659 | 95 | Low | 400527.66 | 0.369 | 3 | 614887.34 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP043 | 2025-11 | 2025-07-05 | 3012841.38 | 1854075 | -1158766.38 | 1158766.38 | 1 | 2025-11-28 | 1 |  |  |  |  | 146 | Low | 610082.43 | 0.198 | 4 | 1243992.57 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP043 | 2025-11 | 2025-09-02 | 2519147.64 | 1854075 | -665072.64 | 665072.64 | 1 | 2025-11-28 | 2 | 3012841.38 | -493693.74 | DOWN | 0.196 | 87 | Low | 914597.86 | 0.357 | 2 | 939477.14 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP043 | 2025-11 | 2025-09-16 | 2193271.96 | 1854075 | -339196.96 | 339196.96 | 1 | 2025-11-28 | 3 | 2519147.64 | -325875.68 | DOWN | 0.1486 | 73 | Low | 905441.77 | 0.394 | 3 | 948633.23 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP043 | 2025-11 | 2025-10-18 | 2041135.45 | 1854075 | -187060.45 | 187060.45 | 0 | 2025-11-28 | 4 | 2193271.96 | -152136.51 | DOWN | 0.0745 | 41 | Medium | 962544.37 | 0.48 | 2 | 891530.63 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP043 | 2025-11 | 2025-10-27 | 1979736.85 | 1854075 | -125661.85 | 125661.85 | 0 | 2025-11-28 | 5 | 2041135.45 | -61398.6 | DOWN | 0.031 | 32 | Medium | 929512.6 | 0.504 | 3 | 924562.4 | 11 | 1.85 | 1.52
P003 | Services | SUP043 | 2025-12 | 2025-09-28 | 2953760.56 | 1603030 | -1350730.56 | 1350730.56 | 1 | 2025-12-28 | 1 |  |  |  |  | 91 | Low | 1137029.77 | 0.378 | 4 | 466000.23 | 10 | 1.08 | 1.22
P003 | Services | SUP043 | 2025-12 | 2025-10-27 | 2356957.89 | 1603030 | -753927.89 | 753927.89 | 1 | 2025-12-28 | 2 | 2953760.56 | -596802.67 | DOWN | 0.2532 | 62 | Low | 1103885.05 | 0.462 | 3 | 499144.95 | 10 | 1.08 | 1.22
P003 | Services | SUP043 | 2025-12 | 2025-10-30 | 2014008.22 | 1603030 | -410978.22 | 410978.22 | 1 | 2025-12-28 | 3 | 2356957.89 | -342949.67 | DOWN | 0.1703 | 59 | Low | 952401.93 | 0.471 | 0 | 650628.07 | 10 | 1.08 | 1.22
P003 | Services | SUP043 | 2025-12 | 2025-12-08 | 1820476.85 | 1603030 | -217446.85 | 217446.85 | 0 | 2025-12-28 | 4 | 2014008.22 | -193531.37 | DOWN | 0.1063 | 20 | Medium | 1052546.26 | 0.585 | 3 | 550483.74 | 10 | 1.08 | 1.22
P003 | Services | SUP043 | 2025-12 | 2025-12-12 | 1735688.01 | 1603030 | -132658.01 | 132658.01 | 0 | 2025-12-28 | 5 | 1820476.85 | -84788.84 | DOWN | 0.0489 | 16 | Medium | 1050002.48 | 0.597 | 4 | 553027.52 | 10 | 1.08 | 1.22
P003 | Services | SUP043 | 2025-12 | 2025-12-12 | 1665486.16 | 1603030 | -62456.16 | 62456.16 | 0 | 2025-12-28 | 6 | 1735688.01 | -70201.85 | DOWN | 0.0422 | 16 | Medium | 1060413.99 | 0.597 | 5 | 542616.01 | 10 | 1.08 | 1.22
P003 | Services | SUP032 | 2025-01 | 2024-08-08 | 1062256.87 | 448112 | -614144.87 | 614144.87 | 1 | 2025-01-28 | 1 |  |  |  |  | 173 | Low | 106819.69 | 0.097 | 1 | 341292.31 | 17 | 1.86 | 1.34
P003 | Services | SUP032 | 2025-01 | 2024-10-12 | 901016.31 | 448112 | -452904.31 | 452904.31 | 1 | 2025-01-28 | 2 | 1062256.87 | -161240.56 | DOWN | 0.179 | 108 | Low | 221426.38 | 0.231 | 3 | 226685.62 | 17 | 1.86 | 1.34
P003 | Services | SUP032 | 2025-01 | 2024-11-08 | 801133.79 | 448112 | -353021.79 | 353021.79 | 1 | 2025-01-28 | 3 | 901016.31 | -99882.52 | DOWN | 0.1247 | 81 | Low | 234855.83 | 0.286 | 5 | 213256.17 | 17 | 1.86 | 1.34
P003 | Services | SUP032 | 2025-01 | 2024-12-22 | 718649.92 | 448112 | -270537.92 | 270537.92 | 1 | 2025-01-28 | 4 | 801133.79 | -82483.87 | DOWN | 0.1148 | 37 | Low | 287604.38 | 0.377 | 4 | 160507.62 | 17 | 1.86 | 1.34
P003 | Services | SUP032 | 2025-01 | 2024-12-25 | 654132.05 | 448112 | -206020.05 | 206020.05 | 1 | 2025-01-28 | 5 | 718649.92 | -64517.87 | DOWN | 0.0986 | 34 | Low | 235227.44 | 0.383 | 0 | 212884.56 | 17 | 1.86 | 1.34
P003 | Services | SUP032 | 2025-01 | 2024-12-30 | 621659.06 | 448112 | -173547.06 | 173547.06 | 1 | 2025-01-28 | 6 | 654132.05 | -32472.99 | DOWN | 0.0522 | 29 | Low | 242727.24 | 0.393 | 2 | 205384.76 | 17 | 1.86 | 1.34
P003 | Services | SUP032 | 2025-02 | 2024-09-01 | 1142100.36 | 502795 | -639305.36 | 639305.36 | 1 | 2025-02-28 | 1 |  |  |  |  | 180 | Low | 101260.72 | 0.088 | 0 | 401534.28 | 17 | 2.1 | 1.03
P003 | Services | SUP032 | 2025-02 | 2024-11-12 | 989203.33 | 502795 | -486408.33 | 486408.33 | 1 | 2025-02-28 | 2 | 1142100.36 | -152897.03 | DOWN | 0.1546 | 108 | Low | 212715.55 | 0.225 | 0 | 290079.45 | 17 | 2.1 | 1.03
P003 | Services | SUP032 | 2025-02 | 2024-12-02 | 888832.3 | 502795 | -386037.3 | 386037.3 | 1 | 2025-02-28 | 3 | 989203.33 | -100371.03 | DOWN | 0.1129 | 88 | Low | 238009.93 | 0.265 | 2 | 264785.07 | 17 | 2.1 | 1.03
P003 | Services | SUP032 | 2025-02 | 2024-12-05 | 791631.19 | 502795 | -288836.19 | 288836.19 | 1 | 2025-02-28 | 4 | 888832.3 | -97201.11 | DOWN | 0.1228 | 85 | Low | 223460.03 | 0.271 | 3 | 279334.97 | 17 | 2.1 | 1.03
P003 | Services | SUP032 | 2025-02 | 2024-12-14 | 724580.54 | 502795 | -221785.54 | 221785.54 | 1 | 2025-02-28 | 5 | 791631.19 | -67050.65 | DOWN | 0.0925 | 76 | Low | 217851.35 | 0.289 | 8 | 284943.65 | 17 | 2.1 | 1.03
P003 | Services | SUP032 | 2025-03 | 2024-10-02 | 494262.9 | 292791 | -201471.9 | 201471.9 | 1 | 2025-03-28 | 1 |  |  |  |  | 177 | Low | 46060.01 | 0.098 | 3 | 246730.99 | 13 | 1.13 | 1.73
P003 | Services | SUP032 | 2025-03 | 2024-10-16 | 437724.64 | 292791 | -144933.64 | 144933.64 | 1 | 2025-03-28 | 2 | 494262.9 | -56538.26 | DOWN | 0.1292 | 163 | Low | 55853.48 | 0.128 | 2 | 236937.52 | 13 | 1.13 | 1.73
P003 | Services | SUP032 | 2025-03 | 2025-01-17 | 396857.54 | 292791 | -104066.54 | 104066.54 | 1 | 2025-03-28 | 3 | 437724.64 | -40867.1 | DOWN | 0.103 | 70 | Low | 139771.97 | 0.336 | 0 | 153019.03 | 13 | 1.13 | 1.73
P003 | Services | SUP032 | 2025-03 | 2025-01-25 | 372880.13 | 292791 | -80089.13 | 80089.13 | 1 | 2025-03-28 | 4 | 396857.54 | -23977.41 | DOWN | 0.0643 | 62 | Low | 131157.9 | 0.354 | 3 | 161633.1 | 13 | 1.13 | 1.73
P003 | Logistics | SUP032 | 2025-04 | 2024-12-01 | 760266.36 | 360008 | -400258.36 | 400258.36 | 1 | 2025-04-28 | 1 |  |  |  |  | 148 | Low | 113475.53 | 0.16 | 1 | 246532.47 | 13 | 1.21 | 1.27
P003 | Logistics | SUP032 | 2025-04 | 2024-12-03 | 652000.54 | 360008 | -291992.54 | 291992.54 | 1 | 2025-04-28 | 2 | 760266.36 | -108265.82 | DOWN | 0.1661 | 146 | Low | 105532.94 | 0.164 | 0 | 254475.06 | 13 | 1.21 | 1.27
P003 | Logistics | SUP032 | 2025-04 | 2025-02-13 | 573349.27 | 360008 | -213341.27 | 213341.27 | 1 | 2025-04-28 | 3 | 652000.54 | -78651.27 | DOWN | 0.1372 | 74 | Low | 178053.51 | 0.324 | 4 | 181954.49 | 13 | 1.21 | 1.27
P003 | Logistics | SUP032 | 2025-04 | 2025-02-16 | 528672.35 | 360008 | -168664.35 | 168664.35 | 1 | 2025-04-28 | 4 | 573349.27 | -44676.92 | DOWN | 0.0845 | 71 | Low | 174896.42 | 0.33 | 2 | 185111.58 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP032 | 2025-05 | 2024-12-20 | 738918.37 | 455930 | -282988.37 | 282988.37 | 1 | 2025-05-28 | 1 |  |  |  |  | 159 | Low | 98677.3 | 0.133 | 2 | 357252.7 | 14 | 1.36 | 1.73
P003 | Mechanical | SUP032 | 2025-05 | 2025-01-03 | 666854.18 | 455930 | -210924.18 | 210924.18 | 1 | 2025-05-28 | 2 | 738918.37 | -72064.19 | DOWN | 0.1081 | 145 | Low | 108708.24 | 0.163 | 4 | 347221.76 | 14 | 1.36 | 1.73
P003 | Mechanical | SUP032 | 2025-05 | 2025-01-23 | 614620.55 | 455930 | -158690.55 | 158690.55 | 1 | 2025-05-28 | 3 | 666854.18 | -52233.63 | DOWN | 0.085 | 125 | Low | 133211.47 | 0.207 | 0 | 322718.53 | 14 | 1.36 | 1.73
P003 | Mechanical | SUP032 | 2025-05 | 2025-03-23 | 572380.18 | 455930 | -116450.18 | 116450.18 | 1 | 2025-05-28 | 4 | 614620.55 | -42240.37 | DOWN | 0.0738 | 66 | Low | 199320.91 | 0.336 | 4 | 256609.09 | 14 | 1.36 | 1.73
P003 | Mechanical | SUP032 | 2025-05 | 2025-04-06 | 540839.96 | 455930 | -84909.96 | 84909.96 | 1 | 2025-05-28 | 5 | 572380.18 | -31540.22 | DOWN | 0.0583 | 52 | Low | 199760.71 | 0.366 | 0 | 256169.29 | 14 | 1.36 | 1.73
P003 | Logistics | SUP032 | 2025-06 | 2025-01-01 | 880538.14 | 444422 | -436116.14 | 436116.14 | 1 | 2025-06-28 | 1 |  |  |  |  | 178 | Low | 87827.18 | 0.095 | 0 | 356594.82 | 22 | 1.47 | 1.51
P003 | Logistics | SUP032 | 2025-06 | 2025-01-23 | 770700.42 | 444422 | -326278.42 | 326278.42 | 1 | 2025-06-28 | 2 | 880538.14 | -109837.72 | DOWN | 0.1425 | 156 | Low | 113885.5 | 0.138 | 2 | 330536.5 | 22 | 1.47 | 1.51
P003 | Logistics | SUP032 | 2025-06 | 2025-03-08 | 703736.64 | 444422 | -259314.64 | 259314.64 | 1 | 2025-06-28 | 3 | 770700.42 | -66963.78 | DOWN | 0.0952 | 112 | Low | 169650.06 | 0.232 | 0 | 274771.94 | 22 | 1.47 | 1.51
P003 | Logistics | SUP032 | 2025-06 | 2025-03-13 | 645112.5 | 444422 | -200690.5 | 200690.5 | 1 | 2025-06-28 | 4 | 703736.64 | -58624.14 | DOWN | 0.0909 | 107 | Low | 167716.86 | 0.243 | 0 | 276705.14 | 22 | 1.47 | 1.51
P003 | Logistics | SUP032 | 2025-06 | 2025-05-10 | 595771.22 | 444422 | -151349.22 | 151349.22 | 1 | 2025-06-28 | 5 | 645112.5 | -49341.28 | DOWN | 0.0828 | 49 | Low | 212838.05 | 0.368 | 2 | 231583.95 | 22 | 1.47 | 1.51
P003 | Logistics | SUP032 | 2025-06 | 2025-06-18 | 571866.62 | 444422 | -127444.62 | 127444.62 | 1 | 2025-06-28 | 6 | 595771.22 | -23904.6 | DOWN | 0.0418 | 10 | Low | 243735.66 | 0.45 | 3 | 200686.34 | 22 | 1.47 | 1.51
P003 | Software | SUP032 | 2025-07 | 2025-03-04 | 1076066.81 | 561598 | -514468.81 | 514468.81 | 1 | 2025-07-28 | 1 |  |  |  |  | 146 | Low | 174386.95 | 0.168 | 3 | 387211.05 | 13 | 0.8 | 1.22
P003 | Software | SUP032 | 2025-07 | 2025-04-07 | 942096.49 | 561598 | -380498.49 | 380498.49 | 1 | 2025-07-28 | 2 | 1076066.81 | -133970.32 | DOWN | 0.1422 | 112 | Low | 219757.53 | 0.245 | 0 | 341840.47 | 13 | 0.8 | 1.22
P003 | Software | SUP032 | 2025-07 | 2025-04-26 | 849786.13 | 561598 | -288188.13 | 288188.13 | 1 | 2025-07-28 | 3 | 942096.49 | -92310.36 | DOWN | 0.1086 | 93 | Low | 246180 | 0.289 | 2 | 315418 | 13 | 0.8 | 1.22
P003 | Software | SUP032 | 2025-07 | 2025-06-15 | 778033.42 | 561598 | -216435.42 | 216435.42 | 1 | 2025-07-28 | 4 | 849786.13 | -71752.71 | DOWN | 0.0922 | 43 | Low | 329344.39 | 0.402 | 4 | 232253.61 | 13 | 0.8 | 1.22
P003 | Software | SUP032 | 2025-07 | 2025-07-03 | 724582.24 | 561598 | -162984.24 | 162984.24 | 1 | 2025-07-28 | 5 | 778033.42 | -53451.18 | DOWN | 0.0738 | 25 | Low | 302108.13 | 0.443 | 5 | 259489.87 | 13 | 0.8 | 1.22
P003 | Software | SUP032 | 2025-07 | 2025-07-16 | 673951.75 | 561598 | -112353.75 | 112353.75 | 1 | 2025-07-28 | 6 | 724582.24 | -50630.49 | DOWN | 0.0751 | 12 | Low | 318718.21 | 0.473 | 0 | 242879.79 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP032 | 2025-08 | 2025-04-08 | 1126546.83 | 633650 | -492896.83 | 492896.83 | 1 | 2025-08-28 | 1 |  |  |  |  | 142 | Low | 201333.61 | 0.17 | 1 | 432316.39 | 7 | 1.37 | 1.47
P003 | Mechanical | SUP032 | 2025-08 | 2025-05-03 | 1014645.3 | 633650 | -380995.3 | 380995.3 | 1 | 2025-08-28 | 2 | 1126546.83 | -111901.53 | DOWN | 0.1103 | 117 | Low | 244000 | 0.224 | 0 | 389650 | 7 | 1.37 | 1.47
P003 | Mechanical | SUP032 | 2025-08 | 2025-05-30 | 915875.69 | 633650 | -282225.69 | 282225.69 | 1 | 2025-08-28 | 3 | 1014645.3 | -98769.61 | DOWN | 0.1078 | 90 | Low | 246709.12 | 0.283 | 1 | 386940.88 | 7 | 1.37 | 1.47
P003 | Mechanical | SUP032 | 2025-08 | 2025-06-09 | 856947.06 | 633650 | -223297.06 | 223297.06 | 1 | 2025-08-28 | 4 | 915875.69 | -58928.63 | DOWN | 0.0688 | 80 | Low | 263878.58 | 0.305 | 1 | 369771.42 | 7 | 1.37 | 1.47
P003 | Mechanical | SUP032 | 2025-08 | 2025-08-11 | 798678.77 | 633650 | -165028.77 | 165028.77 | 1 | 2025-08-28 | 5 | 856947.06 | -58268.29 | DOWN | 0.073 | 17 | Low | 331141.77 | 0.442 | 0 | 302508.23 | 7 | 1.37 | 1.47
P003 | Mechanical | SUP032 | 2025-09 | 2025-05-04 | 3366883.77 | 1939873 | -1427010.77 | 1427010.77 | 1 | 2025-09-28 | 1 |  |  |  |  | 147 | Low | 576930.9 | 0.166 | 0 | 1362942.1 | 10 | 0.71 | 1.27
P003 | Mechanical | SUP032 | 2025-09 | 2025-05-12 | 3024999.41 | 1939873 | -1085126.41 | 1085126.41 | 1 | 2025-09-28 | 2 | 3366883.77 | -341884.36 | DOWN | 0.113 | 139 | Low | 516696.29 | 0.184 | 4 | 1423176.71 | 10 | 0.71 | 1.27
P003 | Mechanical | SUP032 | 2025-09 | 2025-06-01 | 2761455.97 | 1939873 | -821582.97 | 821582.97 | 1 | 2025-09-28 | 3 | 3024999.41 | -263543.44 | DOWN | 0.0954 | 119 | Low | 636149.84 | 0.23 | 0 | 1303723.16 | 10 | 0.71 | 1.27
P003 | Mechanical | SUP032 | 2025-09 | 2025-08-21 | 2543503.4 | 1939873 | -603630.4 | 603630.4 | 1 | 2025-09-28 | 4 | 2761455.97 | -217952.57 | DOWN | 0.0857 | 38 | Low | 1077724.72 | 0.414 | 4 | 862148.28 | 10 | 0.71 | 1.27
P003 | Mechanical | SUP032 | 2025-09 | 2025-09-11 | 2402545.55 | 1939873 | -462672.55 | 462672.55 | 1 | 2025-09-28 | 5 | 2543503.4 | -140957.85 | DOWN | 0.0587 | 17 | Low | 1073410.81 | 0.461 | 4 | 866462.19 | 10 | 0.71 | 1.27
P003 | Mechanical | SUP032 | 2025-10 | 2025-06-26 | 271597.14 | 158814 | -112783.14 | 112783.14 | 1 | 2025-10-28 | 1 |  |  |  |  | 124 | Low | 55509.22 | 0.218 | 2 | 103304.78 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP032 | 2025-10 | 2025-07-25 | 243033.88 | 158814 | -84219.88 | 84219.88 | 1 | 2025-10-28 | 2 | 271597.14 | -28563.26 | DOWN | 0.1175 | 95 | Low | 65472.17 | 0.284 | 3 | 93341.83 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP032 | 2025-10 | 2025-09-16 | 221986.56 | 158814 | -63172.56 | 63172.56 | 1 | 2025-10-28 | 3 | 243033.88 | -21047.32 | DOWN | 0.0948 | 42 | Low | 85774.33 | 0.405 | 4 | 73039.67 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP032 | 2025-10 | 2025-10-14 | 207481.98 | 158814 | -48667.98 | 48667.98 | 1 | 2025-10-28 | 4 | 221986.56 | -14504.58 | DOWN | 0.0699 | 14 | Low | 96403.97 | 0.468 | 3 | 62410.03 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP032 | 2025-10 | 2025-10-15 | 195597.69 | 158814 | -36783.69 | 36783.69 | 1 | 2025-10-28 | 5 | 207481.98 | -11884.29 | DOWN | 0.0608 | 13 | Low | 93723.99 | 0.47 | 4 | 65090.01 | 19 | 0.95 | 0.98
P003 | Services | SUP032 | 2025-11 | 2025-06-03 | 2573452.07 | 1350397 | -1223055.07 | 1223055.07 | 1 | 2025-11-28 | 1 |  |  |  |  | 178 | Low | 245333.23 | 0.091 | 0 | 1105063.77 | 11 | 1.85 | 1.52
P003 | Services | SUP032 | 2025-11 | 2025-06-27 | 2220085.76 | 1350397 | -869688.76 | 869688.76 | 1 | 2025-11-28 | 2 | 2573452.07 | -353366.31 | DOWN | 0.1592 | 154 | Low | 302795.83 | 0.136 | 2 | 1047601.17 | 11 | 1.85 | 1.52
P003 | Services | SUP032 | 2025-11 | 2025-07-30 | 2015191.36 | 1350397 | -664794.36 | 664794.36 | 1 | 2025-11-28 | 3 | 2220085.76 | -204894.4 | DOWN | 0.1017 | 121 | Low | 422771.23 | 0.204 | 0 | 927625.77 | 11 | 1.85 | 1.52
P003 | Services | SUP032 | 2025-11 | 2025-09-09 | 1890414.95 | 1350397 | -540017.95 | 540017.95 | 1 | 2025-11-28 | 4 | 2015191.36 | -124776.41 | DOWN | 0.066 | 80 | Low | 530200.71 | 0.289 | 2 | 820196.29 | 11 | 1.85 | 1.52
P003 | Services | SUP032 | 2025-11 | 2025-09-10 | 1750738.27 | 1350397 | -400341.27 | 400341.27 | 1 | 2025-11-28 | 5 | 1890414.95 | -139676.68 | DOWN | 0.0798 | 79 | Low | 508413.09 | 0.291 | 2 | 841983.91 | 11 | 1.85 | 1.52
P003 | Services | SUP032 | 2025-11 | 2025-10-05 | 1674782.42 | 1350397 | -324385.42 | 324385.42 | 1 | 2025-11-28 | 6 | 1750738.27 | -75955.85 | DOWN | 0.0454 | 54 | Low | 597071.62 | 0.342 | 2 | 753325.38 | 11 | 1.85 | 1.52
P003 | Materials | SUP032 | 2025-12 | 2025-10-04 | 3049086.86 | 1607936 | -1441150.86 | 1441150.86 | 1 | 2025-12-28 | 1 |  |  |  |  | 85 | Low | 859703.17 | 0.304 | 4 | 748232.83 | 10 | 1.08 | 1.22
P003 | Materials | SUP032 | 2025-12 | 2025-10-08 | 2702412.84 | 1607936 | -1094476.84 | 1094476.84 | 1 | 2025-12-28 | 2 | 3049086.86 | -346674.02 | DOWN | 0.1283 | 81 | Low | 895412.64 | 0.313 | 2 | 712523.36 | 10 | 1.08 | 1.22
P003 | Materials | SUP032 | 2025-12 | 2025-10-21 | 2428554.05 | 1607936 | -820618.05 | 820618.05 | 1 | 2025-12-28 | 3 | 2702412.84 | -273858.79 | DOWN | 0.1128 | 68 | Low | 835743.73 | 0.342 | 4 | 772192.27 | 10 | 1.08 | 1.22
P003 | Services | SUP002 | 2025-01 | 2024-08-27 | 2656409.81 | 1741858 | -914551.81 | 914551.81 | 1 | 2025-01-28 | 1 |  |  |  |  | 154 | Low | 588519.26 | 0.212 | 3 | 1153338.74 | 17 | 1.86 | 1.34
P003 | Services | SUP002 | 2025-01 | 2024-09-02 | 2159339.52 | 1741858 | -417481.52 | 417481.52 | 1 | 2025-01-28 | 2 | 2656409.81 | -497070.29 | DOWN | 0.2302 | 148 | Low | 466189.05 | 0.231 | 2 | 1275668.95 | 17 | 1.86 | 1.34
P003 | Services | SUP002 | 2025-01 | 2024-09-27 | 1904319.05 | 1741858 | -162461.05 | 162461.05 | 0 | 2025-01-28 | 3 | 2159339.52 | -255020.47 | DOWN | 0.1339 | 123 | Low | 600100.22 | 0.312 | 3 | 1141757.78 | 17 | 1.86 | 1.34
P003 | Services | SUP002 | 2025-01 | 2024-11-07 | 1777753.67 | 1741858 | -35895.67 | 35895.67 | 0 | 2025-01-28 | 4 | 1904319.05 | -126565.38 | DOWN | 0.0712 | 82 | Low | 781039.88 | 0.444 | 2 | 960818.12 | 17 | 1.86 | 1.34
P003 | Services | SUP002 | 2025-01 | 2024-11-18 | 1801390.37 | 1741858 | -59532.37 | 59532.37 | 0 | 2025-01-28 | 5 | 1777753.67 | 23636.7 | UP | 0.0131 | 71 | Low | 848007.18 | 0.479 | 4 | 893850.82 | 17 | 1.86 | 1.34
P003 | Services | SUP002 | 2025-01 | 2024-12-27 | 1773607.67 | 1741858 | -31749.67 | 31749.67 | 0 | 2025-01-28 | 6 | 1801390.37 | -27782.7 | DOWN | 0.0157 | 32 | Medium | 1134000.71 | 0.604 | 6 | 607857.29 | 17 | 1.86 | 1.34
P003 | Logistics | SUP002 | 2025-02 | 2024-11-08 | 2648036.87 | 1513741 | -1134295.87 | 1134295.87 | 1 | 2025-02-28 | 1 |  |  |  |  | 112 | Low | 897364.25 | 0.338 | 1 | 616376.75 | 17 | 2.1 | 1.03
P003 | Logistics | SUP002 | 2025-02 | 2024-11-22 | 2091946.88 | 1513741 | -578205.88 | 578205.88 | 1 | 2025-02-28 | 2 | 2648036.87 | -556089.99 | DOWN | 0.2658 | 98 | Low | 833364.43 | 0.382 | 4 | 680376.57 | 17 | 2.1 | 1.03
P003 | Logistics | SUP002 | 2025-02 | 2024-11-28 | 1827645.05 | 1513741 | -313904.05 | 313904.05 | 1 | 2025-02-28 | 3 | 2091946.88 | -264301.83 | DOWN | 0.1446 | 92 | Low | 702377.28 | 0.401 | 3 | 811363.72 | 17 | 2.1 | 1.03
P003 | Logistics | SUP002 | 2025-02 | 2024-12-18 | 1647557.63 | 1513741 | -133816.63 | 133816.63 | 0 | 2025-02-28 | 4 | 1827645.05 | -180087.42 | DOWN | 0.1093 | 72 | Low | 808596.06 | 0.464 | 4 | 705144.94 | 17 | 2.1 | 1.03
P003 | Logistics | SUP002 | 2025-02 | 2025-01-12 | 1563754.39 | 1513741 | -50013.39 | 50013.39 | 0 | 2025-02-28 | 5 | 1647557.63 | -83803.24 | DOWN | 0.0536 | 47 | Low | 787697.68 | 0.542 | 3 | 726043.32 | 17 | 2.1 | 1.03
P003 | Logistics | SUP002 | 2025-02 | 2025-02-06 | 1480921.26 | 1513741 | 32819.74 | 32819.74 | 0 | 2025-02-28 | 6 | 1563754.39 | -82833.13 | DOWN | 0.0559 | 22 | Low | 876301.4 | 0.62 | 6 | 637439.6 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP002 | 2025-03 | 2024-10-14 | 1451735.87 | 1211412 | -240323.87 | 240323.87 | 1 | 2025-03-28 | 1 |  |  |  |  | 165 | Low | 258864.43 | 0.192 | 3 | 952547.57 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP002 | 2025-03 | 2024-10-18 | 1311599.53 | 1211412 | -100187.53 | 100187.53 | 0 | 2025-03-28 | 2 | 1451735.87 | -140136.34 | DOWN | 0.1068 | 161 | Low | 273021.29 | 0.206 | 2 | 938390.71 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP002 | 2025-03 | 2024-11-25 | 1260682.15 | 1211412 | -49270.15 | 49270.15 | 0 | 2025-03-28 | 3 | 1311599.53 | -50917.38 | DOWN | 0.0404 | 123 | Low | 427642.52 | 0.339 | 1 | 783769.48 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP002 | 2025-03 | 2025-01-04 | 1226001.9 | 1211412 | -14589.9 | 14589.9 | 0 | 2025-03-28 | 4 | 1260682.15 | -34680.25 | DOWN | 0.0283 | 83 | Low | 595105.29 | 0.478 | 3 | 616306.71 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP002 | 2025-03 | 2025-01-12 | 1211132.57 | 1211412 | 279.43 | 279.43 | 0 | 2025-03-28 | 5 | 1226001.9 | -14869.33 | DOWN | 0.0123 | 75 | Low | 582753.91 | 0.506 | 9 | 628658.09 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP002 | 2025-03 | 2025-02-23 | 1216170.44 | 1211412 | -4758.44 | 4758.44 | 0 | 2025-03-28 | 6 | 1211132.57 | 5037.87 | UP | 0.0041 | 33 | Medium | 812680.95 | 0.653 | 7 | 398731.05 | 13 | 1.13 | 1.73
P003 | Electronics | SUP002 | 2025-04 | 2024-12-13 | 3076204.81 | 2029938 | -1046266.81 | 1046266.81 | 1 | 2025-04-28 | 1 |  |  |  |  | 136 | Low | 920254.01 | 0.29 | 3 | 1109683.99 | 13 | 1.21 | 1.27
P003 | Electronics | SUP002 | 2025-04 | 2025-01-25 | 2519040 | 2029938 | -489102 | 489102 | 1 | 2025-04-28 | 2 | 3076204.81 | -557164.81 | DOWN | 0.2212 | 93 | Low | 1068182.56 | 0.439 | 7 | 961755.44 | 13 | 1.21 | 1.27
P003 | Electronics | SUP002 | 2025-04 | 2025-04-16 | 2229610.39 | 2029938 | -199672.39 | 199672.39 | 0 | 2025-04-28 | 3 | 2519040 | -289429.61 | DOWN | 0.1298 | 12 | Low | 1487755.55 | 0.719 | 2 | 542182.45 | 13 | 1.21 | 1.27
P003 | Logistics | SUP002 | 2025-05 | 2024-12-07 | 3974936.31 | 2318921 | -1656015.31 | 1656015.31 | 1 | 2025-05-28 | 1 |  |  |  |  | 172 | Low | 670416.95 | 0.163 | 0 | 1648504.05 | 14 | 1.36 | 1.73
P003 | Logistics | SUP002 | 2025-05 | 2024-12-11 | 3073008.91 | 2318921 | -754087.91 | 754087.91 | 1 | 2025-05-28 | 2 | 3974936.31 | -901927.4 | DOWN | 0.2935 | 168 | Low | 586231.47 | 0.177 | 0 | 1732689.53 | 14 | 1.36 | 1.73
P003 | Logistics | SUP002 | 2025-05 | 2025-01-07 | 2703126.56 | 2318921 | -384205.56 | 384205.56 | 0 | 2025-05-28 | 3 | 3073008.91 | -369882.35 | DOWN | 0.1368 | 141 | Low | 684354.53 | 0.268 | 2 | 1634566.47 | 14 | 1.36 | 1.73
P003 | Logistics | SUP002 | 2025-05 | 2025-01-18 | 2466829.26 | 2318921 | -147908.26 | 147908.26 | 0 | 2025-05-28 | 4 | 2703126.56 | -236297.3 | DOWN | 0.0958 | 130 | Low | 721365.6 | 0.306 | 0 | 1597555.4 | 14 | 1.36 | 1.73
P003 | Logistics | SUP002 | 2025-05 | 2025-01-28 | 2345075.51 | 2318921 | -26154.51 | 26154.51 | 0 | 2025-05-28 | 5 | 2466829.26 | -121753.75 | DOWN | 0.0519 | 120 | Low | 838165.94 | 0.34 | 0 | 1480755.06 | 14 | 1.36 | 1.73
P003 | Logistics | SUP002 | 2025-05 | 2025-04-13 | 2314053.62 | 2318921 | 4867.38 | 4867.38 | 0 | 2025-05-28 | 6 | 2345075.51 | -31021.89 | DOWN | 0.0134 | 45 | Medium | 1314205.65 | 0.595 | 1 | 1004715.35 | 14 | 1.36 | 1.73
P003 | Software | SUP002 | 2025-06 | 2025-01-20 | 4563292.46 | 2853421 | -1709871.46 | 1709871.46 | 1 | 2025-06-28 | 1 |  |  |  |  | 159 | Low | 929447.92 | 0.205 | 0 | 1923973.08 | 22 | 1.47 | 1.51
P003 | Software | SUP002 | 2025-06 | 2025-02-15 | 3671083.77 | 2853421 | -817662.77 | 817662.77 | 1 | 2025-06-28 | 2 | 4563292.46 | -892208.69 | DOWN | 0.243 | 133 | Low | 1097378.64 | 0.292 | 1 | 1756042.36 | 22 | 1.47 | 1.51
P003 | Software | SUP002 | 2025-06 | 2025-03-01 | 3133952.32 | 2853421 | -280531.32 | 280531.32 | 0 | 2025-06-28 | 3 | 3671083.77 | -537131.45 | DOWN | 0.1714 | 119 | Low | 1116827.52 | 0.339 | 2 | 1736593.48 | 22 | 1.47 | 1.51
P003 | Software | SUP002 | 2025-06 | 2025-04-11 | 2993385.21 | 2853421 | -139964.21 | 139964.21 | 0 | 2025-06-28 | 4 | 3133952.32 | -140567.11 | DOWN | 0.047 | 78 | Low | 1529178.09 | 0.477 | 2 | 1324242.91 | 22 | 1.47 | 1.51
P003 | Software | SUP002 | 2025-06 | 2025-04-25 | 2881385.5 | 2853421 | -27964.5 | 27964.5 | 0 | 2025-06-28 | 5 | 2993385.21 | -111999.71 | DOWN | 0.0389 | 64 | Low | 1519781.5 | 0.524 | 5 | 1333639.5 | 22 | 1.47 | 1.51
P003 | Software | SUP002 | 2025-06 | 2025-05-24 | 2917180.73 | 2853421 | -63759.73 | 63759.73 | 0 | 2025-06-28 | 6 | 2881385.5 | 35795.23 | UP | 0.0123 | 35 | Medium | 1948838.04 | 0.621 | 4 | 904582.96 | 22 | 1.47 | 1.51
P003 | Logistics | SUP002 | 2025-07 | 2025-03-07 | 2334060.98 | 1521047 | -813013.98 | 813013.98 | 1 | 2025-07-28 | 1 |  |  |  |  | 143 | Low | 627854.47 | 0.273 | 2 | 893192.53 | 13 | 0.8 | 1.22
P003 | Logistics | SUP002 | 2025-07 | 2025-04-08 | 1902272.3 | 1521047 | -381225.3 | 381225.3 | 1 | 2025-07-28 | 2 | 2334060.98 | -431788.68 | DOWN | 0.227 | 111 | Low | 690226.2 | 0.386 | 4 | 830820.8 | 13 | 0.8 | 1.22
P003 | Logistics | SUP002 | 2025-07 | 2025-05-24 | 1701240.16 | 1521047 | -180193.16 | 180193.16 | 0 | 2025-07-28 | 3 | 1902272.3 | -201032.14 | DOWN | 0.1182 | 65 | Low | 891479.39 | 0.55 | 3 | 629567.61 | 13 | 0.8 | 1.22
P003 | Logistics | SUP002 | 2025-07 | 2025-06-17 | 1626485.97 | 1521047 | -105438.97 | 105438.97 | 0 | 2025-07-28 | 4 | 1701240.16 | -74754.19 | DOWN | 0.046 | 41 | Medium | 1104372.13 | 0.635 | 4 | 416674.87 | 13 | 0.8 | 1.22
P003 | Software | SUP002 | 2025-08 | 2025-03-22 | 2873035.12 | 1799079 | -1073956.12 | 1073956.12 | 1 | 2025-08-28 | 1 |  |  |  |  | 159 | Low | 612632.32 | 0.207 | 0 | 1186446.68 | 7 | 1.37 | 1.47
P003 | Software | SUP002 | 2025-08 | 2025-04-13 | 2281649.55 | 1799079 | -482570.55 | 482570.55 | 1 | 2025-08-28 | 2 | 2873035.12 | -591385.57 | DOWN | 0.2592 | 137 | Low | 593033.61 | 0.282 | 3 | 1206045.39 | 7 | 1.37 | 1.47
P003 | Software | SUP002 | 2025-08 | 2025-05-08 | 2049564.07 | 1799079 | -250485.07 | 250485.07 | 0 | 2025-08-28 | 3 | 2281649.55 | -232085.48 | DOWN | 0.1132 | 112 | Low | 795331.39 | 0.367 | 2 | 1003747.61 | 7 | 1.37 | 1.47
P003 | Software | SUP002 | 2025-08 | 2025-08-09 | 1927005.24 | 1799079 | -127926.24 | 127926.24 | 0 | 2025-08-28 | 4 | 2049564.07 | -122558.83 | DOWN | 0.0636 | 19 | Medium | 1232015.76 | 0.682 | 4 | 567063.24 | 7 | 1.37 | 1.47
P003 | Logistics | SUP002 | 2025-09 | 2025-04-01 | 359952.44 | 232137 | -127815.44 | 127815.44 | 1 | 2025-09-28 | 1 |  |  |  |  | 180 | Low | 55885.44 | 0.156 | 0 | 176251.56 | 10 | 0.71 | 1.27
P003 | Logistics | SUP002 | 2025-09 | 2025-08-25 | 285107.33 | 232137 | -52970.33 | 52970.33 | 1 | 2025-09-28 | 2 | 359952.44 | -74845.11 | DOWN | 0.2625 | 34 | Low | 200723.08 | 0.659 | 6 | 31413.92 | 10 | 0.71 | 1.27
P003 | Logistics | SUP002 | 2025-09 | 2025-09-01 | 259372.49 | 232137 | -27235.49 | 27235.49 | 0 | 2025-09-28 | 3 | 285107.33 | -25734.84 | DOWN | 0.0992 | 27 | Medium | 163456.91 | 0.684 | 5 | 68680.09 | 10 | 0.71 | 1.27
P003 | Logistics | SUP002 | 2025-10 | 2025-05-30 | 1076313.04 | 707703 | -368610.04 | 368610.04 | 1 | 2025-10-28 | 1 |  |  |  |  | 151 | Low | 269373.09 | 0.245 | 2 | 438329.91 | 19 | 0.95 | 0.98
P003 | Logistics | SUP002 | 2025-10 | 2025-07-15 | 889844.85 | 707703 | -182141.85 | 182141.85 | 1 | 2025-10-28 | 2 | 1076313.04 | -186468.19 | DOWN | 0.2096 | 105 | Low | 352614.61 | 0.408 | 0 | 355088.39 | 19 | 0.95 | 0.98
P003 | Logistics | SUP002 | 2025-10 | 2025-07-24 | 777836 | 707703 | -70133 | 70133 | 0 | 2025-10-28 | 3 | 889844.85 | -112008.85 | DOWN | 0.144 | 96 | Low | 321194.2 | 0.44 | 0 | 386508.8 | 19 | 0.95 | 0.98
P003 | Logistics | SUP002 | 2025-10 | 2025-07-26 | 724046.73 | 707703 | -16343.73 | 16343.73 | 0 | 2025-10-28 | 4 | 777836 | -53789.27 | DOWN | 0.0743 | 94 | Low | 304318.68 | 0.447 | 4 | 403384.32 | 19 | 0.95 | 0.98
P003 | Materials | SUP002 | 2025-11 | 2025-06-26 | 1788069.33 | 1158332 | -629737.33 | 629737.33 | 1 | 2025-11-28 | 1 |  |  |  |  | 155 | Low | 392855.38 | 0.209 | 3 | 765476.62 | 11 | 1.85 | 1.52
P003 | Materials | SUP002 | 2025-11 | 2025-06-30 | 1412368.77 | 1158332 | -254036.77 | 254036.77 | 1 | 2025-11-28 | 2 | 1788069.33 | -375700.56 | DOWN | 0.266 | 151 | Low | 317786.22 | 0.222 | 2 | 840545.78 | 11 | 1.85 | 1.52
P003 | Materials | SUP002 | 2025-11 | 2025-07-22 | 1286318.24 | 1158332 | -127986.24 | 127986.24 | 0 | 2025-11-28 | 3 | 1412368.77 | -126050.53 | DOWN | 0.098 | 129 | Low | 395484.1 | 0.293 | 4 | 762847.9 | 11 | 1.85 | 1.52
P003 | Materials | SUP002 | 2025-11 | 2025-07-27 | 1230260.99 | 1158332 | -71928.99 | 71928.99 | 0 | 2025-11-28 | 4 | 1286318.24 | -56057.25 | DOWN | 0.0456 | 124 | Low | 393986.97 | 0.309 | 2 | 764345.03 | 11 | 1.85 | 1.52
P003 | Materials | SUP002 | 2025-11 | 2025-10-29 | 1190306.65 | 1158332 | -31974.65 | 31974.65 | 0 | 2025-11-28 | 5 | 1230260.99 | -39954.34 | DOWN | 0.0336 | 30 | Medium | 723980.39 | 0.611 | 4 | 434351.61 | 11 | 1.85 | 1.52
P003 | Software | SUP002 | 2025-12 | 2025-07-03 | 3357122 | 2043282 | -1313840 | 1313840 | 1 | 2025-12-28 | 1 |  |  |  |  | 178 | Low | 483933.3 | 0.155 | 3 | 1559348.7 | 10 | 1.08 | 1.22
P003 | Software | SUP002 | 2025-12 | 2025-10-09 | 2651336.26 | 2043282 | -608054.26 | 608054.26 | 1 | 2025-12-28 | 2 | 3357122 | -705785.74 | DOWN | 0.2662 | 80 | Low | 1400172.94 | 0.492 | 8 | 643109.06 | 10 | 1.08 | 1.22
P003 | Software | SUP002 | 2025-12 | 2025-10-30 | 2341363.4 | 2043282 | -298081.4 | 298081.4 | 0 | 2025-12-28 | 3 | 2651336.26 | -309972.86 | DOWN | 0.1324 | 59 | Low | 1272888.74 | 0.565 | 5 | 770393.26 | 10 | 1.08 | 1.22
P003 | Software | SUP002 | 2025-12 | 2025-11-21 | 2149044.91 | 2043282 | -105762.91 | 105762.91 | 0 | 2025-12-28 | 4 | 2341363.4 | -192318.49 | DOWN | 0.0895 | 37 | Medium | 1405944.79 | 0.643 | 5 | 637337.21 | 10 | 1.08 | 1.22
P003 | Software | SUP002 | 2025-12 | 2025-12-03 | 2085560.78 | 2043282 | -42278.78 | 42278.78 | 0 | 2025-12-28 | 5 | 2149044.91 | -63484.13 | DOWN | 0.0304 | 25 | High | 1440912.34 | 0.685 | 3 | 602369.66 | 10 | 1.08 | 1.22
P003 | Logistics | SUP021 | 2025-01 | 2024-08-14 | 4333220.44 | 2508763 | -1824457.44 | 1824457.44 | 1 | 2025-01-28 | 1 |  |  |  |  | 167 | Low | 751127.38 | 0.17 | 0 | 1757635.62 | 17 | 1.86 | 1.34
P003 | Logistics | SUP021 | 2025-01 | 2024-09-11 | 3303204.43 | 2508763 | -794441.43 | 794441.43 | 1 | 2025-01-28 | 2 | 4333220.44 | -1030016.01 | DOWN | 0.3118 | 139 | Low | 913979.95 | 0.26 | 2 | 1594783.05 | 17 | 1.86 | 1.34
P003 | Logistics | SUP021 | 2025-01 | 2024-09-18 | 2897736.48 | 2508763 | -388973.48 | 388973.48 | 0 | 2025-01-28 | 3 | 3303204.43 | -405467.95 | DOWN | 0.1399 | 132 | Low | 854012.98 | 0.283 | 1 | 1654750.02 | 17 | 1.86 | 1.34
P003 | Logistics | SUP021 | 2025-01 | 2024-10-24 | 2630463.77 | 2508763 | -121700.77 | 121700.77 | 0 | 2025-01-28 | 4 | 2897736.48 | -267272.71 | DOWN | 0.1016 | 96 | Low | 1098088.96 | 0.399 | 7 | 1410674.04 | 17 | 1.86 | 1.34
P003 | Logistics | SUP021 | 2025-01 | 2024-10-26 | 2575167.58 | 2508763 | -66404.58 | 66404.58 | 0 | 2025-01-28 | 5 | 2630463.77 | -55296.19 | DOWN | 0.0215 | 94 | Low | 968652.66 | 0.405 | 2 | 1540110.34 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP021 | 2025-02 | 2024-10-30 | 3333551.94 | 2163292 | -1170259.94 | 1170259.94 | 1 | 2025-02-28 | 1 |  |  |  |  | 121 | Low | 1050429.41 | 0.31 | 5 | 1112862.59 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP021 | 2025-02 | 2024-11-03 | 2712588.47 | 2163292 | -549296.47 | 549296.47 | 1 | 2025-02-28 | 2 | 3333551.94 | -620963.47 | DOWN | 0.2289 | 117 | Low | 897476.85 | 0.323 | 3 | 1265815.15 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP021 | 2025-02 | 2024-11-21 | 2477833.1 | 2163292 | -314541.1 | 314541.1 | 0 | 2025-02-28 | 3 | 2712588.47 | -234755.37 | DOWN | 0.0947 | 99 | Low | 870247.23 | 0.379 | 4 | 1293044.77 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP021 | 2025-02 | 2024-12-19 | 2253455.02 | 2163292 | -90163.02 | 90163.02 | 0 | 2025-02-28 | 4 | 2477833.1 | -224378.08 | DOWN | 0.0996 | 71 | Low | 1028380.37 | 0.467 | 4 | 1134911.63 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP021 | 2025-02 | 2025-01-21 | 2202083.51 | 2163292 | -38791.51 | 38791.51 | 0 | 2025-02-28 | 5 | 2253455.02 | -51371.51 | DOWN | 0.0233 | 38 | Low | 1345574.45 | 0.57 | 2 | 817717.55 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP021 | 2025-02 | 2025-01-30 | 2197583.83 | 2163292 | -34291.83 | 34291.83 | 0 | 2025-02-28 | 6 | 2202083.51 | -4499.68 | DOWN | 0.002 | 29 | Low | 1239771.69 | 0.598 | 0 | 923520.31 | 17 | 2.1 | 1.03
P003 | Logistics | SUP021 | 2025-03 | 2024-11-05 | 278550.64 | 165649 | -112901.64 | 112901.64 | 1 | 2025-03-28 | 1 |  |  |  |  | 143 | Low | 69084.16 | 0.269 | 0 | 96564.84 | 13 | 1.13 | 1.73
P003 | Logistics | SUP021 | 2025-03 | 2025-01-18 | 211912.42 | 165649 | -46263.42 | 46263.42 | 1 | 2025-03-28 | 2 | 278550.64 | -66638.22 | DOWN | 0.3145 | 69 | Low | 109916.48 | 0.527 | 2 | 55732.52 | 13 | 1.13 | 1.73
P003 | Logistics | SUP021 | 2025-03 | 2025-01-29 | 189539.19 | 165649 | -23890.19 | 23890.19 | 0 | 2025-03-28 | 3 | 211912.42 | -22373.23 | DOWN | 0.118 | 58 | Medium | 102316.24 | 0.566 | 6 | 63332.76 | 13 | 1.13 | 1.73
P003 | Logistics | SUP021 | 2025-03 | 2025-02-12 | 172094.69 | 165649 | -6445.69 | 6445.69 | 0 | 2025-03-28 | 4 | 189539.19 | -17444.5 | DOWN | 0.1014 | 44 | Medium | 110529.43 | 0.614 | 2 | 55119.57 | 13 | 1.13 | 1.73
P003 | Logistics | SUP021 | 2025-03 | 2025-02-23 | 168990.86 | 165649 | -3341.86 | 3341.86 | 0 | 2025-03-28 | 5 | 172094.69 | -3103.83 | DOWN | 0.0184 | 33 | Medium | 107603.92 | 0.653 | 1 | 58045.08 | 13 | 1.13 | 1.73
P003 | Electronics | SUP021 | 2025-04 | 2024-11-16 | 795330.33 | 520357 | -274973.33 | 274973.33 | 1 | 2025-04-28 | 1 |  |  |  |  | 163 | Low | 151733.1 | 0.197 | 2 | 368623.9 | 13 | 1.21 | 1.27
P003 | Electronics | SUP021 | 2025-04 | 2024-11-23 | 645937.77 | 520357 | -125580.77 | 125580.77 | 1 | 2025-04-28 | 2 | 795330.33 | -149392.56 | DOWN | 0.2313 | 156 | Low | 148287.26 | 0.221 | 4 | 372069.74 | 13 | 1.21 | 1.27
P003 | Electronics | SUP021 | 2025-04 | 2024-12-12 | 585346.36 | 520357 | -64989.36 | 64989.36 | 0 | 2025-04-28 | 3 | 645937.77 | -60591.41 | DOWN | 0.1035 | 137 | Low | 161650.1 | 0.287 | 2 | 358706.9 | 13 | 1.21 | 1.27
P003 | Electronics | SUP021 | 2025-04 | 2024-12-18 | 550403.68 | 520357 | -30046.68 | 30046.68 | 0 | 2025-04-28 | 4 | 585346.36 | -34942.68 | DOWN | 0.0635 | 131 | Low | 173001.69 | 0.308 | 3 | 347355.31 | 13 | 1.21 | 1.27
P003 | Electronics | SUP021 | 2025-04 | 2025-02-16 | 535676.79 | 520357 | -15319.79 | 15319.79 | 0 | 2025-04-28 | 5 | 550403.68 | -14726.89 | DOWN | 0.0275 | 71 | Low | 272880.04 | 0.515 | 0 | 247476.96 | 13 | 1.21 | 1.27
P003 | Electronics | SUP021 | 2025-04 | 2025-03-23 | 532457.76 | 520357 | -12100.76 | 12100.76 | 0 | 2025-04-28 | 6 | 535676.79 | -3219.03 | DOWN | 0.006 | 36 | Medium | 321525.65 | 0.636 | 5 | 198831.35 | 13 | 1.21 | 1.27
P003 | Software | SUP021 | 2025-05 | 2024-12-11 | 297412.71 | 176349 | -121063.71 | 121063.71 | 1 | 2025-05-28 | 1 |  |  |  |  | 168 | Low | 49796.32 | 0.177 | 0 | 126552.68 | 14 | 1.36 | 1.73
P003 | Software | SUP021 | 2025-05 | 2024-12-23 | 225609.46 | 176349 | -49260.46 | 49260.46 | 1 | 2025-05-28 | 2 | 297412.71 | -71803.25 | DOWN | 0.3183 | 156 | Low | 49473.67 | 0.218 | 2 | 126875.33 | 14 | 1.36 | 1.73
P003 | Software | SUP021 | 2025-05 | 2025-01-01 | 195766.76 | 176349 | -19417.76 | 19417.76 | 0 | 2025-05-28 | 3 | 225609.46 | -29842.7 | DOWN | 0.1524 | 147 | Low | 45764.52 | 0.248 | 2 | 130584.48 | 14 | 1.36 | 1.73
P003 | Software | SUP021 | 2025-05 | 2025-02-06 | 188535.85 | 176349 | -12186.85 | 12186.85 | 0 | 2025-05-28 | 4 | 195766.76 | -7230.91 | DOWN | 0.0384 | 111 | Low | 74556.44 | 0.37 | 3 | 101792.56 | 14 | 1.36 | 1.73
P003 | Software | SUP021 | 2025-05 | 2025-02-10 | 177732.23 | 176349 | -1383.23 | 1383.23 | 0 | 2025-05-28 | 5 | 188535.85 | -10803.62 | DOWN | 0.0608 | 107 | Low | 69187.03 | 0.384 | 5 | 107161.97 | 14 | 1.36 | 1.73
P003 | Software | SUP021 | 2025-05 | 2025-02-11 | 175385.76 | 176349 | 963.24 | 963.24 | 0 | 2025-05-28 | 6 | 177732.23 | -2346.47 | DOWN | 0.0134 | 106 | Low | 66501.82 | 0.387 | 3 | 109847.18 | 14 | 1.36 | 1.73
P003 | Services | SUP021 | 2025-06 | 2025-02-06 | 2983171.24 | 1817875 | -1165296.24 | 1165296.24 | 1 | 2025-06-28 | 1 |  |  |  |  | 142 | Low | 728181.52 | 0.262 | 1 | 1089693.48 | 22 | 1.47 | 1.51
P003 | Services | SUP021 | 2025-06 | 2025-05-09 | 2370455.25 | 1817875 | -552580.25 | 552580.25 | 1 | 2025-06-28 | 2 | 2983171.24 | -612715.99 | DOWN | 0.2585 | 50 | Low | 1456762.02 | 0.571 | 3 | 361112.98 | 22 | 1.47 | 1.51
P003 | Services | SUP021 | 2025-06 | 2025-05-10 | 2070413.1 | 1817875 | -252538.1 | 252538.1 | 0 | 2025-06-28 | 3 | 2370455.25 | -300042.15 | DOWN | 0.1449 | 49 | Low | 1133528.93 | 0.574 | 6 | 684346.07 | 22 | 1.47 | 1.51
P003 | Services | SUP021 | 2025-06 | 2025-05-19 | 1931302.02 | 1817875 | -113427.02 | 113427.02 | 0 | 2025-06-28 | 4 | 2070413.1 | -139111.08 | DOWN | 0.072 | 40 | Medium | 1076782.92 | 0.604 | 5 | 741092.08 | 22 | 1.47 | 1.51
P003 | Materials | SUP021 | 2025-07 | 2025-03-25 | 1546961.54 | 1273480 | -273481.54 | 273481.54 | 1 | 2025-07-28 | 1 |  |  |  |  | 125 | Low | 500924.44 | 0.337 | 3 | 772555.56 | 13 | 0.8 | 1.22
P003 | Materials | SUP021 | 2025-07 | 2025-04-16 | 1382729.65 | 1273480 | -109249.65 | 109249.65 | 0 | 2025-07-28 | 2 | 1546961.54 | -164231.89 | DOWN | 0.1188 | 103 | Low | 542571.38 | 0.415 | 6 | 730908.62 | 13 | 0.8 | 1.22
P003 | Materials | SUP021 | 2025-07 | 2025-04-26 | 1313574.13 | 1273480 | -40094.13 | 40094.13 | 0 | 2025-07-28 | 3 | 1382729.65 | -69155.52 | DOWN | 0.0526 | 93 | Low | 556306.08 | 0.45 | 5 | 717173.92 | 13 | 0.8 | 1.22
P003 | Materials | SUP021 | 2025-07 | 2025-07-03 | 1286535.56 | 1273480 | -13055.56 | 13055.56 | 0 | 2025-07-28 | 4 | 1313574.13 | -27038.57 | DOWN | 0.021 | 25 | High | 873808.37 | 0.691 | 4 | 399671.63 | 13 | 0.8 | 1.22
P003 | Services | SUP021 | 2025-08 | 2025-03-31 | 540224.5 | 327932 | -212292.5 | 212292.5 | 1 | 2025-08-28 | 1 |  |  |  |  | 150 | Low | 133176.1 | 0.238 | 1 | 194755.9 | 7 | 1.37 | 1.47
P003 | Services | SUP021 | 2025-08 | 2025-04-06 | 427109.67 | 327932 | -99177.67 | 99177.67 | 1 | 2025-08-28 | 2 | 540224.5 | -113114.83 | DOWN | 0.2648 | 144 | Low | 112783.93 | 0.258 | 0 | 215148.07 | 7 | 1.37 | 1.47
P003 | Services | SUP021 | 2025-08 | 2025-06-08 | 373202.77 | 327932 | -45270.77 | 45270.77 | 0 | 2025-08-28 | 3 | 427109.67 | -53906.9 | DOWN | 0.1444 | 81 | Low | 170711.37 | 0.472 | 4 | 157220.63 | 7 | 1.37 | 1.47
P003 | Services | SUP021 | 2025-08 | 2025-07-18 | 344253.8 | 327932 | -16321.8 | 16321.8 | 0 | 2025-08-28 | 4 | 373202.77 | -28948.97 | DOWN | 0.0841 | 41 | Medium | 201482.48 | 0.608 | 4 | 126449.52 | 7 | 1.37 | 1.47
P003 | Materials | SUP021 | 2025-09 | 2025-04-11 | 1443575.7 | 1025268 | -418307.7 | 418307.7 | 1 | 2025-09-28 | 1 |  |  |  |  | 170 | Low | 244915.27 | 0.177 | 4 | 780352.73 | 10 | 0.71 | 1.27
P003 | Materials | SUP021 | 2025-09 | 2025-04-14 | 1224291.24 | 1025268 | -199023.24 | 199023.24 | 1 | 2025-09-28 | 2 | 1443575.7 | -219284.46 | DOWN | 0.1791 | 167 | Low | 212848.71 | 0.188 | 0 | 812419.29 | 10 | 0.71 | 1.27
P003 | Materials | SUP021 | 2025-09 | 2025-04-25 | 1118065.8 | 1025268 | -92797.8 | 92797.8 | 0 | 2025-09-28 | 3 | 1224291.24 | -106225.44 | DOWN | 0.095 | 156 | Low | 243232.71 | 0.227 | 0 | 782035.29 | 10 | 0.71 | 1.27
P003 | Materials | SUP021 | 2025-09 | 2025-09-01 | 1065028.82 | 1025268 | -39760.82 | 39760.82 | 0 | 2025-09-28 | 4 | 1118065.8 | -53036.98 | DOWN | 0.0498 | 27 | High | 708832.12 | 0.684 | 5 | 316435.88 | 10 | 0.71 | 1.27
P003 | Materials | SUP021 | 2025-10 | 2025-05-31 | 337943.45 | 209202 | -128741.45 | 128741.45 | 1 | 2025-10-28 | 1 |  |  |  |  | 150 | Low | 82688.2 | 0.248 | 1 | 126513.8 | 19 | 0.95 | 0.98
P003 | Materials | SUP021 | 2025-10 | 2025-06-16 | 267268.94 | 209202 | -58066.94 | 58066.94 | 1 | 2025-10-28 | 2 | 337943.45 | -70674.51 | DOWN | 0.2644 | 134 | Low | 79795.6 | 0.305 | 2 | 129406.4 | 19 | 0.95 | 0.98
P003 | Materials | SUP021 | 2025-10 | 2025-08-15 | 236521.42 | 209202 | -27319.42 | 27319.42 | 0 | 2025-10-28 | 3 | 267268.94 | -30747.52 | DOWN | 0.13 | 74 | Low | 117766.06 | 0.518 | 10 | 91435.94 | 19 | 0.95 | 0.98
P003 | Materials | SUP021 | 2025-10 | 2025-09-20 | 222571.38 | 209202 | -13369.38 | 13369.38 | 0 | 2025-10-28 | 4 | 236521.42 | -13950.04 | DOWN | 0.0627 | 38 | Medium | 155046.67 | 0.645 | 4 | 54155.33 | 19 | 0.95 | 0.98
P003 | Materials | SUP021 | 2025-11 | 2025-07-02 | 3201066.84 | 1994466 | -1206600.84 | 1206600.84 | 1 | 2025-11-28 | 1 |  |  |  |  | 149 | Low | 707535.62 | 0.228 | 0 | 1286930.38 | 11 | 1.85 | 1.52
P003 | Materials | SUP021 | 2025-11 | 2025-08-06 | 2567633.88 | 1994466 | -573167.88 | 573167.88 | 1 | 2025-11-28 | 2 | 3201066.84 | -633432.96 | DOWN | 0.2467 | 114 | Low | 855341.6 | 0.341 | 1 | 1139124.4 | 11 | 1.85 | 1.52
P003 | Materials | SUP021 | 2025-11 | 2025-10-18 | 2251619.99 | 1994466 | -257153.99 | 257153.99 | 0 | 2025-11-28 | 3 | 2567633.88 | -316013.89 | DOWN | 0.1403 | 41 | Low | 1279747.98 | 0.576 | 0 | 714718.02 | 11 | 1.85 | 1.52
P003 | Materials | SUP021 | 2025-12 | 2025-07-12 | 2298127.26 | 1590246 | -707881.26 | 707881.26 | 1 | 2025-12-28 | 1 |  |  |  |  | 169 | Low | 402794.36 | 0.179 | 2 | 1187451.64 | 10 | 1.08 | 1.22
P003 | Materials | SUP021 | 2025-12 | 2025-08-29 | 1895285 | 1590246 | -305039 | 305039 | 1 | 2025-12-28 | 2 | 2298127.26 | -402842.26 | DOWN | 0.2125 | 121 | Low | 689704.71 | 0.348 | 1 | 900541.29 | 10 | 1.08 | 1.22
P003 | Materials | SUP021 | 2025-12 | 2025-09-23 | 1728502.86 | 1590246 | -138256.86 | 138256.86 | 0 | 2025-12-28 | 3 | 1895285 | -166782.14 | DOWN | 0.0965 | 96 | Low | 789053.75 | 0.435 | 2 | 801192.25 | 10 | 1.08 | 1.22
P003 | Materials | SUP021 | 2025-12 | 2025-10-08 | 1663903.86 | 1590246 | -73657.86 | 73657.86 | 0 | 2025-12-28 | 4 | 1728502.86 | -64599 | DOWN | 0.0388 | 81 | Low | 790343.07 | 0.488 | 5 | 799902.93 | 10 | 1.08 | 1.22
P003 | Materials | SUP021 | 2025-12 | 2025-10-29 | 1627173.96 | 1590246 | -36927.96 | 36927.96 | 0 | 2025-12-28 | 5 | 1663903.86 | -36729.9 | DOWN | 0.0226 | 60 | Medium | 893477.37 | 0.562 | 5 | 696768.63 | 10 | 1.08 | 1.22
P003 | Materials | SUP021 | 2025-12 | 2025-12-05 | 1600861.15 | 1590246 | -10615.15 | 10615.15 | 0 | 2025-12-28 | 6 | 1627173.96 | -26312.81 | DOWN | 0.0164 | 23 | High | 1110031.28 | 0.692 | 2 | 480214.72 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP014 | 2025-01 | 2024-08-14 | 2043658.64 | 1289086 | -754572.64 | 754572.64 | 1 | 2025-01-28 | 1 |  |  |  |  | 167 | Low | 243260.66 | 0.12 | 1 | 1045825.34 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP014 | 2025-01 | 2024-09-12 | 1708241.19 | 1289086 | -419155.19 | 419155.19 | 1 | 2025-01-28 | 2 | 2043658.64 | -335417.45 | DOWN | 0.1964 | 138 | Low | 337117.01 | 0.186 | 4 | 951968.99 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP014 | 2025-01 | 2025-01-06 | 1541059.8 | 1289086 | -251973.8 | 251973.8 | 1 | 2025-01-28 | 3 | 1708241.19 | -167181.39 | DOWN | 0.1085 | 22 | Low | 636391.55 | 0.449 | 3 | 652694.45 | 17 | 1.86 | 1.34
P003 | Materials | SUP014 | 2025-02 | 2024-09-10 | 3679369.02 | 2107438 | -1571931.02 | 1571931.02 | 1 | 2025-02-28 | 1 |  |  |  |  | 171 | Low | 419942.67 | 0.108 | 1 | 1687495.33 | 17 | 2.1 | 1.03
P003 | Materials | SUP014 | 2025-02 | 2024-10-30 | 3071628.23 | 2107438 | -964190.23 | 964190.23 | 1 | 2025-02-28 | 2 | 3679369.02 | -607740.79 | DOWN | 0.1979 | 121 | Low | 654334.82 | 0.219 | 0 | 1453103.18 | 17 | 2.1 | 1.03
P003 | Materials | SUP014 | 2025-02 | 2024-11-15 | 2666883.38 | 2107438 | -559445.38 | 559445.38 | 1 | 2025-02-28 | 3 | 3071628.23 | -404744.85 | DOWN | 0.1518 | 105 | Low | 651504.19 | 0.254 | 4 | 1455933.81 | 17 | 2.1 | 1.03
P003 | Materials | SUP014 | 2025-02 | 2024-12-07 | 2480462.25 | 2107438 | -373024.25 | 373024.25 | 1 | 2025-02-28 | 4 | 2666883.38 | -186421.13 | DOWN | 0.0752 | 83 | Low | 799421.44 | 0.303 | 6 | 1308016.56 | 17 | 2.1 | 1.03
P003 | Materials | SUP014 | 2025-02 | 2024-12-18 | 2308464.37 | 2107438 | -201026.37 | 201026.37 | 0 | 2025-02-28 | 5 | 2480462.25 | -171997.88 | DOWN | 0.0745 | 72 | Low | 753616.76 | 0.327 | 1 | 1353821.24 | 17 | 2.1 | 1.03
P003 | Materials | SUP014 | 2025-02 | 2025-02-12 | 2238574.63 | 2107438 | -131136.63 | 131136.63 | 0 | 2025-02-28 | 6 | 2308464.37 | -69889.74 | DOWN | 0.0312 | 16 | Low | 988357.36 | 0.451 | 0 | 1119080.64 | 17 | 2.1 | 1.03
P003 | Materials | SUP014 | 2025-03 | 2024-10-08 | 182355.32 | 131387 | -50968.32 | 50968.32 | 1 | 2025-03-28 | 1 |  |  |  |  | 171 | Low | 20901.76 | 0.121 | 1 | 110485.24 | 13 | 1.13 | 1.73
P003 | Materials | SUP014 | 2025-03 | 2024-10-11 | 160892.19 | 131387 | -29505.19 | 29505.19 | 1 | 2025-03-28 | 2 | 182355.32 | -21463.13 | DOWN | 0.1334 | 168 | Low | 19244.48 | 0.128 | 0 | 112142.52 | 13 | 1.13 | 1.73
P003 | Materials | SUP014 | 2025-03 | 2024-12-25 | 150238.6 | 131387 | -18851.6 | 18851.6 | 0 | 2025-03-28 | 3 | 160892.19 | -10653.59 | DOWN | 0.0709 | 93 | Low | 44250.27 | 0.313 | 2 | 87136.73 | 13 | 1.13 | 1.73
P003 | Materials | SUP014 | 2025-03 | 2025-01-22 | 142492.14 | 131387 | -11105.14 | 11105.14 | 0 | 2025-03-28 | 4 | 150238.6 | -7746.46 | DOWN | 0.0544 | 65 | Low | 52030.44 | 0.382 | 1 | 79356.56 | 13 | 1.13 | 1.73
P003 | Software | SUP014 | 2025-04 | 2025-02-09 | 432969.33 | 242316 | -190653.33 | 190653.33 | 1 | 2025-04-28 | 1 |  |  |  |  | 78 | Low | 151488.03 | 0.346 | 3 | 90827.97 | 13 | 1.21 | 1.27
P003 | Software | SUP014 | 2025-04 | 2025-02-14 | 364757 | 242316 | -122441 | 122441 | 1 | 2025-04-28 | 2 | 432969.33 | -68212.33 | DOWN | 0.187 | 73 | Low | 140955.92 | 0.358 | 1 | 101360.08 | 13 | 1.21 | 1.27
P003 | Software | SUP014 | 2025-04 | 2025-02-22 | 321103.08 | 242316 | -78787.08 | 78787.08 | 1 | 2025-04-28 | 3 | 364757 | -43653.92 | DOWN | 0.1359 | 65 | Low | 120734.48 | 0.378 | 0 | 121581.52 | 13 | 1.21 | 1.27
P003 | Software | SUP014 | 2025-04 | 2025-03-11 | 288132.83 | 242316 | -45816.83 | 45816.83 | 1 | 2025-04-28 | 4 | 321103.08 | -32970.25 | DOWN | 0.1144 | 48 | Low | 129193.77 | 0.419 | 7 | 113122.23 | 13 | 1.21 | 1.27
P003 | Software | SUP014 | 2025-04 | 2025-04-04 | 266228.57 | 242316 | -23912.57 | 23912.57 | 0 | 2025-04-28 | 5 | 288132.83 | -21904.26 | DOWN | 0.0823 | 24 | Medium | 120116.32 | 0.478 | 7 | 122199.68 | 13 | 1.21 | 1.27
P003 | Logistics | SUP014 | 2025-05 | 2025-01-01 | 1612011.8 | 1007315 | -604696.8 | 604696.8 | 1 | 2025-05-28 | 1 |  |  |  |  | 147 | Low | 273349.54 | 0.175 | 2 | 733965.46 | 14 | 1.36 | 1.73
P003 | Logistics | SUP014 | 2025-05 | 2025-01-14 | 1350259.32 | 1007315 | -342944.32 | 342944.32 | 1 | 2025-05-28 | 2 | 1612011.8 | -261752.48 | DOWN | 0.1939 | 134 | Low | 268313.42 | 0.206 | 2 | 739001.58 | 14 | 1.36 | 1.73
P003 | Logistics | SUP014 | 2025-05 | 2025-02-13 | 1183152.89 | 1007315 | -175837.89 | 175837.89 | 0 | 2025-05-28 | 3 | 1350259.32 | -167106.43 | DOWN | 0.1412 | 104 | Low | 303643.5 | 0.278 | 2 | 703671.5 | 14 | 1.36 | 1.73
P003 | Logistics | SUP014 | 2025-05 | 2025-02-17 | 1118685.48 | 1007315 | -111370.48 | 111370.48 | 0 | 2025-05-28 | 4 | 1183152.89 | -64467.41 | DOWN | 0.0576 | 100 | Low | 303512.65 | 0.288 | 0 | 703802.35 | 14 | 1.36 | 1.73
P003 | Materials | SUP014 | 2025-06 | 2025-02-19 | 1420576.61 | 972524 | -448052.61 | 448052.61 | 1 | 2025-06-28 | 1 |  |  |  |  | 129 | Low | 290510.46 | 0.215 | 1 | 682013.54 | 22 | 1.47 | 1.51
P003 | Materials | SUP014 | 2025-06 | 2025-03-18 | 1241371.87 | 972524 | -268847.87 | 268847.87 | 1 | 2025-06-28 | 2 | 1420576.61 | -179204.74 | DOWN | 0.1444 | 102 | Low | 329197.84 | 0.279 | 2 | 643326.16 | 22 | 1.47 | 1.51
P003 | Materials | SUP014 | 2025-06 | 2025-04-23 | 1131725.62 | 972524 | -159201.62 | 159201.62 | 0 | 2025-06-28 | 3 | 1241371.87 | -109646.25 | DOWN | 0.0969 | 66 | Low | 430392.76 | 0.364 | 2 | 542131.24 | 22 | 1.47 | 1.51
P003 | Materials | SUP014 | 2025-06 | 2025-05-07 | 1057814.48 | 972524 | -85290.48 | 85290.48 | 0 | 2025-06-28 | 4 | 1131725.62 | -73911.14 | DOWN | 0.0699 | 52 | Low | 435847.14 | 0.398 | 1 | 536676.86 | 22 | 1.47 | 1.51
P003 | Materials | SUP014 | 2025-06 | 2025-06-13 | 1020940.71 | 972524 | -48416.71 | 48416.71 | 0 | 2025-06-28 | 5 | 1057814.48 | -36873.77 | DOWN | 0.0361 | 15 | Medium | 458112.45 | 0.485 | 1 | 514411.55 | 22 | 1.47 | 1.51
P003 | Materials | SUP014 | 2025-06 | 2025-06-18 | 1010387.34 | 972524 | -37863.34 | 37863.34 | 0 | 2025-06-28 | 6 | 1020940.71 | -10553.37 | DOWN | 0.0104 | 10 | Medium | 472329.71 | 0.495 | 5 | 500194.29 | 22 | 1.47 | 1.51
P003 | Services | SUP014 | 2025-07 | 2025-03-06 | 1274222.16 | 696045 | -578177.16 | 578177.16 | 1 | 2025-07-28 | 1 |  |  |  |  | 144 | Low | 235204.41 | 0.19 | 0 | 460840.59 | 13 | 0.8 | 1.22
P003 | Services | SUP014 | 2025-07 | 2025-05-25 | 1047961.37 | 696045 | -351916.37 | 351916.37 | 1 | 2025-07-28 | 2 | 1274222.16 | -226260.79 | DOWN | 0.2159 | 64 | Low | 403675.54 | 0.39 | 2 | 292369.46 | 13 | 0.8 | 1.22
P003 | Services | SUP014 | 2025-07 | 2025-05-25 | 894943.16 | 696045 | -198898.16 | 198898.16 | 1 | 2025-07-28 | 3 | 1047961.37 | -153018.21 | DOWN | 0.171 | 64 | Low | 335935.84 | 0.39 | 2 | 360109.16 | 13 | 0.8 | 1.22
P003 | Services | SUP014 | 2025-07 | 2025-07-18 | 804608.77 | 696045 | -108563.77 | 108563.77 | 0 | 2025-07-28 | 4 | 894943.16 | -90334.39 | DOWN | 0.1123 | 10 | Medium | 436978.88 | 0.522 | 3 | 259066.12 | 13 | 0.8 | 1.22
P003 | Software | SUP014 | 2025-08 | 2025-03-25 | 1327053.96 | 701570 | -625483.96 | 625483.96 | 1 | 2025-08-28 | 1 |  |  |  |  | 156 | Low | 196162.2 | 0.153 | 0 | 505407.8 | 7 | 1.37 | 1.47
P003 | Software | SUP014 | 2025-08 | 2025-05-27 | 1075930.21 | 701570 | -374360.21 | 374360.21 | 1 | 2025-08-28 | 2 | 1327053.96 | -251123.75 | DOWN | 0.2334 | 93 | Low | 338192.1 | 0.304 | 1 | 363377.9 | 7 | 1.37 | 1.47
P003 | Software | SUP014 | 2025-08 | 2025-07-16 | 931687.02 | 701570 | -230117.02 | 230117.02 | 1 | 2025-08-28 | 3 | 1075930.21 | -144243.19 | DOWN | 0.1548 | 43 | Low | 366887.33 | 0.424 | 0 | 334682.67 | 7 | 1.37 | 1.47
P003 | Materials | SUP014 | 2025-09 | 2025-04-09 | 1303882.28 | 755938 | -547944.28 | 547944.28 | 1 | 2025-09-28 | 1 |  |  |  |  | 172 | Low | 165848.61 | 0.12 | 3 | 590089.39 | 10 | 0.71 | 1.27
P003 | Materials | SUP014 | 2025-09 | 2025-06-23 | 1089750.12 | 755938 | -333812.12 | 333812.12 | 1 | 2025-09-28 | 2 | 1303882.28 | -214132.16 | DOWN | 0.1965 | 97 | Low | 347726.05 | 0.307 | 4 | 408211.95 | 10 | 0.71 | 1.27
P003 | Materials | SUP014 | 2025-09 | 2025-06-30 | 946679.35 | 755938 | -190741.35 | 190741.35 | 1 | 2025-09-28 | 3 | 1089750.12 | -143070.77 | DOWN | 0.1511 | 90 | Low | 298187.81 | 0.325 | 3 | 457750.19 | 10 | 0.71 | 1.27
P003 | Materials | SUP014 | 2025-09 | 2025-07-09 | 864571.5 | 755938 | -108633.5 | 108633.5 | 0 | 2025-09-28 | 4 | 946679.35 | -82107.85 | DOWN | 0.095 | 81 | Low | 282526.69 | 0.348 | 3 | 473411.31 | 10 | 0.71 | 1.27
P003 | Materials | SUP014 | 2025-09 | 2025-08-03 | 814322.15 | 755938 | -58384.15 | 58384.15 | 0 | 2025-09-28 | 5 | 864571.5 | -50249.35 | DOWN | 0.0617 | 56 | Low | 313768.02 | 0.41 | 7 | 442169.98 | 10 | 0.71 | 1.27
P003 | Materials | SUP014 | 2025-09 | 2025-09-16 | 796441.98 | 755938 | -40503.98 | 40503.98 | 0 | 2025-09-28 | 6 | 814322.15 | -17880.17 | DOWN | 0.0225 | 12 | Medium | 409693.65 | 0.52 | 6 | 346244.35 | 10 | 0.71 | 1.27
P003 | Mechanical | SUP014 | 2025-10 | 2025-05-22 | 1099651.58 | 786827 | -312824.58 | 312824.58 | 1 | 2025-10-28 | 1 |  |  |  |  | 159 | Low | 170575.6 | 0.152 | 0 | 616251.4 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP014 | 2025-10 | 2025-06-27 | 977690.83 | 786827 | -190863.83 | 190863.83 | 1 | 2025-10-28 | 2 | 1099651.58 | -121960.75 | DOWN | 0.1247 | 123 | Low | 253810.05 | 0.243 | 1 | 533016.95 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP014 | 2025-10 | 2025-06-29 | 900618.85 | 786827 | -113791.85 | 113791.85 | 0 | 2025-10-28 | 3 | 977690.83 | -77071.98 | DOWN | 0.0856 | 121 | Low | 235709.1 | 0.247 | 3 | 551117.9 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP014 | 2025-10 | 2025-07-19 | 857227.88 | 786827 | -70400.88 | 70400.88 | 0 | 2025-10-28 | 4 | 900618.85 | -43390.97 | DOWN | 0.0506 | 101 | Low | 238511.41 | 0.298 | 5 | 548315.59 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP014 | 2025-10 | 2025-07-27 | 833195.57 | 786827 | -46368.57 | 46368.57 | 0 | 2025-10-28 | 5 | 857227.88 | -24032.31 | DOWN | 0.0288 | 93 | Low | 248310.16 | 0.318 | 0 | 538516.84 | 19 | 0.95 | 0.98
P003 | Services | SUP014 | 2025-11 | 2025-07-13 | 2259490.5 | 1450366 | -809124.5 | 809124.5 | 1 | 2025-11-28 | 1 |  |  |  |  | 138 | Low | 404232.85 | 0.186 | 5 | 1046133.15 | 11 | 1.85 | 1.52
P003 | Services | SUP014 | 2025-11 | 2025-09-18 | 1993175.92 | 1450366 | -542809.92 | 542809.92 | 1 | 2025-11-28 | 2 | 2259490.5 | -266314.58 | DOWN | 0.1336 | 71 | Low | 690042.84 | 0.338 | 3 | 760323.16 | 11 | 1.85 | 1.52
P003 | Services | SUP014 | 2025-11 | 2025-11-11 | 1738757.61 | 1450366 | -288391.61 | 288391.61 | 1 | 2025-11-28 | 3 | 1993175.92 | -254418.31 | DOWN | 0.1463 | 17 | Low | 754198.93 | 0.461 | 8 | 696167.07 | 11 | 1.85 | 1.52
P003 | Materials | SUP014 | 2025-12 | 2025-08-06 | 295041.29 | 175472 | -119569.29 | 119569.29 | 1 | 2025-12-28 | 1 |  |  |  |  | 144 | Low | 57141.46 | 0.188 | 4 | 118330.54 | 10 | 1.08 | 1.22
P003 | Materials | SUP014 | 2025-12 | 2025-10-17 | 245831.26 | 175472 | -70359.26 | 70359.26 | 1 | 2025-12-28 | 2 | 295041.29 | -49210.03 | DOWN | 0.2002 | 72 | Low | 88844.15 | 0.366 | 0 | 86627.85 | 10 | 1.08 | 1.22
P003 | Materials | SUP014 | 2025-12 | 2025-12-08 | 218939.11 | 175472 | -43467.11 | 43467.11 | 1 | 2025-12-28 | 3 | 245831.26 | -26892.15 | DOWN | 0.1228 | 20 | Low | 108653.82 | 0.495 | 1 | 66818.18 | 10 | 1.08 | 1.22
P003 | Logistics | SUP003 | 2025-01 | 2024-09-13 | 5554679.26 | 2048571 | -3506108.26 | 3506108.26 | 1 | 2025-01-28 | 1 |  |  |  |  | 137 | Low | 917954.85 | 0.171 | 3 | 1130616.15 | 17 | 1.86 | 1.34
P003 | Logistics | SUP003 | 2025-01 | 2024-10-13 | 4756121.25 | 2048571 | -2707550.25 | 2707550.25 | 1 | 2025-01-28 | 2 | 5554679.26 | -798558.01 | DOWN | 0.1679 | 107 | Low | 1176129.57 | 0.233 | 3 | 872441.43 | 17 | 1.86 | 1.34
P003 | Logistics | SUP003 | 2025-01 | 2024-12-09 | 4101141.2 | 2048571 | -2052570.2 | 2052570.2 | 1 | 2025-01-28 | 3 | 4756121.25 | -654980.05 | DOWN | 0.1597 | 50 | Low | 1394092.58 | 0.35 | 1 | 654478.42 | 17 | 1.86 | 1.34
P003 | Logistics | SUP003 | 2025-01 | 2024-12-17 | 3686194.44 | 2048571 | -1637623.44 | 1637623.44 | 1 | 2025-01-28 | 4 | 4101141.2 | -414946.76 | DOWN | 0.1126 | 42 | Low | 1346089.32 | 0.367 | 0 | 702481.68 | 17 | 1.86 | 1.34
P003 | Logistics | SUP003 | 2025-01 | 2024-12-19 | 3251789.87 | 2048571 | -1203218.87 | 1203218.87 | 1 | 2025-01-28 | 5 | 3686194.44 | -434404.57 | DOWN | 0.1336 | 40 | Low | 1199538.75 | 0.371 | 4 | 849032.25 | 17 | 1.86 | 1.34
P003 | Logistics | SUP003 | 2025-01 | 2024-12-29 | 2897451.35 | 2048571 | -848880.35 | 848880.35 | 1 | 2025-01-28 | 6 | 3251789.87 | -354338.52 | DOWN | 0.1223 | 30 | Low | 1192830.98 | 0.391 | 0 | 855740.02 | 17 | 1.86 | 1.34
P003 | Services | SUP003 | 2025-02 | 2024-09-25 | 3897505.81 | 1759814 | -2137691.81 | 2137691.81 | 1 | 2025-02-28 | 1 |  |  |  |  | 156 | Low | 508867.9 | 0.128 | 2 | 1250946.1 | 17 | 2.1 | 1.03
P003 | Services | SUP003 | 2025-02 | 2024-10-20 | 3359836.06 | 1759814 | -1600022.06 | 1600022.06 | 1 | 2025-02-28 | 2 | 3897505.81 | -537669.75 | DOWN | 0.16 | 131 | Low | 563487.09 | 0.179 | 2 | 1196326.91 | 17 | 2.1 | 1.03
P003 | Services | SUP003 | 2025-02 | 2024-12-15 | 2921952.78 | 1759814 | -1162138.78 | 1162138.78 | 1 | 2025-02-28 | 3 | 3359836.06 | -437883.28 | DOWN | 0.1499 | 75 | Low | 915516.15 | 0.291 | 2 | 844297.85 | 17 | 2.1 | 1.03
P003 | Services | SUP003 | 2025-02 | 2025-01-25 | 2634882.87 | 1759814 | -875068.87 | 875068.87 | 1 | 2025-02-28 | 4 | 2921952.78 | -287069.91 | DOWN | 0.1089 | 34 | Low | 1050432.11 | 0.373 | 3 | 709381.89 | 17 | 2.1 | 1.03
P003 | Services | SUP003 | 2025-02 | 2025-02-07 | 2418331.2 | 1759814 | -658517.2 | 658517.2 | 1 | 2025-02-28 | 5 | 2634882.87 | -216551.67 | DOWN | 0.0895 | 21 | Low | 1009330.62 | 0.4 | 3 | 750483.38 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP003 | 2025-03 | 2024-10-29 | 1501940.47 | 895573 | -606367.47 | 606367.47 | 1 | 2025-03-28 | 1 |  |  |  |  | 150 | Low | 230920.62 | 0.157 | 3 | 664652.38 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP003 | 2025-03 | 2025-01-02 | 1355912.72 | 895573 | -460339.72 | 460339.72 | 1 | 2025-03-28 | 2 | 1501940.47 | -146027.75 | DOWN | 0.1077 | 85 | Low | 395265.65 | 0.302 | 0 | 500307.35 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP003 | 2025-03 | 2025-02-06 | 1238682.87 | 895573 | -343109.87 | 343109.87 | 1 | 2025-03-28 | 3 | 1355912.72 | -117229.85 | DOWN | 0.0946 | 50 | Low | 472455.38 | 0.38 | 1 | 423117.62 | 13 | 1.13 | 1.73
P003 | Electronics | SUP003 | 2025-04 | 2024-11-15 | 2370730.18 | 1118922 | -1251808.18 | 1251808.18 | 1 | 2025-04-28 | 1 |  |  |  |  | 164 | Low | 309656.43 | 0.124 | 2 | 809265.57 | 13 | 1.21 | 1.27
P003 | Electronics | SUP003 | 2025-04 | 2024-12-14 | 2057238.27 | 1118922 | -938316.27 | 938316.27 | 1 | 2025-04-28 | 2 | 2370730.18 | -313491.91 | DOWN | 0.1524 | 135 | Low | 380423.48 | 0.188 | 0 | 738498.52 | 13 | 1.21 | 1.27
P003 | Electronics | SUP003 | 2025-04 | 2025-02-01 | 1849364.8 | 1118922 | -730442.8 | 730442.8 | 1 | 2025-04-28 | 3 | 2057238.27 | -207873.47 | DOWN | 0.1124 | 86 | Low | 516445.59 | 0.297 | 0 | 602476.41 | 13 | 1.21 | 1.27
P003 | Electronics | SUP003 | 2025-04 | 2025-02-13 | 1670989.96 | 1118922 | -552067.96 | 552067.96 | 1 | 2025-04-28 | 4 | 1849364.8 | -178374.84 | DOWN | 0.1067 | 74 | Low | 572155.19 | 0.324 | 0 | 546766.81 | 13 | 1.21 | 1.27
P003 | Electronics | SUP003 | 2025-04 | 2025-03-02 | 1515902.95 | 1118922 | -396980.95 | 396980.95 | 1 | 2025-04-28 | 5 | 1670989.96 | -155087.01 | DOWN | 0.1023 | 57 | Low | 577562.28 | 0.361 | 2 | 541359.72 | 13 | 1.21 | 1.27
P003 | Electronics | SUP003 | 2025-04 | 2025-04-17 | 1426634.35 | 1118922 | -307712.35 | 307712.35 | 1 | 2025-04-28 | 6 | 1515902.95 | -89268.6 | DOWN | 0.0626 | 11 | Low | 633545.91 | 0.463 | 2 | 485376.09 | 13 | 1.21 | 1.27
P003 | Materials | SUP003 | 2025-05 | 2024-12-03 | 849546.83 | 465692 | -383854.83 | 383854.83 | 1 | 2025-05-28 | 1 |  |  |  |  | 176 | Low | 75947.1 | 0.096 | 2 | 389744.9 | 14 | 1.36 | 1.73
P003 | Materials | SUP003 | 2025-05 | 2024-12-17 | 757330.09 | 465692 | -291638.09 | 291638.09 | 1 | 2025-05-28 | 2 | 849546.83 | -92216.74 | DOWN | 0.1218 | 162 | Low | 102918.21 | 0.126 | 0 | 362773.79 | 14 | 1.36 | 1.73
P003 | Materials | SUP003 | 2025-05 | 2025-01-25 | 680586.7 | 465692 | -214894.7 | 214894.7 | 1 | 2025-05-28 | 3 | 757330.09 | -76743.39 | DOWN | 0.1128 | 123 | Low | 147419.18 | 0.211 | 3 | 318272.82 | 14 | 1.36 | 1.73
P003 | Materials | SUP003 | 2025-05 | 2025-01-28 | 627619.54 | 465692 | -161927.54 | 161927.54 | 1 | 2025-05-28 | 4 | 680586.7 | -52967.16 | DOWN | 0.0844 | 120 | Low | 129704.93 | 0.218 | 0 | 335987.07 | 14 | 1.36 | 1.73
P003 | Materials | SUP003 | 2025-05 | 2025-04-06 | 586521.11 | 465692 | -120829.11 | 120829.11 | 1 | 2025-05-28 | 5 | 627619.54 | -41098.43 | DOWN | 0.0701 | 52 | Low | 213847.94 | 0.366 | 1 | 251844.06 | 14 | 1.36 | 1.73
P003 | Materials | SUP003 | 2025-05 | 2025-04-12 | 550244.25 | 465692 | -84552.25 | 84552.25 | 1 | 2025-05-28 | 6 | 586521.11 | -36276.86 | DOWN | 0.0659 | 46 | Low | 193541.35 | 0.379 | 2 | 272150.65 | 14 | 1.36 | 1.73
P003 | Services | SUP003 | 2025-06 | 2025-01-24 | 2981059.4 | 1460936 | -1520123.4 | 1520123.4 | 1 | 2025-06-28 | 1 |  |  |  |  | 155 | Low | 415368.65 | 0.14 | 0 | 1045567.35 | 22 | 1.47 | 1.51
P003 | Services | SUP003 | 2025-06 | 2025-02-17 | 2612767.21 | 1460936 | -1151831.21 | 1151831.21 | 1 | 2025-06-28 | 2 | 2981059.4 | -368292.19 | DOWN | 0.141 | 131 | Low | 514551.24 | 0.191 | 0 | 946384.76 | 22 | 1.47 | 1.51
P003 | Services | SUP003 | 2025-06 | 2025-02-19 | 2276461.41 | 1460936 | -815525.41 | 815525.41 | 1 | 2025-06-28 | 3 | 2612767.21 | -336305.8 | DOWN | 0.1477 | 129 | Low | 470307.77 | 0.196 | 0 | 990628.23 | 22 | 1.47 | 1.51
P003 | Services | SUP003 | 2025-06 | 2025-02-26 | 2085676.91 | 1460936 | -624740.91 | 624740.91 | 1 | 2025-06-28 | 4 | 2276461.41 | -190784.5 | DOWN | 0.0915 | 122 | Low | 420607.54 | 0.211 | 0 | 1040328.46 | 22 | 1.47 | 1.51
P003 | Services | SUP003 | 2025-06 | 2025-05-23 | 1915600.53 | 1460936 | -454664.53 | 454664.53 | 1 | 2025-06-28 | 5 | 2085676.91 | -170076.38 | DOWN | 0.0888 | 36 | Low | 699001.68 | 0.396 | 4 | 761934.32 | 22 | 1.47 | 1.51
P003 | Logistics | SUP003 | 2025-07 | 2025-02-15 | 3034503.54 | 1273338 | -1761165.54 | 1761165.54 | 1 | 2025-07-28 | 1 |  |  |  |  | 163 | Low | 417020.27 | 0.13 | 1 | 856317.73 | 13 | 0.8 | 1.22
P003 | Logistics | SUP003 | 2025-07 | 2025-03-11 | 2636799.53 | 1273338 | -1363461.53 | 1363461.53 | 1 | 2025-07-28 | 2 | 3034503.54 | -397704.01 | DOWN | 0.1508 | 139 | Low | 484044.45 | 0.184 | 3 | 789293.55 | 13 | 0.8 | 1.22
P003 | Logistics | SUP003 | 2025-07 | 2025-07-04 | 2284368.76 | 1273338 | -1011030.76 | 1011030.76 | 1 | 2025-07-28 | 3 | 2636799.53 | -352430.77 | DOWN | 0.1543 | 24 | Low | 980361.49 | 0.445 | 0 | 292976.51 | 13 | 0.8 | 1.22
P003 | Materials | SUP003 | 2025-08 | 2025-07-11 | 926360.96 | 585900 | -340460.96 | 340460.96 | 1 | 2025-08-28 | 1 |  |  |  |  | 48 | Low | 363529.29 | 0.374 | 1 | 222370.71 | 7 | 1.37 | 1.47
P003 | Materials | SUP003 | 2025-08 | 2025-08-02 | 839288.24 | 585900 | -253388.24 | 253388.24 | 1 | 2025-08-28 | 2 | 926360.96 | -87072.72 | DOWN | 0.1037 | 26 | Low | 365740.4 | 0.422 | 5 | 220159.6 | 7 | 1.37 | 1.47
P003 | Materials | SUP003 | 2025-08 | 2025-08-05 | 776642.57 | 585900 | -190742.57 | 190742.57 | 1 | 2025-08-28 | 3 | 839288.24 | -62645.67 | DOWN | 0.0807 | 23 | Low | 330682.92 | 0.429 | 4 | 255217.08 | 7 | 1.37 | 1.47
P003 | Materials | SUP003 | 2025-09 | 2025-04-12 | 520658.01 | 313959 | -206699.01 | 206699.01 | 1 | 2025-09-28 | 1 |  |  |  |  | 169 | Low | 59504.07 | 0.116 | 1 | 254454.93 | 10 | 0.71 | 1.27
P003 | Materials | SUP003 | 2025-09 | 2025-06-01 | 473045.22 | 313959 | -159086.22 | 159086.22 | 1 | 2025-09-28 | 2 | 520658.01 | -47612.79 | DOWN | 0.1007 | 119 | Low | 100712.35 | 0.23 | 1 | 213246.65 | 10 | 0.71 | 1.27
P003 | Materials | SUP003 | 2025-09 | 2025-07-05 | 432009.03 | 313959 | -118050.03 | 118050.03 | 1 | 2025-09-28 | 3 | 473045.22 | -41036.19 | DOWN | 0.095 | 85 | Low | 136564.18 | 0.307 | 3 | 177394.82 | 10 | 0.71 | 1.27
P003 | Materials | SUP003 | 2025-09 | 2025-07-11 | 402204.85 | 313959 | -88245.85 | 88245.85 | 1 | 2025-09-28 | 4 | 432009.03 | -29804.18 | DOWN | 0.0741 | 79 | Low | 122651.75 | 0.32 | 0 | 191307.25 | 10 | 0.71 | 1.27
P003 | Materials | SUP003 | 2025-09 | 2025-07-27 | 381252.09 | 313959 | -67293.09 | 67293.09 | 1 | 2025-09-28 | 5 | 402204.85 | -20952.76 | DOWN | 0.055 | 63 | Low | 141126.67 | 0.357 | 0 | 172832.33 | 10 | 0.71 | 1.27
P003 | Materials | SUP003 | 2025-09 | 2025-08-11 | 366930.22 | 313959 | -52971.22 | 52971.22 | 0 | 2025-09-28 | 6 | 381252.09 | -14321.87 | DOWN | 0.039 | 48 | Low | 141612.11 | 0.391 | 1 | 172346.89 | 10 | 0.71 | 1.27
P003 | Services | SUP003 | 2025-10 | 2025-07-02 | 267566.94 | 146506 | -121060.94 | 121060.94 | 1 | 2025-10-28 | 1 |  |  |  |  | 118 | Low | 63824.74 | 0.232 | 0 | 82681.26 | 19 | 0.95 | 0.98
P003 | Services | SUP003 | 2025-10 | 2025-07-20 | 237015.55 | 146506 | -90509.55 | 90509.55 | 1 | 2025-10-28 | 2 | 267566.94 | -30551.39 | DOWN | 0.1289 | 100 | Low | 63368.89 | 0.273 | 1 | 83137.11 | 19 | 0.95 | 0.98
P003 | Services | SUP003 | 2025-10 | 2025-07-23 | 212279.63 | 146506 | -65773.63 | 65773.63 | 1 | 2025-10-28 | 3 | 237015.55 | -24735.92 | DOWN | 0.1165 | 97 | Low | 62639.71 | 0.28 | 0 | 83866.29 | 19 | 0.95 | 0.98
P003 | Electronics | SUP003 | 2025-11 | 2025-07-23 | 3467931.65 | 1630634 | -1837297.65 | 1837297.65 | 1 | 2025-11-28 | 1 |  |  |  |  | 128 | Low | 651218.76 | 0.19 | 1 | 979415.24 | 11 | 1.85 | 1.52
P003 | Electronics | SUP003 | 2025-11 | 2025-08-08 | 3052764.6 | 1630634 | -1422130.6 | 1422130.6 | 1 | 2025-11-28 | 2 | 3467931.65 | -415167.05 | DOWN | 0.136 | 112 | Low | 653879.05 | 0.223 | 4 | 976754.95 | 11 | 1.85 | 1.52
P003 | Electronics | SUP003 | 2025-11 | 2025-11-09 | 2709698.93 | 1630634 | -1079064.93 | 1079064.93 | 1 | 2025-11-28 | 3 | 3052764.6 | -343065.67 | DOWN | 0.1266 | 19 | Low | 1110095.76 | 0.415 | 5 | 520538.24 | 11 | 1.85 | 1.52
P003 | Electronics | SUP003 | 2025-11 | 2025-11-12 | 2451307.28 | 1630634 | -820673.28 | 820673.28 | 1 | 2025-11-28 | 4 | 2709698.93 | -258391.65 | DOWN | 0.1054 | 16 | Low | 997322.21 | 0.421 | 0 | 633311.79 | 11 | 1.85 | 1.52
P003 | Software | SUP003 | 2025-12 | 2025-08-10 | 987022.47 | 548124 | -438898.47 | 438898.47 | 1 | 2025-12-28 | 1 |  |  |  |  | 140 | Low | 190353.59 | 0.18 | 3 | 357770.41 | 10 | 1.08 | 1.22
P003 | Software | SUP003 | 2025-12 | 2025-10-15 | 885496.46 | 548124 | -337372.46 | 337372.46 | 1 | 2025-12-28 | 2 | 987022.47 | -101526.01 | DOWN | 0.1147 | 74 | Low | 283341.72 | 0.329 | 2 | 264782.28 | 10 | 1.08 | 1.22
P003 | Software | SUP003 | 2025-12 | 2025-11-06 | 798523.39 | 548124 | -250399.39 | 250399.39 | 1 | 2025-12-28 | 3 | 885496.46 | -86973.07 | DOWN | 0.1089 | 52 | Low | 282362.68 | 0.378 | 2 | 265761.32 | 10 | 1.08 | 1.22
P003 | Logistics | SUP022 | 2025-01 | 2024-09-18 | 2523505.14 | 1359595 | -1163910.14 | 1163910.14 | 1 | 2025-01-28 | 1 |  |  |  |  | 132 | Low | 519777.99 | 0.199 | 2 | 839817.01 | 17 | 1.86 | 1.34
P003 | Logistics | SUP022 | 2025-01 | 2024-11-06 | 2050553.23 | 1359595 | -690958.23 | 690958.23 | 1 | 2025-01-28 | 2 | 2523505.14 | -472951.91 | DOWN | 0.2306 | 83 | Low | 637193.93 | 0.31 | 1 | 722401.07 | 17 | 1.86 | 1.34
P003 | Logistics | SUP022 | 2025-01 | 2024-11-08 | 1800836.05 | 1359595 | -441241.05 | 441241.05 | 1 | 2025-01-28 | 3 | 2050553.23 | -249717.18 | DOWN | 0.1387 | 81 | Low | 536933.04 | 0.315 | 4 | 822661.96 | 17 | 1.86 | 1.34
P003 | Logistics | SUP022 | 2025-01 | 2024-11-25 | 1666263.13 | 1359595 | -306668.13 | 306668.13 | 1 | 2025-01-28 | 4 | 1800836.05 | -134572.92 | DOWN | 0.0808 | 64 | Low | 558935.23 | 0.354 | 4 | 800659.77 | 17 | 1.86 | 1.34
P003 | Logistics | SUP022 | 2025-01 | 2024-12-29 | 1584658.23 | 1359595 | -225063.23 | 225063.23 | 0 | 2025-01-28 | 5 | 1666263.13 | -81604.9 | DOWN | 0.0515 | 30 | Low | 638269.29 | 0.431 | 6 | 721325.71 | 17 | 1.86 | 1.34
P003 | Logistics | SUP022 | 2025-01 | 2025-01-18 | 1468777.3 | 1359595 | -109182.3 | 109182.3 | 0 | 2025-01-28 | 6 | 1584658.23 | -115880.93 | DOWN | 0.0789 | 10 | Medium | 674028.52 | 0.474 | 2 | 685566.48 | 17 | 1.86 | 1.34
P003 | Logistics | SUP022 | 2025-02 | 2024-09-05 | 2832185.46 | 1364584 | -1467601.46 | 1467601.46 | 1 | 2025-02-28 | 1 |  |  |  |  | 176 | Low | 294055.58 | 0.097 | 1 | 1070528.42 | 17 | 2.1 | 1.03
P003 | Logistics | SUP022 | 2025-02 | 2024-09-22 | 2273795.91 | 1364584 | -909211.91 | 909211.91 | 1 | 2025-02-28 | 2 | 2832185.46 | -558389.55 | DOWN | 0.2456 | 159 | Low | 312146.92 | 0.135 | 0 | 1052437.08 | 17 | 2.1 | 1.03
P003 | Logistics | SUP022 | 2025-02 | 2024-10-15 | 1908089.34 | 1364584 | -543505.34 | 543505.34 | 1 | 2025-02-28 | 3 | 2273795.91 | -365706.57 | DOWN | 0.1917 | 136 | Low | 381984.74 | 0.186 | 2 | 982599.26 | 17 | 2.1 | 1.03
P003 | Logistics | SUP022 | 2025-02 | 2025-01-07 | 1718093.03 | 1364584 | -353509.03 | 353509.03 | 1 | 2025-02-28 | 4 | 1908089.34 | -189996.31 | DOWN | 0.1106 | 52 | Low | 629811.45 | 0.371 | 2 | 734772.55 | 17 | 2.1 | 1.03
P003 | Software | SUP022 | 2025-03 | 2024-10-01 | 4290532.71 | 2555101 | -1735431.71 | 1735431.71 | 1 | 2025-03-28 | 1 |  |  |  |  | 178 | Low | 475827.5 | 0.108 | 0 | 2079273.5 | 13 | 1.13 | 1.73
P003 | Software | SUP022 | 2025-03 | 2024-12-30 | 3598644.57 | 2555101 | -1043543.57 | 1043543.57 | 1 | 2025-03-28 | 2 | 4290532.71 | -691888.14 | DOWN | 0.1923 | 88 | Low | 1177650.38 | 0.325 | 5 | 1377450.62 | 13 | 1.13 | 1.73
P003 | Software | SUP022 | 2025-03 | 2025-01-31 | 3184862.22 | 2555101 | -629761.22 | 629761.22 | 1 | 2025-03-28 | 3 | 3598644.57 | -413782.35 | DOWN | 0.1299 | 56 | Low | 1368351.77 | 0.404 | 4 | 1186749.23 | 13 | 1.13 | 1.73
P003 | Software | SUP022 | 2025-03 | 2025-02-01 | 2992190.63 | 2555101 | -437089.63 | 437089.63 | 0 | 2025-03-28 | 4 | 3184862.22 | -192671.59 | DOWN | 0.0644 | 55 | Low | 1236475.11 | 0.406 | 3 | 1318625.89 | 13 | 1.13 | 1.73
P003 | Materials | SUP022 | 2025-04 | 2024-12-28 | 1939699.33 | 1346319 | -593380.33 | 593380.33 | 1 | 2025-04-28 | 1 |  |  |  |  | 121 | Low | 474649.04 | 0.241 | 4 | 871669.96 | 13 | 1.21 | 1.27
P003 | Materials | SUP022 | 2025-04 | 2025-01-10 | 1701657.58 | 1346319 | -355338.58 | 355338.58 | 1 | 2025-04-28 | 2 | 1939699.33 | -238041.75 | DOWN | 0.1399 | 108 | Low | 464980.52 | 0.273 | 0 | 881338.48 | 13 | 1.21 | 1.27
P003 | Materials | SUP022 | 2025-04 | 2025-01-24 | 1543048.68 | 1346319 | -196729.68 | 196729.68 | 0 | 2025-04-28 | 3 | 1701657.58 | -158608.9 | DOWN | 0.1028 | 94 | Low | 491335.51 | 0.307 | 0 | 854983.49 | 13 | 1.21 | 1.27
P003 | Services | SUP022 | 2025-05 | 2025-01-06 | 1786590.7 | 1078286 | -708304.7 | 708304.7 | 1 | 2025-05-28 | 1 |  |  |  |  | 142 | Low | 338753.85 | 0.187 | 1 | 739532.15 | 14 | 1.36 | 1.73
P003 | Services | SUP022 | 2025-05 | 2025-02-16 | 1516146.04 | 1078286 | -437860.04 | 437860.04 | 1 | 2025-05-28 | 2 | 1786590.7 | -270444.66 | DOWN | 0.1784 | 101 | Low | 435316.03 | 0.285 | 1 | 642969.97 | 14 | 1.36 | 1.73
P003 | Services | SUP022 | 2025-05 | 2025-04-24 | 1330902.56 | 1078286 | -252616.56 | 252616.56 | 1 | 2025-05-28 | 3 | 1516146.04 | -185243.48 | DOWN | 0.1392 | 34 | Low | 590208.22 | 0.446 | 0 | 488077.78 | 14 | 1.36 | 1.73
P003 | Logistics | SUP022 | 2025-06 | 2024-12-31 | 482437.56 | 242255 | -240182.56 | 240182.56 | 1 | 2025-06-28 | 1 |  |  |  |  | 179 | Low | 53829.25 | 0.104 | 1 | 188425.75 | 22 | 1.47 | 1.51
P003 | Logistics | SUP022 | 2025-06 | 2025-03-24 | 396745.46 | 242255 | -154490.46 | 154490.46 | 1 | 2025-06-28 | 2 | 482437.56 | -85692.1 | DOWN | 0.216 | 96 | Low | 111602.53 | 0.293 | 0 | 130652.47 | 22 | 1.47 | 1.51
P003 | Logistics | SUP022 | 2025-06 | 2025-03-28 | 335600.16 | 242255 | -93345.16 | 93345.16 | 1 | 2025-06-28 | 3 | 396745.46 | -61145.3 | DOWN | 0.1822 | 92 | Low | 93583.51 | 0.303 | 4 | 148671.49 | 22 | 1.47 | 1.51
P003 | Software | SUP022 | 2025-07 | 2025-02-10 | 5317349.47 | 2640401 | -2676948.47 | 2676948.47 | 1 | 2025-07-28 | 1 |  |  |  |  | 168 | Low | 680849.57 | 0.13 | 1 | 1959551.43 | 13 | 0.8 | 1.22
P003 | Software | SUP022 | 2025-07 | 2025-03-11 | 4200216.43 | 2640401 | -1559815.43 | 1559815.43 | 1 | 2025-07-28 | 2 | 5317349.47 | -1117133.04 | DOWN | 0.266 | 139 | Low | 812605.2 | 0.203 | 1 | 1827795.8 | 13 | 0.8 | 1.22
P003 | Software | SUP022 | 2025-07 | 2025-06-28 | 3591329.04 | 2640401 | -950928.04 | 950928.04 | 1 | 2025-07-28 | 3 | 4200216.43 | -608887.39 | DOWN | 0.1695 | 30 | Low | 1740790.85 | 0.475 | 1 | 899610.15 | 13 | 0.8 | 1.22
P003 | Software | SUP022 | 2025-08 | 2025-04-16 | 3556480.16 | 1969512 | -1586968.16 | 1586968.16 | 1 | 2025-08-28 | 1 |  |  |  |  | 134 | Low | 778410.98 | 0.206 | 1 | 1191101.02 | 7 | 1.37 | 1.47
P003 | Software | SUP022 | 2025-08 | 2025-05-30 | 2933791.29 | 1969512 | -964279.29 | 964279.29 | 1 | 2025-08-28 | 2 | 3556480.16 | -622688.87 | DOWN | 0.2122 | 90 | Low | 913048.06 | 0.311 | 0 | 1056463.94 | 7 | 1.37 | 1.47
P003 | Software | SUP022 | 2025-08 | 2025-06-02 | 2585038.97 | 1969512 | -615526.97 | 615526.97 | 1 | 2025-08-28 | 3 | 2933791.29 | -348752.32 | DOWN | 0.1349 | 87 | Low | 788182.96 | 0.318 | 1 | 1181329.04 | 7 | 1.37 | 1.47
P003 | Software | SUP022 | 2025-08 | 2025-06-17 | 2345541.24 | 1969512 | -376029.24 | 376029.24 | 1 | 2025-08-28 | 4 | 2585038.97 | -239497.73 | DOWN | 0.1021 | 72 | Low | 775600.39 | 0.354 | 1 | 1193911.61 | 7 | 1.37 | 1.47
P003 | Software | SUP022 | 2025-08 | 2025-07-11 | 2232265.27 | 1969512 | -262753.27 | 262753.27 | 0 | 2025-08-28 | 5 | 2345541.24 | -113275.97 | DOWN | 0.0507 | 48 | Low | 987031.27 | 0.412 | 4 | 982480.73 | 7 | 1.37 | 1.47
P003 | Services | SUP022 | 2025-09 | 2025-04-19 | 2605476.6 | 1356860 | -1248616.6 | 1248616.6 | 1 | 2025-09-28 | 1 |  |  |  |  | 162 | Low | 405745.12 | 0.145 | 2 | 951114.88 | 10 | 0.71 | 1.27
P003 | Services | SUP022 | 2025-09 | 2025-04-20 | 2122284.46 | 1356860 | -765424.46 | 765424.46 | 1 | 2025-09-28 | 2 | 2605476.6 | -483192.14 | DOWN | 0.2277 | 161 | Low | 314652.7 | 0.148 | 3 | 1042207.3 | 10 | 0.71 | 1.27
P003 | Services | SUP022 | 2025-09 | 2025-07-28 | 1828741.1 | 1356860 | -471881.1 | 471881.1 | 1 | 2025-09-28 | 3 | 2122284.46 | -293543.36 | DOWN | 0.1605 | 62 | Low | 698258.39 | 0.395 | 7 | 658601.61 | 10 | 0.71 | 1.27
P003 | Services | SUP022 | 2025-09 | 2025-09-07 | 1639043.31 | 1356860 | -282183.31 | 282183.31 | 1 | 2025-09-28 | 4 | 1828741.1 | -189697.79 | DOWN | 0.1157 | 21 | Medium | 777330.83 | 0.498 | 3 | 579529.17 | 10 | 0.71 | 1.27
P003 | Mechanical | SUP022 | 2025-10 | 2025-05-01 | 1569299.69 | 938665 | -630634.69 | 630634.69 | 1 | 2025-10-28 | 1 |  |  |  |  | 180 | Low | 184882.6 | 0.11 | 0 | 753782.4 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP022 | 2025-10 | 2025-06-07 | 1326439.86 | 938665 | -387774.86 | 387774.86 | 1 | 2025-10-28 | 2 | 1569299.69 | -242859.83 | DOWN | 0.1831 | 143 | Low | 273766.1 | 0.193 | 0 | 664898.9 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP022 | 2025-10 | 2025-07-09 | 1176900.9 | 938665 | -238235.9 | 238235.9 | 1 | 2025-10-28 | 3 | 1326439.86 | -149538.96 | DOWN | 0.1271 | 111 | Low | 317785.9 | 0.273 | 4 | 620879.1 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP022 | 2025-10 | 2025-07-24 | 1075690.14 | 938665 | -137025.14 | 137025.14 | 0 | 2025-10-28 | 4 | 1176900.9 | -101210.76 | DOWN | 0.0941 | 96 | Low | 357179.26 | 0.31 | 2 | 581485.74 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP022 | 2025-10 | 2025-09-05 | 1017463.09 | 938665 | -78798.09 | 78798.09 | 0 | 2025-10-28 | 5 | 1075690.14 | -58227.05 | DOWN | 0.0572 | 53 | Low | 407214.44 | 0.417 | 3 | 531450.56 | 19 | 0.95 | 0.98
P003 | Software | SUP022 | 2025-11 | 2025-06-06 | 1277233.58 | 813488 | -463745.58 | 463745.58 | 1 | 2025-11-28 | 1 |  |  |  |  | 175 | Low | 133400.37 | 0.102 | 4 | 680087.63 | 11 | 1.85 | 1.52
P003 | Software | SUP022 | 2025-11 | 2025-07-02 | 1094454.28 | 813488 | -280966.28 | 280966.28 | 1 | 2025-11-28 | 2 | 1277233.58 | -182779.3 | DOWN | 0.167 | 149 | Low | 178894.28 | 0.161 | 2 | 634593.72 | 11 | 1.85 | 1.52
P003 | Software | SUP022 | 2025-11 | 2025-08-21 | 984535.25 | 813488 | -171047.25 | 171047.25 | 1 | 2025-11-28 | 3 | 1094454.28 | -109919.03 | DOWN | 0.1116 | 99 | Low | 261959.8 | 0.275 | 4 | 551528.2 | 11 | 1.85 | 1.52
P003 | Software | SUP022 | 2025-11 | 2025-09-18 | 911368.92 | 813488 | -97880.92 | 97880.92 | 0 | 2025-11-28 | 4 | 984535.25 | -73166.33 | DOWN | 0.0803 | 71 | Low | 316772.2 | 0.338 | 1 | 496715.8 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP022 | 2025-12 | 2025-07-01 | 442891.7 | 306199 | -136692.7 | 136692.7 | 1 | 2025-12-28 | 1 |  |  |  |  | 180 | Low | 45700.76 | 0.109 | 0 | 260498.24 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP022 | 2025-12 | 2025-08-10 | 389296.41 | 306199 | -83097.41 | 83097.41 | 1 | 2025-12-28 | 2 | 442891.7 | -53595.29 | DOWN | 0.1377 | 140 | Low | 72228.69 | 0.198 | 0 | 233970.31 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP022 | 2025-12 | 2025-11-17 | 355484.72 | 306199 | -49285.72 | 49285.72 | 0 | 2025-12-28 | 3 | 389296.41 | -33811.69 | DOWN | 0.0951 | 41 | Low | 146205.73 | 0.443 | 5 | 159993.27 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP018 | 2025-01 | 2024-08-03 | 313848.09 | 208538 | -105310.09 | 105310.09 | 1 | 2025-01-28 | 1 |  |  |  |  | 178 | Low | 39915.83 | 0.118 | 0 | 168622.17 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP018 | 2025-01 | 2024-11-19 | 267215.8 | 208538 | -58677.8 | 58677.8 | 1 | 2025-01-28 | 2 | 313848.09 | -46632.29 | DOWN | 0.1745 | 70 | Low | 105477.62 | 0.402 | 4 | 103060.38 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP018 | 2025-01 | 2025-01-15 | 244967.22 | 208538 | -36429.22 | 36429.22 | 0 | 2025-01-28 | 3 | 267215.8 | -22248.58 | DOWN | 0.0908 | 13 | Medium | 126019.18 | 0.554 | 2 | 82518.82 | 17 | 1.86 | 1.34
P003 | Software | SUP018 | 2025-02 | 2024-09-09 | 438770.97 | 239942 | -198828.97 | 198828.97 | 1 | 2025-02-28 | 1 |  |  |  |  | 172 | Low | 52086.81 | 0.125 | 0 | 187855.19 | 17 | 2.1 | 1.03
P003 | Software | SUP018 | 2025-02 | 2024-11-23 | 354109.41 | 239942 | -114167.41 | 114167.41 | 1 | 2025-02-28 | 2 | 438770.97 | -84661.56 | DOWN | 0.2391 | 97 | Low | 112120.83 | 0.321 | 3 | 127821.17 | 17 | 2.1 | 1.03
P003 | Software | SUP018 | 2025-02 | 2024-12-14 | 301548.09 | 239942 | -61606.09 | 61606.09 | 1 | 2025-02-28 | 3 | 354109.41 | -52561.32 | DOWN | 0.1743 | 76 | Low | 106845.21 | 0.376 | 0 | 133096.79 | 17 | 2.1 | 1.03
P003 | Software | SUP018 | 2025-02 | 2025-01-12 | 282609.1 | 239942 | -42667.1 | 42667.1 | 1 | 2025-02-28 | 4 | 301548.09 | -18938.99 | DOWN | 0.067 | 47 | Low | 128572.12 | 0.452 | 2 | 111369.88 | 17 | 2.1 | 1.03
P003 | Materials | SUP018 | 2025-03 | 2024-10-22 | 2386735.18 | 1550632 | -836103.18 | 836103.18 | 1 | 2025-03-28 | 1 |  |  |  |  | 157 | Low | 403803.74 | 0.183 | 2 | 1146828.26 | 13 | 1.13 | 1.73
P003 | Materials | SUP018 | 2025-03 | 2024-12-07 | 1987116.36 | 1550632 | -436484.36 | 436484.36 | 1 | 2025-03-28 | 2 | 2386735.18 | -399618.82 | DOWN | 0.2011 | 111 | Low | 628128.24 | 0.317 | 2 | 922503.76 | 13 | 1.13 | 1.73
P003 | Materials | SUP018 | 2025-03 | 2025-01-31 | 1786778.91 | 1550632 | -236146.91 | 236146.91 | 0 | 2025-03-28 | 3 | 1987116.36 | -200337.45 | DOWN | 0.1121 | 56 | Medium | 873974.62 | 0.477 | 0 | 676657.38 | 13 | 1.13 | 1.73
P003 | Software | SUP018 | 2025-04 | 2024-11-01 | 1418144.49 | 726626 | -691518.49 | 691518.49 | 1 | 2025-04-28 | 1 |  |  |  |  | 178 | Low | 177735.92 | 0.127 | 0 | 548890.08 | 13 | 1.21 | 1.27
P003 | Software | SUP018 | 2025-04 | 2025-02-01 | 1123126.19 | 726626 | -396500.19 | 396500.19 | 1 | 2025-04-28 | 2 | 1418144.49 | -295018.3 | DOWN | 0.2627 | 86 | Low | 434155.87 | 0.386 | 6 | 292470.13 | 13 | 1.21 | 1.27
P003 | Software | SUP018 | 2025-04 | 2025-02-07 | 932407.91 | 726626 | -205781.91 | 205781.91 | 1 | 2025-04-28 | 3 | 1123126.19 | -190718.28 | DOWN | 0.2045 | 80 | Low | 359005.18 | 0.403 | 3 | 367620.82 | 13 | 1.21 | 1.27
P003 | Software | SUP018 | 2025-04 | 2025-03-05 | 829487.91 | 726626 | -102861.91 | 102861.91 | 0 | 2025-04-28 | 4 | 932407.91 | -102920 | DOWN | 0.1241 | 54 | Low | 401960.12 | 0.478 | 2 | 324665.88 | 13 | 1.21 | 1.27
P003 | Software | SUP018 | 2025-04 | 2025-03-24 | 775348.48 | 726626 | -48722.48 | 48722.48 | 0 | 2025-04-28 | 5 | 829487.91 | -54139.43 | DOWN | 0.0698 | 35 | Medium | 385014.39 | 0.533 | 0 | 341611.61 | 13 | 1.21 | 1.27
P003 | Software | SUP018 | 2025-04 | 2025-04-15 | 745102.6 | 726626 | -18476.6 | 18476.6 | 0 | 2025-04-28 | 6 | 775348.48 | -30245.88 | DOWN | 0.0406 | 13 | Medium | 479382.24 | 0.597 | 1 | 247243.76 | 13 | 1.21 | 1.27
P003 | Materials | SUP018 | 2025-05 | 2024-12-18 | 1857666.13 | 1051393 | -806273.13 | 806273.13 | 1 | 2025-05-28 | 1 |  |  |  |  | 161 | Low | 320566.22 | 0.167 | 1 | 730826.78 | 14 | 1.36 | 1.73
P003 | Materials | SUP018 | 2025-05 | 2024-12-21 | 1478949.64 | 1051393 | -427556.64 | 427556.64 | 1 | 2025-05-28 | 2 | 1857666.13 | -378716.49 | DOWN | 0.2561 | 158 | Low | 270594.33 | 0.176 | 0 | 780798.67 | 14 | 1.36 | 1.73
P003 | Materials | SUP018 | 2025-05 | 2024-12-22 | 1301571.53 | 1051393 | -250178.53 | 250178.53 | 1 | 2025-05-28 | 3 | 1478949.64 | -177378.11 | DOWN | 0.1363 | 157 | Low | 223337.42 | 0.178 | 2 | 828055.58 | 14 | 1.36 | 1.73
P003 | Materials | SUP018 | 2025-05 | 2025-04-13 | 1192341.2 | 1051393 | -140948.2 | 140948.2 | 0 | 2025-05-28 | 4 | 1301571.53 | -109230.33 | DOWN | 0.0916 | 45 | Medium | 600852.34 | 0.496 | 7 | 450540.66 | 14 | 1.36 | 1.73
P003 | Materials | SUP018 | 2025-05 | 2025-05-09 | 1120059.65 | 1051393 | -68666.65 | 68666.65 | 0 | 2025-05-28 | 5 | 1192341.2 | -72281.55 | DOWN | 0.0645 | 19 | Medium | 630955.5 | 0.569 | 3 | 420437.5 | 14 | 1.36 | 1.73
P003 | Software | SUP018 | 2025-06 | 2025-03-07 | 4626724.45 | 2301829 | -2324895.45 | 2324895.45 | 1 | 2025-06-28 | 1 |  |  |  |  | 113 | Low | 1316116.39 | 0.299 | 1 | 985712.61 | 22 | 1.47 | 1.51
P003 | Software | SUP018 | 2025-06 | 2025-06-08 | 3516400.38 | 2301829 | -1214571.38 | 1214571.38 | 1 | 2025-06-28 | 2 | 4626724.45 | -1110324.07 | DOWN | 0.3158 | 20 | Low | 1895506.25 | 0.559 | 3 | 406322.75 | 22 | 1.47 | 1.51
P003 | Software | SUP018 | 2025-06 | 2025-06-13 | 2917187.12 | 2301829 | -615358.12 | 615358.12 | 1 | 2025-06-28 | 3 | 3516400.38 | -599213.26 | DOWN | 0.2054 | 15 | Low | 1587834.14 | 0.573 | 6 | 713994.86 | 22 | 1.47 | 1.51
P003 | Services | SUP018 | 2025-07 | 2025-03-07 | 1079582.56 | 582712 | -496870.56 | 496870.56 | 1 | 2025-07-28 | 1 |  |  |  |  | 143 | Low | 243000.47 | 0.227 | 0 | 339711.53 | 13 | 0.8 | 1.22
P003 | Services | SUP018 | 2025-07 | 2025-05-23 | 857423.75 | 582712 | -274711.75 | 274711.75 | 1 | 2025-07-28 | 2 | 1079582.56 | -222158.81 | DOWN | 0.2591 | 66 | Low | 375974.54 | 0.455 | 4 | 206737.46 | 13 | 0.8 | 1.22
P003 | Services | SUP018 | 2025-07 | 2025-06-03 | 724817.99 | 582712 | -142105.99 | 142105.99 | 1 | 2025-07-28 | 3 | 857423.75 | -132605.76 | DOWN | 0.183 | 55 | Low | 376345.05 | 0.488 | 6 | 206366.95 | 13 | 0.8 | 1.22
P003 | Services | SUP018 | 2025-07 | 2025-06-10 | 660608.94 | 582712 | -77896.94 | 77896.94 | 0 | 2025-07-28 | 4 | 724817.99 | -64209.05 | DOWN | 0.0972 | 48 | Medium | 344674.03 | 0.508 | 7 | 238037.97 | 13 | 0.8 | 1.22
P003 | Services | SUP018 | 2025-07 | 2025-06-30 | 624236.36 | 582712 | -41524.36 | 41524.36 | 0 | 2025-07-28 | 5 | 660608.94 | -36372.58 | DOWN | 0.0583 | 28 | Medium | 367255.25 | 0.567 | 0 | 215456.75 | 13 | 0.8 | 1.22
P003 | Software | SUP018 | 2025-08 | 2025-06-13 | 3940555.81 | 2475132 | -1465423.81 | 1465423.81 | 1 | 2025-08-28 | 1 |  |  |  |  | 76 | Low | 1672302.78 | 0.407 | 4 | 802829.22 | 7 | 1.37 | 1.47
P003 | Software | SUP018 | 2025-08 | 2025-07-15 | 3267830.29 | 2475132 | -792698.29 | 792698.29 | 1 | 2025-08-28 | 2 | 3940555.81 | -672725.52 | DOWN | 0.2059 | 44 | Low | 1641212.6 | 0.498 | 3 | 833919.4 | 7 | 1.37 | 1.47
P003 | Software | SUP018 | 2025-08 | 2025-07-16 | 2839859.86 | 2475132 | -364727.86 | 364727.86 | 0 | 2025-08-28 | 3 | 3267830.29 | -427970.43 | DOWN | 0.1507 | 43 | Low | 1473443.25 | 0.501 | 1 | 1001688.75 | 7 | 1.37 | 1.47
P003 | Software | SUP018 | 2025-09 | 2025-05-21 | 909393.26 | 441083 | -468310.26 | 468310.26 | 1 | 2025-09-28 | 1 |  |  |  |  | 130 | Low | 252011.39 | 0.266 | 4 | 189071.61 | 10 | 0.71 | 1.27
P003 | Software | SUP018 | 2025-09 | 2025-06-23 | 686958.17 | 441083 | -245875.17 | 245875.17 | 1 | 2025-09-28 | 2 | 909393.26 | -222435.09 | DOWN | 0.3238 | 97 | Low | 251387.82 | 0.363 | 1 | 189695.18 | 10 | 0.71 | 1.27
P003 | Software | SUP018 | 2025-09 | 2025-08-25 | 571031.8 | 441083 | -129948.8 | 129948.8 | 1 | 2025-09-28 | 3 | 686958.17 | -115926.37 | DOWN | 0.203 | 34 | Low | 289664.95 | 0.55 | 0 | 151418.05 | 10 | 0.71 | 1.27
P003 | Logistics | SUP018 | 2025-10 | 2025-05-28 | 4776325.58 | 2539755 | -2236570.58 | 2236570.58 | 1 | 2025-10-28 | 1 |  |  |  |  | 153 | Low | 953251.35 | 0.198 | 0 | 1586503.65 | 19 | 0.95 | 0.98
P003 | Logistics | SUP018 | 2025-10 | 2025-06-28 | 3735842.91 | 2539755 | -1196087.91 | 1196087.91 | 1 | 2025-10-28 | 2 | 4776325.58 | -1040482.67 | DOWN | 0.2785 | 122 | Low | 1092149.46 | 0.29 | 1 | 1447605.54 | 19 | 0.95 | 0.98
P003 | Logistics | SUP018 | 2025-10 | 2025-06-28 | 3234589.47 | 2539755 | -694834.47 | 694834.47 | 1 | 2025-10-28 | 3 | 3735842.91 | -501253.44 | DOWN | 0.155 | 122 | Low | 964972.72 | 0.29 | 1 | 1574782.28 | 19 | 0.95 | 0.98
P003 | Logistics | SUP018 | 2025-10 | 2025-08-13 | 2980097.13 | 2539755 | -440342.13 | 440342.13 | 0 | 2025-10-28 | 4 | 3234589.47 | -254492.34 | DOWN | 0.0854 | 76 | Low | 1201203.76 | 0.425 | 3 | 1338551.24 | 19 | 0.95 | 0.98
P003 | Logistics | SUP018 | 2025-10 | 2025-09-19 | 2786175.96 | 2539755 | -246420.96 | 246420.96 | 0 | 2025-10-28 | 5 | 2980097.13 | -193921.17 | DOWN | 0.0696 | 39 | Medium | 1445015.05 | 0.535 | 7 | 1094739.95 | 19 | 0.95 | 0.98
P003 | Services | SUP018 | 2025-11 | 2025-07-20 | 3618433.98 | 1969146 | -1649287.98 | 1649287.98 | 1 | 2025-11-28 | 1 |  |  |  |  | 131 | Low | 876477.82 | 0.239 | 0 | 1092668.18 | 11 | 1.85 | 1.52
P003 | Services | SUP018 | 2025-11 | 2025-09-18 | 2846785.41 | 1969146 | -877639.41 | 877639.41 | 1 | 2025-11-28 | 2 | 3618433.98 | -771648.57 | DOWN | 0.2711 | 71 | Low | 1185997.06 | 0.399 | 1 | 783148.94 | 11 | 1.85 | 1.52
P003 | Services | SUP018 | 2025-11 | 2025-10-03 | 2459781.44 | 1969146 | -490635.44 | 490635.44 | 1 | 2025-11-28 | 3 | 2846785.41 | -387003.97 | DOWN | 0.1573 | 56 | Low | 1062252.56 | 0.44 | 6 | 906893.44 | 11 | 1.85 | 1.52
P003 | Services | SUP018 | 2025-12 | 2025-08-29 | 1399611.83 | 844016 | -555595.83 | 555595.83 | 1 | 2025-12-28 | 1 |  |  |  |  | 121 | Low | 418329.71 | 0.29 | 1 | 425686.29 | 10 | 1.08 | 1.22
P003 | Services | SUP018 | 2025-12 | 2025-09-30 | 1148933.14 | 844016 | -304917.14 | 304917.14 | 1 | 2025-12-28 | 2 | 1399611.83 | -250678.69 | DOWN | 0.2182 | 89 | Low | 474113.6 | 0.383 | 1 | 369902.4 | 10 | 1.08 | 1.22
P003 | Services | SUP018 | 2025-12 | 2025-10-12 | 1017557.27 | 844016 | -173541.27 | 173541.27 | 1 | 2025-12-28 | 3 | 1148933.14 | -131375.87 | DOWN | 0.1291 | 77 | Low | 439823.73 | 0.418 | 4 | 404192.27 | 10 | 1.08 | 1.22
P003 | Services | SUP018 | 2025-12 | 2025-11-10 | 930359.65 | 844016 | -86343.65 | 86343.65 | 0 | 2025-12-28 | 4 | 1017557.27 | -87197.62 | DOWN | 0.0937 | 48 | Medium | 463621.49 | 0.503 | 8 | 380394.51 | 10 | 1.08 | 1.22
P003 | Electronics | SUP033 | 2025-01 | 2024-09-08 | 2133275.76 | 1116256 | -1017019.76 | 1017019.76 | 1 | 2025-01-28 | 1 |  |  |  |  | 142 | Low | 436077.69 | 0.209 | 3 | 680178.31 | 17 | 1.86 | 1.34
P003 | Electronics | SUP033 | 2025-01 | 2024-09-10 | 1666616.79 | 1116256 | -550360.79 | 550360.79 | 1 | 2025-01-28 | 2 | 2133275.76 | -466658.97 | DOWN | 0.28 | 140 | Low | 356653 | 0.214 | 1 | 759603 | 17 | 1.86 | 1.34
P003 | Electronics | SUP033 | 2025-01 | 2024-10-08 | 1456175.9 | 1116256 | -339919.9 | 339919.9 | 1 | 2025-01-28 | 3 | 1666616.79 | -210440.89 | DOWN | 0.1445 | 112 | Low | 447578.68 | 0.289 | 3 | 668677.32 | 17 | 1.86 | 1.34
P003 | Electronics | SUP033 | 2025-01 | 2024-10-23 | 1319354.75 | 1116256 | -203098.75 | 203098.75 | 1 | 2025-01-28 | 4 | 1456175.9 | -136821.15 | DOWN | 0.1037 | 97 | Low | 413090.07 | 0.329 | 6 | 703165.93 | 17 | 1.86 | 1.34
P003 | Electronics | SUP033 | 2025-01 | 2025-01-04 | 1245800.76 | 1116256 | -129544.76 | 129544.76 | 0 | 2025-01-28 | 5 | 1319354.75 | -73553.99 | DOWN | 0.059 | 24 | Medium | 628793.68 | 0.525 | 4 | 487462.32 | 17 | 1.86 | 1.34
P003 | Electronics | SUP033 | 2025-01 | 2025-01-11 | 1160367.22 | 1116256 | -44111.22 | 44111.22 | 0 | 2025-01-28 | 6 | 1245800.76 | -85433.54 | DOWN | 0.0736 | 17 | Medium | 656516.09 | 0.544 | 4 | 459739.91 | 17 | 1.86 | 1.34
P003 | Services | SUP033 | 2025-02 | 2024-09-10 | 3442339.5 | 1669046 | -1773293.5 | 1773293.5 | 1 | 2025-02-28 | 1 |  |  |  |  | 171 | Low | 451460.17 | 0.128 | 0 | 1217585.83 | 17 | 2.1 | 1.03
P003 | Services | SUP033 | 2025-02 | 2024-09-10 | 2705039.99 | 1669046 | -1035993.99 | 1035993.99 | 1 | 2025-02-28 | 2 | 3442339.5 | -737299.51 | DOWN | 0.2726 | 171 | Low | 350214.05 | 0.128 | 0 | 1318831.95 | 17 | 2.1 | 1.03
P003 | Services | SUP033 | 2025-02 | 2024-10-02 | 2299546.5 | 1669046 | -630500.5 | 630500.5 | 1 | 2025-02-28 | 3 | 2705039.99 | -405493.49 | DOWN | 0.1763 | 149 | Low | 431268.95 | 0.185 | 0 | 1237777.05 | 17 | 2.1 | 1.03
P003 | Services | SUP033 | 2025-02 | 2024-10-23 | 1950040.4 | 1669046 | -280994.4 | 280994.4 | 0 | 2025-02-28 | 4 | 2299546.5 | -349506.1 | DOWN | 0.1792 | 128 | Low | 502337.26 | 0.24 | 0 | 1166708.74 | 17 | 2.1 | 1.03
P003 | Services | SUP033 | 2025-02 | 2024-10-29 | 1809531.02 | 1669046 | -140485.02 | 140485.02 | 0 | 2025-02-28 | 5 | 1950040.4 | -140509.38 | DOWN | 0.0776 | 122 | Low | 487510.87 | 0.256 | 3 | 1181535.13 | 17 | 2.1 | 1.03
P003 | Services | SUP033 | 2025-02 | 2025-01-17 | 1768080.99 | 1669046 | -99034.99 | 99034.99 | 0 | 2025-02-28 | 6 | 1809531.02 | -41450.03 | DOWN | 0.0234 | 42 | Low | 878771.8 | 0.465 | 4 | 790274.2 | 17 | 2.1 | 1.03
P003 | Logistics | SUP033 | 2025-03 | 2024-12-10 | 2550336.52 | 1404247 | -1146089.52 | 1146089.52 | 1 | 2025-03-28 | 1 |  |  |  |  | 108 | Low | 865793.16 | 0.326 | 0 | 538453.84 | 13 | 1.13 | 1.73
P003 | Logistics | SUP033 | 2025-03 | 2025-01-14 | 2022170.45 | 1404247 | -617923.45 | 617923.45 | 1 | 2025-03-28 | 2 | 2550336.52 | -528166.07 | DOWN | 0.2612 | 73 | Low | 872448.58 | 0.428 | 0 | 531798.42 | 13 | 1.13 | 1.73
P003 | Logistics | SUP033 | 2025-03 | 2025-03-13 | 1741706.33 | 1404247 | -337459.33 | 337459.33 | 1 | 2025-03-28 | 3 | 2022170.45 | -280464.12 | DOWN | 0.161 | 15 | Low | 1010185.97 | 0.596 | 4 | 394061.03 | 13 | 1.13 | 1.73
P003 | Electronics | SUP033 | 2025-04 | 2024-11-14 | 3078662.68 | 1829252 | -1249410.68 | 1249410.68 | 1 | 2025-04-28 | 1 |  |  |  |  | 165 | Low | 473112.2 | 0.159 | 1 | 1356139.8 | 13 | 1.21 | 1.27
P003 | Electronics | SUP033 | 2025-04 | 2024-12-22 | 2543376.01 | 1829252 | -714124.01 | 714124.01 | 1 | 2025-04-28 | 2 | 3078662.68 | -535286.67 | DOWN | 0.2105 | 127 | Low | 641962.56 | 0.268 | 1 | 1187289.44 | 13 | 1.21 | 1.27
P003 | Electronics | SUP033 | 2025-04 | 2025-01-16 | 2245967.9 | 1829252 | -416715.9 | 416715.9 | 1 | 2025-04-28 | 3 | 2543376.01 | -297408.11 | DOWN | 0.1324 | 102 | Low | 793324.73 | 0.34 | 2 | 1035927.27 | 13 | 1.21 | 1.27
P003 | Electronics | SUP033 | 2025-04 | 2025-03-20 | 2055663.91 | 1829252 | -226411.91 | 226411.91 | 0 | 2025-04-28 | 4 | 2245967.9 | -190303.99 | DOWN | 0.0926 | 39 | Medium | 1034006.68 | 0.522 | 1 | 795245.32 | 13 | 1.21 | 1.27
P003 | Electronics | SUP033 | 2025-04 | 2025-04-09 | 1964834.61 | 1829252 | -135582.61 | 135582.61 | 0 | 2025-04-28 | 5 | 2055663.91 | -90829.3 | DOWN | 0.0462 | 19 | Medium | 1218887.99 | 0.579 | 4 | 610364.01 | 13 | 1.21 | 1.27
P003 | Electronics | SUP033 | 2025-04 | 2025-04-18 | 1919450.15 | 1829252 | -90198.15 | 90198.15 | 0 | 2025-04-28 | 6 | 1964834.61 | -45384.46 | DOWN | 0.0236 | 10 | Medium | 1175361.11 | 0.602 | 3 | 653890.89 | 13 | 1.21 | 1.27
P003 | Electronics | SUP033 | 2025-05 | 2025-03-30 | 2642396.67 | 1719487 | -922909.67 | 922909.67 | 1 | 2025-05-28 | 1 |  |  |  |  | 59 | Medium | 1244892.67 | 0.456 | 2 | 474594.33 | 14 | 1.36 | 1.73
P003 | Electronics | SUP033 | 2025-05 | 2025-04-23 | 2259300.73 | 1719487 | -539813.73 | 539813.73 | 1 | 2025-05-28 | 2 | 2642396.67 | -383095.94 | DOWN | 0.1696 | 35 | Low | 1251551.07 | 0.524 | 3 | 467935.93 | 14 | 1.36 | 1.73
P003 | Electronics | SUP033 | 2025-05 | 2025-05-06 | 2030044.24 | 1719487 | -310557.24 | 310557.24 | 1 | 2025-05-28 | 3 | 2259300.73 | -229256.49 | DOWN | 0.1129 | 22 | Medium | 1126653.76 | 0.561 | 4 | 592833.24 | 14 | 1.36 | 1.73
P003 | Electronics | SUP033 | 2025-06 | 2025-01-02 | 871780.67 | 445475 | -426305.67 | 426305.67 | 1 | 2025-06-28 | 1 |  |  |  |  | 177 | Low | 105966.17 | 0.123 | 3 | 339508.83 | 22 | 1.47 | 1.51
P003 | Electronics | SUP033 | 2025-06 | 2025-01-07 | 682400.54 | 445475 | -236925.54 | 236925.54 | 1 | 2025-06-28 | 2 | 871780.67 | -189380.13 | DOWN | 0.2775 | 172 | Low | 91187.66 | 0.134 | 0 | 354287.34 | 22 | 1.47 | 1.51
P003 | Electronics | SUP033 | 2025-06 | 2025-03-13 | 571711.76 | 445475 | -126236.76 | 126236.76 | 1 | 2025-06-28 | 3 | 682400.54 | -110688.78 | DOWN | 0.1936 | 107 | Low | 181715.38 | 0.316 | 2 | 263759.62 | 22 | 1.47 | 1.51
P003 | Logistics | SUP033 | 2025-07 | 2025-02-19 | 3013780.94 | 1681510 | -1332270.94 | 1332270.94 | 1 | 2025-07-28 | 1 |  |  |  |  | 159 | Low | 531050.8 | 0.18 | 1 | 1150459.2 | 13 | 0.8 | 1.22
P003 | Logistics | SUP033 | 2025-07 | 2025-04-05 | 2373235.7 | 1681510 | -691725.7 | 691725.7 | 1 | 2025-07-28 | 2 | 3013780.94 | -640545.24 | DOWN | 0.2699 | 114 | Low | 775749.98 | 0.313 | 0 | 905760.02 | 13 | 0.8 | 1.22
P003 | Logistics | SUP033 | 2025-07 | 2025-05-31 | 2052773.93 | 1681510 | -371263.93 | 371263.93 | 1 | 2025-07-28 | 3 | 2373235.7 | -320461.77 | DOWN | 0.1561 | 58 | Low | 946303.36 | 0.479 | 1 | 735206.64 | 13 | 0.8 | 1.22
P003 | Software | SUP033 | 2025-08 | 2025-03-12 | 1626855.33 | 747634 | -879221.33 | 879221.33 | 1 | 2025-08-28 | 1 |  |  |  |  | 169 | Low | 223653.71 | 0.144 | 3 | 523980.29 | 7 | 1.37 | 1.47
P003 | Software | SUP033 | 2025-08 | 2025-04-26 | 1227600.23 | 747634 | -479966.23 | 479966.23 | 1 | 2025-08-28 | 2 | 1626855.33 | -399255.1 | DOWN | 0.3252 | 124 | Low | 343221.78 | 0.272 | 3 | 404412.22 | 7 | 1.37 | 1.47
P003 | Software | SUP033 | 2025-08 | 2025-06-26 | 999977.97 | 747634 | -252343.97 | 252343.97 | 1 | 2025-08-28 | 3 | 1227600.23 | -227622.26 | DOWN | 0.2276 | 63 | Low | 451635.35 | 0.444 | 3 | 295998.65 | 7 | 1.37 | 1.47
P003 | Software | SUP033 | 2025-08 | 2025-07-14 | 878852.64 | 747634 | -131218.64 | 131218.64 | 0 | 2025-08-28 | 4 | 999977.97 | -121125.33 | DOWN | 0.1378 | 45 | Low | 434085.64 | 0.495 | 4 | 313548.36 | 7 | 1.37 | 1.47
P003 | Software | SUP033 | 2025-08 | 2025-07-22 | 819132.9 | 747634 | -71498.9 | 71498.9 | 0 | 2025-08-28 | 5 | 878852.64 | -59719.74 | DOWN | 0.0729 | 37 | Medium | 421410.31 | 0.518 | 8 | 326223.69 | 7 | 1.37 | 1.47
P003 | Software | SUP033 | 2025-09 | 2025-05-05 | 417258.63 | 231474 | -185784.63 | 185784.63 | 1 | 2025-09-28 | 1 |  |  |  |  | 146 | Low | 86222.47 | 0.219 | 0 | 145251.53 | 10 | 0.71 | 1.27
P003 | Software | SUP033 | 2025-09 | 2025-06-10 | 332081.78 | 231474 | -100607.78 | 100607.78 | 1 | 2025-09-28 | 2 | 417258.63 | -85176.85 | DOWN | 0.2565 | 110 | Low | 107645.49 | 0.325 | 0 | 123828.51 | 10 | 0.71 | 1.27
P003 | Software | SUP033 | 2025-09 | 2025-08-06 | 283525.01 | 231474 | -52051.01 | 52051.01 | 1 | 2025-09-28 | 3 | 332081.78 | -48556.77 | DOWN | 0.1713 | 53 | Low | 139830.37 | 0.493 | 0 | 91643.63 | 10 | 0.71 | 1.27
P003 | Software | SUP033 | 2025-09 | 2025-08-18 | 263720.05 | 231474 | -32246.05 | 32246.05 | 0 | 2025-09-28 | 4 | 283525.01 | -19804.96 | DOWN | 0.0751 | 41 | Medium | 138775.56 | 0.529 | 6 | 92698.44 | 10 | 0.71 | 1.27
P003 | Software | SUP033 | 2025-09 | 2025-09-06 | 245918.7 | 231474 | -14444.7 | 14444.7 | 0 | 2025-09-28 | 5 | 263720.05 | -17801.35 | DOWN | 0.0724 | 22 | Medium | 146224.08 | 0.585 | 7 | 85249.92 | 10 | 0.71 | 1.27
P003 | Materials | SUP033 | 2025-10 | 2025-05-03 | 1457975.21 | 871756 | -586219.21 | 586219.21 | 1 | 2025-10-28 | 1 |  |  |  |  | 178 | Low | 178608.01 | 0.13 | 0 | 693147.99 | 19 | 0.95 | 0.98
P003 | Materials | SUP033 | 2025-10 | 2025-05-13 | 1200742.94 | 871756 | -328986.94 | 328986.94 | 1 | 2025-10-28 | 2 | 1457975.21 | -257232.27 | DOWN | 0.2142 | 168 | Low | 173930.93 | 0.154 | 2 | 697825.07 | 19 | 0.95 | 0.98
P003 | Materials | SUP033 | 2025-10 | 2025-05-23 | 1043885.74 | 871756 | -172129.74 | 172129.74 | 1 | 2025-10-28 | 3 | 1200742.94 | -156857.2 | DOWN | 0.1503 | 158 | Low | 196174.68 | 0.183 | 1 | 675581.32 | 19 | 0.95 | 0.98
P003 | Materials | SUP033 | 2025-10 | 2025-06-01 | 957834.58 | 871756 | -86078.58 | 86078.58 | 0 | 2025-10-28 | 4 | 1043885.74 | -86051.16 | DOWN | 0.0898 | 149 | Low | 195578.34 | 0.21 | 2 | 676177.66 | 19 | 0.95 | 0.98
P003 | Materials | SUP033 | 2025-10 | 2025-07-03 | 925298.66 | 871756 | -53542.66 | 53542.66 | 0 | 2025-10-28 | 5 | 957834.58 | -32535.92 | DOWN | 0.0352 | 117 | Low | 290850.57 | 0.304 | 1 | 580905.43 | 19 | 0.95 | 0.98
P003 | Materials | SUP033 | 2025-10 | 2025-07-15 | 905783.73 | 871756 | -34027.73 | 34027.73 | 0 | 2025-10-28 | 6 | 925298.66 | -19514.93 | DOWN | 0.0215 | 105 | Low | 327591.95 | 0.34 | 8 | 544164.05 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP033 | 2025-11 | 2025-08-18 | 2967037.43 | 1911488 | -1055549.43 | 1055549.43 | 1 | 2025-11-28 | 1 |  |  |  |  | 102 | Low | 872276.27 | 0.316 | 0 | 1039211.73 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP033 | 2025-11 | 2025-08-28 | 2468095.87 | 1911488 | -556607.87 | 556607.87 | 1 | 2025-11-28 | 2 | 2967037.43 | -498941.56 | DOWN | 0.2022 | 92 | Low | 834157.41 | 0.343 | 2 | 1077330.59 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP033 | 2025-11 | 2025-11-12 | 2207950.85 | 1911488 | -296462.85 | 296462.85 | 0 | 2025-11-28 | 3 | 2468095.87 | -260145.02 | DOWN | 0.1178 | 16 | Medium | 1215364.36 | 0.547 | 5 | 696123.64 | 11 | 1.85 | 1.52
P003 | Materials | SUP033 | 2025-12 | 2025-08-24 | 1553845.22 | 871272 | -682573.22 | 682573.22 | 1 | 2025-12-28 | 1 |  |  |  |  | 126 | Low | 403961.1 | 0.275 | 0 | 467310.9 | 10 | 1.08 | 1.22
P003 | Materials | SUP033 | 2025-12 | 2025-10-23 | 1234194.42 | 871272 | -362922.42 | 362922.42 | 1 | 2025-12-28 | 2 | 1553845.22 | -319650.8 | DOWN | 0.259 | 66 | Low | 565127.57 | 0.451 | 1 | 306144.43 | 10 | 1.08 | 1.22
P003 | Materials | SUP033 | 2025-12 | 2025-10-26 | 1074911.65 | 871272 | -203639.65 | 203639.65 | 1 | 2025-12-28 | 3 | 1234194.42 | -159282.77 | DOWN | 0.1482 | 63 | Low | 510030.87 | 0.459 | 5 | 361241.13 | 10 | 1.08 | 1.22
P003 | Materials | SUP033 | 2025-12 | 2025-10-31 | 978699.96 | 871272 | -107427.96 | 107427.96 | 0 | 2025-12-28 | 4 | 1074911.65 | -96211.69 | DOWN | 0.0983 | 58 | Medium | 449048.74 | 0.474 | 1 | 422223.26 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP042 | 2025-01 | 2024-10-06 | 3031371.02 | 2045348 | -986023.02 | 986023.02 | 1 | 2025-01-28 | 1 |  |  |  |  | 114 | Low | 999794.93 | 0.341 | 6 | 1045553.07 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP042 | 2025-01 | 2024-10-25 | 2473291.21 | 2045348 | -427943.21 | 427943.21 | 1 | 2025-01-28 | 2 | 3031371.02 | -558079.81 | DOWN | 0.2256 | 95 | Low | 1053827.24 | 0.402 | 1 | 991520.76 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP042 | 2025-01 | 2024-11-01 | 2234714.41 | 2045348 | -189366.41 | 189366.41 | 0 | 2025-01-28 | 3 | 2473291.21 | -238576.8 | DOWN | 0.1068 | 88 | Low | 972398.69 | 0.424 | 5 | 1072949.31 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP042 | 2025-02 | 2024-10-03 | 890877.54 | 598996 | -291881.54 | 291881.54 | 1 | 2025-02-28 | 1 |  |  |  |  | 148 | Low | 198737.09 | 0.226 | 0 | 400258.91 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP042 | 2025-02 | 2024-10-26 | 725347.56 | 598996 | -126351.56 | 126351.56 | 1 | 2025-02-28 | 2 | 890877.54 | -165529.98 | DOWN | 0.2282 | 125 | Low | 230842.69 | 0.298 | 6 | 368153.31 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP042 | 2025-02 | 2024-11-04 | 652133.76 | 598996 | -53137.76 | 53137.76 | 0 | 2025-02-28 | 3 | 725347.56 | -73213.8 | DOWN | 0.1123 | 116 | Low | 211310.63 | 0.326 | 0 | 387685.37 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP042 | 2025-02 | 2024-11-12 | 612864.1 | 598996 | -13868.1 | 13868.1 | 0 | 2025-02-28 | 4 | 652133.76 | -39269.66 | DOWN | 0.0641 | 108 | Low | 224158.12 | 0.351 | 0 | 374837.88 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP042 | 2025-02 | 2025-01-26 | 600133.71 | 598996 | -1137.71 | 1137.71 | 0 | 2025-02-28 | 5 | 612864.1 | -12730.39 | DOWN | 0.0212 | 33 | Low | 353874.63 | 0.586 | 3 | 245121.37 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP042 | 2025-02 | 2025-02-07 | 590569.69 | 598996 | 8426.31 | 8426.31 | 0 | 2025-02-28 | 6 | 600133.71 | -9564.02 | DOWN | 0.0162 | 21 | Low | 360908 | 0.623 | 5 | 238088 | 17 | 2.1 | 1.03
P003 | Logistics | SUP042 | 2025-03 | 2024-11-22 | 1841631.49 | 1098687 | -742944.49 | 742944.49 | 1 | 2025-03-28 | 1 |  |  |  |  | 126 | Low | 645626.8 | 0.328 | 3 | 453060.2 | 13 | 1.13 | 1.73
P003 | Logistics | SUP042 | 2025-03 | 2025-01-16 | 1402065.13 | 1098687 | -303378.13 | 303378.13 | 1 | 2025-03-28 | 2 | 1841631.49 | -439566.36 | DOWN | 0.3135 | 71 | Low | 739231.26 | 0.52 | 3 | 359455.74 | 13 | 1.13 | 1.73
P003 | Logistics | SUP042 | 2025-03 | 2025-01-26 | 1247517.57 | 1098687 | -148830.57 | 148830.57 | 0 | 2025-03-28 | 3 | 1402065.13 | -154547.56 | DOWN | 0.1239 | 61 | Low | 638924.83 | 0.555 | 0 | 459762.17 | 13 | 1.13 | 1.73
P003 | Mechanical | SUP042 | 2025-04 | 2025-02-28 | 2435847.18 | 1824244 | -611603.18 | 611603.18 | 1 | 2025-04-28 | 1 |  |  |  |  | 59 | Medium | 1352702.16 | 0.557 | 5 | 471541.84 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP042 | 2025-04 | 2025-04-02 | 2108408.74 | 1824244 | -284164.74 | 284164.74 | 0 | 2025-04-28 | 2 | 2435847.18 | -327438.44 | DOWN | 0.1553 | 26 | Low | 1493218.53 | 0.671 | 5 | 331025.47 | 13 | 1.21 | 1.27
P003 | Mechanical | SUP042 | 2025-04 | 2025-04-08 | 1937469.7 | 1824244 | -113225.7 | 113225.7 | 0 | 2025-04-28 | 3 | 2108408.74 | -170939.04 | DOWN | 0.0882 | 20 | Medium | 1393127.46 | 0.692 | 6 | 431116.54 | 13 | 1.21 | 1.27
P003 | Services | SUP042 | 2025-05 | 2024-12-15 | 2010252.42 | 1245665 | -764587.42 | 764587.42 | 1 | 2025-05-28 | 1 |  |  |  |  | 164 | Low | 397804.01 | 0.19 | 4 | 847860.99 | 14 | 1.36 | 1.73
P003 | Services | SUP042 | 2025-05 | 2025-01-24 | 1615631.71 | 1245665 | -369966.71 | 369966.71 | 1 | 2025-05-28 | 2 | 2010252.42 | -394620.71 | DOWN | 0.2443 | 124 | Low | 538218.94 | 0.326 | 2 | 707446.06 | 14 | 1.36 | 1.73
P003 | Services | SUP042 | 2025-05 | 2025-01-29 | 1393386.06 | 1245665 | -147721.06 | 147721.06 | 0 | 2025-05-28 | 3 | 1615631.71 | -222245.65 | DOWN | 0.1595 | 119 | Low | 497808.39 | 0.343 | 2 | 747856.61 | 14 | 1.36 | 1.73
P003 | Services | SUP042 | 2025-05 | 2025-02-19 | 1334084.21 | 1245665 | -88419.21 | 88419.21 | 0 | 2025-05-28 | 4 | 1393386.06 | -59301.85 | DOWN | 0.0445 | 98 | Low | 543747.8 | 0.415 | 2 | 701917.2 | 14 | 1.36 | 1.73
P003 | Services | SUP042 | 2025-05 | 2025-02-26 | 1289376.94 | 1245665 | -43711.94 | 43711.94 | 0 | 2025-05-28 | 5 | 1334084.21 | -44707.27 | DOWN | 0.0347 | 91 | Low | 532495.18 | 0.438 | 5 | 713169.82 | 14 | 1.36 | 1.73
P003 | Services | SUP042 | 2025-05 | 2025-05-05 | 1252347.8 | 1245665 | -6682.8 | 6682.8 | 0 | 2025-05-28 | 6 | 1289376.94 | -37029.14 | DOWN | 0.0296 | 23 | High | 867491.74 | 0.67 | 5 | 378173.26 | 14 | 1.36 | 1.73
P003 | Software | SUP042 | 2025-06 | 2025-01-16 | 635197.35 | 344166 | -291031.35 | 291031.35 | 1 | 2025-06-28 | 1 |  |  |  |  | 163 | Low | 116475.37 | 0.191 | 0 | 227690.63 | 22 | 1.47 | 1.51
P003 | Software | SUP042 | 2025-06 | 2025-05-06 | 468943.78 | 344166 | -124777.78 | 124777.78 | 1 | 2025-06-28 | 2 | 635197.35 | -166253.57 | DOWN | 0.3545 | 53 | Low | 271055.99 | 0.56 | 3 | 73110.01 | 22 | 1.47 | 1.51
P003 | Software | SUP042 | 2025-06 | 2025-05-26 | 402701.56 | 344166 | -58535.56 | 58535.56 | 0 | 2025-06-28 | 3 | 468943.78 | -66242.22 | DOWN | 0.1645 | 33 | Low | 233771.24 | 0.628 | 6 | 110394.76 | 22 | 1.47 | 1.51
P003 | Logistics | SUP042 | 2025-07 | 2025-02-15 | 2695445.89 | 1717630 | -977815.89 | 977815.89 | 1 | 2025-07-28 | 1 |  |  |  |  | 163 | Low | 577765.29 | 0.202 | 3 | 1139864.71 | 13 | 0.8 | 1.22
P003 | Logistics | SUP042 | 2025-07 | 2025-02-20 | 2147327.51 | 1717630 | -429697.51 | 429697.51 | 1 | 2025-07-28 | 2 | 2695445.89 | -548118.38 | DOWN | 0.2553 | 158 | Low | 445267.96 | 0.22 | 0 | 1272362.04 | 13 | 0.8 | 1.22
P003 | Logistics | SUP042 | 2025-07 | 2025-04-13 | 1946994.2 | 1717630 | -229364.2 | 229364.2 | 0 | 2025-07-28 | 3 | 2147327.51 | -200333.31 | DOWN | 0.1029 | 106 | Low | 797959.15 | 0.404 | 2 | 919670.85 | 13 | 0.8 | 1.22
P003 | Logistics | SUP042 | 2025-07 | 2025-04-20 | 1855941.79 | 1717630 | -138311.79 | 138311.79 | 0 | 2025-07-28 | 4 | 1946994.2 | -91052.41 | DOWN | 0.0491 | 99 | Low | 797748.98 | 0.429 | 1 | 919881.02 | 13 | 0.8 | 1.22
P003 | Logistics | SUP042 | 2025-07 | 2025-06-03 | 1747141.4 | 1717630 | -29511.4 | 29511.4 | 0 | 2025-07-28 | 5 | 1855941.79 | -108800.39 | DOWN | 0.0623 | 55 | Medium | 972379.97 | 0.585 | 6 | 745250.03 | 13 | 0.8 | 1.22
P003 | Logistics | SUP042 | 2025-07 | 2025-06-03 | 1713597.15 | 1717630 | 4032.85 | 4032.85 | 0 | 2025-07-28 | 6 | 1747141.4 | -33544.25 | DOWN | 0.0196 | 55 | Medium | 959841.09 | 0.585 | 3 | 757788.91 | 13 | 0.8 | 1.22
P003 | Logistics | SUP042 | 2025-08 | 2025-03-01 | 1300430.93 | 899006 | -401424.93 | 401424.93 | 1 | 2025-08-28 | 1 |  |  |  |  | 180 | Low | 189886.86 | 0.149 | 0 | 709119.14 | 7 | 1.37 | 1.47
P003 | Logistics | SUP042 | 2025-08 | 2025-04-06 | 1071468.04 | 899006 | -172462.04 | 172462.04 | 1 | 2025-08-28 | 2 | 1300430.93 | -228962.89 | DOWN | 0.2137 | 144 | Low | 284660.98 | 0.258 | 1 | 614345.02 | 7 | 1.37 | 1.47
P003 | Logistics | SUP042 | 2025-08 | 2025-04-14 | 975890.04 | 899006 | -76884.04 | 76884.04 | 0 | 2025-08-28 | 3 | 1071468.04 | -95578 | DOWN | 0.0979 | 136 | Low | 291141.05 | 0.285 | 2 | 607864.95 | 7 | 1.37 | 1.47
P003 | Logistics | SUP042 | 2025-08 | 2025-04-22 | 921723.4 | 899006 | -22717.4 | 22717.4 | 0 | 2025-08-28 | 4 | 975890.04 | -54166.64 | DOWN | 0.0588 | 128 | Low | 293632.32 | 0.312 | 1 | 605373.68 | 7 | 1.37 | 1.47
P003 | Logistics | SUP042 | 2025-08 | 2025-07-28 | 895722.79 | 899006 | 3283.21 | 3283.21 | 0 | 2025-08-28 | 5 | 921723.4 | -26000.61 | DOWN | 0.029 | 31 | Medium | 599950.84 | 0.642 | 6 | 299055.16 | 7 | 1.37 | 1.47
P003 | Materials | SUP042 | 2025-09 | 2025-04-02 | 1167719.68 | 769893 | -397826.68 | 397826.68 | 1 | 2025-09-28 | 1 |  |  |  |  | 179 | Low | 175105.43 | 0.156 | 2 | 594787.57 | 10 | 0.71 | 1.27
P003 | Materials | SUP042 | 2025-09 | 2025-05-29 | 940576.32 | 769893 | -170683.32 | 170683.32 | 1 | 2025-09-28 | 2 | 1167719.68 | -227143.36 | DOWN | 0.2415 | 122 | Low | 316349.11 | 0.347 | 5 | 453543.89 | 10 | 0.71 | 1.27
P003 | Materials | SUP042 | 2025-09 | 2025-06-21 | 842713.84 | 769893 | -72820.84 | 72820.84 | 0 | 2025-09-28 | 3 | 940576.32 | -97862.48 | DOWN | 0.1161 | 99 | Low | 370962.55 | 0.429 | 0 | 398930.45 | 10 | 0.71 | 1.27
P003 | Materials | SUP042 | 2025-09 | 2025-08-15 | 795413.13 | 769893 | -25520.13 | 25520.13 | 0 | 2025-09-28 | 4 | 842713.84 | -47300.71 | DOWN | 0.0595 | 44 | Medium | 511981.55 | 0.624 | 6 | 257911.45 | 10 | 0.71 | 1.27
P003 | Logistics | SUP042 | 2025-10 | 2025-06-05 | 1622158.79 | 891226 | -730932.79 | 730932.79 | 1 | 2025-10-28 | 1 |  |  |  |  | 145 | Low | 404941.36 | 0.266 | 2 | 486284.64 | 19 | 0.95 | 0.98
P003 | Logistics | SUP042 | 2025-10 | 2025-07-14 | 1251097.56 | 891226 | -359871.56 | 359871.56 | 1 | 2025-10-28 | 2 | 1622158.79 | -371061.23 | DOWN | 0.2966 | 106 | Low | 502975.59 | 0.404 | 0 | 388250.41 | 19 | 0.95 | 0.98
P003 | Logistics | SUP042 | 2025-10 | 2025-09-06 | 1055353.1 | 891226 | -164127.1 | 164127.1 | 1 | 2025-10-28 | 3 | 1251097.56 | -195744.46 | DOWN | 0.1855 | 52 | Low | 607024.94 | 0.596 | 2 | 284201.06 | 19 | 0.95 | 0.98
P003 | Logistics | SUP042 | 2025-11 | 2025-07-21 | 2701512.43 | 1396368 | -1305144.43 | 1305144.43 | 1 | 2025-11-28 | 1 |  |  |  |  | 130 | Low | 747914.03 | 0.29 | 3 | 648453.97 | 11 | 1.85 | 1.52
P003 | Logistics | SUP042 | 2025-11 | 2025-08-22 | 1924132.69 | 1396368 | -527764.69 | 527764.69 | 1 | 2025-11-28 | 2 | 2701512.43 | -777379.74 | DOWN | 0.404 | 98 | Low | 788020.89 | 0.393 | 5 | 608347.11 | 11 | 1.85 | 1.52
P003 | Logistics | SUP042 | 2025-11 | 2025-08-22 | 1613366.55 | 1396368 | -216998.55 | 216998.55 | 0 | 2025-11-28 | 3 | 1924132.69 | -310766.14 | DOWN | 0.1926 | 98 | Low | 651597.29 | 0.393 | 5 | 744770.71 | 11 | 1.85 | 1.52
P003 | Logistics | SUP042 | 2025-11 | 2025-09-02 | 1449413.58 | 1396368 | -53045.58 | 53045.58 | 0 | 2025-11-28 | 4 | 1613366.55 | -163952.97 | DOWN | 0.1131 | 87 | Low | 644025.9 | 0.428 | 0 | 752342.1 | 11 | 1.85 | 1.52
P003 | Logistics | SUP042 | 2025-11 | 2025-10-14 | 1390474.31 | 1396368 | 5893.69 | 5893.69 | 0 | 2025-11-28 | 5 | 1449413.58 | -58939.27 | DOWN | 0.0424 | 45 | Medium | 738919.9 | 0.563 | 5 | 657448.1 | 11 | 1.85 | 1.52
P003 | Logistics | SUP042 | 2025-11 | 2025-11-14 | 1371381.16 | 1396368 | 24986.84 | 24986.84 | 0 | 2025-11-28 | 6 | 1390474.31 | -19093.15 | DOWN | 0.0139 | 14 | Medium | 953367.79 | 0.663 | 5 | 443000.21 | 11 | 1.85 | 1.52
P003 | Electronics | SUP042 | 2025-12 | 2025-07-05 | 638178.26 | 465344 | -172834.26 | 172834.26 | 1 | 2025-12-28 | 1 |  |  |  |  | 176 | Low | 101197.09 | 0.155 | 2 | 364146.91 | 10 | 1.08 | 1.22
P003 | Electronics | SUP042 | 2025-12 | 2025-10-04 | 542318.59 | 465344 | -76974.59 | 76974.59 | 0 | 2025-12-28 | 2 | 638178.26 | -95859.67 | DOWN | 0.1768 | 85 | Low | 265402.5 | 0.474 | 3 | 199941.5 | 10 | 1.08 | 1.22
P003 | Electronics | SUP042 | 2025-12 | 2025-10-11 | 504025.95 | 465344 | -38681.95 | 38681.95 | 0 | 2025-12-28 | 3 | 542318.59 | -38292.64 | DOWN | 0.076 | 78 | Low | 247290.85 | 0.499 | 3 | 218053.15 | 10 | 1.08 | 1.22
P003 | Electronics | SUP042 | 2025-12 | 2025-11-09 | 482225.61 | 465344 | -16881.61 | 16881.61 | 0 | 2025-12-28 | 4 | 504025.95 | -21800.34 | DOWN | 0.0452 | 49 | Medium | 308258.41 | 0.601 | 4 | 157085.59 | 10 | 1.08 | 1.22
P003 | Electronics | SUP042 | 2025-12 | 2025-12-06 | 468130.46 | 465344 | -2786.46 | 2786.46 | 0 | 2025-12-28 | 5 | 482225.61 | -14095.15 | DOWN | 0.0301 | 22 | High | 321075.92 | 0.695 | 6 | 144268.08 | 10 | 1.08 | 1.22
P003 | Electronics | SUP042 | 2025-12 | 2025-12-09 | 469929.89 | 465344 | -4585.89 | 4585.89 | 0 | 2025-12-28 | 6 | 468130.46 | 1799.43 | UP | 0.0038 | 19 | High | 345894.6 | 0.706 | 6 | 119449.4 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP012 | 2025-01 | 2024-08-30 | 401379.25 | 291222 | -110157.25 | 110157.25 | 1 | 2025-01-28 | 1 |  |  |  |  | 151 | Low | 86363.04 | 0.222 | 2 | 204858.96 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP012 | 2025-01 | 2024-09-18 | 335584.49 | 291222 | -44362.49 | 44362.49 | 0 | 2025-01-28 | 2 | 401379.25 | -65794.76 | DOWN | 0.1961 | 132 | Low | 94363.44 | 0.283 | 0 | 196858.56 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP012 | 2025-01 | 2024-10-24 | 315938.52 | 291222 | -24716.52 | 24716.52 | 0 | 2025-01-28 | 3 | 335584.49 | -19645.97 | DOWN | 0.0622 | 96 | Low | 117087.86 | 0.399 | 3 | 174134.14 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP012 | 2025-01 | 2025-01-13 | 301829.8 | 291222 | -10607.8 | 10607.8 | 0 | 2025-01-28 | 4 | 315938.52 | -14108.72 | DOWN | 0.0467 | 15 | Medium | 213441.52 | 0.659 | 7 | 77780.48 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP012 | 2025-02 | 2024-09-17 | 2559524.54 | 2139361 | -420163.54 | 420163.54 | 1 | 2025-02-28 | 1 |  |  |  |  | 164 | Low | 478511.67 | 0.175 | 0 | 1660849.33 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP012 | 2025-02 | 2024-10-11 | 2297364.96 | 2139361 | -158003.96 | 158003.96 | 0 | 2025-02-28 | 2 | 2559524.54 | -262159.58 | DOWN | 0.1141 | 140 | Low | 574510.22 | 0.251 | 1 | 1564850.78 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP012 | 2025-02 | 2024-12-14 | 2224273.5 | 2139361 | -84912.5 | 84912.5 | 0 | 2025-02-28 | 3 | 2297364.96 | -73091.46 | DOWN | 0.0329 | 76 | Low | 1069039.63 | 0.451 | 0 | 1070321.37 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP012 | 2025-02 | 2025-02-06 | 2162834.82 | 2139361 | -23473.82 | 23473.82 | 0 | 2025-02-28 | 4 | 2224273.5 | -61438.68 | DOWN | 0.0284 | 22 | Low | 1401127.48 | 0.62 | 3 | 738233.52 | 17 | 2.1 | 1.03
P003 | Services | SUP012 | 2025-03 | 2024-12-09 | 2068218.43 | 1326306 | -741912.43 | 741912.43 | 1 | 2025-03-28 | 1 |  |  |  |  | 109 | Low | 778536.37 | 0.388 | 2 | 547769.63 | 13 | 1.13 | 1.73
P003 | Services | SUP012 | 2025-03 | 2025-01-25 | 1629967.69 | 1326306 | -303661.69 | 303661.69 | 1 | 2025-03-28 | 2 | 2068218.43 | -438250.74 | DOWN | 0.2689 | 62 | Low | 941129.78 | 0.552 | 0 | 385176.22 | 13 | 1.13 | 1.73
P003 | Services | SUP012 | 2025-03 | 2025-02-28 | 1466663.39 | 1326306 | -140357.39 | 140357.39 | 0 | 2025-03-28 | 3 | 1629967.69 | -163304.3 | DOWN | 0.1113 | 28 | Medium | 968937.08 | 0.67 | 3 | 357368.92 | 13 | 1.13 | 1.73
P003 | Materials | SUP012 | 2025-04 | 2024-12-17 | 748696.16 | 564749 | -183947.16 | 183947.16 | 1 | 2025-04-28 | 1 |  |  |  |  | 132 | Low | 222305.8 | 0.304 | 3 | 342443.2 | 13 | 1.21 | 1.27
P003 | Materials | SUP012 | 2025-04 | 2025-01-02 | 651040.81 | 564749 | -86291.81 | 86291.81 | 0 | 2025-04-28 | 2 | 748696.16 | -97655.35 | DOWN | 0.15 | 116 | Low | 221805.71 | 0.36 | 1 | 342943.29 | 13 | 1.21 | 1.27
P003 | Materials | SUP012 | 2025-04 | 2025-03-05 | 601624.37 | 564749 | -36875.37 | 36875.37 | 0 | 2025-04-28 | 3 | 651040.81 | -49416.44 | DOWN | 0.0821 | 54 | Medium | 323708.95 | 0.574 | 4 | 241040.05 | 13 | 1.21 | 1.27
P003 | Materials | SUP012 | 2025-04 | 2025-03-24 | 574090.54 | 564749 | -9341.54 | 9341.54 | 0 | 2025-04-28 | 4 | 601624.37 | -27533.83 | DOWN | 0.048 | 35 | Medium | 389812.12 | 0.64 | 7 | 174936.88 | 13 | 1.21 | 1.27
P003 | Materials | SUP012 | 2025-04 | 2025-04-09 | 570858.47 | 564749 | -6109.47 | 6109.47 | 0 | 2025-04-28 | 5 | 574090.54 | -3232.07 | DOWN | 0.0057 | 19 | High | 371287.77 | 0.695 | 5 | 193461.23 | 13 | 1.21 | 1.27
P003 | Electronics | SUP012 | 2025-05 | 2024-12-15 | 1025993.26 | 624888 | -401105.26 | 401105.26 | 1 | 2025-05-28 | 1 |  |  |  |  | 164 | Low | 185458.25 | 0.19 | 2 | 439429.75 | 14 | 1.36 | 1.73
P003 | Electronics | SUP012 | 2025-05 | 2025-02-14 | 799971.51 | 624888 | -175083.51 | 175083.51 | 1 | 2025-05-28 | 2 | 1025993.26 | -226021.75 | DOWN | 0.2825 | 103 | Low | 305110.96 | 0.398 | 2 | 319777.04 | 14 | 1.36 | 1.73
P003 | Electronics | SUP012 | 2025-05 | 2025-02-22 | 715636.63 | 624888 | -90748.63 | 90748.63 | 0 | 2025-05-28 | 3 | 799971.51 | -84334.88 | DOWN | 0.1178 | 95 | Low | 307578.05 | 0.425 | 5 | 317309.95 | 14 | 1.36 | 1.73
P003 | Electronics | SUP012 | 2025-05 | 2025-03-23 | 660943.99 | 624888 | -36055.99 | 36055.99 | 0 | 2025-05-28 | 4 | 715636.63 | -54692.64 | DOWN | 0.0827 | 66 | Low | 364146.88 | 0.523 | 1 | 260741.12 | 14 | 1.36 | 1.73
P003 | Logistics | SUP012 | 2025-06 | 2025-02-05 | 2780669.43 | 1644061 | -1136608.43 | 1136608.43 | 1 | 2025-06-28 | 1 |  |  |  |  | 143 | Low | 745395.97 | 0.258 | 0 | 898665.03 | 22 | 1.47 | 1.51
P003 | Logistics | SUP012 | 2025-06 | 2025-03-05 | 2172833.05 | 1644061 | -528772.05 | 528772.05 | 1 | 2025-06-28 | 2 | 2780669.43 | -607836.38 | DOWN | 0.2797 | 115 | Low | 718198.9 | 0.352 | 3 | 925862.1 | 22 | 1.47 | 1.51
P003 | Logistics | SUP012 | 2025-06 | 2025-05-08 | 1927349.9 | 1644061 | -283288.9 | 283288.9 | 0 | 2025-06-28 | 3 | 2172833.05 | -245483.15 | DOWN | 0.1274 | 51 | Low | 1086804.85 | 0.567 | 4 | 557256.15 | 22 | 1.47 | 1.51
P003 | Logistics | SUP012 | 2025-06 | 2025-05-13 | 1756931.14 | 1644061 | -112870.14 | 112870.14 | 0 | 2025-06-28 | 4 | 1927349.9 | -170418.76 | DOWN | 0.097 | 46 | Medium | 1057977.11 | 0.584 | 4 | 586083.89 | 22 | 1.47 | 1.51
P003 | Logistics | SUP012 | 2025-06 | 2025-05-20 | 1688337.3 | 1644061 | -44276.3 | 44276.3 | 0 | 2025-06-28 | 5 | 1756931.14 | -68593.84 | DOWN | 0.0406 | 39 | Medium | 979273.34 | 0.607 | 5 | 664787.66 | 22 | 1.47 | 1.51
P003 | Services | SUP012 | 2025-07 | 2025-02-13 | 4355612.84 | 2729768 | -1625844.84 | 1625844.84 | 1 | 2025-07-28 | 1 |  |  |  |  | 165 | Low | 899727.69 | 0.195 | 0 | 1830040.31 | 13 | 0.8 | 1.22
P003 | Services | SUP012 | 2025-07 | 2025-02-20 | 3431881.91 | 2729768 | -702113.91 | 702113.91 | 1 | 2025-07-28 | 2 | 4355612.84 | -923730.93 | DOWN | 0.2692 | 158 | Low | 750408.63 | 0.22 | 1 | 1979359.37 | 13 | 0.8 | 1.22
P003 | Services | SUP012 | 2025-07 | 2025-04-13 | 3096097.36 | 2729768 | -366329.36 | 366329.36 | 0 | 2025-07-28 | 3 | 3431881.91 | -335784.55 | DOWN | 0.1085 | 106 | Low | 1295510.92 | 0.404 | 3 | 1434257.08 | 13 | 0.8 | 1.22
P003 | Services | SUP012 | 2025-07 | 2025-04-15 | 2894188.16 | 2729768 | -164420.16 | 164420.16 | 0 | 2025-07-28 | 4 | 3096097.36 | -201909.2 | DOWN | 0.0698 | 104 | Low | 1280583.97 | 0.411 | 4 | 1449184.03 | 13 | 0.8 | 1.22
P003 | Services | SUP012 | 2025-07 | 2025-05-11 | 2822726.77 | 2729768 | -92958.77 | 92958.77 | 0 | 2025-07-28 | 5 | 2894188.16 | -71461.39 | DOWN | 0.0253 | 78 | Low | 1315727.73 | 0.503 | 1 | 1414040.27 | 13 | 0.8 | 1.22
P003 | Services | SUP012 | 2025-07 | 2025-07-01 | 2804776.61 | 2729768 | -75008.61 | 75008.61 | 0 | 2025-07-28 | 6 | 2822726.77 | -17950.16 | DOWN | 0.0064 | 27 | High | 1815669.17 | 0.684 | 1 | 914098.83 | 13 | 0.8 | 1.22
P003 | Services | SUP012 | 2025-08 | 2025-05-09 | 456323.01 | 318436 | -137887.01 | 137887.01 | 1 | 2025-08-28 | 1 |  |  |  |  | 111 | Low | 175138.52 | 0.37 | 7 | 143297.48 | 7 | 1.37 | 1.47
P003 | Services | SUP012 | 2025-08 | 2025-06-11 | 373144.93 | 318436 | -54708.93 | 54708.93 | 0 | 2025-08-28 | 2 | 456323.01 | -83178.08 | DOWN | 0.2229 | 78 | Low | 172346.55 | 0.482 | 4 | 146089.45 | 7 | 1.37 | 1.47
P003 | Services | SUP012 | 2025-08 | 2025-07-15 | 340971.61 | 318436 | -22535.61 | 22535.61 | 0 | 2025-08-28 | 3 | 373144.93 | -32173.32 | DOWN | 0.0944 | 44 | Medium | 205274.31 | 0.597 | 5 | 113161.69 | 7 | 1.37 | 1.47
P003 | Services | SUP012 | 2025-09 | 2025-04-02 | 2823829.03 | 2003752 | -820077.03 | 820077.03 | 1 | 2025-09-28 | 1 |  |  |  |  | 179 | Low | 418325.52 | 0.156 | 1 | 1585426.48 | 10 | 0.71 | 1.27
P003 | Services | SUP012 | 2025-09 | 2025-04-08 | 2396350.37 | 2003752 | -392598.37 | 392598.37 | 1 | 2025-09-28 | 2 | 2823829.03 | -427478.66 | DOWN | 0.1784 | 173 | Low | 384840.61 | 0.167 | 3 | 1618911.39 | 10 | 0.71 | 1.27
P003 | Services | SUP012 | 2025-09 | 2025-06-09 | 2161541.7 | 2003752 | -157789.7 | 157789.7 | 0 | 2025-09-28 | 3 | 2396350.37 | -234808.67 | DOWN | 0.1086 | 111 | Low | 833404.45 | 0.386 | 1 | 1170347.55 | 10 | 0.71 | 1.27
P003 | Services | SUP012 | 2025-09 | 2025-09-12 | 2088512.66 | 2003752 | -84760.66 | 84760.66 | 0 | 2025-09-28 | 4 | 2161541.7 | -73029.04 | DOWN | 0.035 | 16 | High | 1394730.24 | 0.723 | 5 | 609021.76 | 10 | 0.71 | 1.27
P003 | Services | SUP012 | 2025-10 | 2025-05-03 | 2452254.48 | 1618705 | -833549.48 | 833549.48 | 1 | 2025-10-28 | 1 |  |  |  |  | 178 | Low | 370121.74 | 0.156 | 1 | 1248583.26 | 19 | 0.95 | 0.98
P003 | Services | SUP012 | 2025-10 | 2025-06-10 | 1981212.12 | 1618705 | -362507.12 | 362507.12 | 1 | 2025-10-28 | 2 | 2452254.48 | -471042.36 | DOWN | 0.2378 | 140 | Low | 518896.1 | 0.284 | 3 | 1099808.9 | 19 | 0.95 | 0.98
P003 | Services | SUP012 | 2025-10 | 2025-07-26 | 1781730.21 | 1618705 | -163025.21 | 163025.21 | 0 | 2025-10-28 | 3 | 1981212.12 | -199481.91 | DOWN | 0.112 | 94 | Low | 854035.48 | 0.447 | 3 | 764669.52 | 19 | 0.95 | 0.98
P003 | Services | SUP012 | 2025-10 | 2025-08-19 | 1677955.69 | 1618705 | -59250.69 | 59250.69 | 0 | 2025-10-28 | 4 | 1781730.21 | -103774.52 | DOWN | 0.0618 | 70 | Low | 888701.47 | 0.532 | 5 | 730003.53 | 19 | 0.95 | 0.98
P003 | Services | SUP012 | 2025-10 | 2025-08-24 | 1636292.54 | 1618705 | -17587.54 | 17587.54 | 0 | 2025-10-28 | 5 | 1677955.69 | -41663.15 | DOWN | 0.0255 | 65 | Low | 877666.55 | 0.55 | 2 | 741038.45 | 19 | 0.95 | 0.98
P003 | Services | SUP012 | 2025-11 | 2025-08-08 | 819856.49 | 545712 | -274144.49 | 274144.49 | 1 | 2025-11-28 | 1 |  |  |  |  | 112 | Low | 278253.06 | 0.347 | 2 | 267458.94 | 11 | 1.85 | 1.52
P003 | Services | SUP012 | 2025-11 | 2025-10-25 | 676600.19 | 545712 | -130888.19 | 130888.19 | 1 | 2025-11-28 | 2 | 819856.49 | -143256.3 | DOWN | 0.2117 | 34 | Low | 434006.47 | 0.598 | 3 | 111705.53 | 11 | 1.85 | 1.52
P003 | Services | SUP012 | 2025-11 | 2025-11-11 | 607153.43 | 545712 | -61441.43 | 61441.43 | 0 | 2025-11-28 | 3 | 676600.19 | -69446.76 | DOWN | 0.1144 | 17 | Medium | 397220.03 | 0.653 | 6 | 148491.97 | 11 | 1.85 | 1.52
P003 | Services | SUP012 | 2025-11 | 2025-11-16 | 566648.48 | 545712 | -20936.48 | 20936.48 | 0 | 2025-11-28 | 4 | 607153.43 | -40504.95 | DOWN | 0.0715 | 12 | Medium | 370906.98 | 0.669 | 4 | 174805.02 | 11 | 1.85 | 1.52
P003 | Services | SUP012 | 2025-12 | 2025-09-18 | 1170835.9 | 765978 | -404857.9 | 404857.9 | 1 | 2025-12-28 | 1 |  |  |  |  | 101 | Low | 474304.84 | 0.418 | 3 | 291673.16 | 10 | 1.08 | 1.22
P003 | Services | SUP012 | 2025-12 | 2025-09-22 | 950547.37 | 765978 | -184569.37 | 184569.37 | 1 | 2025-12-28 | 2 | 1170835.9 | -220288.53 | DOWN | 0.2317 | 97 | Low | 424822.97 | 0.432 | 5 | 341155.03 | 10 | 1.08 | 1.22
P003 | Services | SUP012 | 2025-12 | 2025-09-27 | 863088.35 | 765978 | -97110.35 | 97110.35 | 0 | 2025-12-28 | 3 | 950547.37 | -87459.02 | DOWN | 0.1013 | 92 | Low | 368581.53 | 0.45 | 3 | 397396.47 | 10 | 1.08 | 1.22
P003 | Electronics | SUP020 | 2025-01 | 2024-08-06 | 2827669.5 | 1429068 | -1398601.5 | 1398601.5 | 1 | 2025-01-28 | 1 |  |  |  |  | 175 | Low | 261116.78 | 0.093 | 3 | 1167951.22 | 17 | 1.86 | 1.34
P003 | Electronics | SUP020 | 2025-01 | 2024-08-11 | 2469266.9 | 1429068 | -1040198.9 | 1040198.9 | 1 | 2025-01-28 | 2 | 2827669.5 | -358402.6 | DOWN | 0.1451 | 170 | Low | 246176.99 | 0.103 | 2 | 1182891.01 | 17 | 1.86 | 1.34
P003 | Electronics | SUP020 | 2025-01 | 2024-08-12 | 2211056.4 | 1429068 | -781988.4 | 781988.4 | 1 | 2025-01-28 | 3 | 2469266.9 | -258210.5 | DOWN | 0.1168 | 169 | Low | 238570.83 | 0.105 | 0 | 1190497.17 | 17 | 1.86 | 1.34
P003 | Electronics | SUP020 | 2025-01 | 2024-10-10 | 2021202.01 | 1429068 | -592134.01 | 592134.01 | 1 | 2025-01-28 | 4 | 2211056.4 | -189854.39 | DOWN | 0.0939 | 110 | Low | 446651.75 | 0.227 | 3 | 982416.25 | 17 | 1.86 | 1.34
P003 | Electronics | SUP020 | 2025-01 | 2024-11-27 | 1871802.29 | 1429068 | -442734.29 | 442734.29 | 1 | 2025-01-28 | 5 | 2021202.01 | -149399.72 | DOWN | 0.0798 | 62 | Low | 619582.73 | 0.325 | 1 | 809485.27 | 17 | 1.86 | 1.34
P003 | Electronics | SUP020 | 2025-01 | 2024-12-04 | 1771179.36 | 1429068 | -342111.36 | 342111.36 | 1 | 2025-01-28 | 6 | 1871802.29 | -100622.93 | DOWN | 0.0568 | 55 | Low | 569658.06 | 0.34 | 3 | 859409.94 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP020 | 2025-02 | 2024-11-16 | 2609699.53 | 1170273 | -1439426.53 | 1439426.53 | 1 | 2025-02-28 | 1 |  |  |  |  | 104 | Low | 629969.43 | 0.233 | 0 | 540303.57 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP020 | 2025-02 | 2024-12-18 | 2256779.71 | 1170273 | -1086506.71 | 1086506.71 | 1 | 2025-02-28 | 2 | 2609699.53 | -352919.82 | DOWN | 0.1564 | 72 | Low | 664355.95 | 0.297 | 5 | 505917.05 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP020 | 2025-02 | 2025-02-09 | 1959959.74 | 1170273 | -789686.74 | 789686.74 | 1 | 2025-02-28 | 3 | 2256779.71 | -296819.97 | DOWN | 0.1514 | 19 | Low | 736003.3 | 0.404 | 1 | 434269.7 | 17 | 2.1 | 1.03
P003 | Mechanical | SUP020 | 2025-02 | 2025-02-18 | 1792394.82 | 1170273 | -622121.82 | 622121.82 | 1 | 2025-02-28 | 4 | 1959959.74 | -167564.92 | DOWN | 0.0935 | 10 | Low | 758575.56 | 0.42 | 0 | 411697.44 | 17 | 2.1 | 1.03
P003 | Logistics | SUP020 | 2025-03 | 2024-10-02 | 5745977.11 | 2503817 | -3242160.11 | 3242160.11 | 1 | 2025-03-28 | 1 |  |  |  |  | 177 | Low | 524659.49 | 0.098 | 3 | 1979157.51 | 13 | 1.13 | 1.73
P003 | Logistics | SUP020 | 2025-03 | 2024-11-06 | 5001850.11 | 2503817 | -2498033.11 | 2498033.11 | 1 | 2025-03-28 | 2 | 5745977.11 | -744127 | DOWN | 0.1488 | 142 | Low | 838206.13 | 0.175 | 2 | 1665610.87 | 13 | 1.13 | 1.73
P003 | Logistics | SUP020 | 2025-03 | 2025-01-14 | 4350987.49 | 2503817 | -1847170.49 | 1847170.49 | 1 | 2025-03-28 | 3 | 5001850.11 | -650862.62 | DOWN | 0.1496 | 73 | Low | 1347555.45 | 0.329 | 4 | 1156261.55 | 13 | 1.13 | 1.73
P003 | Logistics | SUP020 | 2025-03 | 2025-02-26 | 3823330.43 | 2503817 | -1319513.43 | 1319513.43 | 1 | 2025-03-28 | 4 | 4350987.49 | -527657.06 | DOWN | 0.138 | 30 | Low | 1615821.66 | 0.425 | 3 | 887995.34 | 13 | 1.13 | 1.73
P003 | Logistics | SUP020 | 2025-03 | 2025-03-16 | 3513052.79 | 2503817 | -1009235.79 | 1009235.79 | 1 | 2025-03-28 | 5 | 3823330.43 | -310277.64 | DOWN | 0.0883 | 12 | Low | 1755177.42 | 0.465 | 3 | 748639.58 | 13 | 1.13 | 1.73
P003 | Materials | SUP020 | 2025-04 | 2024-11-01 | 210640.45 | 125355 | -85285.45 | 85285.45 | 1 | 2025-04-28 | 1 |  |  |  |  | 178 | Low | 21266.01 | 0.098 | 1 | 104088.99 | 13 | 1.21 | 1.27
P003 | Materials | SUP020 | 2025-04 | 2024-12-08 | 191506.2 | 125355 | -66151.2 | 66151.2 | 1 | 2025-04-28 | 2 | 210640.45 | -19134.25 | DOWN | 0.0999 | 141 | Low | 34515.59 | 0.175 | 4 | 90839.41 | 13 | 1.21 | 1.27
P003 | Materials | SUP020 | 2025-04 | 2025-04-09 | 176172.83 | 125355 | -50817.83 | 50817.83 | 1 | 2025-04-28 | 3 | 191506.2 | -15333.37 | DOWN | 0.087 | 19 | Low | 78682.44 | 0.446 | 2 | 46672.56 | 13 | 1.21 | 1.27
P003 | Logistics | SUP020 | 2025-05 | 2024-12-07 | 336756.74 | 166993 | -169763.74 | 169763.74 | 1 | 2025-05-28 | 1 |  |  |  |  | 172 | Low | 36856.34 | 0.105 | 1 | 130136.66 | 14 | 1.36 | 1.73
P003 | Logistics | SUP020 | 2025-05 | 2024-12-11 | 290491.37 | 166993 | -123498.37 | 123498.37 | 1 | 2025-05-28 | 2 | 336756.74 | -46265.37 | DOWN | 0.1593 | 168 | Low | 31924.29 | 0.113 | 3 | 135068.71 | 14 | 1.36 | 1.73
P003 | Logistics | SUP020 | 2025-05 | 2024-12-16 | 252269.92 | 166993 | -85276.92 | 85276.92 | 1 | 2025-05-28 | 3 | 290491.37 | -38221.45 | DOWN | 0.1515 | 163 | Low | 29941.25 | 0.124 | 3 | 137051.75 | 14 | 1.36 | 1.73
P003 | Logistics | SUP020 | 2025-05 | 2025-01-03 | 232755.44 | 166993 | -65762.44 | 65762.44 | 1 | 2025-05-28 | 4 | 252269.92 | -19514.48 | DOWN | 0.0838 | 145 | Low | 38260.52 | 0.163 | 1 | 128732.48 | 14 | 1.36 | 1.73
P003 | Logistics | SUP020 | 2025-05 | 2025-01-13 | 218134.02 | 166993 | -51141.02 | 51141.02 | 1 | 2025-05-28 | 5 | 232755.44 | -14621.42 | DOWN | 0.067 | 135 | Low | 41929.79 | 0.185 | 0 | 125063.21 | 14 | 1.36 | 1.73
P003 | Logistics | SUP020 | 2025-05 | 2025-03-30 | 205551 | 166993 | -38558 | 38558 | 1 | 2025-05-28 | 6 | 218134.02 | -12583.02 | DOWN | 0.0612 | 59 | Low | 68007.26 | 0.351 | 2 | 98985.74 | 14 | 1.36 | 1.73
P003 | Software | SUP020 | 2025-06 | 2025-04-20 | 4138840.3 | 2088406 | -2050434.3 | 2050434.3 | 1 | 2025-06-28 | 1 |  |  |  |  | 69 | Low | 1433401.87 | 0.325 | 2 | 655004.13 | 22 | 1.47 | 1.51
P003 | Software | SUP020 | 2025-06 | 2025-04-20 | 3655725.36 | 2088406 | -1567319.36 | 1567319.36 | 1 | 2025-06-28 | 2 | 4138840.3 | -483114.94 | DOWN | 0.1322 | 69 | Low | 1156245.8 | 0.325 | 3 | 932160.2 | 22 | 1.47 | 1.51
P003 | Software | SUP020 | 2025-06 | 2025-06-16 | 3236002.73 | 2088406 | -1147596.73 | 1147596.73 | 1 | 2025-06-28 | 3 | 3655725.36 | -419722.63 | DOWN | 0.1297 | 12 | Low | 1468254.76 | 0.447 | 0 | 620151.24 | 22 | 1.47 | 1.51
P003 | Mechanical | SUP020 | 2025-07 | 2025-02-23 | 444597.25 | 263739 | -180858.25 | 180858.25 | 1 | 2025-07-28 | 1 |  |  |  |  | 155 | Low | 62866.93 | 0.148 | 0 | 200872.07 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP020 | 2025-07 | 2025-03-12 | 397162.53 | 263739 | -133423.53 | 133423.53 | 1 | 2025-07-28 | 2 | 444597.25 | -47434.72 | DOWN | 0.1194 | 138 | Low | 68934.31 | 0.186 | 0 | 194804.69 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP020 | 2025-07 | 2025-04-08 | 361722.97 | 263739 | -97983.97 | 97983.97 | 1 | 2025-07-28 | 3 | 397162.53 | -35439.56 | DOWN | 0.098 | 111 | Low | 94593.64 | 0.248 | 3 | 169145.36 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP020 | 2025-07 | 2025-06-13 | 337374.37 | 263739 | -73635.37 | 73635.37 | 1 | 2025-07-28 | 4 | 361722.97 | -24348.6 | DOWN | 0.0722 | 45 | Low | 131561.84 | 0.398 | 5 | 132177.16 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP020 | 2025-07 | 2025-07-17 | 320794.84 | 263739 | -57055.84 | 57055.84 | 1 | 2025-07-28 | 5 | 337374.37 | -16579.53 | DOWN | 0.0517 | 11 | Low | 140289.44 | 0.475 | 4 | 123449.56 | 13 | 0.8 | 1.22
P003 | Logistics | SUP020 | 2025-08 | 2025-03-20 | 3917759.27 | 2000598 | -1917161.27 | 1917161.27 | 1 | 2025-08-28 | 1 |  |  |  |  | 161 | Low | 470227.88 | 0.128 | 0 | 1530370.12 | 7 | 1.37 | 1.47
P003 | Logistics | SUP020 | 2025-08 | 2025-05-20 | 3377320.67 | 2000598 | -1376722.67 | 1376722.67 | 1 | 2025-08-28 | 2 | 3917759.27 | -540438.6 | DOWN | 0.16 | 100 | Low | 949060.88 | 0.261 | 5 | 1051537.12 | 7 | 1.37 | 1.47
P003 | Logistics | SUP020 | 2025-08 | 2025-07-04 | 3020475.01 | 2000598 | -1019877.01 | 1019877.01 | 1 | 2025-08-28 | 3 | 3377320.67 | -356845.66 | DOWN | 0.1181 | 55 | Low | 1060386.95 | 0.359 | 2 | 940211.05 | 7 | 1.37 | 1.47
P003 | Logistics | SUP020 | 2025-08 | 2025-08-10 | 2814590.64 | 2000598 | -813992.64 | 813992.64 | 1 | 2025-08-28 | 4 | 3020475.01 | -205884.37 | DOWN | 0.0731 | 18 | Low | 1328685.67 | 0.44 | 3 | 671912.33 | 7 | 1.37 | 1.47
P003 | Logistics | SUP020 | 2025-08 | 2025-08-18 | 2619747.9 | 2000598 | -619149.9 | 619149.9 | 1 | 2025-08-28 | 5 | 2814590.64 | -194842.74 | DOWN | 0.0744 | 10 | Low | 1197436.87 | 0.455 | 5 | 803161.13 | 7 | 1.37 | 1.47
P003 | Logistics | SUP020 | 2025-09 | 2025-05-15 | 2856518.36 | 1288430 | -1568088.36 | 1568088.36 | 1 | 2025-09-28 | 1 |  |  |  |  | 136 | Low | 554776.02 | 0.191 | 3 | 733653.98 | 10 | 0.71 | 1.27
P003 | Logistics | SUP020 | 2025-09 | 2025-06-22 | 2515677.39 | 1288430 | -1227247.39 | 1227247.39 | 1 | 2025-09-28 | 2 | 2856518.36 | -340840.97 | DOWN | 0.1355 | 98 | Low | 704028.47 | 0.277 | 3 | 584401.53 | 10 | 0.71 | 1.27
P003 | Logistics | SUP020 | 2025-09 | 2025-07-03 | 2248842.97 | 1288430 | -960412.97 | 960412.97 | 1 | 2025-09-28 | 3 | 2515677.39 | -266834.42 | DOWN | 0.1187 | 87 | Low | 640793.77 | 0.302 | 4 | 647636.23 | 10 | 0.71 | 1.27
P003 | Logistics | SUP020 | 2025-09 | 2025-07-13 | 2003435.44 | 1288430 | -715005.44 | 715005.44 | 1 | 2025-09-28 | 4 | 2248842.97 | -245407.53 | DOWN | 0.1225 | 77 | Low | 643681.81 | 0.325 | 0 | 644748.19 | 10 | 0.71 | 1.27
P003 | Logistics | SUP020 | 2025-09 | 2025-07-16 | 1851379.2 | 1288430 | -562949.2 | 562949.2 | 1 | 2025-09-28 | 5 | 2003435.44 | -152056.24 | DOWN | 0.0821 | 74 | Low | 593492.18 | 0.332 | 0 | 694937.82 | 10 | 0.71 | 1.27
P003 | Logistics | SUP020 | 2025-09 | 2025-09-11 | 1672074.09 | 1288430 | -383644.09 | 383644.09 | 1 | 2025-09-28 | 6 | 1851379.2 | -179305.11 | DOWN | 0.1072 | 17 | Low | 793307.39 | 0.461 | 3 | 495122.61 | 10 | 0.71 | 1.27
P003 | Electronics | SUP020 | 2025-10 | 2025-09-10 | 2236102.03 | 1017625 | -1218477.03 | 1218477.03 | 1 | 2025-10-28 | 1 |  |  |  |  | 48 | Low | 881672.91 | 0.391 | 1 | 135952.09 | 19 | 0.95 | 0.98
P003 | Electronics | SUP020 | 2025-10 | 2025-09-21 | 1941627.1 | 1017625 | -924002.1 | 924002.1 | 1 | 2025-10-28 | 2 | 2236102.03 | -294474.93 | DOWN | 0.1517 | 37 | Low | 846507.83 | 0.416 | 5 | 171117.17 | 19 | 0.95 | 0.98
P003 | Electronics | SUP020 | 2025-10 | 2025-10-08 | 1728590.08 | 1017625 | -710965.08 | 710965.08 | 1 | 2025-10-28 | 3 | 1941627.1 | -213037.02 | DOWN | 0.1232 | 20 | Low | 839970.56 | 0.455 | 2 | 177654.44 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP020 | 2025-11 | 2025-06-22 | 2074336.71 | 1013026 | -1061310.71 | 1061310.71 | 1 | 2025-11-28 | 1 |  |  |  |  | 159 | Low | 258157.86 | 0.126 | 0 | 754868.14 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP020 | 2025-11 | 2025-07-18 | 1836421.61 | 1013026 | -823395.61 | 823395.61 | 1 | 2025-11-28 | 2 | 2074336.71 | -237915.1 | DOWN | 0.1296 | 133 | Low | 336070.54 | 0.179 | 0 | 676955.46 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP020 | 2025-11 | 2025-09-02 | 1631047.23 | 1013026 | -618021.23 | 618021.23 | 1 | 2025-11-28 | 3 | 1836421.61 | -205374.38 | DOWN | 0.1259 | 87 | Low | 440351.61 | 0.274 | 0 | 572674.39 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP020 | 2025-11 | 2025-10-03 | 1477163.54 | 1013026 | -464137.54 | 464137.54 | 1 | 2025-11-28 | 4 | 1631047.23 | -153883.69 | DOWN | 0.1042 | 56 | Low | 483589.64 | 0.338 | 1 | 529436.36 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP020 | 2025-11 | 2025-10-25 | 1343290.42 | 1013026 | -330264.42 | 330264.42 | 1 | 2025-11-28 | 5 | 1477163.54 | -133873.12 | DOWN | 0.0997 | 34 | Low | 544617.08 | 0.384 | 3 | 468408.92 | 11 | 1.85 | 1.52
P003 | Software | SUP020 | 2025-12 | 2025-08-07 | 226463.42 | 119046 | -107417.42 | 107417.42 | 1 | 2025-12-28 | 1 |  |  |  |  | 143 | Low | 39928.96 | 0.173 | 6 | 79117.04 | 10 | 1.08 | 1.22
P003 | Software | SUP020 | 2025-12 | 2025-08-19 | 203466.71 | 119046 | -84420.71 | 84420.71 | 1 | 2025-12-28 | 2 | 226463.42 | -22996.71 | DOWN | 0.113 | 131 | Low | 40990.75 | 0.2 | 5 | 78055.25 | 10 | 1.08 | 1.22
P003 | Software | SUP020 | 2025-12 | 2025-08-25 | 183985.16 | 119046 | -64939.16 | 64939.16 | 1 | 2025-12-28 | 3 | 203466.71 | -19481.55 | DOWN | 0.1059 | 125 | Low | 36281.78 | 0.214 | 1 | 82764.22 | 10 | 1.08 | 1.22
P003 | Software | SUP020 | 2025-12 | 2025-10-19 | 170995.73 | 119046 | -51949.73 | 51949.73 | 1 | 2025-12-28 | 4 | 183985.16 | -12989.43 | DOWN | 0.076 | 70 | Low | 53558.79 | 0.338 | 1 | 65487.21 | 10 | 1.08 | 1.22
P003 | Materials | SUP017 | 2025-01 | 2024-08-01 | 3317262.43 | 1732448 | -1584814.43 | 1584814.43 | 1 | 2025-01-28 | 1 |  |  |  |  | 180 | Low | 409978.86 | 0.118 | 3 | 1322469.14 | 17 | 1.86 | 1.34
P003 | Materials | SUP017 | 2025-01 | 2024-08-26 | 2571011.51 | 1732448 | -838563.51 | 838563.51 | 1 | 2025-01-28 | 2 | 3317262.43 | -746250.92 | DOWN | 0.2903 | 155 | Low | 468211.02 | 0.174 | 3 | 1264236.98 | 17 | 1.86 | 1.34
P003 | Materials | SUP017 | 2025-01 | 2024-08-31 | 2174406.21 | 1732448 | -441958.21 | 441958.21 | 1 | 2025-01-28 | 3 | 2571011.51 | -396605.3 | DOWN | 0.1824 | 150 | Low | 410734.42 | 0.187 | 1 | 1321713.58 | 17 | 1.86 | 1.34
P003 | Materials | SUP017 | 2025-01 | 2024-12-04 | 1969745.6 | 1732448 | -237297.6 | 237297.6 | 0 | 2025-01-28 | 4 | 2174406.21 | -204660.61 | DOWN | 0.1039 | 55 | Low | 898970.6 | 0.442 | 2 | 833477.4 | 17 | 1.86 | 1.34
P003 | Materials | SUP017 | 2025-01 | 2024-12-17 | 1833050.5 | 1732448 | -100602.5 | 100602.5 | 0 | 2025-01-28 | 5 | 1969745.6 | -136695.1 | DOWN | 0.0746 | 42 | Medium | 825375.34 | 0.477 | 3 | 907072.66 | 17 | 1.86 | 1.34
P003 | Materials | SUP017 | 2025-02 | 2024-10-28 | 1680173.45 | 859689 | -820484.45 | 820484.45 | 1 | 2025-02-28 | 1 |  |  |  |  | 123 | Low | 430034.6 | 0.253 | 1 | 429654.4 | 17 | 2.1 | 1.03
P003 | Materials | SUP017 | 2025-02 | 2024-11-24 | 1311653.63 | 859689 | -451964.63 | 451964.63 | 1 | 2025-02-28 | 2 | 1680173.45 | -368519.82 | DOWN | 0.281 | 96 | Low | 435909.36 | 0.324 | 1 | 423779.64 | 17 | 2.1 | 1.03
P003 | Materials | SUP017 | 2025-02 | 2024-11-28 | 1093992.09 | 859689 | -234303.09 | 234303.09 | 1 | 2025-02-28 | 3 | 1311653.63 | -217661.54 | DOWN | 0.199 | 92 | Low | 367732.26 | 0.334 | 1 | 491956.74 | 17 | 2.1 | 1.03
P003 | Materials | SUP017 | 2025-02 | 2024-12-02 | 958454.17 | 859689 | -98765.17 | 98765.17 | 0 | 2025-02-28 | 4 | 1093992.09 | -135537.92 | DOWN | 0.1414 | 88 | Low | 328803.72 | 0.345 | 1 | 530885.28 | 17 | 2.1 | 1.03
P003 | Logistics | SUP017 | 2025-03 | 2024-10-22 | 1932554.66 | 914640 | -1017914.66 | 1017914.66 | 1 | 2025-03-28 | 1 |  |  |  |  | 157 | Low | 327856.72 | 0.183 | 2 | 586783.28 | 13 | 1.13 | 1.73
P003 | Logistics | SUP017 | 2025-03 | 2025-02-11 | 1508750.75 | 914640 | -594110.75 | 594110.75 | 1 | 2025-03-28 | 2 | 1932554.66 | -423803.91 | DOWN | 0.2809 | 45 | Low | 791582.11 | 0.509 | 1 | 123057.89 | 13 | 1.13 | 1.73
P003 | Logistics | SUP017 | 2025-03 | 2025-02-17 | 1243699.47 | 914640 | -329059.47 | 329059.47 | 1 | 2025-03-28 | 3 | 1508750.75 | -265051.28 | DOWN | 0.2131 | 39 | Low | 626040.16 | 0.527 | 3 | 288599.84 | 13 | 1.13 | 1.73
P003 | Software | SUP017 | 2025-04 | 2024-10-31 | 2443145.24 | 1533383 | -909762.24 | 909762.24 | 1 | 2025-04-28 | 1 |  |  |  |  | 179 | Low | 313188.43 | 0.127 | 1 | 1220194.57 | 13 | 1.21 | 1.27
P003 | Software | SUP017 | 2025-04 | 2024-11-11 | 2016212.94 | 1533383 | -482829.94 | 482829.94 | 1 | 2025-04-28 | 2 | 2443145.24 | -426932.3 | DOWN | 0.2117 | 168 | Low | 294859.37 | 0.15 | 3 | 1238523.63 | 13 | 1.21 | 1.27
P003 | Software | SUP017 | 2025-04 | 2024-11-28 | 1791830.66 | 1533383 | -258447.66 | 258447.66 | 0 | 2025-04-28 | 3 | 2016212.94 | -224382.28 | DOWN | 0.1252 | 151 | Low | 334698.9 | 0.199 | 3 | 1198684.1 | 13 | 1.21 | 1.27
P003 | Software | SUP017 | 2025-04 | 2024-12-26 | 1670841.21 | 1533383 | -137458.21 | 137458.21 | 0 | 2025-04-28 | 4 | 1791830.66 | -120989.45 | DOWN | 0.0724 | 123 | Low | 461489.92 | 0.28 | 0 | 1071893.08 | 13 | 1.21 | 1.27
P003 | Software | SUP017 | 2025-04 | 2025-04-13 | 1612462.88 | 1533383 | -79079.88 | 79079.88 | 0 | 2025-04-28 | 5 | 1670841.21 | -58378.33 | DOWN | 0.0362 | 15 | Medium | 896813 | 0.591 | 3 | 636570 | 13 | 1.21 | 1.27
P003 | Software | SUP017 | 2025-04 | 2025-04-17 | 1585555.74 | 1533383 | -52172.74 | 52172.74 | 0 | 2025-04-28 | 6 | 1612462.88 | -26907.14 | DOWN | 0.017 | 11 | Medium | 897984.81 | 0.602 | 6 | 635398.19 | 13 | 1.21 | 1.27
P003 | Materials | SUP017 | 2025-05 | 2025-02-10 | 1391793.38 | 806017 | -585776.38 | 585776.38 | 1 | 2025-05-28 | 1 |  |  |  |  | 107 | Low | 450105.05 | 0.32 | 1 | 355911.95 | 14 | 1.36 | 1.73
P003 | Materials | SUP017 | 2025-05 | 2025-03-06 | 1144967.24 | 806017 | -338950.24 | 338950.24 | 1 | 2025-05-28 | 2 | 1391793.38 | -246826.14 | DOWN | 0.2156 | 83 | Low | 476833.13 | 0.388 | 7 | 329183.87 | 14 | 1.36 | 1.73
P003 | Materials | SUP017 | 2025-05 | 2025-04-23 | 998563.33 | 806017 | -192546.33 | 192546.33 | 1 | 2025-05-28 | 3 | 1144967.24 | -146403.91 | DOWN | 0.1466 | 35 | Low | 523900.07 | 0.524 | 4 | 282116.93 | 14 | 1.36 | 1.73
P003 | Materials | SUP017 | 2025-05 | 2025-05-13 | 905555.92 | 806017 | -99538.92 | 99538.92 | 0 | 2025-05-28 | 4 | 998563.33 | -93007.41 | DOWN | 0.1027 | 15 | Medium | 522344.73 | 0.581 | 4 | 283672.27 | 14 | 1.36 | 1.73
P003 | Mechanical | SUP017 | 2025-06 | 2025-01-10 | 970620.39 | 716353 | -254267.39 | 254267.39 | 1 | 2025-06-28 | 1 |  |  |  |  | 169 | Low | 147985.12 | 0.143 | 0 | 568367.88 | 22 | 1.47 | 1.51
P003 | Mechanical | SUP017 | 2025-06 | 2025-01-25 | 861745.08 | 716353 | -145392.08 | 145392.08 | 1 | 2025-06-28 | 2 | 970620.39 | -108875.31 | DOWN | 0.1263 | 154 | Low | 167174.61 | 0.185 | 0 | 549178.39 | 22 | 1.47 | 1.51
P003 | Mechanical | SUP017 | 2025-06 | 2025-02-07 | 789155.03 | 716353 | -72802.03 | 72802.03 | 0 | 2025-06-28 | 3 | 861745.08 | -72590.05 | DOWN | 0.092 | 141 | Low | 169155.86 | 0.221 | 0 | 547197.14 | 22 | 1.47 | 1.51
P003 | Mechanical | SUP017 | 2025-06 | 2025-04-17 | 763459.86 | 716353 | -47106.86 | 47106.86 | 0 | 2025-06-28 | 4 | 789155.03 | -25695.17 | DOWN | 0.0337 | 72 | Low | 319388.78 | 0.414 | 0 | 396964.22 | 22 | 1.47 | 1.51
P003 | Mechanical | SUP017 | 2025-06 | 2025-04-22 | 737467.67 | 716353 | -21114.67 | 21114.67 | 0 | 2025-06-28 | 5 | 763459.86 | -25992.19 | DOWN | 0.0352 | 67 | Low | 330909.7 | 0.428 | 0 | 385443.3 | 22 | 1.47 | 1.51
P003 | Mechanical | SUP017 | 2025-06 | 2025-05-13 | 732876.79 | 716353 | -16523.79 | 16523.79 | 0 | 2025-06-28 | 6 | 737467.67 | -4590.88 | DOWN | 0.0063 | 46 | Medium | 373546.53 | 0.487 | 1 | 342806.47 | 22 | 1.47 | 1.51
P003 | Mechanical | SUP017 | 2025-07 | 2025-02-15 | 2606771.85 | 1674846 | -931925.85 | 931925.85 | 1 | 2025-07-28 | 1 |  |  |  |  | 163 | Low | 471016.63 | 0.168 | 1 | 1203829.37 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP017 | 2025-07 | 2025-03-04 | 2190466.02 | 1674846 | -515620.02 | 515620.02 | 1 | 2025-07-28 | 2 | 2606771.85 | -416305.83 | DOWN | 0.1901 | 146 | Low | 452900.9 | 0.219 | 0 | 1221945.1 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP017 | 2025-07 | 2025-03-07 | 1965738.39 | 1674846 | -290892.39 | 290892.39 | 0 | 2025-07-28 | 3 | 2190466.02 | -224727.63 | DOWN | 0.1143 | 143 | Low | 432314.53 | 0.227 | 3 | 1242531.47 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP017 | 2025-07 | 2025-04-07 | 1834792.78 | 1674846 | -159946.78 | 159946.78 | 0 | 2025-07-28 | 4 | 1965738.39 | -130945.61 | DOWN | 0.0714 | 112 | Low | 550874.01 | 0.319 | 4 | 1123971.99 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP017 | 2025-07 | 2025-06-25 | 1769368.65 | 1674846 | -94522.65 | 94522.65 | 0 | 2025-07-28 | 5 | 1834792.78 | -65424.13 | DOWN | 0.037 | 33 | Medium | 1001547.84 | 0.552 | 3 | 673298.16 | 13 | 0.8 | 1.22
P003 | Services | SUP017 | 2025-08 | 2025-04-19 | 1138378.58 | 575572 | -562806.58 | 562806.58 | 1 | 2025-08-28 | 1 |  |  |  |  | 131 | Low | 303587.79 | 0.252 | 2 | 271984.21 | 7 | 1.37 | 1.47
P003 | Services | SUP017 | 2025-08 | 2025-04-21 | 866836.79 | 575572 | -291264.79 | 291264.79 | 1 | 2025-08-28 | 2 | 1138378.58 | -271541.79 | DOWN | 0.3133 | 129 | Low | 207202.13 | 0.257 | 6 | 368369.87 | 7 | 1.37 | 1.47
P003 | Services | SUP017 | 2025-08 | 2025-06-24 | 751357.6 | 575572 | -175785.6 | 175785.6 | 1 | 2025-08-28 | 3 | 866836.79 | -115479.19 | DOWN | 0.1537 | 65 | Low | 334154.09 | 0.438 | 0 | 241417.91 | 7 | 1.37 | 1.47
P003 | Services | SUP017 | 2025-08 | 2025-07-18 | 684341.56 | 575572 | -108769.56 | 108769.56 | 1 | 2025-08-28 | 4 | 751357.6 | -67016.04 | DOWN | 0.0979 | 41 | Medium | 355050.75 | 0.506 | 3 | 220521.25 | 7 | 1.37 | 1.47
P003 | Services | SUP017 | 2025-08 | 2025-07-18 | 641044.14 | 575572 | -65472.14 | 65472.14 | 0 | 2025-08-28 | 5 | 684341.56 | -43297.42 | DOWN | 0.0675 | 41 | Medium | 322322.21 | 0.506 | 3 | 253249.79 | 7 | 1.37 | 1.47
P003 | Software | SUP017 | 2025-09 | 2025-04-11 | 2170196.64 | 1192231 | -977965.64 | 977965.64 | 1 | 2025-09-28 | 1 |  |  |  |  | 170 | Low | 315020.06 | 0.148 | 4 | 877210.94 | 10 | 0.71 | 1.27
P003 | Software | SUP017 | 2025-09 | 2025-06-08 | 1753649.21 | 1192231 | -561418.21 | 561418.21 | 1 | 2025-09-28 | 2 | 2170196.64 | -416547.43 | DOWN | 0.2375 | 112 | Low | 533257.26 | 0.319 | 0 | 658973.74 | 10 | 0.71 | 1.27
P003 | Software | SUP017 | 2025-09 | 2025-06-09 | 1504169.6 | 1192231 | -311938.6 | 311938.6 | 1 | 2025-09-28 | 3 | 1753649.21 | -249479.61 | DOWN | 0.1659 | 111 | Low | 506027.37 | 0.322 | 2 | 686203.63 | 10 | 0.71 | 1.27
P003 | Software | SUP017 | 2025-09 | 2025-08-05 | 1373879.49 | 1192231 | -181648.49 | 181648.49 | 0 | 2025-09-28 | 4 | 1504169.6 | -130290.11 | DOWN | 0.0948 | 54 | Medium | 661406.53 | 0.49 | 3 | 530824.47 | 10 | 0.71 | 1.27
P003 | Software | SUP017 | 2025-09 | 2025-09-08 | 1293253.42 | 1192231 | -101022.42 | 101022.42 | 0 | 2025-09-28 | 5 | 1373879.49 | -80626.07 | DOWN | 0.0623 | 20 | Medium | 742745.08 | 0.591 | 3 | 449485.92 | 10 | 0.71 | 1.27
P003 | Software | SUP017 | 2025-10 | 2025-05-13 | 3056820.64 | 1775427 | -1281393.64 | 1281393.64 | 1 | 2025-10-28 | 1 |  |  |  |  | 168 | Low | 474948.2 | 0.154 | 2 | 1300478.8 | 19 | 0.95 | 0.98
P003 | Software | SUP017 | 2025-10 | 2025-07-06 | 2523069.2 | 1775427 | -747642.2 | 747642.2 | 1 | 2025-10-28 | 2 | 3056820.64 | -533751.44 | DOWN | 0.2115 | 114 | Low | 803492.83 | 0.313 | 1 | 971934.17 | 19 | 0.95 | 0.98
P003 | Software | SUP017 | 2025-10 | 2025-07-17 | 2150042.46 | 1775427 | -374615.46 | 374615.46 | 1 | 2025-10-28 | 3 | 2523069.2 | -373026.74 | DOWN | 0.1735 | 103 | Low | 714882.98 | 0.346 | 1 | 1060544.02 | 19 | 0.95 | 0.98
P003 | Software | SUP017 | 2025-10 | 2025-08-28 | 1974925.08 | 1775427 | -199498.08 | 199498.08 | 0 | 2025-10-28 | 4 | 2150042.46 | -175117.38 | DOWN | 0.0887 | 61 | Low | 952136.88 | 0.47 | 3 | 823290.12 | 19 | 0.95 | 0.98
P003 | Software | SUP017 | 2025-10 | 2025-10-10 | 1882036.49 | 1775427 | -106609.49 | 106609.49 | 0 | 2025-10-28 | 5 | 1974925.08 | -92888.59 | DOWN | 0.0494 | 18 | Medium | 1060945.08 | 0.597 | 4 | 714481.92 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP017 | 2025-11 | 2025-07-24 | 220442.74 | 142251 | -78191.74 | 78191.74 | 1 | 2025-11-28 | 1 |  |  |  |  | 127 | Low | 58695.28 | 0.249 | 4 | 83555.72 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP017 | 2025-11 | 2025-08-27 | 181857.68 | 142251 | -39606.68 | 39606.68 | 1 | 2025-11-28 | 2 | 220442.74 | -38585.06 | DOWN | 0.2122 | 93 | Low | 64732.27 | 0.34 | 4 | 77518.73 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP017 | 2025-11 | 2025-09-05 | 164620.17 | 142251 | -22369.17 | 22369.17 | 0 | 2025-11-28 | 3 | 181857.68 | -17237.51 | DOWN | 0.1047 | 84 | Low | 59992.13 | 0.365 | 3 | 82258.87 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP017 | 2025-11 | 2025-11-03 | 152860.9 | 142251 | -10609.9 | 10609.9 | 0 | 2025-11-28 | 4 | 164620.17 | -11759.27 | DOWN | 0.0769 | 25 | Medium | 81591.61 | 0.523 | 4 | 60659.39 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP017 | 2025-11 | 2025-11-07 | 145480.93 | 142251 | -3229.93 | 3229.93 | 0 | 2025-11-28 | 5 | 152860.9 | -7379.97 | DOWN | 0.0507 | 21 | Medium | 75169.97 | 0.534 | 6 | 67081.03 | 11 | 1.85 | 1.52
P003 | Materials | SUP017 | 2025-12 | 2025-07-05 | 4140736.03 | 2412243 | -1728493.03 | 1728493.03 | 1 | 2025-12-28 | 1 |  |  |  |  | 176 | Low | 530971.95 | 0.129 | 0 | 1881271.05 | 10 | 1.08 | 1.22
P003 | Materials | SUP017 | 2025-12 | 2025-07-20 | 3387207.71 | 2412243 | -974964.71 | 974964.71 | 1 | 2025-12-28 | 2 | 4140736.03 | -753528.32 | DOWN | 0.2225 | 161 | Low | 554276.96 | 0.173 | 3 | 1857966.04 | 10 | 1.08 | 1.22
P003 | Materials | SUP017 | 2025-12 | 2025-08-24 | 2963113 | 2412243 | -550870 | 550870 | 1 | 2025-12-28 | 3 | 3387207.71 | -424094.71 | DOWN | 0.1431 | 126 | Low | 773969.39 | 0.275 | 4 | 1638273.61 | 10 | 1.08 | 1.22
P003 | Materials | SUP017 | 2025-12 | 2025-11-08 | 2729732.32 | 2412243 | -317489.32 | 317489.32 | 0 | 2025-12-28 | 4 | 2963113 | -233380.68 | DOWN | 0.0855 | 50 | Medium | 1366966.28 | 0.497 | 6 | 1045276.72 | 10 | 1.08 | 1.22
P003 | Materials | SUP017 | 2025-12 | 2025-11-08 | 2603241.9 | 2412243 | -190998.9 | 190998.9 | 0 | 2025-12-28 | 5 | 2729732.32 | -126490.42 | DOWN | 0.0486 | 50 | Medium | 1360082.19 | 0.497 | 1 | 1052160.81 | 10 | 1.08 | 1.22
P003 | Materials | SUP006 | 2025-01 | 2024-10-02 | 722119.36 | 414884 | -307235.36 | 307235.36 | 1 | 2025-01-28 | 1 |  |  |  |  | 118 | Low | 160244.74 | 0.231 | 2 | 254639.26 | 17 | 1.86 | 1.34
P003 | Materials | SUP006 | 2025-01 | 2024-10-20 | 597837.94 | 414884 | -182953.94 | 182953.94 | 1 | 2025-01-28 | 2 | 722119.36 | -124281.42 | DOWN | 0.2079 | 100 | Low | 171195.71 | 0.272 | 2 | 243688.29 | 17 | 1.86 | 1.34
P003 | Materials | SUP006 | 2025-01 | 2024-10-26 | 528290.72 | 414884 | -113406.72 | 113406.72 | 1 | 2025-01-28 | 3 | 597837.94 | -69547.22 | DOWN | 0.1316 | 94 | Low | 147503.41 | 0.286 | 1 | 267380.59 | 17 | 1.86 | 1.34
P003 | Materials | SUP006 | 2025-01 | 2024-12-01 | 486054.94 | 414884 | -71170.94 | 71170.94 | 0 | 2025-01-28 | 4 | 528290.72 | -42235.78 | DOWN | 0.0869 | 58 | Low | 181931.97 | 0.367 | 2 | 232952.03 | 17 | 1.86 | 1.34
P003 | Materials | SUP006 | 2025-01 | 2024-12-18 | 463829.37 | 414884 | -48945.37 | 48945.37 | 0 | 2025-01-28 | 5 | 486054.94 | -22225.57 | DOWN | 0.0479 | 41 | Low | 197144.05 | 0.406 | 1 | 217739.95 | 17 | 1.86 | 1.34
P003 | Logistics | SUP006 | 2025-02 | 2024-10-18 | 2824283.36 | 1599645 | -1224638.36 | 1224638.36 | 1 | 2025-02-28 | 1 |  |  |  |  | 133 | Low | 510856.31 | 0.192 | 2 | 1088788.69 | 17 | 2.1 | 1.03
P003 | Logistics | SUP006 | 2025-02 | 2025-01-07 | 2441819.93 | 1599645 | -842174.93 | 842174.93 | 1 | 2025-02-28 | 2 | 2824283.36 | -382463.43 | DOWN | 0.1566 | 52 | Low | 967192.86 | 0.371 | 4 | 632452.14 | 17 | 2.1 | 1.03
P003 | Logistics | SUP006 | 2025-02 | 2025-01-31 | 2032733.24 | 1599645 | -433088.24 | 433088.24 | 1 | 2025-02-28 | 3 | 2441819.93 | -409086.69 | DOWN | 0.2012 | 28 | Low | 856710.68 | 0.424 | 2 | 742934.32 | 17 | 2.1 | 1.03
P003 | Electronics | SUP006 | 2025-03 | 2024-10-13 | 3591593.88 | 2558576 | -1033017.88 | 1033017.88 | 1 | 2025-03-28 | 1 |  |  |  |  | 166 | Low | 441032.15 | 0.133 | 1 | 2117543.85 | 13 | 1.13 | 1.73
P003 | Electronics | SUP006 | 2025-03 | 2025-01-10 | 3138391.17 | 2558576 | -579815.17 | 579815.17 | 1 | 2025-03-28 | 2 | 3591593.88 | -453202.71 | DOWN | 0.1444 | 77 | Low | 1127937.54 | 0.352 | 2 | 1430638.46 | 13 | 1.13 | 1.73
P003 | Electronics | SUP006 | 2025-03 | 2025-02-02 | 2927257.6 | 2558576 | -368681.6 | 368681.6 | 0 | 2025-03-28 | 3 | 3138391.17 | -211133.57 | DOWN | 0.0721 | 54 | Low | 1155724.44 | 0.409 | 0 | 1402851.56 | 13 | 1.13 | 1.73
P003 | Electronics | SUP006 | 2025-03 | 2025-02-10 | 2761978.9 | 2558576 | -203402.9 | 203402.9 | 0 | 2025-03-28 | 4 | 2927257.6 | -165278.7 | DOWN | 0.0598 | 46 | Low | 1098912.51 | 0.428 | 5 | 1459663.49 | 13 | 1.13 | 1.73
P003 | Electronics | SUP006 | 2025-03 | 2025-02-27 | 2699505.45 | 2558576 | -140929.45 | 140929.45 | 0 | 2025-03-28 | 5 | 2761978.9 | -62473.45 | DOWN | 0.0231 | 29 | Medium | 1181634.67 | 0.47 | 2 | 1376941.33 | 13 | 1.13 | 1.73
P003 | Software | SUP006 | 2025-04 | 2025-01-13 | 3413505.71 | 2006943 | -1406562.71 | 1406562.71 | 1 | 2025-04-28 | 1 |  |  |  |  | 105 | Low | 915160.54 | 0.28 | 4 | 1091782.46 | 13 | 1.21 | 1.27
P003 | Software | SUP006 | 2025-04 | 2025-01-29 | 2809244.12 | 2006943 | -802301.12 | 802301.12 | 1 | 2025-04-28 | 2 | 3413505.71 | -604261.59 | DOWN | 0.2151 | 89 | Low | 872229.17 | 0.319 | 1 | 1134713.83 | 13 | 1.21 | 1.27
P003 | Software | SUP006 | 2025-04 | 2025-02-15 | 2492635.38 | 2006943 | -485692.38 | 485692.38 | 1 | 2025-04-28 | 3 | 2809244.12 | -316608.74 | DOWN | 0.127 | 72 | Low | 970591.75 | 0.361 | 4 | 1036351.25 | 13 | 1.21 | 1.27
P003 | Software | SUP006 | 2025-04 | 2025-03-05 | 2263702.29 | 2006943 | -256759.29 | 256759.29 | 0 | 2025-04-28 | 4 | 2492635.38 | -228933.09 | DOWN | 0.1011 | 54 | Low | 951768.15 | 0.405 | 2 | 1055174.85 | 13 | 1.21 | 1.27
P003 | Software | SUP006 | 2025-04 | 2025-03-23 | 2160779.44 | 2006943 | -153836.44 | 153836.44 | 0 | 2025-04-28 | 5 | 2263702.29 | -102922.85 | DOWN | 0.0476 | 36 | Low | 998399.22 | 0.449 | 2 | 1008543.78 | 13 | 1.21 | 1.27
P003 | Software | SUP006 | 2025-04 | 2025-04-01 | 2139274.14 | 2006943 | -132331.14 | 132331.14 | 0 | 2025-04-28 | 6 | 2160779.44 | -21505.3 | DOWN | 0.0101 | 27 | Medium | 1029989.66 | 0.471 | 4 | 976953.34 | 13 | 1.21 | 1.27
P003 | Services | SUP006 | 2025-05 | 2025-01-13 | 2507707.24 | 1657921 | -849786.24 | 849786.24 | 1 | 2025-05-28 | 1 |  |  |  |  | 135 | Low | 493710.35 | 0.204 | 0 | 1164210.65 | 14 | 1.36 | 1.73
P003 | Services | SUP006 | 2025-05 | 2025-03-21 | 2144127.08 | 1657921 | -486206.08 | 486206.08 | 1 | 2025-05-28 | 2 | 2507707.24 | -363580.16 | DOWN | 0.1696 | 68 | Low | 747161.19 | 0.364 | 0 | 910759.81 | 14 | 1.36 | 1.73
P003 | Services | SUP006 | 2025-05 | 2025-04-30 | 1936737.6 | 1657921 | -278816.6 | 278816.6 | 0 | 2025-05-28 | 3 | 2144127.08 | -207389.48 | DOWN | 0.1071 | 28 | Medium | 881804.94 | 0.46 | 4 | 776116.06 | 14 | 1.36 | 1.73
P003 | Electronics | SUP006 | 2025-06 | 2025-01-11 | 3840887.47 | 2584403 | -1256484.47 | 1256484.47 | 1 | 2025-06-28 | 1 |  |  |  |  | 168 | Low | 496935.62 | 0.123 | 0 | 2087467.38 | 22 | 1.47 | 1.51
P003 | Electronics | SUP006 | 2025-06 | 2025-02-13 | 3302666.82 | 2584403 | -718263.82 | 718263.82 | 1 | 2025-06-28 | 2 | 3840887.47 | -538220.65 | DOWN | 0.163 | 135 | Low | 625544.83 | 0.201 | 0 | 1958858.17 | 22 | 1.47 | 1.51
P003 | Electronics | SUP006 | 2025-06 | 2025-02-17 | 2983561.04 | 2584403 | -399158.04 | 399158.04 | 0 | 2025-06-28 | 3 | 3302666.82 | -319105.78 | DOWN | 0.107 | 131 | Low | 640177.93 | 0.211 | 0 | 1944225.07 | 22 | 1.47 | 1.51
P003 | Electronics | SUP006 | 2025-06 | 2025-03-05 | 2847530.98 | 2584403 | -263127.98 | 263127.98 | 0 | 2025-06-28 | 4 | 2983561.04 | -136030.06 | DOWN | 0.0478 | 115 | Low | 681048.68 | 0.248 | 0 | 1903354.32 | 22 | 1.47 | 1.51
P003 | Electronics | SUP006 | 2025-06 | 2025-05-14 | 2781483.65 | 2584403 | -197080.65 | 197080.65 | 0 | 2025-06-28 | 5 | 2847530.98 | -66047.33 | DOWN | 0.0237 | 45 | Low | 1106237.05 | 0.414 | 3 | 1478165.95 | 22 | 1.47 | 1.51
P003 | Electronics | SUP006 | 2025-06 | 2025-05-25 | 2721614.85 | 2584403 | -137211.85 | 137211.85 | 0 | 2025-06-28 | 6 | 2781483.65 | -59868.8 | DOWN | 0.022 | 34 | Low | 1166570.68 | 0.44 | 5 | 1417832.32 | 22 | 1.47 | 1.51
P003 | Logistics | SUP006 | 2025-07 | 2025-03-07 | 1297457.38 | 704594 | -592863.38 | 592863.38 | 1 | 2025-07-28 | 1 |  |  |  |  | 143 | Low | 257022.58 | 0.193 | 0 | 447571.42 | 13 | 0.8 | 1.22
P003 | Logistics | SUP006 | 2025-07 | 2025-05-09 | 1061549.56 | 704594 | -356955.56 | 356955.56 | 1 | 2025-07-28 | 2 | 1297457.38 | -235907.82 | DOWN | 0.2222 | 80 | Low | 344997.84 | 0.35 | 3 | 359596.16 | 13 | 0.8 | 1.22
P003 | Logistics | SUP006 | 2025-07 | 2025-05-18 | 919417.8 | 704594 | -214823.8 | 214823.8 | 1 | 2025-07-28 | 3 | 1061549.56 | -142131.76 | DOWN | 0.1546 | 71 | Low | 352271.13 | 0.372 | 7 | 352322.87 | 13 | 0.8 | 1.22
P003 | Logistics | SUP006 | 2025-07 | 2025-06-23 | 816469.93 | 704594 | -111875.93 | 111875.93 | 0 | 2025-07-28 | 4 | 919417.8 | -102947.87 | DOWN | 0.1261 | 35 | Low | 378655.95 | 0.463 | 6 | 325938.05 | 13 | 0.8 | 1.22
P003 | Mechanical | SUP006 | 2025-08 | 2025-05-12 | 2647529.98 | 2113019 | -534510.98 | 534510.98 | 1 | 2025-08-28 | 1 |  |  |  |  | 108 | Low | 754820.85 | 0.268 | 0 | 1358198.15 | 7 | 1.37 | 1.47
P003 | Mechanical | SUP006 | 2025-08 | 2025-06-06 | 2419778.87 | 2113019 | -306759.87 | 306759.87 | 0 | 2025-08-28 | 2 | 2647529.98 | -227751.11 | DOWN | 0.0941 | 83 | Low | 837979.31 | 0.328 | 3 | 1275039.69 | 7 | 1.37 | 1.47
P003 | Mechanical | SUP006 | 2025-08 | 2025-06-07 | 2281304.72 | 2113019 | -168285.72 | 168285.72 | 0 | 2025-08-28 | 3 | 2419778.87 | -138474.15 | DOWN | 0.0607 | 82 | Low | 800554.62 | 0.33 | 1 | 1312464.38 | 7 | 1.37 | 1.47
P003 | Mechanical | SUP006 | 2025-08 | 2025-06-16 | 2194881.76 | 2113019 | -81862.76 | 81862.76 | 0 | 2025-08-28 | 4 | 2281304.72 | -86422.96 | DOWN | 0.0394 | 73 | Low | 798888.03 | 0.352 | 1 | 1314130.97 | 7 | 1.37 | 1.47
P003 | Electronics | SUP006 | 2025-09 | 2025-05-19 | 2976514.53 | 1597006 | -1379508.53 | 1379508.53 | 1 | 2025-09-28 | 1 |  |  |  |  | 132 | Low | 648444.76 | 0.22 | 4 | 948561.24 | 10 | 0.71 | 1.27
P003 | Electronics | SUP006 | 2025-09 | 2025-05-19 | 2456650.51 | 1597006 | -859644.51 | 859644.51 | 1 | 2025-09-28 | 2 | 2976514.53 | -519864.02 | DOWN | 0.2116 | 132 | Low | 526812.43 | 0.22 | 0 | 1070193.57 | 10 | 0.71 | 1.27
P003 | Electronics | SUP006 | 2025-09 | 2025-05-31 | 2140529.14 | 1597006 | -543523.14 | 543523.14 | 1 | 2025-09-28 | 3 | 2456650.51 | -316121.37 | DOWN | 0.1477 | 120 | Low | 562804.11 | 0.25 | 4 | 1034201.89 | 10 | 0.71 | 1.27
P003 | Electronics | SUP006 | 2025-09 | 2025-07-11 | 1903792.42 | 1597006 | -306786.42 | 306786.42 | 1 | 2025-09-28 | 4 | 2140529.14 | -236736.72 | DOWN | 0.1244 | 79 | Low | 639387.9 | 0.353 | 10 | 957618.1 | 10 | 0.71 | 1.27
P003 | Electronics | SUP006 | 2025-09 | 2025-07-15 | 1802283.62 | 1597006 | -205277.62 | 205277.62 | 0 | 2025-09-28 | 5 | 1903792.42 | -101508.8 | DOWN | 0.0563 | 75 | Low | 660416.28 | 0.363 | 1 | 936589.72 | 10 | 0.71 | 1.27
P003 | Electronics | SUP006 | 2025-09 | 2025-09-08 | 1706642.87 | 1597006 | -109636.87 | 109636.87 | 0 | 2025-09-28 | 6 | 1802283.62 | -95640.75 | DOWN | 0.056 | 20 | Medium | 813266.38 | 0.5 | 2 | 783739.62 | 10 | 0.71 | 1.27
P003 | Services | SUP006 | 2025-10 | 2025-07-05 | 1881472.04 | 1041941 | -839531.04 | 839531.04 | 1 | 2025-10-28 | 1 |  |  |  |  | 115 | Low | 519863.28 | 0.263 | 3 | 522077.72 | 19 | 0.95 | 0.98
P003 | Services | SUP006 | 2025-10 | 2025-07-25 | 1520797.64 | 1041941 | -478856.64 | 478856.64 | 1 | 2025-10-28 | 2 | 1881472.04 | -360674.4 | DOWN | 0.2372 | 95 | Low | 465143.93 | 0.312 | 3 | 576797.07 | 19 | 0.95 | 0.98
P003 | Services | SUP006 | 2025-10 | 2025-09-03 | 1349712.76 | 1041941 | -307771.76 | 307771.76 | 1 | 2025-10-28 | 3 | 1520797.64 | -171084.88 | DOWN | 0.1268 | 55 | Low | 576777.67 | 0.413 | 1 | 465163.33 | 19 | 0.95 | 0.98
P003 | Services | SUP006 | 2025-10 | 2025-09-25 | 1229976.15 | 1041941 | -188035.15 | 188035.15 | 1 | 2025-10-28 | 4 | 1349712.76 | -119736.61 | DOWN | 0.0973 | 33 | Medium | 594816.05 | 0.468 | 1 | 447124.95 | 19 | 0.95 | 0.98
P003 | Services | SUP006 | 2025-10 | 2025-09-28 | 1156645.82 | 1041941 | -114704.82 | 114704.82 | 0 | 2025-10-28 | 5 | 1229976.15 | -73330.33 | DOWN | 0.0634 | 30 | Medium | 591166 | 0.475 | 4 | 450775 | 19 | 0.95 | 0.98
P003 | Services | SUP006 | 2025-10 | 2025-10-16 | 1094968.01 | 1041941 | -53027.01 | 53027.01 | 0 | 2025-10-28 | 6 | 1156645.82 | -61677.81 | DOWN | 0.0563 | 12 | Medium | 582277.97 | 0.52 | 3 | 459663.03 | 19 | 0.95 | 0.98
P003 | Mechanical | SUP006 | 2025-11 | 2025-07-12 | 2507523.23 | 1700850 | -806673.23 | 806673.23 | 1 | 2025-11-28 | 1 |  |  |  |  | 139 | Low | 486037.34 | 0.184 | 4 | 1214812.66 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP006 | 2025-11 | 2025-08-15 | 2216720.31 | 1700850 | -515870.31 | 515870.31 | 1 | 2025-11-28 | 2 | 2507523.23 | -290802.92 | DOWN | 0.1312 | 105 | Low | 573024.82 | 0.261 | 4 | 1127825.18 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP006 | 2025-11 | 2025-10-16 | 1966830.05 | 1700850 | -265980.05 | 265980.05 | 0 | 2025-11-28 | 3 | 2216720.31 | -249890.26 | DOWN | 0.1271 | 43 | Low | 737184.26 | 0.402 | 4 | 963665.74 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP006 | 2025-11 | 2025-10-29 | 1843597.39 | 1700850 | -142747.39 | 142747.39 | 0 | 2025-11-28 | 4 | 1966830.05 | -123232.66 | DOWN | 0.0668 | 30 | Low | 753528.15 | 0.431 | 2 | 947321.85 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP006 | 2025-11 | 2025-11-04 | 1801383.24 | 1700850 | -100533.24 | 100533.24 | 0 | 2025-11-28 | 5 | 1843597.39 | -42214.15 | DOWN | 0.0234 | 24 | Low | 816021.71 | 0.445 | 3 | 884828.29 | 11 | 1.85 | 1.52
P003 | Mechanical | SUP006 | 2025-11 | 2025-11-18 | 1788602.15 | 1700850 | -87752.15 | 87752.15 | 0 | 2025-11-28 | 6 | 1801383.24 | -12781.09 | DOWN | 0.0071 | 10 | Medium | 851561.9 | 0.474 | 2 | 849288.1 | 11 | 1.85 | 1.52
P003 | Materials | SUP006 | 2025-12 | 2025-08-21 | 1396217.97 | 831623 | -564594.97 | 564594.97 | 1 | 2025-12-28 | 1 |  |  |  |  | 129 | Low | 334963.9 | 0.225 | 2 | 496659.1 | 10 | 1.08 | 1.22
P003 | Materials | SUP006 | 2025-12 | 2025-09-26 | 1179261.15 | 831623 | -347638.15 | 347638.15 | 1 | 2025-12-28 | 2 | 1396217.97 | -216956.82 | DOWN | 0.184 | 93 | Low | 391216.22 | 0.314 | 0 | 440406.78 | 10 | 1.08 | 1.22
P003 | Materials | SUP006 | 2025-12 | 2025-10-12 | 1051138.2 | 831623 | -219515.2 | 219515.2 | 1 | 2025-12-28 | 3 | 1179261.15 | -128122.95 | DOWN | 0.1219 | 77 | Low | 396958.49 | 0.354 | 1 | 434664.51 | 10 | 1.08 | 1.22
P003 | Materials | SUP006 | 2025-12 | 2025-11-15 | 954583.82 | 831623 | -122960.82 | 122960.82 | 0 | 2025-12-28 | 4 | 1051138.2 | -96554.38 | DOWN | 0.1011 | 43 | Low | 427575.83 | 0.438 | 0 | 404047.17 | 10 | 1.08 | 1.22
P003 | Materials | SUP006 | 2025-12 | 2025-11-30 | 913309.74 | 831623 | -81686.74 | 81686.74 | 0 | 2025-12-28 | 5 | 954583.82 | -41274.08 | DOWN | 0.0452 | 28 | Medium | 420716.4 | 0.475 | 5 | 410906.6 | 10 | 1.08 | 1.22
P003 | Mechanical | SUP001 | 2025-01 | 2024-10-07 | 2228428.65 | 1578098 | -650330.65 | 650330.65 | 1 | 2025-01-28 | 1 |  |  |  |  | 113 | Low | 824982.29 | 0.344 | 2 | 753115.71 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP001 | 2025-01 | 2024-10-08 | 1864856.42 | 1578098 | -286758.42 | 286758.42 | 1 | 2025-01-28 | 2 | 2228428.65 | -363572.23 | DOWN | 0.195 | 112 | Low | 606971.51 | 0.347 | 3 | 971126.49 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP001 | 2025-01 | 2024-11-30 | 1713593.47 | 1578098 | -135495.47 | 135495.47 | 0 | 2025-01-28 | 3 | 1864856.42 | -151262.95 | DOWN | 0.0883 | 59 | Medium | 876575.59 | 0.517 | 6 | 701522.41 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP001 | 2025-01 | 2024-12-02 | 1635536.75 | 1578098 | -57438.75 | 57438.75 | 0 | 2025-01-28 | 4 | 1713593.47 | -78056.72 | DOWN | 0.0477 | 57 | Medium | 924460.69 | 0.524 | 3 | 653637.31 | 17 | 1.86 | 1.34
P003 | Mechanical | SUP001 | 2025-01 | 2024-12-26 | 1628239.48 | 1578098 | -50141.48 | 50141.48 | 0 | 2025-01-28 | 5 | 1635536.75 | -7297.27 | DOWN | 0.0045 | 33 | Medium | 1024011.86 | 0.601 | 6 | 554086.14 | 17 | 1.86 | 1.34
P003 | Electronics | SUP001 | 2025-02 | 2024-09-15 | 1450711.04 | 1045532 | -405179.04 | 405179.04 | 1 | 2025-02-28 | 1 |  |  |  |  | 166 | Low | 226140.1 | 0.169 | 1 | 819391.9 | 17 | 2.1 | 1.03
P003 | Electronics | SUP001 | 2025-02 | 2024-09-25 | 1245141.11 | 1045532 | -199609.11 | 199609.11 | 1 | 2025-02-28 | 2 | 1450711.04 | -205569.93 | DOWN | 0.1651 | 156 | Low | 263775.8 | 0.2 | 0 | 781756.2 | 17 | 2.1 | 1.03
P003 | Electronics | SUP001 | 2025-02 | 2024-11-11 | 1110814.12 | 1045532 | -65282.12 | 65282.12 | 0 | 2025-02-28 | 3 | 1245141.11 | -134326.99 | DOWN | 0.1209 | 109 | Low | 405363.4 | 0.348 | 0 | 640168.6 | 17 | 2.1 | 1.03
P003 | Electronics | SUP001 | 2025-02 | 2024-11-12 | 1096067.53 | 1045532 | -50535.53 | 50535.53 | 0 | 2025-02-28 | 4 | 1110814.12 | -14746.59 | DOWN | 0.0135 | 108 | Low | 363271.98 | 0.351 | 2 | 682260.02 | 17 | 2.1 | 1.03
P003 | Electronics | SUP001 | 2025-02 | 2024-11-15 | 1055463.08 | 1045532 | -9931.08 | 9931.08 | 0 | 2025-02-28 | 5 | 1096067.53 | -40604.45 | DOWN | 0.0385 | 105 | Low | 367910.35 | 0.36 | 8 | 677621.65 | 17 | 2.1 | 1.03
P003 | Software | SUP001 | 2025-03 | 2025-01-09 | 1064575.3 | 682406 | -382169.3 | 382169.3 | 1 | 2025-03-28 | 1 |  |  |  |  | 78 | Low | 535589.44 | 0.496 | 7 | 146816.56 | 13 | 1.13 | 1.73
P003 | Software | SUP001 | 2025-03 | 2025-01-12 | 848708.65 | 682406 | -166302.65 | 166302.65 | 1 | 2025-03-28 | 2 | 1064575.3 | -215866.65 | DOWN | 0.2543 | 75 | Low | 437898.04 | 0.506 | 3 | 244507.96 | 13 | 1.13 | 1.73
P003 | Software | SUP001 | 2025-03 | 2025-03-05 | 771016.7 | 682406 | -88610.7 | 88610.7 | 0 | 2025-03-28 | 3 | 848708.65 | -77691.95 | DOWN | 0.1008 | 23 | Medium | 560272.84 | 0.688 | 7 | 122133.16 | 13 | 1.13 | 1.73
P003 | Software | SUP001 | 2025-03 | 2025-03-09 | 719411.12 | 682406 | -37005.12 | 37005.12 | 0 | 2025-03-28 | 4 | 771016.7 | -51605.58 | DOWN | 0.0717 | 19 | Medium | 520522.36 | 0.702 | 7 | 161883.64 | 13 | 1.13 | 1.73
P003 | Services | SUP001 | 2025-04 | 2024-11-02 | 3591422.41 | 2331652 | -1259770.41 | 1259770.41 | 1 | 2025-04-28 | 1 |  |  |  |  | 177 | Low | 534077.33 | 0.152 | 0 | 1797574.67 | 13 | 1.21 | 1.27
P003 | Services | SUP001 | 2025-04 | 2024-11-05 | 2929032.03 | 2331652 | -597380.03 | 597380.03 | 1 | 2025-04-28 | 2 | 3591422.41 | -662390.38 | DOWN | 0.2261 | 174 | Low | 454516.1 | 0.159 | 1 | 1877135.9 | 13 | 1.21 | 1.27
P003 | Services | SUP001 | 2025-04 | 2024-12-11 | 2599454.57 | 2331652 | -267802.57 | 267802.57 | 0 | 2025-04-28 | 3 | 2929032.03 | -329577.46 | DOWN | 0.1268 | 138 | Low | 717843.49 | 0.284 | 0 | 1613808.51 | 13 | 1.21 | 1.27
P003 | Services | SUP001 | 2025-04 | 2025-02-06 | 2498088.03 | 2331652 | -166436.03 | 166436.03 | 0 | 2025-04-28 | 4 | 2599454.57 | -101366.54 | DOWN | 0.0406 | 81 | Low | 1262824.31 | 0.481 | 4 | 1068827.69 | 13 | 1.21 | 1.27
P003 | Services | SUP001 | 2025-05 | 2024-12-03 | 1519593.73 | 947000 | -572593.73 | 572593.73 | 1 | 2025-05-28 | 1 |  |  |  |  | 176 | Low | 213516.8 | 0.15 | 0 | 733483.2 | 14 | 1.36 | 1.73
P003 | Services | SUP001 | 2025-05 | 2024-12-08 | 1224756.81 | 947000 | -277756.81 | 277756.81 | 1 | 2025-05-28 | 2 | 1519593.73 | -294836.92 | DOWN | 0.2407 | 171 | Low | 193122.98 | 0.167 | 0 | 753877.02 | 14 | 1.36 | 1.73
P003 | Services | SUP001 | 2025-05 | 2024-12-14 | 1095580.05 | 947000 | -148580.05 | 148580.05 | 0 | 2025-05-28 | 3 | 1224756.81 | -129176.76 | DOWN | 0.1179 | 165 | Low | 199747.41 | 0.187 | 0 | 747252.59 | 14 | 1.36 | 1.73
P003 | Services | SUP001 | 2025-05 | 2025-02-18 | 1031268.2 | 947000 | -84268.2 | 84268.2 | 0 | 2025-05-28 | 4 | 1095580.05 | -64311.85 | DOWN | 0.0624 | 99 | Low | 430466.64 | 0.411 | 3 | 516533.36 | 14 | 1.36 | 1.73
P003 | Services | SUP001 | 2025-05 | 2025-03-27 | 986704.93 | 947000 | -39704.93 | 39704.93 | 0 | 2025-05-28 | 5 | 1031268.2 | -44563.27 | DOWN | 0.0452 | 62 | Low | 498939.93 | 0.537 | 7 | 448060.07 | 14 | 1.36 | 1.73
P003 | Materials | SUP001 | 2025-06 | 2025-02-08 | 165021.58 | 112491 | -52530.58 | 52530.58 | 1 | 2025-06-28 | 1 |  |  |  |  | 140 | Low | 44753.77 | 0.268 | 0 | 67737.23 | 22 | 1.47 | 1.51
P003 | Materials | SUP001 | 2025-06 | 2025-02-25 | 138527.23 | 112491 | -26036.23 | 26036.23 | 1 | 2025-06-28 | 2 | 165021.58 | -26494.35 | DOWN | 0.1913 | 123 | Low | 46235.6 | 0.326 | 5 | 66255.4 | 22 | 1.47 | 1.51
P003 | Materials | SUP001 | 2025-06 | 2025-04-24 | 126036.38 | 112491 | -13545.38 | 13545.38 | 0 | 2025-06-28 | 3 | 138527.23 | -12490.85 | DOWN | 0.0991 | 65 | Low | 69636.06 | 0.52 | 5 | 42854.94 | 22 | 1.47 | 1.51
P003 | Materials | SUP001 | 2025-06 | 2025-05-24 | 118201.56 | 112491 | -5710.56 | 5710.56 | 0 | 2025-06-28 | 4 | 126036.38 | -7834.82 | DOWN | 0.0663 | 35 | Medium | 72535.58 | 0.621 | 4 | 39955.42 | 22 | 1.47 | 1.51
P003 | Materials | SUP001 | 2025-06 | 2025-06-01 | 113227.24 | 112491 | -736.24 | 736.24 | 0 | 2025-06-28 | 5 | 118201.56 | -4974.32 | DOWN | 0.0439 | 27 | Medium | 67869.05 | 0.648 | 6 | 44621.95 | 22 | 1.47 | 1.51
P003 | Materials | SUP001 | 2025-07 | 2025-04-04 | 1126825.55 | 783034 | -343791.55 | 343791.55 | 1 | 2025-07-28 | 1 |  |  |  |  | 115 | Low | 411642.26 | 0.372 | 2 | 371391.74 | 13 | 0.8 | 1.22
P003 | Materials | SUP001 | 2025-07 | 2025-04-07 | 929419.97 | 783034 | -146385.97 | 146385.97 | 1 | 2025-07-28 | 2 | 1126825.55 | -197405.58 | DOWN | 0.2124 | 112 | Low | 358803.71 | 0.383 | 0 | 424230.29 | 13 | 0.8 | 1.22
P003 | Materials | SUP001 | 2025-07 | 2025-05-19 | 854108.16 | 783034 | -71074.16 | 71074.16 | 0 | 2025-07-28 | 3 | 929419.97 | -75311.81 | DOWN | 0.0882 | 70 | Low | 445782.49 | 0.532 | 1 | 337251.51 | 13 | 0.8 | 1.22
P003 | Materials | SUP001 | 2025-07 | 2025-05-21 | 809498.53 | 783034 | -26464.53 | 26464.53 | 0 | 2025-07-28 | 4 | 854108.16 | -44609.63 | DOWN | 0.0551 | 68 | Low | 435342.7 | 0.539 | 4 | 347691.3 | 13 | 0.8 | 1.22
P003 | Materials | SUP001 | 2025-07 | 2025-06-12 | 794714.49 | 783034 | -11680.49 | 11680.49 | 0 | 2025-07-28 | 5 | 809498.53 | -14784.04 | DOWN | 0.0186 | 46 | Medium | 460638.32 | 0.617 | 6 | 322395.68 | 13 | 0.8 | 1.22
P003 | Software | SUP001 | 2025-08 | 2025-03-02 | 3166642.06 | 2017382 | -1149260.06 | 1149260.06 | 1 | 2025-08-28 | 1 |  |  |  |  | 179 | Low | 435419.92 | 0.149 | 2 | 1581962.08 | 7 | 1.37 | 1.47
P003 | Software | SUP001 | 2025-08 | 2025-04-22 | 2547719.13 | 2017382 | -530337.13 | 530337.13 | 1 | 2025-08-28 | 2 | 3166642.06 | -618922.93 | DOWN | 0.2429 | 128 | Low | 822823.42 | 0.312 | 1 | 1194558.58 | 7 | 1.37 | 1.47
P003 | Software | SUP001 | 2025-08 | 2025-04-23 | 2254308.59 | 2017382 | -236926.59 | 236926.59 | 0 | 2025-08-28 | 3 | 2547719.13 | -293410.54 | DOWN | 0.1302 | 127 | Low | 727173.07 | 0.316 | 0 | 1290208.93 | 7 | 1.37 | 1.47
P003 | Software | SUP001 | 2025-08 | 2025-05-26 | 2106326.26 | 2017382 | -88944.26 | 88944.26 | 0 | 2025-08-28 | 4 | 2254308.59 | -147982.33 | DOWN | 0.0703 | 94 | Low | 969707.04 | 0.428 | 0 | 1047674.96 | 7 | 1.37 | 1.47
P003 | Software | SUP001 | 2025-08 | 2025-06-14 | 2085894.41 | 2017382 | -68512.41 | 68512.41 | 0 | 2025-08-28 | 5 | 2106326.26 | -20431.85 | DOWN | 0.0098 | 75 | Low | 1055585.73 | 0.492 | 0 | 961796.27 | 7 | 1.37 | 1.47
P003 | Software | SUP001 | 2025-08 | 2025-07-04 | 2048976.66 | 2017382 | -31594.66 | 31594.66 | 0 | 2025-08-28 | 6 | 2085894.41 | -36917.75 | DOWN | 0.018 | 55 | Medium | 1106158.65 | 0.56 | 7 | 911223.35 | 7 | 1.37 | 1.47
P003 | Software | SUP001 | 2025-09 | 2025-04-03 | 393884.22 | 267602 | -126282.22 | 126282.22 | 1 | 2025-09-28 | 1 |  |  |  |  | 178 | Low | 60512.7 | 0.156 | 2 | 207089.3 | 10 | 0.71 | 1.27
P003 | Software | SUP001 | 2025-09 | 2025-08-03 | 324571.04 | 267602 | -56969.04 | 56969.04 | 1 | 2025-09-28 | 2 | 393884.22 | -69313.18 | DOWN | 0.2136 | 56 | Low | 185087.49 | 0.581 | 4 | 82514.51 | 10 | 0.71 | 1.27
P003 | Software | SUP001 | 2025-09 | 2025-08-11 | 298202.67 | 267602 | -30600.67 | 30600.67 | 0 | 2025-09-28 | 3 | 324571.04 | -26368.37 | DOWN | 0.0884 | 48 | Medium | 185148.17 | 0.61 | 6 | 82453.83 | 10 | 0.71 | 1.27
P003 | Software | SUP001 | 2025-09 | 2025-08-26 | 283879.6 | 267602 | -16277.6 | 16277.6 | 0 | 2025-09-28 | 4 | 298202.67 | -14323.07 | DOWN | 0.0505 | 33 | Medium | 192921.28 | 0.663 | 0 | 74680.72 | 10 | 0.71 | 1.27
P003 | Software | SUP001 | 2025-09 | 2025-09-06 | 273180.11 | 267602 | -5578.11 | 5578.11 | 0 | 2025-09-28 | 5 | 283879.6 | -10699.49 | DOWN | 0.0392 | 22 | High | 184020 | 0.702 | 6 | 83582 | 10 | 0.71 | 1.27
P003 | Software | SUP001 | 2025-10 | 2025-05-09 | 3485227.7 | 2087244 | -1397983.7 | 1397983.7 | 1 | 2025-10-28 | 1 |  |  |  |  | 172 | Low | 566021.07 | 0.17 | 1 | 1521222.93 | 19 | 0.95 | 0.98
P003 | Software | SUP001 | 2025-10 | 2025-06-05 | 2696218.77 | 2087244 | -608974.77 | 608974.77 | 1 | 2025-10-28 | 2 | 3485227.7 | -789008.93 | DOWN | 0.2926 | 145 | Low | 771476.5 | 0.266 | 2 | 1315767.5 | 19 | 0.95 | 0.98
P003 | Software | SUP001 | 2025-10 | 2025-08-28 | 2315490.01 | 2087244 | -228246.01 | 228246.01 | 0 | 2025-10-28 | 3 | 2696218.77 | -380728.76 | DOWN | 0.1644 | 61 | Low | 1205989.18 | 0.564 | 6 | 881254.82 | 19 | 0.95 | 0.98
P003 | Software | SUP001 | 2025-10 | 2025-08-28 | 2222943.06 | 2087244 | -135699.06 | 135699.06 | 0 | 2025-10-28 | 4 | 2315490.01 | -92546.95 | DOWN | 0.0416 | 61 | Low | 1250691.2 | 0.564 | 0 | 836552.8 | 19 | 0.95 | 0.98
P003 | Logistics | SUP001 | 2025-11 | 2025-06-07 | 2862710.45 | 1446180 | -1416530.45 | 1416530.45 | 1 | 2025-11-28 | 1 |  |  |  |  | 174 | Low | 403858.65 | 0.148 | 4 | 1042321.35 | 11 | 1.85 | 1.52
P003 | Logistics | SUP001 | 2025-11 | 2025-08-15 | 2128325.59 | 1446180 | -682145.59 | 682145.59 | 1 | 2025-11-28 | 2 | 2862710.45 | -734384.86 | DOWN | 0.3451 | 105 | Low | 836664.09 | 0.37 | 4 | 609515.91 | 11 | 1.85 | 1.52
P003 | Logistics | SUP001 | 2025-11 | 2025-08-26 | 1717113.34 | 1446180 | -270933.34 | 270933.34 | 1 | 2025-11-28 | 3 | 2128325.59 | -411212.25 | DOWN | 0.2395 | 94 | Low | 677529.15 | 0.405 | 3 | 768650.85 | 11 | 1.85 | 1.52
P003 | Logistics | SUP001 | 2025-11 | 2025-09-25 | 1547657.42 | 1446180 | -101477.42 | 101477.42 | 0 | 2025-11-28 | 4 | 1717113.34 | -169455.92 | DOWN | 0.1095 | 64 | Low | 776738.5 | 0.502 | 4 | 669441.5 | 11 | 1.85 | 1.52
P003 | Logistics | SUP001 | 2025-12 | 2025-08-05 | 2339428.42 | 1563207 | -776221.42 | 776221.42 | 1 | 2025-12-28 | 1 |  |  |  |  | 145 | Low | 635617.69 | 0.263 | 1 | 927589.31 | 10 | 1.08 | 1.22
P003 | Logistics | SUP001 | 2025-12 | 2025-09-16 | 1893607.13 | 1563207 | -330400.13 | 330400.13 | 1 | 2025-12-28 | 2 | 2339428.42 | -445821.29 | DOWN | 0.2354 | 103 | Low | 740577.74 | 0.411 | 3 | 822629.26 | 10 | 1.08 | 1.22
P003 | Logistics | SUP001 | 2025-12 | 2025-10-16 | 1749617.45 | 1563207 | -186410.45 | 186410.45 | 0 | 2025-12-28 | 3 | 1893607.13 | -143989.68 | DOWN | 0.0823 | 73 | Low | 840726.46 | 0.516 | 6 | 722480.54 | 10 | 1.08 | 1.22
P003 | Services | SUP040 | 2025-01 | 2024-09-21 | 889916.5 | 496431 | -393485.5 | 393485.5 | 1 | 2025-01-28 | 1 |  |  |  |  | 129 | Low | 200132.18 | 0.244 | 1 | 296298.82 | 17 | 1.86 | 1.34
P003 | Services | SUP040 | 2025-01 | 2024-09-29 | 733182.02 | 496431 | -236751.02 | 236751.02 | 1 | 2025-01-28 | 2 | 889916.5 | -156734.48 | DOWN | 0.2138 | 121 | Low | 194633.34 | 0.265 | 2 | 301797.66 | 17 | 1.86 | 1.34
P003 | Services | SUP040 | 2025-01 | 2024-10-15 | 621694.23 | 496431 | -125263.23 | 125263.23 | 1 | 2025-01-28 | 3 | 733182.02 | -111487.79 | DOWN | 0.1793 | 105 | Low | 202466.77 | 0.308 | 3 | 293964.23 | 17 | 1.86 | 1.34
P003 | Services | SUP040 | 2025-01 | 2024-12-22 | 557210.23 | 496431 | -60779.23 | 60779.23 | 0 | 2025-01-28 | 4 | 621694.23 | -64484 | DOWN | 0.1157 | 37 | Medium | 293940.93 | 0.49 | 2 | 202490.07 | 17 | 1.86 | 1.34
P003 | Software | SUP040 | 2025-02 | 2024-09-29 | 2755007.36 | 1687382 | -1067625.36 | 1067625.36 | 1 | 2025-02-28 | 1 |  |  |  |  | 152 | Low | 491986.37 | 0.177 | 0 | 1195395.63 | 17 | 2.1 | 1.03
P003 | Software | SUP040 | 2025-02 | 2024-10-29 | 2291263.43 | 1687382 | -603881.43 | 603881.43 | 1 | 2025-02-28 | 2 | 2755007.36 | -463743.93 | DOWN | 0.2024 | 122 | Low | 616285.38 | 0.256 | 0 | 1071096.62 | 17 | 2.1 | 1.03
P003 | Software | SUP040 | 2025-02 | 2024-12-13 | 2067677.44 | 1687382 | -380295.44 | 380295.44 | 1 | 2025-02-28 | 3 | 2291263.43 | -223585.99 | DOWN | 0.1081 | 77 | Low | 743959.46 | 0.373 | 3 | 943422.54 | 17 | 2.1 | 1.03
P003 | Software | SUP040 | 2025-02 | 2024-12-24 | 1911378.81 | 1687382 | -223996.81 | 223996.81 | 0 | 2025-02-28 | 4 | 2067677.44 | -156298.63 | DOWN | 0.0818 | 66 | Low | 763990.54 | 0.402 | 2 | 923391.46 | 17 | 2.1 | 1.03
P003 | Software | SUP040 | 2025-02 | 2025-01-10 | 1751807.68 | 1687382 | -64425.68 | 64425.68 | 0 | 2025-02-28 | 5 | 1911378.81 | -159571.13 | DOWN | 0.0911 | 49 | Low | 746534.39 | 0.446 | 2 | 940847.61 | 17 | 2.1 | 1.03
P003 | Materials | SUP040 | 2025-03 | 2024-10-29 | 1635737.71 | 937937 | -697800.71 | 697800.71 | 1 | 2025-03-28 | 1 |  |  |  |  | 150 | Low | 315808.89 | 0.204 | 4 | 622128.11 | 13 | 1.13 | 1.73
P003 | Materials | SUP040 | 2025-03 | 2025-01-03 | 1328110.34 | 937937 | -390173.34 | 390173.34 | 1 | 2025-03-28 | 2 | 1635737.71 | -307627.37 | DOWN | 0.2316 | 84 | Low | 519677.74 | 0.396 | 1 | 418259.26 | 13 | 1.13 | 1.73
P003 | Materials | SUP040 | 2025-03 | 2025-01-27 | 1160593.84 | 937937 | -222656.84 | 222656.84 | 1 | 2025-03-28 | 3 | 1328110.34 | -167516.5 | DOWN | 0.1443 | 60 | Low | 499142.22 | 0.465 | 6 | 438794.78 | 13 | 1.13 | 1.73
P003 | Materials | SUP040 | 2025-03 | 2025-02-19 | 1057037.93 | 937937 | -119100.93 | 119100.93 | 0 | 2025-03-28 | 4 | 1160593.84 | -103555.91 | DOWN | 0.098 | 37 | Medium | 552248.39 | 0.532 | 1 | 385688.61 | 13 | 1.13 | 1.73
P003 | Services | SUP040 | 2025-04 | 2025-01-12 | 3747821.33 | 1923418 | -1824403.33 | 1824403.33 | 1 | 2025-04-28 | 1 |  |  |  |  | 106 | Low | 1263905.24 | 0.329 | 0 | 659512.76 | 13 | 1.21 | 1.27
P003 | Services | SUP040 | 2025-04 | 2025-01-17 | 2965010.03 | 1923418 | -1041592.03 | 1041592.03 | 1 | 2025-04-28 | 2 | 3747821.33 | -782811.3 | DOWN | 0.264 | 101 | Low | 1018865.59 | 0.343 | 3 | 904552.41 | 13 | 1.21 | 1.27
P003 | Services | SUP040 | 2025-04 | 2025-02-07 | 2460288.82 | 1923418 | -536870.82 | 536870.82 | 1 | 2025-04-28 | 3 | 2965010.03 | -504721.21 | DOWN | 0.2051 | 80 | Low | 984508.34 | 0.403 | 0 | 938909.66 | 13 | 1.21 | 1.27
P003 | Services | SUP040 | 2025-04 | 2025-02-17 | 2224263.61 | 1923418 | -300845.61 | 300845.61 | 0 | 2025-04-28 | 4 | 2460288.82 | -236025.21 | DOWN | 0.1061 | 70 | Low | 997902.59 | 0.432 | 4 | 925515.41 | 13 | 1.21 | 1.27
P003 | Services | SUP040 | 2025-04 | 2025-03-14 | 2099377.48 | 1923418 | -175959.48 | 175959.48 | 0 | 2025-04-28 | 5 | 2224263.61 | -124886.13 | DOWN | 0.0595 | 45 | Medium | 1067959.62 | 0.504 | 4 | 855458.38 | 13 | 1.21 | 1.27
P003 | Services | SUP040 | 2025-04 | 2025-04-02 | 2034613.39 | 1923418 | -111195.39 | 111195.39 | 0 | 2025-04-28 | 6 | 2099377.48 | -64764.09 | DOWN | 0.0318 | 26 | Medium | 1078932.73 | 0.559 | 5 | 844485.27 | 13 | 1.21 | 1.27
P003 | Software | SUP040 | 2025-05 | 2025-01-20 | 3723272.39 | 1775923 | -1947349.39 | 1947349.39 | 1 | 2025-05-28 | 1 |  |  |  |  | 128 | Low | 911100.49 | 0.261 | 2 | 864822.51 | 14 | 1.36 | 1.73
P003 | Software | SUP040 | 2025-05 | 2025-02-13 | 2795537.16 | 1775923 | -1019614.16 | 1019614.16 | 1 | 2025-05-28 | 2 | 3723272.39 | -927735.23 | DOWN | 0.3319 | 104 | Low | 929327.16 | 0.329 | 1 | 846595.84 | 14 | 1.36 | 1.73
P003 | Software | SUP040 | 2025-05 | 2025-04-17 | 2348003.28 | 1775923 | -572080.28 | 572080.28 | 1 | 2025-05-28 | 3 | 2795537.16 | -447533.88 | DOWN | 0.1906 | 41 | Low | 1210740.48 | 0.507 | 3 | 565182.52 | 14 | 1.36 | 1.73
P003 | Software | SUP040 | 2025-05 | 2025-04-29 | 2096280.45 | 1775923 | -320357.45 | 320357.45 | 1 | 2025-05-28 | 4 | 2348003.28 | -251722.83 | DOWN | 0.1201 | 29 | Low | 1164902.57 | 0.541 | 5 | 611020.43 | 14 | 1.36 | 1.73
P003 | Software | SUP040 | 2025-05 | 2025-05-13 | 1974726.5 | 1775923 | -198803.5 | 198803.5 | 0 | 2025-05-28 | 5 | 2096280.45 | -121553.95 | DOWN | 0.0616 | 15 | Medium | 1214285.79 | 0.581 | 2 | 561637.21 | 14 | 1.36 | 1.73
P003 | Materials | SUP040 | 2025-06 | 2025-01-14 | 1869179.23 | 1066413 | -802766.23 | 802766.23 | 1 | 2025-06-28 | 1 |  |  |  |  | 165 | Low | 266223.27 | 0.154 | 3 | 800189.73 | 22 | 1.47 | 1.51
P003 | Materials | SUP040 | 2025-06 | 2025-02-17 | 1505798.59 | 1066413 | -439385.59 | 439385.59 | 1 | 2025-06-28 | 2 | 1869179.23 | -363380.64 | DOWN | 0.2413 | 131 | Low | 392295.37 | 0.249 | 2 | 674117.63 | 22 | 1.47 | 1.51
P003 | Materials | SUP040 | 2025-06 | 2025-06-17 | 1312383.99 | 1066413 | -245970.99 | 245970.99 | 1 | 2025-06-28 | 3 | 1505798.59 | -193414.6 | DOWN | 0.1474 | 11 | Low | 759488.7 | 0.585 | 4 | 306924.3 | 22 | 1.47 | 1.51
P003 | Software | SUP040 | 2025-07 | 2025-02-19 | 275844.62 | 140066 | -135778.62 | 135778.62 | 1 | 2025-07-28 | 1 |  |  |  |  | 159 | Low | 52832.31 | 0.18 | 0 | 87233.69 | 13 | 0.8 | 1.22
P003 | Software | SUP040 | 2025-07 | 2025-03-04 | 218123.96 | 140066 | -78057.96 | 78057.96 | 1 | 2025-07-28 | 2 | 275844.62 | -57720.66 | DOWN | 0.2646 | 146 | Low | 46791.38 | 0.219 | 0 | 93274.62 | 13 | 0.8 | 1.22
P003 | Software | SUP040 | 2025-07 | 2025-05-04 | 185201.89 | 140066 | -45135.89 | 45135.89 | 1 | 2025-07-28 | 3 | 218123.96 | -32922.07 | DOWN | 0.1778 | 85 | Low | 74090.36 | 0.399 | 3 | 65975.64 | 13 | 0.8 | 1.22
P003 | Software | SUP040 | 2025-07 | 2025-07-15 | 167301.81 | 140066 | -27235.81 | 27235.81 | 1 | 2025-07-28 | 4 | 185201.89 | -17900.08 | DOWN | 0.107 | 13 | Medium | 99967.43 | 0.612 | 8 | 40098.57 | 13 | 0.8 | 1.22
P003 | Software | SUP040 | 2025-08 | 2025-04-20 | 495762.47 | 237627 | -258135.47 | 258135.47 | 1 | 2025-08-28 | 1 |  |  |  |  | 130 | Low | 132627.8 | 0.255 | 0 | 104999.2 | 7 | 1.37 | 1.47
P003 | Software | SUP040 | 2025-08 | 2025-06-12 | 374720.56 | 237627 | -137093.56 | 137093.56 | 1 | 2025-08-28 | 2 | 495762.47 | -121041.91 | DOWN | 0.323 | 77 | Low | 150078.49 | 0.405 | 2 | 87548.51 | 7 | 1.37 | 1.47
P003 | Software | SUP040 | 2025-08 | 2025-06-17 | 310806.4 | 237627 | -73179.4 | 73179.4 | 1 | 2025-08-28 | 3 | 374720.56 | -63914.16 | DOWN | 0.2056 | 72 | Low | 125956.97 | 0.419 | 5 | 111670.03 | 7 | 1.37 | 1.47
P003 | Software | SUP040 | 2025-08 | 2025-07-31 | 282449.74 | 237627 | -44822.74 | 44822.74 | 1 | 2025-08-28 | 4 | 310806.4 | -28356.66 | DOWN | 0.1004 | 28 | Medium | 162611.01 | 0.543 | 6 | 75015.99 | 7 | 1.37 | 1.47
P003 | Software | SUP040 | 2025-08 | 2025-07-31 | 261554.02 | 237627 | -23927.02 | 23927.02 | 0 | 2025-08-28 | 5 | 282449.74 | -20895.72 | DOWN | 0.0799 | 28 | Medium | 146491.38 | 0.543 | 8 | 91135.62 | 7 | 1.37 | 1.47
P003 | Software | SUP040 | 2025-09 | 2025-04-21 | 1848407.31 | 1061173 | -787234.31 | 787234.31 | 1 | 2025-09-28 | 1 |  |  |  |  | 160 | Low | 311022.48 | 0.177 | 1 | 750150.52 | 10 | 0.71 | 1.27
P003 | Software | SUP040 | 2025-09 | 2025-05-18 | 1519974.22 | 1061173 | -458801.22 | 458801.22 | 1 | 2025-09-28 | 2 | 1848407.31 | -328433.09 | DOWN | 0.2161 | 133 | Low | 394149.76 | 0.257 | 2 | 667023.24 | 10 | 0.71 | 1.27
P003 | Software | SUP040 | 2025-09 | 2025-08-27 | 1293003.43 | 1061173 | -231830.43 | 231830.43 | 1 | 2025-09-28 | 3 | 1519974.22 | -226970.79 | DOWN | 0.1755 | 32 | Low | 728126.15 | 0.555 | 4 | 333046.85 | 10 | 0.71 | 1.27
P003 | Software | SUP040 | 2025-09 | 2025-09-12 | 1193795.97 | 1061173 | -132622.97 | 132622.97 | 0 | 2025-09-28 | 4 | 1293003.43 | -99207.46 | DOWN | 0.0831 | 16 | Medium | 776881.66 | 0.603 | 3 | 284291.34 | 10 | 0.71 | 1.27
P003 | Logistics | SUP040 | 2025-10 | 2025-05-14 | 326854.11 | 142534 | -184320.11 | 184320.11 | 1 | 2025-10-28 | 1 |  |  |  |  | 167 | Low | 51477.94 | 0.157 | 1 | 91056.06 | 19 | 0.95 | 0.98
P003 | Logistics | SUP040 | 2025-10 | 2025-06-01 | 241493.26 | 142534 | -98959.26 | 98959.26 | 1 | 2025-10-28 | 2 | 326854.11 | -85360.85 | DOWN | 0.3535 | 149 | Low | 54007.52 | 0.21 | 0 | 88526.48 | 19 | 0.95 | 0.98
P003 | Logistics | SUP040 | 2025-10 | 2025-06-26 | 199783.07 | 142534 | -57249.07 | 57249.07 | 1 | 2025-10-28 | 3 | 241493.26 | -41710.19 | DOWN | 0.2088 | 124 | Low | 55165.21 | 0.284 | 2 | 87368.79 | 19 | 0.95 | 0.98
P003 | Logistics | SUP040 | 2025-10 | 2025-07-22 | 176697.7 | 142534 | -34163.7 | 34163.7 | 1 | 2025-10-28 | 4 | 199783.07 | -23085.37 | DOWN | 0.1306 | 98 | Low | 66673.76 | 0.36 | 0 | 75860.24 | 19 | 0.95 | 0.98
P003 | Logistics | SUP040 | 2025-10 | 2025-08-04 | 162627.46 | 142534 | -20093.46 | 20093.46 | 0 | 2025-10-28 | 5 | 176697.7 | -14070.24 | DOWN | 0.0865 | 85 | Low | 67548.02 | 0.399 | 5 | 74985.98 | 19 | 0.95 | 0.98
P003 | Logistics | SUP040 | 2025-10 | 2025-10-04 | 151888.77 | 142534 | -9354.77 | 9354.77 | 0 | 2025-10-28 | 6 | 162627.46 | -10738.69 | DOWN | 0.0707 | 24 | Medium | 89008.93 | 0.579 | 6 | 53525.07 | 19 | 0.95 | 0.98
P003 | Services | SUP040 | 2025-11 | 2025-08-09 | 1348959.16 | 678138 | -670821.16 | 670821.16 | 1 | 2025-11-28 | 1 |  |  |  |  | 111 | Low | 393506.6 | 0.292 | 2 | 284631.4 | 11 | 1.85 | 1.52
P003 | Services | SUP040 | 2025-11 | 2025-08-19 | 1042886.49 | 678138 | -364748.49 | 364748.49 | 1 | 2025-11-28 | 2 | 1348959.16 | -306072.67 | DOWN | 0.2935 | 101 | Low | 336515.49 | 0.319 | 3 | 341622.51 | 11 | 1.85 | 1.52
P003 | Services | SUP040 | 2025-11 | 2025-08-20 | 853164.86 | 678138 | -175026.86 | 175026.86 | 1 | 2025-11-28 | 3 | 1042886.49 | -189721.63 | DOWN | 0.2224 | 100 | Low | 262166.71 | 0.322 | 2 | 415971.29 | 11 | 1.85 | 1.52
P003 | Services | SUP040 | 2025-11 | 2025-11-04 | 780055.53 | 678138 | -101917.53 | 101917.53 | 0 | 2025-11-28 | 4 | 853164.86 | -73109.33 | DOWN | 0.0937 | 24 | Medium | 415623.27 | 0.525 | 4 | 262514.73 | 11 | 1.85 | 1.52
P003 | Services | SUP040 | 2025-11 | 2025-11-13 | 744271.46 | 678138 | -66133.46 | 66133.46 | 0 | 2025-11-28 | 5 | 780055.53 | -35784.07 | DOWN | 0.0481 | 15 | Medium | 440147.41 | 0.55 | 4 | 237990.59 | 11 | 1.85 | 1.52
P003 | Software | SUP040 | 2025-12 | 2025-09-07 | 2953429.71 | 1423964 | -1529465.71 | 1529465.71 | 1 | 2025-12-28 | 1 |  |  |  |  | 112 | Low | 899829.85 | 0.316 | 1 | 524134.15 | 10 | 1.08 | 1.22
P003 | Software | SUP040 | 2025-12 | 2025-09-08 | 2247501.34 | 1423964 | -823537.34 | 823537.34 | 1 | 2025-12-28 | 2 | 2953429.71 | -705928.37 | DOWN | 0.3141 | 111 | Low | 750375.62 | 0.319 | 4 | 673588.38 | 10 | 1.08 | 1.22
P003 | Software | SUP040 | 2025-12 | 2025-10-17 | 1882816.28 | 1423964 | -458852.28 | 458852.28 | 1 | 2025-12-28 | 3 | 2247501.34 | -364685.06 | DOWN | 0.1937 | 72 | Low | 771525.21 | 0.433 | 2 | 652438.79 | 10 | 1.08 | 1.22
P004 | Software | SUP013 | 2025-01 | 2024-08-30 | 4916545.6 | 2476615 | -2439930.6 | 2439930.6 | 1 | 2025-01-28 | 1 |  |  |  |  | 151 | Low | 775252.3 | 0.157 | 0 | 1701362.7 | 9 | 1 | 1.26
P004 | Software | SUP013 | 2025-01 | 2024-10-23 | 4332863.98 | 2476615 | -1856248.98 | 1856248.98 | 1 | 2025-01-28 | 2 | 4916545.6 | -583681.62 | DOWN | 0.1347 | 97 | Low | 1259677.54 | 0.28 | 4 | 1216937.46 | 9 | 1 | 1.26
P004 | Software | SUP013 | 2025-01 | 2024-11-28 | 3836540.08 | 2476615 | -1359925.08 | 1359925.08 | 1 | 2025-01-28 | 3 | 4332863.98 | -496323.9 | DOWN | 0.1294 | 61 | Low | 1317717.67 | 0.361 | 4 | 1158897.33 | 9 | 1 | 1.26
P004 | Electronics | SUP013 | 2025-02 | 2024-10-22 | 1396979.02 | 634920 | -762059.02 | 762059.02 | 1 | 2025-02-28 | 1 |  |  |  |  | 129 | Low | 276402.77 | 0.201 | 1 | 358517.23 | 13 | 1.26 | 0.97
P004 | Electronics | SUP013 | 2025-02 | 2024-10-26 | 1210371.17 | 634920 | -575451.17 | 575451.17 | 1 | 2025-02-28 | 2 | 1396979.02 | -186607.85 | DOWN | 0.1542 | 125 | Low | 233822.02 | 0.209 | 2 | 401097.98 | 13 | 1.26 | 0.97
P004 | Electronics | SUP013 | 2025-02 | 2024-10-29 | 1060510.95 | 634920 | -425590.95 | 425590.95 | 1 | 2025-02-28 | 3 | 1210371.17 | -149860.22 | DOWN | 0.1413 | 122 | Low | 211283.61 | 0.216 | 2 | 423636.39 | 13 | 1.26 | 0.97
P004 | Electronics | SUP013 | 2025-02 | 2025-02-04 | 964187.17 | 634920 | -329267.17 | 329267.17 | 1 | 2025-02-28 | 4 | 1060510.95 | -96323.78 | DOWN | 0.0999 | 24 | Low | 430720.52 | 0.432 | 0 | 204199.48 | 13 | 1.26 | 0.97
P004 | Electronics | SUP013 | 2025-02 | 2025-02-18 | 889716.84 | 634920 | -254796.84 | 254796.84 | 1 | 2025-02-28 | 5 | 964187.17 | -74470.33 | DOWN | 0.0837 | 10 | Medium | 441677.79 | 0.461 | 4 | 193242.21 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP013 | 2025-03 | 2024-10-10 | 359502.08 | 218282 | -141220.08 | 141220.08 | 1 | 2025-03-28 | 1 |  |  |  |  | 169 | Low | 42485.98 | 0.116 | 2 | 175796.02 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP013 | 2025-03 | 2024-11-05 | 324287.26 | 218282 | -106005.26 | 106005.26 | 1 | 2025-03-28 | 2 | 359502.08 | -35214.82 | DOWN | 0.1086 | 143 | Low | 59610.08 | 0.175 | 2 | 158671.92 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP013 | 2025-03 | 2025-01-15 | 297968.47 | 218282 | -79686.47 | 79686.47 | 1 | 2025-03-28 | 3 | 324287.26 | -26318.79 | DOWN | 0.0883 | 72 | Low | 96527.9 | 0.336 | 2 | 121754.1 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP013 | 2025-03 | 2025-01-26 | 278541.05 | 218282 | -60259.05 | 60259.05 | 1 | 2025-03-28 | 4 | 297968.47 | -19427.42 | DOWN | 0.0697 | 61 | Low | 100347.8 | 0.361 | 4 | 117934.2 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP013 | 2025-03 | 2025-02-11 | 264988.69 | 218282 | -46706.69 | 46706.69 | 1 | 2025-03-28 | 5 | 278541.05 | -13552.36 | DOWN | 0.0511 | 45 | Low | 102671.84 | 0.398 | 3 | 115610.16 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP013 | 2025-04 | 2024-11-27 | 2694543.88 | 1613917 | -1080626.88 | 1080626.88 | 1 | 2025-04-28 | 1 |  |  |  |  | 152 | Low | 391435.18 | 0.143 | 1 | 1222481.82 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP013 | 2025-04 | 2024-12-20 | 2405593.87 | 1613917 | -791676.87 | 791676.87 | 1 | 2025-04-28 | 2 | 2694543.88 | -288950.01 | DOWN | 0.1201 | 129 | Low | 476872.99 | 0.191 | 1 | 1137044.01 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP013 | 2025-04 | 2025-03-09 | 2203774.15 | 1613917 | -589857.15 | 589857.15 | 1 | 2025-04-28 | 3 | 2405593.87 | -201819.72 | DOWN | 0.0916 | 50 | Low | 753330.91 | 0.357 | 4 | 860586.09 | 15 | 1.69 | 1.47
P004 | Logistics | SUP013 | 2025-05 | 2024-12-22 | 2589847.58 | 1210051 | -1379796.58 | 1379796.58 | 1 | 2025-05-28 | 1 |  |  |  |  | 157 | Low | 356151.15 | 0.143 | 0 | 853899.85 | 12 | 1.03 | 1.42
P004 | Logistics | SUP013 | 2025-05 | 2025-01-31 | 2292404.55 | 1210051 | -1082353.55 | 1082353.55 | 1 | 2025-05-28 | 2 | 2589847.58 | -297443.03 | DOWN | 0.1298 | 117 | Low | 512762.21 | 0.233 | 0 | 697288.79 | 12 | 1.03 | 1.42
P004 | Logistics | SUP013 | 2025-05 | 2025-02-01 | 2059604.48 | 1210051 | -849553.48 | 849553.48 | 1 | 2025-05-28 | 3 | 2292404.55 | -232800.07 | DOWN | 0.113 | 116 | Low | 518156.84 | 0.236 | 0 | 691894.16 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP013 | 2025-06 | 2025-01-17 | 1120113.54 | 576397 | -543716.54 | 543716.54 | 1 | 2025-06-28 | 1 |  |  |  |  | 162 | Low | 146200.78 | 0.132 | 1 | 430196.22 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP013 | 2025-06 | 2025-02-03 | 990847.4 | 576397 | -414450.4 | 414450.4 | 1 | 2025-06-28 | 2 | 1120113.54 | -129266.14 | DOWN | 0.1305 | 145 | Low | 171014.21 | 0.17 | 0 | 405382.79 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP013 | 2025-06 | 2025-02-13 | 893102.29 | 576397 | -316705.29 | 316705.29 | 1 | 2025-06-28 | 3 | 990847.4 | -97745.11 | DOWN | 0.1094 | 135 | Low | 175774.56 | 0.193 | 4 | 400622.44 | 15 | 0.81 | 1.56
P004 | Software | SUP013 | 2025-07 | 2025-03-23 | 4203225.85 | 1651084 | -2552141.85 | 2552141.85 | 1 | 2025-07-28 | 1 |  |  |  |  | 127 | Low | 776068.43 | 0.195 | 1 | 875015.57 | 10 | 1.72 | 1
P004 | Software | SUP013 | 2025-07 | 2025-04-13 | 3653307 | 1651084 | -2002223 | 2002223 | 1 | 2025-07-28 | 2 | 4203225.85 | -549918.85 | DOWN | 0.1505 | 106 | Low | 897976.17 | 0.238 | 4 | 753107.83 | 10 | 1.72 | 1
P004 | Software | SUP013 | 2025-07 | 2025-05-26 | 3167376.85 | 1651084 | -1516292.85 | 1516292.85 | 1 | 2025-07-28 | 3 | 3653307 | -485930.15 | DOWN | 0.1534 | 63 | Low | 1057369.87 | 0.328 | 2 | 593714.13 | 10 | 1.72 | 1
P004 | Logistics | SUP013 | 2025-08 | 2025-04-06 | 1639645.19 | 863943 | -775702.19 | 775702.19 | 1 | 2025-08-28 | 1 |  |  |  |  | 144 | Low | 250623.58 | 0.164 | 4 | 613319.42 | 13 | 1.45 | 1.13
P004 | Logistics | SUP013 | 2025-08 | 2025-04-20 | 1440284.32 | 863943 | -576341.32 | 576341.32 | 1 | 2025-08-28 | 2 | 1639645.19 | -199360.87 | DOWN | 0.1384 | 130 | Low | 292973.51 | 0.194 | 1 | 570969.49 | 13 | 1.45 | 1.13
P004 | Logistics | SUP013 | 2025-08 | 2025-04-24 | 1304460.88 | 863943 | -440517.88 | 440517.88 | 1 | 2025-08-28 | 3 | 1440284.32 | -135823.44 | DOWN | 0.1041 | 126 | Low | 270641.25 | 0.203 | 2 | 593301.75 | 13 | 1.45 | 1.13
P004 | Logistics | SUP013 | 2025-08 | 2025-05-08 | 1180605.11 | 863943 | -316662.11 | 316662.11 | 1 | 2025-08-28 | 4 | 1304460.88 | -123855.77 | DOWN | 0.1049 | 112 | Low | 283919.59 | 0.233 | 1 | 580023.41 | 13 | 1.45 | 1.13
P004 | Logistics | SUP013 | 2025-08 | 2025-05-27 | 1108542.78 | 863943 | -244599.78 | 244599.78 | 1 | 2025-08-28 | 5 | 1180605.11 | -72062.33 | DOWN | 0.065 | 93 | Low | 323013.35 | 0.274 | 0 | 540929.65 | 13 | 1.45 | 1.13
P004 | Services | SUP013 | 2025-09 | 2025-04-05 | 4575016.87 | 2140986 | -2434030.87 | 2434030.87 | 1 | 2025-09-28 | 1 |  |  |  |  | 176 | Low | 471900.46 | 0.096 | 0 | 1669085.54 | 12 | 1.31 | 1.3
P004 | Services | SUP013 | 2025-09 | 2025-05-21 | 3894815.81 | 2140986 | -1753829.81 | 1753829.81 | 1 | 2025-09-28 | 2 | 4575016.87 | -680201.06 | DOWN | 0.1746 | 130 | Low | 775889.23 | 0.197 | 0 | 1365096.77 | 12 | 1.31 | 1.3
P004 | Services | SUP013 | 2025-09 | 2025-05-26 | 3439383.24 | 2140986 | -1298397.24 | 1298397.24 | 1 | 2025-09-28 | 3 | 3894815.81 | -455432.57 | DOWN | 0.1324 | 125 | Low | 765584.97 | 0.208 | 0 | 1375401.03 | 12 | 1.31 | 1.3
P004 | Services | SUP013 | 2025-09 | 2025-06-30 | 3106682.04 | 2140986 | -965696.04 | 965696.04 | 1 | 2025-09-28 | 4 | 3439383.24 | -332701.2 | DOWN | 0.1071 | 90 | Low | 884461.05 | 0.285 | 3 | 1256524.95 | 12 | 1.31 | 1.3
P004 | Services | SUP013 | 2025-09 | 2025-09-17 | 2845831 | 2140986 | -704845 | 704845 | 1 | 2025-09-28 | 5 | 3106682.04 | -260851.04 | DOWN | 0.0917 | 11 | Medium | 1241830.45 | 0.458 | 3 | 899155.55 | 12 | 1.31 | 1.3
P004 | Logistics | SUP013 | 2025-10 | 2025-07-15 | 1620630.03 | 655842 | -964788.03 | 964788.03 | 1 | 2025-10-28 | 1 |  |  |  |  | 105 | Low | 381640.84 | 0.25 | 6 | 274201.16 | 16 | 1.37 | 1.4
P004 | Logistics | SUP013 | 2025-10 | 2025-08-06 | 1359560.43 | 655842 | -703718.43 | 703718.43 | 1 | 2025-10-28 | 2 | 1620630.03 | -261069.6 | DOWN | 0.192 | 83 | Low | 402703.94 | 0.298 | 3 | 253138.06 | 16 | 1.37 | 1.4
P004 | Logistics | SUP013 | 2025-10 | 2025-08-18 | 1162294.65 | 655842 | -506452.65 | 506452.65 | 1 | 2025-10-28 | 3 | 1359560.43 | -197265.78 | DOWN | 0.1697 | 71 | Low | 404554.2 | 0.324 | 3 | 251287.8 | 16 | 1.37 | 1.4
P004 | Logistics | SUP013 | 2025-10 | 2025-08-29 | 1016416.85 | 655842 | -360574.85 | 360574.85 | 1 | 2025-10-28 | 4 | 1162294.65 | -145877.8 | DOWN | 0.1435 | 60 | Low | 339213.04 | 0.348 | 3 | 316628.96 | 16 | 1.37 | 1.4
P004 | Electronics | SUP013 | 2025-11 | 2025-06-09 | 3142220.49 | 1412400 | -1729820.49 | 1729820.49 | 1 | 2025-11-28 | 1 |  |  |  |  | 172 | Low | 358147.41 | 0.109 | 0 | 1054252.59 | 7 | 0.59 | 1.31
P004 | Electronics | SUP013 | 2025-11 | 2025-06-14 | 2685204.49 | 1412400 | -1272804.49 | 1272804.49 | 1 | 2025-11-28 | 2 | 3142220.49 | -457016 | DOWN | 0.1702 | 167 | Low | 301490.11 | 0.12 | 0 | 1110909.89 | 7 | 0.59 | 1.31
P004 | Electronics | SUP013 | 2025-11 | 2025-07-03 | 2394898.68 | 1412400 | -982498.68 | 982498.68 | 1 | 2025-11-28 | 3 | 2685204.49 | -290305.81 | DOWN | 0.1212 | 148 | Low | 387972.4 | 0.164 | 0 | 1024427.6 | 7 | 0.59 | 1.31
P004 | Electronics | SUP013 | 2025-11 | 2025-08-28 | 2176222.7 | 1412400 | -763822.7 | 763822.7 | 1 | 2025-11-28 | 4 | 2394898.68 | -218675.98 | DOWN | 0.1005 | 92 | Low | 606231.08 | 0.291 | 1 | 806168.92 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP013 | 2025-12 | 2025-07-19 | 1848332.03 | 1080421 | -767911.03 | 767911.03 | 1 | 2025-12-28 | 1 |  |  |  |  | 162 | Low | 237846.66 | 0.13 | 2 | 842574.34 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP013 | 2025-12 | 2025-10-10 | 1654879.39 | 1080421 | -574458.39 | 574458.39 | 1 | 2025-12-28 | 2 | 1848332.03 | -193452.64 | DOWN | 0.1169 | 79 | Low | 518856.86 | 0.316 | 1 | 561564.14 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP013 | 2025-12 | 2025-11-06 | 1506783.08 | 1080421 | -426362.08 | 426362.08 | 1 | 2025-12-28 | 3 | 1654879.39 | -148096.31 | DOWN | 0.0983 | 52 | Low | 550680.68 | 0.377 | 6 | 529740.32 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP013 | 2025-12 | 2025-11-28 | 1410418.29 | 1080421 | -329997.29 | 329997.29 | 1 | 2025-12-28 | 4 | 1506783.08 | -96364.79 | DOWN | 0.0683 | 30 | Low | 629000.2 | 0.426 | 4 | 451420.8 | 9 | 1.11 | 0.94
P004 | Software | SUP002 | 2025-01 | 2024-08-04 | 577744.23 | 349650 | -228094.23 | 228094.23 | 1 | 2025-01-28 | 1 |  |  |  |  | 177 | Low | 85810.49 | 0.156 | 0 | 263839.51 | 9 | 1 | 1.26
P004 | Software | SUP002 | 2025-01 | 2024-09-16 | 449990.85 | 349650 | -100340.85 | 100340.85 | 1 | 2025-01-28 | 2 | 577744.23 | -127753.38 | DOWN | 0.2839 | 134 | Low | 126808.34 | 0.305 | 3 | 222841.66 | 9 | 1 | 1.26
P004 | Software | SUP002 | 2025-01 | 2024-09-17 | 402223.35 | 349650 | -52573.35 | 52573.35 | 0 | 2025-01-28 | 3 | 449990.85 | -47767.5 | DOWN | 0.1188 | 133 | Low | 116261.02 | 0.308 | 1 | 233388.98 | 9 | 1 | 1.26
P004 | Software | SUP002 | 2025-01 | 2024-12-02 | 368927.68 | 349650 | -19277.68 | 19277.68 | 0 | 2025-01-28 | 4 | 402223.35 | -33295.67 | DOWN | 0.0902 | 57 | Medium | 196997.03 | 0.578 | 2 | 152652.97 | 9 | 1 | 1.26
P004 | Electronics | SUP002 | 2025-02 | 2024-09-08 | 2760516.55 | 1930395 | -830121.55 | 830121.55 | 1 | 2025-02-28 | 1 |  |  |  |  | 173 | Low | 462579.83 | 0.162 | 4 | 1467815.17 | 13 | 1.26 | 0.97
P004 | Electronics | SUP002 | 2025-02 | 2024-09-20 | 2301194.46 | 1930395 | -370799.46 | 370799.46 | 1 | 2025-02-28 | 2 | 2760516.55 | -459322.09 | DOWN | 0.1996 | 161 | Low | 438594.29 | 0.203 | 0 | 1491800.71 | 13 | 1.26 | 0.97
P004 | Electronics | SUP002 | 2025-02 | 2024-11-20 | 2113719 | 1930395 | -183324 | 183324 | 0 | 2025-02-28 | 3 | 2301194.46 | -187475.46 | DOWN | 0.0887 | 100 | Low | 930464.53 | 0.413 | 3 | 999930.47 | 13 | 1.26 | 0.97
P004 | Electronics | SUP002 | 2025-02 | 2025-01-17 | 2008010.42 | 1930395 | -77615.42 | 77615.42 | 0 | 2025-02-28 | 4 | 2113719 | -105708.58 | DOWN | 0.0526 | 42 | Medium | 1276016.63 | 0.612 | 7 | 654378.37 | 13 | 1.26 | 0.97
P004 | Electronics | SUP002 | 2025-02 | 2025-02-04 | 1962178.53 | 1930395 | -31783.53 | 31783.53 | 0 | 2025-02-28 | 5 | 2008010.42 | -45831.89 | DOWN | 0.0234 | 24 | High | 1249011.6 | 0.674 | 3 | 681383.4 | 13 | 1.26 | 0.97
P004 | Electronics | SUP002 | 2025-02 | 2025-02-13 | 1952612.34 | 1930395 | -22217.34 | 22217.34 | 0 | 2025-02-28 | 6 | 1962178.53 | -9566.19 | DOWN | 0.0049 | 15 | High | 1405359.07 | 0.705 | 8 | 525035.93 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP002 | 2025-03 | 2024-11-14 | 700073.86 | 595574 | -104499.86 | 104499.86 | 0 | 2025-03-28 | 1 |  |  |  |  | 134 | Low | 224410.74 | 0.305 | 3 | 371163.26 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP002 | 2025-03 | 2024-12-03 | 641311.9 | 595574 | -45737.9 | 45737.9 | 0 | 2025-03-28 | 2 | 700073.86 | -58761.96 | DOWN | 0.0916 | 115 | Low | 251218.93 | 0.372 | 3 | 344355.07 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP002 | 2025-03 | 2024-12-08 | 614450.03 | 595574 | -18876.03 | 18876.03 | 0 | 2025-03-28 | 3 | 641311.9 | -26861.87 | DOWN | 0.0437 | 110 | Low | 242869.3 | 0.39 | 6 | 352704.7 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP002 | 2025-03 | 2024-12-28 | 606338.4 | 595574 | -10764.4 | 10764.4 | 0 | 2025-03-28 | 4 | 614450.03 | -8111.63 | DOWN | 0.0134 | 90 | Low | 288738.85 | 0.461 | 2 | 306835.15 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP002 | 2025-03 | 2025-01-04 | 600129.14 | 595574 | -4555.14 | 4555.14 | 0 | 2025-03-28 | 5 | 606338.4 | -6209.26 | DOWN | 0.0103 | 83 | Low | 295216.92 | 0.486 | 3 | 300357.08 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP002 | 2025-03 | 2025-02-18 | 599914.71 | 595574 | -4340.71 | 4340.71 | 0 | 2025-03-28 | 6 | 600129.14 | -214.43 | DOWN | 0.0004 | 38 | Medium | 388127.63 | 0.645 | 3 | 207446.37 | 11 | 0.73 | 1.3
P004 | Logistics | SUP002 | 2025-04 | 2024-11-12 | 3005354.36 | 1921634 | -1083720.36 | 1083720.36 | 1 | 2025-04-28 | 1 |  |  |  |  | 167 | Low | 534260.43 | 0.174 | 1 | 1387373.57 | 15 | 1.69 | 1.47
P004 | Logistics | SUP002 | 2025-04 | 2024-11-15 | 2465167.79 | 1921634 | -543533.79 | 543533.79 | 1 | 2025-04-28 | 2 | 3005354.36 | -540186.57 | DOWN | 0.2191 | 164 | Low | 435306.57 | 0.183 | 5 | 1486327.43 | 15 | 1.69 | 1.47
P004 | Logistics | SUP002 | 2025-04 | 2024-11-17 | 2213537.49 | 1921634 | -291903.49 | 291903.49 | 0 | 2025-04-28 | 3 | 2465167.79 | -251630.3 | DOWN | 0.1137 | 162 | Low | 413191.46 | 0.19 | 0 | 1508442.54 | 15 | 1.69 | 1.47
P004 | Logistics | SUP002 | 2025-04 | 2024-12-13 | 2059936.97 | 1921634 | -138302.97 | 138302.97 | 0 | 2025-04-28 | 4 | 2213537.49 | -153600.52 | DOWN | 0.0746 | 136 | Low | 592966.39 | 0.275 | 4 | 1328667.61 | 15 | 1.69 | 1.47
P004 | Logistics | SUP002 | 2025-04 | 2025-02-07 | 2004573.8 | 1921634 | -82939.8 | 82939.8 | 0 | 2025-04-28 | 5 | 2059936.97 | -55363.17 | DOWN | 0.0276 | 80 | Low | 933633.18 | 0.458 | 5 | 988000.82 | 15 | 1.69 | 1.47
P004 | Logistics | SUP002 | 2025-04 | 2025-02-28 | 1919422.38 | 1921634 | 2211.62 | 2211.62 | 0 | 2025-04-28 | 6 | 2004573.8 | -85151.42 | DOWN | 0.0444 | 59 | Medium | 976975.84 | 0.527 | 2 | 944658.16 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP002 | 2025-05 | 2025-01-05 | 3197671.06 | 2749916 | -447755.06 | 447755.06 | 0 | 2025-05-28 | 1 |  |  |  |  | 143 | Low | 875181.33 | 0.272 | 0 | 1874734.67 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP002 | 2025-05 | 2025-02-07 | 2942918.99 | 2749916 | -193002.99 | 193002.99 | 0 | 2025-05-28 | 2 | 3197671.06 | -254752.07 | DOWN | 0.0866 | 110 | Low | 1231445.26 | 0.389 | 7 | 1518470.74 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP002 | 2025-05 | 2025-02-16 | 2852677.61 | 2749916 | -102761.61 | 102761.61 | 0 | 2025-05-28 | 3 | 2942918.99 | -90241.38 | DOWN | 0.0316 | 101 | Low | 1290803.65 | 0.42 | 6 | 1459112.35 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP002 | 2025-05 | 2025-03-29 | 2789397.53 | 2749916 | -39481.53 | 39481.53 | 0 | 2025-05-28 | 4 | 2852677.61 | -63280.08 | DOWN | 0.0227 | 60 | Medium | 1500672.7 | 0.565 | 2 | 1249243.3 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP002 | 2025-05 | 2025-05-10 | 2776973.1 | 2749916 | -27057.1 | 27057.1 | 0 | 2025-05-28 | 5 | 2789397.53 | -12424.43 | DOWN | 0.0045 | 18 | High | 2007736.67 | 0.714 | 8 | 742179.33 | 12 | 1.03 | 1.42
P004 | Electronics | SUP002 | 2025-06 | 2025-01-31 | 3456494.9 | 2181591 | -1274903.9 | 1274903.9 | 1 | 2025-06-28 | 1 |  |  |  |  | 148 | Low | 828736.43 | 0.255 | 5 | 1352854.57 | 15 | 0.81 | 1.56
P004 | Electronics | SUP002 | 2025-06 | 2025-02-06 | 2739902.49 | 2181591 | -558311.49 | 558311.49 | 1 | 2025-06-28 | 2 | 3456494.9 | -716592.41 | DOWN | 0.2615 | 142 | Low | 791417.46 | 0.277 | 2 | 1390173.54 | 15 | 0.81 | 1.56
P004 | Electronics | SUP002 | 2025-06 | 2025-02-10 | 2462071.72 | 2181591 | -280480.72 | 280480.72 | 0 | 2025-06-28 | 3 | 2739902.49 | -277830.77 | DOWN | 0.1128 | 138 | Low | 722605.27 | 0.291 | 0 | 1458985.73 | 15 | 0.81 | 1.56
P004 | Electronics | SUP002 | 2025-06 | 2025-02-21 | 2337310.74 | 2181591 | -155719.74 | 155719.74 | 0 | 2025-06-28 | 4 | 2462071.72 | -124760.98 | DOWN | 0.0534 | 127 | Low | 751146.35 | 0.33 | 3 | 1430444.65 | 15 | 0.81 | 1.56
P004 | Electronics | SUP002 | 2025-06 | 2025-03-17 | 2265271.05 | 2181591 | -83680.05 | 83680.05 | 0 | 2025-06-28 | 5 | 2337310.74 | -72039.69 | DOWN | 0.0318 | 103 | Low | 898343.65 | 0.415 | 5 | 1283247.35 | 15 | 0.81 | 1.56
P004 | Electronics | SUP002 | 2025-06 | 2025-04-16 | 2201965.43 | 2181591 | -20374.43 | 20374.43 | 0 | 2025-06-28 | 6 | 2265271.05 | -63305.62 | DOWN | 0.0287 | 73 | Low | 1064090.03 | 0.521 | 1 | 1117500.97 | 15 | 0.81 | 1.56
P004 | Electronics | SUP002 | 2025-07 | 2025-03-13 | 1858169.68 | 1078129 | -780040.68 | 780040.68 | 1 | 2025-07-28 | 1 |  |  |  |  | 137 | Low | 534881.5 | 0.271 | 2 | 543247.5 | 10 | 1.72 | 1
P004 | Electronics | SUP002 | 2025-07 | 2025-04-03 | 1453785.37 | 1078129 | -375656.37 | 375656.37 | 1 | 2025-07-28 | 2 | 1858169.68 | -404384.31 | DOWN | 0.2782 | 116 | Low | 500857 | 0.339 | 1 | 577272 | 10 | 1.72 | 1
P004 | Electronics | SUP002 | 2025-07 | 2025-06-06 | 1258021.25 | 1078129 | -179892.25 | 179892.25 | 0 | 2025-07-28 | 3 | 1453785.37 | -195764.12 | DOWN | 0.1556 | 52 | Low | 650451.25 | 0.548 | 4 | 427677.75 | 10 | 1.72 | 1
P004 | Mechanical | SUP002 | 2025-08 | 2025-03-15 | 1448058.37 | 1155597 | -292461.37 | 292461.37 | 1 | 2025-08-28 | 1 |  |  |  |  | 166 | Low | 250713.98 | 0.182 | 4 | 904883.02 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP002 | 2025-08 | 2025-04-22 | 1284220.44 | 1155597 | -128623.44 | 128623.44 | 0 | 2025-08-28 | 2 | 1448058.37 | -163837.93 | DOWN | 0.1276 | 128 | Low | 403804.85 | 0.309 | 0 | 751792.15 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP002 | 2025-08 | 2025-07-21 | 1218381.09 | 1155597 | -62784.09 | 62784.09 | 0 | 2025-08-28 | 3 | 1284220.44 | -65839.35 | DOWN | 0.054 | 38 | Medium | 797805.84 | 0.612 | 3 | 357791.16 | 13 | 1.45 | 1.13
P004 | Software | SUP002 | 2025-09 | 2025-06-01 | 1415422.33 | 928438 | -486984.33 | 486984.33 | 1 | 2025-09-28 | 1 |  |  |  |  | 119 | Low | 506382.84 | 0.345 | 6 | 422055.16 | 12 | 1.31 | 1.3
P004 | Software | SUP002 | 2025-09 | 2025-06-15 | 1147797.66 | 928438 | -219359.66 | 219359.66 | 1 | 2025-09-28 | 2 | 1415422.33 | -267624.67 | DOWN | 0.2332 | 105 | Low | 470799.25 | 0.393 | 1 | 457638.75 | 12 | 1.31 | 1.3
P004 | Software | SUP002 | 2025-09 | 2025-07-21 | 1019580.18 | 928438 | -91142.18 | 91142.18 | 0 | 2025-09-28 | 3 | 1147797.66 | -128217.48 | DOWN | 0.1258 | 69 | Low | 490651.76 | 0.516 | 5 | 437786.24 | 12 | 1.31 | 1.3
P004 | Software | SUP002 | 2025-09 | 2025-07-31 | 960886.32 | 928438 | -32448.32 | 32448.32 | 0 | 2025-09-28 | 4 | 1019580.18 | -58693.86 | DOWN | 0.0611 | 59 | Medium | 500247.71 | 0.55 | 3 | 428190.29 | 12 | 1.31 | 1.3
P004 | Software | SUP002 | 2025-09 | 2025-09-03 | 948801.85 | 928438 | -20363.85 | 20363.85 | 0 | 2025-09-28 | 5 | 960886.32 | -12084.47 | DOWN | 0.0127 | 25 | High | 582098.08 | 0.667 | 1 | 346339.92 | 12 | 1.31 | 1.3
P004 | Software | SUP002 | 2025-09 | 2025-09-17 | 935627.22 | 928438 | -7189.22 | 7189.22 | 0 | 2025-09-28 | 6 | 948801.85 | -13174.63 | DOWN | 0.0141 | 11 | High | 656015.1 | 0.714 | 3 | 272422.9 | 12 | 1.31 | 1.3
P004 | Services | SUP002 | 2025-10 | 2025-06-25 | 4150158.06 | 2825014 | -1325144.06 | 1325144.06 | 1 | 2025-10-28 | 1 |  |  |  |  | 125 | Low | 1262489.29 | 0.322 | 0 | 1562524.71 | 16 | 1.37 | 1.4
P004 | Services | SUP002 | 2025-10 | 2025-07-07 | 3345991.39 | 2825014 | -520977.39 | 520977.39 | 1 | 2025-10-28 | 2 | 4150158.06 | -804166.67 | DOWN | 0.2403 | 113 | Low | 1132580.72 | 0.363 | 1 | 1692433.28 | 16 | 1.37 | 1.4
P004 | Services | SUP002 | 2025-10 | 2025-10-04 | 3021560.04 | 2825014 | -196546.04 | 196546.04 | 0 | 2025-10-28 | 3 | 3345991.39 | -324431.35 | DOWN | 0.1074 | 24 | Medium | 1951261.71 | 0.665 | 2 | 873752.29 | 16 | 1.37 | 1.4
P004 | Services | SUP002 | 2025-11 | 2025-06-10 | 267033.17 | 174775 | -92258.17 | 92258.17 | 1 | 2025-11-28 | 1 |  |  |  |  | 171 | Low | 44027.76 | 0.174 | 3 | 130747.24 | 7 | 0.59 | 1.31
P004 | Services | SUP002 | 2025-11 | 2025-06-12 | 217121.61 | 174775 | -42346.61 | 42346.61 | 1 | 2025-11-28 | 2 | 267033.17 | -49911.56 | DOWN | 0.2299 | 169 | Low | 42069.28 | 0.181 | 5 | 132705.72 | 7 | 0.59 | 1.31
P004 | Services | SUP002 | 2025-11 | 2025-07-07 | 193579.14 | 174775 | -18804.14 | 18804.14 | 0 | 2025-11-28 | 3 | 217121.61 | -23542.47 | DOWN | 0.1216 | 144 | Low | 53923.39 | 0.269 | 2 | 120851.61 | 7 | 0.59 | 1.31
P004 | Services | SUP002 | 2025-11 | 2025-08-09 | 182651.19 | 174775 | -7876.19 | 7876.19 | 0 | 2025-11-28 | 4 | 193579.14 | -10927.95 | DOWN | 0.0598 | 111 | Low | 65479.65 | 0.386 | 5 | 109295.35 | 7 | 0.59 | 1.31
P004 | Software | SUP002 | 2025-12 | 2025-07-22 | 638033.21 | 397629 | -240404.21 | 240404.21 | 1 | 2025-12-28 | 1 |  |  |  |  | 159 | Low | 133277.26 | 0.213 | 0 | 264351.74 | 9 | 1.11 | 0.94
P004 | Software | SUP002 | 2025-12 | 2025-07-23 | 514074.54 | 397629 | -116445.54 | 116445.54 | 1 | 2025-12-28 | 2 | 638033.21 | -123958.67 | DOWN | 0.2411 | 158 | Low | 119775.68 | 0.217 | 0 | 277853.32 | 9 | 1.11 | 0.94
P004 | Software | SUP002 | 2025-12 | 2025-09-06 | 456318.07 | 397629 | -58689.07 | 58689.07 | 0 | 2025-12-28 | 3 | 514074.54 | -57756.47 | DOWN | 0.1266 | 113 | Low | 173449.76 | 0.374 | 4 | 224179.24 | 9 | 1.11 | 0.94
P004 | Software | SUP002 | 2025-12 | 2025-12-16 | 426248.87 | 397629 | -28619.87 | 28619.87 | 0 | 2025-12-28 | 4 | 456318.07 | -30069.2 | DOWN | 0.0705 | 12 | Medium | 318970.4 | 0.728 | 8 | 78658.6 | 9 | 1.11 | 0.94
P004 | Electronics | SUP022 | 2025-01 | 2024-08-04 | 727399.7 | 497198 | -230201.7 | 230201.7 | 1 | 2025-01-28 | 1 |  |  |  |  | 177 | Low | 83202.06 | 0.11 | 0 | 413995.94 | 9 | 1 | 1.26
P004 | Electronics | SUP022 | 2025-01 | 2024-10-14 | 631734.73 | 497198 | -134536.73 | 134536.73 | 1 | 2025-01-28 | 2 | 727399.7 | -95664.97 | DOWN | 0.1514 | 106 | Low | 174993.16 | 0.285 | 2 | 322204.84 | 9 | 1 | 1.26
P004 | Electronics | SUP022 | 2025-01 | 2024-10-29 | 583504.32 | 497198 | -86306.32 | 86306.32 | 0 | 2025-01-28 | 3 | 631734.73 | -48230.41 | DOWN | 0.0827 | 91 | Low | 174439.62 | 0.323 | 4 | 322758.38 | 9 | 1 | 1.26
P004 | Electronics | SUP022 | 2025-01 | 2024-12-01 | 546605.97 | 497198 | -49407.97 | 49407.97 | 0 | 2025-01-28 | 4 | 583504.32 | -36898.35 | DOWN | 0.0675 | 58 | Low | 223729.03 | 0.405 | 2 | 273468.97 | 9 | 1 | 1.26
P004 | Electronics | SUP022 | 2025-01 | 2025-01-17 | 532049.38 | 497198 | -34851.38 | 34851.38 | 0 | 2025-01-28 | 5 | 546605.97 | -14556.59 | DOWN | 0.0274 | 11 | Medium | 273910.2 | 0.522 | 8 | 223287.8 | 9 | 1 | 1.26
P004 | Logistics | SUP022 | 2025-02 | 2024-10-22 | 2361784.64 | 1518098 | -843686.64 | 843686.64 | 1 | 2025-02-28 | 1 |  |  |  |  | 129 | Low | 505456.97 | 0.221 | 0 | 1012641.03 | 13 | 1.26 | 0.97
P004 | Logistics | SUP022 | 2025-02 | 2024-11-30 | 2006537.29 | 1518098 | -488439.29 | 488439.29 | 1 | 2025-02-28 | 2 | 2361784.64 | -355247.35 | DOWN | 0.177 | 90 | Low | 667452.36 | 0.315 | 5 | 850645.64 | 13 | 1.26 | 0.97
P004 | Logistics | SUP022 | 2025-02 | 2024-12-17 | 1817268.78 | 1518098 | -299170.78 | 299170.78 | 1 | 2025-02-28 | 3 | 2006537.29 | -189268.51 | DOWN | 0.1041 | 73 | Low | 629939.09 | 0.356 | 2 | 888158.91 | 13 | 1.26 | 0.97
P004 | Logistics | SUP022 | 2025-02 | 2025-01-02 | 1700857.68 | 1518098 | -182759.68 | 182759.68 | 0 | 2025-02-28 | 4 | 1817268.78 | -116411.1 | DOWN | 0.0684 | 57 | Low | 641407.74 | 0.395 | 0 | 876690.26 | 13 | 1.26 | 0.97
P004 | Logistics | SUP022 | 2025-02 | 2025-01-11 | 1640303.17 | 1518098 | -122205.17 | 122205.17 | 0 | 2025-02-28 | 5 | 1700857.68 | -60554.51 | DOWN | 0.0369 | 48 | Low | 733980 | 0.417 | 6 | 784118 | 13 | 1.26 | 0.97
P004 | Logistics | SUP022 | 2025-02 | 2025-01-20 | 1601484.44 | 1518098 | -83386.44 | 83386.44 | 0 | 2025-02-28 | 6 | 1640303.17 | -38818.73 | DOWN | 0.0242 | 39 | Low | 699205.97 | 0.439 | 0 | 818892.03 | 13 | 1.26 | 0.97
P004 | Services | SUP022 | 2025-03 | 2024-11-06 | 2284705.31 | 1543833 | -740872.31 | 740872.31 | 1 | 2025-03-28 | 1 |  |  |  |  | 142 | Low | 417176.18 | 0.195 | 0 | 1126656.82 | 11 | 0.73 | 1.3
P004 | Services | SUP022 | 2025-03 | 2024-11-26 | 2004885.1 | 1543833 | -461052.1 | 461052.1 | 1 | 2025-03-28 | 2 | 2284705.31 | -279820.21 | DOWN | 0.1396 | 122 | Low | 471329.01 | 0.245 | 3 | 1072503.99 | 11 | 0.73 | 1.3
P004 | Services | SUP022 | 2025-03 | 2024-12-21 | 1807413.07 | 1543833 | -263580.07 | 263580.07 | 0 | 2025-03-28 | 3 | 2004885.1 | -197472.03 | DOWN | 0.1093 | 97 | Low | 555782.3 | 0.307 | 1 | 988050.7 | 11 | 0.73 | 1.3
P004 | Services | SUP022 | 2025-03 | 2025-01-05 | 1706676.08 | 1543833 | -162843.08 | 162843.08 | 0 | 2025-03-28 | 4 | 1807413.07 | -100736.99 | DOWN | 0.059 | 82 | Low | 578438.6 | 0.345 | 0 | 965394.4 | 11 | 0.73 | 1.3
P004 | Services | SUP022 | 2025-03 | 2025-03-09 | 1658592.91 | 1543833 | -114759.91 | 114759.91 | 0 | 2025-03-28 | 5 | 1706676.08 | -48083.17 | DOWN | 0.029 | 19 | Medium | 803867.92 | 0.503 | 5 | 739965.08 | 11 | 0.73 | 1.3
P004 | Services | SUP022 | 2025-04 | 2024-10-31 | 759659.87 | 375139 | -384520.87 | 384520.87 | 1 | 2025-04-28 | 1 |  |  |  |  | 179 | Low | 72933.69 | 0.102 | 0 | 302205.31 | 15 | 1.69 | 1.47
P004 | Services | SUP022 | 2025-04 | 2024-12-06 | 592639.14 | 375139 | -217500.14 | 217500.14 | 1 | 2025-04-28 | 2 | 759659.87 | -167020.73 | DOWN | 0.2818 | 143 | Low | 101149.89 | 0.178 | 1 | 273989.11 | 15 | 1.69 | 1.47
P004 | Services | SUP022 | 2025-04 | 2025-01-15 | 505524.78 | 375139 | -130385.78 | 130385.78 | 1 | 2025-04-28 | 3 | 592639.14 | -87114.36 | DOWN | 0.1723 | 103 | Low | 141336.23 | 0.27 | 1 | 233802.77 | 15 | 1.69 | 1.47
P004 | Services | SUP022 | 2025-04 | 2025-01-23 | 442734.58 | 375139 | -67595.58 | 67595.58 | 1 | 2025-04-28 | 4 | 505524.78 | -62790.2 | DOWN | 0.1418 | 95 | Low | 124577.19 | 0.289 | 1 | 250561.81 | 15 | 1.69 | 1.47
P004 | Services | SUP022 | 2025-04 | 2025-02-19 | 412116.38 | 375139 | -36977.38 | 36977.38 | 0 | 2025-04-28 | 5 | 442734.58 | -30618.2 | DOWN | 0.0743 | 68 | Low | 142377.34 | 0.351 | 4 | 232761.66 | 15 | 1.69 | 1.47
P004 | Services | SUP022 | 2025-04 | 2025-04-01 | 391215.12 | 375139 | -16076.12 | 16076.12 | 0 | 2025-04-28 | 6 | 412116.38 | -20901.26 | DOWN | 0.0534 | 27 | Low | 187983.33 | 0.446 | 5 | 187155.67 | 15 | 1.69 | 1.47
P004 | Electronics | SUP022 | 2025-05 | 2024-12-18 | 3041329.55 | 1818816 | -1222513.55 | 1222513.55 | 1 | 2025-05-28 | 1 |  |  |  |  | 161 | Low | 417835.14 | 0.147 | 0 | 1400980.86 | 12 | 1.03 | 1.42
P004 | Electronics | SUP022 | 2025-05 | 2025-02-20 | 2552557.66 | 1818816 | -733741.66 | 733741.66 | 1 | 2025-05-28 | 2 | 3041329.55 | -488771.89 | DOWN | 0.1915 | 97 | Low | 781905.59 | 0.306 | 0 | 1036910.41 | 12 | 1.03 | 1.42
P004 | Electronics | SUP022 | 2025-05 | 2025-04-02 | 2261899.02 | 1818816 | -443083.02 | 443083.02 | 1 | 2025-05-28 | 3 | 2552557.66 | -290658.64 | DOWN | 0.1285 | 56 | Low | 922512.44 | 0.409 | 1 | 896303.56 | 12 | 1.03 | 1.42
P004 | Software | SUP022 | 2025-06 | 2025-01-07 | 2563428.87 | 1262079 | -1301349.87 | 1301349.87 | 1 | 2025-06-28 | 1 |  |  |  |  | 172 | Low | 283956.56 | 0.12 | 0 | 978122.44 | 15 | 0.81 | 1.56
P004 | Software | SUP022 | 2025-06 | 2025-03-23 | 2043754.16 | 1262079 | -781675.16 | 781675.16 | 1 | 2025-06-28 | 2 | 2563428.87 | -519674.71 | DOWN | 0.2543 | 97 | Low | 658447.69 | 0.307 | 6 | 603631.31 | 15 | 0.81 | 1.56
P004 | Software | SUP022 | 2025-06 | 2025-04-10 | 1736950.82 | 1262079 | -474871.82 | 474871.82 | 1 | 2025-06-28 | 3 | 2043754.16 | -306803.34 | DOWN | 0.1766 | 79 | Low | 609336.69 | 0.353 | 1 | 652742.31 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP022 | 2025-07 | 2025-03-05 | 983021.07 | 616290 | -366731.07 | 366731.07 | 1 | 2025-07-28 | 1 |  |  |  |  | 145 | Low | 182945.91 | 0.173 | 4 | 433344.09 | 10 | 1.72 | 1
P004 | Mechanical | SUP022 | 2025-07 | 2025-03-09 | 846636.31 | 616290 | -230346.31 | 230346.31 | 1 | 2025-07-28 | 2 | 983021.07 | -136384.76 | DOWN | 0.1611 | 141 | Low | 154967.26 | 0.182 | 0 | 461322.74 | 10 | 1.72 | 1
P004 | Mechanical | SUP022 | 2025-07 | 2025-06-25 | 753474.65 | 616290 | -137184.65 | 137184.65 | 1 | 2025-07-28 | 3 | 846636.31 | -93161.66 | DOWN | 0.1236 | 33 | Low | 316476.76 | 0.43 | 4 | 299813.24 | 10 | 1.72 | 1
P004 | Mechanical | SUP022 | 2025-07 | 2025-06-30 | 699104.94 | 616290 | -82814.94 | 82814.94 | 0 | 2025-07-28 | 4 | 753474.65 | -54369.71 | DOWN | 0.0778 | 28 | Low | 295689.71 | 0.442 | 3 | 320600.29 | 10 | 1.72 | 1
P004 | Mechanical | SUP022 | 2025-07 | 2025-07-06 | 656455.44 | 616290 | -40165.44 | 40165.44 | 0 | 2025-07-28 | 5 | 699104.94 | -42649.5 | DOWN | 0.065 | 22 | Medium | 302611.54 | 0.456 | 2 | 313678.46 | 10 | 1.72 | 1
P004 | Materials | SUP022 | 2025-08 | 2025-03-21 | 1724103.72 | 943394 | -780709.72 | 780709.72 | 1 | 2025-08-28 | 1 |  |  |  |  | 160 | Low | 255695.78 | 0.142 | 1 | 687698.22 | 13 | 1.45 | 1.13
P004 | Materials | SUP022 | 2025-08 | 2025-04-14 | 1417348.25 | 943394 | -473954.25 | 473954.25 | 1 | 2025-08-28 | 2 | 1724103.72 | -306755.47 | DOWN | 0.2164 | 136 | Low | 284787.4 | 0.199 | 2 | 658606.6 | 13 | 1.45 | 1.13
P004 | Materials | SUP022 | 2025-08 | 2025-05-10 | 1226915.69 | 943394 | -283521.69 | 283521.69 | 1 | 2025-08-28 | 3 | 1417348.25 | -190432.56 | DOWN | 0.1552 | 110 | Low | 319947.43 | 0.261 | 3 | 623446.57 | 13 | 1.45 | 1.13
P004 | Materials | SUP022 | 2025-08 | 2025-06-06 | 1116607.01 | 943394 | -173213.01 | 173213.01 | 1 | 2025-08-28 | 4 | 1226915.69 | -110308.68 | DOWN | 0.0988 | 83 | Low | 380204 | 0.325 | 0 | 563190 | 13 | 1.45 | 1.13
P004 | Materials | SUP022 | 2025-08 | 2025-08-12 | 1038572.4 | 943394 | -95178.4 | 95178.4 | 0 | 2025-08-28 | 5 | 1116607.01 | -78034.61 | DOWN | 0.0751 | 16 | Medium | 495342.93 | 0.484 | 5 | 448051.07 | 13 | 1.45 | 1.13
P004 | Electronics | SUP022 | 2025-09 | 2025-04-22 | 2716834.59 | 1649100 | -1067734.59 | 1067734.59 | 1 | 2025-09-28 | 1 |  |  |  |  | 159 | Low | 369953.44 | 0.147 | 2 | 1279146.56 | 12 | 1.31 | 1.3
P004 | Electronics | SUP022 | 2025-09 | 2025-04-28 | 2277148.82 | 1649100 | -628048.82 | 628048.82 | 1 | 2025-09-28 | 2 | 2716834.59 | -439685.77 | DOWN | 0.1931 | 153 | Low | 342339.64 | 0.161 | 0 | 1306760.36 | 12 | 1.31 | 1.3
P004 | Electronics | SUP022 | 2025-09 | 2025-05-13 | 2046800.44 | 1649100 | -397700.44 | 397700.44 | 1 | 2025-09-28 | 3 | 2277148.82 | -230348.38 | DOWN | 0.1125 | 138 | Low | 419468.25 | 0.198 | 2 | 1229631.75 | 12 | 1.31 | 1.3
P004 | Electronics | SUP022 | 2025-09 | 2025-05-15 | 1896137.55 | 1649100 | -247037.55 | 247037.55 | 0 | 2025-09-28 | 4 | 2046800.44 | -150662.89 | DOWN | 0.0795 | 136 | Low | 390496.27 | 0.202 | 4 | 1258603.73 | 12 | 1.31 | 1.3
P004 | Electronics | SUP022 | 2025-09 | 2025-06-10 | 1802144.2 | 1649100 | -153044.2 | 153044.2 | 0 | 2025-09-28 | 5 | 1896137.55 | -93993.35 | DOWN | 0.0522 | 110 | Low | 446585.4 | 0.265 | 2 | 1202514.6 | 12 | 1.31 | 1.3
P004 | Electronics | SUP022 | 2025-09 | 2025-08-26 | 1754382.11 | 1649100 | -105282.11 | 105282.11 | 0 | 2025-09-28 | 6 | 1802144.2 | -47762.09 | DOWN | 0.0272 | 33 | Medium | 849472.87 | 0.451 | 4 | 799627.13 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP022 | 2025-10 | 2025-05-17 | 816590.72 | 566852 | -249738.72 | 249738.72 | 1 | 2025-10-28 | 1 |  |  |  |  | 164 | Low | 113527.82 | 0.134 | 0 | 453324.18 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP022 | 2025-10 | 2025-06-17 | 723746.25 | 566852 | -156894.25 | 156894.25 | 1 | 2025-10-28 | 2 | 816590.72 | -92844.47 | DOWN | 0.1283 | 133 | Low | 146055.03 | 0.208 | 0 | 420796.97 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP022 | 2025-10 | 2025-07-14 | 668487.88 | 566852 | -101635.88 | 101635.88 | 1 | 2025-10-28 | 3 | 723746.25 | -55258.37 | DOWN | 0.0827 | 106 | Low | 185598.4 | 0.273 | 0 | 381253.6 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP022 | 2025-10 | 2025-10-01 | 622394.59 | 566852 | -55542.59 | 55542.59 | 0 | 2025-10-28 | 4 | 668487.88 | -46093.29 | DOWN | 0.0741 | 27 | Medium | 307383.64 | 0.462 | 1 | 259468.36 | 16 | 1.37 | 1.4
P004 | Services | SUP022 | 2025-11 | 2025-08-15 | 901369.42 | 479893 | -421476.42 | 421476.42 | 1 | 2025-11-28 | 1 |  |  |  |  | 105 | Low | 245975.03 | 0.288 | 0 | 233917.97 | 7 | 0.59 | 1.31
P004 | Services | SUP022 | 2025-11 | 2025-10-03 | 741550.19 | 479893 | -261657.19 | 261657.19 | 1 | 2025-11-28 | 2 | 901369.42 | -159819.23 | DOWN | 0.2155 | 56 | Low | 313480.84 | 0.41 | 3 | 166412.16 | 7 | 0.59 | 1.31
P004 | Services | SUP022 | 2025-11 | 2025-10-29 | 628659.96 | 479893 | -148766.96 | 148766.96 | 1 | 2025-11-28 | 3 | 741550.19 | -112890.23 | DOWN | 0.1796 | 30 | Low | 275066.34 | 0.475 | 4 | 204826.66 | 7 | 0.59 | 1.31
P004 | Electronics | SUP022 | 2025-12 | 2025-07-30 | 1427033.52 | 895332 | -531701.52 | 531701.52 | 1 | 2025-12-28 | 1 |  |  |  |  | 151 | Low | 254469.13 | 0.17 | 2 | 640862.87 | 9 | 1.11 | 0.94
P004 | Electronics | SUP022 | 2025-12 | 2025-08-18 | 1225940.94 | 895332 | -330608.94 | 330608.94 | 1 | 2025-12-28 | 2 | 1427033.52 | -201092.58 | DOWN | 0.164 | 132 | Low | 281512.27 | 0.217 | 0 | 613819.73 | 9 | 1.11 | 0.94
P004 | Electronics | SUP022 | 2025-12 | 2025-08-21 | 1080388.18 | 895332 | -185056.18 | 185056.18 | 1 | 2025-12-28 | 3 | 1225940.94 | -145552.76 | DOWN | 0.1347 | 129 | Low | 232153.82 | 0.225 | 0 | 663178.18 | 9 | 1.11 | 0.94
P004 | Electronics | SUP022 | 2025-12 | 2025-09-20 | 1015158.01 | 895332 | -119826.01 | 119826.01 | 0 | 2025-12-28 | 4 | 1080388.18 | -65230.17 | DOWN | 0.0643 | 99 | Low | 287296.29 | 0.299 | 4 | 608035.71 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP009 | 2025-01 | 2024-08-01 | 309752.94 | 230879 | -78873.94 | 78873.94 | 1 | 2025-01-28 | 1 |  |  |  |  | 180 | Low | 51612.33 | 0.156 | 3 | 179266.67 | 9 | 1 | 1.26
P004 | Mechanical | SUP009 | 2025-01 | 2024-08-31 | 267176.36 | 230879 | -36297.36 | 36297.36 | 0 | 2025-01-28 | 2 | 309752.94 | -42576.58 | DOWN | 0.1594 | 150 | Low | 65483.18 | 0.248 | 1 | 165395.82 | 9 | 1 | 1.26
P004 | Mechanical | SUP009 | 2025-01 | 2024-10-01 | 247250.89 | 230879 | -16371.89 | 16371.89 | 0 | 2025-01-28 | 3 | 267176.36 | -19925.47 | DOWN | 0.0806 | 119 | Low | 91808.22 | 0.358 | 1 | 139070.78 | 9 | 1 | 1.26
P004 | Mechanical | SUP009 | 2025-01 | 2024-10-17 | 238638.28 | 230879 | -7759.28 | 7759.28 | 0 | 2025-01-28 | 4 | 247250.89 | -8612.61 | DOWN | 0.0361 | 103 | Low | 96160.47 | 0.415 | 2 | 134718.53 | 9 | 1 | 1.26
P004 | Mechanical | SUP009 | 2025-01 | 2024-10-20 | 233567.51 | 230879 | -2688.51 | 2688.51 | 0 | 2025-01-28 | 5 | 238638.28 | -5070.77 | DOWN | 0.0217 | 100 | Low | 98742.81 | 0.425 | 3 | 132136.19 | 9 | 1 | 1.26
P004 | Mechanical | SUP009 | 2025-01 | 2024-12-13 | 232287.65 | 230879 | -1408.65 | 1408.65 | 0 | 2025-01-28 | 6 | 233567.51 | -1279.86 | DOWN | 0.0055 | 46 | Medium | 153893.38 | 0.617 | 8 | 76985.62 | 9 | 1 | 1.26
P004 | Logistics | SUP009 | 2025-02 | 2024-10-26 | 2461927.68 | 1648079 | -813848.68 | 813848.68 | 1 | 2025-02-28 | 1 |  |  |  |  | 125 | Low | 820671.4 | 0.327 | 3 | 827407.6 | 13 | 1.26 | 0.97
P004 | Logistics | SUP009 | 2025-02 | 2024-11-15 | 2055923.44 | 1648079 | -407844.44 | 407844.44 | 1 | 2025-02-28 | 2 | 2461927.68 | -406004.24 | DOWN | 0.1975 | 105 | Low | 848867.06 | 0.395 | 1 | 799211.94 | 13 | 1.26 | 0.97
P004 | Logistics | SUP009 | 2025-02 | 2024-12-14 | 1866858.54 | 1648079 | -218779.54 | 218779.54 | 0 | 2025-02-28 | 3 | 2055923.44 | -189064.9 | DOWN | 0.1013 | 76 | Low | 937553.16 | 0.495 | 4 | 710525.84 | 13 | 1.26 | 0.97
P004 | Materials | SUP009 | 2025-03 | 2024-10-23 | 1423244.61 | 1085818 | -337426.61 | 337426.61 | 1 | 2025-03-28 | 1 |  |  |  |  | 156 | Low | 346724.38 | 0.227 | 3 | 739093.62 | 11 | 0.73 | 1.3
P004 | Materials | SUP009 | 2025-03 | 2024-12-31 | 1229527.96 | 1085818 | -143709.96 | 143709.96 | 0 | 2025-03-28 | 2 | 1423244.61 | -193716.65 | DOWN | 0.1576 | 87 | Low | 588435.23 | 0.472 | 4 | 497382.77 | 11 | 0.73 | 1.3
P004 | Materials | SUP009 | 2025-03 | 2025-01-16 | 1145518.84 | 1085818 | -59700.84 | 59700.84 | 0 | 2025-03-28 | 3 | 1229527.96 | -84009.12 | DOWN | 0.0733 | 71 | Low | 631506.43 | 0.528 | 5 | 454311.57 | 11 | 0.73 | 1.3
P004 | Logistics | SUP009 | 2025-04 | 2024-10-30 | 1581095.4 | 820521 | -760574.4 | 760574.4 | 1 | 2025-04-28 | 1 |  |  |  |  | 180 | Low | 221511.09 | 0.144 | 0 | 599009.91 | 15 | 1.69 | 1.47
P004 | Logistics | SUP009 | 2025-04 | 2025-02-24 | 1204610.03 | 820521 | -384089.03 | 384089.03 | 1 | 2025-04-28 | 2 | 1581095.4 | -376485.37 | DOWN | 0.3125 | 63 | Low | 666017.47 | 0.514 | 0 | 154503.53 | 15 | 1.69 | 1.47
P004 | Logistics | SUP009 | 2025-04 | 2025-04-04 | 1011475.94 | 820521 | -190954.94 | 190954.94 | 1 | 2025-04-28 | 3 | 1204610.03 | -193134.09 | DOWN | 0.1909 | 24 | Low | 666313.54 | 0.642 | 3 | 154207.46 | 15 | 1.69 | 1.47
P004 | Services | SUP009 | 2025-05 | 2024-12-06 | 233144.37 | 149671 | -83473.37 | 83473.37 | 1 | 2025-05-28 | 1 |  |  |  |  | 173 | Low | 38398.05 | 0.166 | 1 | 111272.95 | 12 | 1.03 | 1.42
P004 | Services | SUP009 | 2025-05 | 2024-12-25 | 190344.69 | 149671 | -40673.69 | 40673.69 | 1 | 2025-05-28 | 2 | 233144.37 | -42799.68 | DOWN | 0.2249 | 154 | Low | 43396.83 | 0.233 | 0 | 106274.17 | 12 | 1.03 | 1.42
P004 | Services | SUP009 | 2025-05 | 2025-02-08 | 166300.7 | 149671 | -16629.7 | 16629.7 | 0 | 2025-05-28 | 3 | 190344.69 | -24043.99 | DOWN | 0.1446 | 109 | Low | 64127.4 | 0.392 | 1 | 85543.6 | 12 | 1.03 | 1.42
P004 | Services | SUP009 | 2025-05 | 2025-02-25 | 156950.95 | 149671 | -7279.95 | 7279.95 | 0 | 2025-05-28 | 4 | 166300.7 | -9349.75 | DOWN | 0.0596 | 92 | Low | 74468.35 | 0.452 | 5 | 75202.65 | 12 | 1.03 | 1.42
P004 | Services | SUP009 | 2025-05 | 2025-03-12 | 152803.62 | 149671 | -3132.62 | 3132.62 | 0 | 2025-05-28 | 5 | 156950.95 | -4147.33 | DOWN | 0.0271 | 77 | Low | 80016.86 | 0.505 | 6 | 69654.14 | 12 | 1.03 | 1.42
P004 | Services | SUP009 | 2025-05 | 2025-05-04 | 148952.53 | 149671 | 718.47 | 718.47 | 0 | 2025-05-28 | 6 | 152803.62 | -3851.09 | DOWN | 0.0259 | 24 | High | 97539.33 | 0.692 | 3 | 52131.67 | 12 | 1.03 | 1.42
P004 | Software | SUP009 | 2025-06 | 2025-01-14 | 2933233.27 | 1630093 | -1303140.27 | 1303140.27 | 1 | 2025-06-28 | 1 |  |  |  |  | 165 | Low | 588938.62 | 0.195 | 1 | 1041154.38 | 15 | 0.81 | 1.56
P004 | Software | SUP009 | 2025-06 | 2025-02-10 | 2243015.85 | 1630093 | -612922.85 | 612922.85 | 1 | 2025-06-28 | 2 | 2933233.27 | -690217.42 | DOWN | 0.3077 | 138 | Low | 615441.49 | 0.291 | 3 | 1014651.51 | 15 | 0.81 | 1.56
P004 | Software | SUP009 | 2025-06 | 2025-03-15 | 1944731.46 | 1630093 | -314638.46 | 314638.46 | 1 | 2025-06-28 | 3 | 2243015.85 | -298284.39 | DOWN | 0.1534 | 105 | Low | 823338.86 | 0.408 | 0 | 806754.14 | 15 | 0.81 | 1.56
P004 | Software | SUP009 | 2025-06 | 2025-05-12 | 1751956.64 | 1630093 | -121863.64 | 121863.64 | 0 | 2025-06-28 | 4 | 1944731.46 | -192774.82 | DOWN | 0.11 | 47 | Medium | 1137294.86 | 0.613 | 5 | 492798.14 | 15 | 0.81 | 1.56
P004 | Software | SUP009 | 2025-06 | 2025-05-18 | 1699028.78 | 1630093 | -68935.78 | 68935.78 | 0 | 2025-06-28 | 5 | 1751956.64 | -52927.86 | DOWN | 0.0312 | 41 | Medium | 1010424.91 | 0.635 | 7 | 619668.09 | 15 | 0.81 | 1.56
P004 | Logistics | SUP009 | 2025-07 | 2025-02-04 | 1263202.25 | 714384 | -548818.25 | 548818.25 | 1 | 2025-07-28 | 1 |  |  |  |  | 174 | Low | 177414.64 | 0.15 | 0 | 536969.36 | 10 | 1.72 | 1
P004 | Logistics | SUP009 | 2025-07 | 2025-03-01 | 929039.36 | 714384 | -214655.36 | 214655.36 | 1 | 2025-07-28 | 2 | 1263202.25 | -334162.89 | DOWN | 0.3597 | 149 | Low | 217600.68 | 0.232 | 3 | 496783.32 | 10 | 1.72 | 1
P004 | Logistics | SUP009 | 2025-07 | 2025-03-24 | 823943.6 | 714384 | -109559.6 | 109559.6 | 0 | 2025-07-28 | 3 | 929039.36 | -105095.76 | DOWN | 0.1276 | 126 | Low | 262347.56 | 0.307 | 3 | 452036.44 | 10 | 1.72 | 1
P004 | Logistics | SUP009 | 2025-07 | 2025-04-24 | 771743.18 | 714384 | -57359.18 | 57359.18 | 0 | 2025-07-28 | 4 | 823943.6 | -52200.42 | DOWN | 0.0676 | 95 | Low | 315855.58 | 0.408 | 4 | 398528.42 | 10 | 1.72 | 1
P004 | Logistics | SUP009 | 2025-07 | 2025-06-16 | 728232.63 | 714384 | -13848.63 | 13848.63 | 0 | 2025-07-28 | 5 | 771743.18 | -43510.55 | DOWN | 0.0597 | 42 | Medium | 444201.78 | 0.581 | 1 | 270182.22 | 10 | 1.72 | 1
P004 | Logistics | SUP009 | 2025-08 | 2025-03-04 | 1326606.3 | 712589 | -614017.3 | 614017.3 | 1 | 2025-08-28 | 1 |  |  |  |  | 177 | Low | 193856.4 | 0.148 | 4 | 518732.6 | 13 | 1.45 | 1.13
P004 | Logistics | SUP009 | 2025-08 | 2025-05-01 | 999371.27 | 712589 | -286782.27 | 286782.27 | 1 | 2025-08-28 | 2 | 1326606.3 | -327235.03 | DOWN | 0.3274 | 119 | Low | 357099.49 | 0.34 | 4 | 355489.51 | 13 | 1.45 | 1.13
P004 | Logistics | SUP009 | 2025-08 | 2025-06-16 | 844858.73 | 712589 | -132269.73 | 132269.73 | 1 | 2025-08-28 | 3 | 999371.27 | -154512.54 | DOWN | 0.1829 | 73 | Low | 437367.92 | 0.494 | 5 | 275221.08 | 13 | 1.45 | 1.13
P004 | Logistics | SUP009 | 2025-08 | 2025-06-16 | 771724.95 | 712589 | -59135.95 | 59135.95 | 0 | 2025-08-28 | 4 | 844858.73 | -73133.78 | DOWN | 0.0948 | 73 | Low | 380995.8 | 0.494 | 1 | 331593.2 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP009 | 2025-09 | 2025-04-12 | 1762983.43 | 1412732 | -350251.43 | 350251.43 | 1 | 2025-09-28 | 1 |  |  |  |  | 169 | Low | 314242.37 | 0.174 | 0 | 1098489.63 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP009 | 2025-09 | 2025-05-07 | 1563684.33 | 1412732 | -150952.33 | 150952.33 | 0 | 2025-09-28 | 2 | 1762983.43 | -199299.1 | DOWN | 0.1275 | 144 | Low | 422533.25 | 0.26 | 2 | 990198.75 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP009 | 2025-09 | 2025-06-24 | 1486555.1 | 1412732 | -73823.1 | 73823.1 | 0 | 2025-09-28 | 3 | 1563684.33 | -77129.23 | DOWN | 0.0519 | 96 | Low | 653739.61 | 0.424 | 2 | 758992.39 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP009 | 2025-09 | 2025-07-04 | 1437580.46 | 1412732 | -24848.46 | 24848.46 | 0 | 2025-09-28 | 4 | 1486555.1 | -48974.64 | DOWN | 0.0341 | 86 | Low | 669480.73 | 0.458 | 3 | 743251.27 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP009 | 2025-09 | 2025-09-13 | 1431005.63 | 1412732 | -18273.63 | 18273.63 | 0 | 2025-09-28 | 5 | 1437580.46 | -6574.83 | DOWN | 0.0046 | 15 | High | 999128.91 | 0.701 | 5 | 413603.09 | 12 | 1.31 | 1.3
P004 | Electronics | SUP009 | 2025-10 | 2025-06-18 | 1931931.96 | 1435088 | -496843.96 | 496843.96 | 1 | 2025-10-28 | 1 |  |  |  |  | 132 | Low | 536332.52 | 0.299 | 1 | 898755.48 | 16 | 1.37 | 1.4
P004 | Electronics | SUP009 | 2025-10 | 2025-06-29 | 1626769.27 | 1435088 | -191681.27 | 191681.27 | 0 | 2025-10-28 | 2 | 1931931.96 | -305162.69 | DOWN | 0.1876 | 121 | Low | 561711.59 | 0.336 | 1 | 873376.41 | 16 | 1.37 | 1.4
P004 | Electronics | SUP009 | 2025-10 | 2025-08-17 | 1539769.91 | 1435088 | -104681.91 | 104681.91 | 0 | 2025-10-28 | 3 | 1626769.27 | -86999.36 | DOWN | 0.0565 | 72 | Low | 739859.59 | 0.502 | 3 | 695228.41 | 16 | 1.37 | 1.4
P004 | Electronics | SUP009 | 2025-10 | 2025-09-08 | 1470146.46 | 1435088 | -35058.46 | 35058.46 | 0 | 2025-10-28 | 4 | 1539769.91 | -69623.45 | DOWN | 0.0474 | 50 | Medium | 824475.54 | 0.577 | 2 | 610612.46 | 16 | 1.37 | 1.4
P004 | Software | SUP009 | 2025-11 | 2025-06-18 | 2651737.18 | 1754844 | -896893.18 | 896893.18 | 1 | 2025-11-28 | 1 |  |  |  |  | 163 | Low | 520363.5 | 0.202 | 1 | 1234480.5 | 7 | 0.59 | 1.31
P004 | Software | SUP009 | 2025-11 | 2025-08-06 | 2129582.09 | 1754844 | -374738.09 | 374738.09 | 1 | 2025-11-28 | 2 | 2651737.18 | -522155.09 | DOWN | 0.2452 | 114 | Low | 815705.2 | 0.376 | 4 | 939138.8 | 7 | 0.59 | 1.31
P004 | Software | SUP009 | 2025-11 | 2025-08-10 | 1904697.74 | 1754844 | -149853.74 | 149853.74 | 0 | 2025-11-28 | 3 | 2129582.09 | -224884.35 | DOWN | 0.1181 | 110 | Low | 773539.37 | 0.39 | 0 | 981304.63 | 7 | 0.59 | 1.31
P004 | Software | SUP009 | 2025-11 | 2025-08-25 | 1805544.62 | 1754844 | -50700.62 | 50700.62 | 0 | 2025-11-28 | 4 | 1904697.74 | -99153.12 | DOWN | 0.0549 | 95 | Low | 842916.47 | 0.443 | 4 | 911927.53 | 7 | 0.59 | 1.31
P004 | Software | SUP009 | 2025-11 | 2025-09-14 | 1777383.41 | 1754844 | -22539.41 | 22539.41 | 0 | 2025-11-28 | 5 | 1805544.62 | -28161.21 | DOWN | 0.0158 | 75 | Low | 879895.48 | 0.514 | 1 | 874948.52 | 7 | 0.59 | 1.31
P004 | Services | SUP009 | 2025-12 | 2025-07-28 | 2194272.89 | 1423895 | -770377.89 | 770377.89 | 1 | 2025-12-28 | 1 |  |  |  |  | 153 | Low | 473462.48 | 0.234 | 0 | 950432.52 | 9 | 1.11 | 0.94
P004 | Services | SUP009 | 2025-12 | 2025-10-10 | 1777337.56 | 1423895 | -353442.56 | 353442.56 | 1 | 2025-12-28 | 2 | 2194272.89 | -416935.33 | DOWN | 0.2346 | 79 | Low | 917701.16 | 0.493 | 1 | 506193.84 | 9 | 1.11 | 0.94
P004 | Services | SUP009 | 2025-12 | 2025-10-15 | 1586064.06 | 1423895 | -162169.06 | 162169.06 | 0 | 2025-12-28 | 3 | 1777337.56 | -191273.5 | DOWN | 0.1206 | 74 | Low | 827341.09 | 0.511 | 2 | 596553.91 | 9 | 1.11 | 0.94
P004 | Services | SUP009 | 2025-12 | 2025-12-04 | 1495912.55 | 1423895 | -72017.55 | 72017.55 | 0 | 2025-12-28 | 4 | 1586064.06 | -90151.51 | DOWN | 0.0603 | 24 | Medium | 1003407.86 | 0.686 | 6 | 420487.14 | 9 | 1.11 | 0.94
P004 | Software | SUP003 | 2025-01 | 2024-09-18 | 1189673.86 | 563341 | -626332.86 | 626332.86 | 1 | 2025-01-28 | 1 |  |  |  |  | 132 | Low | 229511.81 | 0.2 | 0 | 333829.19 | 9 | 1 | 1.26
P004 | Software | SUP003 | 2025-01 | 2024-09-26 | 1034021.03 | 563341 | -470680.03 | 470680.03 | 1 | 2025-01-28 | 2 | 1189673.86 | -155652.83 | DOWN | 0.1505 | 124 | Low | 223536.17 | 0.218 | 4 | 339804.83 | 9 | 1 | 1.26
P004 | Software | SUP003 | 2025-01 | 2024-11-12 | 911271.81 | 563341 | -347930.81 | 347930.81 | 1 | 2025-01-28 | 3 | 1034021.03 | -122749.22 | DOWN | 0.1347 | 77 | Low | 308171.95 | 0.325 | 0 | 255169.05 | 9 | 1 | 1.26
P004 | Software | SUP003 | 2025-01 | 2024-11-30 | 823474.22 | 563341 | -260133.22 | 260133.22 | 1 | 2025-01-28 | 4 | 911271.81 | -87797.59 | DOWN | 0.1066 | 59 | Low | 283281.06 | 0.366 | 6 | 280059.94 | 9 | 1 | 1.26
P004 | Software | SUP003 | 2025-01 | 2024-12-20 | 770753.1 | 563341 | -207412.1 | 207412.1 | 1 | 2025-01-28 | 5 | 823474.22 | -52721.12 | DOWN | 0.0684 | 39 | Low | 329326.67 | 0.411 | 3 | 234014.33 | 9 | 1 | 1.26
P004 | Software | SUP003 | 2025-01 | 2025-01-14 | 731688 | 563341 | -168347 | 168347 | 1 | 2025-01-28 | 6 | 770753.1 | -39065.1 | DOWN | 0.0534 | 14 | Low | 345917.4 | 0.468 | 3 | 217423.6 | 9 | 1 | 1.26
P004 | Logistics | SUP003 | 2025-02 | 2024-10-11 | 1503759.42 | 740280 | -763479.42 | 763479.42 | 1 | 2025-02-28 | 1 |  |  |  |  | 140 | Low | 270165.79 | 0.176 | 3 | 470114.21 | 13 | 1.26 | 0.97
P004 | Logistics | SUP003 | 2025-02 | 2024-10-25 | 1301284.38 | 740280 | -561004.38 | 561004.38 | 1 | 2025-02-28 | 2 | 1503759.42 | -202475.04 | DOWN | 0.1556 | 126 | Low | 254585.89 | 0.207 | 2 | 485694.11 | 13 | 1.26 | 0.97
P004 | Logistics | SUP003 | 2025-02 | 2024-11-08 | 1138476.91 | 740280 | -398196.91 | 398196.91 | 1 | 2025-02-28 | 3 | 1301284.38 | -162807.47 | DOWN | 0.143 | 112 | Low | 256399.98 | 0.238 | 0 | 483880.02 | 13 | 1.26 | 0.97
P004 | Logistics | SUP003 | 2025-02 | 2024-12-05 | 1033991.25 | 740280 | -293711.25 | 293711.25 | 1 | 2025-02-28 | 4 | 1138476.91 | -104485.66 | DOWN | 0.1011 | 85 | Low | 322258.4 | 0.298 | 0 | 418021.6 | 13 | 1.26 | 0.97
P004 | Logistics | SUP003 | 2025-02 | 2024-12-29 | 968702.95 | 740280 | -228422.95 | 228422.95 | 1 | 2025-02-28 | 5 | 1033991.25 | -65288.3 | DOWN | 0.0674 | 61 | Low | 363301.39 | 0.35 | 3 | 376978.61 | 13 | 1.26 | 0.97
P004 | Logistics | SUP003 | 2025-02 | 2025-01-19 | 911805.08 | 740280 | -171525.08 | 171525.08 | 1 | 2025-02-28 | 6 | 968702.95 | -56897.87 | DOWN | 0.0624 | 40 | Low | 377775.42 | 0.397 | 3 | 362504.58 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP003 | 2025-03 | 2024-11-07 | 1103188.56 | 635368 | -467820.56 | 467820.56 | 1 | 2025-03-28 | 1 |  |  |  |  | 141 | Low | 213435.23 | 0.18 | 1 | 421932.77 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP003 | 2025-03 | 2024-11-29 | 985908.9 | 635368 | -350540.9 | 350540.9 | 1 | 2025-03-28 | 2 | 1103188.56 | -117279.66 | DOWN | 0.119 | 119 | Low | 234048.31 | 0.23 | 4 | 401319.69 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP003 | 2025-03 | 2025-01-03 | 902060.26 | 635368 | -266692.26 | 266692.26 | 1 | 2025-03-28 | 3 | 985908.9 | -83848.64 | DOWN | 0.093 | 84 | Low | 265929.26 | 0.309 | 4 | 369438.74 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP003 | 2025-03 | 2025-01-22 | 831983.12 | 635368 | -196615.12 | 196615.12 | 1 | 2025-03-28 | 4 | 902060.26 | -70077.14 | DOWN | 0.0842 | 65 | Low | 307088.7 | 0.352 | 2 | 328279.3 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP003 | 2025-03 | 2025-02-09 | 783268.64 | 635368 | -147900.64 | 147900.64 | 1 | 2025-03-28 | 5 | 831983.12 | -48714.48 | DOWN | 0.0622 | 47 | Low | 298324.21 | 0.393 | 3 | 337043.79 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP003 | 2025-03 | 2025-02-10 | 742840.39 | 635368 | -107472.39 | 107472.39 | 0 | 2025-03-28 | 6 | 783268.64 | -40428.25 | DOWN | 0.0544 | 46 | Low | 277590.32 | 0.395 | 6 | 357777.68 | 11 | 0.73 | 1.3
P004 | Electronics | SUP003 | 2025-04 | 2025-01-02 | 2862340.44 | 1388055 | -1474285.44 | 1474285.44 | 1 | 2025-04-28 | 1 |  |  |  |  | 116 | Low | 659842.97 | 0.218 | 1 | 728212.03 | 15 | 1.69 | 1.47
P004 | Electronics | SUP003 | 2025-04 | 2025-02-06 | 2492048.58 | 1388055 | -1103993.58 | 1103993.58 | 1 | 2025-04-28 | 2 | 2862340.44 | -370291.86 | DOWN | 0.1486 | 81 | Low | 670737.31 | 0.292 | 1 | 717317.69 | 15 | 1.69 | 1.47
P004 | Electronics | SUP003 | 2025-04 | 2025-03-11 | 2225700.9 | 1388055 | -837645.9 | 837645.9 | 1 | 2025-04-28 | 3 | 2492048.58 | -266347.68 | DOWN | 0.1197 | 48 | Low | 772413.49 | 0.361 | 1 | 615641.51 | 15 | 1.69 | 1.47
P004 | Electronics | SUP003 | 2025-04 | 2025-04-11 | 2062850.23 | 1388055 | -674795.23 | 674795.23 | 1 | 2025-04-28 | 4 | 2225700.9 | -162850.67 | DOWN | 0.0789 | 17 | Low | 925899.08 | 0.426 | 3 | 462155.92 | 15 | 1.69 | 1.47
P004 | Electronics | SUP003 | 2025-04 | 2025-04-14 | 1876048.06 | 1388055 | -487993.06 | 487993.06 | 1 | 2025-04-28 | 5 | 2062850.23 | -186802.17 | DOWN | 0.0996 | 14 | Low | 874830.14 | 0.432 | 1 | 513224.86 | 15 | 1.69 | 1.47
P004 | Electronics | SUP003 | 2025-05 | 2025-02-20 | 781420.79 | 443060 | -338360.79 | 338360.79 | 1 | 2025-05-28 | 1 |  |  |  |  | 97 | Low | 209013.23 | 0.279 | 4 | 234046.77 | 12 | 1.03 | 1.42
P004 | Electronics | SUP003 | 2025-05 | 2025-03-19 | 687438.32 | 443060 | -244378.32 | 244378.32 | 1 | 2025-05-28 | 2 | 781420.79 | -93982.47 | DOWN | 0.1367 | 70 | Low | 234014.67 | 0.34 | 3 | 209045.33 | 12 | 1.03 | 1.42
P004 | Electronics | SUP003 | 2025-05 | 2025-05-03 | 624549.22 | 443060 | -181489.22 | 181489.22 | 1 | 2025-05-28 | 3 | 687438.32 | -62889.1 | DOWN | 0.1007 | 25 | Low | 267329.26 | 0.442 | 2 | 175730.74 | 12 | 1.03 | 1.42
P004 | Electronics | SUP003 | 2025-06 | 2025-02-06 | 3823913 | 1889227 | -1934686 | 1934686 | 1 | 2025-06-28 | 1 |  |  |  |  | 142 | Low | 667512.23 | 0.177 | 0 | 1221714.77 | 15 | 0.81 | 1.56
P004 | Electronics | SUP003 | 2025-06 | 2025-03-20 | 3354184.93 | 1889227 | -1464957.93 | 1464957.93 | 1 | 2025-06-28 | 2 | 3823913 | -469728.07 | DOWN | 0.14 | 100 | Low | 942897.22 | 0.273 | 0 | 946329.78 | 15 | 0.81 | 1.56
P004 | Electronics | SUP003 | 2025-06 | 2025-04-08 | 2999637.32 | 1889227 | -1110410.32 | 1110410.32 | 1 | 2025-06-28 | 3 | 3354184.93 | -354547.61 | DOWN | 0.1182 | 81 | Low | 941581.19 | 0.316 | 3 | 947645.81 | 15 | 0.81 | 1.56
P004 | Electronics | SUP003 | 2025-06 | 2025-04-21 | 2687439.71 | 1889227 | -798212.71 | 798212.71 | 1 | 2025-06-28 | 4 | 2999637.32 | -312197.61 | DOWN | 0.1162 | 68 | Low | 880883.75 | 0.345 | 2 | 1008343.25 | 15 | 0.81 | 1.56
P004 | Electronics | SUP003 | 2025-06 | 2025-05-18 | 2510188.14 | 1889227 | -620961.14 | 620961.14 | 1 | 2025-06-28 | 5 | 2687439.71 | -177251.57 | DOWN | 0.0706 | 41 | Low | 981606.43 | 0.407 | 3 | 907620.57 | 15 | 0.81 | 1.56
P004 | Electronics | SUP003 | 2025-06 | 2025-05-20 | 2342389.17 | 1889227 | -453162.17 | 453162.17 | 1 | 2025-06-28 | 6 | 2510188.14 | -167798.97 | DOWN | 0.0716 | 39 | Low | 982603.96 | 0.411 | 7 | 906623.04 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP003 | 2025-07 | 2025-02-09 | 1016370.8 | 514064 | -502306.8 | 502306.8 | 1 | 2025-07-28 | 1 |  |  |  |  | 169 | Low | 101851.78 | 0.107 | 0 | 412212.22 | 10 | 1.72 | 1
P004 | Mechanical | SUP003 | 2025-07 | 2025-03-22 | 893565.68 | 514064 | -379501.68 | 379501.68 | 1 | 2025-07-28 | 2 | 1016370.8 | -122805.12 | DOWN | 0.1374 | 128 | Low | 172073.47 | 0.192 | 0 | 341990.53 | 10 | 1.72 | 1
P004 | Mechanical | SUP003 | 2025-07 | 2025-05-21 | 797311.19 | 514064 | -283247.19 | 283247.19 | 1 | 2025-07-28 | 3 | 893565.68 | -96254.49 | DOWN | 0.1207 | 68 | Low | 262580.81 | 0.318 | 0 | 251483.19 | 10 | 1.72 | 1
P004 | Mechanical | SUP003 | 2025-07 | 2025-06-05 | 724190.79 | 514064 | -210126.79 | 210126.79 | 1 | 2025-07-28 | 4 | 797311.19 | -73120.4 | DOWN | 0.101 | 53 | Low | 255434.54 | 0.349 | 3 | 258629.46 | 10 | 1.72 | 1
P004 | Mechanical | SUP003 | 2025-07 | 2025-06-21 | 681850.56 | 514064 | -167786.56 | 167786.56 | 1 | 2025-07-28 | 5 | 724190.79 | -42340.23 | DOWN | 0.0621 | 37 | Low | 250854.65 | 0.383 | 2 | 263209.35 | 10 | 1.72 | 1
P004 | Services | SUP003 | 2025-08 | 2025-04-18 | 2121530.16 | 1081648 | -1039882.16 | 1039882.16 | 1 | 2025-08-28 | 1 |  |  |  |  | 132 | Low | 415299.56 | 0.19 | 0 | 666348.44 | 13 | 1.45 | 1.13
P004 | Services | SUP003 | 2025-08 | 2025-05-12 | 1874449.91 | 1081648 | -792801.91 | 792801.91 | 1 | 2025-08-28 | 2 | 2121530.16 | -247080.25 | DOWN | 0.1318 | 108 | Low | 484409.15 | 0.242 | 5 | 597238.85 | 13 | 1.45 | 1.13
P004 | Services | SUP003 | 2025-08 | 2025-05-14 | 1647294.13 | 1081648 | -565646.13 | 565646.13 | 1 | 2025-08-28 | 3 | 1874449.91 | -227155.78 | DOWN | 0.1379 | 106 | Low | 417549.26 | 0.246 | 3 | 664098.74 | 13 | 1.45 | 1.13
P004 | Services | SUP003 | 2025-08 | 2025-07-10 | 1497720.74 | 1081648 | -416072.74 | 416072.74 | 1 | 2025-08-28 | 4 | 1647294.13 | -149573.39 | DOWN | 0.0999 | 49 | Low | 571902.74 | 0.369 | 0 | 509745.26 | 13 | 1.45 | 1.13
P004 | Services | SUP003 | 2025-08 | 2025-07-22 | 1399350.7 | 1081648 | -317702.7 | 317702.7 | 1 | 2025-08-28 | 5 | 1497720.74 | -98370.04 | DOWN | 0.0703 | 37 | Low | 544358.94 | 0.395 | 4 | 537289.06 | 13 | 1.45 | 1.13
P004 | Services | SUP003 | 2025-08 | 2025-08-14 | 1337738.89 | 1081648 | -256090.89 | 256090.89 | 1 | 2025-08-28 | 6 | 1399350.7 | -61611.81 | DOWN | 0.0461 | 14 | Low | 599390.23 | 0.444 | 0 | 482257.77 | 13 | 1.45 | 1.13
P004 | Services | SUP003 | 2025-09 | 2025-04-27 | 2384165.19 | 1364884 | -1019281.19 | 1019281.19 | 1 | 2025-09-28 | 1 |  |  |  |  | 154 | Low | 332874.66 | 0.145 | 0 | 1032009.34 | 12 | 1.31 | 1.3
P004 | Services | SUP003 | 2025-09 | 2025-05-17 | 2159692.61 | 1364884 | -794808.61 | 794808.61 | 1 | 2025-09-28 | 2 | 2384165.19 | -224472.58 | DOWN | 0.1039 | 134 | Low | 385602.54 | 0.188 | 1 | 979281.46 | 12 | 1.31 | 1.3
P004 | Services | SUP003 | 2025-09 | 2025-08-09 | 1942199.9 | 1364884 | -577315.9 | 577315.9 | 1 | 2025-09-28 | 3 | 2159692.61 | -217492.71 | DOWN | 0.112 | 50 | Low | 717753.41 | 0.373 | 2 | 647130.59 | 12 | 1.31 | 1.3
P004 | Software | SUP003 | 2025-10 | 2025-07-20 | 909441.56 | 398489 | -510952.56 | 510952.56 | 1 | 2025-10-28 | 1 |  |  |  |  | 100 | Low | 236052.35 | 0.261 | 0 | 162436.65 | 16 | 1.37 | 1.4
P004 | Software | SUP003 | 2025-10 | 2025-08-03 | 763969.74 | 398489 | -365480.74 | 365480.74 | 1 | 2025-10-28 | 2 | 909441.56 | -145471.82 | DOWN | 0.1904 | 86 | Low | 209254.46 | 0.292 | 2 | 189234.54 | 16 | 1.37 | 1.4
P004 | Software | SUP003 | 2025-10 | 2025-09-08 | 678287.41 | 398489 | -279798.41 | 279798.41 | 1 | 2025-10-28 | 3 | 763969.74 | -85682.33 | DOWN | 0.1263 | 50 | Low | 231971 | 0.37 | 1 | 166518 | 16 | 1.37 | 1.4
P004 | Software | SUP003 | 2025-10 | 2025-09-25 | 601763.66 | 398489 | -203274.66 | 203274.66 | 1 | 2025-10-28 | 4 | 678287.41 | -76523.75 | DOWN | 0.1272 | 33 | Low | 237006.42 | 0.407 | 0 | 161482.58 | 16 | 1.37 | 1.4
P004 | Electronics | SUP003 | 2025-11 | 2025-08-10 | 1322356.77 | 678653 | -643703.77 | 643703.77 | 1 | 2025-11-28 | 1 |  |  |  |  | 110 | Low | 307183.28 | 0.25 | 0 | 371469.72 | 7 | 0.59 | 1.31
P004 | Electronics | SUP003 | 2025-11 | 2025-08-21 | 1152860.47 | 678653 | -474207.47 | 474207.47 | 1 | 2025-11-28 | 2 | 1322356.77 | -169496.3 | DOWN | 0.147 | 99 | Low | 320905.32 | 0.275 | 5 | 357747.68 | 7 | 0.59 | 1.31
P004 | Electronics | SUP003 | 2025-11 | 2025-08-29 | 1047137.87 | 678653 | -368484.87 | 368484.87 | 1 | 2025-11-28 | 3 | 1152860.47 | -105722.6 | DOWN | 0.101 | 91 | Low | 329751.25 | 0.293 | 4 | 348901.75 | 7 | 0.59 | 1.31
P004 | Electronics | SUP003 | 2025-11 | 2025-10-01 | 965156.82 | 678653 | -286503.82 | 286503.82 | 1 | 2025-11-28 | 4 | 1047137.87 | -81981.05 | DOWN | 0.0849 | 58 | Low | 338961.75 | 0.368 | 0 | 339691.25 | 7 | 0.59 | 1.31
P004 | Services | SUP003 | 2025-12 | 2025-08-30 | 2303423.52 | 1082096 | -1221327.52 | 1221327.52 | 1 | 2025-12-28 | 1 |  |  |  |  | 120 | Low | 515950.89 | 0.224 | 2 | 566145.11 | 9 | 1.11 | 0.94
P004 | Services | SUP003 | 2025-12 | 2025-10-14 | 2001177.63 | 1082096 | -919081.63 | 919081.63 | 1 | 2025-12-28 | 2 | 2303423.52 | -302245.89 | DOWN | 0.151 | 75 | Low | 638962.96 | 0.325 | 2 | 443133.04 | 9 | 1.11 | 0.94
P004 | Services | SUP003 | 2025-12 | 2025-10-19 | 1761510.37 | 1082096 | -679414.37 | 679414.37 | 1 | 2025-12-28 | 3 | 2001177.63 | -239667.26 | DOWN | 0.1361 | 70 | Low | 609476.79 | 0.336 | 3 | 472619.21 | 9 | 1.11 | 0.94
P004 | Services | SUP003 | 2025-12 | 2025-10-24 | 1599157.12 | 1082096 | -517061.12 | 517061.12 | 1 | 2025-12-28 | 4 | 1761510.37 | -162353.25 | DOWN | 0.1015 | 65 | Low | 572016.79 | 0.348 | 0 | 510079.21 | 9 | 1.11 | 0.94
P004 | Software | SUP039 | 2025-01 | 2024-09-12 | 3983743.31 | 2203649 | -1780094.31 | 1780094.31 | 1 | 2025-01-28 | 1 |  |  |  |  | 138 | Low | 1035343.99 | 0.242 | 1 | 1168305.01 | 9 | 1 | 1.26
P004 | Software | SUP039 | 2025-01 | 2024-09-20 | 3199667.64 | 2203649 | -996018.64 | 996018.64 | 1 | 2025-01-28 | 2 | 3983743.31 | -784075.67 | DOWN | 0.245 | 130 | Low | 887570.47 | 0.266 | 2 | 1316078.53 | 9 | 1 | 1.26
P004 | Software | SUP039 | 2025-01 | 2024-09-22 | 2796142.29 | 2203649 | -592493.29 | 592493.29 | 1 | 2025-01-28 | 3 | 3199667.64 | -403525.35 | DOWN | 0.1443 | 128 | Low | 803866.24 | 0.272 | 3 | 1399782.76 | 9 | 1 | 1.26
P004 | Software | SUP039 | 2025-01 | 2024-12-03 | 2561792.47 | 2203649 | -358143.47 | 358143.47 | 0 | 2025-01-28 | 4 | 2796142.29 | -234349.82 | DOWN | 0.0915 | 56 | Medium | 1274358.48 | 0.485 | 6 | 929290.52 | 9 | 1 | 1.26
P004 | Software | SUP039 | 2025-01 | 2024-12-20 | 2424006.14 | 2203649 | -220357.14 | 220357.14 | 0 | 2025-01-28 | 5 | 2561792.47 | -137786.33 | DOWN | 0.0568 | 39 | Medium | 1331190.27 | 0.535 | 5 | 872458.73 | 9 | 1 | 1.26
P004 | Software | SUP039 | 2025-01 | 2025-01-18 | 2331413.73 | 2203649 | -127764.73 | 127764.73 | 0 | 2025-01-28 | 6 | 2424006.14 | -92592.41 | DOWN | 0.0397 | 10 | Medium | 1387058.71 | 0.617 | 4 | 816590.29 | 9 | 1 | 1.26
P004 | Electronics | SUP039 | 2025-02 | 2024-11-01 | 2042227.6 | 1110352 | -931875.6 | 931875.6 | 1 | 2025-02-28 | 1 |  |  |  |  | 119 | Low | 601423.25 | 0.289 | 0 | 508928.75 | 13 | 1.26 | 0.97
P004 | Electronics | SUP039 | 2025-02 | 2024-12-04 | 1601319.08 | 1110352 | -490967.08 | 490967.08 | 1 | 2025-02-28 | 2 | 2042227.6 | -440908.52 | DOWN | 0.2753 | 86 | Low | 619283.72 | 0.384 | 4 | 491068.28 | 13 | 1.26 | 0.97
P004 | Electronics | SUP039 | 2025-02 | 2024-12-14 | 1389290.74 | 1110352 | -278938.74 | 278938.74 | 1 | 2025-02-28 | 3 | 1601319.08 | -212028.34 | DOWN | 0.1526 | 76 | Low | 578571.99 | 0.413 | 2 | 531780.01 | 13 | 1.26 | 0.97
P004 | Electronics | SUP039 | 2025-02 | 2024-12-18 | 1260059 | 1110352 | -149707 | 149707 | 0 | 2025-02-28 | 4 | 1389290.74 | -129231.74 | DOWN | 0.1026 | 72 | Low | 506661.93 | 0.424 | 1 | 603690.07 | 13 | 1.26 | 0.97
P004 | Electronics | SUP039 | 2025-02 | 2025-01-28 | 1190387.9 | 1110352 | -80035.9 | 80035.9 | 0 | 2025-02-28 | 5 | 1260059 | -69671.1 | DOWN | 0.0585 | 31 | Medium | 637530.11 | 0.542 | 2 | 472821.89 | 13 | 1.26 | 0.97
P004 | Electronics | SUP039 | 2025-02 | 2025-02-01 | 1157015.31 | 1110352 | -46663.31 | 46663.31 | 0 | 2025-02-28 | 6 | 1190387.9 | -33372.59 | DOWN | 0.0288 | 27 | Medium | 601343.46 | 0.553 | 6 | 509008.54 | 13 | 1.26 | 0.97
P004 | Software | SUP039 | 2025-03 | 2024-10-08 | 3449058.93 | 2140791 | -1308267.93 | 1308267.93 | 1 | 2025-03-28 | 1 |  |  |  |  | 171 | Low | 467767.31 | 0.145 | 0 | 1673023.69 | 11 | 0.73 | 1.3
P004 | Software | SUP039 | 2025-03 | 2024-10-17 | 2883013.9 | 2140791 | -742222.9 | 742222.9 | 1 | 2025-03-28 | 2 | 3449058.93 | -566045.03 | DOWN | 0.1963 | 162 | Low | 496074.16 | 0.171 | 3 | 1644716.84 | 11 | 0.73 | 1.3
P004 | Software | SUP039 | 2025-03 | 2024-11-22 | 2568800.43 | 2140791 | -428009.43 | 428009.43 | 1 | 2025-03-28 | 3 | 2883013.9 | -314213.47 | DOWN | 0.1223 | 126 | Low | 702936.79 | 0.278 | 4 | 1437854.21 | 11 | 0.73 | 1.3
P004 | Software | SUP039 | 2025-03 | 2025-02-25 | 2379496.16 | 2140791 | -238705.16 | 238705.16 | 0 | 2025-03-28 | 4 | 2568800.43 | -189304.27 | DOWN | 0.0796 | 31 | Medium | 1276308.06 | 0.558 | 4 | 864482.94 | 11 | 0.73 | 1.3
P004 | Services | SUP039 | 2025-04 | 2025-01-23 | 1766768.05 | 1078829 | -687939.05 | 687939.05 | 1 | 2025-04-28 | 1 |  |  |  |  | 95 | Low | 571469.42 | 0.341 | 1 | 507359.58 | 15 | 1.69 | 1.47
P004 | Services | SUP039 | 2025-04 | 2025-02-10 | 1452776.11 | 1078829 | -373947.11 | 373947.11 | 1 | 2025-04-28 | 2 | 1766768.05 | -313991.94 | DOWN | 0.2161 | 77 | Low | 573701.05 | 0.39 | 2 | 505127.95 | 15 | 1.69 | 1.47
P004 | Services | SUP039 | 2025-04 | 2025-03-24 | 1309146.9 | 1078829 | -230317.9 | 230317.9 | 1 | 2025-04-28 | 3 | 1452776.11 | -143629.21 | DOWN | 0.1097 | 35 | Medium | 711698.62 | 0.505 | 5 | 367130.38 | 15 | 1.69 | 1.47
P004 | Logistics | SUP039 | 2025-05 | 2024-12-03 | 840229.17 | 469763 | -370466.17 | 370466.17 | 1 | 2025-05-28 | 1 |  |  |  |  | 176 | Low | 107293.28 | 0.13 | 2 | 362469.72 | 12 | 1.03 | 1.42
P004 | Logistics | SUP039 | 2025-05 | 2025-01-06 | 656564.84 | 469763 | -186801.84 | 186801.84 | 1 | 2025-05-28 | 2 | 840229.17 | -183664.33 | DOWN | 0.2797 | 142 | Low | 142298.14 | 0.23 | 4 | 327464.86 | 12 | 1.03 | 1.42
P004 | Logistics | SUP039 | 2025-05 | 2025-02-10 | 580291.83 | 469763 | -110528.83 | 110528.83 | 1 | 2025-05-28 | 3 | 656564.84 | -76273.01 | DOWN | 0.1314 | 107 | Low | 178198.57 | 0.333 | 3 | 291564.43 | 12 | 1.03 | 1.42
P004 | Logistics | SUP039 | 2025-05 | 2025-02-20 | 537062.4 | 469763 | -67299.4 | 67299.4 | 0 | 2025-05-28 | 4 | 580291.83 | -43229.43 | DOWN | 0.0805 | 97 | Low | 189934.92 | 0.362 | 2 | 279828.08 | 12 | 1.03 | 1.42
P004 | Logistics | SUP039 | 2025-05 | 2025-04-15 | 512011.19 | 469763 | -42248.19 | 42248.19 | 0 | 2025-05-28 | 5 | 537062.4 | -25051.21 | DOWN | 0.0489 | 43 | Medium | 258780.55 | 0.521 | 4 | 210982.45 | 12 | 1.03 | 1.42
P004 | Logistics | SUP039 | 2025-05 | 2025-04-30 | 503364.08 | 469763 | -33601.08 | 33601.08 | 0 | 2025-05-28 | 6 | 512011.19 | -8647.11 | DOWN | 0.0172 | 28 | Medium | 277022.23 | 0.565 | 0 | 192740.77 | 12 | 1.03 | 1.42
P004 | Electronics | SUP039 | 2025-06 | 2025-01-05 | 1500201 | 957320 | -542881 | 542881 | 1 | 2025-06-28 | 1 |  |  |  |  | 174 | Low | 212754.03 | 0.136 | 3 | 744565.97 | 15 | 0.81 | 1.56
P004 | Electronics | SUP039 | 2025-06 | 2025-01-11 | 1241497.4 | 957320 | -284177.4 | 284177.4 | 1 | 2025-06-28 | 2 | 1500201 | -258703.6 | DOWN | 0.2084 | 168 | Low | 178541.53 | 0.154 | 3 | 778778.47 | 15 | 0.81 | 1.56
P004 | Electronics | SUP039 | 2025-06 | 2025-01-31 | 1124604.74 | 957320 | -167284.74 | 167284.74 | 0 | 2025-06-28 | 3 | 1241497.4 | -116892.66 | DOWN | 0.1039 | 148 | Low | 226836.95 | 0.213 | 1 | 730483.05 | 15 | 0.81 | 1.56
P004 | Electronics | SUP039 | 2025-06 | 2025-03-03 | 1045616.92 | 957320 | -88296.92 | 88296.92 | 0 | 2025-06-28 | 4 | 1124604.74 | -78987.82 | DOWN | 0.0755 | 117 | Low | 303589.44 | 0.304 | 0 | 653730.56 | 15 | 0.81 | 1.56
P004 | Software | SUP039 | 2025-07 | 2025-04-12 | 2475584.5 | 1283896 | -1191688.5 | 1191688.5 | 1 | 2025-07-28 | 1 |  |  |  |  | 107 | Low | 774166.86 | 0.307 | 2 | 509729.14 | 10 | 1.72 | 1
P004 | Software | SUP039 | 2025-07 | 2025-05-21 | 1945892.68 | 1283896 | -661996.68 | 661996.68 | 1 | 2025-07-28 | 2 | 2475584.5 | -529691.82 | DOWN | 0.2722 | 68 | Low | 806675.98 | 0.413 | 5 | 477220.02 | 10 | 1.72 | 1
P004 | Software | SUP039 | 2025-07 | 2025-07-07 | 1661344.34 | 1283896 | -377448.34 | 377448.34 | 1 | 2025-07-28 | 3 | 1945892.68 | -284548.34 | DOWN | 0.1713 | 21 | Low | 828279.24 | 0.541 | 5 | 455616.76 | 10 | 1.72 | 1
P004 | Software | SUP039 | 2025-07 | 2025-07-07 | 1504729.97 | 1283896 | -220833.97 | 220833.97 | 0 | 2025-07-28 | 4 | 1661344.34 | -156614.37 | DOWN | 0.1041 | 21 | Medium | 805474.87 | 0.541 | 1 | 478421.13 | 10 | 1.72 | 1
P004 | Mechanical | SUP039 | 2025-08 | 2025-03-14 | 502353.31 | 311885 | -190468.31 | 190468.31 | 1 | 2025-08-28 | 1 |  |  |  |  | 167 | Low | 76348.72 | 0.149 | 1 | 235536.28 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP039 | 2025-08 | 2025-05-08 | 413974.94 | 311885 | -102089.94 | 102089.94 | 1 | 2025-08-28 | 2 | 502353.31 | -88378.37 | DOWN | 0.2135 | 112 | Low | 126247.26 | 0.303 | 3 | 185637.74 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP039 | 2025-08 | 2025-05-19 | 371282.19 | 311885 | -59397.19 | 59397.19 | 1 | 2025-08-28 | 3 | 413974.94 | -42692.75 | DOWN | 0.115 | 101 | Low | 122077.56 | 0.334 | 1 | 189807.44 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP039 | 2025-08 | 2025-05-22 | 342309.94 | 311885 | -30424.94 | 30424.94 | 0 | 2025-08-28 | 4 | 371282.19 | -28972.25 | DOWN | 0.0846 | 98 | Low | 126140.46 | 0.342 | 3 | 185744.54 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP039 | 2025-08 | 2025-08-02 | 324878.69 | 311885 | -12993.69 | 12993.69 | 0 | 2025-08-28 | 5 | 342309.94 | -17431.25 | DOWN | 0.0537 | 26 | Medium | 186393.32 | 0.544 | 5 | 125491.68 | 13 | 1.45 | 1.13
P004 | Materials | SUP039 | 2025-09 | 2025-04-23 | 3353540.81 | 2199753 | -1153787.81 | 1153787.81 | 1 | 2025-09-28 | 1 |  |  |  |  | 158 | Low | 579701.87 | 0.177 | 2 | 1620051.13 | 12 | 1.31 | 1.3
P004 | Materials | SUP039 | 2025-09 | 2025-05-31 | 2808992.55 | 2199753 | -609239.55 | 609239.55 | 1 | 2025-09-28 | 2 | 3353540.81 | -544548.26 | DOWN | 0.1939 | 120 | Low | 837896.5 | 0.285 | 2 | 1361856.5 | 12 | 1.31 | 1.3
P004 | Materials | SUP039 | 2025-09 | 2025-06-05 | 2517181.78 | 2199753 | -317428.78 | 317428.78 | 0 | 2025-09-28 | 3 | 2808992.55 | -291810.77 | DOWN | 0.1159 | 115 | Low | 803487.2 | 0.299 | 3 | 1396265.8 | 12 | 1.31 | 1.3
P004 | Materials | SUP039 | 2025-09 | 2025-06-14 | 2372704.2 | 2199753 | -172951.2 | 172951.2 | 0 | 2025-09-28 | 4 | 2517181.78 | -144477.58 | DOWN | 0.0609 | 106 | Low | 776434.89 | 0.325 | 4 | 1423318.11 | 12 | 1.31 | 1.3
P004 | Materials | SUP039 | 2025-09 | 2025-08-03 | 2278844.76 | 2199753 | -79091.76 | 79091.76 | 0 | 2025-09-28 | 5 | 2372704.2 | -93859.44 | DOWN | 0.0412 | 56 | Medium | 1083924.84 | 0.467 | 7 | 1115828.16 | 12 | 1.31 | 1.3
P004 | Materials | SUP039 | 2025-09 | 2025-08-19 | 2239855.23 | 2199753 | -40102.23 | 40102.23 | 0 | 2025-09-28 | 6 | 2278844.76 | -38989.53 | DOWN | 0.0174 | 40 | Medium | 1223725.74 | 0.513 | 7 | 976027.26 | 12 | 1.31 | 1.3
P004 | Electronics | SUP039 | 2025-10 | 2025-06-09 | 1834260.4 | 1020237 | -814023.4 | 814023.4 | 1 | 2025-10-28 | 1 |  |  |  |  | 141 | Low | 391843.35 | 0.223 | 0 | 628393.65 | 16 | 1.37 | 1.4
P004 | Electronics | SUP039 | 2025-10 | 2025-06-25 | 1463333.65 | 1020237 | -443096.65 | 443096.65 | 1 | 2025-10-28 | 2 | 1834260.4 | -370926.75 | DOWN | 0.2535 | 125 | Low | 372588.28 | 0.269 | 0 | 647648.72 | 16 | 1.37 | 1.4
P004 | Electronics | SUP039 | 2025-10 | 2025-07-03 | 1246729.23 | 1020237 | -226492.23 | 226492.23 | 1 | 2025-10-28 | 3 | 1463333.65 | -216604.42 | DOWN | 0.1737 | 117 | Low | 386117.54 | 0.291 | 5 | 634119.46 | 16 | 1.37 | 1.4
P004 | Electronics | SUP039 | 2025-10 | 2025-07-13 | 1164770.24 | 1020237 | -144533.24 | 144533.24 | 0 | 2025-10-28 | 4 | 1246729.23 | -81958.99 | DOWN | 0.0704 | 107 | Low | 384786.72 | 0.32 | 0 | 635450.28 | 16 | 1.37 | 1.4
P004 | Electronics | SUP039 | 2025-11 | 2025-07-28 | 1014644.58 | 590693 | -423951.58 | 423951.58 | 1 | 2025-11-28 | 1 |  |  |  |  | 123 | Low | 309531.5 | 0.287 | 2 | 281161.5 | 7 | 0.59 | 1.31
P004 | Electronics | SUP039 | 2025-11 | 2025-08-30 | 816414.61 | 590693 | -225721.61 | 225721.61 | 1 | 2025-11-28 | 2 | 1014644.58 | -198229.97 | DOWN | 0.2428 | 90 | Low | 300412.04 | 0.384 | 4 | 290280.96 | 7 | 0.59 | 1.31
P004 | Electronics | SUP039 | 2025-11 | 2025-09-06 | 705271.13 | 590693 | -114578.13 | 114578.13 | 1 | 2025-11-28 | 3 | 816414.61 | -111143.48 | DOWN | 0.1576 | 83 | Low | 302684.3 | 0.405 | 2 | 288008.7 | 7 | 0.59 | 1.31
P004 | Electronics | SUP039 | 2025-11 | 2025-09-22 | 648043.33 | 590693 | -57350.33 | 57350.33 | 0 | 2025-11-28 | 4 | 705271.13 | -57227.8 | DOWN | 0.0883 | 67 | Low | 306298.7 | 0.452 | 4 | 284394.3 | 7 | 0.59 | 1.31
P004 | Electronics | SUP039 | 2025-11 | 2025-09-30 | 625798.48 | 590693 | -35105.48 | 35105.48 | 0 | 2025-11-28 | 5 | 648043.33 | -22244.85 | DOWN | 0.0355 | 59 | Medium | 306694.4 | 0.476 | 4 | 283998.6 | 7 | 0.59 | 1.31
P004 | Logistics | SUP039 | 2025-12 | 2025-09-02 | 2701397.56 | 1337357 | -1364040.56 | 1364040.56 | 1 | 2025-12-28 | 1 |  |  |  |  | 117 | Low | 756019.52 | 0.3 | 1 | 581337.48 | 9 | 1.11 | 0.94
P004 | Logistics | SUP039 | 2025-12 | 2025-11-08 | 2065846.71 | 1337357 | -728489.71 | 728489.71 | 1 | 2025-12-28 | 2 | 2701397.56 | -635550.85 | DOWN | 0.3076 | 50 | Low | 991998.35 | 0.496 | 6 | 345358.65 | 9 | 1.11 | 0.94
P004 | Logistics | SUP039 | 2025-12 | 2025-11-16 | 1716129.4 | 1337357 | -378772.4 | 378772.4 | 1 | 2025-12-28 | 3 | 2065846.71 | -349717.31 | DOWN | 0.2038 | 42 | Low | 859230.81 | 0.519 | 5 | 478126.19 | 9 | 1.11 | 0.94
P004 | Logistics | SUP039 | 2025-12 | 2025-12-11 | 1535593.13 | 1337357 | -198236.13 | 198236.13 | 0 | 2025-12-28 | 4 | 1716129.4 | -180536.27 | DOWN | 0.1176 | 17 | Medium | 964907.68 | 0.592 | 2 | 372449.32 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP017 | 2025-01 | 2024-08-13 | 987490.04 | 678061 | -309429.04 | 309429.04 | 1 | 2025-01-28 | 1 |  |  |  |  | 168 | Low | 153806.23 | 0.154 | 1 | 524254.77 | 9 | 1 | 1.26
P004 | Mechanical | SUP017 | 2025-01 | 2024-08-17 | 849712.75 | 678061 | -171651.75 | 171651.75 | 1 | 2025-01-28 | 2 | 987490.04 | -137777.29 | DOWN | 0.1621 | 164 | Low | 148553.7 | 0.165 | 0 | 529507.3 | 9 | 1 | 1.26
P004 | Mechanical | SUP017 | 2025-01 | 2024-10-03 | 776401.21 | 678061 | -98340.21 | 98340.21 | 0 | 2025-01-28 | 3 | 849712.75 | -73311.54 | DOWN | 0.0944 | 117 | Low | 226514.04 | 0.304 | 2 | 451546.96 | 9 | 1 | 1.26
P004 | Mechanical | SUP017 | 2025-01 | 2024-10-09 | 728185.89 | 678061 | -50124.89 | 50124.89 | 0 | 2025-01-28 | 4 | 776401.21 | -48215.32 | DOWN | 0.0662 | 111 | Low | 239869.63 | 0.322 | 0 | 438191.37 | 9 | 1 | 1.26
P004 | Mechanical | SUP017 | 2025-01 | 2024-11-28 | 705920.93 | 678061 | -27859.93 | 27859.93 | 0 | 2025-01-28 | 5 | 728185.89 | -22264.96 | DOWN | 0.0315 | 61 | Low | 309495.97 | 0.47 | 1 | 368565.03 | 9 | 1 | 1.26
P004 | Mechanical | SUP017 | 2025-01 | 2024-12-27 | 693804.65 | 678061 | -15743.65 | 15743.65 | 0 | 2025-01-28 | 6 | 705920.93 | -12116.28 | DOWN | 0.0175 | 32 | Medium | 371635.72 | 0.555 | 1 | 306425.28 | 9 | 1 | 1.26
P004 | Services | SUP017 | 2025-02 | 2024-09-12 | 1722444.07 | 860891 | -861553.07 | 861553.07 | 1 | 2025-02-28 | 1 |  |  |  |  | 169 | Low | 261556.9 | 0.146 | 1 | 599334.1 | 13 | 1.26 | 0.97
P004 | Services | SUP017 | 2025-02 | 2024-12-23 | 1357239.68 | 860891 | -496348.68 | 496348.68 | 1 | 2025-02-28 | 2 | 1722444.07 | -365204.39 | DOWN | 0.2691 | 67 | Low | 552970.35 | 0.438 | 2 | 307920.65 | 13 | 1.26 | 0.97
P004 | Services | SUP017 | 2025-02 | 2025-01-03 | 1125307.02 | 860891 | -264416.02 | 264416.02 | 1 | 2025-02-28 | 3 | 1357239.68 | -231932.66 | DOWN | 0.2061 | 56 | Low | 518809.39 | 0.47 | 6 | 342081.61 | 13 | 1.26 | 0.97
P004 | Electronics | SUP017 | 2025-03 | 2024-10-18 | 1664856.3 | 957324 | -707532.3 | 707532.3 | 1 | 2025-03-28 | 1 |  |  |  |  | 161 | Low | 279042.3 | 0.174 | 0 | 678281.7 | 11 | 0.73 | 1.3
P004 | Electronics | SUP017 | 2025-03 | 2024-11-24 | 1350597.22 | 957324 | -393273.22 | 393273.22 | 1 | 2025-03-28 | 2 | 1664856.3 | -314259.08 | DOWN | 0.2327 | 124 | Low | 356597.24 | 0.284 | 2 | 600726.76 | 11 | 0.73 | 1.3
P004 | Electronics | SUP017 | 2025-03 | 2024-11-28 | 1178187.6 | 957324 | -220863.6 | 220863.6 | 1 | 2025-03-28 | 3 | 1350597.22 | -172409.62 | DOWN | 0.1463 | 120 | Low | 325114.18 | 0.295 | 1 | 632209.82 | 11 | 0.73 | 1.3
P004 | Electronics | SUP017 | 2025-03 | 2024-12-06 | 1064854.4 | 957324 | -107530.4 | 107530.4 | 0 | 2025-03-28 | 4 | 1178187.6 | -113333.2 | DOWN | 0.1064 | 112 | Low | 352886.89 | 0.319 | 3 | 604437.11 | 11 | 0.73 | 1.3
P004 | Electronics | SUP017 | 2025-03 | 2025-01-28 | 1021977.52 | 957324 | -64653.52 | 64653.52 | 0 | 2025-03-28 | 5 | 1064854.4 | -42876.88 | DOWN | 0.042 | 59 | Medium | 464961.96 | 0.476 | 1 | 492362.04 | 11 | 0.73 | 1.3
P004 | Electronics | SUP017 | 2025-03 | 2025-02-05 | 987429.64 | 957324 | -30105.64 | 30105.64 | 0 | 2025-03-28 | 6 | 1021977.52 | -34547.88 | DOWN | 0.035 | 51 | Medium | 470893.65 | 0.499 | 0 | 486430.35 | 11 | 0.73 | 1.3
P004 | Logistics | SUP017 | 2025-04 | 2024-12-18 | 3004890.14 | 1430299 | -1574591.14 | 1574591.14 | 1 | 2025-04-28 | 1 |  |  |  |  | 131 | Low | 787575.81 | 0.243 | 1 | 642723.19 | 15 | 1.69 | 1.47
P004 | Logistics | SUP017 | 2025-04 | 2024-12-29 | 2304501.47 | 1430299 | -874202.47 | 874202.47 | 1 | 2025-04-28 | 2 | 3004890.14 | -700388.67 | DOWN | 0.3039 | 120 | Low | 630999.35 | 0.273 | 0 | 799299.65 | 15 | 1.69 | 1.47
P004 | Logistics | SUP017 | 2025-04 | 2025-01-23 | 1892177.63 | 1430299 | -461878.63 | 461878.63 | 1 | 2025-04-28 | 3 | 2304501.47 | -412323.84 | DOWN | 0.2179 | 95 | Low | 647922.86 | 0.341 | 2 | 782376.14 | 15 | 1.69 | 1.47
P004 | Logistics | SUP017 | 2025-04 | 2025-01-25 | 1650113.15 | 1430299 | -219814.15 | 219814.15 | 0 | 2025-04-28 | 4 | 1892177.63 | -242064.48 | DOWN | 0.1467 | 93 | Low | 597800 | 0.347 | 3 | 832499 | 15 | 1.69 | 1.47
P004 | Logistics | SUP017 | 2025-04 | 2025-04-01 | 1516882.63 | 1430299 | -86583.63 | 86583.63 | 0 | 2025-04-28 | 5 | 1650113.15 | -133230.52 | DOWN | 0.0878 | 27 | Medium | 794324.78 | 0.527 | 3 | 635974.22 | 15 | 1.69 | 1.47
P004 | Logistics | SUP017 | 2025-04 | 2025-04-10 | 1515460.54 | 1430299 | -85161.54 | 85161.54 | 0 | 2025-04-28 | 6 | 1516882.63 | -1422.09 | DOWN | 0.0009 | 18 | Medium | 844266.69 | 0.551 | 5 | 586032.31 | 15 | 1.69 | 1.47
P004 | Materials | SUP017 | 2025-05 | 2025-02-12 | 3442714.95 | 2138957 | -1303757.95 | 1303757.95 | 1 | 2025-05-28 | 1 |  |  |  |  | 105 | Low | 1217448.02 | 0.339 | 1 | 921508.98 | 12 | 1.03 | 1.42
P004 | Materials | SUP017 | 2025-05 | 2025-02-16 | 2881539.67 | 2138957 | -742582.67 | 742582.67 | 1 | 2025-05-28 | 2 | 3442714.95 | -561175.28 | DOWN | 0.1947 | 101 | Low | 1069365.63 | 0.35 | 3 | 1069591.37 | 12 | 1.03 | 1.42
P004 | Materials | SUP017 | 2025-05 | 2025-03-10 | 2548424.77 | 2138957 | -409467.77 | 409467.77 | 1 | 2025-05-28 | 3 | 2881539.67 | -333114.9 | DOWN | 0.1307 | 79 | Low | 1107830.45 | 0.415 | 2 | 1031126.55 | 12 | 1.03 | 1.42
P004 | Software | SUP017 | 2025-06 | 2025-03-02 | 1223495.4 | 558505 | -664990.4 | 664990.4 | 1 | 2025-06-28 | 1 |  |  |  |  | 118 | Low | 358180.21 | 0.301 | 5 | 200324.79 | 15 | 0.81 | 1.56
P004 | Software | SUP017 | 2025-06 | 2025-03-19 | 930489.72 | 558505 | -371984.72 | 371984.72 | 1 | 2025-06-28 | 2 | 1223495.4 | -293005.68 | DOWN | 0.3149 | 101 | Low | 330787.36 | 0.352 | 0 | 227717.64 | 15 | 0.81 | 1.56
P004 | Software | SUP017 | 2025-06 | 2025-04-25 | 774958.02 | 558505 | -216453.02 | 216453.02 | 1 | 2025-06-28 | 3 | 930489.72 | -155531.7 | DOWN | 0.2007 | 64 | Low | 369055.49 | 0.461 | 5 | 189449.51 | 15 | 0.81 | 1.56
P004 | Software | SUP017 | 2025-07 | 2025-02-10 | 2255283.38 | 1111146 | -1144137.38 | 1144137.38 | 1 | 2025-07-28 | 1 |  |  |  |  | 168 | Low | 344008.63 | 0.141 | 1 | 767137.37 | 10 | 1.72 | 1
P004 | Software | SUP017 | 2025-07 | 2025-03-10 | 1746201.67 | 1111146 | -635055.67 | 635055.67 | 1 | 2025-07-28 | 2 | 2255283.38 | -509081.71 | DOWN | 0.2915 | 140 | Low | 373983.54 | 0.218 | 1 | 737162.46 | 10 | 1.72 | 1
P004 | Software | SUP017 | 2025-07 | 2025-04-11 | 1452327.66 | 1111146 | -341181.66 | 341181.66 | 1 | 2025-07-28 | 3 | 1746201.67 | -293874.01 | DOWN | 0.2023 | 108 | Low | 460117.17 | 0.305 | 3 | 651028.83 | 10 | 1.72 | 1
P004 | Software | SUP017 | 2025-07 | 2025-04-25 | 1331280.65 | 1111146 | -220134.65 | 220134.65 | 1 | 2025-07-28 | 4 | 1452327.66 | -121047.01 | DOWN | 0.0909 | 94 | Low | 428639.44 | 0.343 | 6 | 682506.56 | 10 | 1.72 | 1
P004 | Software | SUP017 | 2025-07 | 2025-04-27 | 1207768.28 | 1111146 | -96622.28 | 96622.28 | 0 | 2025-07-28 | 5 | 1331280.65 | -123512.37 | DOWN | 0.1023 | 92 | Low | 396295.81 | 0.348 | 1 | 714850.19 | 10 | 1.72 | 1
P004 | Software | SUP017 | 2025-07 | 2025-07-01 | 1155665.22 | 1111146 | -44519.22 | 44519.22 | 0 | 2025-07-28 | 6 | 1207768.28 | -52103.06 | DOWN | 0.0451 | 27 | Medium | 573348.69 | 0.525 | 5 | 537797.31 | 10 | 1.72 | 1
P004 | Electronics | SUP017 | 2025-08 | 2025-03-11 | 3076372.04 | 1475912 | -1600460.04 | 1600460.04 | 1 | 2025-08-28 | 1 |  |  |  |  | 170 | Low | 421913.27 | 0.14 | 1 | 1053998.73 | 13 | 1.45 | 1.13
P004 | Electronics | SUP017 | 2025-08 | 2025-03-21 | 2337324.33 | 1475912 | -861412.33 | 861412.33 | 1 | 2025-08-28 | 2 | 3076372.04 | -739047.71 | DOWN | 0.3162 | 160 | Low | 369154.01 | 0.168 | 3 | 1106757.99 | 13 | 1.45 | 1.13
P004 | Electronics | SUP017 | 2025-08 | 2025-04-27 | 1940693.24 | 1475912 | -464781.24 | 464781.24 | 1 | 2025-08-28 | 3 | 2337324.33 | -396631.09 | DOWN | 0.2044 | 123 | Low | 560848.08 | 0.272 | 0 | 915063.92 | 13 | 1.45 | 1.13
P004 | Electronics | SUP017 | 2025-08 | 2025-06-19 | 1717043.2 | 1475912 | -241131.2 | 241131.2 | 0 | 2025-08-28 | 4 | 1940693.24 | -223650.04 | DOWN | 0.1303 | 70 | Low | 675051.21 | 0.42 | 4 | 800860.79 | 13 | 1.45 | 1.13
P004 | Electronics | SUP017 | 2025-08 | 2025-07-14 | 1613338.58 | 1475912 | -137426.58 | 137426.58 | 0 | 2025-08-28 | 5 | 1717043.2 | -103704.62 | DOWN | 0.0643 | 45 | Medium | 737540.61 | 0.491 | 3 | 738371.39 | 13 | 1.45 | 1.13
P004 | Logistics | SUP017 | 2025-09 | 2025-04-08 | 1757465.34 | 844656 | -912809.34 | 912809.34 | 1 | 2025-09-28 | 1 |  |  |  |  | 173 | Low | 229610.12 | 0.134 | 2 | 615045.88 | 12 | 1.31 | 1.3
P004 | Logistics | SUP017 | 2025-09 | 2025-05-12 | 1332189.65 | 844656 | -487533.65 | 487533.65 | 1 | 2025-09-28 | 2 | 1757465.34 | -425275.69 | DOWN | 0.3192 | 139 | Low | 296831.9 | 0.231 | 2 | 547824.1 | 12 | 1.31 | 1.3
P004 | Logistics | SUP017 | 2025-09 | 2025-05-30 | 1098012.49 | 844656 | -253356.49 | 253356.49 | 1 | 2025-09-28 | 3 | 1332189.65 | -234177.16 | DOWN | 0.2133 | 121 | Low | 305707.41 | 0.282 | 4 | 538948.59 | 12 | 1.31 | 1.3
P004 | Logistics | SUP017 | 2025-09 | 2025-07-11 | 976690.59 | 844656 | -132034.59 | 132034.59 | 0 | 2025-09-28 | 4 | 1098012.49 | -121321.9 | DOWN | 0.1242 | 79 | Low | 408808.81 | 0.402 | 4 | 435847.19 | 12 | 1.31 | 1.3
P004 | Logistics | SUP017 | 2025-09 | 2025-07-23 | 907501.72 | 844656 | -62845.72 | 62845.72 | 0 | 2025-09-28 | 5 | 976690.59 | -69188.87 | DOWN | 0.0762 | 67 | Low | 419853.68 | 0.436 | 5 | 424802.32 | 12 | 1.31 | 1.3
P004 | Logistics | SUP017 | 2025-09 | 2025-08-15 | 890207.32 | 844656 | -45551.32 | 45551.32 | 0 | 2025-09-28 | 6 | 907501.72 | -17294.4 | DOWN | 0.0194 | 44 | Medium | 458688.39 | 0.501 | 3 | 385967.61 | 12 | 1.31 | 1.3
P004 | Materials | SUP017 | 2025-10 | 2025-05-12 | 853609.18 | 470005 | -383604.18 | 383604.18 | 1 | 2025-10-28 | 1 |  |  |  |  | 169 | Low | 131127.35 | 0.144 | 0 | 338877.65 | 16 | 1.37 | 1.4
P004 | Materials | SUP017 | 2025-10 | 2025-05-16 | 685887.38 | 470005 | -215882.38 | 215882.38 | 1 | 2025-10-28 | 2 | 853609.18 | -167721.8 | DOWN | 0.2445 | 165 | Low | 104274.66 | 0.156 | 6 | 365730.34 | 16 | 1.37 | 1.4
P004 | Materials | SUP017 | 2025-10 | 2025-05-18 | 588825.34 | 470005 | -118820.34 | 118820.34 | 1 | 2025-10-28 | 3 | 685887.38 | -97062.04 | DOWN | 0.1648 | 163 | Low | 102133.31 | 0.161 | 1 | 367871.69 | 16 | 1.37 | 1.4
P004 | Materials | SUP017 | 2025-10 | 2025-06-28 | 535265.51 | 470005 | -65260.51 | 65260.51 | 0 | 2025-10-28 | 4 | 588825.34 | -53559.83 | DOWN | 0.1001 | 122 | Low | 155673.29 | 0.277 | 0 | 314331.71 | 16 | 1.37 | 1.4
P004 | Materials | SUP017 | 2025-10 | 2025-07-25 | 498981.07 | 470005 | -28976.07 | 28976.07 | 0 | 2025-10-28 | 5 | 535265.51 | -36284.44 | DOWN | 0.0727 | 95 | Low | 185240.71 | 0.354 | 1 | 284764.29 | 16 | 1.37 | 1.4
P004 | Materials | SUP017 | 2025-10 | 2025-07-30 | 487961.35 | 470005 | -17956.35 | 17956.35 | 0 | 2025-10-28 | 6 | 498981.07 | -11019.72 | DOWN | 0.0226 | 90 | Low | 182273.65 | 0.368 | 0 | 287731.35 | 16 | 1.37 | 1.4
P004 | Software | SUP017 | 2025-11 | 2025-07-08 | 2158605.94 | 1257328 | -901277.94 | 901277.94 | 1 | 2025-11-28 | 1 |  |  |  |  | 143 | Low | 494928.96 | 0.227 | 0 | 762399.04 | 7 | 0.59 | 1.31
P004 | Software | SUP017 | 2025-11 | 2025-07-28 | 1734273.59 | 1257328 | -476945.59 | 476945.59 | 1 | 2025-11-28 | 2 | 2158605.94 | -424332.35 | DOWN | 0.2447 | 123 | Low | 527262.96 | 0.287 | 1 | 730065.04 | 7 | 0.59 | 1.31
P004 | Software | SUP017 | 2025-11 | 2025-08-28 | 1498751.84 | 1257328 | -241423.84 | 241423.84 | 1 | 2025-11-28 | 3 | 1734273.59 | -235521.75 | DOWN | 0.1571 | 92 | Low | 561103.44 | 0.378 | 2 | 696224.56 | 7 | 0.59 | 1.31
P004 | Software | SUP017 | 2025-11 | 2025-09-19 | 1395186.28 | 1257328 | -137858.28 | 137858.28 | 0 | 2025-11-28 | 4 | 1498751.84 | -103565.56 | DOWN | 0.0742 | 70 | Low | 641985.64 | 0.443 | 2 | 615342.36 | 7 | 0.59 | 1.31
P004 | Software | SUP017 | 2025-11 | 2025-11-03 | 1325719.28 | 1257328 | -68391.28 | 68391.28 | 0 | 2025-11-28 | 5 | 1395186.28 | -69467 | DOWN | 0.0524 | 25 | Medium | 813075.84 | 0.576 | 2 | 444252.16 | 7 | 0.59 | 1.31
P004 | Software | SUP017 | 2025-12 | 2025-08-08 | 734590.43 | 448465 | -286125.43 | 286125.43 | 1 | 2025-12-28 | 1 |  |  |  |  | 142 | Low | 179587.78 | 0.227 | 3 | 268877.22 | 9 | 1.11 | 0.94
P004 | Software | SUP017 | 2025-12 | 2025-08-12 | 604420.04 | 448465 | -155955.04 | 155955.04 | 1 | 2025-12-28 | 2 | 734590.43 | -130170.39 | DOWN | 0.2154 | 138 | Low | 154119.56 | 0.239 | 0 | 294345.44 | 9 | 1.11 | 0.94
P004 | Software | SUP017 | 2025-12 | 2025-10-06 | 534723.25 | 448465 | -86258.25 | 86258.25 | 1 | 2025-12-28 | 3 | 604420.04 | -69696.79 | DOWN | 0.1303 | 83 | Low | 218932.46 | 0.399 | 1 | 229532.54 | 9 | 1.11 | 0.94
P004 | Electronics | SUP038 | 2025-01 | 2024-08-04 | 1778221.64 | 952629 | -825592.64 | 825592.64 | 1 | 2025-01-28 | 1 |  |  |  |  | 177 | Low | 202056.84 | 0.12 | 0 | 750572.16 | 9 | 1 | 1.26
P004 | Electronics | SUP038 | 2025-01 | 2024-09-06 | 1488110.42 | 952629 | -535481.42 | 535481.42 | 1 | 2025-01-28 | 2 | 1778221.64 | -290111.22 | DOWN | 0.195 | 144 | Low | 322500.04 | 0.207 | 1 | 630128.96 | 9 | 1 | 1.26
P004 | Electronics | SUP038 | 2025-01 | 2024-12-16 | 1293609.43 | 952629 | -340980.43 | 340980.43 | 1 | 2025-01-28 | 3 | 1488110.42 | -194500.99 | DOWN | 0.1504 | 43 | Low | 575009.61 | 0.483 | 0 | 377619.39 | 9 | 1 | 1.26
P004 | Electronics | SUP038 | 2025-01 | 2025-01-07 | 1159592.47 | 952629 | -206963.47 | 206963.47 | 1 | 2025-01-28 | 4 | 1293609.43 | -134016.96 | DOWN | 0.1156 | 21 | Low | 662464.34 | 0.543 | 2 | 290164.66 | 9 | 1 | 1.26
P004 | Electronics | SUP038 | 2025-02 | 2024-09-10 | 2683039.3 | 1381260 | -1301779.3 | 1301779.3 | 1 | 2025-02-28 | 1 |  |  |  |  | 171 | Low | 359105.86 | 0.13 | 2 | 1022154.14 | 13 | 1.26 | 0.97
P004 | Electronics | SUP038 | 2025-02 | 2024-11-10 | 2215546.91 | 1381260 | -834286.91 | 834286.91 | 1 | 2025-02-28 | 2 | 2683039.3 | -467492.39 | DOWN | 0.211 | 110 | Low | 624911.87 | 0.291 | 4 | 756348.13 | 13 | 1.26 | 0.97
P004 | Electronics | SUP038 | 2025-02 | 2024-12-17 | 1894418.62 | 1381260 | -513158.62 | 513158.62 | 1 | 2025-02-28 | 3 | 2215546.91 | -321128.29 | DOWN | 0.1695 | 73 | Low | 681303.31 | 0.389 | 2 | 699956.69 | 13 | 1.26 | 0.97
P004 | Electronics | SUP038 | 2025-02 | 2025-01-17 | 1710643.88 | 1381260 | -329383.88 | 329383.88 | 1 | 2025-02-28 | 4 | 1894418.62 | -183774.74 | DOWN | 0.1074 | 42 | Low | 857095.36 | 0.471 | 5 | 524164.64 | 13 | 1.26 | 0.97
P004 | Electronics | SUP038 | 2025-02 | 2025-01-22 | 1593552.21 | 1381260 | -212292.21 | 212292.21 | 0 | 2025-02-28 | 5 | 1710643.88 | -117091.67 | DOWN | 0.0735 | 37 | Low | 823791.1 | 0.484 | 6 | 557468.9 | 13 | 1.26 | 0.97
P004 | Electronics | SUP038 | 2025-02 | 2025-02-12 | 1508768.89 | 1381260 | -127508.89 | 127508.89 | 0 | 2025-02-28 | 6 | 1593552.21 | -84783.32 | DOWN | 0.0562 | 16 | Low | 781306.57 | 0.54 | 1 | 599953.43 | 13 | 1.26 | 0.97
P004 | Logistics | SUP038 | 2025-03 | 2024-11-06 | 435849.16 | 222656 | -213193.16 | 213193.16 | 1 | 2025-03-28 | 1 |  |  |  |  | 142 | Low | 91004.53 | 0.213 | 2 | 131651.47 | 11 | 0.73 | 1.3
P004 | Logistics | SUP038 | 2025-03 | 2024-11-17 | 358650.36 | 222656 | -135994.36 | 135994.36 | 1 | 2025-03-28 | 2 | 435849.16 | -77198.8 | DOWN | 0.2152 | 131 | Low | 89530.64 | 0.243 | 4 | 133125.36 | 11 | 0.73 | 1.3
P004 | Logistics | SUP038 | 2025-03 | 2025-02-28 | 315553.16 | 222656 | -92897.16 | 92897.16 | 1 | 2025-03-28 | 3 | 358650.36 | -43097.2 | DOWN | 0.1366 | 28 | Low | 164559.48 | 0.524 | 6 | 58096.52 | 11 | 0.73 | 1.3
P004 | Software | SUP038 | 2025-04 | 2024-11-15 | 2223066.62 | 987357 | -1235709.62 | 1235709.62 | 1 | 2025-04-28 | 1 |  |  |  |  | 164 | Low | 334642.86 | 0.141 | 2 | 652714.14 | 15 | 1.69 | 1.47
P004 | Software | SUP038 | 2025-04 | 2024-11-29 | 1818807.56 | 987357 | -831450.56 | 831450.56 | 1 | 2025-04-28 | 2 | 2223066.62 | -404259.06 | DOWN | 0.2223 | 150 | Low | 315679.8 | 0.176 | 1 | 671677.2 | 15 | 1.69 | 1.47
P004 | Software | SUP038 | 2025-04 | 2024-12-10 | 1550603.44 | 987357 | -563246.44 | 563246.44 | 1 | 2025-04-28 | 3 | 1818807.56 | -268204.12 | DOWN | 0.173 | 139 | Low | 300302.3 | 0.204 | 4 | 687054.7 | 15 | 1.69 | 1.47
P004 | Software | SUP038 | 2025-04 | 2025-01-29 | 1351318.47 | 987357 | -363961.47 | 363961.47 | 1 | 2025-04-28 | 4 | 1550603.44 | -199284.97 | DOWN | 0.1475 | 89 | Low | 475121.02 | 0.33 | 6 | 512235.98 | 15 | 1.69 | 1.47
P004 | Software | SUP038 | 2025-05 | 2025-01-24 | 2520003.91 | 1448684 | -1071319.91 | 1071319.91 | 1 | 2025-05-28 | 1 |  |  |  |  | 124 | Low | 674174.92 | 0.261 | 1 | 774509.08 | 12 | 1.03 | 1.42
P004 | Software | SUP038 | 2025-05 | 2025-02-16 | 2179436.17 | 1448684 | -730752.17 | 730752.17 | 1 | 2025-05-28 | 2 | 2520003.91 | -340567.74 | DOWN | 0.1563 | 101 | Low | 726775.98 | 0.323 | 3 | 721908.02 | 12 | 1.03 | 1.42
P004 | Software | SUP038 | 2025-05 | 2025-03-10 | 1935706.21 | 1448684 | -487022.21 | 487022.21 | 1 | 2025-05-28 | 3 | 2179436.17 | -243729.96 | DOWN | 0.1259 | 79 | Low | 710699.88 | 0.383 | 0 | 737984.12 | 12 | 1.03 | 1.42
P004 | Software | SUP038 | 2025-05 | 2025-04-25 | 1760121.38 | 1448684 | -311437.38 | 311437.38 | 1 | 2025-05-28 | 4 | 1935706.21 | -175584.83 | DOWN | 0.0998 | 33 | Low | 963310.31 | 0.508 | 2 | 485373.69 | 12 | 1.03 | 1.42
P004 | Software | SUP038 | 2025-05 | 2025-04-26 | 1650889.15 | 1448684 | -202205.15 | 202205.15 | 0 | 2025-05-28 | 5 | 1760121.38 | -109232.23 | DOWN | 0.0662 | 32 | Low | 840229.11 | 0.511 | 2 | 608454.89 | 12 | 1.03 | 1.42
P004 | Software | SUP038 | 2025-05 | 2025-05-05 | 1583477.41 | 1448684 | -134793.41 | 134793.41 | 0 | 2025-05-28 | 6 | 1650889.15 | -67411.74 | DOWN | 0.0426 | 23 | Low | 898491.07 | 0.535 | 2 | 550192.93 | 12 | 1.03 | 1.42
P004 | Logistics | SUP038 | 2025-06 | 2025-04-03 | 778090.21 | 360104 | -417986.21 | 417986.21 | 1 | 2025-06-28 | 1 |  |  |  |  | 86 | Low | 295019.07 | 0.365 | 3 | 65084.93 | 15 | 0.81 | 1.56
P004 | Logistics | SUP038 | 2025-06 | 2025-05-03 | 621120.96 | 360104 | -261016.96 | 261016.96 | 1 | 2025-06-28 | 2 | 778090.21 | -156969.25 | DOWN | 0.2527 | 56 | Low | 279456.35 | 0.447 | 5 | 80647.65 | 15 | 0.81 | 1.56
P004 | Logistics | SUP038 | 2025-06 | 2025-05-21 | 519839.28 | 360104 | -159735.28 | 159735.28 | 1 | 2025-06-28 | 3 | 621120.96 | -101281.68 | DOWN | 0.1948 | 38 | Low | 244521.41 | 0.496 | 5 | 115582.59 | 15 | 0.81 | 1.56
P004 | Logistics | SUP038 | 2025-06 | 2025-06-16 | 460606.63 | 360104 | -100502.63 | 100502.63 | 1 | 2025-06-28 | 4 | 519839.28 | -59232.65 | DOWN | 0.1286 | 12 | Low | 240727.56 | 0.567 | 4 | 119376.44 | 15 | 0.81 | 1.56
P004 | Logistics | SUP038 | 2025-07 | 2025-01-31 | 215637.95 | 118438 | -97199.95 | 97199.95 | 1 | 2025-07-28 | 1 |  |  |  |  | 178 | Low | 22956.15 | 0.11 | 0 | 95481.85 | 10 | 1.72 | 1
P004 | Logistics | SUP038 | 2025-07 | 2025-04-05 | 175411.49 | 118438 | -56973.49 | 56973.49 | 1 | 2025-07-28 | 2 | 215637.95 | -40226.46 | DOWN | 0.2293 | 114 | Low | 44738.58 | 0.266 | 4 | 73699.42 | 10 | 1.72 | 1
P004 | Logistics | SUP038 | 2025-07 | 2025-04-14 | 151836.91 | 118438 | -33398.91 | 33398.91 | 1 | 2025-07-28 | 3 | 175411.49 | -23574.58 | DOWN | 0.1553 | 105 | Low | 41732.43 | 0.289 | 2 | 76705.57 | 10 | 1.72 | 1
P004 | Software | SUP038 | 2025-08 | 2025-03-27 | 1389076.82 | 823594 | -565482.82 | 565482.82 | 1 | 2025-08-28 | 1 |  |  |  |  | 154 | Low | 238542.79 | 0.171 | 0 | 585051.21 | 13 | 1.45 | 1.13
P004 | Software | SUP038 | 2025-08 | 2025-04-15 | 1190606.36 | 823594 | -367012.36 | 367012.36 | 1 | 2025-08-28 | 2 | 1389076.82 | -198470.46 | DOWN | 0.1667 | 135 | Low | 259915.97 | 0.22 | 0 | 563678.03 | 13 | 1.45 | 1.13
P004 | Software | SUP038 | 2025-08 | 2025-06-10 | 1055157 | 823594 | -231563 | 231563 | 1 | 2025-08-28 | 3 | 1190606.36 | -135449.36 | DOWN | 0.1284 | 79 | Low | 361595.51 | 0.365 | 2 | 461998.49 | 13 | 1.45 | 1.13
P004 | Software | SUP038 | 2025-08 | 2025-07-02 | 974790.85 | 823594 | -151196.85 | 151196.85 | 1 | 2025-08-28 | 4 | 1055157 | -80366.15 | DOWN | 0.0824 | 57 | Low | 425269.68 | 0.422 | 0 | 398324.32 | 13 | 1.45 | 1.13
P004 | Software | SUP038 | 2025-08 | 2025-07-02 | 922575.78 | 823594 | -98981.78 | 98981.78 | 0 | 2025-08-28 | 5 | 974790.85 | -52215.07 | DOWN | 0.0566 | 57 | Low | 392416.83 | 0.422 | 1 | 431177.17 | 13 | 1.45 | 1.13
P004 | Software | SUP038 | 2025-08 | 2025-08-06 | 878883.13 | 823594 | -55289.13 | 55289.13 | 0 | 2025-08-28 | 6 | 922575.78 | -43692.65 | DOWN | 0.0497 | 22 | Low | 430578.74 | 0.512 | 3 | 393015.26 | 13 | 1.45 | 1.13
P004 | Materials | SUP038 | 2025-09 | 2025-04-04 | 3327047.82 | 2153491 | -1173556.82 | 1173556.82 | 1 | 2025-09-28 | 1 |  |  |  |  | 177 | Low | 385345.45 | 0.116 | 0 | 1768145.55 | 12 | 1.31 | 1.3
P004 | Materials | SUP038 | 2025-09 | 2025-04-21 | 2885731.49 | 2153491 | -732240.49 | 732240.49 | 1 | 2025-09-28 | 2 | 3327047.82 | -441316.33 | DOWN | 0.1529 | 160 | Low | 475946.42 | 0.158 | 0 | 1677544.58 | 12 | 1.31 | 1.3
P004 | Materials | SUP038 | 2025-09 | 2025-06-22 | 2630466.28 | 2153491 | -476975.28 | 476975.28 | 1 | 2025-09-28 | 3 | 2885731.49 | -255265.21 | DOWN | 0.097 | 98 | Low | 824228.98 | 0.321 | 2 | 1329262.02 | 12 | 1.31 | 1.3
P004 | Materials | SUP038 | 2025-09 | 2025-08-12 | 2483158.85 | 2153491 | -329667.85 | 329667.85 | 0 | 2025-09-28 | 4 | 2630466.28 | -147307.43 | DOWN | 0.0593 | 47 | Low | 1136517.37 | 0.455 | 2 | 1016973.63 | 12 | 1.31 | 1.3
P004 | Materials | SUP038 | 2025-09 | 2025-08-30 | 2361259.03 | 2153491 | -207768.03 | 207768.03 | 0 | 2025-09-28 | 5 | 2483158.85 | -121899.82 | DOWN | 0.0516 | 29 | Low | 1162165.16 | 0.502 | 6 | 991325.84 | 12 | 1.31 | 1.3
P004 | Materials | SUP038 | 2025-09 | 2025-09-10 | 2282953.82 | 2153491 | -129462.82 | 129462.82 | 0 | 2025-09-28 | 6 | 2361259.03 | -78305.21 | DOWN | 0.0343 | 18 | Low | 1222719.98 | 0.531 | 7 | 930771.02 | 12 | 1.31 | 1.3
P004 | Electronics | SUP038 | 2025-10 | 2025-06-28 | 4148466.23 | 2618103 | -1530363.23 | 1530363.23 | 1 | 2025-10-28 | 1 |  |  |  |  | 122 | Low | 1098891.95 | 0.256 | 1 | 1519211.05 | 16 | 1.37 | 1.4
P004 | Electronics | SUP038 | 2025-10 | 2025-08-31 | 3616401.84 | 2618103 | -998298.84 | 998298.84 | 1 | 2025-10-28 | 2 | 4148466.23 | -532064.39 | DOWN | 0.1471 | 58 | Low | 1651608.62 | 0.423 | 4 | 966494.38 | 16 | 1.37 | 1.4
P004 | Electronics | SUP038 | 2025-10 | 2025-09-22 | 3281463.47 | 2618103 | -663360.47 | 663360.47 | 1 | 2025-10-28 | 3 | 3616401.84 | -334938.37 | DOWN | 0.1021 | 36 | Low | 1494548.83 | 0.48 | 4 | 1123554.17 | 16 | 1.37 | 1.4
P004 | Electronics | SUP038 | 2025-10 | 2025-09-24 | 3063538.51 | 2618103 | -445435.51 | 445435.51 | 0 | 2025-10-28 | 4 | 3281463.47 | -217924.96 | DOWN | 0.0711 | 34 | Low | 1465466.34 | 0.486 | 4 | 1152636.66 | 16 | 1.37 | 1.4
P004 | Electronics | SUP038 | 2025-10 | 2025-10-03 | 2887319.47 | 2618103 | -269216.47 | 269216.47 | 0 | 2025-10-28 | 5 | 3063538.51 | -176219.04 | DOWN | 0.061 | 25 | Low | 1515326.51 | 0.509 | 5 | 1102776.49 | 16 | 1.37 | 1.4
P004 | Electronics | SUP038 | 2025-10 | 2025-10-09 | 2761917.31 | 2618103 | -143814.31 | 143814.31 | 0 | 2025-10-28 | 6 | 2887319.47 | -125402.16 | DOWN | 0.0454 | 19 | Low | 1540013.96 | 0.525 | 3 | 1078089.04 | 16 | 1.37 | 1.4
P004 | Materials | SUP038 | 2025-11 | 2025-06-12 | 618866.71 | 365038 | -253828.71 | 253828.71 | 1 | 2025-11-28 | 1 |  |  |  |  | 169 | Low | 86165.37 | 0.139 | 0 | 278872.63 | 7 | 0.59 | 1.31
P004 | Materials | SUP038 | 2025-11 | 2025-07-24 | 531908.81 | 365038 | -166870.81 | 166870.81 | 1 | 2025-11-28 | 2 | 618866.71 | -86957.9 | DOWN | 0.1635 | 127 | Low | 130394.97 | 0.254 | 1 | 234643.03 | 7 | 0.59 | 1.31
P004 | Materials | SUP038 | 2025-11 | 2025-09-25 | 473305.08 | 365038 | -108267.08 | 108267.08 | 1 | 2025-11-28 | 3 | 531908.81 | -58603.73 | DOWN | 0.1238 | 64 | Low | 201246.52 | 0.425 | 5 | 163791.48 | 7 | 0.59 | 1.31
P004 | Materials | SUP038 | 2025-11 | 2025-10-30 | 437325.97 | 365038 | -72287.97 | 72287.97 | 1 | 2025-11-28 | 4 | 473305.08 | -35979.11 | DOWN | 0.0823 | 29 | Low | 218521.5 | 0.521 | 5 | 146516.5 | 7 | 0.59 | 1.31
P004 | Software | SUP038 | 2025-12 | 2025-07-22 | 3902443.52 | 2671642 | -1230801.52 | 1230801.52 | 1 | 2025-12-28 | 1 |  |  |  |  | 159 | Low | 661747.77 | 0.164 | 3 | 2009894.23 | 9 | 1.11 | 0.94
P004 | Software | SUP038 | 2025-12 | 2025-08-12 | 3533342.83 | 2671642 | -861700.83 | 861700.83 | 1 | 2025-12-28 | 2 | 3902443.52 | -369100.69 | DOWN | 0.1045 | 138 | Low | 817226.85 | 0.221 | 2 | 1854415.15 | 9 | 1.11 | 0.94
P004 | Software | SUP038 | 2025-12 | 2025-09-20 | 3239268.95 | 2671642 | -567626.95 | 567626.95 | 1 | 2025-12-28 | 3 | 3533342.83 | -294073.88 | DOWN | 0.0908 | 99 | Low | 1063968.49 | 0.326 | 3 | 1607673.51 | 9 | 1.11 | 0.94
P004 | Software | SUP038 | 2025-12 | 2025-10-02 | 3009424.09 | 2671642 | -337782.09 | 337782.09 | 0 | 2025-12-28 | 4 | 3239268.95 | -229844.86 | DOWN | 0.0764 | 87 | Low | 1153500.72 | 0.358 | 4 | 1518141.28 | 9 | 1.11 | 0.94
P004 | Software | SUP038 | 2025-12 | 2025-11-23 | 2884958.99 | 2671642 | -213316.99 | 213316.99 | 0 | 2025-12-28 | 5 | 3009424.09 | -124465.1 | DOWN | 0.0431 | 35 | Low | 1528234.56 | 0.498 | 3 | 1143407.44 | 9 | 1.11 | 0.94
P004 | Electronics | SUP029 | 2025-01 | 2024-08-17 | 3219566.34 | 2152691 | -1066875.34 | 1066875.34 | 1 | 2025-01-28 | 1 |  |  |  |  | 164 | Low | 606147.27 | 0.199 | 3 | 1546543.73 | 9 | 1 | 1.26
P004 | Electronics | SUP029 | 2025-01 | 2024-10-01 | 2600821.88 | 2152691 | -448130.88 | 448130.88 | 1 | 2025-01-28 | 2 | 3219566.34 | -618744.46 | DOWN | 0.2379 | 119 | Low | 969228.49 | 0.358 | 5 | 1183462.51 | 9 | 1 | 1.26
P004 | Electronics | SUP029 | 2025-01 | 2024-10-22 | 2335879.13 | 2152691 | -183188.13 | 183188.13 | 0 | 2025-01-28 | 3 | 2600821.88 | -264942.75 | DOWN | 0.1134 | 98 | Low | 984331.27 | 0.433 | 2 | 1168359.73 | 9 | 1 | 1.26
P004 | Electronics | SUP029 | 2025-01 | 2024-11-11 | 2230957.51 | 2152691 | -78266.51 | 78266.51 | 0 | 2025-01-28 | 4 | 2335879.13 | -104921.62 | DOWN | 0.047 | 78 | Low | 1036441.93 | 0.503 | 3 | 1116249.07 | 9 | 1 | 1.26
P004 | Services | SUP029 | 2025-02 | 2024-09-11 | 3282604.98 | 1965701 | -1316903.98 | 1316903.98 | 1 | 2025-02-28 | 1 |  |  |  |  | 170 | Low | 558114.46 | 0.172 | 0 | 1407586.54 | 13 | 1.26 | 0.97
P004 | Services | SUP029 | 2025-02 | 2024-09-12 | 2558259.95 | 1965701 | -592558.95 | 592558.95 | 1 | 2025-02-28 | 2 | 3282604.98 | -724345.03 | DOWN | 0.2831 | 169 | Low | 464252.95 | 0.175 | 0 | 1501448.05 | 13 | 1.26 | 0.97
P004 | Services | SUP029 | 2025-02 | 2025-02-04 | 2200583.25 | 1965701 | -234882.25 | 234882.25 | 0 | 2025-02-28 | 3 | 2558259.95 | -357676.7 | DOWN | 0.1625 | 24 | Low | 1576515.18 | 0.674 | 5 | 389185.82 | 13 | 1.26 | 0.97
P004 | Logistics | SUP029 | 2025-03 | 2024-11-05 | 3633372.06 | 2284509 | -1348863.06 | 1348863.06 | 1 | 2025-03-28 | 1 |  |  |  |  | 143 | Low | 927338.03 | 0.273 | 3 | 1357170.97 | 11 | 0.73 | 1.3
P004 | Logistics | SUP029 | 2025-03 | 2024-12-09 | 2944376.4 | 2284509 | -659867.4 | 659867.4 | 1 | 2025-03-28 | 2 | 3633372.06 | -688995.66 | DOWN | 0.234 | 109 | Low | 1128126.64 | 0.394 | 6 | 1156382.36 | 11 | 0.73 | 1.3
P004 | Logistics | SUP029 | 2025-03 | 2024-12-15 | 2605596.5 | 2284509 | -321087.5 | 321087.5 | 0 | 2025-03-28 | 3 | 2944376.4 | -338779.9 | DOWN | 0.13 | 103 | Low | 1084008.65 | 0.415 | 2 | 1200500.35 | 11 | 0.73 | 1.3
P004 | Logistics | SUP029 | 2025-03 | 2024-12-26 | 2409226.01 | 2284509 | -124717.01 | 124717.01 | 0 | 2025-03-28 | 4 | 2605596.5 | -196370.49 | DOWN | 0.0815 | 92 | Low | 1093228.14 | 0.454 | 0 | 1191280.86 | 11 | 0.73 | 1.3
P004 | Logistics | SUP029 | 2025-03 | 2025-02-27 | 2328785.03 | 2284509 | -44276.03 | 44276.03 | 0 | 2025-03-28 | 5 | 2409226.01 | -80440.98 | DOWN | 0.0345 | 29 | High | 1578956.78 | 0.677 | 5 | 705552.22 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP029 | 2025-04 | 2025-01-05 | 2170683.54 | 1613715 | -556968.54 | 556968.54 | 1 | 2025-04-28 | 1 |  |  |  |  | 113 | Low | 752580.49 | 0.35 | 4 | 861134.51 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP029 | 2025-04 | 2025-01-18 | 1846758.03 | 1613715 | -233043.03 | 233043.03 | 0 | 2025-04-28 | 2 | 2170683.54 | -323925.51 | DOWN | 0.1754 | 100 | Low | 761837.17 | 0.393 | 5 | 851877.83 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP029 | 2025-04 | 2025-02-09 | 1734805.83 | 1613715 | -121090.83 | 121090.83 | 0 | 2025-04-28 | 3 | 1846758.03 | -111952.2 | DOWN | 0.0645 | 78 | Low | 832439.92 | 0.465 | 2 | 781275.08 | 15 | 1.69 | 1.47
P004 | Services | SUP029 | 2025-05 | 2025-02-23 | 743416.62 | 470983 | -272433.62 | 272433.62 | 1 | 2025-05-28 | 1 |  |  |  |  | 94 | Low | 304934.47 | 0.445 | 4 | 166048.53 | 12 | 1.03 | 1.42
P004 | Services | SUP029 | 2025-05 | 2025-03-16 | 591359.19 | 470983 | -120376.19 | 120376.19 | 1 | 2025-05-28 | 2 | 743416.62 | -152057.43 | DOWN | 0.2571 | 73 | Low | 293249.2 | 0.519 | 2 | 177733.8 | 12 | 1.03 | 1.42
P004 | Services | SUP029 | 2025-05 | 2025-03-24 | 522682.76 | 470983 | -51699.76 | 51699.76 | 0 | 2025-05-28 | 3 | 591359.19 | -68676.43 | DOWN | 0.1314 | 65 | Low | 278613.92 | 0.548 | 2 | 192369.08 | 12 | 1.03 | 1.42
P004 | Services | SUP029 | 2025-05 | 2025-04-30 | 498677.9 | 470983 | -27694.9 | 27694.9 | 0 | 2025-05-28 | 4 | 522682.76 | -24004.86 | DOWN | 0.0481 | 28 | High | 359253.52 | 0.678 | 5 | 111729.48 | 12 | 1.03 | 1.42
P004 | Electronics | SUP029 | 2025-06 | 2025-01-10 | 2750812.96 | 1993373 | -757439.96 | 757439.96 | 1 | 2025-06-28 | 1 |  |  |  |  | 169 | Low | 480954.94 | 0.181 | 0 | 1512418.06 | 15 | 0.81 | 1.56
P004 | Electronics | SUP029 | 2025-06 | 2025-03-30 | 2321105.92 | 1993373 | -327732.92 | 327732.92 | 0 | 2025-06-28 | 2 | 2750812.96 | -429707.04 | DOWN | 0.1851 | 90 | Low | 1030153.61 | 0.461 | 4 | 963219.39 | 15 | 0.81 | 1.56
P004 | Electronics | SUP029 | 2025-06 | 2025-05-02 | 2139142.17 | 1993373 | -145769.17 | 145769.17 | 0 | 2025-06-28 | 3 | 2321105.92 | -181963.75 | DOWN | 0.0851 | 57 | Medium | 1324789.95 | 0.578 | 4 | 668583.05 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP029 | 2025-07 | 2025-02-05 | 814503.16 | 556187 | -258316.16 | 258316.16 | 1 | 2025-07-28 | 1 |  |  |  |  | 173 | Low | 130158.87 | 0.153 | 2 | 426028.13 | 10 | 1.72 | 1
P004 | Mechanical | SUP029 | 2025-07 | 2025-03-04 | 661267.53 | 556187 | -105080.53 | 105080.53 | 1 | 2025-07-28 | 2 | 814503.16 | -153235.63 | DOWN | 0.2317 | 146 | Low | 166392.77 | 0.241 | 2 | 389794.23 | 10 | 1.72 | 1
P004 | Mechanical | SUP029 | 2025-07 | 2025-04-14 | 594158.55 | 556187 | -37971.55 | 37971.55 | 0 | 2025-07-28 | 3 | 661267.53 | -67108.98 | DOWN | 0.1129 | 105 | Low | 237243.15 | 0.375 | 1 | 318943.85 | 10 | 1.72 | 1
P004 | Mechanical | SUP029 | 2025-07 | 2025-07-04 | 578591.96 | 556187 | -22404.96 | 22404.96 | 0 | 2025-07-28 | 4 | 594158.55 | -15566.59 | DOWN | 0.0269 | 24 | Medium | 361878.65 | 0.64 | 2 | 194308.35 | 10 | 1.72 | 1
P004 | Mechanical | SUP029 | 2025-08 | 2025-05-24 | 2551946.7 | 1599836 | -952110.7 | 952110.7 | 1 | 2025-08-28 | 1 |  |  |  |  | 96 | Low | 1119761.61 | 0.417 | 4 | 480074.39 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP029 | 2025-08 | 2025-06-11 | 2018765.36 | 1599836 | -418929.36 | 418929.36 | 1 | 2025-08-28 | 2 | 2551946.7 | -533181.34 | DOWN | 0.2641 | 78 | Low | 995111.45 | 0.478 | 3 | 604724.55 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP029 | 2025-08 | 2025-06-25 | 1798895.94 | 1599836 | -199059.94 | 199059.94 | 0 | 2025-08-28 | 3 | 2018765.36 | -219869.42 | DOWN | 0.1222 | 64 | Low | 902347.1 | 0.525 | 8 | 697488.9 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP029 | 2025-08 | 2025-08-17 | 1708850.45 | 1599836 | -109014.45 | 109014.45 | 0 | 2025-08-28 | 4 | 1798895.94 | -90045.49 | DOWN | 0.0527 | 11 | Medium | 1204563.48 | 0.703 | 6 | 395272.52 | 13 | 1.45 | 1.13
P004 | Services | SUP029 | 2025-09 | 2025-04-28 | 2894447.73 | 1934228 | -960219.73 | 960219.73 | 1 | 2025-09-28 | 1 |  |  |  |  | 153 | Low | 708239.41 | 0.229 | 1 | 1225988.59 | 12 | 1.31 | 1.3
P004 | Services | SUP029 | 2025-09 | 2025-05-05 | 2348941.76 | 1934228 | -414713.76 | 414713.76 | 1 | 2025-09-28 | 2 | 2894447.73 | -545505.97 | DOWN | 0.2322 | 146 | Low | 592630.02 | 0.253 | 1 | 1341597.98 | 12 | 1.31 | 1.3
P004 | Services | SUP029 | 2025-09 | 2025-08-29 | 2138829.08 | 1934228 | -204601.08 | 204601.08 | 0 | 2025-09-28 | 3 | 2348941.76 | -210112.68 | DOWN | 0.0982 | 30 | Medium | 1348301.35 | 0.649 | 3 | 585926.65 | 12 | 1.31 | 1.3
P004 | Services | SUP029 | 2025-10 | 2025-06-17 | 3102029.1 | 1818198 | -1283831.1 | 1283831.1 | 1 | 2025-10-28 | 1 |  |  |  |  | 133 | Low | 916324.6 | 0.295 | 3 | 901873.4 | 16 | 1.37 | 1.4
P004 | Services | SUP029 | 2025-10 | 2025-07-01 | 2418966.56 | 1818198 | -600768.56 | 600768.56 | 1 | 2025-10-28 | 2 | 3102029.1 | -683062.54 | DOWN | 0.2824 | 119 | Low | 777914.71 | 0.343 | 2 | 1040283.29 | 16 | 1.37 | 1.4
P004 | Services | SUP029 | 2025-10 | 2025-09-27 | 2091987.8 | 1818198 | -273789.8 | 273789.8 | 0 | 2025-10-28 | 3 | 2418966.56 | -326978.76 | DOWN | 0.1563 | 31 | Low | 1301130.59 | 0.642 | 4 | 517067.41 | 16 | 1.37 | 1.4
P004 | Services | SUP029 | 2025-10 | 2025-10-13 | 1965193.07 | 1818198 | -146995.07 | 146995.07 | 0 | 2025-10-28 | 4 | 2091987.8 | -126794.73 | DOWN | 0.0645 | 15 | Medium | 1285217.84 | 0.696 | 9 | 532980.16 | 16 | 1.37 | 1.4
P004 | Services | SUP029 | 2025-11 | 2025-06-24 | 387254.77 | 252591 | -134663.77 | 134663.77 | 1 | 2025-11-28 | 1 |  |  |  |  | 157 | Low | 88509.99 | 0.223 | 0 | 164081.01 | 7 | 0.59 | 1.31
P004 | Services | SUP029 | 2025-11 | 2025-08-23 | 315785.18 | 252591 | -63194.18 | 63194.18 | 1 | 2025-11-28 | 2 | 387254.77 | -71469.59 | DOWN | 0.2263 | 97 | Low | 126834.56 | 0.436 | 6 | 125756.44 | 7 | 0.59 | 1.31
P004 | Services | SUP029 | 2025-11 | 2025-09-25 | 279276.81 | 252591 | -26685.81 | 26685.81 | 0 | 2025-11-28 | 3 | 315785.18 | -36508.37 | DOWN | 0.1307 | 64 | Low | 163352.78 | 0.553 | 6 | 89238.22 | 7 | 0.59 | 1.31
P004 | Software | SUP029 | 2025-12 | 2025-08-09 | 1636995.21 | 1085517 | -551478.21 | 551478.21 | 1 | 2025-12-28 | 1 |  |  |  |  | 141 | Low | 435452.63 | 0.276 | 0 | 650064.37 | 9 | 1.11 | 0.94
P004 | Software | SUP029 | 2025-12 | 2025-10-18 | 1353005.7 | 1085517 | -267488.7 | 267488.7 | 1 | 2025-12-28 | 2 | 1636995.21 | -283989.51 | DOWN | 0.2099 | 71 | Low | 746705.4 | 0.521 | 7 | 338811.6 | 9 | 1.11 | 0.94
P004 | Software | SUP029 | 2025-12 | 2025-10-25 | 1215028.62 | 1085517 | -129511.62 | 129511.62 | 0 | 2025-12-28 | 3 | 1353005.7 | -137977.08 | DOWN | 0.1136 | 64 | Low | 628108.34 | 0.546 | 8 | 457408.66 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP034 | 2025-01 | 2024-08-20 | 2943295.91 | 2584303 | -358992.91 | 358992.91 | 0 | 2025-01-28 | 1 |  |  |  |  | 161 | Low | 619954.85 | 0.209 | 1 | 1964348.15 | 9 | 1 | 1.26
P004 | Mechanical | SUP034 | 2025-01 | 2024-10-09 | 2730387.5 | 2584303 | -146084.5 | 146084.5 | 0 | 2025-01-28 | 2 | 2943295.91 | -212908.41 | DOWN | 0.078 | 111 | Low | 988597.72 | 0.386 | 2 | 1595705.28 | 9 | 1 | 1.26
P004 | Mechanical | SUP034 | 2025-01 | 2024-11-07 | 2645796.13 | 2584303 | -61493.13 | 61493.13 | 0 | 2025-01-28 | 3 | 2730387.5 | -84591.37 | DOWN | 0.032 | 82 | Low | 1388039.67 | 0.489 | 4 | 1196263.33 | 9 | 1 | 1.26
P004 | Mechanical | SUP034 | 2025-01 | 2024-12-28 | 2625071.1 | 2584303 | -40768.1 | 40768.1 | 0 | 2025-01-28 | 4 | 2645796.13 | -20725.03 | DOWN | 0.0079 | 31 | Medium | 1819231.41 | 0.67 | 6 | 765071.59 | 9 | 1 | 1.26
P004 | Mechanical | SUP034 | 2025-02 | 2024-09-17 | 2467615.99 | 1714074 | -753541.99 | 753541.99 | 1 | 2025-02-28 | 1 |  |  |  |  | 164 | Low | 511428.64 | 0.193 | 4 | 1202645.36 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP034 | 2025-02 | 2024-12-03 | 2060524.77 | 1714074 | -346450.77 | 346450.77 | 1 | 2025-02-28 | 2 | 2467615.99 | -407091.22 | DOWN | 0.1976 | 87 | Low | 908272.45 | 0.457 | 4 | 805801.55 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP034 | 2025-02 | 2024-12-24 | 1888858.77 | 1714074 | -174784.77 | 174784.77 | 0 | 2025-02-28 | 3 | 2060524.77 | -171666 | DOWN | 0.0909 | 66 | Low | 932423.86 | 0.529 | 4 | 781650.14 | 13 | 1.26 | 0.97
P004 | Electronics | SUP034 | 2025-03 | 2024-10-12 | 2134944.42 | 1708820 | -426124.42 | 426124.42 | 1 | 2025-03-28 | 1 |  |  |  |  | 167 | Low | 425604.03 | 0.188 | 2 | 1283215.97 | 11 | 0.73 | 1.3
P004 | Electronics | SUP034 | 2025-03 | 2024-10-23 | 1880565.17 | 1708820 | -171745.17 | 171745.17 | 0 | 2025-03-28 | 2 | 2134944.42 | -254379.25 | DOWN | 0.1353 | 156 | Low | 422396.67 | 0.227 | 3 | 1286423.33 | 11 | 0.73 | 1.3
P004 | Electronics | SUP034 | 2025-03 | 2024-11-02 | 1799810.19 | 1708820 | -90990.19 | 90990.19 | 0 | 2025-03-28 | 3 | 1880565.17 | -80754.98 | DOWN | 0.0449 | 146 | Low | 494966.54 | 0.262 | 0 | 1213853.46 | 11 | 0.73 | 1.3
P004 | Electronics | SUP034 | 2025-03 | 2024-11-09 | 1763689.15 | 1708820 | -54869.15 | 54869.15 | 0 | 2025-03-28 | 4 | 1799810.19 | -36121.04 | DOWN | 0.0205 | 139 | Low | 509121.8 | 0.287 | 2 | 1199698.2 | 11 | 0.73 | 1.3
P004 | Electronics | SUP034 | 2025-03 | 2025-01-21 | 1750769.67 | 1708820 | -41949.67 | 41949.67 | 0 | 2025-03-28 | 5 | 1763689.15 | -12919.48 | DOWN | 0.0074 | 66 | Low | 1019308.94 | 0.546 | 3 | 689511.06 | 11 | 0.73 | 1.3
P004 | Electronics | SUP034 | 2025-03 | 2025-02-09 | 1743735.55 | 1708820 | -34915.55 | 34915.55 | 0 | 2025-03-28 | 6 | 1750769.67 | -7034.12 | DOWN | 0.004 | 47 | Medium | 1106847.17 | 0.613 | 4 | 601972.83 | 11 | 0.73 | 1.3
P004 | Electronics | SUP034 | 2025-04 | 2024-12-27 | 2522548.17 | 1756946 | -765602.17 | 765602.17 | 1 | 2025-04-28 | 1 |  |  |  |  | 122 | Low | 754655 | 0.321 | 5 | 1002291 | 15 | 1.69 | 1.47
P004 | Electronics | SUP034 | 2025-04 | 2025-01-03 | 2101967.2 | 1756946 | -345021.2 | 345021.2 | 1 | 2025-04-28 | 2 | 2522548.17 | -420580.97 | DOWN | 0.2001 | 115 | Low | 681150.06 | 0.344 | 3 | 1075795.94 | 15 | 1.69 | 1.47
P004 | Electronics | SUP034 | 2025-04 | 2025-01-07 | 1925498.2 | 1756946 | -168552.2 | 168552.2 | 0 | 2025-04-28 | 3 | 2101967.2 | -176469 | DOWN | 0.0916 | 111 | Low | 681606.37 | 0.357 | 4 | 1075339.63 | 15 | 1.69 | 1.47
P004 | Electronics | SUP034 | 2025-04 | 2025-01-24 | 1857480.41 | 1756946 | -100534.41 | 100534.41 | 0 | 2025-04-28 | 4 | 1925498.2 | -68017.79 | DOWN | 0.0366 | 94 | Low | 713351.4 | 0.413 | 4 | 1043594.6 | 15 | 1.69 | 1.47
P004 | Electronics | SUP034 | 2025-04 | 2025-02-24 | 1772589.41 | 1756946 | -15643.41 | 15643.41 | 0 | 2025-04-28 | 5 | 1857480.41 | -84891 | DOWN | 0.0479 | 63 | Low | 841909.31 | 0.514 | 2 | 915036.69 | 15 | 1.69 | 1.47
P004 | Electronics | SUP034 | 2025-04 | 2025-03-30 | 1767399.47 | 1756946 | -10453.47 | 10453.47 | 0 | 2025-04-28 | 6 | 1772589.41 | -5189.94 | DOWN | 0.0029 | 29 | Medium | 1028383.54 | 0.625 | 7 | 728562.46 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP034 | 2025-05 | 2025-01-25 | 2143456.01 | 1735178 | -408278.01 | 408278.01 | 1 | 2025-05-28 | 1 |  |  |  |  | 123 | Low | 684651.5 | 0.343 | 0 | 1050526.5 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP034 | 2025-05 | 2025-02-23 | 1922984.26 | 1735178 | -187806.26 | 187806.26 | 0 | 2025-05-28 | 2 | 2143456.01 | -220471.75 | DOWN | 0.1147 | 94 | Low | 868197.44 | 0.445 | 5 | 866980.56 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP034 | 2025-05 | 2025-03-20 | 1809634.83 | 1735178 | -74456.83 | 74456.83 | 0 | 2025-05-28 | 3 | 1922984.26 | -113349.43 | DOWN | 0.0626 | 69 | Low | 957744.05 | 0.533 | 3 | 777433.95 | 12 | 1.03 | 1.42
P004 | Logistics | SUP034 | 2025-06 | 2025-01-12 | 3127338.52 | 1893402 | -1233936.52 | 1233936.52 | 1 | 2025-06-28 | 1 |  |  |  |  | 167 | Low | 613596.31 | 0.188 | 4 | 1279805.69 | 15 | 0.81 | 1.56
P004 | Logistics | SUP034 | 2025-06 | 2025-04-06 | 2404484 | 1893402 | -511082 | 511082 | 1 | 2025-06-28 | 2 | 3127338.52 | -722854.52 | DOWN | 0.3006 | 83 | Low | 1100285.32 | 0.486 | 7 | 793116.68 | 15 | 0.81 | 1.56
P004 | Logistics | SUP034 | 2025-06 | 2025-06-18 | 2151096.23 | 1893402 | -257694.23 | 257694.23 | 0 | 2025-06-28 | 3 | 2404484 | -253387.77 | DOWN | 0.1178 | 10 | Medium | 1488776.53 | 0.741 | 5 | 404625.47 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP034 | 2025-07 | 2025-01-31 | 1159966.94 | 852630 | -307336.94 | 307336.94 | 1 | 2025-07-28 | 1 |  |  |  |  | 178 | Low | 172423.88 | 0.144 | 2 | 680206.12 | 10 | 1.72 | 1
P004 | Mechanical | SUP034 | 2025-07 | 2025-02-15 | 982749.58 | 852630 | -130119.58 | 130119.58 | 0 | 2025-07-28 | 2 | 1159966.94 | -177217.36 | DOWN | 0.1803 | 163 | Low | 180442.26 | 0.186 | 4 | 672187.74 | 10 | 1.72 | 1
P004 | Mechanical | SUP034 | 2025-07 | 2025-03-18 | 901347.52 | 852630 | -48717.52 | 48717.52 | 0 | 2025-07-28 | 3 | 982749.58 | -81402.06 | DOWN | 0.0903 | 132 | Low | 249660.36 | 0.287 | 4 | 602969.64 | 10 | 1.72 | 1
P004 | Mechanical | SUP034 | 2025-07 | 2025-04-10 | 879595.13 | 852630 | -26965.13 | 26965.13 | 0 | 2025-07-28 | 4 | 901347.52 | -21752.39 | DOWN | 0.0247 | 109 | Low | 311038.83 | 0.362 | 4 | 541591.17 | 10 | 1.72 | 1
P004 | Mechanical | SUP034 | 2025-07 | 2025-05-03 | 873817.86 | 852630 | -21187.86 | 21187.86 | 0 | 2025-07-28 | 5 | 879595.13 | -5777.27 | DOWN | 0.0066 | 86 | Low | 363715.94 | 0.437 | 0 | 488914.06 | 10 | 1.72 | 1
P004 | Mechanical | SUP034 | 2025-07 | 2025-06-22 | 864691.21 | 852630 | -12061.21 | 12061.21 | 0 | 2025-07-28 | 6 | 873817.86 | -9126.65 | DOWN | 0.0106 | 36 | Medium | 545630.7 | 0.6 | 2 | 306999.3 | 10 | 1.72 | 1
P004 | Electronics | SUP034 | 2025-08 | 2025-05-24 | 1916422.41 | 1385232 | -531190.41 | 531190.41 | 1 | 2025-08-28 | 1 |  |  |  |  | 96 | Low | 799752.01 | 0.417 | 0 | 585479.99 | 13 | 1.45 | 1.13
P004 | Electronics | SUP034 | 2025-08 | 2025-06-10 | 1611553.66 | 1385232 | -226321.66 | 226321.66 | 0 | 2025-08-28 | 2 | 1916422.41 | -304868.75 | DOWN | 0.1892 | 79 | Low | 752932.61 | 0.474 | 0 | 632299.39 | 13 | 1.45 | 1.13
P004 | Electronics | SUP034 | 2025-08 | 2025-07-27 | 1466334.76 | 1385232 | -81102.76 | 81102.76 | 0 | 2025-08-28 | 3 | 1611553.66 | -145218.9 | DOWN | 0.099 | 32 | Medium | 874855.52 | 0.632 | 3 | 510376.48 | 13 | 1.45 | 1.13
P004 | Electronics | SUP034 | 2025-08 | 2025-08-08 | 1402172.04 | 1385232 | -16940.04 | 16940.04 | 0 | 2025-08-28 | 4 | 1466334.76 | -64162.72 | DOWN | 0.0458 | 20 | Medium | 926827.94 | 0.673 | 3 | 458404.06 | 13 | 1.45 | 1.13
P004 | Software | SUP034 | 2025-09 | 2025-05-27 | 2621532.52 | 1459189 | -1162343.52 | 1162343.52 | 1 | 2025-09-28 | 1 |  |  |  |  | 124 | Low | 895604.58 | 0.328 | 0 | 563584.42 | 12 | 1.31 | 1.3
P004 | Software | SUP034 | 2025-09 | 2025-06-29 | 1952984.43 | 1459189 | -493795.43 | 493795.43 | 1 | 2025-09-28 | 2 | 2621532.52 | -668548.09 | DOWN | 0.3423 | 91 | Low | 893638.63 | 0.441 | 4 | 565550.37 | 12 | 1.31 | 1.3
P004 | Software | SUP034 | 2025-09 | 2025-07-26 | 1705975.25 | 1459189 | -246786.25 | 246786.25 | 0 | 2025-09-28 | 3 | 1952984.43 | -247009.18 | DOWN | 0.1448 | 64 | Low | 869371.79 | 0.533 | 3 | 589817.21 | 12 | 1.31 | 1.3
P004 | Software | SUP034 | 2025-09 | 2025-08-09 | 1546187.03 | 1459189 | -86998.03 | 86998.03 | 0 | 2025-09-28 | 4 | 1705975.25 | -159788.22 | DOWN | 0.1033 | 50 | Medium | 953690.12 | 0.581 | 1 | 505498.88 | 12 | 1.31 | 1.3
P004 | Services | SUP034 | 2025-10 | 2025-05-20 | 3210988.48 | 2022938 | -1188050.48 | 1188050.48 | 1 | 2025-10-28 | 1 |  |  |  |  | 161 | Low | 641347.49 | 0.2 | 3 | 1381590.51 | 16 | 1.37 | 1.4
P004 | Services | SUP034 | 2025-10 | 2025-05-30 | 2526310.29 | 2022938 | -503372.29 | 503372.29 | 1 | 2025-10-28 | 2 | 3210988.48 | -684678.19 | DOWN | 0.271 | 151 | Low | 621526.82 | 0.234 | 1 | 1401411.18 | 16 | 1.37 | 1.4
P004 | Services | SUP034 | 2025-10 | 2025-06-12 | 2262291.4 | 2022938 | -239353.4 | 239353.4 | 0 | 2025-10-28 | 3 | 2526310.29 | -264018.89 | DOWN | 0.1167 | 138 | Low | 655595.82 | 0.278 | 0 | 1367342.18 | 16 | 1.37 | 1.4
P004 | Services | SUP034 | 2025-10 | 2025-06-13 | 2148350.59 | 2022938 | -125412.59 | 125412.59 | 0 | 2025-10-28 | 4 | 2262291.4 | -113940.81 | DOWN | 0.053 | 137 | Low | 627405.56 | 0.282 | 0 | 1395532.44 | 16 | 1.37 | 1.4
P004 | Services | SUP034 | 2025-10 | 2025-07-09 | 2107586.81 | 2022938 | -84648.81 | 84648.81 | 0 | 2025-10-28 | 5 | 2148350.59 | -40763.78 | DOWN | 0.0193 | 111 | Low | 815221.78 | 0.37 | 3 | 1207716.22 | 16 | 1.37 | 1.4
P004 | Services | SUP034 | 2025-10 | 2025-08-18 | 2071785.57 | 2022938 | -48847.57 | 48847.57 | 0 | 2025-10-28 | 6 | 2107586.81 | -35801.24 | DOWN | 0.0173 | 71 | Low | 1057733.67 | 0.506 | 2 | 965204.33 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP034 | 2025-11 | 2025-08-06 | 3132088.58 | 2436359 | -695729.58 | 695729.58 | 1 | 2025-11-28 | 1 |  |  |  |  | 114 | Low | 1167580.87 | 0.376 | 3 | 1268778.13 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP034 | 2025-11 | 2025-08-25 | 2760628.73 | 2436359 | -324269.73 | 324269.73 | 0 | 2025-11-28 | 2 | 3132088.58 | -371459.85 | DOWN | 0.1346 | 95 | Low | 1293785.35 | 0.443 | 6 | 1142573.65 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP034 | 2025-11 | 2025-09-20 | 2590540.63 | 2436359 | -154181.63 | 154181.63 | 0 | 2025-11-28 | 3 | 2760628.73 | -170088.1 | DOWN | 0.0657 | 69 | Low | 1352408.51 | 0.535 | 3 | 1083950.49 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP034 | 2025-11 | 2025-09-20 | 2497579.23 | 2436359 | -61220.23 | 61220.23 | 0 | 2025-11-28 | 4 | 2590540.63 | -92961.4 | DOWN | 0.0372 | 69 | Low | 1275454.12 | 0.535 | 5 | 1160904.88 | 7 | 0.59 | 1.31
P004 | Services | SUP034 | 2025-12 | 2025-08-19 | 3600701.25 | 2257085 | -1343616.25 | 1343616.25 | 1 | 2025-12-28 | 1 |  |  |  |  | 131 | Low | 1108390.12 | 0.311 | 6 | 1148694.88 | 9 | 1.11 | 0.94
P004 | Services | SUP034 | 2025-12 | 2025-09-26 | 2900131.73 | 2257085 | -643046.73 | 643046.73 | 1 | 2025-12-28 | 2 | 3600701.25 | -700569.52 | DOWN | 0.2416 | 93 | Low | 1330255.69 | 0.444 | 3 | 926829.31 | 9 | 1.11 | 0.94
P004 | Services | SUP034 | 2025-12 | 2025-11-24 | 2573501.35 | 2257085 | -316416.35 | 316416.35 | 0 | 2025-12-28 | 3 | 2900131.73 | -326630.38 | DOWN | 0.1269 | 34 | Low | 1772640.99 | 0.651 | 5 | 484444.01 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP049 | 2025-01 | 2024-08-11 | 2299517.84 | 1564888 | -734629.84 | 734629.84 | 1 | 2025-01-28 | 1 |  |  |  |  | 170 | Low | 297740.99 | 0.125 | 0 | 1267147.01 | 9 | 1 | 1.26
P004 | Mechanical | SUP049 | 2025-01 | 2024-08-26 | 2017163.32 | 1564888 | -452275.32 | 452275.32 | 1 | 2025-01-28 | 2 | 2299517.84 | -282354.52 | DOWN | 0.14 | 155 | Low | 318265.55 | 0.162 | 0 | 1246622.45 | 9 | 1 | 1.26
P004 | Mechanical | SUP049 | 2025-01 | 2024-10-10 | 1842620.9 | 1564888 | -277732.9 | 277732.9 | 1 | 2025-01-28 | 3 | 2017163.32 | -174542.42 | DOWN | 0.0947 | 110 | Low | 533667.58 | 0.275 | 0 | 1031220.42 | 9 | 1 | 1.26
P004 | Mechanical | SUP049 | 2025-01 | 2024-11-17 | 1738706.82 | 1564888 | -173818.82 | 173818.82 | 0 | 2025-01-28 | 4 | 1842620.9 | -103914.08 | DOWN | 0.0598 | 72 | Low | 593367.61 | 0.37 | 0 | 971520.39 | 9 | 1 | 1.26
P004 | Mechanical | SUP049 | 2025-01 | 2024-12-23 | 1668713.24 | 1564888 | -103825.24 | 103825.24 | 0 | 2025-01-28 | 5 | 1738706.82 | -69993.58 | DOWN | 0.0419 | 36 | Medium | 809975.44 | 0.46 | 3 | 754912.56 | 9 | 1 | 1.26
P004 | Mechanical | SUP049 | 2025-01 | 2025-01-15 | 1633144.37 | 1564888 | -68256.37 | 68256.37 | 0 | 2025-01-28 | 6 | 1668713.24 | -35568.87 | DOWN | 0.0218 | 13 | Medium | 819696.65 | 0.518 | 6 | 745191.35 | 9 | 1 | 1.26
P004 | Materials | SUP049 | 2025-02 | 2024-09-01 | 2221666.14 | 1570167 | -651499.14 | 651499.14 | 1 | 2025-02-28 | 1 |  |  |  |  | 180 | Low | 245312.6 | 0.107 | 0 | 1324854.4 | 13 | 1.26 | 0.97
P004 | Materials | SUP049 | 2025-02 | 2024-11-18 | 1968786.28 | 1570167 | -398619.28 | 398619.28 | 1 | 2025-02-28 | 2 | 2221666.14 | -252879.86 | DOWN | 0.1284 | 102 | Low | 553324.49 | 0.286 | 5 | 1016842.51 | 13 | 1.26 | 0.97
P004 | Materials | SUP049 | 2025-02 | 2024-11-26 | 1804529.94 | 1570167 | -234362.94 | 234362.94 | 0 | 2025-02-28 | 3 | 1968786.28 | -164256.34 | DOWN | 0.091 | 94 | Low | 526897.49 | 0.305 | 3 | 1043269.51 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP049 | 2025-03 | 2024-10-06 | 3234221.44 | 2498839 | -735382.44 | 735382.44 | 1 | 2025-03-28 | 1 |  |  |  |  | 173 | Low | 396686.32 | 0.118 | 4 | 2102152.68 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP049 | 2025-03 | 2024-11-02 | 2920697.85 | 2498839 | -421858.85 | 421858.85 | 0 | 2025-03-28 | 2 | 3234221.44 | -313523.59 | DOWN | 0.1073 | 146 | Low | 567846.33 | 0.185 | 0 | 1930992.67 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP049 | 2025-03 | 2024-11-13 | 2737122.49 | 2498839 | -238283.49 | 238283.49 | 0 | 2025-03-28 | 3 | 2920697.85 | -183575.36 | DOWN | 0.0671 | 135 | Low | 586485.14 | 0.213 | 3 | 1912353.86 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP049 | 2025-03 | 2025-03-01 | 2639985.08 | 2498839 | -141146.08 | 141146.08 | 0 | 2025-03-28 | 4 | 2737122.49 | -97137.41 | DOWN | 0.0368 | 27 | Medium | 1322803.92 | 0.483 | 4 | 1176035.08 | 11 | 0.73 | 1.3
P004 | Electronics | SUP049 | 2025-04 | 2024-12-18 | 2224369.81 | 1492856 | -731513.81 | 731513.81 | 1 | 2025-04-28 | 1 |  |  |  |  | 131 | Low | 470503.51 | 0.205 | 0 | 1022352.49 | 15 | 1.69 | 1.47
P004 | Electronics | SUP049 | 2025-04 | 2024-12-23 | 1957830.87 | 1492856 | -464974.87 | 464974.87 | 1 | 2025-04-28 | 2 | 2224369.81 | -266538.94 | DOWN | 0.1361 | 126 | Low | 419862.45 | 0.217 | 0 | 1072993.55 | 15 | 1.69 | 1.47
P004 | Electronics | SUP049 | 2025-04 | 2025-02-07 | 1789428.31 | 1492856 | -296572.31 | 296572.31 | 1 | 2025-04-28 | 3 | 1957830.87 | -168402.56 | DOWN | 0.0941 | 80 | Low | 598925.9 | 0.323 | 4 | 893930.1 | 15 | 1.69 | 1.47
P004 | Electronics | SUP049 | 2025-04 | 2025-03-24 | 1678273.08 | 1492856 | -185417.08 | 185417.08 | 0 | 2025-04-28 | 4 | 1789428.31 | -111155.23 | DOWN | 0.0662 | 35 | Low | 674208.79 | 0.427 | 0 | 818647.21 | 15 | 1.69 | 1.47
P004 | Electronics | SUP049 | 2025-04 | 2025-04-12 | 1608676.39 | 1492856 | -115820.39 | 115820.39 | 0 | 2025-04-28 | 5 | 1678273.08 | -69596.69 | DOWN | 0.0433 | 16 | Medium | 787696.07 | 0.471 | 4 | 705159.93 | 15 | 1.69 | 1.47
P004 | Materials | SUP049 | 2025-05 | 2025-01-07 | 1918331.61 | 1110695 | -807636.61 | 807636.61 | 1 | 2025-05-28 | 1 |  |  |  |  | 141 | Low | 381703.97 | 0.197 | 0 | 728991.03 | 12 | 1.03 | 1.42
P004 | Materials | SUP049 | 2025-05 | 2025-01-29 | 1583605.67 | 1110695 | -472910.67 | 472910.67 | 1 | 2025-05-28 | 2 | 1918331.61 | -334725.94 | DOWN | 0.2114 | 119 | Low | 400360.5 | 0.252 | 3 | 710334.5 | 12 | 1.03 | 1.42
P004 | Materials | SUP049 | 2025-05 | 2025-03-07 | 1406797.19 | 1110695 | -296102.19 | 296102.19 | 1 | 2025-05-28 | 3 | 1583605.67 | -176808.48 | DOWN | 0.1257 | 82 | Low | 508472.7 | 0.344 | 0 | 602222.3 | 12 | 1.03 | 1.42
P004 | Materials | SUP049 | 2025-05 | 2025-03-23 | 1297225.33 | 1110695 | -186530.33 | 186530.33 | 0 | 2025-05-28 | 4 | 1406797.19 | -109571.86 | DOWN | 0.0845 | 66 | Low | 488236.41 | 0.384 | 0 | 622458.59 | 12 | 1.03 | 1.42
P004 | Logistics | SUP049 | 2025-06 | 2025-03-14 | 2205132.47 | 1095494 | -1109638.47 | 1109638.47 | 1 | 2025-06-28 | 1 |  |  |  |  | 106 | Low | 672451.44 | 0.285 | 2 | 423042.56 | 15 | 0.81 | 1.56
P004 | Logistics | SUP049 | 2025-06 | 2025-04-07 | 1737224.22 | 1095494 | -641730.22 | 641730.22 | 1 | 2025-06-28 | 2 | 2205132.47 | -467908.25 | DOWN | 0.2693 | 82 | Low | 578947.5 | 0.345 | 0 | 516546.5 | 15 | 0.81 | 1.56
P004 | Logistics | SUP049 | 2025-06 | 2025-04-08 | 1512999.55 | 1095494 | -417505.55 | 417505.55 | 1 | 2025-06-28 | 3 | 1737224.22 | -224224.67 | DOWN | 0.1482 | 81 | Low | 538613.29 | 0.348 | 3 | 556880.71 | 15 | 0.81 | 1.56
P004 | Logistics | SUP049 | 2025-06 | 2025-04-18 | 1351933.71 | 1095494 | -256439.71 | 256439.71 | 1 | 2025-06-28 | 4 | 1512999.55 | -161065.84 | DOWN | 0.1191 | 71 | Low | 500855.27 | 0.372 | 5 | 594638.73 | 15 | 0.81 | 1.56
P004 | Logistics | SUP049 | 2025-06 | 2025-04-30 | 1236361.3 | 1095494 | -140867.3 | 140867.3 | 0 | 2025-06-28 | 5 | 1351933.71 | -115572.41 | DOWN | 0.0935 | 59 | Low | 535937.37 | 0.403 | 4 | 559556.63 | 15 | 0.81 | 1.56
P004 | Logistics | SUP049 | 2025-06 | 2025-05-17 | 1176483.45 | 1095494 | -80989.45 | 80989.45 | 0 | 2025-06-28 | 6 | 1236361.3 | -59877.85 | DOWN | 0.0509 | 42 | Low | 509349.75 | 0.445 | 1 | 586144.25 | 15 | 0.81 | 1.56
P004 | Software | SUP049 | 2025-07 | 2025-04-27 | 1908820.43 | 985353 | -923467.43 | 923467.43 | 1 | 2025-07-28 | 1 |  |  |  |  | 92 | Low | 578107.09 | 0.295 | 0 | 407245.91 | 10 | 1.72 | 1
P004 | Software | SUP049 | 2025-07 | 2025-07-07 | 1518102.37 | 985353 | -532749.37 | 532749.37 | 1 | 2025-07-28 | 2 | 1908820.43 | -390718.06 | DOWN | 0.2574 | 21 | Low | 718762.92 | 0.458 | 5 | 266590.08 | 10 | 1.72 | 1
P004 | Software | SUP049 | 2025-07 | 2025-07-15 | 1291373.17 | 985353 | -306020.17 | 306020.17 | 1 | 2025-07-28 | 3 | 1518102.37 | -226729.2 | DOWN | 0.1756 | 13 | Low | 620708.33 | 0.476 | 4 | 364644.67 | 10 | 1.72 | 1
P004 | Logistics | SUP049 | 2025-08 | 2025-06-15 | 1453352.06 | 788345 | -665007.06 | 665007.06 | 1 | 2025-08-28 | 1 |  |  |  |  | 74 | Low | 521437.04 | 0.346 | 3 | 266907.96 | 13 | 1.45 | 1.13
P004 | Logistics | SUP049 | 2025-08 | 2025-06-16 | 1160028.87 | 788345 | -371683.87 | 371683.87 | 1 | 2025-08-28 | 2 | 1453352.06 | -293323.19 | DOWN | 0.2529 | 73 | Low | 429465.81 | 0.349 | 5 | 358879.19 | 13 | 1.45 | 1.13
P004 | Logistics | SUP049 | 2025-08 | 2025-08-11 | 996551.58 | 788345 | -208206.58 | 208206.58 | 1 | 2025-08-28 | 3 | 1160028.87 | -163477.29 | DOWN | 0.164 | 17 | Low | 499190.76 | 0.481 | 5 | 289154.24 | 13 | 1.45 | 1.13
P004 | Logistics | SUP049 | 2025-09 | 2025-05-31 | 2327884.7 | 1145328 | -1182556.7 | 1182556.7 | 1 | 2025-09-28 | 1 |  |  |  |  | 120 | Low | 597928.33 | 0.241 | 1 | 547399.67 | 12 | 1.31 | 1.3
P004 | Logistics | SUP049 | 2025-09 | 2025-08-05 | 1844439.03 | 1145328 | -699111.03 | 699111.03 | 1 | 2025-09-28 | 2 | 2327884.7 | -483445.67 | DOWN | 0.2621 | 54 | Low | 719171.25 | 0.4 | 2 | 426156.75 | 12 | 1.31 | 1.3
P004 | Logistics | SUP049 | 2025-09 | 2025-08-28 | 1549705.09 | 1145328 | -404377.09 | 404377.09 | 1 | 2025-09-28 | 3 | 1844439.03 | -294733.94 | DOWN | 0.1902 | 31 | Low | 734789.77 | 0.456 | 10 | 410538.23 | 12 | 1.31 | 1.3
P004 | Logistics | SUP049 | 2025-10 | 2025-06-21 | 804859.68 | 454731 | -350128.68 | 350128.68 | 1 | 2025-10-28 | 1 |  |  |  |  | 129 | Low | 172776.41 | 0.218 | 0 | 281954.59 | 16 | 1.37 | 1.4
P004 | Logistics | SUP049 | 2025-10 | 2025-07-08 | 668830.99 | 454731 | -214099.99 | 214099.99 | 1 | 2025-10-28 | 2 | 804859.68 | -136028.69 | DOWN | 0.2034 | 112 | Low | 175903.83 | 0.259 | 1 | 278827.17 | 16 | 1.37 | 1.4
P004 | Logistics | SUP049 | 2025-10 | 2025-07-11 | 575765.59 | 454731 | -121034.59 | 121034.59 | 1 | 2025-10-28 | 3 | 668830.99 | -93065.4 | DOWN | 0.1616 | 109 | Low | 156647.16 | 0.266 | 0 | 298083.84 | 16 | 1.37 | 1.4
P004 | Logistics | SUP049 | 2025-10 | 2025-08-23 | 516053.24 | 454731 | -61322.24 | 61322.24 | 0 | 2025-10-28 | 4 | 575765.59 | -59712.35 | DOWN | 0.1157 | 66 | Low | 198749.05 | 0.369 | 2 | 255981.95 | 16 | 1.37 | 1.4
P004 | Logistics | SUP049 | 2025-10 | 2025-08-24 | 495895.31 | 454731 | -41164.31 | 41164.31 | 0 | 2025-10-28 | 5 | 516053.24 | -20157.93 | DOWN | 0.0406 | 65 | Low | 189211.45 | 0.371 | 1 | 265519.55 | 16 | 1.37 | 1.4
P004 | Electronics | SUP049 | 2025-11 | 2025-08-22 | 1590885.52 | 979923 | -610962.52 | 610962.52 | 1 | 2025-11-28 | 1 |  |  |  |  | 98 | Low | 473658.28 | 0.305 | 1 | 506264.72 | 7 | 0.59 | 1.31
P004 | Electronics | SUP049 | 2025-11 | 2025-08-24 | 1349811.62 | 979923 | -369888.62 | 369888.62 | 1 | 2025-11-28 | 2 | 1590885.52 | -241073.9 | DOWN | 0.1786 | 96 | Low | 423481.87 | 0.31 | 3 | 556441.13 | 7 | 0.59 | 1.31
P004 | Electronics | SUP049 | 2025-11 | 2025-09-30 | 1215184.74 | 979923 | -235261.74 | 235261.74 | 1 | 2025-11-28 | 3 | 1349811.62 | -134626.88 | DOWN | 0.1108 | 59 | Low | 483194.83 | 0.403 | 8 | 496728.17 | 7 | 0.59 | 1.31
P004 | Electronics | SUP049 | 2025-12 | 2025-07-22 | 1560096.79 | 1089031 | -471065.79 | 471065.79 | 1 | 2025-12-28 | 1 |  |  |  |  | 159 | Low | 216947.28 | 0.151 | 2 | 872083.72 | 9 | 1.11 | 0.94
P004 | Electronics | SUP049 | 2025-12 | 2025-08-08 | 1362438.2 | 1089031 | -273407.2 | 273407.2 | 1 | 2025-12-28 | 2 | 1560096.79 | -197658.59 | DOWN | 0.1451 | 142 | Low | 251697.18 | 0.192 | 0 | 837333.82 | 9 | 1.11 | 0.94
P004 | Electronics | SUP049 | 2025-12 | 2025-08-13 | 1250098.12 | 1089031 | -161067.12 | 161067.12 | 0 | 2025-12-28 | 3 | 1362438.2 | -112340.08 | DOWN | 0.0899 | 137 | Low | 266642.11 | 0.205 | 0 | 822388.89 | 9 | 1.11 | 0.94
P004 | Electronics | SUP049 | 2025-12 | 2025-08-16 | 1182276.62 | 1089031 | -93245.62 | 93245.62 | 0 | 2025-12-28 | 4 | 1250098.12 | -67821.5 | DOWN | 0.0574 | 134 | Low | 248400.97 | 0.212 | 0 | 840630.03 | 9 | 1.11 | 0.94
P004 | Electronics | SUP049 | 2025-12 | 2025-08-26 | 1148819.73 | 1089031 | -59788.73 | 59788.73 | 0 | 2025-12-28 | 5 | 1182276.62 | -33456.89 | DOWN | 0.0291 | 124 | Low | 257929.47 | 0.237 | 0 | 831101.53 | 9 | 1.11 | 0.94
P004 | Electronics | SUP049 | 2025-12 | 2025-08-29 | 1121134.58 | 1089031 | -32103.58 | 32103.58 | 0 | 2025-12-28 | 6 | 1148819.73 | -27685.15 | DOWN | 0.0247 | 121 | Low | 253498.74 | 0.244 | 1 | 835532.26 | 9 | 1.11 | 0.94
P004 | Services | SUP006 | 2025-01 | 2024-10-11 | 2494272.54 | 1407708 | -1086564.54 | 1086564.54 | 1 | 2025-01-28 | 1 |  |  |  |  | 109 | Low | 680950.57 | 0.278 | 4 | 726757.43 | 9 | 1 | 1.26
P004 | Services | SUP006 | 2025-01 | 2024-11-06 | 2037436.34 | 1407708 | -629728.34 | 629728.34 | 1 | 2025-01-28 | 2 | 2494272.54 | -456836.2 | DOWN | 0.2242 | 83 | Low | 694772.26 | 0.343 | 1 | 712935.74 | 9 | 1 | 1.26
P004 | Services | SUP006 | 2025-01 | 2024-11-10 | 1782725.28 | 1407708 | -375017.28 | 375017.28 | 1 | 2025-01-28 | 3 | 2037436.34 | -254711.06 | DOWN | 0.1429 | 79 | Low | 629533.73 | 0.353 | 1 | 778174.27 | 9 | 1 | 1.26
P004 | Services | SUP006 | 2025-01 | 2024-11-16 | 1658251.13 | 1407708 | -250543.13 | 250543.13 | 1 | 2025-01-28 | 4 | 1782725.28 | -124474.15 | DOWN | 0.0751 | 73 | Low | 619090.81 | 0.368 | 2 | 788617.19 | 9 | 1 | 1.26
P004 | Services | SUP006 | 2025-01 | 2024-12-19 | 1533221.36 | 1407708 | -125513.36 | 125513.36 | 0 | 2025-01-28 | 5 | 1658251.13 | -125029.77 | DOWN | 0.0815 | 40 | Medium | 681283.44 | 0.45 | 0 | 726424.56 | 9 | 1 | 1.26
P004 | Services | SUP006 | 2025-01 | 2025-01-16 | 1490751.94 | 1407708 | -83043.94 | 83043.94 | 0 | 2025-01-28 | 6 | 1533221.36 | -42469.42 | DOWN | 0.0285 | 12 | Medium | 743546.64 | 0.52 | 7 | 664161.36 | 9 | 1 | 1.26
P004 | Electronics | SUP006 | 2025-02 | 2024-09-29 | 670871.79 | 452207 | -218664.79 | 218664.79 | 1 | 2025-02-28 | 1 |  |  |  |  | 152 | Low | 112440.59 | 0.165 | 0 | 339766.41 | 13 | 1.26 | 0.97
P004 | Electronics | SUP006 | 2025-02 | 2024-12-20 | 582110.46 | 452207 | -129903.46 | 129903.46 | 1 | 2025-02-28 | 2 | 670871.79 | -88761.33 | DOWN | 0.1525 | 70 | Low | 220214.46 | 0.364 | 0 | 231992.54 | 13 | 1.26 | 0.97
P004 | Electronics | SUP006 | 2025-02 | 2025-01-29 | 533112.52 | 452207 | -80905.52 | 80905.52 | 1 | 2025-02-28 | 3 | 582110.46 | -48997.94 | DOWN | 0.0919 | 30 | Medium | 229968.13 | 0.461 | 5 | 222238.87 | 13 | 1.26 | 0.97
P004 | Materials | SUP006 | 2025-03 | 2024-11-14 | 2475281.16 | 1636177 | -839104.16 | 839104.16 | 1 | 2025-03-28 | 1 |  |  |  |  | 134 | Low | 529256.83 | 0.215 | 3 | 1106920.17 | 11 | 0.73 | 1.3
P004 | Materials | SUP006 | 2025-03 | 2024-11-17 | 2161467.53 | 1636177 | -525290.53 | 525290.53 | 1 | 2025-03-28 | 2 | 2475281.16 | -313813.63 | DOWN | 0.1452 | 131 | Low | 460888.04 | 0.223 | 3 | 1175288.96 | 11 | 0.73 | 1.3
P004 | Materials | SUP006 | 2025-03 | 2025-01-12 | 1957500.69 | 1636177 | -321323.69 | 321323.69 | 1 | 2025-03-28 | 3 | 2161467.53 | -203966.84 | DOWN | 0.1042 | 75 | Low | 744753.38 | 0.363 | 5 | 891423.62 | 11 | 0.73 | 1.3
P004 | Materials | SUP006 | 2025-03 | 2025-01-27 | 1818227.91 | 1636177 | -182050.91 | 182050.91 | 0 | 2025-03-28 | 4 | 1957500.69 | -139272.78 | DOWN | 0.0766 | 60 | Low | 750212.17 | 0.4 | 7 | 885964.83 | 11 | 0.73 | 1.3
P004 | Materials | SUP006 | 2025-03 | 2025-02-24 | 1753720.31 | 1636177 | -117543.31 | 117543.31 | 0 | 2025-03-28 | 5 | 1818227.91 | -64507.6 | DOWN | 0.0368 | 32 | Medium | 873363.03 | 0.47 | 3 | 762813.97 | 11 | 0.73 | 1.3
P004 | Materials | SUP006 | 2025-03 | 2025-02-27 | 1710817.53 | 1636177 | -74640.53 | 74640.53 | 0 | 2025-03-28 | 6 | 1753720.31 | -42902.78 | DOWN | 0.0251 | 29 | Medium | 776755.37 | 0.478 | 4 | 859421.63 | 11 | 0.73 | 1.3
P004 | Electronics | SUP006 | 2025-04 | 2024-11-02 | 3844987.61 | 2511844 | -1333143.61 | 1333143.61 | 1 | 2025-04-28 | 1 |  |  |  |  | 177 | Low | 406263.73 | 0.102 | 0 | 2105580.27 | 15 | 1.69 | 1.47
P004 | Electronics | SUP006 | 2025-04 | 2024-11-26 | 3249698.6 | 2511844 | -737854.6 | 737854.6 | 1 | 2025-04-28 | 2 | 3844987.61 | -595289.01 | DOWN | 0.1832 | 153 | Low | 542529 | 0.155 | 0 | 1969315 | 15 | 1.69 | 1.47
P004 | Electronics | SUP006 | 2025-04 | 2025-03-08 | 2958389.69 | 2511844 | -446545.69 | 446545.69 | 1 | 2025-04-28 | 3 | 3249698.6 | -291308.91 | DOWN | 0.0985 | 51 | Low | 1089840.04 | 0.39 | 5 | 1422003.96 | 15 | 1.69 | 1.47
P004 | Electronics | SUP006 | 2025-04 | 2025-03-18 | 2712944.35 | 2511844 | -201100.35 | 201100.35 | 0 | 2025-04-28 | 4 | 2958389.69 | -245445.34 | DOWN | 0.0905 | 41 | Low | 1135105.32 | 0.413 | 1 | 1376738.68 | 15 | 1.69 | 1.47
P004 | Electronics | SUP006 | 2025-04 | 2025-03-22 | 2647863.75 | 2511844 | -136019.75 | 136019.75 | 0 | 2025-04-28 | 5 | 2712944.35 | -65080.6 | DOWN | 0.0246 | 37 | Low | 1106417.26 | 0.423 | 1 | 1405426.74 | 15 | 1.69 | 1.47
P004 | Services | SUP006 | 2025-05 | 2025-03-16 | 485717.11 | 313104 | -172613.11 | 172613.11 | 1 | 2025-05-28 | 1 |  |  |  |  | 73 | Low | 187779.46 | 0.366 | 4 | 125324.54 | 12 | 1.03 | 1.42
P004 | Services | SUP006 | 2025-05 | 2025-04-08 | 420467.3 | 313104 | -107363.3 | 107363.3 | 1 | 2025-05-28 | 2 | 485717.11 | -65249.81 | DOWN | 0.1552 | 50 | Low | 179663.22 | 0.423 | 1 | 133440.78 | 12 | 1.03 | 1.42
P004 | Services | SUP006 | 2025-05 | 2025-05-01 | 377548.35 | 313104 | -64444.35 | 64444.35 | 1 | 2025-05-28 | 3 | 420467.3 | -42918.95 | DOWN | 0.1137 | 27 | Medium | 195104.7 | 0.481 | 6 | 117999.3 | 12 | 1.03 | 1.42
P004 | Services | SUP006 | 2025-05 | 2025-05-12 | 347147.85 | 313104 | -34043.85 | 34043.85 | 0 | 2025-05-28 | 4 | 377548.35 | -30400.5 | DOWN | 0.0876 | 16 | Medium | 188857.68 | 0.508 | 5 | 124246.32 | 12 | 1.03 | 1.42
P004 | Logistics | SUP006 | 2025-06 | 2025-01-03 | 3902290.61 | 2376844 | -1525446.61 | 1525446.61 | 1 | 2025-06-28 | 1 |  |  |  |  | 176 | Low | 421144.68 | 0.11 | 0 | 1955699.32 | 15 | 0.81 | 1.56
P004 | Logistics | SUP006 | 2025-06 | 2025-03-10 | 3354816.72 | 2376844 | -977972.72 | 977972.72 | 1 | 2025-06-28 | 2 | 3902290.61 | -547473.89 | DOWN | 0.1632 | 110 | Low | 940345.51 | 0.275 | 0 | 1436498.49 | 15 | 0.81 | 1.56
P004 | Logistics | SUP006 | 2025-06 | 2025-04-06 | 2966938.77 | 2376844 | -590094.77 | 590094.77 | 1 | 2025-06-28 | 3 | 3354816.72 | -387877.95 | DOWN | 0.1307 | 83 | Low | 1029457.87 | 0.343 | 2 | 1347386.13 | 15 | 0.81 | 1.56
P004 | Materials | SUP006 | 2025-07 | 2025-05-08 | 1440000.84 | 915293 | -524707.84 | 524707.84 | 1 | 2025-07-28 | 1 |  |  |  |  | 81 | Low | 487625.93 | 0.32 | 6 | 427667.07 | 10 | 1.72 | 1
P004 | Materials | SUP006 | 2025-07 | 2025-06-08 | 1257373.64 | 915293 | -342080.64 | 342080.64 | 1 | 2025-07-28 | 2 | 1440000.84 | -182627.2 | DOWN | 0.1452 | 50 | Low | 462902.05 | 0.391 | 4 | 452390.95 | 10 | 1.72 | 1
P004 | Materials | SUP006 | 2025-07 | 2025-06-16 | 1116399.2 | 915293 | -201106.2 | 201106.2 | 1 | 2025-07-28 | 3 | 1257373.64 | -140974.44 | DOWN | 0.1263 | 42 | Low | 489617.97 | 0.41 | 0 | 425675.03 | 10 | 1.72 | 1
P004 | Materials | SUP006 | 2025-08 | 2025-06-11 | 685971.01 | 485746 | -200225.01 | 200225.01 | 1 | 2025-08-28 | 1 |  |  |  |  | 78 | Low | 244064.14 | 0.337 | 0 | 241681.86 | 13 | 1.45 | 1.13
P004 | Materials | SUP006 | 2025-08 | 2025-06-19 | 609637.94 | 485746 | -123891.94 | 123891.94 | 1 | 2025-08-28 | 2 | 685971.01 | -76333.07 | DOWN | 0.1252 | 70 | Low | 205823.18 | 0.356 | 2 | 279922.82 | 13 | 1.45 | 1.13
P004 | Materials | SUP006 | 2025-08 | 2025-06-22 | 554152.23 | 485746 | -68406.23 | 68406.23 | 0 | 2025-08-28 | 3 | 609637.94 | -55485.71 | DOWN | 0.1001 | 67 | Low | 193134.66 | 0.363 | 3 | 292611.34 | 13 | 1.45 | 1.13
P004 | Materials | SUP006 | 2025-08 | 2025-07-04 | 526139.45 | 485746 | -40393.45 | 40393.45 | 0 | 2025-08-28 | 4 | 554152.23 | -28012.78 | DOWN | 0.0532 | 55 | Low | 212951.97 | 0.391 | 6 | 272794.03 | 13 | 1.45 | 1.13
P004 | Materials | SUP006 | 2025-08 | 2025-07-07 | 510894.53 | 485746 | -25148.53 | 25148.53 | 0 | 2025-08-28 | 5 | 526139.45 | -15244.92 | DOWN | 0.0298 | 52 | Low | 198480.54 | 0.398 | 2 | 287265.46 | 13 | 1.45 | 1.13
P004 | Electronics | SUP006 | 2025-09 | 2025-05-06 | 964409.51 | 555464 | -408945.51 | 408945.51 | 1 | 2025-09-28 | 1 |  |  |  |  | 145 | Low | 171091.59 | 0.181 | 3 | 384372.41 | 12 | 1.31 | 1.3
P004 | Electronics | SUP006 | 2025-09 | 2025-06-05 | 788317.26 | 555464 | -232853.26 | 232853.26 | 1 | 2025-09-28 | 2 | 964409.51 | -176092.25 | DOWN | 0.2234 | 115 | Low | 211503.35 | 0.253 | 0 | 343960.65 | 12 | 1.31 | 1.3
P004 | Electronics | SUP006 | 2025-09 | 2025-08-24 | 704198.11 | 555464 | -148734.11 | 148734.11 | 1 | 2025-09-28 | 3 | 788317.26 | -84119.15 | DOWN | 0.1195 | 35 | Low | 310484.19 | 0.446 | 2 | 244979.81 | 12 | 1.31 | 1.3
P004 | Electronics | SUP006 | 2025-09 | 2025-09-02 | 642324.12 | 555464 | -86860.12 | 86860.12 | 0 | 2025-09-28 | 4 | 704198.11 | -61873.99 | DOWN | 0.0963 | 26 | Medium | 300141.94 | 0.468 | 3 | 255322.06 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP006 | 2025-10 | 2025-05-20 | 2440559.36 | 1654564 | -785995.36 | 785995.36 | 1 | 2025-10-28 | 1 |  |  |  |  | 161 | Low | 367991.89 | 0.141 | 0 | 1286572.11 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP006 | 2025-10 | 2025-06-26 | 2121295.11 | 1654564 | -466731.11 | 466731.11 | 1 | 2025-10-28 | 2 | 2440559.36 | -319264.25 | DOWN | 0.1505 | 124 | Low | 463258.2 | 0.23 | 0 | 1191305.8 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP006 | 2025-10 | 2025-07-10 | 1936722.4 | 1654564 | -282158.4 | 282158.4 | 0 | 2025-10-28 | 3 | 2121295.11 | -184572.71 | DOWN | 0.0953 | 110 | Low | 536023.72 | 0.263 | 5 | 1118540.28 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP006 | 2025-10 | 2025-07-17 | 1820796.48 | 1654564 | -166232.48 | 166232.48 | 0 | 2025-10-28 | 4 | 1936722.4 | -115925.92 | DOWN | 0.0637 | 103 | Low | 485871.63 | 0.28 | 1 | 1168692.37 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP006 | 2025-10 | 2025-08-29 | 1742917.86 | 1654564 | -88353.86 | 88353.86 | 0 | 2025-10-28 | 5 | 1820796.48 | -77878.62 | DOWN | 0.0447 | 60 | Low | 699549.45 | 0.383 | 3 | 955014.55 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP006 | 2025-10 | 2025-09-29 | 1698186.67 | 1654564 | -43622.67 | 43622.67 | 0 | 2025-10-28 | 6 | 1742917.86 | -44731.19 | DOWN | 0.0263 | 29 | Medium | 758209.81 | 0.457 | 3 | 896354.19 | 16 | 1.37 | 1.4
P004 | Logistics | SUP006 | 2025-11 | 2025-06-22 | 382353.15 | 228070 | -154283.15 | 154283.15 | 1 | 2025-11-28 | 1 |  |  |  |  | 159 | Low | 59977.93 | 0.152 | 2 | 168092.07 | 7 | 0.59 | 1.31
P004 | Logistics | SUP006 | 2025-11 | 2025-06-25 | 320549.23 | 228070 | -92479.23 | 92479.23 | 1 | 2025-11-28 | 2 | 382353.15 | -61803.92 | DOWN | 0.1928 | 156 | Low | 50053.67 | 0.16 | 0 | 178016.33 | 7 | 0.59 | 1.31
P004 | Logistics | SUP006 | 2025-11 | 2025-06-29 | 277736.5 | 228070 | -49666.5 | 49666.5 | 1 | 2025-11-28 | 3 | 320549.23 | -42812.73 | DOWN | 0.1541 | 152 | Low | 44032.11 | 0.17 | 3 | 184037.89 | 7 | 0.59 | 1.31
P004 | Logistics | SUP006 | 2025-11 | 2025-07-07 | 255636.09 | 228070 | -27566.09 | 27566.09 | 0 | 2025-11-28 | 4 | 277736.5 | -22100.41 | DOWN | 0.0865 | 144 | Low | 47213.78 | 0.19 | 3 | 180856.22 | 7 | 0.59 | 1.31
P004 | Logistics | SUP006 | 2025-11 | 2025-07-23 | 244009.35 | 228070 | -15939.35 | 15939.35 | 0 | 2025-11-28 | 5 | 255636.09 | -11626.74 | DOWN | 0.0476 | 128 | Low | 53578.13 | 0.23 | 0 | 174491.87 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP006 | 2025-12 | 2025-07-07 | 199725.16 | 136081 | -63644.16 | 63644.16 | 1 | 2025-12-28 | 1 |  |  |  |  | 174 | Low | 22025.06 | 0.114 | 1 | 114055.94 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP006 | 2025-12 | 2025-08-01 | 174589.81 | 136081 | -38508.81 | 38508.81 | 1 | 2025-12-28 | 2 | 199725.16 | -25135.35 | DOWN | 0.144 | 149 | Low | 31504.92 | 0.175 | 0 | 104576.08 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP006 | 2025-12 | 2025-08-09 | 158591.76 | 136081 | -22510.76 | 22510.76 | 0 | 2025-12-28 | 3 | 174589.81 | -15998.05 | DOWN | 0.1009 | 141 | Low | 29509.76 | 0.195 | 1 | 106571.24 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP006 | 2025-12 | 2025-09-10 | 148868.49 | 136081 | -12787.49 | 12787.49 | 0 | 2025-12-28 | 4 | 158591.76 | -9723.27 | DOWN | 0.0653 | 109 | Low | 39771 | 0.274 | 0 | 96310 | 9 | 1.11 | 0.94
P004 | Services | SUP031 | 2025-01 | 2024-08-10 | 282547.4 | 166774 | -115773.4 | 115773.4 | 1 | 2025-01-28 | 1 |  |  |  |  | 171 | Low | 48347.78 | 0.174 | 1 | 118426.22 | 9 | 1 | 1.26
P004 | Services | SUP031 | 2025-01 | 2024-08-11 | 221315.19 | 166774 | -54541.19 | 54541.19 | 1 | 2025-01-28 | 2 | 282547.4 | -61232.21 | DOWN | 0.2767 | 170 | Low | 40876.25 | 0.177 | 3 | 125897.75 | 9 | 1 | 1.26
P004 | Services | SUP031 | 2025-01 | 2024-12-08 | 192682.11 | 166774 | -25908.11 | 25908.11 | 0 | 2025-01-28 | 3 | 221315.19 | -28633.08 | DOWN | 0.1486 | 51 | Low | 116906.97 | 0.599 | 7 | 49867.03 | 9 | 1 | 1.26
P004 | Mechanical | SUP031 | 2025-02 | 2024-09-15 | 2205053.63 | 1766856 | -438197.63 | 438197.63 | 1 | 2025-02-28 | 1 |  |  |  |  | 166 | Low | 398756.43 | 0.186 | 0 | 1368099.57 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP031 | 2025-02 | 2024-10-06 | 1959911.24 | 1766856 | -193055.24 | 193055.24 | 0 | 2025-02-28 | 2 | 2205053.63 | -245142.39 | DOWN | 0.1251 | 145 | Low | 487518.72 | 0.258 | 0 | 1279337.28 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP031 | 2025-02 | 2024-11-23 | 1854091.83 | 1766856 | -87235.83 | 87235.83 | 0 | 2025-02-28 | 3 | 1959911.24 | -105819.41 | DOWN | 0.0571 | 97 | Low | 766389.15 | 0.423 | 1 | 1000466.85 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP031 | 2025-02 | 2025-01-16 | 1814508.2 | 1766856 | -47652.2 | 47652.2 | 0 | 2025-02-28 | 4 | 1854091.83 | -39583.63 | DOWN | 0.0218 | 43 | Medium | 1135665.33 | 0.609 | 5 | 631190.67 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP031 | 2025-02 | 2025-02-06 | 1778814.59 | 1766856 | -11958.59 | 11958.59 | 0 | 2025-02-28 | 5 | 1814508.2 | -35693.61 | DOWN | 0.0201 | 22 | High | 1263450.89 | 0.681 | 2 | 503405.11 | 13 | 1.26 | 0.97
P004 | Services | SUP031 | 2025-03 | 2024-10-22 | 1311628.66 | 881866 | -429762.66 | 429762.66 | 1 | 2025-03-28 | 1 |  |  |  |  | 157 | Low | 285528.13 | 0.223 | 0 | 596337.87 | 11 | 0.73 | 1.3
P004 | Services | SUP031 | 2025-03 | 2024-11-23 | 1063097.94 | 881866 | -181231.94 | 181231.94 | 1 | 2025-03-28 | 2 | 1311628.66 | -248530.72 | DOWN | 0.2338 | 125 | Low | 375369.76 | 0.337 | 4 | 506496.24 | 11 | 0.73 | 1.3
P004 | Services | SUP031 | 2025-03 | 2024-11-24 | 952101.47 | 881866 | -70235.47 | 70235.47 | 0 | 2025-03-28 | 3 | 1063097.94 | -110996.47 | DOWN | 0.1166 | 124 | Low | 311829.23 | 0.34 | 3 | 570036.77 | 11 | 0.73 | 1.3
P004 | Services | SUP031 | 2025-03 | 2024-12-04 | 924248.43 | 881866 | -42382.43 | 42382.43 | 0 | 2025-03-28 | 4 | 952101.47 | -27853.04 | DOWN | 0.0301 | 114 | Low | 370049.16 | 0.376 | 7 | 511816.84 | 11 | 0.73 | 1.3
P004 | Software | SUP031 | 2025-04 | 2024-12-16 | 265838.53 | 173432 | -92406.53 | 92406.53 | 1 | 2025-04-28 | 1 |  |  |  |  | 133 | Low | 79204.11 | 0.285 | 2 | 94227.89 | 15 | 1.69 | 1.47
P004 | Software | SUP031 | 2025-04 | 2025-02-20 | 214645.72 | 173432 | -41213.72 | 41213.72 | 1 | 2025-04-28 | 2 | 265838.53 | -51192.81 | DOWN | 0.2385 | 67 | Low | 112465.21 | 0.501 | 0 | 60966.79 | 15 | 1.69 | 1.47
P004 | Software | SUP031 | 2025-04 | 2025-03-30 | 194897.32 | 173432 | -21465.32 | 21465.32 | 0 | 2025-04-28 | 3 | 214645.72 | -19748.4 | DOWN | 0.1013 | 29 | Medium | 113747.35 | 0.625 | 5 | 59684.65 | 15 | 1.69 | 1.47
P004 | Electronics | SUP031 | 2025-05 | 2025-01-07 | 2430389.01 | 1700744 | -729645.01 | 729645.01 | 1 | 2025-05-28 | 1 |  |  |  |  | 141 | Low | 679447.1 | 0.279 | 0 | 1021296.9 | 12 | 1.03 | 1.42
P004 | Electronics | SUP031 | 2025-05 | 2025-01-09 | 2029245.1 | 1700744 | -328501.1 | 328501.1 | 1 | 2025-05-28 | 2 | 2430389.01 | -401143.91 | DOWN | 0.1977 | 139 | Low | 598226.9 | 0.286 | 0 | 1102517.1 | 12 | 1.03 | 1.42
P004 | Electronics | SUP031 | 2025-05 | 2025-02-20 | 1845795.85 | 1700744 | -145051.85 | 145051.85 | 0 | 2025-05-28 | 3 | 2029245.1 | -183449.25 | DOWN | 0.0994 | 97 | Low | 738890.69 | 0.435 | 3 | 961853.31 | 12 | 1.03 | 1.42
P004 | Logistics | SUP031 | 2025-06 | 2025-02-24 | 827389.18 | 516967 | -310422.18 | 310422.18 | 1 | 2025-06-28 | 1 |  |  |  |  | 124 | Low | 271455.44 | 0.34 | 2 | 245511.56 | 15 | 0.81 | 1.56
P004 | Logistics | SUP031 | 2025-06 | 2025-03-24 | 661749.45 | 516967 | -144782.45 | 144782.45 | 1 | 2025-06-28 | 2 | 827389.18 | -165639.73 | DOWN | 0.2503 | 96 | Low | 281729.73 | 0.44 | 6 | 235237.27 | 15 | 0.81 | 1.56
P004 | Logistics | SUP031 | 2025-06 | 2025-05-20 | 590246.59 | 516967 | -73279.59 | 73279.59 | 0 | 2025-06-28 | 3 | 661749.45 | -71502.86 | DOWN | 0.1211 | 39 | Low | 377019.47 | 0.642 | 2 | 139947.53 | 15 | 0.81 | 1.56
P004 | Logistics | SUP031 | 2025-06 | 2025-06-03 | 550817.67 | 516967 | -33850.67 | 33850.67 | 0 | 2025-06-28 | 4 | 590246.59 | -39428.92 | DOWN | 0.0716 | 25 | Medium | 370587.45 | 0.691 | 6 | 146379.55 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP031 | 2025-07 | 2025-02-07 | 150000.07 | 110490 | -39510.07 | 39510.07 | 1 | 2025-07-28 | 1 |  |  |  |  | 171 | Low | 23291.23 | 0.16 | 3 | 87198.77 | 10 | 1.72 | 1
P004 | Mechanical | SUP031 | 2025-07 | 2025-03-20 | 128551.92 | 110490 | -18061.92 | 18061.92 | 0 | 2025-07-28 | 2 | 150000.07 | -21448.15 | DOWN | 0.1668 | 130 | Low | 40461.63 | 0.294 | 0 | 70028.37 | 10 | 1.72 | 1
P004 | Mechanical | SUP031 | 2025-07 | 2025-05-13 | 119148.21 | 110490 | -8658.21 | 8658.21 | 0 | 2025-07-28 | 3 | 128551.92 | -9403.71 | DOWN | 0.0789 | 76 | Low | 59323.42 | 0.47 | 6 | 51166.58 | 10 | 1.72 | 1
P004 | Mechanical | SUP031 | 2025-07 | 2025-06-11 | 114622.21 | 110490 | -4132.21 | 4132.21 | 0 | 2025-07-28 | 4 | 119148.21 | -4526 | DOWN | 0.0395 | 47 | Medium | 69844.86 | 0.565 | 5 | 40645.14 | 10 | 1.72 | 1
P004 | Mechanical | SUP031 | 2025-07 | 2025-07-02 | 114155.25 | 110490 | -3665.25 | 3665.25 | 0 | 2025-07-28 | 5 | 114622.21 | -466.96 | DOWN | 0.0041 | 26 | Medium | 69839.86 | 0.633 | 7 | 40650.14 | 10 | 1.72 | 1
P004 | Mechanical | SUP031 | 2025-07 | 2025-07-11 | 113588.71 | 110490 | -3098.71 | 3098.71 | 0 | 2025-07-28 | 6 | 114155.25 | -566.54 | DOWN | 0.005 | 17 | Medium | 73012.08 | 0.662 | 5 | 37477.92 | 10 | 1.72 | 1
P004 | Mechanical | SUP031 | 2025-08 | 2025-04-09 | 3164007.14 | 2101990 | -1062017.14 | 1062017.14 | 1 | 2025-08-28 | 1 |  |  |  |  | 141 | Low | 848584.46 | 0.266 | 3 | 1253405.54 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP031 | 2025-08 | 2025-05-01 | 2595278.24 | 2101990 | -493288.24 | 493288.24 | 1 | 2025-08-28 | 2 | 3164007.14 | -568728.9 | DOWN | 0.2191 | 119 | Low | 904912.67 | 0.34 | 5 | 1197077.33 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP031 | 2025-08 | 2025-05-07 | 2317748.63 | 2101990 | -215758.63 | 215758.63 | 0 | 2025-08-28 | 3 | 2595278.24 | -277529.61 | DOWN | 0.1197 | 113 | Low | 829142.51 | 0.36 | 6 | 1272847.49 | 13 | 1.45 | 1.13
P004 | Services | SUP031 | 2025-09 | 2025-04-14 | 2547934.48 | 1659471 | -888463.48 | 888463.48 | 1 | 2025-09-28 | 1 |  |  |  |  | 167 | Low | 429081.66 | 0.181 | 0 | 1230389.34 | 12 | 1.31 | 1.3
P004 | Services | SUP031 | 2025-09 | 2025-07-27 | 2066205.59 | 1659471 | -406734.59 | 406734.59 | 1 | 2025-09-28 | 2 | 2547934.48 | -481728.89 | DOWN | 0.2331 | 63 | Low | 1026440.61 | 0.537 | 7 | 633030.39 | 12 | 1.31 | 1.3
P004 | Services | SUP031 | 2025-09 | 2025-08-31 | 1855141.24 | 1659471 | -195670.24 | 195670.24 | 0 | 2025-09-28 | 3 | 2066205.59 | -211064.35 | DOWN | 0.1138 | 28 | Medium | 1255233.99 | 0.656 | 3 | 404237.01 | 12 | 1.31 | 1.3
P004 | Services | SUP031 | 2025-09 | 2025-09-18 | 1754995.07 | 1659471 | -95524.07 | 95524.07 | 0 | 2025-09-28 | 4 | 1855141.24 | -100146.17 | DOWN | 0.0571 | 10 | High | 1264634.71 | 0.714 | 7 | 394836.29 | 12 | 1.31 | 1.3
P004 | Software | SUP031 | 2025-10 | 2025-05-13 | 184890.1 | 129267 | -55623.1 | 55623.1 | 1 | 2025-10-28 | 1 |  |  |  |  | 168 | Low | 30355.42 | 0.177 | 2 | 98911.58 | 16 | 1.37 | 1.4
P004 | Software | SUP031 | 2025-10 | 2025-06-09 | 156004.45 | 129267 | -26737.45 | 26737.45 | 1 | 2025-10-28 | 2 | 184890.1 | -28885.65 | DOWN | 0.1852 | 141 | Low | 39779.08 | 0.268 | 4 | 89487.92 | 16 | 1.37 | 1.4
P004 | Software | SUP031 | 2025-10 | 2025-07-16 | 139215.03 | 129267 | -9948.03 | 9948.03 | 0 | 2025-10-28 | 3 | 156004.45 | -16789.42 | DOWN | 0.1206 | 104 | Low | 54307.84 | 0.394 | 3 | 74959.16 | 16 | 1.37 | 1.4
P004 | Software | SUP031 | 2025-10 | 2025-09-03 | 135715.65 | 129267 | -6448.65 | 6448.65 | 0 | 2025-10-28 | 4 | 139215.03 | -3499.38 | DOWN | 0.0258 | 55 | Medium | 70182.07 | 0.56 | 7 | 59084.93 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP031 | 2025-11 | 2025-07-17 | 1058892.22 | 737833 | -321059.22 | 321059.22 | 1 | 2025-11-28 | 1 |  |  |  |  | 134 | Low | 334302.93 | 0.305 | 0 | 403530.07 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP031 | 2025-11 | 2025-08-31 | 882594.51 | 737833 | -144761.51 | 144761.51 | 1 | 2025-11-28 | 2 | 1058892.22 | -176297.71 | DOWN | 0.1997 | 89 | Low | 380948.3 | 0.464 | 2 | 356884.7 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP031 | 2025-11 | 2025-09-22 | 798357.19 | 737833 | -60524.19 | 60524.19 | 0 | 2025-11-28 | 3 | 882594.51 | -84237.32 | DOWN | 0.1055 | 67 | Low | 411246.79 | 0.542 | 1 | 326586.21 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP031 | 2025-11 | 2025-10-09 | 769465.47 | 737833 | -31632.47 | 31632.47 | 0 | 2025-11-28 | 4 | 798357.19 | -28891.72 | DOWN | 0.0375 | 50 | Medium | 491269.88 | 0.603 | 3 | 246563.12 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP031 | 2025-12 | 2025-08-05 | 665842.54 | 487995 | -177847.54 | 177847.54 | 1 | 2025-12-28 | 1 |  |  |  |  | 145 | Low | 173171.56 | 0.262 | 3 | 314823.44 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP031 | 2025-12 | 2025-09-08 | 565978.31 | 487995 | -77983.31 | 77983.31 | 0 | 2025-12-28 | 2 | 665842.54 | -99864.23 | DOWN | 0.1764 | 111 | Low | 202839.49 | 0.381 | 6 | 285155.51 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP031 | 2025-12 | 2025-10-25 | 522844.42 | 487995 | -34849.42 | 34849.42 | 0 | 2025-12-28 | 3 | 565978.31 | -43133.89 | DOWN | 0.0825 | 64 | Low | 303485.35 | 0.546 | 4 | 184509.65 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP031 | 2025-12 | 2025-12-03 | 506431.99 | 487995 | -18436.99 | 18436.99 | 0 | 2025-12-28 | 4 | 522844.42 | -16412.43 | DOWN | 0.0324 | 25 | High | 343522.83 | 0.682 | 5 | 144472.17 | 9 | 1.11 | 0.94
P004 | Logistics | SUP024 | 2025-01 | 2024-08-08 | 4614082.44 | 2031804 | -2582278.44 | 2582278.44 | 1 | 2025-01-28 | 1 |  |  |  |  | 173 | Low | 612693.38 | 0.139 | 0 | 1419110.62 | 9 | 1 | 1.26
P004 | Logistics | SUP024 | 2025-01 | 2024-10-21 | 3493470.1 | 2031804 | -1461666.1 | 1461666.1 | 1 | 2025-01-28 | 2 | 4614082.44 | -1120612.34 | DOWN | 0.3208 | 99 | Low | 1328906.21 | 0.358 | 1 | 702897.79 | 9 | 1 | 1.26
P004 | Logistics | SUP024 | 2025-01 | 2024-11-07 | 2793676.93 | 2031804 | -761872.93 | 761872.93 | 1 | 2025-01-28 | 3 | 3493470.1 | -699793.17 | DOWN | 0.2505 | 82 | Low | 1051175.37 | 0.408 | 1 | 980628.63 | 9 | 1 | 1.26
P004 | Logistics | SUP024 | 2025-01 | 2024-11-29 | 2418951.74 | 2031804 | -387147.74 | 387147.74 | 1 | 2025-01-28 | 4 | 2793676.93 | -374725.19 | DOWN | 0.1549 | 60 | Low | 1072079.93 | 0.473 | 8 | 959724.07 | 9 | 1 | 1.26
P004 | Logistics | SUP024 | 2025-01 | 2024-12-19 | 2216505.9 | 2031804 | -184701.9 | 184701.9 | 0 | 2025-01-28 | 5 | 2418951.74 | -202445.84 | DOWN | 0.0913 | 40 | Medium | 1141691.52 | 0.532 | 4 | 890112.48 | 9 | 1 | 1.26
P004 | Services | SUP024 | 2025-02 | 2024-09-17 | 3353749.7 | 1620198 | -1733551.7 | 1733551.7 | 1 | 2025-02-28 | 1 |  |  |  |  | 164 | Low | 573649.74 | 0.16 | 1 | 1046548.26 | 13 | 1.26 | 0.97
P004 | Services | SUP024 | 2025-02 | 2024-11-05 | 2543203.99 | 1620198 | -923005.99 | 923005.99 | 1 | 2025-02-28 | 2 | 3353749.7 | -810545.71 | DOWN | 0.3187 | 115 | Low | 789114.18 | 0.301 | 7 | 831083.82 | 13 | 1.26 | 0.97
P004 | Services | SUP024 | 2025-02 | 2025-01-23 | 2166300.19 | 1620198 | -546102.19 | 546102.19 | 1 | 2025-02-28 | 3 | 2543203.99 | -376903.8 | DOWN | 0.174 | 36 | Low | 1087639.98 | 0.527 | 1 | 532558.02 | 13 | 1.26 | 0.97
P004 | Electronics | SUP024 | 2025-03 | 2024-11-02 | 1498786.49 | 919730 | -579056.49 | 579056.49 | 1 | 2025-03-28 | 1 |  |  |  |  | 146 | Low | 323266.12 | 0.219 | 1 | 596463.88 | 11 | 0.73 | 1.3
P004 | Electronics | SUP024 | 2025-03 | 2024-12-24 | 1238487.96 | 919730 | -318757.96 | 318757.96 | 1 | 2025-03-28 | 2 | 1498786.49 | -260298.53 | DOWN | 0.2102 | 94 | Low | 482689.95 | 0.372 | 0 | 437040.05 | 11 | 0.73 | 1.3
P004 | Electronics | SUP024 | 2025-03 | 2025-02-25 | 1085089.03 | 919730 | -165359.03 | 165359.03 | 1 | 2025-03-28 | 3 | 1238487.96 | -153398.93 | DOWN | 0.1414 | 31 | Low | 582123.37 | 0.558 | 9 | 337606.63 | 11 | 0.73 | 1.3
P004 | Electronics | SUP024 | 2025-03 | 2025-03-09 | 1020254.52 | 919730 | -100524.52 | 100524.52 | 0 | 2025-03-28 | 4 | 1085089.03 | -64834.51 | DOWN | 0.0635 | 19 | Medium | 625551.11 | 0.594 | 4 | 294178.89 | 11 | 0.73 | 1.3
P004 | Software | SUP024 | 2025-04 | 2025-01-12 | 1790828.64 | 872495 | -918333.64 | 918333.64 | 1 | 2025-04-28 | 1 |  |  |  |  | 106 | Low | 550720.75 | 0.311 | 4 | 321774.25 | 15 | 1.69 | 1.47
P004 | Software | SUP024 | 2025-04 | 2025-01-19 | 1362111.4 | 872495 | -489616.4 | 489616.4 | 1 | 2025-04-28 | 2 | 1790828.64 | -428717.24 | DOWN | 0.3147 | 99 | Low | 448563.03 | 0.33 | 0 | 423931.97 | 15 | 1.69 | 1.47
P004 | Software | SUP024 | 2025-04 | 2025-02-03 | 1112516.93 | 872495 | -240021.93 | 240021.93 | 1 | 2025-04-28 | 3 | 1362111.4 | -249594.47 | DOWN | 0.2244 | 84 | Low | 430871.43 | 0.371 | 2 | 441623.57 | 15 | 1.69 | 1.47
P004 | Software | SUP024 | 2025-04 | 2025-02-15 | 995318.88 | 872495 | -122823.88 | 122823.88 | 0 | 2025-04-28 | 4 | 1112516.93 | -117198.05 | DOWN | 0.1177 | 72 | Low | 394693.49 | 0.404 | 4 | 477801.51 | 15 | 1.69 | 1.47
P004 | Software | SUP024 | 2025-04 | 2025-04-14 | 959710.75 | 872495 | -87215.75 | 87215.75 | 0 | 2025-04-28 | 5 | 995318.88 | -35608.13 | DOWN | 0.0371 | 14 | Medium | 518171.33 | 0.562 | 8 | 354323.67 | 15 | 1.69 | 1.47
P004 | Electronics | SUP024 | 2025-05 | 2024-12-07 | 1897348.83 | 1171968 | -725380.83 | 725380.83 | 1 | 2025-05-28 | 1 |  |  |  |  | 172 | Low | 287445.54 | 0.141 | 0 | 884522.46 | 12 | 1.03 | 1.42
P004 | Electronics | SUP024 | 2025-05 | 2024-12-12 | 1593626.47 | 1171968 | -421658.47 | 421658.47 | 1 | 2025-05-28 | 2 | 1897348.83 | -303722.36 | DOWN | 0.1906 | 167 | Low | 236123.5 | 0.156 | 2 | 935844.5 | 12 | 1.03 | 1.42
P004 | Electronics | SUP024 | 2025-05 | 2025-03-16 | 1413110.08 | 1171968 | -241142.08 | 241142.08 | 1 | 2025-05-28 | 3 | 1593626.47 | -180516.39 | DOWN | 0.1277 | 73 | Low | 584370.38 | 0.433 | 2 | 587597.62 | 12 | 1.03 | 1.42
P004 | Electronics | SUP024 | 2025-05 | 2025-03-18 | 1307442.81 | 1171968 | -135474.81 | 135474.81 | 0 | 2025-05-28 | 4 | 1413110.08 | -105667.27 | DOWN | 0.0808 | 71 | Low | 572326.24 | 0.439 | 1 | 599641.76 | 12 | 1.03 | 1.42
P004 | Services | SUP024 | 2025-06 | 2025-01-06 | 3436140.65 | 1962424 | -1473716.65 | 1473716.65 | 1 | 2025-06-28 | 1 |  |  |  |  | 173 | Low | 454137.24 | 0.139 | 2 | 1508286.76 | 15 | 0.81 | 1.56
P004 | Services | SUP024 | 2025-06 | 2025-03-04 | 2745895.91 | 1962424 | -783471.91 | 783471.91 | 1 | 2025-06-28 | 2 | 3436140.65 | -690244.74 | DOWN | 0.2514 | 116 | Low | 778448.54 | 0.307 | 2 | 1183975.46 | 15 | 0.81 | 1.56
P004 | Services | SUP024 | 2025-06 | 2025-03-04 | 2399775.53 | 1962424 | -437351.53 | 437351.53 | 1 | 2025-06-28 | 3 | 2745895.91 | -346120.38 | DOWN | 0.1442 | 116 | Low | 757622.17 | 0.307 | 0 | 1204801.83 | 15 | 0.81 | 1.56
P004 | Services | SUP024 | 2025-06 | 2025-03-09 | 2187897.95 | 1962424 | -225473.95 | 225473.95 | 0 | 2025-06-28 | 4 | 2399775.53 | -211877.58 | DOWN | 0.0968 | 111 | Low | 682332 | 0.322 | 0 | 1280092 | 15 | 0.81 | 1.56
P004 | Services | SUP024 | 2025-06 | 2025-04-01 | 2103071.36 | 1962424 | -140647.36 | 140647.36 | 0 | 2025-06-28 | 5 | 2187897.95 | -84826.59 | DOWN | 0.0403 | 88 | Low | 848206.57 | 0.39 | 3 | 1114217.43 | 15 | 0.81 | 1.56
P004 | Services | SUP024 | 2025-06 | 2025-06-11 | 2017019.23 | 1962424 | -54595.23 | 54595.23 | 0 | 2025-06-28 | 6 | 2103071.36 | -86052.13 | DOWN | 0.0427 | 17 | Medium | 1135811.75 | 0.6 | 2 | 826612.25 | 15 | 0.81 | 1.56
P004 | Software | SUP024 | 2025-07 | 2025-02-06 | 972693.66 | 537889 | -434804.66 | 434804.66 | 1 | 2025-07-28 | 1 |  |  |  |  | 172 | Low | 123190.01 | 0.131 | 4 | 414698.99 | 10 | 1.72 | 1
P004 | Software | SUP024 | 2025-07 | 2025-02-11 | 765105.52 | 537889 | -227216.52 | 227216.52 | 1 | 2025-07-28 | 2 | 972693.66 | -207588.14 | DOWN | 0.2713 | 167 | Low | 118387.99 | 0.144 | 3 | 419501.01 | 10 | 1.72 | 1
P004 | Software | SUP024 | 2025-07 | 2025-02-20 | 669943.53 | 537889 | -132054.53 | 132054.53 | 1 | 2025-07-28 | 3 | 765105.52 | -95161.99 | DOWN | 0.142 | 158 | Low | 111344.16 | 0.169 | 1 | 426544.84 | 10 | 1.72 | 1
P004 | Software | SUP024 | 2025-07 | 2025-04-20 | 627460.88 | 537889 | -89571.88 | 89571.88 | 0 | 2025-07-28 | 4 | 669943.53 | -42482.65 | DOWN | 0.0677 | 99 | Low | 222535.41 | 0.329 | 4 | 315353.59 | 10 | 1.72 | 1
P004 | Software | SUP024 | 2025-07 | 2025-05-13 | 571112.48 | 537889 | -33223.48 | 33223.48 | 0 | 2025-07-28 | 5 | 627460.88 | -56348.4 | DOWN | 0.0987 | 76 | Low | 232515.89 | 0.392 | 5 | 305373.11 | 10 | 1.72 | 1
P004 | Materials | SUP024 | 2025-08 | 2025-05-21 | 4514299.7 | 2217468 | -2296831.7 | 2296831.7 | 1 | 2025-08-28 | 1 |  |  |  |  | 99 | Low | 1566233.75 | 0.339 | 1 | 651234.25 | 13 | 1.45 | 1.13
P004 | Materials | SUP024 | 2025-08 | 2025-05-25 | 3526742.92 | 2217468 | -1309274.92 | 1309274.92 | 1 | 2025-08-28 | 2 | 4514299.7 | -987556.78 | DOWN | 0.28 | 95 | Low | 1275586.75 | 0.35 | 5 | 941881.25 | 13 | 1.45 | 1.13
P004 | Materials | SUP024 | 2025-08 | 2025-06-25 | 2916921.44 | 2217468 | -699453.44 | 699453.44 | 1 | 2025-08-28 | 3 | 3526742.92 | -609821.48 | DOWN | 0.2091 | 64 | Low | 1269191.15 | 0.437 | 5 | 948276.85 | 13 | 1.45 | 1.13
P004 | Electronics | SUP024 | 2025-09 | 2025-06-13 | 831815.1 | 482218 | -349597.1 | 349597.1 | 1 | 2025-09-28 | 1 |  |  |  |  | 107 | Low | 278336.66 | 0.322 | 4 | 203881.34 | 12 | 1.31 | 1.3
P004 | Electronics | SUP024 | 2025-09 | 2025-06-25 | 681622.72 | 482218 | -199404.72 | 199404.72 | 1 | 2025-09-28 | 2 | 831815.1 | -150192.38 | DOWN | 0.2203 | 95 | Low | 258243.26 | 0.356 | 4 | 223974.74 | 12 | 1.31 | 1.3
P004 | Electronics | SUP024 | 2025-09 | 2025-08-04 | 591299.82 | 482218 | -109081.82 | 109081.82 | 1 | 2025-09-28 | 3 | 681622.72 | -90322.9 | DOWN | 0.1528 | 55 | Low | 290055.78 | 0.47 | 4 | 192162.22 | 12 | 1.31 | 1.3
P004 | Electronics | SUP024 | 2025-09 | 2025-08-11 | 542715.52 | 482218 | -60497.52 | 60497.52 | 0 | 2025-09-28 | 4 | 591299.82 | -48584.3 | DOWN | 0.0895 | 48 | Medium | 272756.17 | 0.49 | 0 | 209461.83 | 12 | 1.31 | 1.3
P004 | Electronics | SUP024 | 2025-09 | 2025-08-25 | 512679.47 | 482218 | -30461.47 | 30461.47 | 0 | 2025-09-28 | 5 | 542715.52 | -30036.05 | DOWN | 0.0586 | 34 | Medium | 253252.15 | 0.53 | 8 | 228965.85 | 12 | 1.31 | 1.3
P004 | Materials | SUP024 | 2025-10 | 2025-06-16 | 2006155.34 | 1235280 | -770875.34 | 770875.34 | 1 | 2025-10-28 | 1 |  |  |  |  | 134 | Low | 482253.15 | 0.243 | 2 | 753026.85 | 16 | 1.37 | 1.4
P004 | Materials | SUP024 | 2025-10 | 2025-07-14 | 1652026.14 | 1235280 | -416746.14 | 416746.14 | 1 | 2025-10-28 | 2 | 2006155.34 | -354129.2 | DOWN | 0.2144 | 106 | Low | 534868.59 | 0.322 | 0 | 700411.41 | 16 | 1.37 | 1.4
P004 | Materials | SUP024 | 2025-10 | 2025-08-13 | 1462346.49 | 1235280 | -227066.49 | 227066.49 | 1 | 2025-10-28 | 3 | 1652026.14 | -189679.65 | DOWN | 0.1297 | 76 | Low | 563766.79 | 0.407 | 2 | 671513.21 | 16 | 1.37 | 1.4
P004 | Materials | SUP024 | 2025-10 | 2025-08-20 | 1360269.25 | 1235280 | -124989.25 | 124989.25 | 0 | 2025-10-28 | 4 | 1462346.49 | -102077.24 | DOWN | 0.075 | 69 | Low | 577692.97 | 0.427 | 7 | 657587.03 | 16 | 1.37 | 1.4
P004 | Materials | SUP024 | 2025-10 | 2025-09-14 | 1295340.38 | 1235280 | -60060.38 | 60060.38 | 0 | 2025-10-28 | 5 | 1360269.25 | -64928.87 | DOWN | 0.0501 | 44 | Medium | 661460.15 | 0.498 | 2 | 573819.85 | 16 | 1.37 | 1.4
P004 | Materials | SUP024 | 2025-10 | 2025-09-29 | 1277577.65 | 1235280 | -42297.65 | 42297.65 | 0 | 2025-10-28 | 6 | 1295340.38 | -17762.73 | DOWN | 0.0139 | 29 | Medium | 641552.36 | 0.54 | 4 | 593727.64 | 16 | 1.37 | 1.4
P004 | Software | SUP024 | 2025-11 | 2025-08-09 | 734427.31 | 373575 | -360852.31 | 360852.31 | 1 | 2025-11-28 | 1 |  |  |  |  | 111 | Low | 236450.67 | 0.322 | 0 | 137124.33 | 7 | 0.59 | 1.31
P004 | Software | SUP024 | 2025-11 | 2025-08-16 | 570379.2 | 373575 | -196804.2 | 196804.2 | 1 | 2025-11-28 | 2 | 734427.31 | -164048.11 | DOWN | 0.2876 | 104 | Low | 192422.4 | 0.343 | 2 | 181152.6 | 7 | 0.59 | 1.31
P004 | Software | SUP024 | 2025-11 | 2025-09-05 | 481146.5 | 373575 | -107571.5 | 107571.5 | 1 | 2025-11-28 | 3 | 570379.2 | -89232.7 | DOWN | 0.1855 | 84 | Low | 194506.86 | 0.402 | 2 | 179068.14 | 7 | 0.59 | 1.31
P004 | Software | SUP024 | 2025-11 | 2025-09-11 | 428660.96 | 373575 | -55085.96 | 55085.96 | 0 | 2025-11-28 | 4 | 481146.5 | -52485.54 | DOWN | 0.1224 | 78 | Low | 184154.85 | 0.42 | 0 | 189420.15 | 7 | 0.59 | 1.31
P004 | Software | SUP024 | 2025-11 | 2025-10-05 | 406735.99 | 373575 | -33160.99 | 33160.99 | 0 | 2025-11-28 | 5 | 428660.96 | -21924.97 | DOWN | 0.0539 | 54 | Medium | 200061.05 | 0.49 | 4 | 173513.95 | 7 | 0.59 | 1.31
P004 | Software | SUP024 | 2025-11 | 2025-10-06 | 392128.83 | 373575 | -18553.83 | 18553.83 | 0 | 2025-11-28 | 6 | 406735.99 | -14607.16 | DOWN | 0.0373 | 53 | Medium | 196059.75 | 0.493 | 5 | 177515.25 | 7 | 0.59 | 1.31
P004 | Software | SUP024 | 2025-12 | 2025-07-09 | 1318853.45 | 655194 | -663659.45 | 663659.45 | 1 | 2025-12-28 | 1 |  |  |  |  | 172 | Low | 173002.93 | 0.14 | 0 | 482191.07 | 9 | 1.11 | 0.94
P004 | Software | SUP024 | 2025-12 | 2025-08-26 | 1002700.31 | 655194 | -347506.31 | 347506.31 | 1 | 2025-12-28 | 2 | 1318853.45 | -316153.14 | DOWN | 0.3153 | 124 | Low | 273947.84 | 0.28 | 2 | 381246.16 | 9 | 1.11 | 0.94
P004 | Software | SUP024 | 2025-12 | 2025-10-16 | 833452.48 | 655194 | -178258.48 | 178258.48 | 1 | 2025-12-28 | 3 | 1002700.31 | -169247.83 | DOWN | 0.2031 | 73 | Low | 361240.11 | 0.429 | 3 | 293953.89 | 9 | 1.11 | 0.94
P004 | Software | SUP024 | 2025-12 | 2025-11-23 | 766583.11 | 655194 | -111389.11 | 111389.11 | 0 | 2025-12-28 | 4 | 833452.48 | -66869.37 | DOWN | 0.0872 | 35 | Medium | 405653.2 | 0.539 | 2 | 249540.8 | 9 | 1.11 | 0.94
P004 | Materials | SUP005 | 2025-01 | 2024-08-10 | 3469079.42 | 2640951 | -828128.42 | 828128.42 | 1 | 2025-01-28 | 1 |  |  |  |  | 171 | Low | 627405.52 | 0.174 | 2 | 2013545.48 | 9 | 1 | 1.26
P004 | Materials | SUP005 | 2025-01 | 2024-08-11 | 3022534.68 | 2640951 | -381583.68 | 381583.68 | 0 | 2025-01-28 | 2 | 3469079.42 | -446544.74 | DOWN | 0.1477 | 170 | Low | 503695.15 | 0.177 | 0 | 2137255.85 | 9 | 1 | 1.26
P004 | Materials | SUP005 | 2025-01 | 2024-09-03 | 2828023.55 | 2640951 | -187072.55 | 187072.55 | 0 | 2025-01-28 | 3 | 3022534.68 | -194511.13 | DOWN | 0.0688 | 147 | Low | 716901.75 | 0.259 | 4 | 1924049.25 | 9 | 1 | 1.26
P004 | Materials | SUP005 | 2025-01 | 2024-11-03 | 2701170.98 | 2640951 | -60219.98 | 60219.98 | 0 | 2025-01-28 | 4 | 2828023.55 | -126852.57 | DOWN | 0.047 | 86 | Low | 1250664.53 | 0.475 | 3 | 1390286.47 | 9 | 1 | 1.26
P004 | Materials | SUP005 | 2025-01 | 2024-12-24 | 2692324.03 | 2640951 | -51373.03 | 51373.03 | 0 | 2025-01-28 | 5 | 2701170.98 | -8846.95 | DOWN | 0.0033 | 35 | Medium | 1882124.57 | 0.656 | 5 | 758826.43 | 9 | 1 | 1.26
P004 | Materials | SUP005 | 2025-01 | 2025-01-01 | 2658539.8 | 2640951 | -17588.8 | 17588.8 | 0 | 2025-01-28 | 6 | 2692324.03 | -33784.23 | DOWN | 0.0127 | 27 | High | 1906309.19 | 0.684 | 4 | 734641.81 | 9 | 1 | 1.26
P004 | Software | SUP005 | 2025-02 | 2024-10-08 | 2092684.57 | 1228255 | -864429.57 | 864429.57 | 1 | 2025-02-28 | 1 |  |  |  |  | 143 | Low | 580841.4 | 0.265 | 1 | 647413.6 | 13 | 1.26 | 0.97
P004 | Software | SUP005 | 2025-02 | 2024-10-22 | 1645879.68 | 1228255 | -417624.68 | 417624.68 | 1 | 2025-02-28 | 2 | 2092684.57 | -446804.89 | DOWN | 0.2715 | 129 | Low | 539955.39 | 0.313 | 1 | 688299.61 | 13 | 1.26 | 0.97
P004 | Software | SUP005 | 2025-02 | 2025-01-04 | 1436600.7 | 1228255 | -208345.7 | 208345.7 | 0 | 2025-02-28 | 3 | 1645879.68 | -209278.98 | DOWN | 0.1457 | 55 | Low | 797044.59 | 0.567 | 5 | 431210.41 | 13 | 1.26 | 0.97
P004 | Software | SUP005 | 2025-02 | 2025-01-17 | 1335870.65 | 1228255 | -107615.65 | 107615.65 | 0 | 2025-02-28 | 4 | 1436600.7 | -100730.05 | DOWN | 0.0754 | 42 | Medium | 856437.53 | 0.612 | 2 | 371817.47 | 13 | 1.26 | 0.97
P004 | Software | SUP005 | 2025-02 | 2025-01-28 | 1284086.95 | 1228255 | -55831.95 | 55831.95 | 0 | 2025-02-28 | 5 | 1335870.65 | -51783.7 | DOWN | 0.0403 | 31 | Medium | 817186.33 | 0.65 | 7 | 411068.67 | 13 | 1.26 | 0.97
P004 | Electronics | SUP005 | 2025-03 | 2024-11-06 | 393938.49 | 274549 | -119389.49 | 119389.49 | 1 | 2025-03-28 | 1 |  |  |  |  | 142 | Low | 110466.99 | 0.277 | 0 | 164082.01 | 11 | 0.73 | 1.3
P004 | Electronics | SUP005 | 2025-03 | 2024-12-28 | 330774.4 | 274549 | -56225.4 | 56225.4 | 1 | 2025-03-28 | 2 | 393938.49 | -63164.09 | DOWN | 0.191 | 90 | Low | 151581.08 | 0.461 | 4 | 122967.92 | 11 | 0.73 | 1.3
P004 | Electronics | SUP005 | 2025-03 | 2025-02-25 | 302672.38 | 274549 | -28123.38 | 28123.38 | 0 | 2025-03-28 | 3 | 330774.4 | -28102.02 | DOWN | 0.0928 | 31 | Medium | 195848.77 | 0.67 | 2 | 78700.23 | 11 | 0.73 | 1.3
P004 | Electronics | SUP005 | 2025-03 | 2025-03-07 | 286620.96 | 274549 | -12071.96 | 12071.96 | 0 | 2025-03-28 | 4 | 302672.38 | -16051.42 | DOWN | 0.056 | 21 | High | 210766.43 | 0.706 | 7 | 63782.57 | 11 | 0.73 | 1.3
P004 | Software | SUP005 | 2025-04 | 2024-11-01 | 1787177.07 | 1170933 | -616244.07 | 616244.07 | 1 | 2025-04-28 | 1 |  |  |  |  | 178 | Low | 273219.83 | 0.144 | 0 | 897713.17 | 15 | 1.69 | 1.47
P004 | Software | SUP005 | 2025-04 | 2024-11-26 | 1435752.92 | 1170933 | -264819.92 | 264819.92 | 1 | 2025-04-28 | 2 | 1787177.07 | -351424.15 | DOWN | 0.2448 | 153 | Low | 296303.78 | 0.219 | 0 | 874629.22 | 15 | 1.69 | 1.47
P004 | Software | SUP005 | 2025-04 | 2024-12-22 | 1286493.77 | 1170933 | -115560.77 | 115560.77 | 0 | 2025-04-28 | 3 | 1435752.92 | -149259.15 | DOWN | 0.116 | 127 | Low | 421120.56 | 0.305 | 4 | 749812.44 | 15 | 1.69 | 1.47
P004 | Software | SUP005 | 2025-04 | 2025-02-15 | 1214262.43 | 1170933 | -43329.43 | 43329.43 | 0 | 2025-04-28 | 4 | 1286493.77 | -72231.34 | DOWN | 0.0595 | 72 | Low | 611962.92 | 0.485 | 0 | 558970.08 | 15 | 1.69 | 1.47
P004 | Software | SUP005 | 2025-04 | 2025-03-07 | 1186581.72 | 1170933 | -15648.72 | 15648.72 | 0 | 2025-04-28 | 5 | 1214262.43 | -27680.71 | DOWN | 0.0233 | 52 | Medium | 703930.9 | 0.55 | 4 | 467002.1 | 15 | 1.69 | 1.47
P004 | Software | SUP005 | 2025-04 | 2025-04-03 | 1181601.82 | 1170933 | -10668.82 | 10668.82 | 0 | 2025-04-28 | 6 | 1186581.72 | -4979.9 | DOWN | 0.0042 | 25 | Medium | 706919.21 | 0.638 | 3 | 464013.79 | 15 | 1.69 | 1.47
P004 | Electronics | SUP005 | 2025-05 | 2024-12-22 | 2086294.5 | 1330363 | -755931.5 | 755931.5 | 1 | 2025-05-28 | 1 |  |  |  |  | 157 | Low | 455499.71 | 0.223 | 0 | 874863.29 | 12 | 1.03 | 1.42
P004 | Electronics | SUP005 | 2025-05 | 2025-02-22 | 1656079.06 | 1330363 | -325716.06 | 325716.06 | 1 | 2025-05-28 | 2 | 2086294.5 | -430215.44 | DOWN | 0.2598 | 95 | Low | 734405.68 | 0.442 | 2 | 595957.32 | 12 | 1.03 | 1.42
P004 | Electronics | SUP005 | 2025-05 | 2025-05-17 | 1477626.06 | 1330363 | -147263.06 | 147263.06 | 0 | 2025-05-28 | 3 | 1656079.06 | -178453 | DOWN | 0.1208 | 11 | Low | 1084609.3 | 0.738 | 3 | 245753.7 | 12 | 1.03 | 1.42
P004 | Materials | SUP005 | 2025-06 | 2025-01-19 | 1669587.51 | 1134899 | -534688.51 | 534688.51 | 1 | 2025-06-28 | 1 |  |  |  |  | 160 | Low | 357745.93 | 0.213 | 3 | 777153.07 | 15 | 0.81 | 1.56
P004 | Materials | SUP005 | 2025-06 | 2025-01-22 | 1370293.86 | 1134899 | -235394.86 | 235394.86 | 1 | 2025-06-28 | 2 | 1669587.51 | -299293.65 | DOWN | 0.2184 | 157 | Low | 324134.41 | 0.223 | 1 | 810764.59 | 15 | 0.81 | 1.56
P004 | Materials | SUP005 | 2025-06 | 2025-02-28 | 1235030.54 | 1134899 | -100131.54 | 100131.54 | 0 | 2025-06-28 | 3 | 1370293.86 | -135263.32 | DOWN | 0.1095 | 120 | Low | 433897.65 | 0.355 | 1 | 701001.35 | 15 | 0.81 | 1.56
P004 | Materials | SUP005 | 2025-06 | 2025-03-05 | 1183114.84 | 1134899 | -48215.84 | 48215.84 | 0 | 2025-06-28 | 4 | 1235030.54 | -51915.7 | DOWN | 0.0439 | 115 | Low | 409324.4 | 0.372 | 3 | 725574.6 | 15 | 0.81 | 1.56
P004 | Logistics | SUP005 | 2025-07 | 2025-02-27 | 2285022.5 | 1322656 | -962366.5 | 962366.5 | 1 | 2025-07-28 | 1 |  |  |  |  | 151 | Low | 547719.58 | 0.225 | 2 | 774936.42 | 10 | 1.72 | 1
P004 | Logistics | SUP005 | 2025-07 | 2025-04-23 | 1732843.74 | 1322656 | -410187.74 | 410187.74 | 1 | 2025-07-28 | 2 | 2285022.5 | -552178.76 | DOWN | 0.3187 | 96 | Low | 735258.46 | 0.405 | 3 | 587397.54 | 10 | 1.72 | 1
P004 | Logistics | SUP005 | 2025-07 | 2025-04-24 | 1463001.82 | 1322656 | -140345.82 | 140345.82 | 0 | 2025-07-28 | 3 | 1732843.74 | -269841.92 | DOWN | 0.1844 | 95 | Low | 596212.57 | 0.408 | 2 | 726443.43 | 10 | 1.72 | 1
P004 | Logistics | SUP005 | 2025-07 | 2025-06-03 | 1402936.44 | 1322656 | -80280.44 | 80280.44 | 0 | 2025-07-28 | 4 | 1463001.82 | -60065.38 | DOWN | 0.0428 | 55 | Medium | 796589.3 | 0.538 | 4 | 526066.7 | 10 | 1.72 | 1
P004 | Software | SUP005 | 2025-08 | 2025-03-05 | 2575582.58 | 1887897 | -687685.58 | 687685.58 | 1 | 2025-08-28 | 1 |  |  |  |  | 176 | Low | 373376.39 | 0.148 | 0 | 1514520.61 | 13 | 1.45 | 1.13
P004 | Software | SUP005 | 2025-08 | 2025-03-21 | 2160090.19 | 1887897 | -272193.19 | 272193.19 | 0 | 2025-08-28 | 2 | 2575582.58 | -415492.39 | DOWN | 0.1923 | 160 | Low | 464138.74 | 0.202 | 2 | 1423758.26 | 13 | 1.45 | 1.13
P004 | Software | SUP005 | 2025-08 | 2025-05-03 | 2025004.83 | 1887897 | -137107.83 | 137107.83 | 0 | 2025-08-28 | 3 | 2160090.19 | -135085.36 | DOWN | 0.0667 | 117 | Low | 691599.99 | 0.346 | 0 | 1196297.01 | 13 | 1.45 | 1.13
P004 | Electronics | SUP005 | 2025-09 | 2025-04-26 | 3721977.1 | 2653117 | -1068860.1 | 1068860.1 | 1 | 2025-09-28 | 1 |  |  |  |  | 155 | Low | 776151.8 | 0.222 | 0 | 1876965.2 | 12 | 1.31 | 1.3
P004 | Electronics | SUP005 | 2025-09 | 2025-06-05 | 3173109.88 | 2653117 | -519992.88 | 519992.88 | 1 | 2025-09-28 | 2 | 3721977.1 | -548867.22 | DOWN | 0.173 | 115 | Low | 1067674.55 | 0.359 | 1 | 1585442.45 | 12 | 1.31 | 1.3
P004 | Electronics | SUP005 | 2025-09 | 2025-08-06 | 2921625.8 | 2653117 | -268508.8 | 268508.8 | 0 | 2025-09-28 | 3 | 3173109.88 | -251484.08 | DOWN | 0.0861 | 53 | Medium | 1645937.74 | 0.571 | 1 | 1007179.26 | 12 | 1.31 | 1.3
P004 | Electronics | SUP005 | 2025-09 | 2025-08-31 | 2785341.73 | 2653117 | -132224.73 | 132224.73 | 0 | 2025-09-28 | 4 | 2921625.8 | -136284.07 | DOWN | 0.0489 | 28 | High | 1760822.58 | 0.656 | 4 | 892294.42 | 12 | 1.31 | 1.3
P004 | Materials | SUP005 | 2025-10 | 2025-07-08 | 2410945.49 | 1849355 | -561590.49 | 561590.49 | 1 | 2025-10-28 | 1 |  |  |  |  | 112 | Low | 870463.6 | 0.367 | 3 | 978891.4 | 16 | 1.37 | 1.4
P004 | Materials | SUP005 | 2025-10 | 2025-08-12 | 2072816.77 | 1849355 | -223461.77 | 223461.77 | 0 | 2025-10-28 | 2 | 2410945.49 | -338128.72 | DOWN | 0.1631 | 77 | Low | 961293.8 | 0.485 | 0 | 888061.2 | 16 | 1.37 | 1.4
P004 | Materials | SUP005 | 2025-10 | 2025-09-30 | 1953027.95 | 1849355 | -103672.95 | 103672.95 | 0 | 2025-10-28 | 3 | 2072816.77 | -119788.82 | DOWN | 0.0613 | 28 | Medium | 1209978.7 | 0.652 | 5 | 639376.3 | 16 | 1.37 | 1.4
P004 | Software | SUP005 | 2025-11 | 2025-06-17 | 3285566.86 | 2213916 | -1071650.86 | 1071650.86 | 1 | 2025-11-28 | 1 |  |  |  |  | 164 | Low | 621331.24 | 0.199 | 0 | 1592584.76 | 7 | 0.59 | 1.31
P004 | Software | SUP005 | 2025-11 | 2025-08-01 | 2746571.41 | 2213916 | -532655.41 | 532655.41 | 1 | 2025-11-28 | 2 | 3285566.86 | -538995.45 | DOWN | 0.1962 | 119 | Low | 1044901.88 | 0.358 | 0 | 1169014.12 | 7 | 0.59 | 1.31
P004 | Software | SUP005 | 2025-11 | 2025-10-01 | 2448800.6 | 2213916 | -234884.6 | 234884.6 | 0 | 2025-11-28 | 3 | 2746571.41 | -297770.81 | DOWN | 0.1216 | 58 | Low | 1316593.14 | 0.574 | 6 | 897322.86 | 7 | 0.59 | 1.31
P004 | Software | SUP005 | 2025-11 | 2025-10-23 | 2336731.12 | 2213916 | -122815.12 | 122815.12 | 0 | 2025-11-28 | 4 | 2448800.6 | -112069.48 | DOWN | 0.048 | 36 | Medium | 1610076.87 | 0.652 | 6 | 603839.13 | 7 | 0.59 | 1.31
P004 | Logistics | SUP005 | 2025-12 | 2025-07-13 | 3162682.14 | 1965917 | -1196765.14 | 1196765.14 | 1 | 2025-12-28 | 1 |  |  |  |  | 168 | Low | 548825.05 | 0.182 | 0 | 1417091.95 | 9 | 1.11 | 0.94
P004 | Logistics | SUP005 | 2025-12 | 2025-08-04 | 2511133.53 | 1965917 | -545216.53 | 545216.53 | 1 | 2025-12-28 | 2 | 3162682.14 | -651548.61 | DOWN | 0.2595 | 146 | Low | 665721.58 | 0.259 | 0 | 1300195.42 | 9 | 1.11 | 0.94
P004 | Logistics | SUP005 | 2025-12 | 2025-10-12 | 2258238.3 | 1965917 | -292321.3 | 292321.3 | 0 | 2025-12-28 | 3 | 2511133.53 | -252895.23 | DOWN | 0.112 | 77 | Low | 1102344.78 | 0.5 | 2 | 863572.22 | 9 | 1.11 | 0.94
P004 | Logistics | SUP005 | 2025-12 | 2025-11-08 | 2102623.11 | 1965917 | -136706.11 | 136706.11 | 0 | 2025-12-28 | 4 | 2258238.3 | -155615.19 | DOWN | 0.074 | 50 | Medium | 1274271.61 | 0.595 | 2 | 691645.39 | 9 | 1.11 | 0.94
P004 | Logistics | SUP036 | 2025-01 | 2024-08-08 | 1342968.07 | 794126 | -548842.07 | 548842.07 | 1 | 2025-01-28 | 1 |  |  |  |  | 173 | Low | 157828.13 | 0.118 | 2 | 636297.87 | 9 | 1 | 1.26
P004 | Logistics | SUP036 | 2025-01 | 2024-08-15 | 1138865.43 | 794126 | -344739.43 | 344739.43 | 1 | 2025-01-28 | 2 | 1342968.07 | -204102.64 | DOWN | 0.1792 | 166 | Low | 158357.11 | 0.135 | 0 | 635768.89 | 9 | 1 | 1.26
P004 | Logistics | SUP036 | 2025-01 | 2024-08-29 | 982567.55 | 794126 | -188441.55 | 188441.55 | 1 | 2025-01-28 | 3 | 1138865.43 | -156297.88 | DOWN | 0.1591 | 152 | Low | 180268.41 | 0.17 | 3 | 613857.59 | 9 | 1 | 1.26
P004 | Logistics | SUP036 | 2025-01 | 2024-09-25 | 888233.44 | 794126 | -94107.44 | 94107.44 | 0 | 2025-01-28 | 4 | 982567.55 | -94334.11 | DOWN | 0.1062 | 125 | Low | 218652.3 | 0.237 | 4 | 575473.7 | 9 | 1 | 1.26
P004 | Materials | SUP036 | 2025-02 | 2024-09-08 | 1841936.17 | 1311852 | -530084.17 | 530084.17 | 1 | 2025-02-28 | 1 |  |  |  |  | 173 | Low | 202633.82 | 0.114 | 0 | 1109218.18 | 13 | 1.26 | 0.97
P004 | Materials | SUP036 | 2025-02 | 2024-11-07 | 1643164.39 | 1311852 | -331312.39 | 331312.39 | 1 | 2025-02-28 | 2 | 1841936.17 | -198771.78 | DOWN | 0.121 | 113 | Low | 428580.78 | 0.259 | 3 | 883271.22 | 13 | 1.26 | 0.97
P004 | Materials | SUP036 | 2025-02 | 2024-11-12 | 1512924.65 | 1311852 | -201072.65 | 201072.65 | 0 | 2025-02-28 | 3 | 1643164.39 | -130239.74 | DOWN | 0.0861 | 108 | Low | 428209.85 | 0.272 | 3 | 883642.15 | 13 | 1.26 | 0.97
P004 | Materials | SUP036 | 2025-02 | 2024-12-22 | 1419745.92 | 1311852 | -107893.92 | 107893.92 | 0 | 2025-02-28 | 4 | 1512924.65 | -93178.73 | DOWN | 0.0656 | 68 | Low | 546678.94 | 0.369 | 6 | 765173.06 | 13 | 1.26 | 0.97
P004 | Materials | SUP036 | 2025-02 | 2025-02-16 | 1381936.57 | 1311852 | -70084.57 | 70084.57 | 0 | 2025-02-28 | 5 | 1419745.92 | -37809.35 | DOWN | 0.0274 | 12 | Medium | 749728.12 | 0.504 | 4 | 562123.88 | 13 | 1.26 | 0.97
P004 | Materials | SUP036 | 2025-03 | 2024-10-13 | 2215873.31 | 1342271 | -873602.31 | 873602.31 | 1 | 2025-03-28 | 1 |  |  |  |  | 166 | Low | 306751.54 | 0.135 | 2 | 1035519.46 | 11 | 0.73 | 1.3
P004 | Materials | SUP036 | 2025-03 | 2024-11-30 | 1860366.65 | 1342271 | -518095.65 | 518095.65 | 1 | 2025-03-28 | 2 | 2215873.31 | -355506.66 | DOWN | 0.1911 | 118 | Low | 441786.69 | 0.255 | 3 | 900484.31 | 11 | 0.73 | 1.3
P004 | Materials | SUP036 | 2025-03 | 2024-12-05 | 1652616.99 | 1342271 | -310345.99 | 310345.99 | 1 | 2025-03-28 | 3 | 1860366.65 | -207749.66 | DOWN | 0.1257 | 113 | Low | 461112.17 | 0.268 | 7 | 881158.83 | 11 | 0.73 | 1.3
P004 | Materials | SUP036 | 2025-03 | 2024-12-13 | 1516613.26 | 1342271 | -174342.26 | 174342.26 | 0 | 2025-03-28 | 4 | 1652616.99 | -136003.73 | DOWN | 0.0897 | 105 | Low | 451447.97 | 0.288 | 3 | 890823.03 | 11 | 0.73 | 1.3
P004 | Materials | SUP036 | 2025-03 | 2025-02-10 | 1450989.59 | 1342271 | -108718.59 | 108718.59 | 0 | 2025-03-28 | 5 | 1516613.26 | -65623.67 | DOWN | 0.0452 | 46 | Low | 632647.5 | 0.435 | 6 | 709623.5 | 11 | 0.73 | 1.3
P004 | Materials | SUP036 | 2025-03 | 2025-02-22 | 1403670.42 | 1342271 | -61399.42 | 61399.42 | 0 | 2025-03-28 | 6 | 1450989.59 | -47319.17 | DOWN | 0.0337 | 34 | Medium | 672649.99 | 0.465 | 5 | 669621.01 | 11 | 0.73 | 1.3
P004 | Services | SUP036 | 2025-04 | 2024-11-03 | 2945281.64 | 1653062 | -1292219.64 | 1292219.64 | 1 | 2025-04-28 | 1 |  |  |  |  | 176 | Low | 316355.19 | 0.102 | 0 | 1336706.81 | 15 | 1.69 | 1.47
P004 | Services | SUP036 | 2025-04 | 2024-12-12 | 2445968.95 | 1653062 | -792906.95 | 792906.95 | 1 | 2025-04-28 | 2 | 2945281.64 | -499312.69 | DOWN | 0.2041 | 137 | Low | 460931.64 | 0.192 | 4 | 1192130.36 | 15 | 1.69 | 1.47
P004 | Services | SUP036 | 2025-04 | 2025-02-26 | 2089267.05 | 1653062 | -436205.05 | 436205.05 | 1 | 2025-04-28 | 3 | 2445968.95 | -356701.9 | DOWN | 0.1707 | 61 | Low | 755612.82 | 0.367 | 0 | 897449.18 | 15 | 1.69 | 1.47
P004 | Services | SUP036 | 2025-04 | 2025-03-24 | 1907884.36 | 1653062 | -254822.36 | 254822.36 | 0 | 2025-04-28 | 4 | 2089267.05 | -181382.69 | DOWN | 0.0951 | 35 | Low | 809879.47 | 0.427 | 2 | 843182.53 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP036 | 2025-05 | 2025-03-12 | 430166.82 | 331142 | -99024.82 | 99024.82 | 1 | 2025-05-28 | 1 |  |  |  |  | 77 | Low | 152236.56 | 0.356 | 1 | 178905.44 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP036 | 2025-05 | 2025-03-25 | 388279.57 | 331142 | -57137.57 | 57137.57 | 0 | 2025-05-28 | 2 | 430166.82 | -41887.25 | DOWN | 0.1079 | 64 | Low | 154567.84 | 0.389 | 0 | 176574.16 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP036 | 2025-05 | 2025-04-08 | 365538.47 | 331142 | -34396.47 | 34396.47 | 0 | 2025-05-28 | 3 | 388279.57 | -22741.1 | DOWN | 0.0622 | 50 | Low | 161064 | 0.423 | 1 | 170078 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP036 | 2025-05 | 2025-05-18 | 352561.2 | 331142 | -21419.2 | 21419.2 | 0 | 2025-05-28 | 4 | 365538.47 | -12977.27 | DOWN | 0.0368 | 10 | Medium | 169055.33 | 0.521 | 5 | 162086.67 | 12 | 1.03 | 1.42
P004 | Electronics | SUP036 | 2025-06 | 2025-02-27 | 2699374.75 | 1837420 | -861954.75 | 861954.75 | 1 | 2025-06-28 | 1 |  |  |  |  | 121 | Low | 668593.51 | 0.247 | 1 | 1168826.49 | 15 | 0.81 | 1.56
P004 | Electronics | SUP036 | 2025-06 | 2025-03-19 | 2333440.71 | 1837420 | -496020.71 | 496020.71 | 1 | 2025-06-28 | 2 | 2699374.75 | -365934.04 | DOWN | 0.1568 | 101 | Low | 743715.38 | 0.298 | 4 | 1093704.62 | 15 | 0.81 | 1.56
P004 | Electronics | SUP036 | 2025-06 | 2025-05-29 | 2110527.09 | 1837420 | -273107.09 | 273107.09 | 0 | 2025-06-28 | 3 | 2333440.71 | -222913.62 | DOWN | 0.1056 | 30 | Medium | 939871.13 | 0.475 | 4 | 897548.87 | 15 | 0.81 | 1.56
P004 | Software | SUP036 | 2025-07 | 2025-02-04 | 3297614.18 | 1799999 | -1497615.18 | 1497615.18 | 1 | 2025-07-28 | 1 |  |  |  |  | 174 | Low | 337995.43 | 0.106 | 0 | 1462003.57 | 10 | 1.72 | 1
P004 | Software | SUP036 | 2025-07 | 2025-05-31 | 2736854.64 | 1799999 | -936855.64 | 936855.64 | 1 | 2025-07-28 | 2 | 3297614.18 | -560759.54 | DOWN | 0.2049 | 58 | Low | 1039164.03 | 0.373 | 2 | 760834.97 | 10 | 1.72 | 1
P004 | Software | SUP036 | 2025-07 | 2025-06-09 | 2433447.98 | 1799999 | -633448.98 | 633448.98 | 1 | 2025-07-28 | 3 | 2736854.64 | -303406.66 | DOWN | 0.1247 | 49 | Low | 957585.07 | 0.394 | 0 | 842413.93 | 10 | 1.72 | 1
P004 | Software | SUP036 | 2025-08 | 2025-03-07 | 2617093.89 | 1369944 | -1247149.89 | 1247149.89 | 1 | 2025-08-28 | 1 |  |  |  |  | 174 | Low | 275255.82 | 0.109 | 0 | 1094688.18 | 13 | 1.45 | 1.13
P004 | Software | SUP036 | 2025-08 | 2025-03-14 | 2092483.28 | 1369944 | -722539.28 | 722539.28 | 1 | 2025-08-28 | 2 | 2617093.89 | -524610.61 | DOWN | 0.2507 | 167 | Low | 261765.45 | 0.126 | 3 | 1108178.55 | 13 | 1.45 | 1.13
P004 | Software | SUP036 | 2025-08 | 2025-04-05 | 1825630.31 | 1369944 | -455686.31 | 455686.31 | 1 | 2025-08-28 | 3 | 2092483.28 | -266852.97 | DOWN | 0.1462 | 145 | Low | 330017.31 | 0.178 | 0 | 1039926.69 | 13 | 1.45 | 1.13
P004 | Software | SUP036 | 2025-08 | 2025-05-26 | 1655003.81 | 1369944 | -285059.81 | 285059.81 | 1 | 2025-08-28 | 4 | 1825630.31 | -170626.5 | DOWN | 0.1031 | 94 | Low | 509695.22 | 0.299 | 4 | 860248.78 | 13 | 1.45 | 1.13
P004 | Software | SUP036 | 2025-08 | 2025-06-18 | 1529878.43 | 1369944 | -159934.43 | 159934.43 | 0 | 2025-08-28 | 5 | 1655003.81 | -125125.38 | DOWN | 0.0818 | 71 | Low | 507591.42 | 0.353 | 3 | 862352.58 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP036 | 2025-09 | 2025-05-14 | 1008730.53 | 766620 | -242110.53 | 242110.53 | 1 | 2025-09-28 | 1 |  |  |  |  | 137 | Low | 197406.42 | 0.2 | 3 | 569213.58 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP036 | 2025-09 | 2025-05-28 | 912910.62 | 766620 | -146290.62 | 146290.62 | 1 | 2025-09-28 | 2 | 1008730.53 | -95819.91 | DOWN | 0.105 | 123 | Low | 221885.11 | 0.234 | 4 | 544734.89 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP036 | 2025-09 | 2025-05-28 | 856713.93 | 766620 | -90093.93 | 90093.93 | 0 | 2025-09-28 | 3 | 912910.62 | -56196.69 | DOWN | 0.0656 | 123 | Low | 207677.88 | 0.234 | 2 | 558942.12 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP036 | 2025-09 | 2025-09-16 | 813961.18 | 766620 | -47341.18 | 47341.18 | 0 | 2025-09-28 | 4 | 856713.93 | -42752.75 | DOWN | 0.0525 | 12 | Medium | 438210.71 | 0.501 | 4 | 328409.29 | 12 | 1.31 | 1.3
P004 | Logistics | SUP036 | 2025-10 | 2025-07-26 | 735461.71 | 372729 | -362732.71 | 362732.71 | 1 | 2025-10-28 | 1 |  |  |  |  | 94 | Low | 217898.5 | 0.302 | 5 | 154830.5 | 16 | 1.37 | 1.4
P004 | Logistics | SUP036 | 2025-10 | 2025-08-08 | 586702.95 | 372729 | -213973.95 | 213973.95 | 1 | 2025-10-28 | 2 | 735461.71 | -148758.76 | DOWN | 0.2536 | 81 | Low | 182572.74 | 0.333 | 2 | 190156.26 | 16 | 1.37 | 1.4
P004 | Logistics | SUP036 | 2025-10 | 2025-08-10 | 514657.24 | 372729 | -141928.24 | 141928.24 | 1 | 2025-10-28 | 3 | 586702.95 | -72045.71 | DOWN | 0.14 | 79 | Low | 183420.64 | 0.338 | 3 | 189308.36 | 16 | 1.37 | 1.4
P004 | Logistics | SUP036 | 2025-10 | 2025-08-26 | 457476.08 | 372729 | -84747.08 | 84747.08 | 1 | 2025-10-28 | 4 | 514657.24 | -57181.16 | DOWN | 0.125 | 63 | Low | 177729.44 | 0.376 | 1 | 194999.56 | 16 | 1.37 | 1.4
P004 | Logistics | SUP036 | 2025-10 | 2025-09-24 | 420044.47 | 372729 | -47315.47 | 47315.47 | 0 | 2025-10-28 | 5 | 457476.08 | -37431.61 | DOWN | 0.0891 | 34 | Low | 193507.57 | 0.445 | 3 | 179221.43 | 16 | 1.37 | 1.4
P004 | Logistics | SUP036 | 2025-10 | 2025-10-08 | 398355.89 | 372729 | -25626.89 | 25626.89 | 0 | 2025-10-28 | 6 | 420044.47 | -21688.58 | DOWN | 0.0544 | 20 | Medium | 185657.56 | 0.479 | 4 | 187071.44 | 16 | 1.37 | 1.4
P004 | Materials | SUP036 | 2025-11 | 2025-08-25 | 2315182.26 | 1627921 | -687261.26 | 687261.26 | 1 | 2025-11-28 | 1 |  |  |  |  | 95 | Low | 671926.63 | 0.312 | 4 | 955994.37 | 7 | 0.59 | 1.31
P004 | Materials | SUP036 | 2025-11 | 2025-10-13 | 2054877.25 | 1627921 | -426956.25 | 426956.25 | 1 | 2025-11-28 | 2 | 2315182.26 | -260305.01 | DOWN | 0.1267 | 46 | Low | 924127.57 | 0.435 | 3 | 703793.43 | 7 | 0.59 | 1.31
P004 | Materials | SUP036 | 2025-11 | 2025-10-21 | 1891690.18 | 1627921 | -263769.18 | 263769.18 | 0 | 2025-11-28 | 3 | 2054877.25 | -163187.07 | DOWN | 0.0863 | 38 | Medium | 858417.87 | 0.455 | 2 | 769503.13 | 7 | 0.59 | 1.31
P004 | Materials | SUP036 | 2025-11 | 2025-10-26 | 1780370.63 | 1627921 | -152449.63 | 152449.63 | 0 | 2025-11-28 | 4 | 1891690.18 | -111319.55 | DOWN | 0.0625 | 33 | Medium | 887762.21 | 0.468 | 4 | 740158.79 | 7 | 0.59 | 1.31
P004 | Materials | SUP036 | 2025-11 | 2025-11-07 | 1716579.65 | 1627921 | -88658.65 | 88658.65 | 0 | 2025-11-28 | 5 | 1780370.63 | -63790.98 | DOWN | 0.0372 | 21 | Medium | 825180.42 | 0.498 | 0 | 802740.58 | 7 | 0.59 | 1.31
P004 | Services | SUP036 | 2025-12 | 2025-07-07 | 996943.89 | 709588 | -287355.89 | 287355.89 | 1 | 2025-12-28 | 1 |  |  |  |  | 174 | Low | 105649.08 | 0.114 | 4 | 603938.92 | 9 | 1.11 | 0.94
P004 | Services | SUP036 | 2025-12 | 2025-08-14 | 876719.25 | 709588 | -167131.25 | 167131.25 | 1 | 2025-12-28 | 2 | 996943.89 | -120224.64 | DOWN | 0.1371 | 136 | Low | 195368.72 | 0.207 | 0 | 514219.28 | 9 | 1.11 | 0.94
P004 | Services | SUP036 | 2025-12 | 2025-08-18 | 802132.6 | 709588 | -92544.6 | 92544.6 | 0 | 2025-12-28 | 3 | 876719.25 | -74586.65 | DOWN | 0.093 | 132 | Low | 186717.48 | 0.217 | 1 | 522870.52 | 9 | 1.11 | 0.94
P004 | Services | SUP036 | 2025-12 | 2025-09-02 | 774170.52 | 709588 | -64582.52 | 64582.52 | 0 | 2025-12-28 | 4 | 802132.6 | -27962.08 | DOWN | 0.0361 | 117 | Low | 204282.47 | 0.254 | 0 | 505305.53 | 9 | 1.11 | 0.94
P004 | Services | SUP036 | 2025-12 | 2025-12-06 | 749710.95 | 709588 | -40122.95 | 40122.95 | 0 | 2025-12-28 | 5 | 774170.52 | -24459.57 | DOWN | 0.0326 | 22 | Medium | 368545.93 | 0.489 | 5 | 341042.07 | 9 | 1.11 | 0.94
P004 | Services | SUP036 | 2025-12 | 2025-12-13 | 727686.17 | 709588 | -18098.17 | 18098.17 | 0 | 2025-12-28 | 6 | 749710.95 | -22024.78 | DOWN | 0.0303 | 15 | Medium | 392529.92 | 0.506 | 5 | 317058.08 | 9 | 1.11 | 0.94
P004 | Logistics | SUP046 | 2025-01 | 2024-08-14 | 2454926.29 | 1543805 | -911121.29 | 911121.29 | 1 | 2025-01-28 | 1 |  |  |  |  | 167 | Low | 446813.86 | 0.188 | 1 | 1096991.14 | 9 | 1 | 1.26
P004 | Logistics | SUP046 | 2025-01 | 2024-09-15 | 1955075.53 | 1543805 | -411270.53 | 411270.53 | 1 | 2025-01-28 | 2 | 2454926.29 | -499850.76 | DOWN | 0.2557 | 135 | Low | 622562.8 | 0.301 | 2 | 921242.2 | 9 | 1 | 1.26
P004 | Logistics | SUP046 | 2025-01 | 2024-09-15 | 1742349.55 | 1543805 | -198544.55 | 198544.55 | 0 | 2025-01-28 | 3 | 1955075.53 | -212725.98 | DOWN | 0.1221 | 135 | Low | 523418.88 | 0.301 | 0 | 1020386.12 | 9 | 1 | 1.26
P004 | Logistics | SUP046 | 2025-01 | 2024-10-31 | 1667899.12 | 1543805 | -124094.12 | 124094.12 | 0 | 2025-01-28 | 4 | 1742349.55 | -74450.43 | DOWN | 0.0446 | 89 | Low | 780657.08 | 0.464 | 6 | 763147.92 | 9 | 1 | 1.26
P004 | Logistics | SUP046 | 2025-01 | 2024-12-14 | 1634316.88 | 1543805 | -90511.88 | 90511.88 | 0 | 2025-01-28 | 5 | 1667899.12 | -33582.24 | DOWN | 0.0205 | 45 | Medium | 941843.91 | 0.62 | 8 | 601961.09 | 9 | 1 | 1.26
P004 | Materials | SUP046 | 2025-02 | 2024-09-08 | 284285.73 | 191737 | -92548.73 | 92548.73 | 1 | 2025-02-28 | 1 |  |  |  |  | 173 | Low | 48017.35 | 0.162 | 0 | 143719.65 | 13 | 1.26 | 0.97
P004 | Materials | SUP046 | 2025-02 | 2024-10-20 | 234331.12 | 191737 | -42594.12 | 42594.12 | 1 | 2025-02-28 | 2 | 284285.73 | -49954.61 | DOWN | 0.2132 | 131 | Low | 75774.48 | 0.306 | 4 | 115962.52 | 13 | 1.26 | 0.97
P004 | Materials | SUP046 | 2025-02 | 2024-12-22 | 210390.85 | 191737 | -18653.85 | 18653.85 | 0 | 2025-02-28 | 3 | 234331.12 | -23940.27 | DOWN | 0.1138 | 68 | Low | 116203.13 | 0.523 | 6 | 75533.87 | 13 | 1.26 | 0.97
P004 | Electronics | SUP046 | 2025-03 | 2024-10-26 | 664067.95 | 437208 | -226859.95 | 226859.95 | 1 | 2025-03-28 | 1 |  |  |  |  | 153 | Low | 157830 | 0.238 | 0 | 279378 | 11 | 0.73 | 1.3
P004 | Electronics | SUP046 | 2025-03 | 2024-11-15 | 542268.92 | 437208 | -105060.92 | 105060.92 | 1 | 2025-03-28 | 2 | 664067.95 | -121799.03 | DOWN | 0.2246 | 133 | Low | 169830.52 | 0.308 | 3 | 267377.48 | 11 | 0.73 | 1.3
P004 | Electronics | SUP046 | 2025-03 | 2024-11-22 | 488812.55 | 437208 | -51604.55 | 51604.55 | 0 | 2025-03-28 | 3 | 542268.92 | -53456.37 | DOWN | 0.1094 | 126 | Low | 159781.88 | 0.333 | 1 | 277426.12 | 11 | 0.73 | 1.3
P004 | Electronics | SUP046 | 2025-03 | 2025-02-11 | 458365.08 | 437208 | -21157.08 | 21157.08 | 0 | 2025-03-28 | 4 | 488812.55 | -30447.47 | DOWN | 0.0664 | 45 | Medium | 284736.33 | 0.62 | 0 | 152471.67 | 11 | 0.73 | 1.3
P004 | Electronics | SUP046 | 2025-03 | 2025-03-16 | 452202.01 | 437208 | -14994.01 | 14994.01 | 0 | 2025-03-28 | 5 | 458365.08 | -6163.07 | DOWN | 0.0136 | 12 | High | 355047 | 0.737 | 3 | 82161 | 11 | 0.73 | 1.3
P004 | Software | SUP046 | 2025-04 | 2024-11-10 | 964945.32 | 599236 | -365709.32 | 365709.32 | 1 | 2025-04-28 | 1 |  |  |  |  | 169 | Low | 161913.4 | 0.167 | 2 | 437322.6 | 15 | 1.69 | 1.47
P004 | Software | SUP046 | 2025-04 | 2024-11-24 | 748478.71 | 599236 | -149242.71 | 149242.71 | 1 | 2025-04-28 | 2 | 964945.32 | -216466.61 | DOWN | 0.2892 | 155 | Low | 150654.3 | 0.213 | 1 | 448581.7 | 15 | 1.69 | 1.47
P004 | Software | SUP046 | 2025-04 | 2024-12-18 | 681060.62 | 599236 | -81824.62 | 81824.62 | 0 | 2025-04-28 | 3 | 748478.71 | -67418.09 | DOWN | 0.099 | 131 | Low | 201631.58 | 0.291 | 4 | 397604.42 | 15 | 1.69 | 1.47
P004 | Software | SUP046 | 2025-04 | 2025-01-25 | 652735.38 | 599236 | -53499.38 | 53499.38 | 0 | 2025-04-28 | 4 | 681060.62 | -28325.24 | DOWN | 0.0434 | 93 | Low | 287009.06 | 0.416 | 3 | 312226.94 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP046 | 2025-05 | 2025-02-12 | 3122127.47 | 2377691 | -744436.47 | 744436.47 | 1 | 2025-05-28 | 1 |  |  |  |  | 105 | Low | 1361150.05 | 0.406 | 5 | 1016540.95 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP046 | 2025-05 | 2025-02-20 | 2720592.41 | 2377691 | -342901.41 | 342901.41 | 0 | 2025-05-28 | 2 | 3122127.47 | -401535.06 | DOWN | 0.1476 | 97 | Low | 1158742.85 | 0.435 | 6 | 1218948.15 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP046 | 2025-05 | 2025-03-08 | 2525013.74 | 2377691 | -147322.74 | 147322.74 | 0 | 2025-05-28 | 3 | 2720592.41 | -195578.67 | DOWN | 0.0775 | 81 | Low | 1245045.87 | 0.491 | 1 | 1132645.13 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP046 | 2025-05 | 2025-03-18 | 2453350.35 | 2377691 | -75659.35 | 75659.35 | 0 | 2025-05-28 | 4 | 2525013.74 | -71663.39 | DOWN | 0.0292 | 71 | Low | 1238963.86 | 0.526 | 2 | 1138727.14 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP046 | 2025-05 | 2025-04-07 | 2405710.26 | 2377691 | -28019.26 | 28019.26 | 0 | 2025-05-28 | 5 | 2453350.35 | -47640.09 | DOWN | 0.0198 | 51 | Medium | 1490609.81 | 0.597 | 3 | 887081.19 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP046 | 2025-05 | 2025-05-10 | 2398136.46 | 2377691 | -20445.46 | 20445.46 | 0 | 2025-05-28 | 6 | 2405710.26 | -7573.8 | DOWN | 0.0032 | 18 | High | 1823855.88 | 0.714 | 9 | 553835.12 | 12 | 1.03 | 1.42
P004 | Materials | SUP046 | 2025-06 | 2025-02-16 | 372638.01 | 294347 | -78291.01 | 78291.01 | 1 | 2025-06-28 | 1 |  |  |  |  | 132 | Low | 115576.61 | 0.312 | 5 | 178770.39 | 15 | 0.81 | 1.56
P004 | Materials | SUP046 | 2025-06 | 2025-03-14 | 332664.1 | 294347 | -38317.1 | 38317.1 | 0 | 2025-06-28 | 2 | 372638.01 | -39973.91 | DOWN | 0.1202 | 106 | Low | 136891.12 | 0.404 | 2 | 157455.88 | 15 | 0.81 | 1.56
P004 | Materials | SUP046 | 2025-06 | 2025-03-20 | 314579.37 | 294347 | -20232.37 | 20232.37 | 0 | 2025-06-28 | 3 | 332664.1 | -18084.73 | DOWN | 0.0575 | 100 | Low | 138082.44 | 0.425 | 0 | 156264.56 | 15 | 0.81 | 1.56
P004 | Materials | SUP046 | 2025-06 | 2025-05-22 | 304781.13 | 294347 | -10434.13 | 10434.13 | 0 | 2025-06-28 | 4 | 314579.37 | -9798.24 | DOWN | 0.0321 | 37 | Medium | 205028.73 | 0.649 | 4 | 89318.27 | 15 | 0.81 | 1.56
P004 | Logistics | SUP046 | 2025-07 | 2025-03-13 | 3744567.67 | 2338207 | -1406360.67 | 1406360.67 | 1 | 2025-07-28 | 1 |  |  |  |  | 137 | Low | 1001957.53 | 0.271 | 0 | 1336249.47 | 10 | 1.72 | 1
P004 | Logistics | SUP046 | 2025-07 | 2025-04-11 | 2944875.17 | 2338207 | -606668.17 | 606668.17 | 1 | 2025-07-28 | 2 | 3744567.67 | -799692.5 | DOWN | 0.2716 | 108 | Low | 1155537.21 | 0.366 | 0 | 1182669.79 | 10 | 1.72 | 1
P004 | Logistics | SUP046 | 2025-07 | 2025-05-30 | 2684591.26 | 2338207 | -346384.26 | 346384.26 | 0 | 2025-07-28 | 3 | 2944875.17 | -260283.91 | DOWN | 0.097 | 59 | Medium | 1419807.03 | 0.525 | 3 | 918399.97 | 10 | 1.72 | 1
P004 | Logistics | SUP046 | 2025-07 | 2025-07-05 | 2454284.9 | 2338207 | -116077.9 | 116077.9 | 0 | 2025-07-28 | 4 | 2684591.26 | -230306.36 | DOWN | 0.0938 | 23 | Medium | 1471015.32 | 0.643 | 6 | 867191.68 | 10 | 1.72 | 1
P004 | Mechanical | SUP046 | 2025-08 | 2025-03-01 | 1005743.53 | 706070 | -299673.53 | 299673.53 | 1 | 2025-08-28 | 1 |  |  |  |  | 180 | Low | 152315.18 | 0.148 | 3 | 553754.82 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP046 | 2025-08 | 2025-03-22 | 833872.16 | 706070 | -127802.16 | 127802.16 | 1 | 2025-08-28 | 2 | 1005743.53 | -171871.37 | DOWN | 0.2061 | 159 | Low | 159314.45 | 0.205 | 4 | 546755.55 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP046 | 2025-08 | 2025-04-07 | 761760.18 | 706070 | -55690.18 | 55690.18 | 0 | 2025-08-28 | 3 | 833872.16 | -72111.98 | DOWN | 0.0947 | 143 | Low | 187324.31 | 0.259 | 5 | 518745.69 | 13 | 1.45 | 1.13
P004 | Electronics | SUP046 | 2025-09 | 2025-04-11 | 188830.45 | 114623 | -74207.45 | 74207.45 | 1 | 2025-09-28 | 1 |  |  |  |  | 170 | Low | 33823.54 | 0.171 | 1 | 80799.46 | 12 | 1.31 | 1.3
P004 | Electronics | SUP046 | 2025-09 | 2025-05-02 | 148946.3 | 114623 | -34323.3 | 34323.3 | 1 | 2025-09-28 | 2 | 188830.45 | -39884.15 | DOWN | 0.2678 | 149 | Low | 37964.26 | 0.243 | 0 | 76658.74 | 12 | 1.31 | 1.3
P004 | Electronics | SUP046 | 2025-09 | 2025-05-08 | 129795.31 | 114623 | -15172.31 | 15172.31 | 0 | 2025-09-28 | 3 | 148946.3 | -19150.99 | DOWN | 0.1475 | 143 | Low | 31889.1 | 0.263 | 1 | 82733.9 | 12 | 1.31 | 1.3
P004 | Electronics | SUP046 | 2025-09 | 2025-08-08 | 122834.28 | 114623 | -8211.28 | 8211.28 | 0 | 2025-09-28 | 4 | 129795.31 | -6961.03 | DOWN | 0.0567 | 51 | Medium | 67867.17 | 0.578 | 6 | 46755.83 | 12 | 1.31 | 1.3
P004 | Electronics | SUP046 | 2025-09 | 2025-08-29 | 118936.7 | 114623 | -4313.7 | 4313.7 | 0 | 2025-09-28 | 5 | 122834.28 | -3897.58 | DOWN | 0.0328 | 30 | Medium | 81348.47 | 0.649 | 6 | 33274.53 | 12 | 1.31 | 1.3
P004 | Materials | SUP046 | 2025-10 | 2025-07-17 | 582961.97 | 387503 | -195458.97 | 195458.97 | 1 | 2025-10-28 | 1 |  |  |  |  | 103 | Low | 224099.17 | 0.397 | 5 | 163403.83 | 16 | 1.37 | 1.4
P004 | Materials | SUP046 | 2025-10 | 2025-09-09 | 480474.85 | 387503 | -92971.85 | 92971.85 | 1 | 2025-10-28 | 2 | 582961.97 | -102487.12 | DOWN | 0.2133 | 49 | Low | 300296.94 | 0.58 | 3 | 87206.06 | 16 | 1.37 | 1.4
P004 | Materials | SUP046 | 2025-10 | 2025-10-11 | 426550.32 | 387503 | -39047.32 | 39047.32 | 0 | 2025-10-28 | 3 | 480474.85 | -53924.53 | DOWN | 0.1264 | 17 | Low | 272834.43 | 0.689 | 4 | 114668.57 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP046 | 2025-11 | 2025-07-28 | 421566.05 | 316933 | -104633.05 | 104633.05 | 1 | 2025-11-28 | 1 |  |  |  |  | 123 | Low | 139707.36 | 0.344 | 1 | 177225.64 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP046 | 2025-11 | 2025-08-14 | 363052.62 | 316933 | -46119.62 | 46119.62 | 0 | 2025-11-28 | 2 | 421566.05 | -58513.43 | DOWN | 0.1612 | 106 | Low | 148875.37 | 0.404 | 2 | 168057.63 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP046 | 2025-11 | 2025-09-19 | 339327.88 | 316933 | -22394.88 | 22394.88 | 0 | 2025-11-28 | 3 | 363052.62 | -23724.74 | DOWN | 0.0699 | 70 | Low | 169718.31 | 0.532 | 5 | 147214.69 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP046 | 2025-11 | 2025-09-25 | 328899.63 | 316933 | -11966.63 | 11966.63 | 0 | 2025-11-28 | 4 | 339327.88 | -10428.25 | DOWN | 0.0317 | 64 | Low | 188327.36 | 0.553 | 1 | 128605.64 | 7 | 0.59 | 1.31
P004 | Materials | SUP046 | 2025-12 | 2025-08-10 | 1301092.06 | 1050521 | -250571.06 | 250571.06 | 1 | 2025-12-28 | 1 |  |  |  |  | 140 | Low | 392790.55 | 0.28 | 3 | 657730.45 | 9 | 1.11 | 0.94
P004 | Materials | SUP046 | 2025-12 | 2025-09-19 | 1172479.64 | 1050521 | -121958.64 | 121958.64 | 0 | 2025-12-28 | 2 | 1301092.06 | -128612.42 | DOWN | 0.1097 | 100 | Low | 498573.58 | 0.42 | 7 | 551947.42 | 9 | 1.11 | 0.94
P004 | Materials | SUP046 | 2025-12 | 2025-11-22 | 1109222.55 | 1050521 | -58701.55 | 58701.55 | 0 | 2025-12-28 | 3 | 1172479.64 | -63257.09 | DOWN | 0.057 | 36 | Medium | 770556.7 | 0.644 | 4 | 279964.3 | 9 | 1.11 | 0.94
P004 | Services | SUP040 | 2025-01 | 2024-08-20 | 1374810.45 | 744758 | -630052.45 | 630052.45 | 1 | 2025-01-28 | 1 |  |  |  |  | 161 | Low | 255404.43 | 0.174 | 3 | 489353.57 | 9 | 1 | 1.26
P004 | Services | SUP040 | 2025-01 | 2024-09-09 | 1089509.85 | 744758 | -344751.85 | 344751.85 | 1 | 2025-01-28 | 2 | 1374810.45 | -285300.6 | DOWN | 0.2619 | 141 | Low | 273889.35 | 0.233 | 3 | 470868.65 | 9 | 1 | 1.26
P004 | Services | SUP040 | 2025-01 | 2024-09-17 | 945123.49 | 744758 | -200365.49 | 200365.49 | 1 | 2025-01-28 | 3 | 1089509.85 | -144386.36 | DOWN | 0.1528 | 133 | Low | 227982.93 | 0.257 | 0 | 516775.07 | 9 | 1 | 1.26
P004 | Services | SUP040 | 2025-01 | 2024-09-22 | 852548.91 | 744758 | -107790.91 | 107790.91 | 0 | 2025-01-28 | 4 | 945123.49 | -92574.58 | DOWN | 0.1086 | 128 | Low | 214391.72 | 0.272 | 1 | 530366.28 | 9 | 1 | 1.26
P004 | Services | SUP040 | 2025-01 | 2024-10-06 | 811484.48 | 744758 | -66726.48 | 66726.48 | 0 | 2025-01-28 | 5 | 852548.91 | -41064.43 | DOWN | 0.0506 | 114 | Low | 268688.08 | 0.313 | 0 | 476069.92 | 9 | 1 | 1.26
P004 | Mechanical | SUP040 | 2025-02 | 2024-10-27 | 3699181.47 | 2195549 | -1503632.47 | 1503632.47 | 1 | 2025-02-28 | 1 |  |  |  |  | 124 | Low | 1041644.94 | 0.275 | 1 | 1153904.06 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP040 | 2025-02 | 2024-11-29 | 3026152.71 | 2195549 | -830603.71 | 830603.71 | 1 | 2025-02-28 | 2 | 3699181.47 | -673028.76 | DOWN | 0.2224 | 91 | Low | 1189530.17 | 0.37 | 1 | 1006018.83 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP040 | 2025-02 | 2024-12-19 | 2653551.96 | 2195549 | -458002.96 | 458002.96 | 1 | 2025-02-28 | 3 | 3026152.71 | -372600.75 | DOWN | 0.1404 | 71 | Low | 1209910.23 | 0.427 | 3 | 985638.77 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP040 | 2025-02 | 2025-01-14 | 2437744.46 | 2195549 | -242195.46 | 242195.46 | 0 | 2025-02-28 | 4 | 2653551.96 | -215807.5 | DOWN | 0.0885 | 45 | Medium | 1268966.99 | 0.501 | 4 | 926582.01 | 13 | 1.26 | 0.97
P004 | Materials | SUP040 | 2025-03 | 2024-10-13 | 2584993.43 | 1547452 | -1037541.43 | 1037541.43 | 1 | 2025-03-28 | 1 |  |  |  |  | 166 | Low | 414205.33 | 0.16 | 0 | 1133246.67 | 11 | 0.73 | 1.3
P004 | Materials | SUP040 | 2025-03 | 2024-11-28 | 2139692.62 | 1547452 | -592240.62 | 592240.62 | 1 | 2025-03-28 | 2 | 2584993.43 | -445300.81 | DOWN | 0.2081 | 120 | Low | 658266.88 | 0.295 | 4 | 889185.12 | 11 | 0.73 | 1.3
P004 | Materials | SUP040 | 2025-03 | 2025-01-09 | 1873550.99 | 1547452 | -326098.99 | 326098.99 | 1 | 2025-03-28 | 3 | 2139692.62 | -266141.63 | DOWN | 0.1421 | 78 | Low | 819781.33 | 0.42 | 3 | 727670.67 | 11 | 0.73 | 1.3
P004 | Materials | SUP040 | 2025-03 | 2025-02-05 | 1721213.4 | 1547452 | -173761.4 | 173761.4 | 0 | 2025-03-28 | 4 | 1873550.99 | -152337.59 | DOWN | 0.0885 | 51 | Medium | 814495.5 | 0.499 | 5 | 732956.5 | 11 | 0.73 | 1.3
P004 | Materials | SUP040 | 2025-03 | 2025-02-26 | 1639518.48 | 1547452 | -92066.48 | 92066.48 | 0 | 2025-03-28 | 5 | 1721213.4 | -81694.92 | DOWN | 0.0498 | 30 | Medium | 934680.92 | 0.561 | 4 | 612771.08 | 11 | 0.73 | 1.3
P004 | Materials | SUP040 | 2025-03 | 2025-03-11 | 1605552.51 | 1547452 | -58100.51 | 58100.51 | 0 | 2025-03-28 | 6 | 1639518.48 | -33965.97 | DOWN | 0.0212 | 17 | Medium | 933453.02 | 0.6 | 6 | 613998.98 | 11 | 0.73 | 1.3
P004 | Services | SUP040 | 2025-04 | 2024-12-04 | 3249810.46 | 1579477 | -1670333.46 | 1670333.46 | 1 | 2025-04-28 | 1 |  |  |  |  | 145 | Low | 688834.61 | 0.205 | 0 | 890642.39 | 15 | 1.69 | 1.47
P004 | Services | SUP040 | 2025-04 | 2024-12-08 | 2447535.64 | 1579477 | -868058.64 | 868058.64 | 1 | 2025-04-28 | 2 | 3249810.46 | -802274.82 | DOWN | 0.3278 | 141 | Low | 511845.52 | 0.216 | 4 | 1067631.48 | 15 | 1.69 | 1.47
P004 | Services | SUP040 | 2025-04 | 2025-04-13 | 2068664.39 | 1579477 | -489187.39 | 489187.39 | 1 | 2025-04-28 | 3 | 2447535.64 | -378871.25 | DOWN | 0.1831 | 15 | Low | 1175812.59 | 0.559 | 4 | 403664.41 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP040 | 2025-05 | 2024-12-10 | 3151716.87 | 2032461 | -1119255.87 | 1119255.87 | 1 | 2025-05-28 | 1 |  |  |  |  | 169 | Low | 508113.53 | 0.15 | 0 | 1524347.47 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP040 | 2025-05 | 2025-02-04 | 2631079.52 | 2032461 | -598618.52 | 598618.52 | 1 | 2025-05-28 | 2 | 3151716.87 | -520637.35 | DOWN | 0.1979 | 113 | Low | 782062.34 | 0.315 | 2 | 1250398.66 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP040 | 2025-05 | 2025-03-21 | 2350545.73 | 2032461 | -318084.73 | 318084.73 | 0 | 2025-05-28 | 3 | 2631079.52 | -280533.79 | DOWN | 0.1193 | 68 | Low | 1083652.97 | 0.447 | 3 | 948808.03 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP040 | 2025-05 | 2025-05-04 | 2199850.73 | 2032461 | -167389.73 | 167389.73 | 0 | 2025-05-28 | 4 | 2350545.73 | -150695 | DOWN | 0.0685 | 24 | Medium | 1184316.35 | 0.577 | 2 | 848144.65 | 12 | 1.03 | 1.42
P004 | Services | SUP040 | 2025-06 | 2025-01-26 | 3325088.37 | 1804149 | -1520939.37 | 1520939.37 | 1 | 2025-06-28 | 1 |  |  |  |  | 153 | Low | 646272.18 | 0.198 | 4 | 1157876.82 | 15 | 0.81 | 1.56
P004 | Services | SUP040 | 2025-06 | 2025-02-21 | 2682380.82 | 1804149 | -878231.82 | 878231.82 | 1 | 2025-06-28 | 2 | 3325088.37 | -642707.55 | DOWN | 0.2396 | 127 | Low | 700592.79 | 0.275 | 1 | 1103556.21 | 15 | 0.81 | 1.56
P004 | Services | SUP040 | 2025-06 | 2025-03-08 | 2252311.03 | 1804149 | -448162.03 | 448162.03 | 1 | 2025-06-28 | 3 | 2682380.82 | -430069.79 | DOWN | 0.1909 | 112 | Low | 716331.01 | 0.319 | 2 | 1087817.99 | 15 | 0.81 | 1.56
P004 | Services | SUP040 | 2025-06 | 2025-03-21 | 2078432.56 | 1804149 | -274283.56 | 274283.56 | 0 | 2025-06-28 | 4 | 2252311.03 | -173878.47 | DOWN | 0.0837 | 99 | Low | 788752.29 | 0.358 | 3 | 1015396.71 | 15 | 0.81 | 1.56
P004 | Services | SUP040 | 2025-06 | 2025-04-03 | 1938082.66 | 1804149 | -133933.66 | 133933.66 | 0 | 2025-06-28 | 5 | 2078432.56 | -140349.9 | DOWN | 0.0724 | 86 | Low | 724864.78 | 0.396 | 1 | 1079284.22 | 15 | 0.81 | 1.56
P004 | Services | SUP040 | 2025-06 | 2025-05-29 | 1870163.58 | 1804149 | -66014.58 | 66014.58 | 0 | 2025-06-28 | 6 | 1938082.66 | -67919.08 | DOWN | 0.0363 | 30 | Medium | 1060214.95 | 0.561 | 1 | 743934.05 | 15 | 0.81 | 1.56
P004 | Services | SUP040 | 2025-07 | 2025-02-05 | 4303154.84 | 2347215 | -1955939.84 | 1955939.84 | 1 | 2025-07-28 | 1 |  |  |  |  | 173 | Low | 531915.28 | 0.128 | 2 | 1815299.72 | 10 | 1.72 | 1
P004 | Services | SUP040 | 2025-07 | 2025-02-09 | 3508742.07 | 2347215 | -1161527.07 | 1161527.07 | 1 | 2025-07-28 | 2 | 4303154.84 | -794412.77 | DOWN | 0.2264 | 169 | Low | 463065.86 | 0.139 | 0 | 1884149.14 | 10 | 1.72 | 1
P004 | Services | SUP040 | 2025-07 | 2025-05-31 | 3049893.65 | 2347215 | -702678.65 | 702678.65 | 1 | 2025-07-28 | 3 | 3508742.07 | -458848.42 | DOWN | 0.1504 | 58 | Low | 1264452.5 | 0.441 | 2 | 1082762.5 | 10 | 1.72 | 1
P004 | Software | SUP040 | 2025-08 | 2025-05-20 | 753717.76 | 409552 | -344165.76 | 344165.76 | 1 | 2025-08-28 | 1 |  |  |  |  | 100 | Low | 238054.3 | 0.336 | 1 | 171497.7 | 13 | 1.45 | 1.13
P004 | Software | SUP040 | 2025-08 | 2025-05-30 | 583998.62 | 409552 | -174446.62 | 174446.62 | 1 | 2025-08-28 | 2 | 753717.76 | -169719.14 | DOWN | 0.2906 | 90 | Low | 204514.24 | 0.364 | 0 | 205037.76 | 13 | 1.45 | 1.13
P004 | Software | SUP040 | 2025-08 | 2025-07-09 | 507924 | 409552 | -98372 | 98372 | 1 | 2025-08-28 | 3 | 583998.62 | -76074.62 | DOWN | 0.1498 | 50 | Low | 235650.55 | 0.477 | 4 | 173901.45 | 13 | 1.45 | 1.13
P004 | Software | SUP040 | 2025-08 | 2025-07-21 | 472248.02 | 409552 | -62696.02 | 62696.02 | 0 | 2025-08-28 | 4 | 507924 | -35675.98 | DOWN | 0.0755 | 38 | Medium | 234471.22 | 0.51 | 1 | 175080.78 | 13 | 1.45 | 1.13
P004 | Materials | SUP040 | 2025-09 | 2025-04-28 | 2514954.14 | 1407880 | -1107074.14 | 1107074.14 | 1 | 2025-09-28 | 1 |  |  |  |  | 153 | Low | 517378.18 | 0.191 | 1 | 890501.82 | 12 | 1.31 | 1.3
P004 | Materials | SUP040 | 2025-09 | 2025-06-15 | 2035855.76 | 1407880 | -627975.76 | 627975.76 | 1 | 2025-09-28 | 2 | 2514954.14 | -479098.38 | DOWN | 0.2353 | 105 | Low | 698218.93 | 0.328 | 2 | 709661.07 | 12 | 1.31 | 1.3
P004 | Materials | SUP040 | 2025-09 | 2025-06-20 | 1730453.68 | 1407880 | -322573.68 | 322573.68 | 1 | 2025-09-28 | 3 | 2035855.76 | -305402.08 | DOWN | 0.1765 | 100 | Low | 598956.28 | 0.342 | 7 | 808923.72 | 12 | 1.31 | 1.3
P004 | Materials | SUP040 | 2025-09 | 2025-07-02 | 1579346.98 | 1407880 | -171466.98 | 171466.98 | 0 | 2025-09-28 | 4 | 1730453.68 | -151106.7 | DOWN | 0.0957 | 88 | Low | 583509.08 | 0.376 | 4 | 824370.92 | 12 | 1.31 | 1.3
P004 | Materials | SUP040 | 2025-09 | 2025-07-08 | 1498994.86 | 1407880 | -91114.86 | 91114.86 | 0 | 2025-09-28 | 5 | 1579346.98 | -80352.12 | DOWN | 0.0536 | 82 | Low | 581001.34 | 0.393 | 4 | 826878.66 | 12 | 1.31 | 1.3
P004 | Materials | SUP040 | 2025-09 | 2025-08-26 | 1462679.06 | 1407880 | -54799.06 | 54799.06 | 0 | 2025-09-28 | 6 | 1498994.86 | -36315.8 | DOWN | 0.0248 | 33 | Medium | 803294.14 | 0.533 | 4 | 604585.86 | 12 | 1.31 | 1.3
P004 | Software | SUP040 | 2025-10 | 2025-06-02 | 1517919.9 | 833965 | -683954.9 | 683954.9 | 1 | 2025-10-28 | 1 |  |  |  |  | 148 | Low | 308961.97 | 0.204 | 2 | 525003.03 | 16 | 1.37 | 1.4
P004 | Software | SUP040 | 2025-10 | 2025-06-06 | 1214914.98 | 833965 | -380949.98 | 380949.98 | 1 | 2025-10-28 | 2 | 1517919.9 | -303004.92 | DOWN | 0.2494 | 144 | Low | 258650.64 | 0.215 | 0 | 575314.36 | 16 | 1.37 | 1.4
P004 | Software | SUP040 | 2025-10 | 2025-07-07 | 1037052.58 | 833965 | -203087.58 | 203087.58 | 1 | 2025-10-28 | 3 | 1214914.98 | -177862.4 | DOWN | 0.1715 | 113 | Low | 332539.21 | 0.303 | 3 | 501425.79 | 16 | 1.37 | 1.4
P004 | Software | SUP040 | 2025-10 | 2025-07-17 | 944674.5 | 833965 | -110709.5 | 110709.5 | 0 | 2025-10-28 | 4 | 1037052.58 | -92378.08 | DOWN | 0.0978 | 103 | Low | 312029.98 | 0.331 | 4 | 521935.02 | 16 | 1.37 | 1.4
P004 | Software | SUP040 | 2025-10 | 2025-08-13 | 909586.31 | 833965 | -75621.31 | 75621.31 | 0 | 2025-10-28 | 5 | 944674.5 | -35088.19 | DOWN | 0.0386 | 76 | Low | 380754.24 | 0.407 | 2 | 453210.76 | 16 | 1.37 | 1.4
P004 | Software | SUP040 | 2025-10 | 2025-09-20 | 880197.63 | 833965 | -46232.63 | 46232.63 | 0 | 2025-10-28 | 6 | 909586.31 | -29388.68 | DOWN | 0.0334 | 38 | Medium | 464155.14 | 0.515 | 5 | 369809.86 | 16 | 1.37 | 1.4
P004 | Services | SUP040 | 2025-11 | 2025-06-12 | 2136894.67 | 1087671 | -1049223.67 | 1049223.67 | 1 | 2025-11-28 | 1 |  |  |  |  | 169 | Low | 301994.83 | 0.151 | 0 | 785676.17 | 7 | 0.59 | 1.31
P004 | Services | SUP040 | 2025-11 | 2025-07-21 | 1692147.37 | 1087671 | -604476.37 | 604476.37 | 1 | 2025-11-28 | 2 | 2136894.67 | -444747.3 | DOWN | 0.2628 | 130 | Low | 417444.95 | 0.266 | 0 | 670226.05 | 7 | 0.59 | 1.31
P004 | Services | SUP040 | 2025-11 | 2025-08-01 | 1402305.89 | 1087671 | -314634.89 | 314634.89 | 1 | 2025-11-28 | 3 | 1692147.37 | -289841.48 | DOWN | 0.2067 | 119 | Low | 444769.32 | 0.298 | 2 | 642901.68 | 7 | 0.59 | 1.31
P004 | Services | SUP040 | 2025-11 | 2025-09-21 | 1276981.01 | 1087671 | -189310.01 | 189310.01 | 0 | 2025-11-28 | 4 | 1402305.89 | -125324.88 | DOWN | 0.0981 | 68 | Low | 618606.7 | 0.449 | 0 | 469064.3 | 7 | 0.59 | 1.31
P004 | Services | SUP040 | 2025-11 | 2025-10-26 | 1194321.98 | 1087671 | -106650.98 | 106650.98 | 0 | 2025-11-28 | 5 | 1276981.01 | -82659.03 | DOWN | 0.0692 | 33 | Medium | 695766.66 | 0.552 | 5 | 391904.34 | 7 | 0.59 | 1.31
P004 | Logistics | SUP040 | 2025-12 | 2025-09-26 | 897803.7 | 449230 | -448573.7 | 448573.7 | 1 | 2025-12-28 | 1 |  |  |  |  | 93 | Low | 329114.85 | 0.37 | 2 | 120115.15 | 9 | 1.11 | 0.94
P004 | Logistics | SUP040 | 2025-12 | 2025-10-09 | 687745.26 | 449230 | -238515.26 | 238515.26 | 1 | 2025-12-28 | 2 | 897803.7 | -210058.44 | DOWN | 0.3054 | 80 | Low | 291174.86 | 0.408 | 0 | 158055.14 | 9 | 1.11 | 0.94
P004 | Logistics | SUP040 | 2025-12 | 2025-11-28 | 582874.5 | 449230 | -133644.5 | 133644.5 | 1 | 2025-12-28 | 3 | 687745.26 | -104870.76 | DOWN | 0.1799 | 30 | Low | 302091.64 | 0.554 | 7 | 147138.36 | 9 | 1.11 | 0.94
P004 | Logistics | SUP007 | 2025-01 | 2024-09-03 | 2502503.62 | 1499244 | -1003259.62 | 1003259.62 | 1 | 2025-01-28 | 1 |  |  |  |  | 147 | Low | 513368.49 | 0.199 | 0 | 985875.51 | 9 | 1 | 1.26
P004 | Logistics | SUP007 | 2025-01 | 2024-09-10 | 2107823.3 | 1499244 | -608579.3 | 608579.3 | 1 | 2025-01-28 | 2 | 2502503.62 | -394680.32 | DOWN | 0.1872 | 140 | Low | 457028.29 | 0.218 | 0 | 1042215.71 | 9 | 1 | 1.26
P004 | Logistics | SUP007 | 2025-01 | 2024-09-17 | 1865740.21 | 1499244 | -366496.21 | 366496.21 | 1 | 2025-01-28 | 3 | 2107823.3 | -242083.09 | DOWN | 0.1298 | 133 | Low | 428385.48 | 0.237 | 3 | 1070858.52 | 9 | 1 | 1.26
P004 | Services | SUP007 | 2025-02 | 2024-10-14 | 2066369.24 | 1058710 | -1007659.24 | 1007659.24 | 1 | 2025-02-28 | 1 |  |  |  |  | 137 | Low | 449856.39 | 0.22 | 5 | 608853.61 | 13 | 1.26 | 0.97
P004 | Services | SUP007 | 2025-02 | 2024-11-15 | 1695997.81 | 1058710 | -637287.81 | 637287.81 | 1 | 2025-02-28 | 2 | 2066369.24 | -370371.43 | DOWN | 0.2184 | 105 | Low | 501907.62 | 0.304 | 2 | 556802.38 | 13 | 1.26 | 0.97
P004 | Services | SUP007 | 2025-02 | 2024-12-06 | 1442897.51 | 1058710 | -384187.51 | 384187.51 | 1 | 2025-02-28 | 3 | 1695997.81 | -253100.3 | DOWN | 0.1754 | 84 | Low | 512018.38 | 0.36 | 3 | 546691.62 | 13 | 1.26 | 0.97
P004 | Services | SUP007 | 2025-02 | 2024-12-21 | 1294414.64 | 1058710 | -235704.64 | 235704.64 | 1 | 2025-02-28 | 4 | 1442897.51 | -148482.87 | DOWN | 0.1147 | 69 | Low | 540553.89 | 0.399 | 4 | 518156.11 | 13 | 1.26 | 0.97
P004 | Services | SUP007 | 2025-02 | 2024-12-27 | 1205298.44 | 1058710 | -146588.44 | 146588.44 | 0 | 2025-02-28 | 5 | 1294414.64 | -89116.2 | DOWN | 0.0739 | 63 | Low | 503319.11 | 0.415 | 3 | 555390.89 | 13 | 1.26 | 0.97
P004 | Electronics | SUP007 | 2025-03 | 2024-11-21 | 1317076.17 | 858271 | -458805.17 | 458805.17 | 1 | 2025-03-28 | 1 |  |  |  |  | 127 | Low | 310734.53 | 0.254 | 3 | 547536.47 | 11 | 0.73 | 1.3
P004 | Electronics | SUP007 | 2025-03 | 2024-11-27 | 1169735.75 | 858271 | -311464.75 | 311464.75 | 1 | 2025-03-28 | 2 | 1317076.17 | -147340.42 | DOWN | 0.126 | 121 | Low | 296034.54 | 0.27 | 1 | 562236.46 | 11 | 0.73 | 1.3
P004 | Electronics | SUP007 | 2025-03 | 2024-12-25 | 1054169.75 | 858271 | -195898.75 | 195898.75 | 1 | 2025-03-28 | 3 | 1169735.75 | -115566 | DOWN | 0.1096 | 93 | Low | 358257.68 | 0.346 | 0 | 500013.32 | 11 | 0.73 | 1.3
P004 | Electronics | SUP007 | 2025-03 | 2025-01-06 | 974965.14 | 858271 | -116694.14 | 116694.14 | 0 | 2025-03-28 | 4 | 1054169.75 | -79204.61 | DOWN | 0.0812 | 81 | Low | 381160.81 | 0.379 | 4 | 477110.19 | 11 | 0.73 | 1.3
P004 | Electronics | SUP007 | 2025-03 | 2025-03-16 | 943435.27 | 858271 | -85164.27 | 85164.27 | 0 | 2025-03-28 | 5 | 974965.14 | -31529.87 | DOWN | 0.0334 | 12 | Medium | 549392.39 | 0.567 | 2 | 308878.61 | 11 | 0.73 | 1.3
P004 | Logistics | SUP007 | 2025-04 | 2025-01-06 | 1871680.68 | 980542 | -891138.68 | 891138.68 | 1 | 2025-04-28 | 1 |  |  |  |  | 112 | Low | 527196.9 | 0.272 | 0 | 453345.1 | 15 | 1.69 | 1.47
P004 | Logistics | SUP007 | 2025-04 | 2025-01-17 | 1578830.73 | 980542 | -598288.73 | 598288.73 | 1 | 2025-04-28 | 2 | 1871680.68 | -292849.95 | DOWN | 0.1855 | 101 | Low | 436638.35 | 0.3 | 2 | 543903.65 | 15 | 1.69 | 1.47
P004 | Logistics | SUP007 | 2025-04 | 2025-03-01 | 1341363.47 | 980542 | -360821.47 | 360821.47 | 1 | 2025-04-28 | 3 | 1578830.73 | -237467.26 | DOWN | 0.177 | 58 | Low | 517212.3 | 0.408 | 6 | 463329.7 | 15 | 1.69 | 1.47
P004 | Logistics | SUP007 | 2025-04 | 2025-04-13 | 1184392.61 | 980542 | -203850.61 | 203850.61 | 1 | 2025-04-28 | 4 | 1341363.47 | -156970.86 | DOWN | 0.1325 | 15 | Low | 589673.5 | 0.516 | 3 | 390868.5 | 15 | 1.69 | 1.47
P004 | Electronics | SUP007 | 2025-05 | 2025-01-08 | 1301407.06 | 691153 | -610254.06 | 610254.06 | 1 | 2025-05-28 | 1 |  |  |  |  | 140 | Low | 305124.65 | 0.217 | 2 | 386028.35 | 12 | 1.03 | 1.42
P004 | Electronics | SUP007 | 2025-05 | 2025-02-13 | 1079643.77 | 691153 | -388490.77 | 388490.77 | 1 | 2025-05-28 | 2 | 1301407.06 | -221763.29 | DOWN | 0.2054 | 104 | Low | 365450.36 | 0.315 | 1 | 325702.64 | 12 | 1.03 | 1.42
P004 | Electronics | SUP007 | 2025-05 | 2025-03-01 | 935662.56 | 691153 | -244509.56 | 244509.56 | 1 | 2025-05-28 | 3 | 1079643.77 | -143981.21 | DOWN | 0.1539 | 88 | Low | 355013.08 | 0.359 | 0 | 336139.92 | 12 | 1.03 | 1.42
P004 | Electronics | SUP007 | 2025-05 | 2025-04-09 | 858954.47 | 691153 | -167801.47 | 167801.47 | 1 | 2025-05-28 | 4 | 935662.56 | -76708.09 | DOWN | 0.0893 | 49 | Medium | 393483.35 | 0.465 | 0 | 297669.65 | 12 | 1.03 | 1.42
P004 | Software | SUP007 | 2025-06 | 2024-12-30 | 1012841.17 | 529209 | -483632.17 | 483632.17 | 1 | 2025-06-28 | 1 |  |  |  |  | 180 | Low | 121770.22 | 0.12 | 0 | 407438.78 | 15 | 0.81 | 1.56
P004 | Software | SUP007 | 2025-06 | 2025-01-17 | 842671.11 | 529209 | -313462.11 | 313462.11 | 1 | 2025-06-28 | 2 | 1012841.17 | -170170.06 | DOWN | 0.2019 | 162 | Low | 137728.3 | 0.158 | 0 | 391480.7 | 15 | 0.81 | 1.56
P004 | Software | SUP007 | 2025-06 | 2025-01-21 | 723691.75 | 529209 | -194482.75 | 194482.75 | 1 | 2025-06-28 | 3 | 842671.11 | -118979.36 | DOWN | 0.1644 | 158 | Low | 116533.35 | 0.169 | 0 | 412675.65 | 15 | 0.81 | 1.56
P004 | Software | SUP007 | 2025-06 | 2025-02-13 | 668054.65 | 529209 | -138845.65 | 138845.65 | 1 | 2025-06-28 | 4 | 723691.75 | -55637.1 | DOWN | 0.0833 | 135 | Low | 162138.74 | 0.232 | 4 | 367070.26 | 15 | 0.81 | 1.56
P004 | Software | SUP007 | 2025-06 | 2025-02-26 | 624280.04 | 529209 | -95071.04 | 95071.04 | 1 | 2025-06-28 | 5 | 668054.65 | -43774.61 | DOWN | 0.0701 | 122 | Low | 173684.99 | 0.267 | 3 | 355524.01 | 15 | 0.81 | 1.56
P004 | Software | SUP007 | 2025-06 | 2025-05-01 | 600402.45 | 529209 | -71193.45 | 71193.45 | 0 | 2025-06-28 | 6 | 624280.04 | -23877.59 | DOWN | 0.0398 | 58 | Low | 283355.84 | 0.442 | 6 | 245853.16 | 15 | 0.81 | 1.56
P004 | Services | SUP007 | 2025-07 | 2025-03-24 | 3605717.41 | 1684416 | -1921301.41 | 1921301.41 | 1 | 2025-07-28 | 1 |  |  |  |  | 126 | Low | 916954.04 | 0.236 | 2 | 767461.96 | 10 | 1.72 | 1
P004 | Services | SUP007 | 2025-07 | 2025-04-05 | 2840874.44 | 1684416 | -1156458.44 | 1156458.44 | 1 | 2025-07-28 | 2 | 3605717.41 | -764842.97 | DOWN | 0.2692 | 114 | Low | 739426.69 | 0.266 | 3 | 944989.31 | 10 | 1.72 | 1
P004 | Services | SUP007 | 2025-07 | 2025-04-22 | 2411757.45 | 1684416 | -727341.45 | 727341.45 | 1 | 2025-07-28 | 3 | 2840874.44 | -429116.99 | DOWN | 0.1779 | 97 | Low | 697656.62 | 0.309 | 1 | 986759.38 | 10 | 1.72 | 1
P004 | Services | SUP007 | 2025-07 | 2025-06-21 | 2142897.52 | 1684416 | -458481.52 | 458481.52 | 1 | 2025-07-28 | 4 | 2411757.45 | -268859.93 | DOWN | 0.1255 | 37 | Low | 948304.65 | 0.459 | 4 | 736111.35 | 10 | 1.72 | 1
P004 | Electronics | SUP007 | 2025-08 | 2025-03-31 | 593288.64 | 387333 | -205955.64 | 205955.64 | 1 | 2025-08-28 | 1 |  |  |  |  | 150 | Low | 109464.85 | 0.181 | 0 | 277868.15 | 13 | 1.45 | 1.13
P004 | Electronics | SUP007 | 2025-08 | 2025-04-14 | 520767.24 | 387333 | -133434.24 | 133434.24 | 1 | 2025-08-28 | 2 | 593288.64 | -72521.4 | DOWN | 0.1393 | 136 | Low | 110832.19 | 0.217 | 3 | 276500.81 | 13 | 1.45 | 1.13
P004 | Electronics | SUP007 | 2025-08 | 2025-04-18 | 471516.71 | 387333 | -84183.71 | 84183.71 | 1 | 2025-08-28 | 3 | 520767.24 | -49250.53 | DOWN | 0.1045 | 132 | Low | 108347.85 | 0.228 | 2 | 278985.15 | 13 | 1.45 | 1.13
P004 | Electronics | SUP007 | 2025-08 | 2025-07-27 | 435995.97 | 387333 | -48662.97 | 48662.97 | 0 | 2025-08-28 | 4 | 471516.71 | -35520.74 | DOWN | 0.0815 | 32 | Medium | 204450.4 | 0.486 | 1 | 182882.6 | 13 | 1.45 | 1.13
P004 | Logistics | SUP007 | 2025-09 | 2025-04-06 | 5053883.77 | 2739746 | -2314137.77 | 2314137.77 | 1 | 2025-09-28 | 1 |  |  |  |  | 175 | Low | 625247.4 | 0.118 | 0 | 2114498.6 | 12 | 1.31 | 1.3
P004 | Logistics | SUP007 | 2025-09 | 2025-04-27 | 4238058.25 | 2739746 | -1498312.25 | 1498312.25 | 1 | 2025-09-28 | 2 | 5053883.77 | -815825.52 | DOWN | 0.1925 | 154 | Low | 695673.15 | 0.174 | 0 | 2044072.85 | 12 | 1.31 | 1.3
P004 | Logistics | SUP007 | 2025-09 | 2025-05-25 | 3759529.81 | 2739746 | -1019783.81 | 1019783.81 | 1 | 2025-09-28 | 3 | 4238058.25 | -478528.44 | DOWN | 0.1273 | 126 | Low | 911334.24 | 0.247 | 0 | 1828411.76 | 12 | 1.31 | 1.3
P004 | Logistics | SUP007 | 2025-09 | 2025-08-14 | 3405168.98 | 2739746 | -665422.98 | 665422.98 | 1 | 2025-09-28 | 4 | 3759529.81 | -354360.83 | DOWN | 0.1041 | 45 | Medium | 1502008.96 | 0.46 | 3 | 1237737.04 | 12 | 1.31 | 1.3
P004 | Logistics | SUP007 | 2025-09 | 2025-09-05 | 3115432.1 | 2739746 | -375686.1 | 375686.1 | 0 | 2025-09-28 | 5 | 3405168.98 | -289736.88 | DOWN | 0.093 | 23 | Medium | 1666926.96 | 0.518 | 3 | 1072819.04 | 12 | 1.31 | 1.3
P004 | Materials | SUP007 | 2025-10 | 2025-05-03 | 4227555.17 | 2306817 | -1920738.17 | 1920738.17 | 1 | 2025-10-28 | 1 |  |  |  |  | 178 | Low | 477256.8 | 0.115 | 3 | 1829560.2 | 16 | 1.37 | 1.4
P004 | Materials | SUP007 | 2025-10 | 2025-05-27 | 3535216.65 | 2306817 | -1228399.65 | 1228399.65 | 1 | 2025-10-28 | 2 | 4227555.17 | -692338.52 | DOWN | 0.1958 | 154 | Low | 637692.29 | 0.172 | 1 | 1669124.71 | 16 | 1.37 | 1.4
P004 | Materials | SUP007 | 2025-10 | 2025-06-23 | 3116947.51 | 2306817 | -810130.51 | 810130.51 | 1 | 2025-10-28 | 3 | 3535216.65 | -418269.14 | DOWN | 0.1342 | 127 | Low | 786353.06 | 0.243 | 1 | 1520463.94 | 16 | 1.37 | 1.4
P004 | Materials | SUP007 | 2025-10 | 2025-08-09 | 2853367.58 | 2306817 | -546550.58 | 546550.58 | 1 | 2025-10-28 | 4 | 3116947.51 | -263579.93 | DOWN | 0.0924 | 80 | Low | 1063738.44 | 0.366 | 4 | 1243078.56 | 16 | 1.37 | 1.4
P004 | Materials | SUP007 | 2025-10 | 2025-09-05 | 2659747.69 | 2306817 | -352930.69 | 352930.69 | 0 | 2025-10-28 | 5 | 2853367.58 | -193619.89 | DOWN | 0.0728 | 53 | Low | 1124301.13 | 0.436 | 4 | 1182515.87 | 16 | 1.37 | 1.4
P004 | Materials | SUP007 | 2025-10 | 2025-09-08 | 2517355.93 | 2306817 | -210538.93 | 210538.93 | 0 | 2025-10-28 | 6 | 2659747.69 | -142391.76 | DOWN | 0.0566 | 50 | Low | 1084211.97 | 0.444 | 3 | 1222605.03 | 16 | 1.37 | 1.4
P004 | Electronics | SUP007 | 2025-11 | 2025-08-19 | 4631688.6 | 2336090 | -2295598.6 | 2295598.6 | 1 | 2025-11-28 | 1 |  |  |  |  | 101 | Low | 1392958.6 | 0.325 | 0 | 943131.4 | 7 | 0.59 | 1.31
P004 | Electronics | SUP007 | 2025-11 | 2025-09-07 | 3839036.09 | 2336090 | -1502946.09 | 1502946.09 | 1 | 2025-11-28 | 2 | 4631688.6 | -792652.51 | DOWN | 0.2065 | 82 | Low | 1470291.82 | 0.376 | 4 | 865798.18 | 7 | 0.59 | 1.31
P004 | Electronics | SUP007 | 2025-11 | 2025-09-10 | 3302044.9 | 2336090 | -965954.9 | 965954.9 | 1 | 2025-11-28 | 3 | 3839036.09 | -536991.19 | DOWN | 0.1626 | 79 | Low | 1257772.62 | 0.385 | 0 | 1078317.38 | 7 | 0.59 | 1.31
P004 | Electronics | SUP007 | 2025-11 | 2025-09-10 | 2961930.51 | 2336090 | -625840.51 | 625840.51 | 1 | 2025-11-28 | 4 | 3302044.9 | -340114.39 | DOWN | 0.1148 | 79 | Low | 1153297.83 | 0.385 | 2 | 1182792.17 | 7 | 0.59 | 1.31
P004 | Materials | SUP007 | 2025-12 | 2025-07-05 | 2029141.06 | 1109870 | -919271.06 | 919271.06 | 1 | 2025-12-28 | 1 |  |  |  |  | 176 | Low | 237097.55 | 0.118 | 2 | 872772.45 | 9 | 1.11 | 0.94
P004 | Materials | SUP007 | 2025-12 | 2025-07-11 | 1725156.27 | 1109870 | -615286.27 | 615286.27 | 1 | 2025-12-28 | 2 | 2029141.06 | -303984.79 | DOWN | 0.1762 | 170 | Low | 229572.74 | 0.135 | 5 | 880297.26 | 9 | 1.11 | 0.94
P004 | Materials | SUP007 | 2025-12 | 2025-07-26 | 1504883.84 | 1109870 | -395013.84 | 395013.84 | 1 | 2025-12-28 | 3 | 1725156.27 | -220272.43 | DOWN | 0.1464 | 155 | Low | 243172.4 | 0.175 | 1 | 866697.6 | 9 | 1.11 | 0.94
P004 | Materials | SUP007 | 2025-12 | 2025-07-26 | 1355360.89 | 1109870 | -245490.89 | 245490.89 | 1 | 2025-12-28 | 4 | 1504883.84 | -149522.95 | DOWN | 0.1103 | 155 | Low | 225855.01 | 0.175 | 0 | 884014.99 | 9 | 1.11 | 0.94
P004 | Materials | SUP007 | 2025-12 | 2025-11-18 | 1260252.39 | 1109870 | -150382.39 | 150382.39 | 0 | 2025-12-28 | 5 | 1355360.89 | -95108.5 | DOWN | 0.0755 | 40 | Medium | 629044.9 | 0.485 | 5 | 480825.1 | 9 | 1.11 | 0.94
P004 | Materials | SUP007 | 2025-12 | 2025-12-17 | 1210270.93 | 1109870 | -100400.93 | 100400.93 | 0 | 2025-12-28 | 6 | 1260252.39 | -49981.46 | DOWN | 0.0413 | 11 | Medium | 733300.44 | 0.563 | 6 | 376569.56 | 9 | 1.11 | 0.94
P004 | Electronics | SUP030 | 2025-01 | 2024-08-03 | 1244636.62 | 776346 | -468290.62 | 468290.62 | 1 | 2025-01-28 | 1 |  |  |  |  | 178 | Low | 166740.73 | 0.13 | 0 | 609605.27 | 9 | 1 | 1.26
P004 | Electronics | SUP030 | 2025-01 | 2024-08-30 | 1027045.72 | 776346 | -250699.72 | 250699.72 | 1 | 2025-01-28 | 2 | 1244636.62 | -217590.9 | DOWN | 0.2119 | 151 | Low | 222836.28 | 0.204 | 3 | 553509.72 | 9 | 1 | 1.26
P004 | Electronics | SUP030 | 2025-01 | 2024-09-05 | 908761.86 | 776346 | -132415.86 | 132415.86 | 0 | 2025-01-28 | 3 | 1027045.72 | -118283.86 | DOWN | 0.1302 | 145 | Low | 216070.4 | 0.222 | 0 | 560275.6 | 9 | 1 | 1.26
P004 | Electronics | SUP030 | 2025-01 | 2024-11-12 | 858553.59 | 776346 | -82207.59 | 82207.59 | 0 | 2025-01-28 | 4 | 908761.86 | -50208.27 | DOWN | 0.0585 | 77 | Low | 355124.45 | 0.423 | 2 | 421221.55 | 9 | 1 | 1.26
P004 | Electronics | SUP030 | 2025-01 | 2024-11-17 | 818350.75 | 776346 | -42004.75 | 42004.75 | 0 | 2025-01-28 | 5 | 858553.59 | -40202.84 | DOWN | 0.0491 | 72 | Low | 374538.63 | 0.437 | 4 | 401807.37 | 9 | 1 | 1.26
P004 | Electronics | SUP030 | 2025-01 | 2025-01-12 | 795963.83 | 776346 | -19617.83 | 19617.83 | 0 | 2025-01-28 | 6 | 818350.75 | -22386.92 | DOWN | 0.0281 | 16 | Medium | 466363.88 | 0.603 | 3 | 309982.12 | 9 | 1 | 1.26
P004 | Electronics | SUP030 | 2025-02 | 2024-09-26 | 3917844.97 | 2118772 | -1799072.97 | 1799072.97 | 1 | 2025-02-28 | 1 |  |  |  |  | 155 | Low | 734376.23 | 0.186 | 1 | 1384395.77 | 13 | 1.26 | 0.97
P004 | Electronics | SUP030 | 2025-02 | 2024-10-11 | 3096631.56 | 2118772 | -977859.56 | 977859.56 | 1 | 2025-02-28 | 2 | 3917844.97 | -821213.41 | DOWN | 0.2652 | 140 | Low | 718265.22 | 0.229 | 0 | 1400506.78 | 13 | 1.26 | 0.97
P004 | Electronics | SUP030 | 2025-02 | 2025-02-18 | 2687616.59 | 2118772 | -568844.59 | 568844.59 | 1 | 2025-02-28 | 3 | 3096631.56 | -409014.97 | DOWN | 0.1522 | 10 | Low | 1607173.3 | 0.599 | 2 | 511598.7 | 13 | 1.26 | 0.97
P004 | Logistics | SUP030 | 2025-03 | 2024-10-03 | 2456384.55 | 1377547 | -1078837.55 | 1078837.55 | 1 | 2025-03-28 | 1 |  |  |  |  | 176 | Low | 338038.04 | 0.13 | 2 | 1039508.96 | 11 | 0.73 | 1.3
P004 | Logistics | SUP030 | 2025-03 | 2024-12-01 | 1992216.78 | 1377547 | -614669.78 | 614669.78 | 1 | 2025-03-28 | 2 | 2456384.55 | -464167.77 | DOWN | 0.233 | 117 | Low | 625871.42 | 0.304 | 4 | 751675.58 | 11 | 0.73 | 1.3
P004 | Logistics | SUP030 | 2025-03 | 2025-01-14 | 1720659.96 | 1377547 | -343112.96 | 343112.96 | 1 | 2025-03-28 | 3 | 1992216.78 | -271556.82 | DOWN | 0.1578 | 73 | Low | 806817.49 | 0.434 | 2 | 570729.51 | 11 | 0.73 | 1.3
P004 | Logistics | SUP030 | 2025-03 | 2025-01-24 | 1531475.96 | 1377547 | -153928.96 | 153928.96 | 0 | 2025-03-28 | 4 | 1720659.96 | -189184 | DOWN | 0.1235 | 63 | Low | 736064.65 | 0.464 | 3 | 641482.35 | 11 | 0.73 | 1.3
P004 | Logistics | SUP030 | 2025-03 | 2025-01-26 | 1477343.96 | 1377547 | -99796.96 | 99796.96 | 0 | 2025-03-28 | 5 | 1531475.96 | -54132 | DOWN | 0.0366 | 61 | Low | 697048.43 | 0.47 | 3 | 680498.57 | 11 | 0.73 | 1.3
P004 | Services | SUP030 | 2025-04 | 2025-01-02 | 2593740.28 | 1464464 | -1129276.28 | 1129276.28 | 1 | 2025-04-28 | 1 |  |  |  |  | 116 | Low | 723064.08 | 0.284 | 2 | 741399.92 | 15 | 1.69 | 1.47
P004 | Services | SUP030 | 2025-04 | 2025-01-13 | 2083784.21 | 1464464 | -619320.21 | 619320.21 | 1 | 2025-04-28 | 2 | 2593740.28 | -509956.07 | DOWN | 0.2447 | 105 | Low | 613270.5 | 0.314 | 2 | 851193.5 | 15 | 1.69 | 1.47
P004 | Services | SUP030 | 2025-04 | 2025-03-08 | 1808733.68 | 1464464 | -344269.68 | 344269.68 | 1 | 2025-04-28 | 3 | 2083784.21 | -275050.53 | DOWN | 0.1521 | 51 | Low | 877248.17 | 0.461 | 3 | 587215.83 | 15 | 1.69 | 1.47
P004 | Materials | SUP030 | 2025-05 | 2024-12-26 | 3045682.51 | 1937163 | -1108519.51 | 1108519.51 | 1 | 2025-05-28 | 1 |  |  |  |  | 153 | Low | 570960.92 | 0.197 | 0 | 1366202.08 | 12 | 1.03 | 1.42
P004 | Materials | SUP030 | 2025-05 | 2025-01-22 | 2539662.01 | 1937163 | -602499.01 | 602499.01 | 1 | 2025-05-28 | 2 | 3045682.51 | -506020.5 | DOWN | 0.1992 | 126 | Low | 675573.46 | 0.277 | 2 | 1261589.54 | 12 | 1.03 | 1.42
P004 | Materials | SUP030 | 2025-05 | 2025-02-08 | 2274508.2 | 1937163 | -337345.2 | 337345.2 | 0 | 2025-05-28 | 3 | 2539662.01 | -265153.81 | DOWN | 0.1166 | 109 | Low | 761895.76 | 0.327 | 1 | 1175267.24 | 12 | 1.03 | 1.42
P004 | Logistics | SUP030 | 2025-06 | 2025-01-31 | 1484519.44 | 756360 | -728159.44 | 728159.44 | 1 | 2025-06-28 | 1 |  |  |  |  | 148 | Low | 290949.06 | 0.213 | 3 | 465410.94 | 15 | 0.81 | 1.56
P004 | Logistics | SUP030 | 2025-06 | 2025-02-10 | 1132635.54 | 756360 | -376275.54 | 376275.54 | 1 | 2025-06-28 | 2 | 1484519.44 | -351883.9 | DOWN | 0.3107 | 138 | Low | 281604.42 | 0.242 | 0 | 474755.58 | 15 | 0.81 | 1.56
P004 | Logistics | SUP030 | 2025-06 | 2025-04-01 | 979490.55 | 756360 | -223130.55 | 223130.55 | 1 | 2025-06-28 | 3 | 1132635.54 | -153144.99 | DOWN | 0.1564 | 88 | Low | 366989.67 | 0.39 | 1 | 389370.33 | 15 | 0.81 | 1.56
P004 | Logistics | SUP030 | 2025-06 | 2025-04-14 | 874116.71 | 756360 | -117756.71 | 117756.71 | 0 | 2025-06-28 | 4 | 979490.55 | -105373.84 | DOWN | 0.1205 | 75 | Low | 393381.32 | 0.428 | 0 | 362978.68 | 15 | 0.81 | 1.56
P004 | Materials | SUP030 | 2025-07 | 2025-01-29 | 388646.43 | 208243 | -180403.43 | 180403.43 | 1 | 2025-07-28 | 1 |  |  |  |  | 180 | Low | 43822.9 | 0.12 | 0 | 164420.1 | 10 | 1.72 | 1
P004 | Materials | SUP030 | 2025-07 | 2025-03-04 | 313732.45 | 208243 | -105489.45 | 105489.45 | 1 | 2025-07-28 | 2 | 388646.43 | -74913.98 | DOWN | 0.2388 | 146 | Low | 62416.16 | 0.201 | 0 | 145826.84 | 10 | 1.72 | 1
P004 | Materials | SUP030 | 2025-07 | 2025-06-09 | 269178.84 | 208243 | -60935.84 | 60935.84 | 1 | 2025-07-28 | 3 | 313732.45 | -44553.61 | DOWN | 0.1655 | 49 | Low | 119051.83 | 0.465 | 3 | 89191.17 | 10 | 1.72 | 1
P004 | Materials | SUP030 | 2025-07 | 2025-07-03 | 242374.05 | 208243 | -34131.05 | 34131.05 | 0 | 2025-07-28 | 4 | 269178.84 | -26804.79 | DOWN | 0.1106 | 25 | Medium | 125820.73 | 0.53 | 5 | 82422.27 | 10 | 1.72 | 1
P004 | Mechanical | SUP030 | 2025-08 | 2025-03-21 | 737413.59 | 442889 | -294524.59 | 294524.59 | 1 | 2025-08-28 | 1 |  |  |  |  | 160 | Low | 133381.57 | 0.168 | 1 | 309507.43 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP030 | 2025-08 | 2025-05-30 | 612525.76 | 442889 | -169636.76 | 169636.76 | 1 | 2025-08-28 | 2 | 737413.59 | -124887.83 | DOWN | 0.2039 | 90 | Low | 215466.25 | 0.364 | 2 | 227422.75 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP030 | 2025-08 | 2025-07-24 | 541298.14 | 442889 | -98409.14 | 98409.14 | 1 | 2025-08-28 | 3 | 612525.76 | -71227.62 | DOWN | 0.1316 | 35 | Low | 267646.95 | 0.519 | 4 | 175242.05 | 13 | 1.45 | 1.13
P004 | Services | SUP030 | 2025-09 | 2025-04-10 | 4802603.25 | 2430411 | -2372192.25 | 2372192.25 | 1 | 2025-09-28 | 1 |  |  |  |  | 171 | Low | 632480.41 | 0.14 | 0 | 1797930.59 | 12 | 1.31 | 1.3
P004 | Services | SUP030 | 2025-09 | 2025-07-10 | 3820484.01 | 2430411 | -1390073.01 | 1390073.01 | 1 | 2025-09-28 | 2 | 4802603.25 | -982119.24 | DOWN | 0.2571 | 80 | Low | 1587421.69 | 0.399 | 6 | 842989.31 | 12 | 1.31 | 1.3
P004 | Services | SUP030 | 2025-09 | 2025-08-19 | 3166099.65 | 2430411 | -735688.65 | 735688.65 | 1 | 2025-09-28 | 3 | 3820484.01 | -654384.36 | DOWN | 0.2067 | 40 | Low | 1737858.13 | 0.513 | 5 | 692552.87 | 12 | 1.31 | 1.3
P004 | Services | SUP030 | 2025-10 | 2025-06-29 | 4841535.37 | 2376093 | -2465442.37 | 2465442.37 | 1 | 2025-10-28 | 1 |  |  |  |  | 121 | Low | 1348572.71 | 0.28 | 1 | 1027520.29 | 16 | 1.37 | 1.4
P004 | Services | SUP030 | 2025-10 | 2025-07-29 | 3686232.65 | 2376093 | -1310139.65 | 1310139.65 | 1 | 2025-10-28 | 2 | 4841535.37 | -1155302.72 | DOWN | 0.3134 | 91 | Low | 1288145.46 | 0.365 | 3 | 1087947.54 | 16 | 1.37 | 1.4
P004 | Services | SUP030 | 2025-10 | 2025-08-14 | 3040217.33 | 2376093 | -664124.33 | 664124.33 | 1 | 2025-10-28 | 3 | 3686232.65 | -646015.32 | DOWN | 0.2125 | 75 | Low | 1209334.77 | 0.41 | 5 | 1166758.23 | 16 | 1.37 | 1.4
P004 | Services | SUP030 | 2025-10 | 2025-08-14 | 2764317 | 2376093 | -388224 | 388224 | 0 | 2025-10-28 | 4 | 3040217.33 | -275900.33 | DOWN | 0.0998 | 75 | Low | 1136949.92 | 0.41 | 5 | 1239143.08 | 16 | 1.37 | 1.4
P004 | Materials | SUP030 | 2025-11 | 2025-07-27 | 996003.52 | 605238 | -390765.52 | 390765.52 | 1 | 2025-11-28 | 1 |  |  |  |  | 124 | Low | 276040.51 | 0.284 | 0 | 329197.49 | 7 | 0.59 | 1.31
P004 | Materials | SUP030 | 2025-11 | 2025-08-26 | 823886.08 | 605238 | -218648.08 | 218648.08 | 1 | 2025-11-28 | 2 | 996003.52 | -172117.44 | DOWN | 0.2089 | 94 | Low | 285101.82 | 0.372 | 3 | 320136.18 | 7 | 0.59 | 1.31
P004 | Materials | SUP030 | 2025-11 | 2025-09-01 | 725637.68 | 605238 | -120399.68 | 120399.68 | 1 | 2025-11-28 | 3 | 823886.08 | -98248.4 | DOWN | 0.1354 | 88 | Low | 288620.58 | 0.39 | 2 | 316617.42 | 7 | 0.59 | 1.31
P004 | Materials | SUP030 | 2025-11 | 2025-09-20 | 673036.82 | 605238 | -67798.82 | 67798.82 | 0 | 2025-11-28 | 4 | 725637.68 | -52600.86 | DOWN | 0.0782 | 69 | Low | 294959.79 | 0.446 | 5 | 310278.21 | 7 | 0.59 | 1.31
P004 | Materials | SUP030 | 2025-11 | 2025-09-22 | 642399.06 | 605238 | -37161.06 | 37161.06 | 0 | 2025-11-28 | 5 | 673036.82 | -30637.76 | DOWN | 0.0477 | 67 | Low | 308207.26 | 0.452 | 0 | 297030.74 | 7 | 0.59 | 1.31
P004 | Electronics | SUP030 | 2025-12 | 2025-08-12 | 3769848.8 | 1850432 | -1919416.8 | 1919416.8 | 1 | 2025-12-28 | 1 |  |  |  |  | 138 | Low | 948465.41 | 0.239 | 0 | 901966.59 | 9 | 1.11 | 0.94
P004 | Electronics | SUP030 | 2025-12 | 2025-09-04 | 2939974.88 | 1850432 | -1089542.88 | 1089542.88 | 1 | 2025-12-28 | 2 | 3769848.8 | -829873.92 | DOWN | 0.2823 | 115 | Low | 934174.16 | 0.306 | 1 | 916257.84 | 9 | 1.11 | 0.94
P004 | Electronics | SUP030 | 2025-12 | 2025-11-01 | 2485845.11 | 1850432 | -635413.11 | 635413.11 | 1 | 2025-12-28 | 3 | 2939974.88 | -454129.77 | DOWN | 0.1827 | 57 | Low | 1146999.57 | 0.475 | 5 | 703432.43 | 9 | 1.11 | 0.94
P004 | Electronics | SUP030 | 2025-12 | 2025-11-22 | 2216050.84 | 1850432 | -365618.84 | 365618.84 | 1 | 2025-12-28 | 4 | 2485845.11 | -269794.27 | DOWN | 0.1217 | 36 | Low | 1116720.49 | 0.537 | 4 | 733711.51 | 9 | 1.11 | 0.94
P004 | Logistics | SUP011 | 2025-01 | 2024-08-05 | 2479152.06 | 1271713 | -1207439.06 | 1207439.06 | 1 | 2025-01-28 | 1 |  |  |  |  | 176 | Low | 323482.06 | 0.13 | 0 | 948230.94 | 9 | 1 | 1.26
P004 | Logistics | SUP011 | 2025-01 | 2024-08-20 | 1905028.85 | 1271713 | -633315.85 | 633315.85 | 1 | 2025-01-28 | 2 | 2479152.06 | -574123.21 | DOWN | 0.3014 | 161 | Low | 318728.48 | 0.174 | 0 | 952984.52 | 9 | 1 | 1.26
P004 | Logistics | SUP011 | 2025-01 | 2024-10-03 | 1611388.15 | 1271713 | -339675.15 | 339675.15 | 1 | 2025-01-28 | 3 | 1905028.85 | -293640.7 | DOWN | 0.1822 | 117 | Low | 486246.95 | 0.304 | 6 | 785466.05 | 9 | 1 | 1.26
P004 | Logistics | SUP011 | 2025-01 | 2024-10-30 | 1453423.52 | 1271713 | -181710.52 | 181710.52 | 0 | 2025-01-28 | 4 | 1611388.15 | -157964.63 | DOWN | 0.1087 | 90 | Low | 578263.11 | 0.384 | 6 | 693449.89 | 9 | 1 | 1.26
P004 | Logistics | SUP011 | 2025-01 | 2024-12-21 | 1361773.9 | 1271713 | -90060.9 | 90060.9 | 0 | 2025-01-28 | 5 | 1453423.52 | -91649.62 | DOWN | 0.0673 | 38 | Medium | 753946.01 | 0.538 | 5 | 517766.99 | 9 | 1 | 1.26
P004 | Logistics | SUP011 | 2025-01 | 2025-01-06 | 1294749.07 | 1271713 | -23036.07 | 23036.07 | 0 | 2025-01-28 | 6 | 1361773.9 | -67024.83 | DOWN | 0.0518 | 22 | Medium | 796927.54 | 0.585 | 6 | 474785.46 | 9 | 1 | 1.26
P004 | Logistics | SUP011 | 2025-02 | 2024-09-02 | 1320284.59 | 654680 | -665604.59 | 665604.59 | 1 | 2025-02-28 | 1 |  |  |  |  | 179 | Low | 160954.18 | 0.126 | 2 | 493725.82 | 13 | 1.26 | 0.97
P004 | Logistics | SUP011 | 2025-02 | 2024-11-14 | 1028790.82 | 654680 | -374110.82 | 374110.82 | 1 | 2025-02-28 | 2 | 1320284.59 | -291493.77 | DOWN | 0.2833 | 106 | Low | 336910.97 | 0.327 | 0 | 317769.03 | 13 | 1.26 | 0.97
P004 | Logistics | SUP011 | 2025-02 | 2024-12-24 | 882775.87 | 654680 | -228095.87 | 228095.87 | 1 | 2025-02-28 | 3 | 1028790.82 | -146014.95 | DOWN | 0.1654 | 66 | Low | 419735.88 | 0.441 | 0 | 234944.12 | 13 | 1.26 | 0.97
P004 | Logistics | SUP011 | 2025-02 | 2025-01-07 | 786651.68 | 654680 | -131971.68 | 131971.68 | 1 | 2025-02-28 | 4 | 882775.87 | -96124.19 | DOWN | 0.1222 | 52 | Low | 349857.9 | 0.481 | 4 | 304822.1 | 13 | 1.26 | 0.97
P004 | Logistics | SUP011 | 2025-02 | 2025-02-16 | 718760.15 | 654680 | -64080.15 | 64080.15 | 0 | 2025-02-28 | 5 | 786651.68 | -67891.53 | DOWN | 0.0945 | 12 | Medium | 414240.71 | 0.596 | 1 | 240439.29 | 13 | 1.26 | 0.97
P004 | Logistics | SUP011 | 2025-02 | 2025-02-17 | 701436.02 | 654680 | -46756.02 | 46756.02 | 0 | 2025-02-28 | 6 | 718760.15 | -17324.13 | DOWN | 0.0247 | 11 | Medium | 434502.41 | 0.599 | 6 | 220177.59 | 13 | 1.26 | 0.97
P004 | Logistics | SUP011 | 2025-03 | 2024-10-03 | 1550428.03 | 850594 | -699834.03 | 699834.03 | 1 | 2025-03-28 | 1 |  |  |  |  | 176 | Low | 187437.65 | 0.13 | 1 | 663156.35 | 11 | 0.73 | 1.3
P004 | Logistics | SUP011 | 2025-03 | 2024-10-31 | 1266786.44 | 850594 | -416192.44 | 416192.44 | 1 | 2025-03-28 | 2 | 1550428.03 | -283641.59 | DOWN | 0.2239 | 148 | Low | 278813.02 | 0.213 | 3 | 571780.98 | 11 | 0.73 | 1.3
P004 | Logistics | SUP011 | 2025-03 | 2025-01-21 | 1092136.7 | 850594 | -241542.7 | 241542.7 | 1 | 2025-03-28 | 3 | 1266786.44 | -174649.74 | DOWN | 0.1599 | 66 | Low | 507679.71 | 0.455 | 4 | 342914.29 | 11 | 0.73 | 1.3
P004 | Logistics | SUP011 | 2025-03 | 2025-01-29 | 1004493.89 | 850594 | -153899.89 | 153899.89 | 1 | 2025-03-28 | 4 | 1092136.7 | -87642.81 | DOWN | 0.0873 | 58 | Medium | 479692.06 | 0.479 | 3 | 370901.94 | 11 | 0.73 | 1.3
P004 | Logistics | SUP011 | 2025-03 | 2025-02-21 | 933287.62 | 850594 | -82693.62 | 82693.62 | 0 | 2025-03-28 | 5 | 1004493.89 | -71206.27 | DOWN | 0.0763 | 35 | Medium | 529242.83 | 0.547 | 4 | 321351.17 | 11 | 0.73 | 1.3
P004 | Logistics | SUP011 | 2025-03 | 2025-02-23 | 901178.41 | 850594 | -50584.41 | 50584.41 | 0 | 2025-03-28 | 6 | 933287.62 | -32109.21 | DOWN | 0.0356 | 33 | Medium | 501327.03 | 0.552 | 9 | 349266.97 | 11 | 0.73 | 1.3
P004 | Services | SUP011 | 2025-04 | 2024-11-06 | 4036121.68 | 2042848 | -1993273.68 | 1993273.68 | 1 | 2025-04-28 | 1 |  |  |  |  | 173 | Low | 491541.87 | 0.128 | 4 | 1551306.13 | 15 | 1.69 | 1.47
P004 | Services | SUP011 | 2025-04 | 2024-11-30 | 3096340.28 | 2042848 | -1053492.28 | 1053492.28 | 1 | 2025-04-28 | 2 | 4036121.68 | -939781.4 | DOWN | 0.3035 | 149 | Low | 642600.85 | 0.194 | 6 | 1400247.15 | 15 | 1.69 | 1.47
P004 | Services | SUP011 | 2025-04 | 2024-12-03 | 2630908.35 | 2042848 | -588060.35 | 588060.35 | 1 | 2025-04-28 | 3 | 3096340.28 | -465431.93 | DOWN | 0.1769 | 146 | Low | 489294.54 | 0.202 | 3 | 1553553.46 | 15 | 1.69 | 1.47
P004 | Services | SUP011 | 2025-04 | 2024-12-18 | 2344982.41 | 2042848 | -302134.41 | 302134.41 | 0 | 2025-04-28 | 4 | 2630908.35 | -285925.94 | DOWN | 0.1219 | 131 | Low | 595463.54 | 0.243 | 0 | 1447384.46 | 15 | 1.69 | 1.47
P004 | Services | SUP011 | 2025-04 | 2025-01-14 | 2177299.65 | 2042848 | -134451.65 | 134451.65 | 0 | 2025-04-28 | 5 | 2344982.41 | -167682.76 | DOWN | 0.077 | 104 | Low | 652127.26 | 0.317 | 5 | 1390720.74 | 15 | 1.69 | 1.47
P004 | Services | SUP011 | 2025-04 | 2025-02-28 | 2132883.52 | 2042848 | -90035.52 | 90035.52 | 0 | 2025-04-28 | 6 | 2177299.65 | -44416.13 | DOWN | 0.0208 | 59 | Low | 878499.54 | 0.439 | 2 | 1164348.46 | 15 | 1.69 | 1.47
P004 | Mechanical | SUP011 | 2025-05 | 2024-12-01 | 1551775.98 | 1105338 | -446437.98 | 446437.98 | 1 | 2025-05-28 | 1 |  |  |  |  | 178 | Low | 203443.26 | 0.13 | 1 | 901894.74 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP011 | 2025-05 | 2024-12-27 | 1354770.83 | 1105338 | -249432.83 | 249432.83 | 1 | 2025-05-28 | 2 | 1551775.98 | -197005.15 | DOWN | 0.1454 | 152 | Low | 256156.66 | 0.2 | 0 | 849181.34 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP011 | 2025-05 | 2025-03-11 | 1235757.93 | 1105338 | -130419.93 | 130419.93 | 0 | 2025-05-28 | 3 | 1354770.83 | -119012.9 | DOWN | 0.0963 | 78 | Low | 510892.78 | 0.418 | 0 | 594445.22 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP011 | 2025-05 | 2025-04-12 | 1178137.07 | 1105338 | -72799.07 | 72799.07 | 0 | 2025-05-28 | 4 | 1235757.93 | -57620.86 | DOWN | 0.0489 | 46 | Medium | 557396.61 | 0.512 | 3 | 547941.39 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP011 | 2025-05 | 2025-05-14 | 1144151.32 | 1105338 | -38813.32 | 38813.32 | 0 | 2025-05-28 | 5 | 1178137.07 | -33985.75 | DOWN | 0.0297 | 14 | Medium | 745636.52 | 0.606 | 4 | 359701.48 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP011 | 2025-05 | 2025-05-15 | 1121694.95 | 1105338 | -16356.95 | 16356.95 | 0 | 2025-05-28 | 6 | 1144151.32 | -22456.37 | DOWN | 0.02 | 13 | Medium | 723042.9 | 0.609 | 4 | 382295.1 | 12 | 1.03 | 1.42
P004 | Software | SUP011 | 2025-06 | 2025-01-15 | 2596946.95 | 1233543 | -1363403.95 | 1363403.95 | 1 | 2025-06-28 | 1 |  |  |  |  | 164 | Low | 423848.19 | 0.165 | 2 | 809694.81 | 15 | 0.81 | 1.56
P004 | Software | SUP011 | 2025-06 | 2025-01-22 | 1954694.58 | 1233543 | -721151.58 | 721151.58 | 1 | 2025-06-28 | 2 | 2596946.95 | -642252.37 | DOWN | 0.3286 | 157 | Low | 376581.54 | 0.186 | 2 | 856961.46 | 15 | 0.81 | 1.56
P004 | Software | SUP011 | 2025-06 | 2025-03-11 | 1638706.12 | 1233543 | -405163.12 | 405163.12 | 1 | 2025-06-28 | 3 | 1954694.58 | -315988.46 | DOWN | 0.1928 | 109 | Low | 536730.75 | 0.328 | 2 | 696812.25 | 15 | 0.81 | 1.56
P004 | Software | SUP011 | 2025-06 | 2025-05-03 | 1448766.35 | 1233543 | -215223.35 | 215223.35 | 0 | 2025-06-28 | 4 | 1638706.12 | -189939.77 | DOWN | 0.1311 | 56 | Low | 754613.14 | 0.485 | 4 | 478929.86 | 15 | 0.81 | 1.56
P004 | Software | SUP011 | 2025-06 | 2025-05-07 | 1360775.83 | 1233543 | -127232.83 | 127232.83 | 0 | 2025-06-28 | 5 | 1448766.35 | -87990.52 | DOWN | 0.0647 | 52 | Medium | 626000.41 | 0.496 | 1 | 607542.59 | 15 | 0.81 | 1.56
P004 | Software | SUP011 | 2025-06 | 2025-06-04 | 1292789.59 | 1233543 | -59246.59 | 59246.59 | 0 | 2025-06-28 | 6 | 1360775.83 | -67986.24 | DOWN | 0.0526 | 24 | Medium | 800258.88 | 0.579 | 5 | 433284.12 | 15 | 0.81 | 1.56
P004 | Logistics | SUP011 | 2025-07 | 2025-02-19 | 2633613.23 | 1308252 | -1325361.23 | 1325361.23 | 1 | 2025-07-28 | 1 |  |  |  |  | 159 | Low | 402945.72 | 0.166 | 0 | 905306.28 | 10 | 1.72 | 1
P004 | Logistics | SUP011 | 2025-07 | 2025-05-09 | 2055398.59 | 1308252 | -747146.59 | 747146.59 | 1 | 2025-07-28 | 2 | 2633613.23 | -578214.64 | DOWN | 0.2813 | 80 | Low | 730020.56 | 0.381 | 4 | 578231.44 | 10 | 1.72 | 1
P004 | Logistics | SUP011 | 2025-07 | 2025-05-29 | 1737526.45 | 1308252 | -429274.45 | 429274.45 | 1 | 2025-07-28 | 3 | 2055398.59 | -317872.14 | DOWN | 0.1829 | 60 | Low | 725217.89 | 0.435 | 2 | 583034.11 | 10 | 1.72 | 1
P004 | Logistics | SUP011 | 2025-07 | 2025-07-18 | 1505027.15 | 1308252 | -196775.15 | 196775.15 | 0 | 2025-07-28 | 4 | 1737526.45 | -232499.3 | DOWN | 0.1545 | 10 | Low | 797767.09 | 0.568 | 2 | 510484.91 | 10 | 1.72 | 1
P004 | Materials | SUP011 | 2025-08 | 2025-03-19 | 1818580.92 | 1208441 | -610139.92 | 610139.92 | 1 | 2025-08-28 | 1 |  |  |  |  | 162 | Low | 280491.39 | 0.163 | 0 | 927949.61 | 13 | 1.45 | 1.13
P004 | Materials | SUP011 | 2025-08 | 2025-03-25 | 1525643.41 | 1208441 | -317202.41 | 317202.41 | 1 | 2025-08-28 | 2 | 1818580.92 | -292937.51 | DOWN | 0.192 | 156 | Low | 282628.66 | 0.179 | 2 | 925812.34 | 13 | 1.45 | 1.13
P004 | Materials | SUP011 | 2025-08 | 2025-05-21 | 1382903.37 | 1208441 | -174462.37 | 174462.37 | 0 | 2025-08-28 | 3 | 1525643.41 | -142740.04 | DOWN | 0.1032 | 99 | Low | 433844.7 | 0.339 | 4 | 774596.3 | 13 | 1.45 | 1.13
P004 | Electronics | SUP011 | 2025-09 | 2025-06-09 | 1226508.12 | 690535 | -535973.12 | 535973.12 | 1 | 2025-09-28 | 1 |  |  |  |  | 111 | Low | 369585.54 | 0.31 | 3 | 320949.46 | 12 | 1.31 | 1.3
P004 | Electronics | SUP011 | 2025-09 | 2025-08-08 | 989922.77 | 690535 | -299387.77 | 299387.77 | 1 | 2025-09-28 | 2 | 1226508.12 | -236585.35 | DOWN | 0.239 | 51 | Low | 495299.99 | 0.481 | 0 | 195235.01 | 12 | 1.31 | 1.3
P004 | Electronics | SUP011 | 2025-09 | 2025-09-06 | 863968.47 | 690535 | -173433.47 | 173433.47 | 1 | 2025-09-28 | 3 | 989922.77 | -125954.3 | DOWN | 0.1458 | 22 | Low | 464932.98 | 0.564 | 5 | 225602.02 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP011 | 2025-10 | 2025-05-08 | 2457839.26 | 1547121 | -910718.26 | 910718.26 | 1 | 2025-10-28 | 1 |  |  |  |  | 173 | Low | 327881.45 | 0.133 | 2 | 1219239.55 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP011 | 2025-10 | 2025-06-11 | 2074048.57 | 1547121 | -526927.57 | 526927.57 | 1 | 2025-10-28 | 2 | 2457839.26 | -383790.69 | DOWN | 0.185 | 139 | Low | 501852.54 | 0.229 | 4 | 1045268.46 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP011 | 2025-10 | 2025-06-25 | 1827511.55 | 1547121 | -280390.55 | 280390.55 | 1 | 2025-10-28 | 3 | 2074048.57 | -246537.02 | DOWN | 0.1349 | 125 | Low | 514836.13 | 0.269 | 3 | 1032284.87 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP011 | 2025-10 | 2025-09-21 | 1698356.4 | 1547121 | -151235.4 | 151235.4 | 0 | 2025-10-28 | 4 | 1827511.55 | -129155.15 | DOWN | 0.076 | 37 | Medium | 843722.68 | 0.518 | 5 | 703398.32 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP011 | 2025-10 | 2025-10-10 | 1625609.35 | 1547121 | -78488.35 | 78488.35 | 0 | 2025-10-28 | 5 | 1698356.4 | -72747.05 | DOWN | 0.0448 | 18 | Medium | 942568.03 | 0.571 | 8 | 604552.97 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP011 | 2025-10 | 2025-10-11 | 1586773.11 | 1547121 | -39652.11 | 39652.11 | 0 | 2025-10-28 | 6 | 1625609.35 | -38836.24 | DOWN | 0.0245 | 17 | Medium | 865166.43 | 0.574 | 4 | 681954.57 | 16 | 1.37 | 1.4
P004 | Logistics | SUP011 | 2025-11 | 2025-08-07 | 3017614.83 | 1582455 | -1435159.83 | 1435159.83 | 1 | 2025-11-28 | 1 |  |  |  |  | 113 | Low | 879432.66 | 0.316 | 7 | 703022.34 | 7 | 0.59 | 1.31
P004 | Logistics | SUP011 | 2025-11 | 2025-09-21 | 2343928.36 | 1582455 | -761473.36 | 761473.36 | 1 | 2025-11-28 | 2 | 3017614.83 | -673686.47 | DOWN | 0.2874 | 68 | Low | 1109085.92 | 0.449 | 3 | 473369.08 | 7 | 0.59 | 1.31
P004 | Logistics | SUP011 | 2025-11 | 2025-11-13 | 1991884.61 | 1582455 | -409429.61 | 409429.61 | 1 | 2025-11-28 | 3 | 2343928.36 | -352043.75 | DOWN | 0.1767 | 15 | Low | 1142063.54 | 0.606 | 6 | 440391.46 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP011 | 2025-12 | 2025-07-19 | 2306356.94 | 1601898 | -704458.94 | 704458.94 | 1 | 2025-12-28 | 1 |  |  |  |  | 162 | Low | 395082.55 | 0.169 | 0 | 1206815.45 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP011 | 2025-12 | 2025-10-08 | 1999975.77 | 1601898 | -398077.77 | 398077.77 | 1 | 2025-12-28 | 2 | 2306356.94 | -306381.17 | DOWN | 0.1532 | 81 | Low | 839199.12 | 0.405 | 1 | 762698.88 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP011 | 2025-12 | 2025-10-22 | 1828198.75 | 1601898 | -226300.75 | 226300.75 | 0 | 2025-12-28 | 3 | 1999975.77 | -171777.02 | DOWN | 0.094 | 67 | Low | 816000.66 | 0.446 | 4 | 785897.34 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP011 | 2025-12 | 2025-11-15 | 1726681.48 | 1601898 | -124783.48 | 124783.48 | 0 | 2025-12-28 | 4 | 1828198.75 | -101517.27 | DOWN | 0.0588 | 43 | Medium | 903654.94 | 0.516 | 2 | 698243.06 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP011 | 2025-12 | 2025-12-06 | 1673001.06 | 1601898 | -71103.06 | 71103.06 | 0 | 2025-12-28 | 5 | 1726681.48 | -53680.42 | DOWN | 0.0321 | 22 | Medium | 899659.29 | 0.577 | 3 | 702238.71 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP004 | 2025-01 | 2024-08-21 | 1381551.27 | 906511 | -475040.27 | 475040.27 | 1 | 2025-01-28 | 1 |  |  |  |  | 160 | Low | 201272.07 | 0.136 | 4 | 705238.93 | 9 | 1 | 1.26
P004 | Mechanical | SUP004 | 2025-01 | 2024-08-26 | 1257518.13 | 906511 | -351007.13 | 351007.13 | 1 | 2025-01-28 | 2 | 1381551.27 | -124033.14 | DOWN | 0.0986 | 155 | Low | 183059.09 | 0.148 | 2 | 723451.91 | 9 | 1 | 1.26
P004 | Mechanical | SUP004 | 2025-01 | 2024-09-26 | 1164917.55 | 906511 | -258406.55 | 258406.55 | 1 | 2025-01-28 | 3 | 1257518.13 | -92600.58 | DOWN | 0.0795 | 124 | Low | 246868.31 | 0.218 | 1 | 659642.69 | 9 | 1 | 1.26
P004 | Mechanical | SUP004 | 2025-01 | 2024-12-04 | 1103980.2 | 906511 | -197469.2 | 197469.2 | 1 | 2025-01-28 | 4 | 1164917.55 | -60937.35 | DOWN | 0.0552 | 55 | Low | 429585.4 | 0.375 | 6 | 476925.6 | 9 | 1 | 1.26
P004 | Services | SUP004 | 2025-02 | 2024-09-02 | 2285627.6 | 1440474 | -845153.6 | 845153.6 | 1 | 2025-02-28 | 1 |  |  |  |  | 179 | Low | 211741.92 | 0.097 | 4 | 1228732.08 | 13 | 1.26 | 0.97
P004 | Services | SUP004 | 2025-02 | 2024-09-18 | 2063166.21 | 1440474 | -622692.21 | 622692.21 | 1 | 2025-02-28 | 2 | 2285627.6 | -222461.39 | DOWN | 0.1078 | 163 | Low | 247898.57 | 0.126 | 0 | 1192575.43 | 13 | 1.26 | 0.97
P004 | Services | SUP004 | 2025-02 | 2024-11-27 | 1879822.17 | 1440474 | -439348.17 | 439348.17 | 1 | 2025-02-28 | 3 | 2063166.21 | -183344.04 | DOWN | 0.0975 | 93 | Low | 561454.83 | 0.28 | 0 | 879019.17 | 13 | 1.26 | 0.97
P004 | Services | SUP004 | 2025-02 | 2024-12-02 | 1787512.18 | 1440474 | -347038.18 | 347038.18 | 1 | 2025-02-28 | 4 | 1879822.17 | -92309.99 | DOWN | 0.0516 | 88 | Low | 500753.05 | 0.291 | 0 | 939720.95 | 13 | 1.26 | 0.97
P004 | Services | SUP004 | 2025-02 | 2025-02-05 | 1690220.66 | 1440474 | -249746.66 | 249746.66 | 0 | 2025-02-28 | 5 | 1787512.18 | -97291.52 | DOWN | 0.0576 | 23 | Low | 736620.19 | 0.434 | 7 | 703853.81 | 13 | 1.26 | 0.97
P004 | Services | SUP004 | 2025-02 | 2025-02-14 | 1637413.48 | 1440474 | -196939.48 | 196939.48 | 0 | 2025-02-28 | 6 | 1690220.66 | -52807.18 | DOWN | 0.0323 | 14 | Low | 723452.99 | 0.454 | 4 | 717021.01 | 13 | 1.26 | 0.97
P004 | Services | SUP004 | 2025-03 | 2024-10-07 | 720514.75 | 364107 | -356407.75 | 356407.75 | 1 | 2025-03-28 | 1 |  |  |  |  | 172 | Low | 77958.4 | 0.109 | 0 | 286148.6 | 11 | 0.73 | 1.3
P004 | Services | SUP004 | 2025-03 | 2025-01-23 | 641403.26 | 364107 | -277296.26 | 277296.26 | 1 | 2025-03-28 | 2 | 720514.75 | -79111.49 | DOWN | 0.1233 | 64 | Low | 234562.56 | 0.355 | 1 | 129544.44 | 11 | 0.73 | 1.3
P004 | Services | SUP004 | 2025-03 | 2025-02-10 | 579712.51 | 364107 | -215605.51 | 215605.51 | 1 | 2025-03-28 | 3 | 641403.26 | -61690.75 | DOWN | 0.1064 | 46 | Low | 239445.21 | 0.395 | 2 | 124661.79 | 11 | 0.73 | 1.3
P004 | Services | SUP004 | 2025-03 | 2025-03-13 | 518701.08 | 364107 | -154594.08 | 154594.08 | 1 | 2025-03-28 | 4 | 579712.51 | -61011.43 | DOWN | 0.1176 | 15 | Low | 236536.06 | 0.466 | 4 | 127570.94 | 11 | 0.73 | 1.3
P004 | Services | SUP004 | 2025-04 | 2024-12-13 | 1900977.17 | 1188564 | -712413.17 | 712413.17 | 1 | 2025-04-28 | 1 |  |  |  |  | 136 | Low | 337552.51 | 0.176 | 3 | 851011.49 | 15 | 1.69 | 1.47
P004 | Services | SUP004 | 2025-04 | 2024-12-16 | 1707833.95 | 1188564 | -519269.95 | 519269.95 | 1 | 2025-04-28 | 2 | 1900977.17 | -193143.22 | DOWN | 0.1131 | 133 | Low | 321205.46 | 0.183 | 4 | 867358.54 | 15 | 1.69 | 1.47
P004 | Services | SUP004 | 2025-04 | 2025-02-16 | 1569433.6 | 1188564 | -380869.6 | 380869.6 | 1 | 2025-04-28 | 3 | 1707833.95 | -138400.35 | DOWN | 0.0882 | 71 | Low | 504395.37 | 0.313 | 1 | 684168.63 | 15 | 1.69 | 1.47
P004 | Services | SUP004 | 2025-04 | 2025-02-22 | 1462969.74 | 1188564 | -274405.74 | 274405.74 | 1 | 2025-04-28 | 4 | 1569433.6 | -106463.86 | DOWN | 0.0728 | 65 | Low | 485943.3 | 0.325 | 3 | 702620.7 | 15 | 1.69 | 1.47
P004 | Services | SUP004 | 2025-05 | 2024-12-25 | 968714.3 | 511309 | -457405.3 | 457405.3 | 1 | 2025-05-28 | 1 |  |  |  |  | 154 | Low | 146110.82 | 0.149 | 0 | 365198.18 | 12 | 1.03 | 1.42
P004 | Services | SUP004 | 2025-05 | 2025-01-11 | 868601.48 | 511309 | -357292.48 | 357292.48 | 1 | 2025-05-28 | 2 | 968714.3 | -100112.82 | DOWN | 0.1153 | 137 | Low | 163084.32 | 0.188 | 7 | 348224.68 | 12 | 1.03 | 1.42
P004 | Services | SUP004 | 2025-05 | 2025-03-20 | 778570.64 | 511309 | -267261.64 | 267261.64 | 1 | 2025-05-28 | 3 | 868601.48 | -90030.84 | DOWN | 0.1156 | 69 | Low | 263824.34 | 0.342 | 3 | 247484.66 | 12 | 1.03 | 1.42
P004 | Services | SUP004 | 2025-05 | 2025-04-20 | 719744.78 | 511309 | -208435.78 | 208435.78 | 1 | 2025-05-28 | 4 | 778570.64 | -58825.86 | DOWN | 0.0817 | 38 | Low | 301828.2 | 0.412 | 4 | 209480.8 | 12 | 1.03 | 1.42
P004 | Services | SUP004 | 2025-05 | 2025-05-14 | 673605.38 | 511309 | -162296.38 | 162296.38 | 1 | 2025-05-28 | 5 | 719744.78 | -46139.4 | DOWN | 0.0685 | 14 | Low | 338658.49 | 0.467 | 5 | 172650.51 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP004 | 2025-06 | 2025-01-28 | 2859892.39 | 1778869 | -1081023.39 | 1081023.39 | 1 | 2025-06-28 | 1 |  |  |  |  | 151 | Low | 419801.64 | 0.157 | 0 | 1359067.36 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP004 | 2025-06 | 2025-02-17 | 2599572.48 | 1778869 | -820703.48 | 820703.48 | 1 | 2025-06-28 | 2 | 2859892.39 | -260319.91 | DOWN | 0.1001 | 131 | Low | 520502.6 | 0.202 | 4 | 1258366.4 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP004 | 2025-06 | 2025-03-10 | 2403691.91 | 1778869 | -624822.91 | 624822.91 | 1 | 2025-06-28 | 3 | 2599572.48 | -195880.57 | DOWN | 0.0815 | 110 | Low | 568578.85 | 0.25 | 4 | 1210290.15 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP004 | 2025-06 | 2025-06-02 | 2246014.08 | 1778869 | -467145.08 | 467145.08 | 1 | 2025-06-28 | 4 | 2403691.91 | -157677.83 | DOWN | 0.0702 | 26 | Low | 992606.89 | 0.441 | 5 | 786262.11 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP004 | 2025-06 | 2025-06-07 | 2121460.97 | 1778869 | -342591.97 | 342591.97 | 1 | 2025-06-28 | 5 | 2246014.08 | -124553.11 | DOWN | 0.0587 | 21 | Low | 949993.58 | 0.452 | 2 | 828875.42 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP004 | 2025-06 | 2025-06-09 | 2040829.48 | 1778869 | -261960.48 | 261960.48 | 0 | 2025-06-28 | 6 | 2121460.97 | -80631.49 | DOWN | 0.0395 | 19 | Low | 899235.9 | 0.457 | 5 | 879633.1 | 15 | 0.81 | 1.56
P004 | Logistics | SUP004 | 2025-07 | 2025-02-08 | 825617.12 | 436634 | -388983.12 | 388983.12 | 1 | 2025-07-28 | 1 |  |  |  |  | 170 | Low | 88862.2 | 0.105 | 1 | 347771.8 | 10 | 1.72 | 1
P004 | Logistics | SUP004 | 2025-07 | 2025-03-05 | 732523.52 | 436634 | -295889.52 | 295889.52 | 1 | 2025-07-28 | 2 | 825617.12 | -93093.6 | DOWN | 0.1271 | 145 | Low | 121928.33 | 0.157 | 2 | 314705.67 | 10 | 1.72 | 1
P004 | Logistics | SUP004 | 2025-07 | 2025-04-22 | 642639.62 | 436634 | -206005.62 | 206005.62 | 1 | 2025-07-28 | 3 | 732523.52 | -89883.9 | DOWN | 0.1399 | 97 | Low | 169945.8 | 0.257 | 3 | 266688.2 | 10 | 1.72 | 1
P004 | Materials | SUP004 | 2025-08 | 2025-03-03 | 1254649.54 | 754147 | -500502.54 | 500502.54 | 1 | 2025-08-28 | 1 |  |  |  |  | 178 | Low | 126931.66 | 0.095 | 0 | 627215.34 | 13 | 1.45 | 1.13
P004 | Materials | SUP004 | 2025-08 | 2025-03-21 | 1136684.42 | 754147 | -382537.42 | 382537.42 | 1 | 2025-08-28 | 2 | 1254649.54 | -117965.12 | DOWN | 0.1038 | 160 | Low | 144406.3 | 0.129 | 0 | 609740.7 | 13 | 1.45 | 1.13
P004 | Materials | SUP004 | 2025-08 | 2025-07-08 | 1033135.47 | 754147 | -278988.47 | 278988.47 | 1 | 2025-08-28 | 3 | 1136684.42 | -103548.95 | DOWN | 0.1002 | 51 | Low | 367674.16 | 0.364 | 0 | 386472.84 | 13 | 1.45 | 1.13
P004 | Logistics | SUP004 | 2025-09 | 2025-04-01 | 502157.85 | 262581 | -239576.85 | 239576.85 | 1 | 2025-09-28 | 1 |  |  |  |  | 180 | Low | 47969.26 | 0.096 | 3 | 214611.74 | 12 | 1.31 | 1.3
P004 | Logistics | SUP004 | 2025-09 | 2025-04-05 | 440757.12 | 262581 | -178176.12 | 178176.12 | 1 | 2025-09-28 | 2 | 502157.85 | -61400.73 | DOWN | 0.1393 | 176 | Low | 44798.02 | 0.096 | 2 | 217782.98 | 12 | 1.31 | 1.3
P004 | Logistics | SUP004 | 2025-09 | 2025-05-13 | 395614.96 | 262581 | -133033.96 | 133033.96 | 1 | 2025-09-28 | 3 | 440757.12 | -45142.16 | DOWN | 0.1141 | 138 | Low | 75835.48 | 0.18 | 0 | 186745.52 | 12 | 1.31 | 1.3
P004 | Logistics | SUP004 | 2025-09 | 2025-06-29 | 361499.4 | 262581 | -98918.4 | 98918.4 | 1 | 2025-09-28 | 4 | 395614.96 | -34115.56 | DOWN | 0.0944 | 91 | Low | 103880.99 | 0.283 | 1 | 158700.01 | 12 | 1.31 | 1.3
P004 | Logistics | SUP004 | 2025-09 | 2025-08-25 | 337477.14 | 262581 | -74896.14 | 74896.14 | 1 | 2025-09-28 | 5 | 361499.4 | -24022.26 | DOWN | 0.0712 | 34 | Low | 131854.99 | 0.408 | 1 | 130726.01 | 12 | 1.31 | 1.3
P004 | Logistics | SUP004 | 2025-09 | 2025-09-11 | 321809.1 | 262581 | -59228.1 | 59228.1 | 1 | 2025-09-28 | 6 | 337477.14 | -15668.04 | DOWN | 0.0487 | 17 | Low | 131939.45 | 0.445 | 1 | 130641.55 | 12 | 1.31 | 1.3
P004 | Services | SUP004 | 2025-10 | 2025-06-20 | 3212281.09 | 1652771 | -1559510.09 | 1559510.09 | 1 | 2025-10-28 | 1 |  |  |  |  | 130 | Low | 676193.56 | 0.196 | 2 | 976577.44 | 16 | 1.37 | 1.4
P004 | Services | SUP004 | 2025-10 | 2025-06-28 | 2788915.18 | 1652771 | -1136144.18 | 1136144.18 | 1 | 2025-10-28 | 2 | 3212281.09 | -423365.91 | DOWN | 0.1518 | 122 | Low | 604700.66 | 0.213 | 2 | 1048070.34 | 16 | 1.37 | 1.4
P004 | Services | SUP004 | 2025-10 | 2025-08-26 | 2491047.3 | 1652771 | -838276.3 | 838276.3 | 1 | 2025-10-28 | 3 | 2788915.18 | -297867.88 | DOWN | 0.1196 | 63 | Low | 895322.14 | 0.342 | 1 | 757448.86 | 16 | 1.37 | 1.4
P004 | Logistics | SUP004 | 2025-11 | 2025-07-02 | 3495693.02 | 1577319 | -1918374.02 | 1918374.02 | 1 | 2025-11-28 | 1 |  |  |  |  | 149 | Low | 544442.56 | 0.161 | 0 | 1032876.44 | 7 | 0.59 | 1.31
P004 | Logistics | SUP004 | 2025-11 | 2025-08-08 | 3040491.25 | 1577319 | -1463172.25 | 1463172.25 | 1 | 2025-11-28 | 2 | 3495693.02 | -455201.77 | DOWN | 0.1497 | 112 | Low | 784415.64 | 0.245 | 2 | 792903.36 | 7 | 0.59 | 1.31
P004 | Logistics | SUP004 | 2025-11 | 2025-08-22 | 2699339.84 | 1577319 | -1122020.84 | 1122020.84 | 1 | 2025-11-28 | 3 | 3040491.25 | -341151.41 | DOWN | 0.1264 | 98 | Low | 790867.46 | 0.277 | 2 | 786451.54 | 7 | 0.59 | 1.31
P004 | Logistics | SUP004 | 2025-11 | 2025-09-12 | 2436867.44 | 1577319 | -859548.44 | 859548.44 | 1 | 2025-11-28 | 4 | 2699339.84 | -262472.4 | DOWN | 0.1077 | 77 | Low | 852518.48 | 0.325 | 3 | 724800.52 | 7 | 0.59 | 1.31
P004 | Logistics | SUP004 | 2025-11 | 2025-09-28 | 2255064.43 | 1577319 | -677745.43 | 677745.43 | 1 | 2025-11-28 | 5 | 2436867.44 | -181803.01 | DOWN | 0.0806 | 61 | Low | 839394.97 | 0.361 | 6 | 737924.03 | 7 | 0.59 | 1.31
P004 | Logistics | SUP004 | 2025-11 | 2025-10-01 | 2078226.42 | 1577319 | -500907.42 | 500907.42 | 1 | 2025-11-28 | 6 | 2255064.43 | -176838.01 | DOWN | 0.0851 | 58 | Low | 714183.33 | 0.368 | 0 | 863135.67 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP004 | 2025-12 | 2025-07-03 | 3920723.66 | 2264990 | -1655733.66 | 1655733.66 | 1 | 2025-12-28 | 1 |  |  |  |  | 178 | Low | 371473.42 | 0.099 | 0 | 1893516.58 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP004 | 2025-12 | 2025-07-17 | 3509248.8 | 2264990 | -1244258.8 | 1244258.8 | 1 | 2025-12-28 | 2 | 3920723.66 | -411474.86 | DOWN | 0.1173 | 164 | Low | 455515.1 | 0.126 | 3 | 1809474.9 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP004 | 2025-12 | 2025-08-16 | 3196082.27 | 2264990 | -931092.27 | 931092.27 | 1 | 2025-12-28 | 3 | 3509248.8 | -313166.53 | DOWN | 0.098 | 134 | Low | 663855.9 | 0.193 | 0 | 1601134.1 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP004 | 2025-12 | 2025-08-27 | 2950565.23 | 2264990 | -685575.23 | 685575.23 | 1 | 2025-12-28 | 4 | 3196082.27 | -245517.04 | DOWN | 0.0832 | 123 | Low | 637940.6 | 0.218 | 4 | 1627049.4 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP004 | 2025-12 | 2025-11-12 | 2793452.14 | 2264990 | -528462.14 | 528462.14 | 1 | 2025-12-28 | 5 | 2950565.23 | -157113.09 | DOWN | 0.0562 | 46 | Low | 1119308.19 | 0.39 | 1 | 1145681.81 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP004 | 2025-12 | 2025-12-09 | 2647301.71 | 2264990 | -382311.71 | 382311.71 | 0 | 2025-12-28 | 6 | 2793452.14 | -146150.43 | DOWN | 0.0552 | 19 | Low | 1110148.84 | 0.451 | 5 | 1154841.16 | 9 | 1.11 | 0.94
P004 | Materials | SUP016 | 2025-01 | 2024-08-07 | 1639747.78 | 979693 | -660054.78 | 660054.78 | 1 | 2025-01-28 | 1 |  |  |  |  | 174 | Low | 196545.1 | 0.115 | 0 | 783147.9 | 9 | 1 | 1.26
P004 | Materials | SUP016 | 2025-01 | 2024-08-26 | 1377732.78 | 979693 | -398039.78 | 398039.78 | 1 | 2025-01-28 | 2 | 1639747.78 | -262015 | DOWN | 0.1902 | 155 | Low | 224804.63 | 0.162 | 2 | 754888.37 | 9 | 1 | 1.26
P004 | Materials | SUP016 | 2025-01 | 2024-11-07 | 1230608.77 | 979693 | -250915.77 | 250915.77 | 1 | 2025-01-28 | 3 | 1377732.78 | -147124.01 | DOWN | 0.1196 | 82 | Low | 391093.43 | 0.345 | 1 | 588599.57 | 9 | 1 | 1.26
P004 | Materials | SUP016 | 2025-02 | 2024-11-12 | 369461.59 | 267928 | -101533.59 | 101533.59 | 1 | 2025-02-28 | 1 |  |  |  |  | 108 | Low | 102404.09 | 0.272 | 5 | 165523.91 | 13 | 1.26 | 0.97
P004 | Materials | SUP016 | 2025-02 | 2025-01-24 | 328811.43 | 267928 | -60883.43 | 60883.43 | 1 | 2025-02-28 | 2 | 369461.59 | -40650.16 | DOWN | 0.1236 | 35 | Low | 146825.6 | 0.449 | 5 | 121102.4 | 13 | 1.26 | 0.97
P004 | Materials | SUP016 | 2025-02 | 2025-02-08 | 305141.45 | 267928 | -37213.45 | 37213.45 | 0 | 2025-02-28 | 3 | 328811.43 | -23669.98 | DOWN | 0.0776 | 20 | Medium | 145670.98 | 0.485 | 6 | 122257.02 | 13 | 1.26 | 0.97
P004 | Services | SUP016 | 2025-03 | 2024-10-25 | 378912.53 | 222097 | -156815.53 | 156815.53 | 1 | 2025-03-28 | 1 |  |  |  |  | 154 | Low | 58741.65 | 0.165 | 5 | 163355.35 | 11 | 0.73 | 1.3
P004 | Services | SUP016 | 2025-03 | 2024-11-20 | 313343.12 | 222097 | -91246.12 | 91246.12 | 1 | 2025-03-28 | 2 | 378912.53 | -65569.41 | DOWN | 0.2093 | 128 | Low | 71569.31 | 0.23 | 1 | 150527.69 | 11 | 0.73 | 1.3
P004 | Services | SUP016 | 2025-03 | 2025-01-29 | 273686.39 | 222097 | -51589.39 | 51589.39 | 1 | 2025-03-28 | 3 | 313343.12 | -39656.73 | DOWN | 0.1449 | 58 | Low | 108435.73 | 0.405 | 2 | 113661.27 | 11 | 0.73 | 1.3
P004 | Services | SUP016 | 2025-03 | 2025-02-03 | 250664.75 | 222097 | -28567.75 | 28567.75 | 0 | 2025-03-28 | 4 | 273686.39 | -23021.64 | DOWN | 0.0918 | 53 | Low | 100713.26 | 0.417 | 5 | 121383.74 | 11 | 0.73 | 1.3
P004 | Services | SUP016 | 2025-03 | 2025-02-06 | 241250.15 | 222097 | -19153.15 | 19153.15 | 0 | 2025-03-28 | 5 | 250664.75 | -9414.6 | DOWN | 0.039 | 50 | Low | 94809.37 | 0.425 | 4 | 127287.63 | 11 | 0.73 | 1.3
P004 | Materials | SUP016 | 2025-04 | 2024-12-04 | 353424.49 | 225896 | -127528.49 | 127528.49 | 1 | 2025-04-28 | 1 |  |  |  |  | 145 | Low | 65359.85 | 0.173 | 0 | 160536.15 | 15 | 1.69 | 1.47
P004 | Materials | SUP016 | 2025-04 | 2025-02-27 | 298183.56 | 225896 | -72287.56 | 72287.56 | 1 | 2025-04-28 | 2 | 353424.49 | -55240.93 | DOWN | 0.1853 | 60 | Low | 106256.04 | 0.369 | 3 | 119639.96 | 15 | 1.69 | 1.47
P004 | Materials | SUP016 | 2025-04 | 2025-03-04 | 272043.74 | 225896 | -46147.74 | 46147.74 | 1 | 2025-04-28 | 3 | 298183.56 | -26139.82 | DOWN | 0.0961 | 55 | Low | 104200.89 | 0.381 | 5 | 121695.11 | 15 | 1.69 | 1.47
P004 | Software | SUP016 | 2025-05 | 2025-03-15 | 2180284.05 | 1334940 | -845344.05 | 845344.05 | 1 | 2025-05-28 | 1 |  |  |  |  | 74 | Low | 785544.47 | 0.364 | 8 | 549395.53 | 12 | 1.03 | 1.42
P004 | Software | SUP016 | 2025-05 | 2025-03-27 | 1857275.65 | 1334940 | -522335.65 | 522335.65 | 1 | 2025-05-28 | 2 | 2180284.05 | -323008.4 | DOWN | 0.1739 | 62 | Low | 715434.52 | 0.394 | 5 | 619505.48 | 12 | 1.03 | 1.42
P004 | Software | SUP016 | 2025-05 | 2025-04-30 | 1676770.55 | 1334940 | -341830.55 | 341830.55 | 1 | 2025-05-28 | 3 | 1857275.65 | -180505.1 | DOWN | 0.1077 | 28 | Medium | 740496.75 | 0.478 | 2 | 594443.25 | 12 | 1.03 | 1.42
P004 | Electronics | SUP016 | 2025-06 | 2025-03-04 | 1351845.19 | 881355 | -470490.19 | 470490.19 | 1 | 2025-06-28 | 1 |  |  |  |  | 116 | Low | 350494.18 | 0.26 | 0 | 530860.82 | 15 | 0.81 | 1.56
P004 | Electronics | SUP016 | 2025-06 | 2025-04-10 | 1174001.49 | 881355 | -292646.49 | 292646.49 | 1 | 2025-06-28 | 2 | 1351845.19 | -177843.7 | DOWN | 0.1515 | 79 | Low | 445206.49 | 0.353 | 0 | 436148.51 | 15 | 0.81 | 1.56
P004 | Electronics | SUP016 | 2025-06 | 2025-04-26 | 1059357.56 | 881355 | -178002.56 | 178002.56 | 1 | 2025-06-28 | 3 | 1174001.49 | -114643.93 | DOWN | 0.1082 | 63 | Low | 445229.13 | 0.393 | 6 | 436125.87 | 15 | 0.81 | 1.56
P004 | Electronics | SUP016 | 2025-06 | 2025-05-17 | 993168.14 | 881355 | -111813.14 | 111813.14 | 0 | 2025-06-28 | 4 | 1059357.56 | -66189.42 | DOWN | 0.0666 | 42 | Low | 456240.59 | 0.445 | 5 | 425114.41 | 15 | 0.81 | 1.56
P004 | Services | SUP016 | 2025-07 | 2025-01-31 | 388521.59 | 235597 | -152924.59 | 152924.59 | 1 | 2025-07-28 | 1 |  |  |  |  | 178 | Low | 38305.84 | 0.101 | 1 | 197291.16 | 10 | 1.72 | 1
P004 | Services | SUP016 | 2025-07 | 2025-04-12 | 330331.57 | 235597 | -94734.57 | 94734.57 | 1 | 2025-07-28 | 2 | 388521.59 | -58190.02 | DOWN | 0.1762 | 107 | Low | 92093.09 | 0.26 | 2 | 143503.91 | 10 | 1.72 | 1
P004 | Services | SUP016 | 2025-07 | 2025-06-20 | 284975.36 | 235597 | -49378.36 | 49378.36 | 1 | 2025-07-28 | 3 | 330331.57 | -45356.21 | DOWN | 0.1592 | 38 | Low | 119372.89 | 0.419 | 1 | 116224.11 | 10 | 1.72 | 1
P004 | Software | SUP016 | 2025-08 | 2025-05-04 | 2146789.54 | 1255170 | -891619.54 | 891619.54 | 1 | 2025-08-28 | 1 |  |  |  |  | 116 | Low | 568956.61 | 0.247 | 3 | 686213.39 | 13 | 1.45 | 1.13
P004 | Software | SUP016 | 2025-08 | 2025-05-16 | 1776873.63 | 1255170 | -521703.63 | 521703.63 | 1 | 2025-08-28 | 2 | 2146789.54 | -369915.91 | DOWN | 0.2082 | 104 | Low | 477687.52 | 0.275 | 3 | 777482.48 | 13 | 1.45 | 1.13
P004 | Software | SUP016 | 2025-08 | 2025-06-23 | 1586404.33 | 1255170 | -331234.33 | 331234.33 | 1 | 2025-08-28 | 3 | 1776873.63 | -190469.3 | DOWN | 0.1201 | 66 | Low | 606939.99 | 0.365 | 4 | 648230.01 | 13 | 1.45 | 1.13
P004 | Electronics | SUP016 | 2025-09 | 2025-04-16 | 2588350.67 | 1551742 | -1036608.67 | 1036608.67 | 1 | 2025-09-28 | 1 |  |  |  |  | 165 | Low | 333969.12 | 0.133 | 2 | 1217772.88 | 12 | 1.31 | 1.3
P004 | Electronics | SUP016 | 2025-09 | 2025-04-25 | 2169957.05 | 1551742 | -618215.05 | 618215.05 | 1 | 2025-09-28 | 2 | 2588350.67 | -418393.62 | DOWN | 0.1928 | 156 | Low | 324938.07 | 0.154 | 6 | 1226803.93 | 12 | 1.31 | 1.3
P004 | Electronics | SUP016 | 2025-09 | 2025-05-07 | 1903824.05 | 1551742 | -352082.05 | 352082.05 | 1 | 2025-09-28 | 3 | 2169957.05 | -266133 | DOWN | 0.1398 | 144 | Low | 336646.79 | 0.183 | 4 | 1215095.21 | 12 | 1.31 | 1.3
P004 | Electronics | SUP016 | 2025-09 | 2025-07-16 | 1738266.56 | 1551742 | -186524.56 | 186524.56 | 0 | 2025-09-28 | 4 | 1903824.05 | -165557.49 | DOWN | 0.0952 | 74 | Low | 590767.89 | 0.352 | 5 | 960974.11 | 12 | 1.31 | 1.3
P004 | Electronics | SUP016 | 2025-09 | 2025-07-28 | 1653882.74 | 1551742 | -102140.74 | 102140.74 | 0 | 2025-09-28 | 5 | 1738266.56 | -84383.82 | DOWN | 0.051 | 62 | Low | 623841.53 | 0.381 | 2 | 927900.47 | 12 | 1.31 | 1.3
P004 | Electronics | SUP016 | 2025-09 | 2025-09-08 | 1615054.72 | 1551742 | -63312.72 | 63312.72 | 0 | 2025-09-28 | 6 | 1653882.74 | -38828.02 | DOWN | 0.024 | 20 | Medium | 739316.26 | 0.482 | 8 | 812425.74 | 12 | 1.31 | 1.3
P004 | Electronics | SUP016 | 2025-10 | 2025-05-29 | 386657.85 | 218371 | -168286.85 | 168286.85 | 1 | 2025-10-28 | 1 |  |  |  |  | 152 | Low | 65394.37 | 0.163 | 0 | 152976.63 | 16 | 1.37 | 1.4
P004 | Electronics | SUP016 | 2025-10 | 2025-08-05 | 324712.46 | 218371 | -106341.46 | 106341.46 | 1 | 2025-10-28 | 2 | 386657.85 | -61945.39 | DOWN | 0.1908 | 84 | Low | 107230.52 | 0.326 | 6 | 111140.48 | 16 | 1.37 | 1.4
P004 | Electronics | SUP016 | 2025-10 | 2025-08-15 | 287192.86 | 218371 | -68821.86 | 68821.86 | 1 | 2025-10-28 | 3 | 324712.46 | -37519.6 | DOWN | 0.1306 | 74 | Low | 100510.59 | 0.349 | 0 | 117860.41 | 16 | 1.37 | 1.4
P004 | Software | SUP016 | 2025-11 | 2025-06-05 | 491498.08 | 251477 | -240021.08 | 240021.08 | 1 | 2025-11-28 | 1 |  |  |  |  | 176 | Low | 51740.9 | 0.11 | 3 | 199736.1 | 7 | 0.59 | 1.31
P004 | Software | SUP016 | 2025-11 | 2025-06-22 | 398919.32 | 251477 | -147442.32 | 147442.32 | 1 | 2025-11-28 | 2 | 491498.08 | -92578.76 | DOWN | 0.2321 | 159 | Low | 62796.51 | 0.152 | 0 | 188680.49 | 7 | 0.59 | 1.31
P004 | Software | SUP016 | 2025-11 | 2025-08-24 | 344578.75 | 251477 | -93101.75 | 93101.75 | 1 | 2025-11-28 | 3 | 398919.32 | -54340.57 | DOWN | 0.1577 | 96 | Low | 102053.67 | 0.31 | 4 | 149423.33 | 7 | 0.59 | 1.31
P004 | Software | SUP016 | 2025-11 | 2025-10-22 | 303004.45 | 251477 | -51527.45 | 51527.45 | 1 | 2025-11-28 | 4 | 344578.75 | -41574.3 | DOWN | 0.1372 | 37 | Low | 143099.09 | 0.458 | 4 | 108377.91 | 7 | 0.59 | 1.31
P004 | Materials | SUP016 | 2025-12 | 2025-07-05 | 2478419.29 | 1772226 | -706193.29 | 706193.29 | 1 | 2025-12-28 | 1 |  |  |  |  | 176 | Low | 284176.67 | 0.109 | 3 | 1488049.33 | 9 | 1.11 | 0.94
P004 | Materials | SUP016 | 2025-12 | 2025-09-16 | 2178179.92 | 1772226 | -405953.92 | 405953.92 | 1 | 2025-12-28 | 2 | 2478419.29 | -300239.37 | DOWN | 0.1378 | 103 | Low | 580890.58 | 0.289 | 0 | 1191335.42 | 9 | 1.11 | 0.94
P004 | Materials | SUP016 | 2025-12 | 2025-11-11 | 1999917.47 | 1772226 | -227691.47 | 227691.47 | 0 | 2025-12-28 | 3 | 2178179.92 | -178262.45 | DOWN | 0.0891 | 47 | Low | 900975.98 | 0.427 | 3 | 871250.02 | 9 | 1.11 | 0.94
P004 | Materials | SUP016 | 2025-12 | 2025-12-13 | 1909932.53 | 1772226 | -137706.53 | 137706.53 | 0 | 2025-12-28 | 4 | 1999917.47 | -89984.94 | DOWN | 0.0471 | 15 | Medium | 924053.32 | 0.506 | 4 | 848172.68 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP012 | 2025-01 | 2024-08-08 | 1389260.59 | 1130670 | -258590.59 | 258590.59 | 1 | 2025-01-28 | 1 |  |  |  |  | 173 | Low | 216883.43 | 0.167 | 4 | 913786.57 | 9 | 1 | 1.26
P004 | Mechanical | SUP012 | 2025-01 | 2024-08-20 | 1240245.68 | 1130670 | -109575.68 | 109575.68 | 0 | 2025-01-28 | 2 | 1389260.59 | -149014.91 | DOWN | 0.1201 | 161 | Low | 245125.4 | 0.209 | 1 | 885544.6 | 9 | 1 | 1.26
P004 | Mechanical | SUP012 | 2025-01 | 2024-09-26 | 1186444.48 | 1130670 | -55774.48 | 55774.48 | 0 | 2025-01-28 | 3 | 1240245.68 | -53801.2 | DOWN | 0.0453 | 124 | Low | 433556.65 | 0.34 | 1 | 697113.35 | 9 | 1 | 1.26
P004 | Mechanical | SUP012 | 2025-01 | 2024-11-29 | 1157020.87 | 1130670 | -26350.87 | 26350.87 | 0 | 2025-01-28 | 4 | 1186444.48 | -29423.61 | DOWN | 0.0254 | 60 | Medium | 667511.43 | 0.567 | 8 | 463158.57 | 9 | 1 | 1.26
P004 | Software | SUP012 | 2025-02 | 2024-09-12 | 3881665.52 | 2367705 | -1513960.52 | 1513960.52 | 1 | 2025-02-28 | 1 |  |  |  |  | 169 | Low | 695319.18 | 0.175 | 0 | 1672385.82 | 13 | 1.26 | 0.97
P004 | Software | SUP012 | 2025-02 | 2024-09-23 | 2989846.79 | 2367705 | -622141.79 | 622141.79 | 1 | 2025-02-28 | 2 | 3881665.52 | -891818.73 | DOWN | 0.2983 | 158 | Low | 643648.17 | 0.213 | 3 | 1724056.83 | 13 | 1.26 | 0.97
P004 | Software | SUP012 | 2025-02 | 2024-12-25 | 2652506.41 | 2367705 | -284801.41 | 284801.41 | 0 | 2025-02-28 | 3 | 2989846.79 | -337340.38 | DOWN | 0.1272 | 65 | Low | 1405933.47 | 0.533 | 2 | 961771.53 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP012 | 2025-03 | 2024-09-30 | 2897206.63 | 2335271 | -561935.63 | 561935.63 | 1 | 2025-03-28 | 1 |  |  |  |  | 179 | Low | 485180.29 | 0.156 | 0 | 1850090.71 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP012 | 2025-03 | 2024-10-05 | 2572682.52 | 2335271 | -237411.52 | 237411.52 | 0 | 2025-03-28 | 2 | 2897206.63 | -324524.11 | DOWN | 0.1261 | 174 | Low | 416902.77 | 0.163 | 0 | 1918368.23 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP012 | 2025-03 | 2024-10-24 | 2447140.13 | 2335271 | -111869.13 | 111869.13 | 0 | 2025-03-28 | 3 | 2572682.52 | -125542.39 | DOWN | 0.0513 | 155 | Low | 548538.21 | 0.23 | 3 | 1786732.79 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP012 | 2025-03 | 2024-12-26 | 2386403.28 | 2335271 | -51132.28 | 51132.28 | 0 | 2025-03-28 | 4 | 2447140.13 | -60736.85 | DOWN | 0.0255 | 92 | Low | 1041074.81 | 0.454 | 5 | 1294196.19 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP012 | 2025-03 | 2024-12-29 | 2347984.21 | 2335271 | -12713.21 | 12713.21 | 0 | 2025-03-28 | 5 | 2386403.28 | -38419.07 | DOWN | 0.0164 | 89 | Low | 1031151.69 | 0.464 | 5 | 1304119.31 | 11 | 0.73 | 1.3
P004 | Mechanical | SUP012 | 2025-03 | 2025-01-29 | 2334680.74 | 2335271 | 590.26 | 590.26 | 0 | 2025-03-28 | 6 | 2347984.21 | -13303.47 | DOWN | 0.0057 | 58 | Medium | 1368438.76 | 0.574 | 5 | 966832.24 | 11 | 0.73 | 1.3
P004 | Electronics | SUP012 | 2025-04 | 2024-11-05 | 901194.83 | 672087 | -229107.83 | 229107.83 | 1 | 2025-04-28 | 1 |  |  |  |  | 174 | Low | 127611.16 | 0.151 | 3 | 544475.84 | 15 | 1.69 | 1.47
P004 | Electronics | SUP012 | 2025-04 | 2024-11-15 | 790917.98 | 672087 | -118830.98 | 118830.98 | 1 | 2025-04-28 | 2 | 901194.83 | -110276.85 | DOWN | 0.1394 | 164 | Low | 148369.26 | 0.183 | 0 | 523717.74 | 15 | 1.69 | 1.47
P004 | Electronics | SUP012 | 2025-04 | 2024-11-30 | 729171.4 | 672087 | -57084.4 | 57084.4 | 0 | 2025-04-28 | 3 | 790917.98 | -61746.58 | DOWN | 0.0847 | 149 | Low | 173022.13 | 0.232 | 1 | 499064.87 | 15 | 1.69 | 1.47
P004 | Electronics | SUP012 | 2025-04 | 2025-01-19 | 691471.95 | 672087 | -19384.95 | 19384.95 | 0 | 2025-04-28 | 4 | 729171.4 | -37699.45 | DOWN | 0.0545 | 99 | Low | 267867.24 | 0.396 | 3 | 404219.76 | 15 | 1.69 | 1.47
P004 | Electronics | SUP012 | 2025-04 | 2025-03-19 | 684816.3 | 672087 | -12729.3 | 12729.3 | 0 | 2025-04-28 | 5 | 691471.95 | -6655.65 | DOWN | 0.0097 | 40 | Medium | 411097.94 | 0.589 | 7 | 260989.06 | 15 | 1.69 | 1.47
P004 | Electronics | SUP012 | 2025-04 | 2025-04-10 | 666340.07 | 672087 | 5746.93 | 5746.93 | 0 | 2025-04-28 | 6 | 684816.3 | -18476.23 | DOWN | 0.0277 | 18 | Medium | 442690.38 | 0.661 | 2 | 229396.62 | 15 | 1.69 | 1.47
P004 | Software | SUP012 | 2025-05 | 2024-12-04 | 3766681.85 | 2164834 | -1601847.85 | 1601847.85 | 1 | 2025-05-28 | 1 |  |  |  |  | 175 | Low | 556931.12 | 0.159 | 3 | 1607902.88 | 12 | 1.03 | 1.42
P004 | Software | SUP012 | 2025-05 | 2025-01-08 | 2876049.32 | 2164834 | -711215.32 | 711215.32 | 1 | 2025-05-28 | 2 | 3766681.85 | -890632.53 | DOWN | 0.3097 | 140 | Low | 840309.49 | 0.283 | 1 | 1324524.51 | 12 | 1.03 | 1.42
P004 | Software | SUP012 | 2025-05 | 2025-01-23 | 2505881.34 | 2164834 | -341047.34 | 341047.34 | 0 | 2025-05-28 | 3 | 2876049.32 | -370167.98 | DOWN | 0.1477 | 125 | Low | 815994.7 | 0.336 | 3 | 1348839.3 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP012 | 2025-06 | 2025-02-07 | 2101641.51 | 1653549 | -448092.51 | 448092.51 | 1 | 2025-06-28 | 1 |  |  |  |  | 141 | Low | 619810.27 | 0.28 | 2 | 1033738.73 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP012 | 2025-06 | 2025-03-16 | 1843101.94 | 1653549 | -189552.94 | 189552.94 | 0 | 2025-06-28 | 2 | 2101641.51 | -258539.57 | DOWN | 0.1403 | 104 | Low | 717872.7 | 0.411 | 0 | 935676.3 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP012 | 2025-06 | 2025-03-26 | 1743558.6 | 1653549 | -90009.6 | 90009.6 | 0 | 2025-06-28 | 3 | 1843101.94 | -99543.34 | DOWN | 0.0571 | 94 | Low | 735303.32 | 0.447 | 3 | 918245.68 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP012 | 2025-06 | 2025-04-04 | 1694188.51 | 1653549 | -40639.51 | 40639.51 | 0 | 2025-06-28 | 4 | 1743558.6 | -49370.09 | DOWN | 0.0291 | 85 | Low | 754481.42 | 0.479 | 4 | 899067.58 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP012 | 2025-06 | 2025-04-21 | 1673722.07 | 1653549 | -20173.07 | 20173.07 | 0 | 2025-06-28 | 5 | 1694188.51 | -20466.44 | DOWN | 0.0122 | 68 | Low | 876226.86 | 0.539 | 0 | 777322.14 | 15 | 0.81 | 1.56
P004 | Materials | SUP012 | 2025-07 | 2025-02-15 | 1578291.01 | 1263235 | -315056.01 | 315056.01 | 1 | 2025-07-28 | 1 |  |  |  |  | 163 | Low | 299848.32 | 0.186 | 1 | 963386.68 | 10 | 1.72 | 1
P004 | Materials | SUP012 | 2025-07 | 2025-06-12 | 1399847.45 | 1263235 | -136612.45 | 136612.45 | 0 | 2025-07-28 | 2 | 1578291.01 | -178443.56 | DOWN | 0.1275 | 46 | Low | 819567.49 | 0.568 | 6 | 443667.51 | 10 | 1.72 | 1
P004 | Materials | SUP012 | 2025-07 | 2025-07-16 | 1321256.27 | 1263235 | -58021.27 | 58021.27 | 0 | 2025-07-28 | 3 | 1399847.45 | -78591.18 | DOWN | 0.0595 | 12 | Medium | 857401.37 | 0.679 | 5 | 405833.63 | 10 | 1.72 | 1
P004 | Electronics | SUP012 | 2025-08 | 2025-03-13 | 3309707.15 | 2385284 | -924423.15 | 924423.15 | 1 | 2025-08-28 | 1 |  |  |  |  | 168 | Low | 570904.33 | 0.175 | 0 | 1814379.67 | 13 | 1.45 | 1.13
P004 | Electronics | SUP012 | 2025-08 | 2025-03-27 | 2776255.87 | 2385284 | -390971.87 | 390971.87 | 0 | 2025-08-28 | 2 | 3309707.15 | -533451.28 | DOWN | 0.1921 | 154 | Low | 583072.14 | 0.222 | 0 | 1802211.86 | 13 | 1.45 | 1.13
P004 | Electronics | SUP012 | 2025-08 | 2025-06-22 | 2543178.42 | 2385284 | -157894.42 | 157894.42 | 0 | 2025-08-28 | 3 | 2776255.87 | -233077.45 | DOWN | 0.0916 | 67 | Low | 1245432.7 | 0.515 | 8 | 1139851.3 | 13 | 1.45 | 1.13
P004 | Electronics | SUP012 | 2025-08 | 2025-06-25 | 2442137.72 | 2385284 | -56853.72 | 56853.72 | 0 | 2025-08-28 | 4 | 2543178.42 | -101040.7 | DOWN | 0.0414 | 64 | Low | 1349589.51 | 0.525 | 3 | 1035694.49 | 13 | 1.45 | 1.13
P004 | Electronics | SUP012 | 2025-08 | 2025-07-20 | 2421247.7 | 2385284 | -35963.7 | 35963.7 | 0 | 2025-08-28 | 5 | 2442137.72 | -20890.02 | DOWN | 0.0086 | 39 | Medium | 1397685.37 | 0.609 | 4 | 987598.63 | 13 | 1.45 | 1.13
P004 | Electronics | SUP012 | 2025-08 | 2025-08-04 | 2406360.67 | 2385284 | -21076.67 | 21076.67 | 0 | 2025-08-28 | 6 | 2421247.7 | -14887.03 | DOWN | 0.0062 | 24 | Medium | 1614009.27 | 0.659 | 7 | 771274.73 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP012 | 2025-09 | 2025-05-14 | 2497741.65 | 1781128 | -716613.65 | 716613.65 | 1 | 2025-09-28 | 1 |  |  |  |  | 137 | Low | 757866.29 | 0.284 | 4 | 1023261.71 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP012 | 2025-09 | 2025-06-28 | 2112034.06 | 1781128 | -330906.06 | 330906.06 | 1 | 2025-09-28 | 2 | 2497741.65 | -385707.59 | DOWN | 0.1826 | 92 | Low | 908973.26 | 0.438 | 2 | 872154.74 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP012 | 2025-09 | 2025-07-29 | 1939300.56 | 1781128 | -158172.56 | 158172.56 | 0 | 2025-09-28 | 3 | 2112034.06 | -172733.5 | DOWN | 0.0891 | 61 | Low | 1119328.58 | 0.544 | 2 | 661799.42 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP012 | 2025-09 | 2025-08-07 | 1867474.34 | 1781128 | -86346.34 | 86346.34 | 0 | 2025-09-28 | 4 | 1939300.56 | -71826.22 | DOWN | 0.0385 | 52 | Medium | 1113237.68 | 0.574 | 7 | 667890.32 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP012 | 2025-09 | 2025-08-09 | 1803040.64 | 1781128 | -21912.64 | 21912.64 | 0 | 2025-09-28 | 5 | 1867474.34 | -64433.7 | DOWN | 0.0357 | 50 | Medium | 1062737.25 | 0.581 | 1 | 718390.75 | 12 | 1.31 | 1.3
P004 | Materials | SUP012 | 2025-10 | 2025-05-07 | 4416912.32 | 2777846 | -1639066.32 | 1639066.32 | 1 | 2025-10-28 | 1 |  |  |  |  | 174 | Low | 698742.28 | 0.156 | 1 | 2079103.72 | 16 | 1.37 | 1.4
P004 | Materials | SUP012 | 2025-10 | 2025-07-27 | 3536247.1 | 2777846 | -758401.1 | 758401.1 | 1 | 2025-10-28 | 2 | 4416912.32 | -880665.22 | DOWN | 0.249 | 93 | Low | 1604252.43 | 0.431 | 0 | 1173593.57 | 16 | 1.37 | 1.4
P004 | Materials | SUP012 | 2025-10 | 2025-08-25 | 3093827.74 | 2777846 | -315981.74 | 315981.74 | 0 | 2025-10-28 | 3 | 3536247.1 | -442419.36 | DOWN | 0.143 | 64 | Low | 1727265.99 | 0.53 | 4 | 1050580.01 | 16 | 1.37 | 1.4
P004 | Electronics | SUP012 | 2025-11 | 2025-07-15 | 2828479.55 | 1993466 | -835013.55 | 835013.55 | 1 | 2025-11-28 | 1 |  |  |  |  | 136 | Low | 831127.77 | 0.298 | 5 | 1162338.23 | 7 | 0.59 | 1.31
P004 | Electronics | SUP012 | 2025-11 | 2025-09-16 | 2381116.95 | 1993466 | -387650.95 | 387650.95 | 1 | 2025-11-28 | 2 | 2828479.55 | -447362.6 | DOWN | 0.1879 | 73 | Low | 1144700.19 | 0.521 | 4 | 848765.81 | 7 | 0.59 | 1.31
P004 | Electronics | SUP012 | 2025-11 | 2025-09-17 | 2141968.49 | 1993466 | -148502.49 | 148502.49 | 0 | 2025-11-28 | 3 | 2381116.95 | -239148.46 | DOWN | 0.1116 | 72 | Low | 1070737.84 | 0.525 | 4 | 922728.16 | 7 | 0.59 | 1.31
P004 | Electronics | SUP012 | 2025-11 | 2025-09-23 | 2079276.74 | 1993466 | -85810.74 | 85810.74 | 0 | 2025-11-28 | 4 | 2141968.49 | -62691.75 | DOWN | 0.0302 | 66 | Low | 1147481.79 | 0.546 | 1 | 845984.21 | 7 | 0.59 | 1.31
P004 | Electronics | SUP012 | 2025-11 | 2025-10-05 | 2007735.26 | 1993466 | -14269.26 | 14269.26 | 0 | 2025-11-28 | 5 | 2079276.74 | -71541.48 | DOWN | 0.0356 | 54 | Medium | 1106287.11 | 0.589 | 2 | 887178.89 | 7 | 0.59 | 1.31
P004 | Electronics | SUP012 | 2025-11 | 2025-10-29 | 1989679.99 | 1993466 | 3786.01 | 3786.01 | 0 | 2025-11-28 | 6 | 2007735.26 | -18055.27 | DOWN | 0.0091 | 30 | High | 1292030.22 | 0.674 | 1 | 701435.78 | 7 | 0.59 | 1.31
P004 | Logistics | SUP012 | 2025-12 | 2025-08-20 | 3589662.95 | 1944744 | -1644918.95 | 1644918.95 | 1 | 2025-12-28 | 1 |  |  |  |  | 130 | Low | 1191990.16 | 0.315 | 0 | 752753.84 | 9 | 1.11 | 0.94
P004 | Logistics | SUP012 | 2025-12 | 2025-09-06 | 2720039.03 | 1944744 | -775295.03 | 775295.03 | 1 | 2025-12-28 | 2 | 3589662.95 | -869623.92 | DOWN | 0.3197 | 113 | Low | 964026.86 | 0.374 | 5 | 980717.14 | 9 | 1.11 | 0.94
P004 | Logistics | SUP012 | 2025-12 | 2025-09-19 | 2234244.6 | 1944744 | -289500.6 | 289500.6 | 0 | 2025-12-28 | 3 | 2720039.03 | -485794.43 | DOWN | 0.2174 | 100 | Low | 999511.69 | 0.42 | 2 | 945232.31 | 9 | 1.11 | 0.94
P004 | Software | SUP047 | 2025-01 | 2024-09-16 | 1421881.87 | 917315 | -504566.87 | 504566.87 | 1 | 2025-01-28 | 1 |  |  |  |  | 134 | Low | 421782.06 | 0.305 | 1 | 495532.94 | 9 | 1 | 1.26
P004 | Software | SUP047 | 2025-01 | 2024-10-06 | 1162008.39 | 917315 | -244693.39 | 244693.39 | 1 | 2025-01-28 | 2 | 1421881.87 | -259873.48 | DOWN | 0.2236 | 114 | Low | 462208.24 | 0.376 | 4 | 455106.76 | 9 | 1 | 1.26
P004 | Software | SUP047 | 2025-01 | 2024-11-26 | 1031244.59 | 917315 | -113929.59 | 113929.59 | 0 | 2025-01-28 | 3 | 1162008.39 | -130763.8 | DOWN | 0.1268 | 63 | Low | 544117.43 | 0.557 | 2 | 373197.57 | 9 | 1 | 1.26
P004 | Mechanical | SUP047 | 2025-02 | 2024-09-10 | 3085804.06 | 2021451 | -1064353.06 | 1064353.06 | 1 | 2025-02-28 | 1 |  |  |  |  | 171 | Low | 523235.08 | 0.168 | 0 | 1498215.92 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP047 | 2025-02 | 2024-11-19 | 2516685.37 | 2021451 | -495234.37 | 495234.37 | 1 | 2025-02-28 | 2 | 3085804.06 | -569118.69 | DOWN | 0.2261 | 101 | Low | 1042264.09 | 0.409 | 2 | 979186.91 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP047 | 2025-02 | 2024-11-20 | 2239902.37 | 2021451 | -218451.37 | 218451.37 | 0 | 2025-02-28 | 3 | 2516685.37 | -276783 | DOWN | 0.1236 | 100 | Low | 987677.61 | 0.413 | 5 | 1033773.39 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP047 | 2025-02 | 2024-11-29 | 2114231.42 | 2021451 | -92780.42 | 92780.42 | 0 | 2025-02-28 | 4 | 2239902.37 | -125670.95 | DOWN | 0.0594 | 91 | Low | 889500.45 | 0.444 | 3 | 1131950.55 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP047 | 2025-02 | 2025-01-31 | 2065700.53 | 2021451 | -44249.53 | 44249.53 | 0 | 2025-02-28 | 5 | 2114231.42 | -48530.89 | DOWN | 0.0235 | 28 | High | 1350383.89 | 0.66 | 5 | 671067.11 | 13 | 1.26 | 0.97
P004 | Logistics | SUP047 | 2025-03 | 2024-11-09 | 3470495.9 | 2140415 | -1330080.9 | 1330080.9 | 1 | 2025-03-28 | 1 |  |  |  |  | 139 | Low | 993567.6 | 0.287 | 1 | 1146847.4 | 11 | 0.73 | 1.3
P004 | Logistics | SUP047 | 2025-03 | 2024-11-16 | 2777961.73 | 2140415 | -637546.73 | 637546.73 | 1 | 2025-03-28 | 2 | 3470495.9 | -692534.17 | DOWN | 0.2493 | 132 | Low | 906407.12 | 0.312 | 1 | 1234007.88 | 11 | 0.73 | 1.3
P004 | Logistics | SUP047 | 2025-03 | 2024-12-02 | 2377128.56 | 2140415 | -236713.56 | 236713.56 | 0 | 2025-03-28 | 3 | 2777961.73 | -400833.17 | DOWN | 0.1686 | 116 | Low | 941192.45 | 0.369 | 1 | 1199222.55 | 11 | 0.73 | 1.3
P004 | Logistics | SUP047 | 2025-03 | 2025-02-28 | 2261197.57 | 2140415 | -120782.57 | 120782.57 | 0 | 2025-03-28 | 4 | 2377128.56 | -115930.99 | DOWN | 0.0513 | 28 | High | 1647801.75 | 0.681 | 1 | 492613.25 | 11 | 0.73 | 1.3
P004 | Logistics | SUP047 | 2025-03 | 2025-03-08 | 2181338.15 | 2140415 | -40923.15 | 40923.15 | 0 | 2025-03-28 | 5 | 2261197.57 | -79859.42 | DOWN | 0.0366 | 20 | High | 1544400.44 | 0.709 | 4 | 596014.56 | 11 | 0.73 | 1.3
P004 | Software | SUP047 | 2025-04 | 2024-12-23 | 2133829.76 | 1308540 | -825289.76 | 825289.76 | 1 | 2025-04-28 | 1 |  |  |  |  | 126 | Low | 707523.52 | 0.308 | 0 | 601016.48 | 15 | 1.69 | 1.47
P004 | Software | SUP047 | 2025-04 | 2025-02-01 | 1711714.22 | 1308540 | -403174.22 | 403174.22 | 1 | 2025-04-28 | 2 | 2133829.76 | -422115.54 | DOWN | 0.2466 | 86 | Low | 719600.16 | 0.439 | 7 | 588939.84 | 15 | 1.69 | 1.47
P004 | Software | SUP047 | 2025-04 | 2025-03-29 | 1520420.6 | 1308540 | -211880.6 | 211880.6 | 0 | 2025-04-28 | 3 | 1711714.22 | -191293.62 | DOWN | 0.1258 | 30 | Low | 998463.26 | 0.622 | 3 | 310076.74 | 15 | 1.69 | 1.47
P004 | Software | SUP047 | 2025-04 | 2025-03-30 | 1378454.17 | 1308540 | -69914.17 | 69914.17 | 0 | 2025-04-28 | 4 | 1520420.6 | -141966.43 | DOWN | 0.103 | 29 | Medium | 901690.17 | 0.625 | 7 | 406849.83 | 15 | 1.69 | 1.47
P004 | Software | SUP047 | 2025-04 | 2025-04-04 | 1312730.83 | 1308540 | -4190.83 | 4190.83 | 0 | 2025-04-28 | 5 | 1378454.17 | -65723.34 | DOWN | 0.0501 | 24 | Medium | 813173.3 | 0.642 | 10 | 495366.7 | 15 | 1.69 | 1.47
P004 | Services | SUP047 | 2025-05 | 2025-01-08 | 3612536.52 | 2496408 | -1116128.52 | 1116128.52 | 1 | 2025-05-28 | 1 |  |  |  |  | 140 | Low | 1075055 | 0.283 | 2 | 1421353 | 12 | 1.03 | 1.42
P004 | Services | SUP047 | 2025-05 | 2025-01-30 | 2986795.63 | 2496408 | -490387.63 | 490387.63 | 1 | 2025-05-28 | 2 | 3612536.52 | -625740.89 | DOWN | 0.2095 | 118 | Low | 1043087.89 | 0.36 | 2 | 1453320.11 | 12 | 1.03 | 1.42
P004 | Services | SUP047 | 2025-05 | 2025-05-01 | 2679698.86 | 2496408 | -183290.86 | 183290.86 | 0 | 2025-05-28 | 3 | 2986795.63 | -307096.77 | DOWN | 0.1146 | 27 | Medium | 1813671.56 | 0.682 | 4 | 682736.44 | 12 | 1.03 | 1.42
P004 | Services | SUP047 | 2025-05 | 2025-05-15 | 2568117.68 | 2496408 | -71709.68 | 71709.68 | 0 | 2025-05-28 | 4 | 2679698.86 | -111581.18 | DOWN | 0.0434 | 13 | High | 1979933.59 | 0.731 | 9 | 516474.41 | 12 | 1.03 | 1.42
P004 | Services | SUP047 | 2025-06 | 2025-02-18 | 1781096.4 | 1172611 | -608485.4 | 608485.4 | 1 | 2025-06-28 | 1 |  |  |  |  | 130 | Low | 543953.35 | 0.319 | 3 | 628657.65 | 15 | 0.81 | 1.56
P004 | Services | SUP047 | 2025-06 | 2025-03-21 | 1424919.54 | 1172611 | -252308.54 | 252308.54 | 1 | 2025-06-28 | 2 | 1781096.4 | -356176.86 | DOWN | 0.25 | 99 | Low | 596103.68 | 0.429 | 3 | 576507.32 | 15 | 0.81 | 1.56
P004 | Services | SUP047 | 2025-06 | 2025-04-11 | 1267856.58 | 1172611 | -95245.58 | 95245.58 | 0 | 2025-06-28 | 3 | 1424919.54 | -157062.96 | DOWN | 0.1239 | 78 | Low | 635260.19 | 0.503 | 7 | 537350.81 | 15 | 0.81 | 1.56
P004 | Services | SUP047 | 2025-07 | 2025-02-21 | 2449631.54 | 1452400 | -997231.54 | 997231.54 | 1 | 2025-07-28 | 1 |  |  |  |  | 157 | Low | 511948.95 | 0.206 | 0 | 940451.05 | 10 | 1.72 | 1
P004 | Services | SUP047 | 2025-07 | 2025-03-04 | 1937035.62 | 1452400 | -484635.62 | 484635.62 | 1 | 2025-07-28 | 2 | 2449631.54 | -512595.92 | DOWN | 0.2646 | 146 | Low | 484396.88 | 0.241 | 1 | 968003.12 | 10 | 1.72 | 1
P004 | Services | SUP047 | 2025-07 | 2025-05-03 | 1678427.93 | 1452400 | -226027.93 | 226027.93 | 0 | 2025-07-28 | 3 | 1937035.62 | -258607.69 | DOWN | 0.1541 | 86 | Low | 743547.28 | 0.437 | 5 | 708852.72 | 10 | 1.72 | 1
P004 | Services | SUP047 | 2025-07 | 2025-05-06 | 1594114.99 | 1452400 | -141714.99 | 141714.99 | 0 | 2025-07-28 | 4 | 1678427.93 | -84312.94 | DOWN | 0.0529 | 83 | Low | 687546.9 | 0.447 | 5 | 764853.1 | 10 | 1.72 | 1
P004 | Services | SUP047 | 2025-07 | 2025-06-06 | 1488763.89 | 1452400 | -36363.89 | 36363.89 | 0 | 2025-07-28 | 5 | 1594114.99 | -105351.1 | DOWN | 0.0708 | 52 | Medium | 813141.79 | 0.548 | 5 | 639258.21 | 10 | 1.72 | 1
P004 | Services | SUP047 | 2025-07 | 2025-06-21 | 1469869.8 | 1452400 | -17469.8 | 17469.8 | 0 | 2025-07-28 | 6 | 1488763.89 | -18894.09 | DOWN | 0.0129 | 37 | Medium | 846756.85 | 0.597 | 3 | 605643.15 | 10 | 1.72 | 1
P004 | Materials | SUP047 | 2025-08 | 2025-03-07 | 2692314.27 | 2049487 | -642827.27 | 642827.27 | 1 | 2025-08-28 | 1 |  |  |  |  | 174 | Low | 422748.58 | 0.155 | 0 | 1626738.42 | 13 | 1.45 | 1.13
P004 | Materials | SUP047 | 2025-08 | 2025-04-29 | 2324123.52 | 2049487 | -274636.52 | 274636.52 | 0 | 2025-08-28 | 2 | 2692314.27 | -368190.75 | DOWN | 0.1584 | 121 | Low | 809755.02 | 0.333 | 3 | 1239731.98 | 13 | 1.45 | 1.13
P004 | Materials | SUP047 | 2025-08 | 2025-07-12 | 2156999.07 | 2049487 | -107512.07 | 107512.07 | 0 | 2025-08-28 | 3 | 2324123.52 | -167124.45 | DOWN | 0.0775 | 47 | Medium | 1281488.67 | 0.582 | 0 | 767998.33 | 13 | 1.45 | 1.13
P004 | Materials | SUP047 | 2025-08 | 2025-07-20 | 2079752.66 | 2049487 | -30265.66 | 30265.66 | 0 | 2025-08-28 | 4 | 2156999.07 | -77246.41 | DOWN | 0.0371 | 39 | Medium | 1302473.6 | 0.609 | 5 | 747013.4 | 13 | 1.45 | 1.13
P004 | Services | SUP047 | 2025-09 | 2025-05-10 | 742646.45 | 423451 | -319195.45 | 319195.45 | 1 | 2025-09-28 | 1 |  |  |  |  | 141 | Low | 195752.03 | 0.27 | 1 | 227698.97 | 12 | 1.31 | 1.3
P004 | Services | SUP047 | 2025-09 | 2025-07-10 | 565917.42 | 423451 | -142466.42 | 142466.42 | 1 | 2025-09-28 | 2 | 742646.45 | -176729.03 | DOWN | 0.3123 | 80 | Low | 252973.96 | 0.479 | 2 | 170477.04 | 12 | 1.31 | 1.3
P004 | Services | SUP047 | 2025-09 | 2025-09-02 | 482983.54 | 423451 | -59532.54 | 59532.54 | 0 | 2025-09-28 | 3 | 565917.42 | -82933.88 | DOWN | 0.1717 | 26 | Low | 314331.54 | 0.663 | 0 | 109119.46 | 12 | 1.31 | 1.3
P004 | Logistics | SUP047 | 2025-10 | 2025-05-22 | 353732.07 | 223415 | -130317.07 | 130317.07 | 1 | 2025-10-28 | 1 |  |  |  |  | 159 | Low | 72282.11 | 0.207 | 2 | 151132.89 | 16 | 1.37 | 1.4
P004 | Logistics | SUP047 | 2025-10 | 2025-07-29 | 285171.78 | 223415 | -61756.78 | 61756.78 | 1 | 2025-10-28 | 2 | 353732.07 | -68560.29 | DOWN | 0.2404 | 91 | Low | 134395.64 | 0.438 | 0 | 89019.36 | 16 | 1.37 | 1.4
P004 | Logistics | SUP047 | 2025-10 | 2025-09-04 | 251058.4 | 223415 | -27643.4 | 27643.4 | 0 | 2025-10-28 | 3 | 285171.78 | -34113.38 | DOWN | 0.1359 | 54 | Low | 144519.18 | 0.564 | 4 | 78895.82 | 16 | 1.37 | 1.4
P004 | Logistics | SUP047 | 2025-10 | 2025-09-30 | 240077.84 | 223415 | -16662.84 | 16662.84 | 0 | 2025-10-28 | 4 | 251058.4 | -10980.56 | DOWN | 0.0457 | 28 | High | 164930.74 | 0.652 | 5 | 58484.26 | 16 | 1.37 | 1.4
P004 | Logistics | SUP047 | 2025-11 | 2025-06-05 | 2461379.9 | 1462863 | -998516.9 | 998516.9 | 1 | 2025-11-28 | 1 |  |  |  |  | 176 | Low | 404825.38 | 0.156 | 2 | 1058037.62 | 7 | 0.59 | 1.31
P004 | Logistics | SUP047 | 2025-11 | 2025-09-10 | 1924898.95 | 1462863 | -462035.95 | 462035.95 | 1 | 2025-11-28 | 2 | 2461379.9 | -536480.95 | DOWN | 0.2787 | 79 | Low | 923158.19 | 0.5 | 0 | 539704.81 | 7 | 0.59 | 1.31
P004 | Logistics | SUP047 | 2025-11 | 2025-10-07 | 1638683.97 | 1462863 | -175820.97 | 175820.97 | 0 | 2025-11-28 | 3 | 1924898.95 | -286214.98 | DOWN | 0.1747 | 52 | Low | 1039779.75 | 0.596 | 5 | 423083.25 | 7 | 0.59 | 1.31
P004 | Logistics | SUP047 | 2025-11 | 2025-10-25 | 1529100.39 | 1462863 | -66237.39 | 66237.39 | 0 | 2025-11-28 | 4 | 1638683.97 | -109583.58 | DOWN | 0.0717 | 34 | Medium | 984606.34 | 0.659 | 2 | 478256.66 | 7 | 0.59 | 1.31
P004 | Materials | SUP047 | 2025-12 | 2025-07-10 | 1811611.29 | 1325339 | -486272.29 | 486272.29 | 1 | 2025-12-28 | 1 |  |  |  |  | 171 | Low | 299310.87 | 0.171 | 3 | 1026028.13 | 9 | 1.11 | 0.94
P004 | Materials | SUP047 | 2025-12 | 2025-09-07 | 1556740.67 | 1325339 | -231401.67 | 231401.67 | 0 | 2025-12-28 | 2 | 1811611.29 | -254870.62 | DOWN | 0.1637 | 112 | Low | 603653.51 | 0.378 | 3 | 721685.49 | 9 | 1.11 | 0.94
P004 | Materials | SUP047 | 2025-12 | 2025-09-19 | 1424039.21 | 1325339 | -98700.21 | 98700.21 | 0 | 2025-12-28 | 3 | 1556740.67 | -132701.46 | DOWN | 0.0932 | 100 | Low | 634932.65 | 0.42 | 1 | 690406.35 | 9 | 1.11 | 0.94
P004 | Materials | SUP047 | 2025-12 | 2025-10-12 | 1371804.38 | 1325339 | -46465.38 | 46465.38 | 0 | 2025-12-28 | 4 | 1424039.21 | -52234.83 | DOWN | 0.0381 | 77 | Low | 663177.78 | 0.5 | 2 | 662161.22 | 9 | 1.11 | 0.94
P004 | Software | SUP041 | 2025-01 | 2024-08-12 | 2702042.69 | 1432151 | -1269891.69 | 1269891.69 | 1 | 2025-01-28 | 1 |  |  |  |  | 169 | Low | 369868.37 | 0.128 | 0 | 1062282.63 | 9 | 1 | 1.26
P004 | Software | SUP041 | 2025-01 | 2024-12-20 | 2200657.27 | 1432151 | -768506.27 | 768506.27 | 1 | 2025-01-28 | 2 | 2702042.69 | -501385.42 | DOWN | 0.2278 | 39 | Low | 1054466.68 | 0.453 | 1 | 377684.32 | 9 | 1 | 1.26
P004 | Software | SUP041 | 2025-01 | 2024-12-20 | 1875007.79 | 1432151 | -442856.79 | 442856.79 | 1 | 2025-01-28 | 3 | 2200657.27 | -325649.48 | DOWN | 0.1737 | 39 | Low | 841114.03 | 0.453 | 3 | 591036.97 | 9 | 1 | 1.26
P004 | Electronics | SUP041 | 2025-02 | 2024-09-22 | 2971835.84 | 1667854 | -1303981.84 | 1303981.84 | 1 | 2025-02-28 | 1 |  |  |  |  | 159 | Low | 428210.93 | 0.148 | 2 | 1239643.07 | 13 | 1.26 | 0.97
P004 | Electronics | SUP041 | 2025-02 | 2024-11-05 | 2450748.94 | 1667854 | -782894.94 | 782894.94 | 1 | 2025-02-28 | 2 | 2971835.84 | -521086.9 | DOWN | 0.2126 | 115 | Low | 636082.07 | 0.255 | 0 | 1031771.93 | 13 | 1.26 | 0.97
P004 | Electronics | SUP041 | 2025-02 | 2024-11-12 | 2126491.64 | 1667854 | -458637.64 | 458637.64 | 1 | 2025-02-28 | 3 | 2450748.94 | -324257.3 | DOWN | 0.1525 | 108 | Low | 580839.41 | 0.272 | 2 | 1087014.59 | 13 | 1.26 | 0.97
P004 | Electronics | SUP041 | 2025-02 | 2025-02-16 | 1949143.53 | 1667854 | -281289.53 | 281289.53 | 0 | 2025-02-28 | 4 | 2126491.64 | -177348.11 | DOWN | 0.091 | 12 | Medium | 1051738.48 | 0.504 | 1 | 616115.52 | 13 | 1.26 | 0.97
P004 | Logistics | SUP041 | 2025-03 | 2024-11-09 | 3501594.79 | 1861884 | -1639710.79 | 1639710.79 | 1 | 2025-03-28 | 1 |  |  |  |  | 139 | Low | 660050.31 | 0.203 | 3 | 1201833.69 | 11 | 0.73 | 1.3
P004 | Logistics | SUP041 | 2025-03 | 2025-01-03 | 2897691.54 | 1861884 | -1035807.54 | 1035807.54 | 1 | 2025-03-28 | 2 | 3501594.79 | -603903.25 | DOWN | 0.2084 | 84 | Low | 1058936.14 | 0.34 | 3 | 802947.86 | 11 | 0.73 | 1.3
P004 | Logistics | SUP041 | 2025-03 | 2025-01-11 | 2427268.47 | 1861884 | -565384.47 | 565384.47 | 1 | 2025-03-28 | 3 | 2897691.54 | -470423.07 | DOWN | 0.1938 | 76 | Low | 809659.89 | 0.36 | 1 | 1052224.11 | 11 | 0.73 | 1.3
P004 | Logistics | SUP041 | 2025-03 | 2025-01-16 | 2222394.54 | 1861884 | -360510.54 | 360510.54 | 1 | 2025-03-28 | 4 | 2427268.47 | -204873.93 | DOWN | 0.0922 | 71 | Low | 840787.33 | 0.372 | 1 | 1021096.67 | 11 | 0.73 | 1.3
P004 | Logistics | SUP041 | 2025-04 | 2024-12-01 | 248708.32 | 127534 | -121174.32 | 121174.32 | 1 | 2025-04-28 | 1 |  |  |  |  | 148 | Low | 40433.82 | 0.166 | 0 | 87100.18 | 15 | 1.69 | 1.47
P004 | Logistics | SUP041 | 2025-04 | 2024-12-09 | 195157.63 | 127534 | -67623.63 | 67623.63 | 1 | 2025-04-28 | 2 | 248708.32 | -53550.69 | DOWN | 0.2744 | 140 | Low | 35964.74 | 0.185 | 3 | 91569.26 | 15 | 1.69 | 1.47
P004 | Logistics | SUP041 | 2025-04 | 2025-03-28 | 169162.39 | 127534 | -41628.39 | 41628.39 | 1 | 2025-04-28 | 3 | 195157.63 | -25995.24 | DOWN | 0.1537 | 31 | Low | 71905.84 | 0.436 | 1 | 55628.16 | 15 | 1.69 | 1.47
P004 | Materials | SUP041 | 2025-05 | 2025-01-08 | 1808942.09 | 1035278 | -773664.09 | 773664.09 | 1 | 2025-05-28 | 1 |  |  |  |  | 140 | Low | 357258.8 | 0.199 | 1 | 678019.2 | 12 | 1.03 | 1.42
P004 | Materials | SUP041 | 2025-05 | 2025-01-09 | 1504232.73 | 1035278 | -468954.73 | 468954.73 | 1 | 2025-05-28 | 2 | 1808942.09 | -304709.36 | DOWN | 0.2026 | 139 | Low | 280295.16 | 0.202 | 4 | 754982.84 | 12 | 1.03 | 1.42
P004 | Materials | SUP041 | 2025-05 | 2025-01-11 | 1307126.31 | 1035278 | -271848.31 | 271848.31 | 1 | 2025-05-28 | 3 | 1504232.73 | -197106.42 | DOWN | 0.1508 | 137 | Low | 255412.33 | 0.207 | 3 | 779865.67 | 12 | 1.03 | 1.42
P004 | Materials | SUP041 | 2025-05 | 2025-03-03 | 1208110.06 | 1035278 | -172832.06 | 172832.06 | 0 | 2025-05-28 | 4 | 1307126.31 | -99016.25 | DOWN | 0.082 | 86 | Low | 422694.71 | 0.334 | 3 | 612583.29 | 12 | 1.03 | 1.42
P004 | Materials | SUP041 | 2025-05 | 2025-04-12 | 1131692.07 | 1035278 | -96414.07 | 96414.07 | 0 | 2025-05-28 | 5 | 1208110.06 | -76417.99 | DOWN | 0.0675 | 46 | Low | 513163.82 | 0.433 | 6 | 522114.18 | 12 | 1.03 | 1.42
P004 | Materials | SUP041 | 2025-05 | 2025-05-04 | 1087380.43 | 1035278 | -52102.43 | 52102.43 | 0 | 2025-05-28 | 6 | 1131692.07 | -44311.64 | DOWN | 0.0408 | 24 | Medium | 516465.24 | 0.488 | 1 | 518812.76 | 12 | 1.03 | 1.42
P004 | Electronics | SUP041 | 2025-06 | 2025-01-15 | 1509827.29 | 903695 | -606132.29 | 606132.29 | 1 | 2025-06-28 | 1 |  |  |  |  | 164 | Low | 222098.2 | 0.14 | 2 | 681596.8 | 15 | 0.81 | 1.56
P004 | Electronics | SUP041 | 2025-06 | 2025-03-27 | 1250031.04 | 903695 | -346336.04 | 346336.04 | 1 | 2025-06-28 | 2 | 1509827.29 | -259796.25 | DOWN | 0.2078 | 93 | Low | 416081.46 | 0.318 | 5 | 487613.54 | 15 | 0.81 | 1.56
P004 | Electronics | SUP041 | 2025-06 | 2025-05-21 | 1102608.85 | 903695 | -198913.85 | 198913.85 | 1 | 2025-06-28 | 3 | 1250031.04 | -147422.19 | DOWN | 0.1337 | 38 | Low | 499954.41 | 0.455 | 5 | 403740.59 | 15 | 0.81 | 1.56
P004 | Logistics | SUP041 | 2025-07 | 2025-03-07 | 652084.9 | 352984 | -299100.9 | 299100.9 | 1 | 2025-07-28 | 1 |  |  |  |  | 143 | Low | 121408.63 | 0.177 | 0 | 231575.37 | 10 | 1.72 | 1
P004 | Logistics | SUP041 | 2025-07 | 2025-03-16 | 533247.77 | 352984 | -180263.77 | 180263.77 | 1 | 2025-07-28 | 2 | 652084.9 | -118837.13 | DOWN | 0.2229 | 134 | Low | 101984.46 | 0.198 | 3 | 250999.54 | 10 | 1.72 | 1
P004 | Logistics | SUP041 | 2025-07 | 2025-03-22 | 453291.54 | 352984 | -100307.54 | 100307.54 | 1 | 2025-07-28 | 3 | 533247.77 | -79956.23 | DOWN | 0.1764 | 128 | Low | 98039.77 | 0.212 | 2 | 254944.23 | 10 | 1.72 | 1
P004 | Logistics | SUP041 | 2025-07 | 2025-03-25 | 403912.17 | 352984 | -50928.17 | 50928.17 | 0 | 2025-07-28 | 4 | 453291.54 | -49379.37 | DOWN | 0.1223 | 125 | Low | 88058.61 | 0.219 | 0 | 264925.39 | 10 | 1.72 | 1
P004 | Logistics | SUP041 | 2025-07 | 2025-04-22 | 372800.88 | 352984 | -19816.88 | 19816.88 | 0 | 2025-07-28 | 5 | 403912.17 | -31111.29 | DOWN | 0.0835 | 97 | Low | 108507.41 | 0.283 | 5 | 244476.59 | 10 | 1.72 | 1
P004 | Logistics | SUP041 | 2025-07 | 2025-05-01 | 377627.29 | 352984 | -24643.29 | 24643.29 | 0 | 2025-07-28 | 6 | 372800.88 | 4826.41 | UP | 0.0128 | 88 | Low | 121702.46 | 0.304 | 0 | 231281.54 | 10 | 1.72 | 1
P004 | Materials | SUP041 | 2025-08 | 2025-03-30 | 2773816.86 | 1759229 | -1014587.86 | 1014587.86 | 1 | 2025-08-28 | 1 |  |  |  |  | 151 | Low | 447807.81 | 0.164 | 1 | 1311421.19 | 13 | 1.45 | 1.13
P004 | Materials | SUP041 | 2025-08 | 2025-05-11 | 2386091.68 | 1759229 | -626862.68 | 626862.68 | 1 | 2025-08-28 | 2 | 2773816.86 | -387725.18 | DOWN | 0.1625 | 109 | Low | 591659.14 | 0.263 | 2 | 1167569.86 | 13 | 1.45 | 1.13
P004 | Materials | SUP041 | 2025-08 | 2025-05-11 | 2142647.4 | 1759229 | -383418.4 | 383418.4 | 1 | 2025-08-28 | 3 | 2386091.68 | -243444.28 | DOWN | 0.1136 | 109 | Low | 555107.65 | 0.263 | 0 | 1204121.35 | 13 | 1.45 | 1.13
P004 | Materials | SUP041 | 2025-08 | 2025-06-15 | 2009358.54 | 1759229 | -250129.54 | 250129.54 | 0 | 2025-08-28 | 4 | 2142647.4 | -133288.86 | DOWN | 0.0663 | 74 | Low | 728608.51 | 0.346 | 0 | 1030620.49 | 13 | 1.45 | 1.13
P004 | Materials | SUP041 | 2025-08 | 2025-06-15 | 1884865.03 | 1759229 | -125636.03 | 125636.03 | 0 | 2025-08-28 | 5 | 2009358.54 | -124493.51 | DOWN | 0.066 | 74 | Low | 684968.02 | 0.346 | 2 | 1074260.98 | 13 | 1.45 | 1.13
P004 | Materials | SUP041 | 2025-09 | 2025-04-10 | 3305995.28 | 2307731 | -998264.28 | 998264.28 | 1 | 2025-09-28 | 1 |  |  |  |  | 171 | Low | 373969.17 | 0.118 | 1 | 1933761.83 | 12 | 1.31 | 1.3
P004 | Materials | SUP041 | 2025-09 | 2025-04-10 | 2898219.34 | 2307731 | -590488.34 | 590488.34 | 1 | 2025-09-28 | 2 | 3305995.28 | -407775.94 | DOWN | 0.1407 | 171 | Low | 355397.39 | 0.118 | 2 | 1952333.61 | 12 | 1.31 | 1.3
P004 | Materials | SUP041 | 2025-09 | 2025-05-01 | 2677655.64 | 2307731 | -369924.64 | 369924.64 | 0 | 2025-09-28 | 3 | 2898219.34 | -220563.7 | DOWN | 0.0824 | 150 | Low | 435153.8 | 0.169 | 0 | 1872577.2 | 12 | 1.31 | 1.3
P004 | Materials | SUP041 | 2025-09 | 2025-06-01 | 2516932.31 | 2307731 | -209201.31 | 209201.31 | 0 | 2025-09-28 | 4 | 2677655.64 | -160723.33 | DOWN | 0.0639 | 119 | Low | 656519.17 | 0.243 | 1 | 1651211.83 | 12 | 1.31 | 1.3
P004 | Materials | SUP041 | 2025-09 | 2025-09-18 | 2432382.12 | 2307731 | -124651.12 | 124651.12 | 0 | 2025-09-28 | 5 | 2516932.31 | -84550.19 | DOWN | 0.0348 | 10 | Medium | 1188618.29 | 0.504 | 2 | 1119112.71 | 12 | 1.31 | 1.3
P004 | Software | SUP041 | 2025-10 | 2025-06-17 | 277672.89 | 168826 | -108846.89 | 108846.89 | 1 | 2025-10-28 | 1 |  |  |  |  | 133 | Low | 59028.26 | 0.208 | 5 | 109797.74 | 16 | 1.37 | 1.4
P004 | Software | SUP041 | 2025-10 | 2025-07-08 | 237092.96 | 168826 | -68266.96 | 68266.96 | 1 | 2025-10-28 | 2 | 277672.89 | -40579.93 | DOWN | 0.1712 | 112 | Low | 61209.29 | 0.259 | 1 | 107616.71 | 16 | 1.37 | 1.4
P004 | Software | SUP041 | 2025-10 | 2025-08-14 | 208207.55 | 168826 | -39381.55 | 39381.55 | 1 | 2025-10-28 | 3 | 237092.96 | -28885.41 | DOWN | 0.1387 | 75 | Low | 73920.51 | 0.347 | 4 | 94905.49 | 16 | 1.37 | 1.4
P004 | Software | SUP041 | 2025-10 | 2025-08-20 | 190495.27 | 168826 | -21669.27 | 21669.27 | 0 | 2025-10-28 | 4 | 208207.55 | -17712.28 | DOWN | 0.093 | 69 | Low | 68397.7 | 0.361 | 1 | 100428.3 | 16 | 1.37 | 1.4
P004 | Software | SUP041 | 2025-10 | 2025-09-16 | 183885.37 | 168826 | -15059.37 | 15059.37 | 0 | 2025-10-28 | 5 | 190495.27 | -6609.9 | DOWN | 0.0359 | 42 | Low | 83395.01 | 0.426 | 6 | 85430.99 | 16 | 1.37 | 1.4
P004 | Software | SUP041 | 2025-10 | 2025-09-29 | 178333.84 | 168826 | -9507.84 | 9507.84 | 0 | 2025-10-28 | 6 | 183885.37 | -5551.53 | DOWN | 0.0311 | 29 | Medium | 80776.17 | 0.457 | 3 | 88049.83 | 16 | 1.37 | 1.4
P004 | Software | SUP041 | 2025-11 | 2025-08-02 | 2041749.68 | 1152621 | -889128.68 | 889128.68 | 1 | 2025-11-28 | 1 |  |  |  |  | 118 | Low | 479522.62 | 0.255 | 0 | 673098.38 | 7 | 0.59 | 1.31
P004 | Software | SUP041 | 2025-11 | 2025-09-19 | 1712582.12 | 1152621 | -559961.12 | 559961.12 | 1 | 2025-11-28 | 2 | 2041749.68 | -329167.56 | DOWN | 0.1922 | 70 | Low | 620966.31 | 0.375 | 1 | 531654.69 | 7 | 0.59 | 1.31
P004 | Software | SUP041 | 2025-11 | 2025-10-24 | 1488109.48 | 1152621 | -335488.48 | 335488.48 | 1 | 2025-11-28 | 3 | 1712582.12 | -224472.64 | DOWN | 0.1508 | 35 | Low | 704223.95 | 0.463 | 2 | 448397.05 | 7 | 0.59 | 1.31
P004 | Software | SUP041 | 2025-11 | 2025-11-16 | 1338185.21 | 1152621 | -185564.21 | 185564.21 | 0 | 2025-11-28 | 4 | 1488109.48 | -149924.27 | DOWN | 0.112 | 12 | Medium | 734925.6 | 0.52 | 1 | 417695.4 | 7 | 0.59 | 1.31
P004 | Mechanical | SUP041 | 2025-12 | 2025-07-21 | 2045777.94 | 1249037 | -796740.94 | 796740.94 | 1 | 2025-12-28 | 1 |  |  |  |  | 160 | Low | 326918.89 | 0.148 | 0 | 922118.11 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP041 | 2025-12 | 2025-08-16 | 1736892.76 | 1249037 | -487855.76 | 487855.76 | 1 | 2025-12-28 | 2 | 2045777.94 | -308885.18 | DOWN | 0.1778 | 134 | Low | 391100.74 | 0.212 | 2 | 857936.26 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP041 | 2025-12 | 2025-09-07 | 1549194.59 | 1249037 | -300157.59 | 300157.59 | 1 | 2025-12-28 | 3 | 1736892.76 | -187698.17 | DOWN | 0.1212 | 112 | Low | 423049.41 | 0.266 | 3 | 825987.59 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP041 | 2025-12 | 2025-10-30 | 1433590.56 | 1249037 | -184553.56 | 184553.56 | 0 | 2025-12-28 | 4 | 1549194.59 | -115604.03 | DOWN | 0.0806 | 59 | Low | 608646 | 0.397 | 4 | 640391 | 9 | 1.11 | 0.94
P004 | Mechanical | SUP041 | 2025-12 | 2025-12-16 | 1356205.48 | 1249037 | -107168.48 | 107168.48 | 0 | 2025-12-28 | 5 | 1433590.56 | -77385.08 | DOWN | 0.0571 | 12 | Medium | 739473.68 | 0.513 | 3 | 509563.32 | 9 | 1.11 | 0.94
P004 | Electronics | SUP043 | 2025-01 | 2024-08-16 | 921086.52 | 491796 | -429290.52 | 429290.52 | 1 | 2025-01-28 | 1 |  |  |  |  | 165 | Low | 150030.13 | 0.163 | 2 | 341765.87 | 9 | 1 | 1.26
P004 | Electronics | SUP043 | 2025-01 | 2024-09-14 | 724686.8 | 491796 | -232890.8 | 232890.8 | 1 | 2025-01-28 | 2 | 921086.52 | -196399.72 | DOWN | 0.271 | 136 | Low | 173015.19 | 0.248 | 2 | 318780.81 | 9 | 1 | 1.26
P004 | Electronics | SUP043 | 2025-01 | 2024-09-27 | 617825.27 | 491796 | -126029.27 | 126029.27 | 1 | 2025-01-28 | 3 | 724686.8 | -106861.53 | DOWN | 0.173 | 123 | Low | 169395.4 | 0.287 | 1 | 322400.6 | 9 | 1 | 1.26
P004 | Electronics | SUP043 | 2025-01 | 2024-10-28 | 564811.67 | 491796 | -73015.67 | 73015.67 | 0 | 2025-01-28 | 4 | 617825.27 | -53013.6 | DOWN | 0.0939 | 92 | Low | 207010.39 | 0.378 | 0 | 284785.61 | 9 | 1 | 1.26
P004 | Electronics | SUP043 | 2025-01 | 2024-11-18 | 525946.29 | 491796 | -34150.29 | 34150.29 | 0 | 2025-01-28 | 5 | 564811.67 | -38865.38 | DOWN | 0.0739 | 71 | Low | 235730.64 | 0.44 | 5 | 256065.36 | 9 | 1 | 1.26
P004 | Logistics | SUP043 | 2025-02 | 2024-11-03 | 3592296.05 | 1595484 | -1996812.05 | 1996812.05 | 1 | 2025-02-28 | 1 |  |  |  |  | 117 | Low | 1068818.02 | 0.295 | 0 | 526665.98 | 13 | 1.26 | 0.97
P004 | Logistics | SUP043 | 2025-02 | 2025-01-17 | 2707230.47 | 1595484 | -1111746.47 | 1111746.47 | 1 | 2025-02-28 | 2 | 3592296.05 | -885065.58 | DOWN | 0.3269 | 42 | Low | 1399063.76 | 0.51 | 3 | 196420.24 | 13 | 1.26 | 0.97
P004 | Logistics | SUP043 | 2025-02 | 2025-02-17 | 2228671.07 | 1595484 | -633187.07 | 633187.07 | 1 | 2025-02-28 | 3 | 2707230.47 | -478559.4 | DOWN | 0.2147 | 11 | Low | 1281857.31 | 0.599 | 4 | 313626.69 | 13 | 1.26 | 0.97
P004 | Materials | SUP043 | 2025-03 | 2024-10-25 | 3502887.72 | 2186183 | -1316704.72 | 1316704.72 | 1 | 2025-03-28 | 1 |  |  |  |  | 154 | Low | 697062.36 | 0.195 | 2 | 1489120.64 | 11 | 0.73 | 1.3
P004 | Materials | SUP043 | 2025-03 | 2024-10-29 | 2881378.94 | 2186183 | -695195.94 | 695195.94 | 1 | 2025-03-28 | 2 | 3502887.72 | -621508.78 | DOWN | 0.2157 | 150 | Low | 602844.16 | 0.207 | 1 | 1583338.84 | 11 | 0.73 | 1.3
P004 | Materials | SUP043 | 2025-03 | 2024-11-24 | 2582486.83 | 2186183 | -396303.83 | 396303.83 | 1 | 2025-03-28 | 3 | 2881378.94 | -298892.11 | DOWN | 0.1157 | 124 | Low | 709219.68 | 0.284 | 3 | 1476963.32 | 11 | 0.73 | 1.3
P004 | Materials | SUP043 | 2025-03 | 2025-03-02 | 2419874.97 | 2186183 | -233691.97 | 233691.97 | 0 | 2025-03-28 | 4 | 2582486.83 | -162611.86 | DOWN | 0.0672 | 26 | Medium | 1446702.7 | 0.573 | 7 | 739480.3 | 11 | 0.73 | 1.3
P004 | Materials | SUP043 | 2025-03 | 2025-03-12 | 2310786.94 | 2186183 | -124603.94 | 124603.94 | 0 | 2025-03-28 | 5 | 2419874.97 | -109088.03 | DOWN | 0.0472 | 16 | Medium | 1398904.75 | 0.603 | 6 | 787278.25 | 11 | 0.73 | 1.3
P004 | Logistics | SUP043 | 2025-04 | 2024-10-31 | 1673587.98 | 742622 | -930965.98 | 930965.98 | 1 | 2025-04-28 | 1 |  |  |  |  | 179 | Low | 209340.95 | 0.12 | 0 | 533281.05 | 15 | 1.69 | 1.47
P004 | Logistics | SUP043 | 2025-04 | 2024-12-10 | 1257582.28 | 742622 | -514960.28 | 514960.28 | 1 | 2025-04-28 | 2 | 1673587.98 | -416005.7 | DOWN | 0.3308 | 139 | Low | 299851.7 | 0.221 | 1 | 442770.3 | 15 | 1.69 | 1.47
P004 | Logistics | SUP043 | 2025-04 | 2025-01-24 | 1018191.9 | 742622 | -275569.9 | 275569.9 | 1 | 2025-04-28 | 3 | 1257582.28 | -239390.38 | DOWN | 0.2351 | 94 | Low | 334522.87 | 0.344 | 0 | 408099.13 | 15 | 1.69 | 1.47
P004 | Logistics | SUP043 | 2025-04 | 2025-02-28 | 908777.55 | 742622 | -166155.55 | 166155.55 | 1 | 2025-04-28 | 4 | 1018191.9 | -109414.35 | DOWN | 0.1204 | 59 | Low | 429298.92 | 0.439 | 3 | 313323.08 | 15 | 1.69 | 1.47
P004 | Logistics | SUP043 | 2025-04 | 2025-03-29 | 819661.25 | 742622 | -77039.25 | 77039.25 | 0 | 2025-04-28 | 5 | 908777.55 | -89116.3 | DOWN | 0.1087 | 30 | Medium | 401101.64 | 0.518 | 2 | 341520.36 | 15 | 1.69 | 1.47
P004 | Logistics | SUP043 | 2025-04 | 2025-04-08 | 793291.67 | 742622 | -50669.67 | 50669.67 | 0 | 2025-04-28 | 6 | 819661.25 | -26369.58 | DOWN | 0.0332 | 20 | Medium | 411745.94 | 0.546 | 4 | 330876.06 | 15 | 1.69 | 1.47
P004 | Logistics | SUP043 | 2025-05 | 2025-01-14 | 3300727.7 | 1645902 | -1654825.7 | 1654825.7 | 1 | 2025-05-28 | 1 |  |  |  |  | 134 | Low | 809069.84 | 0.253 | 4 | 836832.16 | 12 | 1.03 | 1.42
P004 | Logistics | SUP043 | 2025-05 | 2025-02-16 | 2558281.73 | 1645902 | -912379.73 | 912379.73 | 1 | 2025-05-28 | 2 | 3300727.7 | -742445.97 | DOWN | 0.2902 | 101 | Low | 913778.76 | 0.35 | 4 | 732123.24 | 12 | 1.03 | 1.42
P004 | Logistics | SUP043 | 2025-05 | 2025-02-27 | 2171869.66 | 1645902 | -525967.66 | 525967.66 | 1 | 2025-05-28 | 3 | 2558281.73 | -386412.07 | DOWN | 0.1779 | 90 | Low | 823833.56 | 0.383 | 2 | 822068.44 | 12 | 1.03 | 1.42
P004 | Logistics | SUP043 | 2025-05 | 2025-03-07 | 1925540.75 | 1645902 | -279638.75 | 279638.75 | 0 | 2025-05-28 | 4 | 2171869.66 | -246328.91 | DOWN | 0.1279 | 82 | Low | 722696.04 | 0.406 | 3 | 923205.96 | 12 | 1.03 | 1.42
P004 | Logistics | SUP043 | 2025-05 | 2025-03-27 | 1828223.4 | 1645902 | -182321.4 | 182321.4 | 0 | 2025-05-28 | 5 | 1925540.75 | -97317.35 | DOWN | 0.0532 | 62 | Low | 782891.26 | 0.465 | 0 | 863010.74 | 12 | 1.03 | 1.42
P004 | Electronics | SUP043 | 2025-06 | 2025-03-14 | 3448544.75 | 2317191 | -1131353.75 | 1131353.75 | 1 | 2025-06-28 | 1 |  |  |  |  | 106 | Low | 1116277.5 | 0.337 | 2 | 1200913.5 | 15 | 0.81 | 1.56
P004 | Electronics | SUP043 | 2025-06 | 2025-04-21 | 2971170.35 | 2317191 | -653979.35 | 653979.35 | 1 | 2025-06-28 | 2 | 3448544.75 | -477374.4 | DOWN | 0.1607 | 68 | Low | 1386967.66 | 0.449 | 3 | 930223.34 | 15 | 0.81 | 1.56
P004 | Electronics | SUP043 | 2025-06 | 2025-05-04 | 2656826.79 | 2317191 | -339635.79 | 339635.79 | 0 | 2025-06-28 | 3 | 2971170.35 | -314343.56 | DOWN | 0.1183 | 55 | Medium | 1244142.55 | 0.488 | 2 | 1073048.45 | 15 | 0.81 | 1.56
P004 | Software | SUP043 | 2025-07 | 2025-03-28 | 1478151.23 | 723402 | -754749.23 | 754749.23 | 1 | 2025-07-28 | 1 |  |  |  |  | 122 | Low | 375691.07 | 0.267 | 1 | 347710.93 | 10 | 1.72 | 1
P004 | Software | SUP043 | 2025-07 | 2025-04-26 | 1141963.52 | 723402 | -418561.52 | 418561.52 | 1 | 2025-07-28 | 2 | 1478151.23 | -336187.71 | DOWN | 0.2944 | 93 | Low | 406661.89 | 0.345 | 2 | 316740.11 | 10 | 1.72 | 1
P004 | Software | SUP043 | 2025-07 | 2025-05-04 | 931998.34 | 723402 | -208596.34 | 208596.34 | 1 | 2025-07-28 | 3 | 1141963.52 | -209965.18 | DOWN | 0.2253 | 85 | Low | 328852.63 | 0.367 | 2 | 394549.37 | 10 | 1.72 | 1
P004 | Mechanical | SUP043 | 2025-08 | 2025-05-01 | 1508877.62 | 1061923 | -446954.62 | 446954.62 | 1 | 2025-08-28 | 1 |  |  |  |  | 119 | Low | 425191.05 | 0.283 | 1 | 636731.95 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP043 | 2025-08 | 2025-06-12 | 1294642.41 | 1061923 | -232719.41 | 232719.41 | 1 | 2025-08-28 | 2 | 1508877.62 | -214235.21 | DOWN | 0.1655 | 77 | Low | 486475.04 | 0.401 | 4 | 575447.96 | 13 | 1.45 | 1.13
P004 | Mechanical | SUP043 | 2025-08 | 2025-07-09 | 1190090.88 | 1061923 | -128167.88 | 128167.88 | 0 | 2025-08-28 | 3 | 1294642.41 | -104551.53 | DOWN | 0.0879 | 50 | Medium | 528657.21 | 0.477 | 3 | 533265.79 | 13 | 1.45 | 1.13
P004 | Electronics | SUP043 | 2025-09 | 2025-04-22 | 2237347.01 | 1242175 | -995172.01 | 995172.01 | 1 | 2025-09-28 | 1 |  |  |  |  | 159 | Low | 408641.98 | 0.174 | 0 | 833533.02 | 12 | 1.31 | 1.3
P004 | Electronics | SUP043 | 2025-09 | 2025-04-26 | 1796010.02 | 1242175 | -553835.02 | 553835.02 | 1 | 2025-09-28 | 2 | 2237347.01 | -441336.99 | DOWN | 0.2457 | 155 | Low | 331080.22 | 0.185 | 3 | 911094.78 | 12 | 1.31 | 1.3
P004 | Electronics | SUP043 | 2025-09 | 2025-05-24 | 1544635.1 | 1242175 | -302460.1 | 302460.1 | 1 | 2025-09-28 | 3 | 1796010.02 | -251374.92 | DOWN | 0.1627 | 127 | Low | 384676.19 | 0.265 | 0 | 857498.81 | 12 | 1.31 | 1.3
P004 | Mechanical | SUP043 | 2025-10 | 2025-05-25 | 280883.79 | 145351 | -135532.79 | 135532.79 | 1 | 2025-10-28 | 1 |  |  |  |  | 156 | Low | 49272.11 | 0.181 | 2 | 96078.89 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP043 | 2025-10 | 2025-06-21 | 217041.12 | 145351 | -71690.12 | 71690.12 | 1 | 2025-10-28 | 2 | 280883.79 | -63842.67 | DOWN | 0.2942 | 129 | Low | 58742.36 | 0.257 | 2 | 86608.64 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP043 | 2025-10 | 2025-07-28 | 184309.81 | 145351 | -38958.81 | 38958.81 | 1 | 2025-10-28 | 3 | 217041.12 | -32731.31 | DOWN | 0.1776 | 92 | Low | 70056.48 | 0.362 | 0 | 75294.52 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP043 | 2025-10 | 2025-08-13 | 167583.31 | 145351 | -22232.31 | 22232.31 | 0 | 2025-10-28 | 4 | 184309.81 | -16726.5 | DOWN | 0.0998 | 76 | Low | 71357.63 | 0.407 | 0 | 73993.37 | 16 | 1.37 | 1.4
P004 | Mechanical | SUP043 | 2025-10 | 2025-08-24 | 157091.14 | 145351 | -11740.14 | 11740.14 | 0 | 2025-10-28 | 5 | 167583.31 | -10492.17 | DOWN | 0.0668 | 65 | Low | 65109.48 | 0.438 | 6 | 80241.52 | 16 | 1.37 | 1.4
P004 | Logistics | SUP043 | 2025-11 | 2025-07-11 | 2594261.07 | 1285004 | -1309257.07 | 1309257.07 | 1 | 2025-11-28 | 1 |  |  |  |  | 140 | Low | 635226.76 | 0.236 | 0 | 649777.24 | 7 | 0.59 | 1.31
P004 | Logistics | SUP043 | 2025-11 | 2025-08-23 | 2042294.03 | 1285004 | -757290.03 | 757290.03 | 1 | 2025-11-28 | 2 | 2594261.07 | -551967.04 | DOWN | 0.2703 | 97 | Low | 765427.02 | 0.363 | 2 | 519576.98 | 7 | 0.59 | 1.31
P004 | Logistics | SUP043 | 2025-11 | 2025-09-27 | 1726105.25 | 1285004 | -441101.25 | 441101.25 | 1 | 2025-11-28 | 3 | 2042294.03 | -316188.78 | DOWN | 0.1832 | 62 | Low | 751266.14 | 0.467 | 0 | 533737.86 | 7 | 0.59 | 1.31
P004 | Software | SUP043 | 2025-12 | 2025-09-24 | 1239546.89 | 627837 | -611709.89 | 611709.89 | 1 | 2025-12-28 | 1 |  |  |  |  | 95 | Low | 466181.64 | 0.365 | 1 | 161655.36 | 9 | 1.11 | 0.94
P004 | Software | SUP043 | 2025-12 | 2025-09-25 | 961754.78 | 627837 | -333917.78 | 333917.78 | 1 | 2025-12-28 | 2 | 1239546.89 | -277792.11 | DOWN | 0.2888 | 94 | Low | 339819.41 | 0.367 | 3 | 288017.59 | 9 | 1.11 | 0.94
P004 | Software | SUP043 | 2025-12 | 2025-10-20 | 825738.16 | 627837 | -197901.16 | 197901.16 | 1 | 2025-12-28 | 3 | 961754.78 | -136016.62 | DOWN | 0.1647 | 69 | Low | 352364.81 | 0.44 | 4 | 275472.19 | 9 | 1.11 | 0.94
P004 | Software | SUP043 | 2025-12 | 2025-11-20 | 734802.62 | 627837 | -106965.62 | 106965.62 | 0 | 2025-12-28 | 4 | 825738.16 | -90935.54 | DOWN | 0.1238 | 38 | Low | 403192.41 | 0.531 | 4 | 224644.59 | 9 | 1.11 | 0.94
P004 | Logistics | SUP048 | 2025-01 | 2024-08-27 | 5255439.83 | 2095386 | -3160053.83 | 3160053.83 | 1 | 2025-01-28 | 1 |  |  |  |  | 154 | Low | 731460.27 | 0.15 | 0 | 1363925.73 | 9 | 1 | 1.26
P004 | Logistics | SUP048 | 2025-01 | 2024-10-26 | 4475413.71 | 2095386 | -2380027.71 | 2380027.71 | 1 | 2025-01-28 | 2 | 5255439.83 | -780026.12 | DOWN | 0.1743 | 94 | Low | 1367190.86 | 0.286 | 3 | 728195.14 | 9 | 1 | 1.26
P004 | Logistics | SUP048 | 2025-01 | 2024-11-08 | 3889731.7 | 2095386 | -1794345.7 | 1794345.7 | 1 | 2025-01-28 | 3 | 4475413.71 | -585682.01 | DOWN | 0.1506 | 81 | Low | 1274809.84 | 0.316 | 4 | 820576.16 | 9 | 1 | 1.26
P004 | Logistics | SUP048 | 2025-01 | 2024-12-02 | 3419520.88 | 2095386 | -1324134.88 | 1324134.88 | 1 | 2025-01-28 | 4 | 3889731.7 | -470210.82 | DOWN | 0.1375 | 57 | Low | 1265414.04 | 0.37 | 3 | 829971.96 | 9 | 1 | 1.26
P004 | Mechanical | SUP048 | 2025-02 | 2024-09-29 | 1082787.23 | 651379 | -431408.23 | 431408.23 | 1 | 2025-02-28 | 1 |  |  |  |  | 152 | Low | 152310.53 | 0.15 | 3 | 499068.47 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP048 | 2025-02 | 2024-10-23 | 972637.24 | 651379 | -321258.24 | 321258.24 | 1 | 2025-02-28 | 2 | 1082787.23 | -110149.99 | DOWN | 0.1132 | 128 | Low | 198808.65 | 0.203 | 2 | 452570.35 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP048 | 2025-02 | 2024-12-13 | 894383.29 | 651379 | -243004.29 | 243004.29 | 1 | 2025-02-28 | 3 | 972637.24 | -78253.95 | DOWN | 0.0875 | 77 | Low | 262828.22 | 0.315 | 4 | 388550.78 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP048 | 2025-02 | 2024-12-24 | 833469.4 | 651379 | -182090.4 | 182090.4 | 1 | 2025-02-28 | 4 | 894383.29 | -60913.89 | DOWN | 0.0731 | 66 | Low | 304054.08 | 0.339 | 1 | 347324.92 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP048 | 2025-02 | 2024-12-26 | 791863.52 | 651379 | -140484.52 | 140484.52 | 1 | 2025-02-28 | 5 | 833469.4 | -41605.88 | DOWN | 0.0525 | 64 | Low | 276054.87 | 0.344 | 4 | 375324.13 | 13 | 1.26 | 0.97
P004 | Mechanical | SUP048 | 2025-02 | 2024-12-29 | 753129.47 | 651379 | -101750.47 | 101750.47 | 0 | 2025-02-28 | 6 | 791863.52 | -38734.05 | DOWN | 0.0514 | 61 | Low | 266591.47 | 0.35 | 3 | 384787.53 | 13 | 1.26 | 0.97
P004 | Logistics | SUP048 | 2025-03 | 2024-11-01 | 1233708.83 | 655450 | -578258.83 | 578258.83 | 1 | 2025-03-28 | 1 |  |  |  |  | 147 | Low | 194239.58 | 0.166 | 0 | 461210.42 | 11 | 0.73 | 1.3
P004 | Logistics | SUP048 | 2025-03 | 2024-11-09 | 1093508.11 | 655450 | -438058.11 | 438058.11 | 1 | 2025-03-28 | 2 | 1233708.83 | -140200.72 | DOWN | 0.1282 | 139 | Low | 208695.03 | 0.184 | 2 | 446754.97 | 11 | 0.73 | 1.3
P004 | Logistics | SUP048 | 2025-03 | 2024-11-24 | 1003941.11 | 655450 | -348491.11 | 348491.11 | 1 | 2025-03-28 | 3 | 1093508.11 | -89567 | DOWN | 0.0892 | 124 | Low | 235176.39 | 0.218 | 1 | 420273.61 | 11 | 0.73 | 1.3
P004 | Logistics | SUP048 | 2025-03 | 2025-01-11 | 935349.61 | 655450 | -279899.61 | 279899.61 | 1 | 2025-03-28 | 4 | 1003941.11 | -68591.5 | DOWN | 0.0733 | 76 | Low | 295435.91 | 0.327 | 0 | 360014.09 | 11 | 0.73 | 1.3
P004 | Logistics | SUP048 | 2025-03 | 2025-01-24 | 884262.29 | 655450 | -228812.29 | 228812.29 | 1 | 2025-03-28 | 5 | 935349.61 | -51087.32 | DOWN | 0.0578 | 63 | Low | 304806 | 0.357 | 4 | 350644 | 11 | 0.73 | 1.3
P004 | Logistics | SUP048 | 2025-03 | 2025-03-08 | 828154.52 | 655450 | -172704.52 | 172704.52 | 1 | 2025-03-28 | 6 | 884262.29 | -56107.77 | DOWN | 0.0678 | 20 | Medium | 390757.36 | 0.455 | 3 | 264692.64 | 11 | 0.73 | 1.3
P004 | Materials | SUP048 | 2025-04 | 2024-11-24 | 3525761.65 | 2362157 | -1163604.65 | 1163604.65 | 1 | 2025-04-28 | 1 |  |  |  |  | 155 | Low | 481548.11 | 0.136 | 0 | 1880608.89 | 15 | 1.69 | 1.47
P004 | Materials | SUP048 | 2025-04 | 2024-11-29 | 3236167.01 | 2362157 | -874010.01 | 874010.01 | 1 | 2025-04-28 | 2 | 3525761.65 | -289594.64 | DOWN | 0.0895 | 150 | Low | 464530.85 | 0.147 | 1 | 1897626.15 | 15 | 1.69 | 1.47
P004 | Materials | SUP048 | 2025-04 | 2025-01-16 | 3050964.12 | 2362157 | -688807.12 | 688807.12 | 1 | 2025-04-28 | 3 | 3236167.01 | -185202.89 | DOWN | 0.0607 | 102 | Low | 732589.92 | 0.248 | 3 | 1629567.08 | 15 | 1.69 | 1.47
P004 | Materials | SUP048 | 2025-04 | 2025-02-28 | 2818513.34 | 2362157 | -456356.34 | 456356.34 | 1 | 2025-04-28 | 4 | 3050964.12 | -232450.78 | DOWN | 0.0825 | 59 | Low | 994701.43 | 0.338 | 6 | 1367455.57 | 15 | 1.69 | 1.47
P004 | Software | SUP048 | 2025-05 | 2024-12-03 | 652728.36 | 370143 | -282585.36 | 282585.36 | 1 | 2025-05-28 | 1 |  |  |  |  | 176 | Low | 67673.88 | 0.1 | 0 | 302469.12 | 12 | 1.03 | 1.42
P004 | Software | SUP048 | 2025-05 | 2024-12-30 | 570917.16 | 370143 | -200774.16 | 200774.16 | 1 | 2025-05-28 | 2 | 652728.36 | -81811.2 | DOWN | 0.1433 | 149 | Low | 86707.52 | 0.161 | 2 | 283435.48 | 12 | 1.03 | 1.42
P004 | Software | SUP048 | 2025-05 | 2025-01-15 | 525961.99 | 370143 | -155818.99 | 155818.99 | 1 | 2025-05-28 | 3 | 570917.16 | -44955.17 | DOWN | 0.0855 | 133 | Low | 109186.39 | 0.197 | 2 | 260956.61 | 12 | 1.03 | 1.42
P004 | Software | SUP048 | 2025-05 | 2025-03-01 | 479821.55 | 370143 | -109678.55 | 109678.55 | 1 | 2025-05-28 | 4 | 525961.99 | -46140.44 | DOWN | 0.0962 | 88 | Low | 146491.62 | 0.299 | 3 | 223651.38 | 12 | 1.03 | 1.42
P004 | Software | SUP048 | 2025-05 | 2025-04-06 | 448530.48 | 370143 | -78387.48 | 78387.48 | 1 | 2025-05-28 | 5 | 479821.55 | -31291.07 | DOWN | 0.0698 | 52 | Low | 183917 | 0.38 | 2 | 186226 | 12 | 1.03 | 1.42
P004 | Software | SUP048 | 2025-05 | 2025-05-14 | 424577.51 | 370143 | -54434.51 | 54434.51 | 0 | 2025-05-28 | 6 | 448530.48 | -23952.97 | DOWN | 0.0564 | 14 | Medium | 187634.34 | 0.467 | 3 | 182508.66 | 12 | 1.03 | 1.42
P004 | Mechanical | SUP048 | 2025-06 | 2025-01-30 | 2784086.79 | 1746761 | -1037325.79 | 1037325.79 | 1 | 2025-06-28 | 1 |  |  |  |  | 149 | Low | 473989.83 | 0.161 | 2 | 1272771.17 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP048 | 2025-06 | 2025-02-12 | 2531193.6 | 1746761 | -784432.6 | 784432.6 | 1 | 2025-06-28 | 2 | 2784086.79 | -252893.19 | DOWN | 0.0999 | 136 | Low | 465797.71 | 0.191 | 1 | 1280963.29 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP048 | 2025-06 | 2025-04-28 | 2324153.7 | 1746761 | -577392.7 | 577392.7 | 1 | 2025-06-28 | 3 | 2531193.6 | -207039.9 | DOWN | 0.0891 | 61 | Low | 875833.33 | 0.361 | 1 | 870927.67 | 15 | 0.81 | 1.56
P004 | Mechanical | SUP048 | 2025-06 | 2025-05-03 | 2188257.66 | 1746761 | -441496.66 | 441496.66 | 1 | 2025-06-28 | 4 | 2324153.7 | -135896.04 | DOWN | 0.0621 | 56 | Low | 802720.86 | 0.373 | 3 | 944040.14 | 15 | 0.81 | 1.56
P004 | Electronics | SUP048 | 2025-07 | 2025-03-07 | 1721472.7 | 786171 | -935301.7 | 935301.7 | 1 | 2025-07-28 | 1 |  |  |  |  | 143 | Low | 298175.67 | 0.161 | 0 | 487995.33 | 10 | 1.72 | 1
P004 | Electronics | SUP048 | 2025-07 | 2025-04-26 | 1473558.01 | 786171 | -687387.01 | 687387.01 | 1 | 2025-07-28 | 2 | 1721472.7 | -247914.69 | DOWN | 0.1682 | 93 | Low | 419348.42 | 0.266 | 0 | 366822.58 | 10 | 1.72 | 1
P004 | Electronics | SUP048 | 2025-07 | 2025-05-25 | 1312766.44 | 786171 | -526595.44 | 526595.44 | 1 | 2025-07-28 | 3 | 1473558.01 | -160791.57 | DOWN | 0.1225 | 64 | Low | 405202.28 | 0.326 | 3 | 380968.72 | 10 | 1.72 | 1
P004 | Electronics | SUP048 | 2025-07 | 2025-06-05 | 1194194.83 | 786171 | -408023.83 | 408023.83 | 1 | 2025-07-28 | 4 | 1312766.44 | -118571.61 | DOWN | 0.0993 | 53 | Low | 403501.59 | 0.349 | 0 | 382669.41 | 10 | 1.72 | 1
P004 | Electronics | SUP048 | 2025-07 | 2025-07-09 | 1101009.38 | 786171 | -314838.38 | 314838.38 | 1 | 2025-07-28 | 5 | 1194194.83 | -93185.45 | DOWN | 0.0846 | 19 | Low | 498001.14 | 0.42 | 1 | 288169.86 | 10 | 1.72 | 1
P004 | Materials | SUP048 | 2025-08 | 2025-03-08 | 436755.97 | 255436 | -181319.97 | 181319.97 | 1 | 2025-08-28 | 1 |  |  |  |  | 173 | Low | 42507.76 | 0.101 | 0 | 212928.24 | 13 | 1.45 | 1.13
P004 | Materials | SUP048 | 2025-08 | 2025-03-16 | 394755.8 | 255436 | -139319.8 | 139319.8 | 1 | 2025-08-28 | 2 | 436755.97 | -42000.17 | DOWN | 0.1064 | 165 | Low | 45442.08 | 0.119 | 0 | 209993.92 | 13 | 1.45 | 1.13
P004 | Materials | SUP048 | 2025-08 | 2025-03-16 | 359392.57 | 255436 | -103956.57 | 103956.57 | 1 | 2025-08-28 | 3 | 394755.8 | -35363.23 | DOWN | 0.0984 | 165 | Low | 42921.52 | 0.119 | 1 | 212514.48 | 13 | 1.45 | 1.13
P004 | Materials | SUP048 | 2025-08 | 2025-04-19 | 331749.78 | 255436 | -76313.78 | 76313.78 | 1 | 2025-08-28 | 4 | 359392.57 | -27642.79 | DOWN | 0.0833 | 131 | Low | 63839.16 | 0.192 | 2 | 191596.84 | 13 | 1.45 | 1.13
P004 | Materials | SUP048 | 2025-08 | 2025-06-26 | 309358.6 | 255436 | -53922.6 | 53922.6 | 1 | 2025-08-28 | 5 | 331749.78 | -22391.18 | DOWN | 0.0724 | 63 | Low | 101573.23 | 0.339 | 6 | 153862.77 | 13 | 1.45 | 1.13
P004 | Logistics | SUP048 | 2025-09 | 2025-04-08 | 3908078.26 | 2006424 | -1901654.26 | 1901654.26 | 1 | 2025-09-28 | 1 |  |  |  |  | 173 | Low | 380750.96 | 0.103 | 2 | 1625673.04 | 12 | 1.31 | 1.3
P004 | Logistics | SUP048 | 2025-09 | 2025-05-09 | 3398538.84 | 2006424 | -1392114.84 | 1392114.84 | 1 | 2025-09-28 | 2 | 3908078.26 | -509539.42 | DOWN | 0.1499 | 142 | Low | 547922.26 | 0.171 | 1 | 1458501.74 | 12 | 1.31 | 1.3
P004 | Logistics | SUP048 | 2025-09 | 2025-06-19 | 2974511.29 | 2006424 | -968087.29 | 968087.29 | 1 | 2025-09-28 | 3 | 3398538.84 | -424027.55 | DOWN | 0.1426 | 101 | Low | 743445 | 0.261 | 4 | 1262979 | 12 | 1.31 | 1.3
P004 | Logistics | SUP048 | 2025-09 | 2025-07-18 | 2665018.87 | 2006424 | -658594.87 | 658594.87 | 1 | 2025-09-28 | 4 | 2974511.29 | -309492.42 | DOWN | 0.1161 | 72 | Low | 889693.96 | 0.324 | 0 | 1116730.04 | 12 | 1.31 | 1.3
P004 | Logistics | SUP048 | 2025-10 | 2025-05-07 | 3344684.41 | 1705613 | -1639071.41 | 1639071.41 | 1 | 2025-10-28 | 1 |  |  |  |  | 174 | Low | 339354.91 | 0.1 | 2 | 1366258.09 | 16 | 1.37 | 1.4
P004 | Logistics | SUP048 | 2025-10 | 2025-06-20 | 2881332.23 | 1705613 | -1175719.23 | 1175719.23 | 1 | 2025-10-28 | 2 | 3344684.41 | -463352.18 | DOWN | 0.1608 | 130 | Low | 557697.23 | 0.196 | 0 | 1147915.77 | 16 | 1.37 | 1.4
P004 | Logistics | SUP048 | 2025-10 | 2025-06-27 | 2634830.85 | 1705613 | -929217.85 | 929217.85 | 1 | 2025-10-28 | 3 | 2881332.23 | -246501.38 | DOWN | 0.0936 | 123 | Low | 565949.94 | 0.211 | 0 | 1139663.06 | 16 | 1.37 | 1.4
P004 | Logistics | SUP048 | 2025-10 | 2025-07-01 | 2366549.73 | 1705613 | -660936.73 | 660936.73 | 1 | 2025-10-28 | 4 | 2634830.85 | -268281.12 | DOWN | 0.1134 | 119 | Low | 553766.05 | 0.22 | 0 | 1151846.95 | 16 | 1.37 | 1.4
P004 | Logistics | SUP048 | 2025-10 | 2025-08-14 | 2158368.05 | 1705613 | -452755.05 | 452755.05 | 1 | 2025-10-28 | 5 | 2366549.73 | -208181.68 | DOWN | 0.0965 | 75 | Low | 704428.29 | 0.316 | 0 | 1001184.71 | 16 | 1.37 | 1.4
P004 | Logistics | SUP048 | 2025-10 | 2025-10-11 | 2032051.92 | 1705613 | -326438.92 | 326438.92 | 1 | 2025-10-28 | 6 | 2158368.05 | -126316.13 | DOWN | 0.0622 | 17 | Low | 865602.06 | 0.442 | 6 | 840010.94 | 16 | 1.37 | 1.4
P004 | Software | SUP048 | 2025-11 | 2025-07-31 | 2977676.9 | 1342139 | -1635537.9 | 1635537.9 | 1 | 2025-11-28 | 1 |  |  |  |  | 120 | Low | 663252.96 | 0.227 | 4 | 678886.04 | 7 | 0.59 | 1.31
P004 | Software | SUP048 | 2025-11 | 2025-09-14 | 2609104.46 | 1342139 | -1266965.46 | 1266965.46 | 1 | 2025-11-28 | 2 | 2977676.9 | -368572.44 | DOWN | 0.1413 | 75 | Low | 926131.15 | 0.33 | 2 | 416007.85 | 7 | 0.59 | 1.31
P004 | Software | SUP048 | 2025-11 | 2025-09-14 | 2330889.96 | 1342139 | -988750.96 | 988750.96 | 1 | 2025-11-28 | 3 | 2609104.46 | -278214.5 | DOWN | 0.1194 | 75 | Low | 782825.96 | 0.33 | 5 | 559313.04 | 7 | 0.59 | 1.31
P004 | Software | SUP048 | 2025-11 | 2025-09-20 | 2067119.43 | 1342139 | -724980.43 | 724980.43 | 1 | 2025-11-28 | 4 | 2330889.96 | -263770.53 | DOWN | 0.1276 | 69 | Low | 726606.4 | 0.343 | 6 | 615532.6 | 7 | 0.59 | 1.31
P004 | Software | SUP048 | 2025-11 | 2025-10-23 | 1905194.25 | 1342139 | -563055.25 | 563055.25 | 1 | 2025-11-28 | 5 | 2067119.43 | -161925.18 | DOWN | 0.085 | 36 | Low | 817267.43 | 0.418 | 1 | 524871.57 | 7 | 0.59 | 1.31
P004 | Software | SUP048 | 2025-11 | 2025-11-10 | 1786794.89 | 1342139 | -444655.89 | 444655.89 | 1 | 2025-11-28 | 6 | 1905194.25 | -118399.36 | DOWN | 0.0663 | 18 | Medium | 806060.88 | 0.459 | 4 | 536078.12 | 7 | 0.59 | 1.31
P004 | Electronics | SUP048 | 2025-12 | 2025-10-01 | 3776694.32 | 1863147 | -1913547.32 | 1913547.32 | 1 | 2025-12-28 | 1 |  |  |  |  | 88 | Low | 1080745.86 | 0.296 | 7 | 782401.14 | 9 | 1.11 | 0.94
P004 | Electronics | SUP048 | 2025-12 | 2025-10-22 | 3304741.02 | 1863147 | -1441594.02 | 1441594.02 | 1 | 2025-12-28 | 2 | 3776694.32 | -471953.3 | DOWN | 0.1428 | 67 | Low | 1221764.68 | 0.343 | 0 | 641382.32 | 9 | 1.11 | 0.94
P004 | Electronics | SUP048 | 2025-12 | 2025-11-12 | 2929005.86 | 1863147 | -1065858.86 | 1065858.86 | 1 | 2025-12-28 | 3 | 3304741.02 | -375735.16 | DOWN | 0.1283 | 46 | Low | 1150305.27 | 0.39 | 0 | 712841.73 | 9 | 1.11 | 0.94
P004 | Electronics | SUP048 | 2025-12 | 2025-11-16 | 2700759.59 | 1863147 | -837612.59 | 837612.59 | 1 | 2025-12-28 | 4 | 2929005.86 | -228246.27 | DOWN | 0.0845 | 42 | Low | 1133744.01 | 0.399 | 2 | 729402.99 | 9 | 1.11 | 0.94
P005 | Mechanical | SUP044 | 2025-01 | 2024-08-16 | 344785.23 | 272087 | -72698.23 | 72698.23 | 1 | 2025-01-28 | 1 |  |  |  |  | 165 | Low | 59167.77 | 0.185 | 0 | 212919.23 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP044 | 2025-01 | 2024-09-03 | 301957.51 | 272087 | -29870.51 | 29870.51 | 0 | 2025-01-28 | 2 | 344785.23 | -42827.72 | DOWN | 0.1418 | 147 | Low | 68755.69 | 0.246 | 2 | 203331.31 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP044 | 2025-01 | 2024-11-02 | 286717.27 | 272087 | -14630.27 | 14630.27 | 0 | 2025-01-28 | 3 | 301957.51 | -15240.24 | DOWN | 0.0532 | 87 | Low | 127568.29 | 0.448 | 5 | 144518.71 | 8 | 1.44 | 1.07
P005 | Logistics | SUP044 | 2025-02 | 2024-10-13 | 410533.64 | 246776 | -163757.64 | 163757.64 | 1 | 2025-02-28 | 1 |  |  |  |  | 138 | Low | 119750.83 | 0.272 | 4 | 127025.17 | 7 | 1.56 | 1.03
P005 | Logistics | SUP044 | 2025-02 | 2024-11-13 | 317997.82 | 246776 | -71221.82 | 71221.82 | 1 | 2025-02-28 | 2 | 410533.64 | -92535.82 | DOWN | 0.291 | 107 | Low | 113408.26 | 0.375 | 2 | 133367.74 | 7 | 1.56 | 1.03
P005 | Logistics | SUP044 | 2025-02 | 2025-01-12 | 273319.99 | 246776 | -26543.99 | 26543.99 | 0 | 2025-02-28 | 3 | 317997.82 | -44677.83 | DOWN | 0.1635 | 47 | Low | 150060.62 | 0.575 | 3 | 96715.38 | 7 | 1.56 | 1.03
P005 | Services | SUP044 | 2025-03 | 2024-11-03 | 1659543.23 | 1150859 | -508684.23 | 508684.23 | 1 | 2025-03-28 | 1 |  |  |  |  | 145 | Low | 407805.14 | 0.266 | 5 | 743053.86 | 0 | 0.76 | 1.01
P005 | Services | SUP044 | 2025-03 | 2024-11-14 | 1402456.77 | 1150859 | -251597.77 | 251597.77 | 1 | 2025-03-28 | 2 | 1659543.23 | -257086.46 | DOWN | 0.1833 | 134 | Low | 401010.68 | 0.305 | 0 | 749848.32 | 0 | 0.76 | 1.01
P005 | Services | SUP044 | 2025-03 | 2024-12-01 | 1277302.6 | 1150859 | -126443.6 | 126443.6 | 0 | 2025-03-28 | 3 | 1402456.77 | -125154.17 | DOWN | 0.098 | 117 | Low | 477750.49 | 0.365 | 2 | 673108.51 | 0 | 0.76 | 1.01
P005 | Services | SUP044 | 2025-03 | 2025-01-25 | 1224563.16 | 1150859 | -73704.16 | 73704.16 | 0 | 2025-03-28 | 4 | 1277302.6 | -52739.44 | DOWN | 0.0431 | 62 | Low | 727385.65 | 0.56 | 3 | 423473.35 | 0 | 0.76 | 1.01
P005 | Services | SUP044 | 2025-03 | 2025-01-27 | 1202375.14 | 1150859 | -51516.14 | 51516.14 | 0 | 2025-03-28 | 5 | 1224563.16 | -22188.02 | DOWN | 0.0185 | 60 | Medium | 640955.86 | 0.567 | 5 | 509903.14 | 0 | 0.76 | 1.01
P005 | Services | SUP044 | 2025-03 | 2025-03-08 | 1187505.34 | 1150859 | -36646.34 | 36646.34 | 0 | 2025-03-28 | 6 | 1202375.14 | -14869.8 | DOWN | 0.0125 | 20 | High | 822054.53 | 0.709 | 5 | 328804.47 | 0 | 0.76 | 1.01
P005 | Electronics | SUP044 | 2025-04 | 2024-11-09 | 1707304.2 | 1157546 | -549758.2 | 549758.2 | 1 | 2025-04-28 | 1 |  |  |  |  | 170 | Low | 289562.62 | 0.167 | 0 | 867983.38 | 2 | 1.52 | 1.28
P005 | Electronics | SUP044 | 2025-04 | 2024-11-17 | 1424125.28 | 1157546 | -266579.28 | 266579.28 | 1 | 2025-04-28 | 2 | 1707304.2 | -283178.92 | DOWN | 0.1988 | 162 | Low | 266525.39 | 0.194 | 0 | 891020.61 | 2 | 1.52 | 1.28
P005 | Electronics | SUP044 | 2025-04 | 2025-01-03 | 1291042.04 | 1157546 | -133496.04 | 133496.04 | 0 | 2025-04-28 | 3 | 1424125.28 | -133083.24 | DOWN | 0.1031 | 115 | Low | 460174.28 | 0.35 | 4 | 697371.72 | 2 | 1.52 | 1.28
P005 | Electronics | SUP044 | 2025-04 | 2025-01-21 | 1211418.06 | 1157546 | -53872.06 | 53872.06 | 0 | 2025-04-28 | 4 | 1291042.04 | -79623.98 | DOWN | 0.0657 | 97 | Low | 506099.19 | 0.41 | 4 | 651446.81 | 2 | 1.52 | 1.28
P005 | Electronics | SUP044 | 2025-04 | 2025-03-12 | 1178256.21 | 1157546 | -20710.21 | 20710.21 | 0 | 2025-04-28 | 5 | 1211418.06 | -33161.85 | DOWN | 0.0281 | 47 | Medium | 633625.26 | 0.577 | 6 | 523920.74 | 2 | 1.52 | 1.28
P005 | Materials | SUP044 | 2025-05 | 2025-01-27 | 2462445.7 | 1953955 | -508490.7 | 508490.7 | 1 | 2025-05-28 | 1 |  |  |  |  | 121 | Low | 834387.06 | 0.346 | 2 | 1119567.94 | 6 | 1.12 | 1.51
P005 | Materials | SUP044 | 2025-05 | 2025-03-04 | 2202676.83 | 1953955 | -248721.83 | 248721.83 | 0 | 2025-05-28 | 2 | 2462445.7 | -259768.87 | DOWN | 0.1179 | 85 | Low | 981395.73 | 0.472 | 5 | 972559.27 | 6 | 1.12 | 1.51
P005 | Materials | SUP044 | 2025-05 | 2025-04-15 | 2065531.36 | 1953955 | -111576.36 | 111576.36 | 0 | 2025-05-28 | 3 | 2202676.83 | -137145.47 | DOWN | 0.0664 | 43 | Medium | 1334263.61 | 0.619 | 8 | 619691.39 | 6 | 1.12 | 1.51
P005 | Materials | SUP044 | 2025-05 | 2025-05-07 | 1992117.77 | 1953955 | -38162.77 | 38162.77 | 0 | 2025-05-28 | 4 | 2065531.36 | -73413.59 | DOWN | 0.0369 | 21 | High | 1348440.01 | 0.696 | 5 | 605514.99 | 6 | 1.12 | 1.51
P005 | Services | SUP044 | 2025-06 | 2025-01-05 | 3021739.01 | 1964733 | -1057006.01 | 1057006.01 | 1 | 2025-06-28 | 1 |  |  |  |  | 174 | Low | 458502.18 | 0.161 | 0 | 1506230.82 | 7 | 1.1 | 1.21
P005 | Services | SUP044 | 2025-06 | 2025-01-22 | 2400518.53 | 1964733 | -435785.53 | 435785.53 | 1 | 2025-06-28 | 2 | 3021739.01 | -621220.48 | DOWN | 0.2588 | 157 | Low | 524540.11 | 0.221 | 0 | 1440192.89 | 7 | 1.1 | 1.21
P005 | Services | SUP044 | 2025-06 | 2025-02-05 | 2171155.65 | 1964733 | -206422.65 | 206422.65 | 0 | 2025-06-28 | 3 | 2400518.53 | -229362.88 | DOWN | 0.1056 | 143 | Low | 584949.61 | 0.27 | 1 | 1379783.39 | 7 | 1.1 | 1.21
P005 | Services | SUP044 | 2025-06 | 2025-04-08 | 2083687.27 | 1964733 | -118954.27 | 118954.27 | 0 | 2025-06-28 | 4 | 2171155.65 | -87468.38 | DOWN | 0.042 | 81 | Low | 1073266.32 | 0.487 | 0 | 891466.68 | 7 | 1.1 | 1.21
P005 | Services | SUP044 | 2025-06 | 2025-06-17 | 1991192.89 | 1964733 | -26459.89 | 26459.89 | 0 | 2025-06-28 | 5 | 2083687.27 | -92494.38 | DOWN | 0.0465 | 11 | High | 1388258.26 | 0.732 | 5 | 576474.74 | 7 | 1.1 | 1.21
P005 | Services | SUP044 | 2025-07 | 2025-02-10 | 2206242.86 | 1616902 | -589340.86 | 589340.86 | 1 | 2025-07-28 | 1 |  |  |  |  | 168 | Low | 416192.08 | 0.18 | 4 | 1200709.92 | 1 | 1.18 | 1.15
P005 | Services | SUP044 | 2025-07 | 2025-03-27 | 1857604.73 | 1616902 | -240702.73 | 240702.73 | 0 | 2025-07-28 | 2 | 2206242.86 | -348638.13 | DOWN | 0.1877 | 123 | Low | 632132.66 | 0.337 | 5 | 984769.34 | 1 | 1.18 | 1.15
P005 | Services | SUP044 | 2025-07 | 2025-06-11 | 1691647.48 | 1616902 | -74745.48 | 74745.48 | 0 | 2025-07-28 | 3 | 1857604.73 | -165957.25 | DOWN | 0.0981 | 47 | Medium | 1020522.89 | 0.6 | 5 | 596379.11 | 1 | 1.18 | 1.15
P005 | Electronics | SUP044 | 2025-08 | 2025-05-02 | 1416722.92 | 1009874 | -406848.92 | 406848.92 | 1 | 2025-08-28 | 1 |  |  |  |  | 118 | Low | 507936.11 | 0.334 | 1 | 501937.89 | 8 | 1.7 | 1.32
P005 | Electronics | SUP044 | 2025-08 | 2025-06-01 | 1192395.95 | 1009874 | -182521.95 | 182521.95 | 1 | 2025-08-28 | 2 | 1416722.92 | -224326.97 | DOWN | 0.1881 | 88 | Low | 498858.63 | 0.432 | 2 | 511015.37 | 8 | 1.7 | 1.32
P005 | Electronics | SUP044 | 2025-08 | 2025-08-08 | 1103036.48 | 1009874 | -93162.48 | 93162.48 | 0 | 2025-08-28 | 3 | 1192395.95 | -89359.47 | DOWN | 0.081 | 20 | Medium | 733373.2 | 0.654 | 2 | 276500.8 | 8 | 1.7 | 1.32
P005 | Materials | SUP044 | 2025-09 | 2025-04-20 | 3520986.38 | 2398297 | -1122689.38 | 1122689.38 | 1 | 2025-09-28 | 1 |  |  |  |  | 161 | Low | 734267.22 | 0.209 | 0 | 1664029.78 | 0 | 0.5 | 0.8
P005 | Materials | SUP044 | 2025-09 | 2025-04-22 | 2916415.44 | 2398297 | -518118.44 | 518118.44 | 1 | 2025-09-28 | 2 | 3520986.38 | -604570.94 | DOWN | 0.2073 | 159 | Low | 615139.6 | 0.216 | 2 | 1783157.4 | 0 | 0.5 | 0.8
P005 | Materials | SUP044 | 2025-09 | 2025-05-24 | 2633434.43 | 2398297 | -235137.43 | 235137.43 | 0 | 2025-09-28 | 3 | 2916415.44 | -282981.01 | DOWN | 0.1075 | 127 | Low | 922615.66 | 0.33 | 3 | 1475681.34 | 0 | 0.5 | 0.8
P005 | Materials | SUP044 | 2025-09 | 2025-06-12 | 2516871.36 | 2398297 | -118574.36 | 118574.36 | 0 | 2025-09-28 | 4 | 2633434.43 | -116563.07 | DOWN | 0.0463 | 108 | Low | 938419.88 | 0.397 | 3 | 1459877.12 | 0 | 0.5 | 0.8
P005 | Materials | SUP044 | 2025-09 | 2025-06-30 | 2453575.16 | 2398297 | -55278.16 | 55278.16 | 0 | 2025-09-28 | 5 | 2516871.36 | -63296.2 | DOWN | 0.0258 | 90 | Low | 1187659.99 | 0.461 | 2 | 1210637.01 | 0 | 0.5 | 0.8
P005 | Materials | SUP044 | 2025-09 | 2025-07-11 | 2427112.11 | 2398297 | -28815.11 | 28815.11 | 0 | 2025-09-28 | 6 | 2453575.16 | -26463.05 | DOWN | 0.0109 | 79 | Low | 1227984.23 | 0.5 | 4 | 1170312.77 | 0 | 0.5 | 0.8
P005 | Materials | SUP044 | 2025-10 | 2025-06-13 | 1505466.54 | 1169263 | -336203.54 | 336203.54 | 1 | 2025-10-28 | 1 |  |  |  |  | 137 | Low | 411261.11 | 0.289 | 0 | 758001.89 | 4 | 1.15 | 0.8
P005 | Materials | SUP044 | 2025-10 | 2025-08-14 | 1318522.93 | 1169263 | -149259.93 | 149259.93 | 0 | 2025-10-28 | 2 | 1505466.54 | -186943.61 | DOWN | 0.1418 | 75 | Low | 669130.11 | 0.505 | 4 | 500132.89 | 4 | 1.15 | 0.8
P005 | Materials | SUP044 | 2025-10 | 2025-09-29 | 1231993.19 | 1169263 | -62730.19 | 62730.19 | 0 | 2025-10-28 | 3 | 1318522.93 | -86529.74 | DOWN | 0.0702 | 29 | Medium | 834462.97 | 0.665 | 5 | 334800.03 | 4 | 1.15 | 0.8
P005 | Materials | SUP044 | 2025-10 | 2025-10-04 | 1190890.43 | 1169263 | -21627.43 | 21627.43 | 0 | 2025-10-28 | 4 | 1231993.19 | -41102.76 | DOWN | 0.0345 | 24 | High | 865107.71 | 0.683 | 7 | 304155.29 | 4 | 1.15 | 0.8
P005 | Materials | SUP044 | 2025-10 | 2025-10-07 | 1183318.81 | 1169263 | -14055.81 | 14055.81 | 0 | 2025-10-28 | 5 | 1190890.43 | -7571.62 | DOWN | 0.0064 | 21 | High | 801628.92 | 0.693 | 5 | 367634.08 | 4 | 1.15 | 0.8
P005 | Logistics | SUP044 | 2025-11 | 2025-06-07 | 2060259.38 | 1423706 | -636553.38 | 636553.38 | 1 | 2025-11-28 | 1 |  |  |  |  | 174 | Low | 329663.5 | 0.157 | 1 | 1094042.5 | 4 | 1.35 | 1.5
P005 | Logistics | SUP044 | 2025-11 | 2025-06-08 | 1690230.07 | 1423706 | -266524.07 | 266524.07 | 1 | 2025-11-28 | 2 | 2060259.38 | -370029.31 | DOWN | 0.2189 | 173 | Low | 279851.2 | 0.16 | 1 | 1143854.8 | 4 | 1.35 | 1.5
P005 | Logistics | SUP044 | 2025-11 | 2025-06-17 | 1581881.08 | 1423706 | -158175.08 | 158175.08 | 0 | 2025-11-28 | 3 | 1690230.07 | -108348.99 | DOWN | 0.0685 | 164 | Low | 321534.62 | 0.191 | 3 | 1102171.38 | 4 | 1.35 | 1.5
P005 | Logistics | SUP044 | 2025-11 | 2025-07-01 | 1486924.76 | 1423706 | -63218.76 | 63218.76 | 0 | 2025-11-28 | 4 | 1581881.08 | -94956.32 | DOWN | 0.0639 | 150 | Low | 326857.66 | 0.238 | 0 | 1096848.34 | 4 | 1.35 | 1.5
P005 | Logistics | SUP044 | 2025-11 | 2025-10-08 | 1424741.15 | 1423706 | -1035.15 | 1035.15 | 0 | 2025-11-28 | 5 | 1486924.76 | -62183.61 | DOWN | 0.0436 | 51 | Medium | 834228.22 | 0.575 | 3 | 589477.78 | 4 | 1.35 | 1.5
P005 | Logistics | SUP044 | 2025-11 | 2025-11-09 | 1445987.01 | 1423706 | -22281.01 | 22281.01 | 0 | 2025-11-28 | 6 | 1424741.15 | 21245.86 | UP | 0.0147 | 19 | High | 1014974.5 | 0.684 | 6 | 408731.5 | 4 | 1.35 | 1.5
P005 | Software | SUP044 | 2025-12 | 2025-07-27 | 2259931.28 | 1699410 | -560521.28 | 560521.28 | 1 | 2025-12-28 | 1 |  |  |  |  | 154 | Low | 536945.94 | 0.234 | 1 | 1162464.06 | 7 | 0.73 | 1.27
P005 | Software | SUP044 | 2025-12 | 2025-08-02 | 1980013.41 | 1699410 | -280603.41 | 280603.41 | 0 | 2025-12-28 | 2 | 2259931.28 | -279917.87 | DOWN | 0.1414 | 148 | Low | 479701.95 | 0.255 | 4 | 1219708.05 | 7 | 0.73 | 1.27
P005 | Software | SUP044 | 2025-12 | 2025-09-06 | 1813146.82 | 1699410 | -113736.82 | 113736.82 | 0 | 2025-12-28 | 3 | 1980013.41 | -166866.59 | DOWN | 0.092 | 113 | Low | 738836.44 | 0.379 | 6 | 960573.56 | 7 | 0.73 | 1.27
P005 | Software | SUP044 | 2025-12 | 2025-10-30 | 1745728.85 | 1699410 | -46318.85 | 46318.85 | 0 | 2025-12-28 | 4 | 1813146.82 | -67417.97 | DOWN | 0.0386 | 59 | Medium | 944549.96 | 0.571 | 4 | 754860.04 | 7 | 0.73 | 1.27
P005 | Software | SUP044 | 2025-12 | 2025-12-11 | 1705610.34 | 1699410 | -6200.34 | 6200.34 | 0 | 2025-12-28 | 5 | 1745728.85 | -40118.51 | DOWN | 0.0235 | 17 | High | 1306081.84 | 0.72 | 10 | 393328.16 | 7 | 0.73 | 1.27
P005 | Software | SUP044 | 2025-12 | 2025-12-14 | 1711168.75 | 1699410 | -11758.75 | 11758.75 | 0 | 2025-12-28 | 6 | 1705610.34 | 5558.41 | UP | 0.0032 | 14 | High | 1279777.48 | 0.73 | 9 | 419632.52 | 7 | 0.73 | 1.27
P005 | Logistics | SUP034 | 2025-01 | 2024-09-20 | 2902807.98 | 1915535 | -987272.98 | 987272.98 | 1 | 2025-01-28 | 1 |  |  |  |  | 130 | Low | 834510.1 | 0.303 | 0 | 1081024.9 | 8 | 1.44 | 1.07
P005 | Logistics | SUP034 | 2025-01 | 2024-10-14 | 2355591.53 | 1915535 | -440056.53 | 440056.53 | 1 | 2025-01-28 | 2 | 2902807.98 | -547216.45 | DOWN | 0.2323 | 106 | Low | 976157.35 | 0.384 | 5 | 939377.65 | 8 | 1.44 | 1.07
P005 | Logistics | SUP034 | 2025-01 | 2024-12-04 | 2128236.6 | 1915535 | -212701.6 | 212701.6 | 0 | 2025-01-28 | 3 | 2355591.53 | -227354.93 | DOWN | 0.1068 | 55 | Medium | 1193135.56 | 0.556 | 2 | 722399.44 | 8 | 1.44 | 1.07
P005 | Services | SUP034 | 2025-02 | 2024-09-12 | 475875.92 | 342581 | -133294.92 | 133294.92 | 1 | 2025-02-28 | 1 |  |  |  |  | 169 | Low | 81777.17 | 0.169 | 0 | 260803.83 | 7 | 1.56 | 1.03
P005 | Services | SUP034 | 2025-02 | 2024-10-17 | 410589.66 | 342581 | -68008.66 | 68008.66 | 1 | 2025-02-28 | 2 | 475875.92 | -65286.26 | DOWN | 0.159 | 134 | Low | 114920.78 | 0.286 | 4 | 227660.22 | 7 | 1.56 | 1.03
P005 | Services | SUP034 | 2025-02 | 2024-10-27 | 373072.36 | 342581 | -30491.36 | 30491.36 | 0 | 2025-02-28 | 3 | 410589.66 | -37517.3 | DOWN | 0.1006 | 124 | Low | 109920.52 | 0.319 | 0 | 232660.48 | 7 | 1.56 | 1.03
P005 | Services | SUP034 | 2025-02 | 2024-11-09 | 353972.55 | 342581 | -11391.55 | 11391.55 | 0 | 2025-02-28 | 4 | 373072.36 | -19099.81 | DOWN | 0.054 | 111 | Low | 128309.23 | 0.362 | 3 | 214271.77 | 7 | 1.56 | 1.03
P005 | Services | SUP034 | 2025-02 | 2024-11-12 | 345587.28 | 342581 | -3006.28 | 3006.28 | 0 | 2025-02-28 | 5 | 353972.55 | -8385.27 | DOWN | 0.0243 | 108 | Low | 120779.05 | 0.372 | 2 | 221801.95 | 7 | 1.56 | 1.03
P005 | Materials | SUP034 | 2025-03 | 2024-11-04 | 201001.29 | 156411 | -44590.29 | 44590.29 | 1 | 2025-03-28 | 1 |  |  |  |  | 144 | Low | 56750.66 | 0.269 | 1 | 99660.34 | 0 | 0.76 | 1.01
P005 | Materials | SUP034 | 2025-03 | 2024-12-02 | 176174.26 | 156411 | -19763.26 | 19763.26 | 0 | 2025-03-28 | 2 | 201001.29 | -24827.03 | DOWN | 0.1409 | 116 | Low | 68585.92 | 0.369 | 3 | 87825.08 | 0 | 0.76 | 1.01
P005 | Materials | SUP034 | 2025-03 | 2024-12-15 | 164219.29 | 156411 | -7808.29 | 7808.29 | 0 | 2025-03-28 | 3 | 176174.26 | -11954.97 | DOWN | 0.0728 | 103 | Low | 73030.01 | 0.415 | 9 | 83380.99 | 0 | 0.76 | 1.01
P005 | Materials | SUP034 | 2025-03 | 2025-03-08 | 158787.22 | 156411 | -2376.22 | 2376.22 | 0 | 2025-03-28 | 4 | 164219.29 | -5432.07 | DOWN | 0.0342 | 20 | High | 110400.5 | 0.709 | 6 | 46010.5 | 0 | 0.76 | 1.01
P005 | Materials | SUP034 | 2025-03 | 2025-03-11 | 158733.98 | 156411 | -2322.98 | 2322.98 | 0 | 2025-03-28 | 5 | 158787.22 | -53.24 | DOWN | 0.0003 | 17 | High | 118964.03 | 0.72 | 2 | 37446.97 | 0 | 0.76 | 1.01
P005 | Services | SUP034 | 2025-04 | 2024-12-19 | 2109035.83 | 1654118 | -454917.83 | 454917.83 | 1 | 2025-04-28 | 1 |  |  |  |  | 130 | Low | 625221.89 | 0.3 | 0 | 1028896.11 | 2 | 1.52 | 1.28
P005 | Services | SUP034 | 2025-04 | 2025-03-12 | 1877561.99 | 1654118 | -223443.99 | 223443.99 | 0 | 2025-04-28 | 2 | 2109035.83 | -231473.84 | DOWN | 0.1233 | 47 | Low | 1064598.07 | 0.577 | 6 | 589519.93 | 2 | 1.52 | 1.28
P005 | Services | SUP034 | 2025-04 | 2025-04-12 | 1765733.74 | 1654118 | -111615.74 | 111615.74 | 0 | 2025-04-28 | 3 | 1877561.99 | -111828.25 | DOWN | 0.0633 | 16 | Medium | 1291111.42 | 0.681 | 7 | 363006.58 | 2 | 1.52 | 1.28
P005 | Materials | SUP034 | 2025-05 | 2025-03-10 | 920167.08 | 763664 | -156503.08 | 156503.08 | 1 | 2025-05-28 | 1 |  |  |  |  | 79 | Low | 436756.95 | 0.493 | 8 | 326907.05 | 6 | 1.12 | 1.51
P005 | Materials | SUP034 | 2025-05 | 2025-04-18 | 829024.65 | 763664 | -65360.65 | 65360.65 | 0 | 2025-05-28 | 2 | 920167.08 | -91142.43 | DOWN | 0.1099 | 40 | Medium | 540738.38 | 0.629 | 4 | 222925.62 | 6 | 1.12 | 1.51
P005 | Materials | SUP034 | 2025-05 | 2025-04-19 | 787677.44 | 763664 | -24013.44 | 24013.44 | 0 | 2025-05-28 | 3 | 829024.65 | -41347.21 | DOWN | 0.0525 | 39 | Medium | 490853.97 | 0.633 | 5 | 272810.03 | 6 | 1.12 | 1.51
P005 | Materials | SUP034 | 2025-05 | 2025-04-22 | 778858.51 | 763664 | -15194.51 | 15194.51 | 0 | 2025-05-28 | 4 | 787677.44 | -8818.93 | DOWN | 0.0113 | 36 | Medium | 524020.76 | 0.643 | 4 | 239643.24 | 6 | 1.12 | 1.51
P005 | Logistics | SUP034 | 2025-06 | 2025-01-19 | 2373625.38 | 1497663 | -875962.38 | 875962.38 | 1 | 2025-06-28 | 1 |  |  |  |  | 160 | Low | 533728.73 | 0.21 | 2 | 963934.27 | 7 | 1.1 | 1.21
P005 | Logistics | SUP034 | 2025-06 | 2025-03-18 | 1869306.3 | 1497663 | -371643.3 | 371643.3 | 1 | 2025-06-28 | 2 | 2373625.38 | -504319.08 | DOWN | 0.2698 | 102 | Low | 720307.6 | 0.413 | 3 | 777355.4 | 7 | 1.1 | 1.21
P005 | Logistics | SUP034 | 2025-06 | 2025-03-24 | 1640957.71 | 1497663 | -143294.71 | 143294.71 | 0 | 2025-06-28 | 3 | 1869306.3 | -228348.59 | DOWN | 0.1392 | 96 | Low | 749628.95 | 0.434 | 3 | 748034.05 | 7 | 1.1 | 1.21
P005 | Logistics | SUP034 | 2025-06 | 2025-06-02 | 1539247.48 | 1497663 | -41584.48 | 41584.48 | 0 | 2025-06-28 | 4 | 1640957.71 | -101710.23 | DOWN | 0.0661 | 26 | Medium | 1058590.66 | 0.68 | 8 | 439072.34 | 7 | 1.1 | 1.21
P005 | Logistics | SUP034 | 2025-07 | 2025-03-12 | 2375734.65 | 1521379 | -854355.65 | 854355.65 | 1 | 2025-07-28 | 1 |  |  |  |  | 138 | Low | 664873.95 | 0.285 | 1 | 856505.05 | 1 | 1.18 | 1.15
P005 | Logistics | SUP034 | 2025-07 | 2025-03-22 | 1900199.49 | 1521379 | -378820.49 | 378820.49 | 1 | 2025-07-28 | 2 | 2375734.65 | -475535.16 | DOWN | 0.2503 | 128 | Low | 607436.9 | 0.319 | 1 | 913942.1 | 1 | 1.18 | 1.15
P005 | Logistics | SUP034 | 2025-07 | 2025-05-23 | 1732312.12 | 1521379 | -210933.12 | 210933.12 | 0 | 2025-07-28 | 3 | 1900199.49 | -167887.37 | DOWN | 0.0969 | 66 | Low | 918034.52 | 0.534 | 4 | 603344.48 | 1 | 1.18 | 1.15
P005 | Logistics | SUP034 | 2025-07 | 2025-06-10 | 1634795.19 | 1521379 | -113416.19 | 113416.19 | 0 | 2025-07-28 | 4 | 1732312.12 | -97516.93 | DOWN | 0.0597 | 48 | Medium | 912917.14 | 0.597 | 5 | 608461.86 | 1 | 1.18 | 1.15
P005 | Logistics | SUP034 | 2025-07 | 2025-06-11 | 1551226.31 | 1521379 | -29847.31 | 29847.31 | 0 | 2025-07-28 | 5 | 1634795.19 | -83568.88 | DOWN | 0.0539 | 47 | Medium | 984096.13 | 0.6 | 5 | 537282.87 | 1 | 1.18 | 1.15
P005 | Logistics | SUP034 | 2025-07 | 2025-07-16 | 1507787.36 | 1521379 | 13591.64 | 13591.64 | 0 | 2025-07-28 | 6 | 1551226.31 | -43438.95 | DOWN | 0.0288 | 12 | High | 1040439.79 | 0.722 | 4 | 480939.21 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP034 | 2025-08 | 2025-03-18 | 3759975.45 | 2633404 | -1126571.45 | 1126571.45 | 1 | 2025-08-28 | 1 |  |  |  |  | 163 | Low | 736579.11 | 0.186 | 3 | 1896824.89 | 8 | 1.7 | 1.32
P005 | Mechanical | SUP034 | 2025-08 | 2025-04-19 | 3175725.86 | 2633404 | -542321.86 | 542321.86 | 1 | 2025-08-28 | 2 | 3759975.45 | -584249.59 | DOWN | 0.184 | 131 | Low | 988091.08 | 0.291 | 1 | 1645312.92 | 8 | 1.7 | 1.32
P005 | Mechanical | SUP034 | 2025-08 | 2025-06-24 | 2912437.25 | 2633404 | -279033.25 | 279033.25 | 0 | 2025-08-28 | 3 | 3175725.86 | -263288.61 | DOWN | 0.0904 | 65 | Low | 1504749.35 | 0.507 | 6 | 1128654.65 | 8 | 1.7 | 1.32
P005 | Mechanical | SUP034 | 2025-08 | 2025-07-02 | 2759334.77 | 2633404 | -125930.77 | 125930.77 | 0 | 2025-08-28 | 4 | 2912437.25 | -153102.48 | DOWN | 0.0555 | 57 | Medium | 1459092.37 | 0.533 | 1 | 1174311.63 | 8 | 1.7 | 1.32
P005 | Mechanical | SUP034 | 2025-08 | 2025-07-10 | 2668580.59 | 2633404 | -35176.59 | 35176.59 | 0 | 2025-08-28 | 5 | 2759334.77 | -90754.18 | DOWN | 0.034 | 49 | Medium | 1581925.5 | 0.559 | 1 | 1051478.5 | 8 | 1.7 | 1.32
P005 | Mechanical | SUP034 | 2025-08 | 2025-07-25 | 2672238.06 | 2633404 | -38834.06 | 38834.06 | 0 | 2025-08-28 | 6 | 2668580.59 | 3657.47 | UP | 0.0014 | 34 | Medium | 1706746.47 | 0.608 | 6 | 926657.53 | 8 | 1.7 | 1.32
P005 | Electronics | SUP034 | 2025-09 | 2025-04-29 | 1440090.69 | 1075275 | -364815.69 | 364815.69 | 1 | 2025-09-28 | 1 |  |  |  |  | 152 | Low | 357689.23 | 0.241 | 2 | 717585.77 | 0 | 0.5 | 0.8
P005 | Electronics | SUP034 | 2025-09 | 2025-07-16 | 1222247.25 | 1075275 | -146972.25 | 146972.25 | 0 | 2025-09-28 | 2 | 1440090.69 | -217843.44 | DOWN | 0.1782 | 74 | Low | 646006.7 | 0.518 | 3 | 429268.3 | 0 | 0.5 | 0.8
P005 | Electronics | SUP034 | 2025-09 | 2025-08-04 | 1152580.16 | 1075275 | -77305.16 | 77305.16 | 0 | 2025-09-28 | 3 | 1222247.25 | -69667.09 | DOWN | 0.0604 | 55 | Medium | 699710.84 | 0.585 | 4 | 375564.16 | 0 | 0.5 | 0.8
P005 | Materials | SUP034 | 2025-10 | 2025-05-22 | 1960889.49 | 1504590 | -456299.49 | 456299.49 | 1 | 2025-10-28 | 1 |  |  |  |  | 159 | Low | 444996.69 | 0.212 | 0 | 1059593.31 | 4 | 1.15 | 0.8
P005 | Materials | SUP034 | 2025-10 | 2025-06-02 | 1697055.9 | 1504590 | -192465.9 | 192465.9 | 0 | 2025-10-28 | 2 | 1960889.49 | -263833.59 | DOWN | 0.1555 | 148 | Low | 421730.67 | 0.251 | 0 | 1082859.33 | 4 | 1.15 | 0.8
P005 | Materials | SUP034 | 2025-10 | 2025-06-30 | 1581975.91 | 1504590 | -77385.91 | 77385.91 | 0 | 2025-10-28 | 3 | 1697055.9 | -115079.99 | DOWN | 0.0727 | 120 | Low | 531195.08 | 0.348 | 1 | 973394.92 | 4 | 1.15 | 0.8
P005 | Materials | SUP034 | 2025-10 | 2025-07-27 | 1528618.78 | 1504590 | -24028.78 | 24028.78 | 0 | 2025-10-28 | 4 | 1581975.91 | -53357.13 | DOWN | 0.0349 | 93 | Low | 636450.32 | 0.442 | 1 | 868139.68 | 4 | 1.15 | 0.8
P005 | Software | SUP034 | 2025-11 | 2025-07-21 | 437244.52 | 264687 | -172557.52 | 172557.52 | 1 | 2025-11-28 | 1 |  |  |  |  | 130 | Low | 123203.66 | 0.306 | 3 | 141483.34 | 4 | 1.35 | 1.5
P005 | Software | SUP034 | 2025-11 | 2025-08-21 | 338675.17 | 264687 | -73988.17 | 73988.17 | 1 | 2025-11-28 | 2 | 437244.52 | -98569.35 | DOWN | 0.291 | 99 | Low | 135112.97 | 0.412 | 5 | 129574.03 | 4 | 1.35 | 1.5
P005 | Software | SUP034 | 2025-11 | 2025-09-16 | 298844.25 | 264687 | -34157.25 | 34157.25 | 0 | 2025-11-28 | 3 | 338675.17 | -39830.92 | DOWN | 0.1333 | 73 | Low | 147439.42 | 0.5 | 0 | 117247.58 | 4 | 1.35 | 1.5
P005 | Software | SUP034 | 2025-11 | 2025-11-04 | 285412.37 | 264687 | -20725.37 | 20725.37 | 0 | 2025-11-28 | 4 | 298844.25 | -13431.88 | DOWN | 0.0471 | 24 | High | 203908.75 | 0.667 | 9 | 60778.25 | 4 | 1.35 | 1.5
P005 | Services | SUP034 | 2025-12 | 2025-07-31 | 3638694.58 | 2592889 | -1045805.58 | 1045805.58 | 1 | 2025-12-28 | 1 |  |  |  |  | 150 | Low | 955148.13 | 0.248 | 1 | 1637740.87 | 7 | 0.73 | 1.27
P005 | Services | SUP034 | 2025-12 | 2025-10-13 | 3048312.1 | 2592889 | -455423.1 | 455423.1 | 0 | 2025-12-28 | 2 | 3638694.58 | -590382.48 | DOWN | 0.1937 | 76 | Low | 1487132.32 | 0.511 | 6 | 1105756.68 | 7 | 0.73 | 1.27
P005 | Services | SUP034 | 2025-12 | 2025-11-08 | 2792309.16 | 2592889 | -199420.16 | 199420.16 | 0 | 2025-12-28 | 3 | 3048312.1 | -256002.94 | DOWN | 0.0917 | 50 | Medium | 1733479.52 | 0.603 | 0 | 859409.48 | 7 | 0.73 | 1.27
P005 | Services | SUP034 | 2025-12 | 2025-12-07 | 2648135.22 | 2592889 | -55246.22 | 55246.22 | 0 | 2025-12-28 | 4 | 2792309.16 | -144173.94 | DOWN | 0.0544 | 21 | High | 1869134.29 | 0.706 | 7 | 723754.71 | 7 | 0.73 | 1.27
P005 | Software | SUP030 | 2025-01 | 2024-09-08 | 2486526.15 | 1251542 | -1234984.15 | 1234984.15 | 1 | 2025-01-28 | 1 |  |  |  |  | 142 | Low | 534905.68 | 0.219 | 4 | 716636.32 | 8 | 1.44 | 1.07
P005 | Software | SUP030 | 2025-01 | 2024-10-14 | 1924033.29 | 1251542 | -672491.29 | 672491.29 | 1 | 2025-01-28 | 2 | 2486526.15 | -562492.86 | DOWN | 0.2924 | 106 | Low | 572786.35 | 0.32 | 0 | 678755.65 | 8 | 1.44 | 1.07
P005 | Software | SUP030 | 2025-01 | 2024-12-08 | 1647409.67 | 1251542 | -395867.67 | 395867.67 | 1 | 2025-01-28 | 3 | 1924033.29 | -276623.62 | DOWN | 0.1679 | 51 | Low | 800323.44 | 0.474 | 0 | 451218.56 | 8 | 1.44 | 1.07
P005 | Materials | SUP030 | 2025-02 | 2024-09-07 | 3229929.28 | 2354978 | -874951.28 | 874951.28 | 1 | 2025-02-28 | 1 |  |  |  |  | 174 | Low | 426941.81 | 0.127 | 3 | 1928036.19 | 7 | 1.56 | 1.03
P005 | Materials | SUP030 | 2025-02 | 2024-11-04 | 2827883.42 | 2354978 | -472905.42 | 472905.42 | 1 | 2025-02-28 | 2 | 3229929.28 | -402045.86 | DOWN | 0.1422 | 116 | Low | 767402.87 | 0.288 | 1 | 1587575.13 | 7 | 1.56 | 1.03
P005 | Materials | SUP030 | 2025-02 | 2025-02-02 | 2627724.71 | 2354978 | -272746.71 | 272746.71 | 0 | 2025-02-28 | 3 | 2827883.42 | -200158.71 | DOWN | 0.0762 | 26 | Medium | 1407809.71 | 0.537 | 6 | 947168.29 | 7 | 1.56 | 1.03
P005 | Materials | SUP030 | 2025-03 | 2024-10-26 | 1627122.27 | 957653 | -669469.27 | 669469.27 | 1 | 2025-03-28 | 1 |  |  |  |  | 153 | Low | 320826.54 | 0.198 | 0 | 636826.46 | 0 | 0.76 | 1.01
P005 | Materials | SUP030 | 2025-03 | 2024-10-30 | 1338414.96 | 957653 | -380761.96 | 380761.96 | 1 | 2025-03-28 | 2 | 1627122.27 | -288707.31 | DOWN | 0.2157 | 149 | Low | 300669.73 | 0.21 | 0 | 656983.27 | 0 | 0.76 | 1.01
P005 | Materials | SUP030 | 2025-03 | 2024-11-04 | 1162097.75 | 957653 | -204444.75 | 204444.75 | 1 | 2025-03-28 | 3 | 1338414.96 | -176317.21 | DOWN | 0.1517 | 144 | Low | 257110.54 | 0.225 | 0 | 700542.46 | 0 | 0.76 | 1.01
P005 | Materials | SUP030 | 2025-03 | 2024-11-22 | 1061410.05 | 957653 | -103757.05 | 103757.05 | 0 | 2025-03-28 | 4 | 1162097.75 | -100687.7 | DOWN | 0.0949 | 126 | Low | 285618.2 | 0.278 | 1 | 672034.8 | 0 | 0.76 | 1.01
P005 | Materials | SUP030 | 2025-03 | 2024-12-12 | 1006787.96 | 957653 | -49134.96 | 49134.96 | 0 | 2025-03-28 | 5 | 1061410.05 | -54622.09 | DOWN | 0.0543 | 106 | Low | 318608.16 | 0.337 | 2 | 639044.84 | 0 | 0.76 | 1.01
P005 | Materials | SUP030 | 2025-03 | 2025-03-02 | 985623.99 | 957653 | -27970.99 | 27970.99 | 0 | 2025-03-28 | 6 | 1006787.96 | -21163.97 | DOWN | 0.0215 | 26 | Medium | 531887.66 | 0.573 | 4 | 425765.34 | 0 | 0.76 | 1.01
P005 | Materials | SUP030 | 2025-04 | 2024-11-24 | 2880900.55 | 1674637 | -1206263.55 | 1206263.55 | 1 | 2025-04-28 | 1 |  |  |  |  | 155 | Low | 533235.17 | 0.181 | 0 | 1141401.83 | 2 | 1.52 | 1.28
P005 | Materials | SUP030 | 2025-04 | 2024-12-28 | 2307299.34 | 1674637 | -632662.34 | 632662.34 | 1 | 2025-04-28 | 2 | 2880900.55 | -573601.21 | DOWN | 0.2486 | 121 | Low | 612453.26 | 0.275 | 2 | 1062183.74 | 2 | 1.52 | 1.28
P005 | Materials | SUP030 | 2025-04 | 2024-12-31 | 2004312.31 | 1674637 | -329675.31 | 329675.31 | 1 | 2025-04-28 | 3 | 2307299.34 | -302987.03 | DOWN | 0.1512 | 118 | Low | 607924.77 | 0.284 | 0 | 1066712.23 | 2 | 1.52 | 1.28
P005 | Materials | SUP030 | 2025-04 | 2025-02-16 | 1866983.84 | 1674637 | -192346.84 | 192346.84 | 0 | 2025-04-28 | 4 | 2004312.31 | -137328.47 | DOWN | 0.0736 | 71 | Low | 725339.45 | 0.414 | 4 | 949297.55 | 2 | 1.52 | 1.28
P005 | Materials | SUP030 | 2025-04 | 2025-03-16 | 1778707.36 | 1674637 | -104070.36 | 104070.36 | 0 | 2025-04-28 | 5 | 1866983.84 | -88276.48 | DOWN | 0.0496 | 43 | Medium | 845349.61 | 0.492 | 1 | 829287.39 | 2 | 1.52 | 1.28
P005 | Software | SUP030 | 2025-05 | 2025-01-25 | 1240988.06 | 743820 | -497168.06 | 497168.06 | 1 | 2025-05-28 | 1 |  |  |  |  | 123 | Low | 374985.26 | 0.283 | 3 | 368834.74 | 6 | 1.12 | 1.51
P005 | Software | SUP030 | 2025-05 | 2025-02-07 | 1014895.24 | 743820 | -271075.24 | 271075.24 | 1 | 2025-05-28 | 2 | 1240988.06 | -226092.82 | DOWN | 0.2228 | 110 | Low | 335344.81 | 0.32 | 2 | 408475.19 | 6 | 1.12 | 1.51
P005 | Software | SUP030 | 2025-05 | 2025-03-21 | 907723.12 | 743820 | -163903.12 | 163903.12 | 1 | 2025-05-28 | 3 | 1014895.24 | -107172.12 | DOWN | 0.1181 | 68 | Low | 417096.82 | 0.443 | 3 | 326723.18 | 6 | 1.12 | 1.51
P005 | Software | SUP030 | 2025-05 | 2025-04-01 | 832809.9 | 743820 | -88989.9 | 88989.9 | 0 | 2025-05-28 | 4 | 907723.12 | -74913.22 | DOWN | 0.09 | 57 | Medium | 420354.09 | 0.475 | 1 | 323465.91 | 6 | 1.12 | 1.51
P005 | Software | SUP030 | 2025-05 | 2025-04-12 | 788098.68 | 743820 | -44278.68 | 44278.68 | 0 | 2025-05-28 | 5 | 832809.9 | -44711.22 | DOWN | 0.0567 | 46 | Medium | 394670.36 | 0.507 | 7 | 349149.64 | 6 | 1.12 | 1.51
P005 | Materials | SUP030 | 2025-06 | 2025-01-04 | 640274.86 | 401980 | -238294.86 | 238294.86 | 1 | 2025-06-28 | 1 |  |  |  |  | 175 | Low | 83700.37 | 0.131 | 0 | 318279.63 | 7 | 1.1 | 1.21
P005 | Materials | SUP030 | 2025-06 | 2025-02-23 | 532057.35 | 401980 | -130077.35 | 130077.35 | 1 | 2025-06-28 | 2 | 640274.86 | -108217.51 | DOWN | 0.2034 | 125 | Low | 142893.72 | 0.277 | 2 | 259086.28 | 7 | 1.1 | 1.21
P005 | Materials | SUP030 | 2025-06 | 2025-02-27 | 471163.74 | 401980 | -69183.74 | 69183.74 | 0 | 2025-06-28 | 3 | 532057.35 | -60893.61 | DOWN | 0.1292 | 121 | Low | 133702.79 | 0.289 | 2 | 268277.21 | 7 | 1.1 | 1.21
P005 | Materials | SUP030 | 2025-06 | 2025-04-24 | 437739.07 | 401980 | -35759.07 | 35759.07 | 0 | 2025-06-28 | 4 | 471163.74 | -33424.67 | DOWN | 0.0764 | 65 | Low | 184192.27 | 0.453 | 2 | 217787.73 | 7 | 1.1 | 1.21
P005 | Logistics | SUP030 | 2025-07 | 2025-03-10 | 606293.07 | 294827 | -311466.07 | 311466.07 | 1 | 2025-07-28 | 1 |  |  |  |  | 140 | Low | 148885.72 | 0.231 | 1 | 145941.28 | 1 | 1.18 | 1.15
P005 | Logistics | SUP030 | 2025-07 | 2025-03-14 | 456310.38 | 294827 | -161483.38 | 161483.38 | 1 | 2025-07-28 | 2 | 606293.07 | -149982.69 | DOWN | 0.3287 | 136 | Low | 105881.54 | 0.243 | 1 | 188945.46 | 1 | 1.18 | 1.15
P005 | Logistics | SUP030 | 2025-07 | 2025-03-31 | 380556.55 | 294827 | -85729.55 | 85729.55 | 1 | 2025-07-28 | 3 | 456310.38 | -75753.83 | DOWN | 0.1991 | 119 | Low | 111553.51 | 0.292 | 4 | 183273.49 | 1 | 1.18 | 1.15
P005 | Materials | SUP030 | 2025-08 | 2025-04-12 | 1834261.57 | 1238412 | -595849.57 | 595849.57 | 1 | 2025-08-28 | 1 |  |  |  |  | 138 | Low | 379574.47 | 0.223 | 2 | 858837.53 | 8 | 1.7 | 1.32
P005 | Materials | SUP030 | 2025-08 | 2025-05-04 | 1535193.53 | 1238412 | -296781.53 | 296781.53 | 1 | 2025-08-28 | 2 | 1834261.57 | -299068.04 | DOWN | 0.1948 | 116 | Low | 430739.8 | 0.283 | 3 | 807672.2 | 8 | 1.7 | 1.32
P005 | Materials | SUP030 | 2025-08 | 2025-05-09 | 1406919 | 1238412 | -168507 | 168507 | 0 | 2025-08-28 | 3 | 1535193.53 | -128274.53 | DOWN | 0.0912 | 111 | Low | 417048.86 | 0.297 | 3 | 821363.14 | 8 | 1.7 | 1.32
P005 | Materials | SUP030 | 2025-08 | 2025-07-01 | 1331039.6 | 1238412 | -92627.6 | 92627.6 | 0 | 2025-08-28 | 4 | 1406919 | -75879.4 | DOWN | 0.057 | 58 | Low | 609660.73 | 0.442 | 4 | 628751.27 | 8 | 1.7 | 1.32
P005 | Materials | SUP030 | 2025-08 | 2025-07-19 | 1301290.11 | 1238412 | -62878.11 | 62878.11 | 0 | 2025-08-28 | 5 | 1331039.6 | -29749.49 | DOWN | 0.0229 | 40 | Medium | 674593.02 | 0.491 | 5 | 563818.98 | 8 | 1.7 | 1.32
P005 | Logistics | SUP030 | 2025-09 | 2025-05-17 | 3567738.41 | 1810612 | -1757126.41 | 1757126.41 | 1 | 2025-09-28 | 1 |  |  |  |  | 134 | Low | 899618.21 | 0.254 | 0 | 910993.79 | 0 | 0.5 | 0.8
P005 | Logistics | SUP030 | 2025-09 | 2025-06-17 | 2708901.89 | 1810612 | -898289.89 | 898289.89 | 1 | 2025-09-28 | 2 | 3567738.41 | -858836.52 | DOWN | 0.317 | 103 | Low | 898599.47 | 0.346 | 2 | 912012.53 | 0 | 0.5 | 0.8
P005 | Logistics | SUP030 | 2025-09 | 2025-07-19 | 2356266.72 | 1810612 | -545654.72 | 545654.72 | 1 | 2025-09-28 | 3 | 2708901.89 | -352635.17 | DOWN | 0.1497 | 71 | Low | 1119352.39 | 0.44 | 5 | 691259.61 | 0 | 0.5 | 0.8
P005 | Logistics | SUP030 | 2025-09 | 2025-07-31 | 2134969.34 | 1810612 | -324357.34 | 324357.34 | 1 | 2025-09-28 | 4 | 2356266.72 | -221297.38 | DOWN | 0.1037 | 59 | Medium | 981730.12 | 0.476 | 4 | 828881.88 | 0 | 0.5 | 0.8
P005 | Logistics | SUP030 | 2025-09 | 2025-08-12 | 1969262.21 | 1810612 | -158650.21 | 158650.21 | 0 | 2025-09-28 | 5 | 2134969.34 | -165707.13 | DOWN | 0.0841 | 47 | Medium | 970522.78 | 0.511 | 5 | 840089.22 | 0 | 0.5 | 0.8
P005 | Logistics | SUP030 | 2025-09 | 2025-08-16 | 1884253.53 | 1810612 | -73641.53 | 73641.53 | 0 | 2025-09-28 | 6 | 1969262.21 | -85008.68 | DOWN | 0.0451 | 43 | Medium | 970609.13 | 0.523 | 0 | 840002.87 | 0 | 0.5 | 0.8
P005 | Software | SUP030 | 2025-10 | 2025-06-09 | 3349736.92 | 1873696 | -1476040.92 | 1476040.92 | 1 | 2025-10-28 | 1 |  |  |  |  | 141 | Low | 811858.78 | 0.229 | 0 | 1061837.22 | 4 | 1.15 | 0.8
P005 | Software | SUP030 | 2025-10 | 2025-06-21 | 2685740.04 | 1873696 | -812044.04 | 812044.04 | 1 | 2025-10-28 | 2 | 3349736.92 | -663996.88 | DOWN | 0.2472 | 129 | Low | 657524.73 | 0.264 | 2 | 1216171.27 | 4 | 1.15 | 0.8
P005 | Software | SUP030 | 2025-10 | 2025-07-02 | 2338040.72 | 1873696 | -464344.72 | 464344.72 | 1 | 2025-10-28 | 3 | 2685740.04 | -347699.32 | DOWN | 0.1487 | 118 | Low | 659778.31 | 0.296 | 1 | 1213917.69 | 4 | 1.15 | 0.8
P005 | Software | SUP030 | 2025-10 | 2025-09-21 | 2134544.05 | 1873696 | -260848.05 | 260848.05 | 0 | 2025-10-28 | 4 | 2338040.72 | -203496.67 | DOWN | 0.0953 | 37 | Medium | 1195174.83 | 0.531 | 2 | 678521.17 | 4 | 1.15 | 0.8
P005 | Software | SUP030 | 2025-10 | 2025-10-14 | 1999145.19 | 1873696 | -125449.19 | 125449.19 | 0 | 2025-10-28 | 5 | 2134544.05 | -135398.86 | DOWN | 0.0677 | 14 | Medium | 1186434.26 | 0.598 | 2 | 687261.74 | 4 | 1.15 | 0.8
P005 | Electronics | SUP030 | 2025-11 | 2025-08-12 | 482398.41 | 262699 | -219699.41 | 219699.41 | 1 | 2025-11-28 | 1 |  |  |  |  | 108 | Low | 152132.62 | 0.318 | 0 | 110566.38 | 4 | 1.35 | 1.5
P005 | Electronics | SUP030 | 2025-11 | 2025-10-27 | 384846.52 | 262699 | -122147.52 | 122147.52 | 1 | 2025-11-28 | 2 | 482398.41 | -97551.89 | DOWN | 0.2535 | 32 | Low | 216372.26 | 0.533 | 6 | 46326.74 | 4 | 1.35 | 1.5
P005 | Electronics | SUP030 | 2025-11 | 2025-11-14 | 325406.72 | 262699 | -62707.72 | 62707.72 | 1 | 2025-11-28 | 3 | 384846.52 | -59439.8 | DOWN | 0.1827 | 14 | Low | 203917.76 | 0.584 | 3 | 58781.24 | 4 | 1.35 | 1.5
P005 | Mechanical | SUP030 | 2025-12 | 2025-07-29 | 2863623.3 | 1733582 | -1130041.3 | 1130041.3 | 1 | 2025-12-28 | 1 |  |  |  |  | 152 | Low | 575325.2 | 0.201 | 1 | 1158256.8 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP030 | 2025-12 | 2025-07-30 | 2356142.66 | 1733582 | -622560.66 | 622560.66 | 1 | 2025-12-28 | 2 | 2863623.3 | -507480.64 | DOWN | 0.2154 | 151 | Low | 498998.63 | 0.204 | 3 | 1234583.37 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP030 | 2025-12 | 2025-08-19 | 2064957.81 | 1733582 | -331375.81 | 331375.81 | 1 | 2025-12-28 | 3 | 2356142.66 | -291184.85 | DOWN | 0.141 | 131 | Low | 541453.13 | 0.263 | 1 | 1192128.87 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP030 | 2025-12 | 2025-08-20 | 1921650.09 | 1733582 | -188068.09 | 188068.09 | 0 | 2025-12-28 | 4 | 2064957.81 | -143307.72 | DOWN | 0.0746 | 130 | Low | 474747.84 | 0.266 | 1 | 1258834.16 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP030 | 2025-12 | 2025-12-01 | 1828286.49 | 1733582 | -94704.49 | 94704.49 | 0 | 2025-12-28 | 5 | 1921650.09 | -93363.6 | DOWN | 0.0511 | 27 | Medium | 1047104.46 | 0.57 | 5 | 686477.54 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP030 | 2025-12 | 2025-12-17 | 1787515.68 | 1733582 | -53933.68 | 53933.68 | 0 | 2025-12-28 | 6 | 1828286.49 | -40770.81 | DOWN | 0.0228 | 11 | Medium | 1097829.79 | 0.617 | 5 | 635752.21 | 7 | 0.73 | 1.27
P005 | Services | SUP015 | 2025-01 | 2024-08-13 | 2813120.11 | 1825937 | -987183.11 | 987183.11 | 1 | 2025-01-28 | 1 |  |  |  |  | 168 | Low | 465603.34 | 0.175 | 0 | 1360333.66 | 8 | 1.44 | 1.07
P005 | Services | SUP015 | 2025-01 | 2024-09-27 | 2225184.49 | 1825937 | -399247.49 | 399247.49 | 1 | 2025-01-28 | 2 | 2813120.11 | -587935.62 | DOWN | 0.2642 | 123 | Low | 750521.99 | 0.327 | 0 | 1075415.01 | 8 | 1.44 | 1.07
P005 | Services | SUP015 | 2025-01 | 2024-10-09 | 2004117.39 | 1825937 | -178180.39 | 178180.39 | 0 | 2025-01-28 | 3 | 2225184.49 | -221067.1 | DOWN | 0.1103 | 111 | Low | 702999.11 | 0.367 | 1 | 1122937.89 | 8 | 1.44 | 1.07
P005 | Services | SUP015 | 2025-01 | 2024-10-28 | 1907842.65 | 1825937 | -81905.65 | 81905.65 | 0 | 2025-01-28 | 4 | 2004117.39 | -96274.74 | DOWN | 0.0505 | 92 | Low | 821921.03 | 0.431 | 4 | 1004015.97 | 8 | 1.44 | 1.07
P005 | Services | SUP015 | 2025-01 | 2024-11-18 | 1893531.7 | 1825937 | -67594.7 | 67594.7 | 0 | 2025-01-28 | 5 | 1907842.65 | -14310.95 | DOWN | 0.0076 | 71 | Low | 925270.06 | 0.502 | 0 | 900666.94 | 8 | 1.44 | 1.07
P005 | Services | SUP015 | 2025-01 | 2024-12-19 | 1858754.66 | 1825937 | -32817.66 | 32817.66 | 0 | 2025-01-28 | 6 | 1893531.7 | -34777.04 | DOWN | 0.0187 | 40 | Medium | 1191206.86 | 0.606 | 6 | 634730.14 | 8 | 1.44 | 1.07
P005 | Materials | SUP015 | 2025-02 | 2024-11-22 | 618201.57 | 449230 | -168971.57 | 168971.57 | 1 | 2025-02-28 | 1 |  |  |  |  | 98 | Low | 230875.98 | 0.405 | 6 | 218354.02 | 7 | 1.56 | 1.03
P005 | Materials | SUP015 | 2025-02 | 2024-12-27 | 520990.07 | 449230 | -71760.07 | 71760.07 | 0 | 2025-02-28 | 2 | 618201.57 | -97211.5 | DOWN | 0.1866 | 63 | Low | 271536.46 | 0.522 | 4 | 177693.54 | 7 | 1.56 | 1.03
P005 | Materials | SUP015 | 2025-02 | 2025-01-31 | 477810.96 | 449230 | -28580.96 | 28580.96 | 0 | 2025-02-28 | 3 | 520990.07 | -43179.11 | DOWN | 0.0904 | 28 | Medium | 322449.07 | 0.638 | 4 | 126780.93 | 7 | 1.56 | 1.03
P005 | Software | SUP015 | 2025-03 | 2024-12-21 | 2701954.58 | 1763037 | -938917.58 | 938917.58 | 1 | 2025-03-28 | 1 |  |  |  |  | 97 | Low | 1260585.59 | 0.436 | 6 | 502451.41 | 0 | 0.76 | 1.01
P005 | Software | SUP015 | 2025-03 | 2025-01-16 | 2193459.63 | 1763037 | -430422.63 | 430422.63 | 1 | 2025-03-28 | 2 | 2701954.58 | -508494.95 | DOWN | 0.2318 | 71 | Low | 1186463.97 | 0.528 | 4 | 576573.03 | 0 | 0.76 | 1.01
P005 | Software | SUP015 | 2025-03 | 2025-02-02 | 1929849.9 | 1763037 | -166812.9 | 166812.9 | 0 | 2025-03-28 | 3 | 2193459.63 | -263609.73 | DOWN | 0.1366 | 54 | Low | 1190404.51 | 0.589 | 4 | 572632.49 | 0 | 0.76 | 1.01
P005 | Software | SUP015 | 2025-03 | 2025-02-26 | 1807803.65 | 1763037 | -44766.65 | 44766.65 | 0 | 2025-03-28 | 4 | 1929849.9 | -122046.25 | DOWN | 0.0675 | 30 | Medium | 1130866.65 | 0.674 | 3 | 632170.35 | 0 | 0.76 | 1.01
P005 | Software | SUP015 | 2025-04 | 2024-11-18 | 2089329.06 | 1377514 | -711815.06 | 711815.06 | 1 | 2025-04-28 | 1 |  |  |  |  | 161 | Low | 439844.54 | 0.197 | 0 | 937669.46 | 2 | 1.52 | 1.28
P005 | Software | SUP015 | 2025-04 | 2024-12-30 | 1700776.47 | 1377514 | -323262.47 | 323262.47 | 1 | 2025-04-28 | 2 | 2089329.06 | -388552.59 | DOWN | 0.2285 | 119 | Low | 581570.68 | 0.337 | 2 | 795943.32 | 2 | 1.52 | 1.28
P005 | Software | SUP015 | 2025-04 | 2025-01-18 | 1504262.45 | 1377514 | -126748.45 | 126748.45 | 0 | 2025-04-28 | 3 | 1700776.47 | -196514.02 | DOWN | 0.1306 | 100 | Low | 566897.5 | 0.4 | 0 | 810616.5 | 2 | 1.52 | 1.28
P005 | Software | SUP015 | 2025-04 | 2025-02-16 | 1397549.96 | 1377514 | -20035.96 | 20035.96 | 0 | 2025-04-28 | 4 | 1504262.45 | -106712.49 | DOWN | 0.0764 | 71 | Low | 735404.52 | 0.497 | 0 | 642109.48 | 2 | 1.52 | 1.28
P005 | Logistics | SUP015 | 2025-05 | 2024-12-10 | 692491.33 | 441717 | -250774.33 | 250774.33 | 1 | 2025-05-28 | 1 |  |  |  |  | 169 | Low | 128937.06 | 0.178 | 2 | 312779.94 | 6 | 1.12 | 1.51
P005 | Logistics | SUP015 | 2025-05 | 2025-01-23 | 541179.76 | 441717 | -99462.76 | 99462.76 | 1 | 2025-05-28 | 2 | 692491.33 | -151311.57 | DOWN | 0.2796 | 125 | Low | 166934.49 | 0.332 | 4 | 274782.51 | 6 | 1.12 | 1.51
P005 | Logistics | SUP015 | 2025-05 | 2025-01-30 | 494231.44 | 441717 | -52514.44 | 52514.44 | 0 | 2025-05-28 | 3 | 541179.76 | -46948.32 | DOWN | 0.095 | 118 | Low | 165666.04 | 0.357 | 8 | 276050.96 | 6 | 1.12 | 1.51
P005 | Logistics | SUP015 | 2025-05 | 2025-04-02 | 458111.57 | 441717 | -16394.57 | 16394.57 | 0 | 2025-05-28 | 4 | 494231.44 | -36119.87 | DOWN | 0.0788 | 56 | Medium | 247229.36 | 0.573 | 4 | 194487.64 | 6 | 1.12 | 1.51
P005 | Logistics | SUP015 | 2025-05 | 2025-04-05 | 451942.51 | 441717 | -10225.51 | 10225.51 | 0 | 2025-05-28 | 5 | 458111.57 | -6169.06 | DOWN | 0.0137 | 53 | Medium | 252438.16 | 0.584 | 0 | 189278.84 | 6 | 1.12 | 1.51
P005 | Logistics | SUP015 | 2025-05 | 2025-04-10 | 453046.67 | 441717 | -11329.67 | 11329.67 | 0 | 2025-05-28 | 6 | 451942.51 | 1104.16 | UP | 0.0024 | 48 | Medium | 253555.54 | 0.601 | 6 | 188161.46 | 6 | 1.12 | 1.51
P005 | Software | SUP015 | 2025-06 | 2025-01-27 | 1412965.1 | 884200 | -528765.1 | 528765.1 | 1 | 2025-06-28 | 1 |  |  |  |  | 152 | Low | 352676.16 | 0.238 | 2 | 531523.84 | 7 | 1.1 | 1.21
P005 | Software | SUP015 | 2025-06 | 2025-02-23 | 1105491.78 | 884200 | -221291.78 | 221291.78 | 1 | 2025-06-28 | 2 | 1412965.1 | -307473.32 | DOWN | 0.2781 | 125 | Low | 345927.35 | 0.333 | 1 | 538272.65 | 7 | 1.1 | 1.21
P005 | Software | SUP015 | 2025-06 | 2025-03-08 | 981313.9 | 884200 | -97113.9 | 97113.9 | 0 | 2025-06-28 | 3 | 1105491.78 | -124177.88 | DOWN | 0.1265 | 112 | Low | 346936.06 | 0.378 | 7 | 537263.94 | 7 | 1.1 | 1.21
P005 | Software | SUP015 | 2025-06 | 2025-05-11 | 923366.78 | 884200 | -39166.78 | 39166.78 | 0 | 2025-06-28 | 4 | 981313.9 | -57947.12 | DOWN | 0.0628 | 48 | Medium | 595907.85 | 0.603 | 6 | 288292.15 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP015 | 2025-07 | 2025-03-30 | 1857228.2 | 1581478 | -275750.2 | 275750.2 | 0 | 2025-07-28 | 1 |  |  |  |  | 120 | Low | 657477.94 | 0.347 | 2 | 924000.06 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP015 | 2025-07 | 2025-05-04 | 1709729.95 | 1581478 | -128251.95 | 128251.95 | 0 | 2025-07-28 | 2 | 1857228.2 | -147498.25 | DOWN | 0.0863 | 85 | Low | 789719.99 | 0.469 | 5 | 791758.01 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP015 | 2025-07 | 2025-05-21 | 1638984.08 | 1581478 | -57506.08 | 57506.08 | 0 | 2025-07-28 | 3 | 1709729.95 | -70745.87 | DOWN | 0.0432 | 68 | Low | 893885.09 | 0.528 | 3 | 687592.91 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP015 | 2025-07 | 2025-07-07 | 1595469.65 | 1581478 | -13991.65 | 13991.65 | 0 | 2025-07-28 | 4 | 1638984.08 | -43514.43 | DOWN | 0.0273 | 21 | High | 1171156.49 | 0.691 | 7 | 410321.51 | 1 | 1.18 | 1.15
P005 | Logistics | SUP015 | 2025-08 | 2025-03-11 | 2721388.42 | 1718063 | -1003325.42 | 1003325.42 | 1 | 2025-08-28 | 1 |  |  |  |  | 170 | Low | 423550.09 | 0.164 | 1 | 1294512.91 | 8 | 1.7 | 1.32
P005 | Logistics | SUP015 | 2025-08 | 2025-04-17 | 2256025.76 | 1718063 | -537962.76 | 537962.76 | 1 | 2025-08-28 | 2 | 2721388.42 | -465362.66 | DOWN | 0.2063 | 133 | Low | 623321.72 | 0.285 | 4 | 1094741.28 | 8 | 1.7 | 1.32
P005 | Logistics | SUP015 | 2025-08 | 2025-05-04 | 1987412.79 | 1718063 | -269349.79 | 269349.79 | 0 | 2025-08-28 | 3 | 2256025.76 | -268612.97 | DOWN | 0.1352 | 116 | Low | 692907.17 | 0.34 | 3 | 1025155.83 | 8 | 1.7 | 1.32
P005 | Logistics | SUP015 | 2025-08 | 2025-05-12 | 1809163.46 | 1718063 | -91100.46 | 91100.46 | 0 | 2025-08-28 | 4 | 1987412.79 | -178249.33 | DOWN | 0.0985 | 108 | Low | 621047.92 | 0.366 | 2 | 1097015.08 | 8 | 1.7 | 1.32
P005 | Logistics | SUP015 | 2025-08 | 2025-07-19 | 1786940.23 | 1718063 | -68877.23 | 68877.23 | 0 | 2025-08-28 | 5 | 1809163.46 | -22223.23 | DOWN | 0.0124 | 40 | Medium | 1004807.49 | 0.589 | 4 | 713255.51 | 8 | 1.7 | 1.32
P005 | Materials | SUP015 | 2025-09 | 2025-04-27 | 2314288.65 | 1609182 | -705106.65 | 705106.65 | 1 | 2025-09-28 | 1 |  |  |  |  | 154 | Low | 542163.44 | 0.234 | 1 | 1067018.56 | 0 | 0.5 | 0.8
P005 | Materials | SUP015 | 2025-09 | 2025-06-08 | 1911364.58 | 1609182 | -302182.58 | 302182.58 | 1 | 2025-09-28 | 2 | 2314288.65 | -402924.07 | DOWN | 0.2108 | 112 | Low | 680997.83 | 0.383 | 2 | 928184.17 | 0 | 0.5 | 0.8
P005 | Materials | SUP015 | 2025-09 | 2025-06-17 | 1746495.66 | 1609182 | -137313.66 | 137313.66 | 0 | 2025-09-28 | 3 | 1911364.58 | -164868.92 | DOWN | 0.0944 | 103 | Low | 744921.01 | 0.415 | 3 | 864260.99 | 0 | 0.5 | 0.8
P005 | Materials | SUP015 | 2025-09 | 2025-08-12 | 1662004.76 | 1609182 | -52822.76 | 52822.76 | 0 | 2025-09-28 | 4 | 1746495.66 | -84490.9 | DOWN | 0.0508 | 47 | Medium | 1045757.42 | 0.613 | 5 | 563424.58 | 0 | 0.5 | 0.8
P005 | Materials | SUP015 | 2025-09 | 2025-08-27 | 1629549.85 | 1609182 | -20367.85 | 20367.85 | 0 | 2025-09-28 | 5 | 1662004.76 | -32454.91 | DOWN | 0.0199 | 32 | Medium | 1080371.29 | 0.667 | 6 | 528810.71 | 0 | 0.5 | 0.8
P005 | Materials | SUP015 | 2025-09 | 2025-09-03 | 1604675.74 | 1609182 | 4506.26 | 4506.26 | 0 | 2025-09-28 | 6 | 1629549.85 | -24874.11 | DOWN | 0.0155 | 25 | High | 1062714.83 | 0.691 | 7 | 546467.17 | 0 | 0.5 | 0.8
P005 | Software | SUP015 | 2025-10 | 2025-05-01 | 418516.13 | 251178 | -167338.13 | 167338.13 | 1 | 2025-10-28 | 1 |  |  |  |  | 180 | Low | 67685.87 | 0.153 | 0 | 183492.13 | 4 | 1.15 | 0.8
P005 | Software | SUP015 | 2025-10 | 2025-05-21 | 327149.48 | 251178 | -75971.48 | 75971.48 | 1 | 2025-10-28 | 2 | 418516.13 | -91366.65 | DOWN | 0.2793 | 160 | Low | 72843.36 | 0.209 | 0 | 178334.64 | 4 | 1.15 | 0.8
P005 | Software | SUP015 | 2025-10 | 2025-10-13 | 278769.9 | 251178 | -27591.9 | 27591.9 | 0 | 2025-10-28 | 3 | 327149.48 | -48379.58 | DOWN | 0.1735 | 15 | Low | 213977.44 | 0.714 | 1 | 37200.56 | 4 | 1.15 | 0.8
P005 | Logistics | SUP015 | 2025-11 | 2025-06-04 | 1418577.64 | 810432 | -608145.64 | 608145.64 | 1 | 2025-11-28 | 1 |  |  |  |  | 177 | Low | 208208.4 | 0.15 | 2 | 602223.6 | 4 | 1.35 | 1.5
P005 | Logistics | SUP015 | 2025-11 | 2025-06-14 | 1081677.88 | 810432 | -271245.88 | 271245.88 | 1 | 2025-11-28 | 2 | 1418577.64 | -336899.76 | DOWN | 0.3115 | 167 | Low | 195322.84 | 0.18 | 2 | 615109.16 | 4 | 1.35 | 1.5
P005 | Logistics | SUP015 | 2025-11 | 2025-07-19 | 924200.37 | 810432 | -113768.37 | 113768.37 | 0 | 2025-11-28 | 3 | 1081677.88 | -157477.51 | DOWN | 0.1704 | 132 | Low | 274983.69 | 0.299 | 3 | 535448.31 | 4 | 1.35 | 1.5
P005 | Logistics | SUP015 | 2025-11 | 2025-08-20 | 883311.47 | 810432 | -72879.47 | 72879.47 | 0 | 2025-11-28 | 4 | 924200.37 | -40888.9 | DOWN | 0.0463 | 100 | Low | 381063.96 | 0.408 | 3 | 429368.04 | 4 | 1.35 | 1.5
P005 | Logistics | SUP015 | 2025-11 | 2025-10-29 | 853026.9 | 810432 | -42594.9 | 42594.9 | 0 | 2025-11-28 | 5 | 883311.47 | -30284.57 | DOWN | 0.0355 | 30 | Medium | 524815.59 | 0.646 | 7 | 285616.41 | 4 | 1.35 | 1.5
P005 | Mechanical | SUP015 | 2025-12 | 2025-07-27 | 3347283.65 | 2558897 | -788386.65 | 788386.65 | 1 | 2025-12-28 | 1 |  |  |  |  | 154 | Low | 821190.18 | 0.234 | 0 | 1737706.82 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP015 | 2025-12 | 2025-10-02 | 2904825.9 | 2558897 | -345928.9 | 345928.9 | 0 | 2025-12-28 | 2 | 3347283.65 | -442457.75 | DOWN | 0.1523 | 87 | Low | 1317176.52 | 0.472 | 4 | 1241720.48 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP015 | 2025-12 | 2025-10-05 | 2714134.34 | 2558897 | -155237.34 | 155237.34 | 0 | 2025-12-28 | 3 | 2904825.9 | -190691.56 | DOWN | 0.0703 | 84 | Low | 1378062.19 | 0.482 | 2 | 1180834.81 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP015 | 2025-12 | 2025-10-20 | 2613037.96 | 2558897 | -54140.96 | 54140.96 | 0 | 2025-12-28 | 4 | 2714134.34 | -101096.38 | DOWN | 0.0387 | 69 | Low | 1296985.7 | 0.535 | 0 | 1261911.3 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP015 | 2025-12 | 2025-11-16 | 2581055.65 | 2558897 | -22158.65 | 22158.65 | 0 | 2025-12-28 | 5 | 2613037.96 | -31982.31 | DOWN | 0.0124 | 42 | Medium | 1608171.51 | 0.631 | 0 | 950725.49 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP015 | 2025-12 | 2025-12-06 | 2560502.11 | 2558897 | -1605.11 | 1605.11 | 0 | 2025-12-28 | 6 | 2581055.65 | -20553.54 | DOWN | 0.008 | 22 | High | 1913203.32 | 0.702 | 8 | 645693.68 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP041 | 2025-01 | 2024-08-23 | 884940.51 | 640455 | -244485.51 | 244485.51 | 1 | 2025-01-28 | 1 |  |  |  |  | 158 | Low | 132035.71 | 0.147 | 2 | 508419.29 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP041 | 2025-01 | 2024-09-05 | 782418.53 | 640455 | -141963.53 | 141963.53 | 1 | 2025-01-28 | 2 | 884940.51 | -102521.98 | DOWN | 0.131 | 145 | Low | 134877.03 | 0.178 | 0 | 505577.97 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP041 | 2025-01 | 2024-09-10 | 726356.84 | 640455 | -85901.84 | 85901.84 | 0 | 2025-01-28 | 3 | 782418.53 | -56061.69 | DOWN | 0.0772 | 140 | Low | 133368.33 | 0.19 | 2 | 507086.67 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP041 | 2025-01 | 2024-09-14 | 691651.13 | 640455 | -51196.13 | 51196.13 | 0 | 2025-01-28 | 4 | 726356.84 | -34705.71 | DOWN | 0.0502 | 136 | Low | 127594.95 | 0.199 | 1 | 512860.05 | 8 | 1.44 | 1.07
P005 | Services | SUP041 | 2025-02 | 2024-10-10 | 3327029.92 | 2061135 | -1265894.92 | 1265894.92 | 1 | 2025-02-28 | 1 |  |  |  |  | 141 | Low | 626708.92 | 0.185 | 0 | 1434426.08 | 7 | 1.56 | 1.03
P005 | Services | SUP041 | 2025-02 | 2024-11-02 | 2802534.15 | 2061135 | -741399.15 | 741399.15 | 1 | 2025-02-28 | 2 | 3327029.92 | -524495.77 | DOWN | 0.1872 | 118 | Low | 711214.53 | 0.239 | 1 | 1349920.47 | 7 | 1.56 | 1.03
P005 | Services | SUP041 | 2025-02 | 2024-11-06 | 2526855.32 | 2061135 | -465720.32 | 465720.32 | 1 | 2025-02-28 | 3 | 2802534.15 | -275678.83 | DOWN | 0.1091 | 114 | Low | 654059.17 | 0.248 | 3 | 1407075.83 | 7 | 1.56 | 1.03
P005 | Services | SUP041 | 2025-02 | 2024-12-13 | 2354254.07 | 2061135 | -293119.07 | 293119.07 | 0 | 2025-02-28 | 4 | 2526855.32 | -172601.25 | DOWN | 0.0733 | 77 | Low | 831508 | 0.335 | 3 | 1229627 | 7 | 1.56 | 1.03
P005 | Services | SUP041 | 2025-02 | 2025-01-03 | 2227202.38 | 2061135 | -166067.38 | 166067.38 | 0 | 2025-02-28 | 5 | 2354254.07 | -127051.69 | DOWN | 0.057 | 56 | Low | 805625.82 | 0.384 | 4 | 1255509.18 | 7 | 1.56 | 1.03
P005 | Services | SUP041 | 2025-02 | 2025-01-10 | 2181096.58 | 2061135 | -119961.58 | 119961.58 | 0 | 2025-02-28 | 6 | 2227202.38 | -46105.8 | DOWN | 0.0211 | 49 | Low | 874942.54 | 0.401 | 1 | 1186192.46 | 7 | 1.56 | 1.03
P005 | Materials | SUP041 | 2025-03 | 2024-11-22 | 775953.58 | 467631 | -308322.58 | 308322.58 | 1 | 2025-03-28 | 1 |  |  |  |  | 126 | Low | 186437.42 | 0.235 | 0 | 281193.58 | 0 | 0.76 | 1.01
P005 | Materials | SUP041 | 2025-03 | 2024-11-28 | 648426.58 | 467631 | -180795.58 | 180795.58 | 1 | 2025-03-28 | 2 | 775953.58 | -127527 | DOWN | 0.1967 | 120 | Low | 154992.61 | 0.25 | 5 | 312638.39 | 0 | 0.76 | 1.01
P005 | Materials | SUP041 | 2025-03 | 2025-03-01 | 580988.1 | 467631 | -113357.1 | 113357.1 | 1 | 2025-03-28 | 3 | 648426.58 | -67438.48 | DOWN | 0.1161 | 27 | Medium | 265973.05 | 0.483 | 2 | 201657.95 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP041 | 2025-04 | 2024-12-18 | 2332519.77 | 1715353 | -617166.77 | 617166.77 | 1 | 2025-04-28 | 1 |  |  |  |  | 131 | Low | 517983.85 | 0.209 | 2 | 1197369.15 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP041 | 2025-04 | 2025-03-07 | 2103203.48 | 1715353 | -387850.48 | 387850.48 | 1 | 2025-04-28 | 2 | 2332519.77 | -229316.29 | DOWN | 0.109 | 52 | Low | 838799.73 | 0.395 | 7 | 876553.27 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP041 | 2025-04 | 2025-03-21 | 1945290.63 | 1715353 | -229937.63 | 229937.63 | 0 | 2025-04-28 | 3 | 2103203.48 | -157912.85 | DOWN | 0.0812 | 38 | Low | 838362.52 | 0.428 | 3 | 876990.48 | 2 | 1.52 | 1.28
P005 | Electronics | SUP041 | 2025-05 | 2024-12-01 | 1789211.18 | 1029001 | -760210.18 | 760210.18 | 1 | 2025-05-28 | 1 |  |  |  |  | 178 | Low | 197082.6 | 0.108 | 1 | 831918.4 | 6 | 1.12 | 1.51
P005 | Electronics | SUP041 | 2025-05 | 2024-12-10 | 1480367.15 | 1029001 | -451366.15 | 451366.15 | 1 | 2025-05-28 | 2 | 1789211.18 | -308844.03 | DOWN | 0.2086 | 169 | Low | 192146.32 | 0.126 | 0 | 836854.68 | 6 | 1.12 | 1.51
P005 | Electronics | SUP041 | 2025-05 | 2025-01-05 | 1288176.46 | 1029001 | -259175.46 | 259175.46 | 1 | 2025-05-28 | 3 | 1480367.15 | -192190.69 | DOWN | 0.1492 | 143 | Low | 232092.46 | 0.19 | 5 | 796908.54 | 6 | 1.12 | 1.51
P005 | Electronics | SUP041 | 2025-05 | 2025-01-15 | 1185073.03 | 1029001 | -156072.03 | 156072.03 | 0 | 2025-05-28 | 4 | 1288176.46 | -103103.43 | DOWN | 0.087 | 133 | Low | 260324.06 | 0.214 | 0 | 768676.94 | 6 | 1.12 | 1.51
P005 | Electronics | SUP041 | 2025-05 | 2025-05-07 | 1121195.94 | 1029001 | -92194.94 | 92194.94 | 0 | 2025-05-28 | 5 | 1185073.03 | -63877.09 | DOWN | 0.057 | 21 | Medium | 524633.92 | 0.49 | 8 | 504367.08 | 6 | 1.12 | 1.51
P005 | Materials | SUP041 | 2025-06 | 2025-01-30 | 1352902.96 | 893287 | -459615.96 | 459615.96 | 1 | 2025-06-28 | 1 |  |  |  |  | 149 | Low | 219520.83 | 0.175 | 2 | 673766.17 | 7 | 1.1 | 1.21
P005 | Materials | SUP041 | 2025-06 | 2025-01-31 | 1172513.41 | 893287 | -279226.41 | 279226.41 | 1 | 2025-06-28 | 2 | 1352902.96 | -180389.55 | DOWN | 0.1538 | 148 | Low | 205088.55 | 0.178 | 0 | 688198.45 | 7 | 1.1 | 1.21
P005 | Materials | SUP041 | 2025-06 | 2025-02-27 | 1067681.1 | 893287 | -174394.1 | 174394.1 | 1 | 2025-06-28 | 3 | 1172513.41 | -104832.31 | DOWN | 0.0982 | 121 | Low | 251272.63 | 0.245 | 0 | 642014.37 | 7 | 1.1 | 1.21
P005 | Materials | SUP041 | 2025-06 | 2025-04-08 | 996491.79 | 893287 | -103204.79 | 103204.79 | 0 | 2025-06-28 | 4 | 1067681.1 | -71189.31 | DOWN | 0.0714 | 81 | Low | 363007.78 | 0.343 | 3 | 530279.22 | 7 | 1.1 | 1.21
P005 | Materials | SUP041 | 2025-06 | 2025-04-29 | 961239.96 | 893287 | -67952.96 | 67952.96 | 0 | 2025-06-28 | 5 | 996491.79 | -35251.83 | DOWN | 0.0367 | 60 | Low | 351557.8 | 0.395 | 2 | 541729.2 | 7 | 1.1 | 1.21
P005 | Electronics | SUP041 | 2025-07 | 2025-02-20 | 2611603.56 | 1856515 | -755088.56 | 755088.56 | 1 | 2025-07-28 | 1 |  |  |  |  | 158 | Low | 384601.5 | 0.152 | 2 | 1471913.5 | 1 | 1.18 | 1.15
P005 | Electronics | SUP041 | 2025-07 | 2025-03-03 | 2282703.76 | 1856515 | -426188.76 | 426188.76 | 1 | 2025-07-28 | 2 | 2611603.56 | -328899.8 | DOWN | 0.1441 | 147 | Low | 412342.93 | 0.179 | 0 | 1444172.07 | 1 | 1.18 | 1.15
P005 | Electronics | SUP041 | 2025-07 | 2025-03-31 | 2095995.56 | 1856515 | -239480.56 | 239480.56 | 0 | 2025-07-28 | 3 | 2282703.76 | -186708.2 | DOWN | 0.0891 | 119 | Low | 507382.78 | 0.247 | 2 | 1349132.22 | 1 | 1.18 | 1.15
P005 | Electronics | SUP041 | 2025-07 | 2025-05-06 | 2002613.5 | 1856515 | -146098.5 | 146098.5 | 0 | 2025-07-28 | 4 | 2095995.56 | -93382.06 | DOWN | 0.0466 | 83 | Low | 710176.54 | 0.335 | 1 | 1146338.46 | 1 | 1.18 | 1.15
P005 | Electronics | SUP041 | 2025-07 | 2025-05-26 | 1953456.8 | 1856515 | -96941.8 | 96941.8 | 0 | 2025-07-28 | 5 | 2002613.5 | -49156.7 | DOWN | 0.0252 | 63 | Low | 806723.8 | 0.384 | 8 | 1049791.2 | 1 | 1.18 | 1.15
P005 | Services | SUP041 | 2025-08 | 2025-03-19 | 1418900.73 | 811993 | -606907.73 | 606907.73 | 1 | 2025-08-28 | 1 |  |  |  |  | 162 | Low | 185776.58 | 0.134 | 1 | 626216.42 | 8 | 1.7 | 1.32
P005 | Services | SUP041 | 2025-08 | 2025-07-04 | 1180822.67 | 811993 | -368829.67 | 368829.67 | 1 | 2025-08-28 | 2 | 1418900.73 | -238078.06 | DOWN | 0.2016 | 55 | Low | 456480.21 | 0.381 | 2 | 355512.79 | 8 | 1.7 | 1.32
P005 | Services | SUP041 | 2025-08 | 2025-07-09 | 1023004.17 | 811993 | -211011.17 | 211011.17 | 1 | 2025-08-28 | 3 | 1180822.67 | -157818.5 | DOWN | 0.1543 | 50 | Low | 373814.3 | 0.392 | 4 | 438178.7 | 8 | 1.7 | 1.32
P005 | Services | SUP041 | 2025-08 | 2025-07-29 | 946513.17 | 811993 | -134520.17 | 134520.17 | 0 | 2025-08-28 | 4 | 1023004.17 | -76491 | DOWN | 0.0808 | 30 | Low | 435288.17 | 0.438 | 4 | 376704.83 | 8 | 1.7 | 1.32
P005 | Services | SUP041 | 2025-08 | 2025-08-02 | 886575.34 | 811993 | -74582.34 | 74582.34 | 0 | 2025-08-28 | 5 | 946513.17 | -59937.83 | DOWN | 0.0676 | 26 | Low | 366046.75 | 0.447 | 5 | 445946.25 | 8 | 1.7 | 1.32
P005 | Services | SUP041 | 2025-09 | 2025-04-11 | 3333087.56 | 1867978 | -1465109.56 | 1465109.56 | 1 | 2025-09-28 | 1 |  |  |  |  | 170 | Low | 405003.63 | 0.125 | 2 | 1462974.37 | 0 | 0.5 | 0.8
P005 | Services | SUP041 | 2025-09 | 2025-08-13 | 2735710.16 | 1867978 | -867732.16 | 867732.16 | 1 | 2025-09-28 | 2 | 3333087.56 | -597377.4 | DOWN | 0.2184 | 46 | Low | 1236899.91 | 0.435 | 6 | 631078.09 | 0 | 0.5 | 0.8
P005 | Services | SUP041 | 2025-09 | 2025-09-01 | 2383594.44 | 1867978 | -515616.44 | 515616.44 | 1 | 2025-09-28 | 3 | 2735710.16 | -352115.72 | DOWN | 0.1477 | 27 | Low | 1066132.18 | 0.483 | 5 | 801845.82 | 0 | 0.5 | 0.8
P005 | Software | SUP041 | 2025-10 | 2025-05-11 | 3864588.93 | 2155175 | -1709413.93 | 1709413.93 | 1 | 2025-10-28 | 1 |  |  |  |  | 170 | Low | 499927.98 | 0.123 | 1 | 1655247.02 | 4 | 1.15 | 0.8
P005 | Software | SUP041 | 2025-10 | 2025-06-19 | 3247297.47 | 2155175 | -1092122.47 | 1092122.47 | 1 | 2025-10-28 | 2 | 3864588.93 | -617291.46 | DOWN | 0.1901 | 131 | Low | 714514.22 | 0.219 | 1 | 1440660.78 | 4 | 1.15 | 0.8
P005 | Software | SUP041 | 2025-10 | 2025-07-09 | 2807281.11 | 2155175 | -652106.11 | 652106.11 | 1 | 2025-10-28 | 3 | 3247297.47 | -440016.36 | DOWN | 0.1567 | 111 | Low | 783263.65 | 0.268 | 0 | 1371911.35 | 4 | 1.15 | 0.8
P005 | Software | SUP041 | 2025-10 | 2025-08-27 | 2511969.58 | 2155175 | -356794.58 | 356794.58 | 0 | 2025-10-28 | 4 | 2807281.11 | -295311.53 | DOWN | 0.1176 | 62 | Low | 1004209.88 | 0.388 | 4 | 1150965.12 | 4 | 1.15 | 0.8
P005 | Software | SUP041 | 2025-10 | 2025-10-10 | 2406905.58 | 2155175 | -251730.58 | 251730.58 | 0 | 2025-10-28 | 5 | 2511969.58 | -105064 | DOWN | 0.0437 | 18 | Medium | 1186813.92 | 0.496 | 4 | 968361.08 | 4 | 1.15 | 0.8
P005 | Materials | SUP041 | 2025-11 | 2025-07-14 | 1295431.5 | 789645 | -505786.5 | 505786.5 | 1 | 2025-11-28 | 1 |  |  |  |  | 137 | Low | 249911.06 | 0.199 | 3 | 539733.94 | 4 | 1.35 | 1.5
P005 | Materials | SUP041 | 2025-11 | 2025-07-28 | 1095840.94 | 789645 | -306195.94 | 306195.94 | 1 | 2025-11-28 | 2 | 1295431.5 | -199590.56 | DOWN | 0.1821 | 123 | Low | 271422.64 | 0.233 | 0 | 518222.36 | 4 | 1.35 | 1.5
P005 | Materials | SUP041 | 2025-11 | 2025-08-28 | 978023.42 | 789645 | -188378.42 | 188378.42 | 1 | 2025-11-28 | 3 | 1095840.94 | -117817.52 | DOWN | 0.1205 | 92 | Low | 308236.94 | 0.307 | 2 | 481408.06 | 4 | 1.35 | 1.5
P005 | Software | SUP041 | 2025-12 | 2025-07-20 | 2751234.12 | 1792037 | -959197.12 | 959197.12 | 1 | 2025-12-28 | 1 |  |  |  |  | 161 | Low | 417939.91 | 0.148 | 2 | 1374097.09 | 7 | 0.73 | 1.27
P005 | Software | SUP041 | 2025-12 | 2025-10-16 | 2338915.33 | 1792037 | -546878.33 | 546878.33 | 1 | 2025-12-28 | 2 | 2751234.12 | -412318.79 | DOWN | 0.1763 | 73 | Low | 834092.38 | 0.368 | 1 | 957944.62 | 7 | 0.73 | 1.27
P005 | Software | SUP041 | 2025-12 | 2025-10-30 | 2152159.57 | 1792037 | -360122.57 | 360122.57 | 1 | 2025-12-28 | 3 | 2338915.33 | -186755.76 | DOWN | 0.0868 | 59 | Low | 814847.25 | 0.403 | 2 | 977189.75 | 7 | 0.73 | 1.27
P005 | Software | SUP041 | 2025-12 | 2025-10-30 | 2028412.27 | 1792037 | -236375.27 | 236375.27 | 0 | 2025-12-28 | 4 | 2152159.57 | -123747.3 | DOWN | 0.061 | 59 | Low | 764215.03 | 0.403 | 4 | 1027821.97 | 7 | 0.73 | 1.27
P005 | Electronics | SUP002 | 2025-01 | 2024-08-03 | 2711453.44 | 1890852 | -820601.44 | 820601.44 | 1 | 2025-01-28 | 1 |  |  |  |  | 178 | Low | 408833.4 | 0.148 | 1 | 1482018.6 | 8 | 1.44 | 1.07
P005 | Electronics | SUP002 | 2025-01 | 2024-11-05 | 2248177.21 | 1890852 | -357325.21 | 357325.21 | 1 | 2025-01-28 | 2 | 2711453.44 | -463276.23 | DOWN | 0.2061 | 84 | Low | 1066246.32 | 0.458 | 2 | 824605.68 | 8 | 1.44 | 1.07
P005 | Electronics | SUP002 | 2025-01 | 2024-12-14 | 2050293.6 | 1890852 | -159441.6 | 159441.6 | 0 | 2025-01-28 | 3 | 2248177.21 | -197883.61 | DOWN | 0.0965 | 45 | Medium | 1259974.47 | 0.589 | 5 | 630877.53 | 8 | 1.44 | 1.07
P005 | Software | SUP002 | 2025-02 | 2024-09-14 | 2302719.29 | 1528735 | -773984.29 | 773984.29 | 1 | 2025-02-28 | 1 |  |  |  |  | 167 | Low | 390885.76 | 0.176 | 0 | 1137849.24 | 7 | 1.56 | 1.03
P005 | Software | SUP002 | 2025-02 | 2024-10-08 | 1847033.64 | 1528735 | -318298.64 | 318298.64 | 1 | 2025-02-28 | 2 | 2302719.29 | -455685.65 | DOWN | 0.2467 | 143 | Low | 473104.03 | 0.256 | 0 | 1055630.97 | 7 | 1.56 | 1.03
P005 | Software | SUP002 | 2025-02 | 2024-11-06 | 1689392.17 | 1528735 | -160657.17 | 160657.17 | 0 | 2025-02-28 | 3 | 1847033.64 | -157641.47 | DOWN | 0.0933 | 114 | Low | 593972.98 | 0.352 | 0 | 934762.02 | 7 | 1.56 | 1.03
P005 | Software | SUP002 | 2025-02 | 2024-11-13 | 1633043.59 | 1528735 | -104308.59 | 104308.59 | 0 | 2025-02-28 | 4 | 1689392.17 | -56348.58 | DOWN | 0.0345 | 107 | Low | 645896.32 | 0.375 | 2 | 882838.68 | 7 | 1.56 | 1.03
P005 | Software | SUP002 | 2025-02 | 2025-01-12 | 1552763.29 | 1528735 | -24028.29 | 24028.29 | 0 | 2025-02-28 | 5 | 1633043.59 | -80280.3 | DOWN | 0.0517 | 47 | Medium | 857744.58 | 0.575 | 1 | 670990.42 | 7 | 1.56 | 1.03
P005 | Services | SUP002 | 2025-03 | 2024-10-14 | 1167753.34 | 792115 | -375638.34 | 375638.34 | 1 | 2025-03-28 | 1 |  |  |  |  | 165 | Low | 224537.8 | 0.195 | 4 | 567577.2 | 0 | 0.76 | 1.01
P005 | Services | SUP002 | 2025-03 | 2024-10-22 | 966143.83 | 792115 | -174028.83 | 174028.83 | 1 | 2025-03-28 | 2 | 1167753.34 | -201609.51 | DOWN | 0.2087 | 157 | Low | 221341.12 | 0.223 | 1 | 570773.88 | 0 | 0.76 | 1.01
P005 | Services | SUP002 | 2025-03 | 2024-10-23 | 857973.99 | 792115 | -65858.99 | 65858.99 | 0 | 2025-03-28 | 3 | 966143.83 | -108169.84 | DOWN | 0.1261 | 156 | Low | 183217.48 | 0.227 | 1 | 608897.52 | 0 | 0.76 | 1.01
P005 | Services | SUP002 | 2025-03 | 2024-12-09 | 828058.49 | 792115 | -35943.49 | 35943.49 | 0 | 2025-03-28 | 4 | 857973.99 | -29915.5 | DOWN | 0.0361 | 109 | Low | 317230.33 | 0.394 | 0 | 474884.67 | 0 | 0.76 | 1.01
P005 | Services | SUP002 | 2025-03 | 2025-01-04 | 814082.05 | 792115 | -21967.05 | 21967.05 | 0 | 2025-03-28 | 5 | 828058.49 | -13976.44 | DOWN | 0.0172 | 83 | Low | 401603.81 | 0.486 | 3 | 390511.19 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP002 | 2025-04 | 2024-12-30 | 1466398.04 | 1086933 | -379465.04 | 379465.04 | 1 | 2025-04-28 | 1 |  |  |  |  | 119 | Low | 528717.71 | 0.337 | 2 | 558215.29 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP002 | 2025-04 | 2025-01-29 | 1267904.96 | 1086933 | -180971.96 | 180971.96 | 0 | 2025-04-28 | 2 | 1466398.04 | -198493.08 | DOWN | 0.1566 | 89 | Low | 597219.03 | 0.437 | 1 | 489713.97 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP002 | 2025-04 | 2025-04-04 | 1166592.05 | 1086933 | -79659.05 | 79659.05 | 0 | 2025-04-28 | 3 | 1267904.96 | -101312.91 | DOWN | 0.0868 | 24 | Medium | 792716.81 | 0.654 | 5 | 294216.19 | 2 | 1.52 | 1.28
P005 | Logistics | SUP002 | 2025-05 | 2024-12-04 | 1314648.83 | 787430 | -527218.83 | 527218.83 | 1 | 2025-05-28 | 1 |  |  |  |  | 175 | Low | 197808.11 | 0.157 | 1 | 589621.89 | 6 | 1.12 | 1.51
P005 | Logistics | SUP002 | 2025-05 | 2025-01-01 | 1023025.88 | 787430 | -235595.88 | 235595.88 | 1 | 2025-05-28 | 2 | 1314648.83 | -291622.95 | DOWN | 0.2851 | 147 | Low | 251932.82 | 0.255 | 1 | 535497.18 | 6 | 1.12 | 1.51
P005 | Logistics | SUP002 | 2025-05 | 2025-03-16 | 905940.9 | 787430 | -118510.9 | 118510.9 | 0 | 2025-05-28 | 3 | 1023025.88 | -117084.98 | DOWN | 0.1292 | 73 | Low | 456768.72 | 0.514 | 5 | 330661.28 | 6 | 1.12 | 1.51
P005 | Software | SUP002 | 2025-06 | 2025-04-07 | 3841557.8 | 2284837 | -1556720.8 | 1556720.8 | 1 | 2025-06-28 | 1 |  |  |  |  | 82 | Low | 1883840.81 | 0.483 | 1 | 400996.19 | 7 | 1.1 | 1.21
P005 | Software | SUP002 | 2025-06 | 2025-04-20 | 2973431.24 | 2284837 | -688594.24 | 688594.24 | 1 | 2025-06-28 | 2 | 3841557.8 | -868126.56 | DOWN | 0.292 | 69 | Low | 1487994.07 | 0.529 | 2 | 796842.93 | 7 | 1.1 | 1.21
P005 | Software | SUP002 | 2025-06 | 2025-04-30 | 2591708.14 | 2284837 | -306871.14 | 306871.14 | 0 | 2025-06-28 | 3 | 2973431.24 | -381723.1 | DOWN | 0.1473 | 59 | Low | 1541986.71 | 0.564 | 4 | 742850.29 | 7 | 1.1 | 1.21
P005 | Software | SUP002 | 2025-06 | 2025-05-02 | 2446098.44 | 2284837 | -161261.44 | 161261.44 | 0 | 2025-06-28 | 4 | 2591708.14 | -145609.7 | DOWN | 0.0595 | 57 | Medium | 1460602.27 | 0.571 | 4 | 824234.73 | 7 | 1.1 | 1.21
P005 | Materials | SUP002 | 2025-07 | 2025-02-16 | 2989577.23 | 2283629 | -705948.23 | 705948.23 | 1 | 2025-07-28 | 1 |  |  |  |  | 162 | Low | 608681.74 | 0.201 | 2 | 1674947.26 | 1 | 1.18 | 1.15
P005 | Materials | SUP002 | 2025-07 | 2025-02-21 | 2621539.56 | 2283629 | -337910.56 | 337910.56 | 0 | 2025-07-28 | 2 | 2989577.23 | -368037.67 | DOWN | 0.1404 | 157 | Low | 573548.32 | 0.219 | 5 | 1710080.68 | 1 | 1.18 | 1.15
P005 | Materials | SUP002 | 2025-07 | 2025-02-21 | 2461192.24 | 2283629 | -177563.24 | 177563.24 | 0 | 2025-07-28 | 3 | 2621539.56 | -160347.32 | DOWN | 0.0652 | 157 | Low | 570565.82 | 0.219 | 2 | 1713063.18 | 1 | 1.18 | 1.15
P005 | Materials | SUP002 | 2025-07 | 2025-04-28 | 2349055.01 | 2283629 | -65426.01 | 65426.01 | 0 | 2025-07-28 | 4 | 2461192.24 | -112137.23 | DOWN | 0.0477 | 91 | Low | 975373.72 | 0.448 | 8 | 1308255.28 | 1 | 1.18 | 1.15
P005 | Materials | SUP002 | 2025-07 | 2025-06-17 | 2296607.88 | 2283629 | -12978.88 | 12978.88 | 0 | 2025-07-28 | 5 | 2349055.01 | -52447.13 | DOWN | 0.0228 | 41 | Medium | 1508026.38 | 0.621 | 4 | 775602.62 | 1 | 1.18 | 1.15
P005 | Materials | SUP002 | 2025-07 | 2025-07-15 | 2299129.7 | 2283629 | -15500.7 | 15500.7 | 0 | 2025-07-28 | 6 | 2296607.88 | 2521.82 | UP | 0.0011 | 13 | High | 1652852.91 | 0.718 | 6 | 630776.09 | 1 | 1.18 | 1.15
P005 | Software | SUP002 | 2025-08 | 2025-05-09 | 3405502.94 | 2170987 | -1234515.94 | 1234515.94 | 1 | 2025-08-28 | 1 |  |  |  |  | 111 | Low | 1167216.71 | 0.357 | 3 | 1003770.29 | 8 | 1.7 | 1.32
P005 | Software | SUP002 | 2025-08 | 2025-05-18 | 2750253.6 | 2170987 | -579266.6 | 579266.6 | 1 | 2025-08-28 | 2 | 3405502.94 | -655249.34 | DOWN | 0.2383 | 102 | Low | 1014385.08 | 0.386 | 5 | 1156601.92 | 8 | 1.7 | 1.32
P005 | Software | SUP002 | 2025-08 | 2025-07-21 | 2384179.07 | 2170987 | -213192.07 | 213192.07 | 0 | 2025-08-28 | 3 | 2750253.6 | -366074.53 | DOWN | 0.1535 | 38 | Low | 1413291.14 | 0.595 | 3 | 757695.86 | 8 | 1.7 | 1.32
P005 | Software | SUP002 | 2025-08 | 2025-08-18 | 2286788.55 | 2170987 | -115801.55 | 115801.55 | 0 | 2025-08-28 | 4 | 2384179.07 | -97390.52 | DOWN | 0.0426 | 10 | Medium | 1594156.85 | 0.684 | 6 | 576830.15 | 8 | 1.7 | 1.32
P005 | Software | SUP002 | 2025-08 | 2025-08-18 | 2191204.48 | 2170987 | -20217.48 | 20217.48 | 0 | 2025-08-28 | 5 | 2286788.55 | -95584.07 | DOWN | 0.0436 | 10 | Medium | 1501161.67 | 0.684 | 5 | 669825.33 | 8 | 1.7 | 1.32
P005 | Logistics | SUP002 | 2025-09 | 2025-05-17 | 2967790.07 | 2066000 | -901790.07 | 901790.07 | 1 | 2025-09-28 | 1 |  |  |  |  | 134 | Low | 918219.17 | 0.305 | 3 | 1147780.83 | 0 | 0.5 | 0.8
P005 | Logistics | SUP002 | 2025-09 | 2025-06-27 | 2474936.66 | 2066000 | -408936.66 | 408936.66 | 1 | 2025-09-28 | 2 | 2967790.07 | -492853.41 | DOWN | 0.1991 | 93 | Low | 1175465.85 | 0.45 | 0 | 890534.15 | 0 | 0.5 | 0.8
P005 | Logistics | SUP002 | 2025-09 | 2025-08-12 | 2231672.42 | 2066000 | -165672.42 | 165672.42 | 0 | 2025-09-28 | 3 | 2474936.66 | -243264.24 | DOWN | 0.109 | 47 | Medium | 1353328.38 | 0.613 | 5 | 712671.62 | 0 | 0.5 | 0.8
P005 | Logistics | SUP002 | 2025-09 | 2025-08-26 | 2176837.2 | 2066000 | -110837.2 | 110837.2 | 0 | 2025-09-28 | 4 | 2231672.42 | -54835.22 | DOWN | 0.0252 | 33 | Medium | 1455885.26 | 0.663 | 5 | 610114.74 | 0 | 0.5 | 0.8
P005 | Logistics | SUP002 | 2025-10 | 2025-05-01 | 3388618.81 | 2254274 | -1134344.81 | 1134344.81 | 1 | 2025-10-28 | 1 |  |  |  |  | 180 | Low | 514002.6 | 0.153 | 2 | 1740271.4 | 4 | 1.15 | 0.8
P005 | Logistics | SUP002 | 2025-10 | 2025-06-01 | 2799403.66 | 2254274 | -545129.66 | 545129.66 | 1 | 2025-10-28 | 2 | 3388618.81 | -589215.15 | DOWN | 0.2105 | 149 | Low | 725662.94 | 0.247 | 2 | 1528611.06 | 4 | 1.15 | 0.8
P005 | Logistics | SUP002 | 2025-10 | 2025-09-10 | 2491625.68 | 2254274 | -237351.68 | 237351.68 | 0 | 2025-10-28 | 3 | 2799403.66 | -307777.98 | DOWN | 0.1235 | 48 | Low | 1375828.66 | 0.599 | 3 | 878445.34 | 4 | 1.15 | 0.8
P005 | Electronics | SUP002 | 2025-11 | 2025-07-11 | 2190119.18 | 1564201 | -625918.18 | 625918.18 | 1 | 2025-11-28 | 1 |  |  |  |  | 140 | Low | 622621.18 | 0.272 | 1 | 941579.82 | 4 | 1.35 | 1.5
P005 | Electronics | SUP002 | 2025-11 | 2025-10-21 | 1842472.96 | 1564201 | -278271.96 | 278271.96 | 1 | 2025-11-28 | 2 | 2190119.18 | -347646.22 | DOWN | 0.1887 | 38 | Low | 1071297.89 | 0.619 | 7 | 492903.11 | 4 | 1.35 | 1.5
P005 | Electronics | SUP002 | 2025-11 | 2025-10-24 | 1689448.37 | 1564201 | -125247.37 | 125247.37 | 0 | 2025-11-28 | 3 | 1842472.96 | -153024.59 | DOWN | 0.0906 | 35 | Medium | 1092757.6 | 0.629 | 7 | 471443.4 | 4 | 1.35 | 1.5
P005 | Electronics | SUP002 | 2025-11 | 2025-11-07 | 1617236.57 | 1564201 | -53035.57 | 53035.57 | 0 | 2025-11-28 | 4 | 1689448.37 | -72211.8 | DOWN | 0.0447 | 21 | High | 1075767.96 | 0.677 | 1 | 488433.04 | 4 | 1.35 | 1.5
P005 | Materials | SUP002 | 2025-12 | 2025-09-16 | 2673131.17 | 2281302 | -391829.17 | 391829.17 | 0 | 2025-12-28 | 1 |  |  |  |  | 103 | Low | 1131287.67 | 0.415 | 2 | 1150014.33 | 7 | 0.73 | 1.27
P005 | Materials | SUP002 | 2025-12 | 2025-09-29 | 2468601.46 | 2281302 | -187299.46 | 187299.46 | 0 | 2025-12-28 | 2 | 2673131.17 | -204529.71 | DOWN | 0.0829 | 90 | Low | 1157987.63 | 0.461 | 5 | 1123314.37 | 7 | 0.73 | 1.27
P005 | Materials | SUP002 | 2025-12 | 2025-10-09 | 2384961.35 | 2281302 | -103659.35 | 103659.35 | 0 | 2025-12-28 | 3 | 2468601.46 | -83640.11 | DOWN | 0.0351 | 80 | Low | 1198452.71 | 0.496 | 4 | 1082849.29 | 7 | 0.73 | 1.27
P005 | Materials | SUP002 | 2025-12 | 2025-11-03 | 2339541.89 | 2281302 | -58239.89 | 58239.89 | 0 | 2025-12-28 | 4 | 2384961.35 | -45419.46 | DOWN | 0.0194 | 55 | Medium | 1275619.84 | 0.585 | 4 | 1005682.16 | 7 | 0.73 | 1.27
P005 | Materials | SUP002 | 2025-12 | 2025-11-03 | 2303438.47 | 2281302 | -22136.47 | 22136.47 | 0 | 2025-12-28 | 5 | 2339541.89 | -36103.42 | DOWN | 0.0157 | 55 | Medium | 1445906.7 | 0.585 | 6 | 835395.3 | 7 | 0.73 | 1.27
P005 | Materials | SUP002 | 2025-12 | 2025-12-07 | 2308951.08 | 2281302 | -27649.08 | 27649.08 | 0 | 2025-12-28 | 6 | 2303438.47 | 5512.61 | UP | 0.0024 | 21 | High | 1659174.09 | 0.706 | 5 | 622127.91 | 7 | 0.73 | 1.27
P005 | Electronics | SUP006 | 2025-01 | 2024-09-04 | 3728241.7 | 2420436 | -1307805.7 | 1307805.7 | 1 | 2025-01-28 | 1 |  |  |  |  | 146 | Low | 655127.52 | 0.176 | 0 | 1765308.48 | 8 | 1.44 | 1.07
P005 | Electronics | SUP006 | 2025-01 | 2024-10-13 | 3188386.77 | 2420436 | -767950.77 | 767950.77 | 1 | 2025-01-28 | 2 | 3728241.7 | -539854.93 | DOWN | 0.1693 | 107 | Low | 792280.19 | 0.268 | 0 | 1628155.81 | 8 | 1.44 | 1.07
P005 | Electronics | SUP006 | 2025-01 | 2024-11-16 | 2852763.3 | 2420436 | -432327.3 | 432327.3 | 1 | 2025-01-28 | 3 | 3188386.77 | -335623.47 | DOWN | 0.1176 | 73 | Low | 937174.12 | 0.349 | 2 | 1483261.88 | 8 | 1.44 | 1.07
P005 | Electronics | SUP006 | 2025-01 | 2024-11-22 | 2672872.16 | 2420436 | -252436.16 | 252436.16 | 0 | 2025-01-28 | 4 | 2852763.3 | -179891.14 | DOWN | 0.0673 | 67 | Low | 918040.18 | 0.363 | 1 | 1502395.82 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP006 | 2025-02 | 2024-09-06 | 760320.22 | 570370 | -189950.22 | 189950.22 | 1 | 2025-02-28 | 1 |  |  |  |  | 175 | Low | 77892.01 | 0.105 | 0 | 492477.99 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP006 | 2025-02 | 2024-09-16 | 684415.48 | 570370 | -114045.48 | 114045.48 | 1 | 2025-02-28 | 2 | 760320.22 | -75904.74 | DOWN | 0.1109 | 165 | Low | 93501.59 | 0.129 | 0 | 476868.41 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP006 | 2025-02 | 2025-01-01 | 643260.41 | 570370 | -72890.41 | 72890.41 | 0 | 2025-02-28 | 3 | 684415.48 | -41155.07 | DOWN | 0.064 | 58 | Low | 233122.7 | 0.379 | 6 | 337247.3 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP006 | 2025-02 | 2025-01-14 | 605958.26 | 570370 | -35588.26 | 35588.26 | 0 | 2025-02-28 | 4 | 643260.41 | -37302.15 | DOWN | 0.0616 | 45 | Low | 241452.24 | 0.41 | 8 | 328917.76 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP006 | 2025-02 | 2025-01-20 | 593611.94 | 570370 | -23241.94 | 23241.94 | 0 | 2025-02-28 | 5 | 605958.26 | -12346.32 | DOWN | 0.0208 | 39 | Low | 260339.15 | 0.424 | 1 | 310030.85 | 7 | 1.56 | 1.03
P005 | Software | SUP006 | 2025-03 | 2024-12-13 | 1177963.43 | 750791 | -427172.43 | 427172.43 | 1 | 2025-03-28 | 1 |  |  |  |  | 105 | Low | 327318.25 | 0.288 | 2 | 423472.75 | 0 | 0.76 | 1.01
P005 | Software | SUP006 | 2025-03 | 2025-02-01 | 1005721.72 | 750791 | -254930.72 | 254930.72 | 1 | 2025-03-28 | 2 | 1177963.43 | -172241.71 | DOWN | 0.1713 | 55 | Low | 435642.33 | 0.413 | 2 | 315148.67 | 0 | 0.76 | 1.01
P005 | Software | SUP006 | 2025-03 | 2025-03-16 | 891023.9 | 750791 | -140232.9 | 140232.9 | 1 | 2025-03-28 | 3 | 1005721.72 | -114697.82 | DOWN | 0.1287 | 12 | Low | 451172.01 | 0.52 | 1 | 299618.99 | 0 | 0.76 | 1.01
P005 | Logistics | SUP006 | 2025-04 | 2024-11-05 | 2524072.19 | 1546087 | -977985.19 | 977985.19 | 1 | 2025-04-28 | 1 |  |  |  |  | 174 | Low | 283772.85 | 0.108 | 1 | 1262314.15 | 2 | 1.52 | 1.28
P005 | Logistics | SUP006 | 2025-04 | 2025-02-10 | 2129926.65 | 1546087 | -583839.65 | 583839.65 | 1 | 2025-04-28 | 2 | 2524072.19 | -394145.54 | DOWN | 0.1851 | 77 | Low | 701645.68 | 0.337 | 0 | 844441.32 | 2 | 1.52 | 1.28
P005 | Logistics | SUP006 | 2025-04 | 2025-02-14 | 1957939.42 | 1546087 | -411852.42 | 411852.42 | 1 | 2025-04-28 | 3 | 2129926.65 | -171987.23 | DOWN | 0.0878 | 73 | Low | 649798.88 | 0.346 | 3 | 896288.12 | 2 | 1.52 | 1.28
P005 | Logistics | SUP006 | 2025-04 | 2025-03-08 | 1780297.55 | 1546087 | -234210.55 | 234210.55 | 0 | 2025-04-28 | 4 | 1957939.42 | -177641.87 | DOWN | 0.0998 | 51 | Low | 699530.49 | 0.398 | 1 | 846556.51 | 2 | 1.52 | 1.28
P005 | Logistics | SUP006 | 2025-04 | 2025-03-09 | 1707274.98 | 1546087 | -161187.98 | 161187.98 | 0 | 2025-04-28 | 5 | 1780297.55 | -73022.57 | DOWN | 0.0428 | 50 | Low | 634091.1 | 0.4 | 1 | 911995.9 | 2 | 1.52 | 1.28
P005 | Logistics | SUP006 | 2025-04 | 2025-03-23 | 1675214.44 | 1546087 | -129127.44 | 129127.44 | 0 | 2025-04-28 | 6 | 1707274.98 | -32060.54 | DOWN | 0.0191 | 36 | Low | 687361.77 | 0.433 | 3 | 858725.23 | 2 | 1.52 | 1.28
P005 | Services | SUP006 | 2025-05 | 2025-01-04 | 1598455.13 | 1008779 | -589676.13 | 589676.13 | 1 | 2025-05-28 | 1 |  |  |  |  | 144 | Low | 301430.72 | 0.187 | 3 | 707348.28 | 6 | 1.12 | 1.51
P005 | Services | SUP006 | 2025-05 | 2025-02-15 | 1384007.68 | 1008779 | -375228.68 | 375228.68 | 1 | 2025-05-28 | 2 | 1598455.13 | -214447.45 | DOWN | 0.1549 | 102 | Low | 429993.9 | 0.291 | 0 | 578785.1 | 6 | 1.12 | 1.51
P005 | Services | SUP006 | 2025-05 | 2025-05-03 | 1227166.14 | 1008779 | -218387.14 | 218387.14 | 1 | 2025-05-28 | 3 | 1384007.68 | -156841.54 | DOWN | 0.1278 | 25 | Low | 581196.97 | 0.481 | 5 | 427582.03 | 6 | 1.12 | 1.51
P005 | Services | SUP006 | 2025-06 | 2025-02-19 | 211963.27 | 131382 | -80581.27 | 80581.27 | 1 | 2025-06-28 | 1 |  |  |  |  | 129 | Low | 51197.88 | 0.225 | 2 | 80184.12 | 7 | 1.1 | 1.21
P005 | Services | SUP006 | 2025-06 | 2025-03-30 | 178155.16 | 131382 | -46773.16 | 46773.16 | 1 | 2025-06-28 | 2 | 211963.27 | -33808.11 | DOWN | 0.1898 | 90 | Low | 57955.34 | 0.321 | 0 | 73426.66 | 7 | 1.1 | 1.21
P005 | Services | SUP006 | 2025-06 | 2025-04-07 | 157602.87 | 131382 | -26220.87 | 26220.87 | 1 | 2025-06-28 | 3 | 178155.16 | -20552.29 | DOWN | 0.1304 | 82 | Low | 53369.5 | 0.341 | 3 | 78012.5 | 7 | 1.1 | 1.21
P005 | Services | SUP006 | 2025-06 | 2025-05-28 | 147654.03 | 131382 | -16272.03 | 16272.03 | 0 | 2025-06-28 | 4 | 157602.87 | -9948.84 | DOWN | 0.0674 | 31 | Medium | 72373.18 | 0.467 | 7 | 59008.82 | 7 | 1.1 | 1.21
P005 | Services | SUP006 | 2025-06 | 2025-06-07 | 140804.04 | 131382 | -9422.04 | 9422.04 | 0 | 2025-06-28 | 5 | 147654.03 | -6849.99 | DOWN | 0.0486 | 21 | Medium | 64337.01 | 0.492 | 6 | 67044.99 | 7 | 1.1 | 1.21
P005 | Materials | SUP006 | 2025-07 | 2025-03-06 | 211055.84 | 144092 | -66963.84 | 66963.84 | 1 | 2025-07-28 | 1 |  |  |  |  | 144 | Low | 36249.18 | 0.186 | 0 | 107842.82 | 1 | 1.18 | 1.15
P005 | Materials | SUP006 | 2025-07 | 2025-06-08 | 184423.52 | 144092 | -40331.52 | 40331.52 | 1 | 2025-07-28 | 2 | 211055.84 | -26632.32 | DOWN | 0.1444 | 50 | Low | 78192.59 | 0.416 | 6 | 65899.41 | 1 | 1.18 | 1.15
P005 | Materials | SUP006 | 2025-07 | 2025-06-11 | 169314.49 | 144092 | -25222.49 | 25222.49 | 0 | 2025-07-28 | 3 | 184423.52 | -15109.03 | DOWN | 0.0892 | 47 | Low | 67370.45 | 0.423 | 0 | 76721.55 | 1 | 1.18 | 1.15
P005 | Materials | SUP006 | 2025-07 | 2025-07-06 | 159020.65 | 144092 | -14928.65 | 14928.65 | 0 | 2025-07-28 | 4 | 169314.49 | -10293.84 | DOWN | 0.0647 | 22 | Medium | 72642.11 | 0.485 | 6 | 71449.89 | 1 | 1.18 | 1.15
P005 | Electronics | SUP006 | 2025-08 | 2025-04-20 | 254951.7 | 149931 | -105020.7 | 105020.7 | 1 | 2025-08-28 | 1 |  |  |  |  | 130 | Low | 53316.1 | 0.208 | 2 | 96614.9 | 8 | 1.7 | 1.32
P005 | Electronics | SUP006 | 2025-08 | 2025-05-15 | 211855.31 | 149931 | -61924.31 | 61924.31 | 1 | 2025-08-28 | 2 | 254951.7 | -43096.39 | DOWN | 0.2034 | 105 | Low | 53732.4 | 0.265 | 2 | 96198.6 | 8 | 1.7 | 1.32
P005 | Electronics | SUP006 | 2025-08 | 2025-05-21 | 187526.45 | 149931 | -37595.45 | 37595.45 | 1 | 2025-08-28 | 3 | 211855.31 | -24328.86 | DOWN | 0.1297 | 99 | Low | 48580.63 | 0.279 | 0 | 101350.37 | 8 | 1.7 | 1.32
P005 | Electronics | SUP006 | 2025-08 | 2025-05-26 | 173088.31 | 149931 | -23157.31 | 23157.31 | 0 | 2025-08-28 | 4 | 187526.45 | -14438.14 | DOWN | 0.0834 | 94 | Low | 46790.76 | 0.291 | 0 | 103140.24 | 8 | 1.7 | 1.32
P005 | Electronics | SUP006 | 2025-08 | 2025-07-14 | 165364.19 | 149931 | -15433.19 | 15433.19 | 0 | 2025-08-28 | 5 | 173088.31 | -7724.12 | DOWN | 0.0467 | 45 | Low | 67994.6 | 0.404 | 5 | 81936.4 | 8 | 1.7 | 1.32
P005 | Logistics | SUP006 | 2025-09 | 2025-04-08 | 941115.43 | 586602 | -354513.43 | 354513.43 | 1 | 2025-09-28 | 1 |  |  |  |  | 173 | Low | 114606.02 | 0.118 | 0 | 471995.98 | 0 | 0.5 | 0.8
P005 | Logistics | SUP006 | 2025-09 | 2025-05-28 | 788893.86 | 586602 | -202291.86 | 202291.86 | 1 | 2025-09-28 | 2 | 941115.43 | -152221.57 | DOWN | 0.193 | 123 | Low | 193109.36 | 0.243 | 3 | 393492.64 | 0 | 0.5 | 0.8
P005 | Logistics | SUP006 | 2025-09 | 2025-08-08 | 719326.9 | 586602 | -132724.9 | 132724.9 | 1 | 2025-09-28 | 3 | 788893.86 | -69566.96 | DOWN | 0.0967 | 51 | Low | 318358.23 | 0.423 | 4 | 268243.77 | 0 | 0.5 | 0.8
P005 | Logistics | SUP006 | 2025-09 | 2025-09-06 | 667499.09 | 586602 | -80897.09 | 80897.09 | 0 | 2025-09-28 | 4 | 719326.9 | -51827.81 | DOWN | 0.0776 | 22 | Medium | 337567.73 | 0.495 | 9 | 249034.27 | 0 | 0.5 | 0.8
P005 | Logistics | SUP006 | 2025-09 | 2025-09-07 | 634315.19 | 586602 | -47713.19 | 47713.19 | 0 | 2025-09-28 | 5 | 667499.09 | -33183.9 | DOWN | 0.0523 | 21 | Medium | 314814.76 | 0.498 | 1 | 271787.24 | 0 | 0.5 | 0.8
P005 | Electronics | SUP006 | 2025-10 | 2025-05-02 | 1863967.54 | 1309507 | -554460.54 | 554460.54 | 1 | 2025-10-28 | 1 |  |  |  |  | 179 | Low | 196807.45 | 0.108 | 2 | 1112699.55 | 4 | 1.15 | 0.8
P005 | Electronics | SUP006 | 2025-10 | 2025-06-09 | 1660782.5 | 1309507 | -351275.5 | 351275.5 | 1 | 2025-10-28 | 2 | 1863967.54 | -203185.04 | DOWN | 0.1223 | 141 | Low | 332588.67 | 0.194 | 1 | 976918.33 | 4 | 1.15 | 0.8
P005 | Electronics | SUP006 | 2025-10 | 2025-06-27 | 1512695.76 | 1309507 | -203188.76 | 203188.76 | 0 | 2025-10-28 | 3 | 1660782.5 | -148086.74 | DOWN | 0.0979 | 123 | Low | 348400.61 | 0.238 | 3 | 961106.39 | 4 | 1.15 | 0.8
P005 | Services | SUP006 | 2025-11 | 2025-06-13 | 3039856.88 | 1742248 | -1297608.88 | 1297608.88 | 1 | 2025-11-28 | 1 |  |  |  |  | 168 | Low | 363063.12 | 0.125 | 0 | 1379184.88 | 4 | 1.35 | 1.5
P005 | Services | SUP006 | 2025-11 | 2025-08-19 | 2531385.19 | 1742248 | -789137.19 | 789137.19 | 1 | 2025-11-28 | 2 | 3039856.88 | -508471.69 | DOWN | 0.2009 | 101 | Low | 771543.68 | 0.286 | 0 | 970704.32 | 4 | 1.35 | 1.5
P005 | Services | SUP006 | 2025-11 | 2025-10-01 | 2171552.31 | 1742248 | -429304.31 | 429304.31 | 1 | 2025-11-28 | 3 | 2531385.19 | -359832.88 | DOWN | 0.1657 | 58 | Low | 837614.74 | 0.389 | 6 | 904633.26 | 4 | 1.35 | 1.5
P005 | Mechanical | SUP006 | 2025-12 | 2025-07-22 | 2836444.24 | 2257986 | -578458.24 | 578458.24 | 1 | 2025-12-28 | 1 |  |  |  |  | 159 | Low | 427237.48 | 0.152 | 1 | 1830748.52 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP006 | 2025-12 | 2025-09-18 | 2613486.79 | 2257986 | -355500.79 | 355500.79 | 0 | 2025-12-28 | 2 | 2836444.24 | -222957.45 | DOWN | 0.0853 | 101 | Low | 722111.5 | 0.298 | 0 | 1535874.5 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP006 | 2025-12 | 2025-10-13 | 2470565.69 | 2257986 | -212579.69 | 212579.69 | 0 | 2025-12-28 | 3 | 2613486.79 | -142921.1 | DOWN | 0.0578 | 76 | Low | 827843.66 | 0.36 | 1 | 1430142.34 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP006 | 2025-12 | 2025-10-28 | 2384875.04 | 2257986 | -126889.04 | 126889.04 | 0 | 2025-12-28 | 4 | 2470565.69 | -85690.65 | DOWN | 0.0359 | 61 | Low | 876580.7 | 0.398 | 4 | 1381405.3 | 7 | 0.73 | 1.27
P005 | Software | SUP003 | 2025-01 | 2024-08-23 | 966904.32 | 562713 | -404191.32 | 404191.32 | 1 | 2025-01-28 | 1 |  |  |  |  | 158 | Low | 130136.88 | 0.134 | 3 | 432576.12 | 8 | 1.44 | 1.07
P005 | Software | SUP003 | 2025-01 | 2024-10-07 | 876949.96 | 562713 | -314236.96 | 314236.96 | 1 | 2025-01-28 | 2 | 966904.32 | -89954.36 | DOWN | 0.1026 | 113 | Low | 199533.41 | 0.231 | 0 | 363179.59 | 8 | 1.44 | 1.07
P005 | Software | SUP003 | 2025-01 | 2024-10-25 | 797528.39 | 562713 | -234815.39 | 234815.39 | 1 | 2025-01-28 | 3 | 876949.96 | -79421.57 | DOWN | 0.0996 | 95 | Low | 226404.29 | 0.27 | 2 | 336308.71 | 8 | 1.44 | 1.07
P005 | Software | SUP003 | 2025-01 | 2024-12-20 | 739362.03 | 562713 | -176649.03 | 176649.03 | 1 | 2025-01-28 | 4 | 797528.39 | -58166.36 | DOWN | 0.0787 | 39 | Low | 286765.39 | 0.391 | 0 | 275947.61 | 8 | 1.44 | 1.07
P005 | Software | SUP003 | 2025-01 | 2025-01-06 | 695537.46 | 562713 | -132824.46 | 132824.46 | 1 | 2025-01-28 | 5 | 739362.03 | -43824.57 | DOWN | 0.063 | 22 | Low | 277362.85 | 0.427 | 1 | 285350.15 | 8 | 1.44 | 1.07
P005 | Logistics | SUP003 | 2025-02 | 2024-09-19 | 2437701.88 | 1412365 | -1025336.88 | 1025336.88 | 1 | 2025-02-28 | 1 |  |  |  |  | 162 | Low | 299387.52 | 0.124 | 0 | 1112977.48 | 7 | 1.56 | 1.03
P005 | Logistics | SUP003 | 2025-02 | 2024-10-10 | 2196633.92 | 1412365 | -784268.92 | 784268.92 | 1 | 2025-02-28 | 2 | 2437701.88 | -241067.96 | DOWN | 0.1097 | 141 | Low | 369739.78 | 0.168 | 1 | 1042625.22 | 7 | 1.56 | 1.03
P005 | Logistics | SUP003 | 2025-02 | 2024-11-11 | 1944602.61 | 1412365 | -532237.61 | 532237.61 | 1 | 2025-02-28 | 3 | 2196633.92 | -252031.31 | DOWN | 0.1296 | 109 | Low | 470648.27 | 0.236 | 4 | 941716.73 | 7 | 1.56 | 1.03
P005 | Logistics | SUP003 | 2025-02 | 2024-12-03 | 1803044.28 | 1412365 | -390679.28 | 390679.28 | 1 | 2025-02-28 | 4 | 1944602.61 | -141558.33 | DOWN | 0.0785 | 87 | Low | 532749.57 | 0.283 | 2 | 879615.43 | 7 | 1.56 | 1.03
P005 | Logistics | SUP003 | 2025-02 | 2025-02-01 | 1753678.67 | 1412365 | -341313.67 | 341313.67 | 1 | 2025-02-28 | 5 | 1803044.28 | -49365.61 | DOWN | 0.0281 | 27 | Low | 741434.68 | 0.411 | 2 | 670930.32 | 7 | 1.56 | 1.03
P005 | Logistics | SUP003 | 2025-02 | 2025-02-09 | 1683032.13 | 1412365 | -270667.13 | 270667.13 | 1 | 2025-02-28 | 6 | 1753678.67 | -70646.54 | DOWN | 0.042 | 19 | Low | 712160.66 | 0.428 | 0 | 700204.34 | 7 | 1.56 | 1.03
P005 | Electronics | SUP003 | 2025-03 | 2024-10-26 | 426472.87 | 228956 | -197516.87 | 197516.87 | 1 | 2025-03-28 | 1 |  |  |  |  | 153 | Low | 62909.63 | 0.152 | 2 | 166046.37 | 0 | 0.76 | 1.01
P005 | Electronics | SUP003 | 2025-03 | 2024-12-20 | 377633.61 | 228956 | -148677.61 | 148677.61 | 1 | 2025-03-28 | 2 | 426472.87 | -48839.26 | DOWN | 0.1293 | 98 | Low | 107556.75 | 0.277 | 4 | 121399.25 | 0 | 0.76 | 1.01
P005 | Electronics | SUP003 | 2025-03 | 2025-02-12 | 340817.72 | 228956 | -111861.72 | 111861.72 | 1 | 2025-03-28 | 3 | 377633.61 | -36815.89 | DOWN | 0.108 | 44 | Low | 125451.54 | 0.4 | 1 | 103504.46 | 0 | 0.76 | 1.01
P005 | Electronics | SUP003 | 2025-03 | 2025-02-16 | 313902.1 | 228956 | -84946.1 | 84946.1 | 1 | 2025-03-28 | 4 | 340817.72 | -26915.62 | DOWN | 0.0857 | 40 | Low | 121204.88 | 0.409 | 4 | 107751.12 | 0 | 0.76 | 1.01
P005 | Services | SUP003 | 2025-04 | 2024-11-01 | 1445443.17 | 889963 | -555480.17 | 555480.17 | 1 | 2025-04-28 | 1 |  |  |  |  | 178 | Low | 126709.03 | 0.094 | 1 | 763253.97 | 2 | 1.52 | 1.28
P005 | Services | SUP003 | 2025-04 | 2024-11-26 | 1276990.9 | 889963 | -387027.9 | 387027.9 | 1 | 2025-04-28 | 2 | 1445443.17 | -168452.27 | DOWN | 0.1319 | 153 | Low | 186852.1 | 0.143 | 0 | 703110.9 | 2 | 1.52 | 1.28
P005 | Services | SUP003 | 2025-04 | 2024-12-18 | 1187304.96 | 889963 | -297341.96 | 297341.96 | 1 | 2025-04-28 | 3 | 1276990.9 | -89685.94 | DOWN | 0.0755 | 131 | Low | 234668.35 | 0.19 | 4 | 655294.65 | 2 | 1.52 | 1.28
P005 | Services | SUP003 | 2025-04 | 2025-04-14 | 1101915.95 | 889963 | -211952.95 | 211952.95 | 1 | 2025-04-28 | 4 | 1187304.96 | -85389.01 | DOWN | 0.0775 | 14 | Low | 451623.87 | 0.441 | 1 | 438339.13 | 2 | 1.52 | 1.28
P005 | Materials | SUP003 | 2025-05 | 2024-12-01 | 3079170.41 | 1732908 | -1346262.41 | 1346262.41 | 1 | 2025-05-28 | 1 |  |  |  |  | 178 | Low | 295450.98 | 0.099 | 0 | 1437457.02 | 6 | 1.12 | 1.51
P005 | Materials | SUP003 | 2025-05 | 2024-12-04 | 2753056.83 | 1732908 | -1020148.83 | 1020148.83 | 1 | 2025-05-28 | 2 | 3079170.41 | -326113.58 | DOWN | 0.1185 | 175 | Low | 294891.04 | 0.101 | 0 | 1438016.96 | 6 | 1.12 | 1.51
P005 | Materials | SUP003 | 2025-05 | 2025-01-07 | 2514512.98 | 1732908 | -781604.98 | 781604.98 | 1 | 2025-05-28 | 3 | 2753056.83 | -238543.85 | DOWN | 0.0949 | 141 | Low | 467787.43 | 0.177 | 3 | 1265120.57 | 6 | 1.12 | 1.51
P005 | Materials | SUP003 | 2025-05 | 2025-02-13 | 2315442.48 | 1732908 | -582534.48 | 582534.48 | 1 | 2025-05-28 | 4 | 2514512.98 | -199070.5 | DOWN | 0.086 | 104 | Low | 630296.81 | 0.26 | 2 | 1102611.19 | 6 | 1.12 | 1.51
P005 | Materials | SUP003 | 2025-05 | 2025-03-28 | 2163573.8 | 1732908 | -430665.8 | 430665.8 | 1 | 2025-05-28 | 5 | 2315442.48 | -151868.68 | DOWN | 0.0702 | 61 | Low | 758876.79 | 0.356 | 2 | 974031.21 | 6 | 1.12 | 1.51
P005 | Materials | SUP003 | 2025-05 | 2025-04-04 | 2048369.87 | 1732908 | -315461.87 | 315461.87 | 1 | 2025-05-28 | 6 | 2163573.8 | -115203.93 | DOWN | 0.0562 | 54 | Low | 748569.38 | 0.372 | 3 | 984338.62 | 6 | 1.12 | 1.51
P005 | Logistics | SUP003 | 2025-06 | 2025-02-15 | 3837842.94 | 2202620 | -1635222.94 | 1635222.94 | 1 | 2025-06-28 | 1 |  |  |  |  | 133 | Low | 768900.12 | 0.195 | 1 | 1433719.88 | 7 | 1.1 | 1.21
P005 | Logistics | SUP003 | 2025-06 | 2025-03-27 | 3404133.07 | 2202620 | -1201513.07 | 1201513.07 | 1 | 2025-06-28 | 2 | 3837842.94 | -433709.87 | DOWN | 0.1274 | 93 | Low | 942910.77 | 0.285 | 3 | 1259709.23 | 7 | 1.1 | 1.21
P005 | Logistics | SUP003 | 2025-06 | 2025-05-20 | 3155815.86 | 2202620 | -953195.86 | 953195.86 | 1 | 2025-06-28 | 3 | 3404133.07 | -248317.21 | DOWN | 0.0787 | 39 | Low | 1253302.02 | 0.406 | 3 | 949317.98 | 7 | 1.1 | 1.21
P005 | Materials | SUP003 | 2025-07 | 2025-02-18 | 2028879.74 | 1205908 | -822971.74 | 822971.74 | 1 | 2025-07-28 | 1 |  |  |  |  | 160 | Low | 273951.84 | 0.133 | 0 | 931956.16 | 1 | 1.18 | 1.15
P005 | Materials | SUP003 | 2025-07 | 2025-04-07 | 1805783.39 | 1205908 | -599875.39 | 599875.39 | 1 | 2025-07-28 | 2 | 2028879.74 | -223096.35 | DOWN | 0.1235 | 112 | Low | 459937.46 | 0.24 | 0 | 745970.54 | 1 | 1.18 | 1.15
P005 | Materials | SUP003 | 2025-07 | 2025-05-06 | 1653001.38 | 1205908 | -447093.38 | 447093.38 | 1 | 2025-07-28 | 3 | 1805783.39 | -152782.01 | DOWN | 0.0924 | 83 | Low | 482268.95 | 0.305 | 0 | 723639.05 | 1 | 1.18 | 1.15
P005 | Materials | SUP003 | 2025-07 | 2025-05-26 | 1530319.94 | 1205908 | -324411.94 | 324411.94 | 1 | 2025-07-28 | 4 | 1653001.38 | -122681.44 | DOWN | 0.0802 | 63 | Low | 523113.14 | 0.349 | 2 | 682794.86 | 1 | 1.18 | 1.15
P005 | Materials | SUP003 | 2025-07 | 2025-07-15 | 1456503.79 | 1205908 | -250595.79 | 250595.79 | 1 | 2025-07-28 | 5 | 1530319.94 | -73816.15 | DOWN | 0.0507 | 13 | Low | 648130.55 | 0.461 | 7 | 557777.45 | 1 | 1.18 | 1.15
P005 | Software | SUP003 | 2025-08 | 2025-03-11 | 1375136.08 | 709322 | -665814.08 | 665814.08 | 1 | 2025-08-28 | 1 |  |  |  |  | 170 | Low | 140173.42 | 0.105 | 0 | 569148.58 | 8 | 1.7 | 1.32
P005 | Software | SUP003 | 2025-08 | 2025-04-18 | 1197182.48 | 709322 | -487860.48 | 487860.48 | 1 | 2025-08-28 | 2 | 1375136.08 | -177953.6 | DOWN | 0.1486 | 132 | Low | 218756.08 | 0.185 | 1 | 490565.92 | 8 | 1.7 | 1.32
P005 | Software | SUP003 | 2025-08 | 2025-07-20 | 1103115.86 | 709322 | -393793.86 | 393793.86 | 1 | 2025-08-28 | 3 | 1197182.48 | -94066.62 | DOWN | 0.0853 | 39 | Low | 442831.87 | 0.379 | 3 | 266490.13 | 8 | 1.7 | 1.32
P005 | Software | SUP003 | 2025-08 | 2025-07-25 | 985191.51 | 709322 | -275869.51 | 275869.51 | 1 | 2025-08-28 | 4 | 1103115.86 | -117924.35 | DOWN | 0.1197 | 34 | Low | 389771.35 | 0.39 | 4 | 319550.65 | 8 | 1.7 | 1.32
P005 | Software | SUP003 | 2025-08 | 2025-08-18 | 906918.3 | 709322 | -197596.3 | 197596.3 | 1 | 2025-08-28 | 5 | 985191.51 | -78273.21 | DOWN | 0.0863 | 10 | Low | 384723.92 | 0.438 | 3 | 324598.08 | 8 | 1.7 | 1.32
P005 | Software | SUP003 | 2025-09 | 2025-04-25 | 3716984.57 | 2120239 | -1596745.57 | 1596745.57 | 1 | 2025-09-28 | 1 |  |  |  |  | 156 | Low | 499900.37 | 0.145 | 2 | 1620338.63 | 0 | 0.5 | 0.8
P005 | Software | SUP003 | 2025-09 | 2025-06-23 | 3273244.16 | 2120239 | -1153005.16 | 1153005.16 | 1 | 2025-09-28 | 2 | 3716984.57 | -443740.41 | DOWN | 0.1356 | 97 | Low | 912988.8 | 0.28 | 3 | 1207250.2 | 0 | 0.5 | 0.8
P005 | Software | SUP003 | 2025-09 | 2025-08-06 | 3016824.16 | 2120239 | -896585.16 | 896585.16 | 1 | 2025-09-28 | 3 | 3273244.16 | -256420 | DOWN | 0.085 | 53 | Low | 1074172.42 | 0.38 | 2 | 1046066.58 | 0 | 0.5 | 0.8
P005 | Electronics | SUP003 | 2025-10 | 2025-05-15 | 2913108.43 | 1827953 | -1085155.43 | 1085155.43 | 1 | 2025-10-28 | 1 |  |  |  |  | 166 | Low | 345762.73 | 0.121 | 1 | 1482190.27 | 4 | 1.15 | 0.8
P005 | Electronics | SUP003 | 2025-10 | 2025-06-17 | 2642454.75 | 1827953 | -814501.75 | 814501.75 | 1 | 2025-10-28 | 2 | 2913108.43 | -270653.68 | DOWN | 0.1024 | 133 | Low | 549333.22 | 0.194 | 1 | 1278619.78 | 4 | 1.15 | 0.8
P005 | Electronics | SUP003 | 2025-10 | 2025-07-06 | 2440688.8 | 1827953 | -612735.8 | 612735.8 | 1 | 2025-10-28 | 3 | 2642454.75 | -201765.95 | DOWN | 0.0827 | 114 | Low | 586523.45 | 0.237 | 2 | 1241429.55 | 4 | 1.15 | 0.8
P005 | Electronics | SUP003 | 2025-10 | 2025-07-18 | 2267044.36 | 1827953 | -439091.36 | 439091.36 | 1 | 2025-10-28 | 4 | 2440688.8 | -173644.44 | DOWN | 0.0766 | 102 | Low | 614359.84 | 0.263 | 0 | 1213593.16 | 4 | 1.15 | 0.8
P005 | Electronics | SUP003 | 2025-10 | 2025-07-28 | 2156189.05 | 1827953 | -328236.05 | 328236.05 | 1 | 2025-10-28 | 5 | 2267044.36 | -110855.31 | DOWN | 0.0514 | 92 | Low | 629539.02 | 0.286 | 0 | 1198413.98 | 4 | 1.15 | 0.8
P005 | Electronics | SUP003 | 2025-10 | 2025-08-29 | 2084756.8 | 1827953 | -256803.8 | 256803.8 | 0 | 2025-10-28 | 6 | 2156189.05 | -71432.25 | DOWN | 0.0343 | 60 | Low | 717142.79 | 0.357 | 1 | 1110810.21 | 4 | 1.15 | 0.8
P005 | Software | SUP003 | 2025-11 | 2025-06-21 | 489218.12 | 251736 | -237482.12 | 237482.12 | 1 | 2025-11-28 | 1 |  |  |  |  | 160 | Low | 59755 | 0.131 | 2 | 191981 | 4 | 1.35 | 1.5
P005 | Software | SUP003 | 2025-11 | 2025-07-22 | 430755.65 | 251736 | -179019.65 | 179019.65 | 1 | 2025-11-28 | 2 | 489218.12 | -58462.47 | DOWN | 0.1357 | 129 | Low | 81170.93 | 0.198 | 3 | 170565.07 | 4 | 1.35 | 1.5
P005 | Software | SUP003 | 2025-11 | 2025-07-24 | 391030.37 | 251736 | -139294.37 | 139294.37 | 1 | 2025-11-28 | 3 | 430755.65 | -39725.28 | DOWN | 0.1016 | 127 | Low | 78581.65 | 0.203 | 5 | 173154.35 | 4 | 1.35 | 1.5
P005 | Software | SUP003 | 2025-11 | 2025-10-28 | 361795.52 | 251736 | -110059.52 | 110059.52 | 1 | 2025-11-28 | 4 | 391030.37 | -29234.85 | DOWN | 0.0808 | 31 | Low | 156553.82 | 0.412 | 3 | 95182.18 | 4 | 1.35 | 1.5
P005 | Software | SUP003 | 2025-11 | 2025-11-09 | 340579 | 251736 | -88843 | 88843 | 1 | 2025-11-28 | 5 | 361795.52 | -21216.52 | DOWN | 0.0623 | 19 | Low | 138276.54 | 0.438 | 3 | 113459.46 | 4 | 1.35 | 1.5
P005 | Software | SUP003 | 2025-11 | 2025-11-13 | 310827.43 | 251736 | -59091.43 | 59091.43 | 1 | 2025-11-28 | 6 | 340579 | -29751.57 | DOWN | 0.0957 | 15 | Low | 147087.01 | 0.447 | 0 | 104648.99 | 4 | 1.35 | 1.5
P005 | Logistics | SUP003 | 2025-12 | 2025-08-14 | 834828.33 | 401097 | -433731.33 | 433731.33 | 1 | 2025-12-28 | 1 |  |  |  |  | 136 | Low | 159668.18 | 0.191 | 0 | 241428.82 | 7 | 0.73 | 1.27
P005 | Logistics | SUP003 | 2025-12 | 2025-08-20 | 718281.17 | 401097 | -317184.17 | 317184.17 | 1 | 2025-12-28 | 2 | 834828.33 | -116547.16 | DOWN | 0.1623 | 130 | Low | 147586.41 | 0.205 | 0 | 253510.59 | 7 | 0.73 | 1.27
P005 | Logistics | SUP003 | 2025-12 | 2025-09-02 | 624254.97 | 401097 | -223157.97 | 223157.97 | 1 | 2025-12-28 | 3 | 718281.17 | -94026.2 | DOWN | 0.1506 | 117 | Low | 157407.45 | 0.234 | 4 | 243689.55 | 7 | 0.73 | 1.27
P005 | Logistics | SUP003 | 2025-12 | 2025-09-14 | 569950.64 | 401097 | -168853.64 | 168853.64 | 1 | 2025-12-28 | 4 | 624254.97 | -54304.33 | DOWN | 0.0953 | 105 | Low | 140871.07 | 0.261 | 3 | 260225.93 | 7 | 0.73 | 1.27
P005 | Logistics | SUP003 | 2025-12 | 2025-10-28 | 518015.56 | 401097 | -116918.56 | 116918.56 | 1 | 2025-12-28 | 5 | 569950.64 | -51935.08 | DOWN | 0.1003 | 61 | Low | 189767.43 | 0.361 | 3 | 211329.57 | 7 | 0.73 | 1.27
P005 | Logistics | SUP003 | 2025-12 | 2025-12-13 | 491789.19 | 401097 | -90692.19 | 90692.19 | 1 | 2025-12-28 | 6 | 518015.56 | -26226.37 | DOWN | 0.0533 | 15 | Low | 242168.25 | 0.466 | 5 | 158928.75 | 7 | 0.73 | 1.27
P005 | Services | SUP019 | 2025-01 | 2024-08-25 | 1613914.6 | 885088 | -728826.6 | 728826.6 | 1 | 2025-01-28 | 1 |  |  |  |  | 156 | Low | 242766.51 | 0.152 | 0 | 642321.49 | 8 | 1.44 | 1.07
P005 | Services | SUP019 | 2025-01 | 2024-10-01 | 1325304.02 | 885088 | -440216.02 | 440216.02 | 1 | 2025-01-28 | 2 | 1613914.6 | -288610.58 | DOWN | 0.2178 | 119 | Low | 297588.4 | 0.24 | 0 | 587499.6 | 8 | 1.44 | 1.07
P005 | Services | SUP019 | 2025-01 | 2024-11-23 | 1153101.54 | 885088 | -268013.54 | 268013.54 | 1 | 2025-01-28 | 3 | 1325304.02 | -172202.48 | DOWN | 0.1493 | 66 | Low | 408327.15 | 0.366 | 4 | 476760.85 | 8 | 1.44 | 1.07
P005 | Services | SUP019 | 2025-01 | 2024-11-24 | 1060339.04 | 885088 | -175251.04 | 175251.04 | 1 | 2025-01-28 | 4 | 1153101.54 | -92762.5 | DOWN | 0.0875 | 65 | Low | 381253.92 | 0.368 | 2 | 503834.08 | 8 | 1.44 | 1.07
P005 | Software | SUP019 | 2025-02 | 2024-09-08 | 2784490.59 | 1478776 | -1305714.59 | 1305714.59 | 1 | 2025-02-28 | 1 |  |  |  |  | 173 | Low | 283330.91 | 0.11 | 0 | 1195445.09 | 7 | 1.56 | 1.03
P005 | Software | SUP019 | 2025-02 | 2024-10-27 | 2306699.14 | 1478776 | -827923.14 | 827923.14 | 1 | 2025-02-28 | 2 | 2784490.59 | -477791.45 | DOWN | 0.2071 | 124 | Low | 486025.79 | 0.225 | 3 | 992750.21 | 7 | 1.56 | 1.03
P005 | Software | SUP019 | 2025-02 | 2024-11-06 | 1914429.6 | 1478776 | -435653.6 | 435653.6 | 1 | 2025-02-28 | 3 | 2306699.14 | -392269.54 | DOWN | 0.2049 | 114 | Low | 448594.57 | 0.248 | 6 | 1030181.43 | 7 | 1.56 | 1.03
P005 | Software | SUP019 | 2025-02 | 2025-01-10 | 1744934.33 | 1478776 | -266158.33 | 266158.33 | 1 | 2025-02-28 | 4 | 1914429.6 | -169495.27 | DOWN | 0.0971 | 49 | Low | 748700.75 | 0.401 | 0 | 730075.25 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP019 | 2025-03 | 2025-01-09 | 3209281.57 | 2395850 | -813431.57 | 813431.57 | 1 | 2025-03-28 | 1 |  |  |  |  | 78 | Low | 1150052.61 | 0.355 | 0 | 1245797.39 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP019 | 2025-03 | 2025-02-23 | 2889657.15 | 2395850 | -493807.15 | 493807.15 | 1 | 2025-03-28 | 2 | 3209281.57 | -319624.42 | DOWN | 0.1106 | 33 | Medium | 1420869.95 | 0.468 | 7 | 974980.05 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP019 | 2025-03 | 2025-03-05 | 2688209.05 | 2395850 | -292359.05 | 292359.05 | 0 | 2025-03-28 | 3 | 2889657.15 | -201448.1 | DOWN | 0.0749 | 23 | Medium | 1422717.22 | 0.493 | 9 | 973132.78 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP019 | 2025-03 | 2025-03-08 | 2572091.1 | 2395850 | -176241.1 | 176241.1 | 0 | 2025-03-28 | 4 | 2688209.05 | -116117.95 | DOWN | 0.0451 | 20 | Medium | 1223305.59 | 0.5 | 4 | 1172544.41 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP019 | 2025-04 | 2025-01-03 | 1790047.57 | 1402880 | -387167.57 | 387167.57 | 1 | 2025-04-28 | 1 |  |  |  |  | 115 | Low | 448926.31 | 0.247 | 0 | 953953.69 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP019 | 2025-04 | 2025-02-20 | 1642324.5 | 1402880 | -239444.5 | 239444.5 | 0 | 2025-04-28 | 2 | 1790047.57 | -147723.07 | DOWN | 0.0899 | 67 | Low | 583395.5 | 0.36 | 6 | 819484.5 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP019 | 2025-04 | 2025-02-24 | 1556300.39 | 1402880 | -153420.39 | 153420.39 | 0 | 2025-04-28 | 3 | 1642324.5 | -86024.11 | DOWN | 0.0553 | 63 | Low | 569585.68 | 0.369 | 6 | 833294.32 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP019 | 2025-04 | 2025-03-24 | 1482657.72 | 1402880 | -79777.72 | 79777.72 | 0 | 2025-04-28 | 4 | 1556300.39 | -73642.67 | DOWN | 0.0497 | 35 | Low | 614096.8 | 0.435 | 2 | 788783.2 | 2 | 1.52 | 1.28
P005 | Services | SUP019 | 2025-05 | 2024-12-09 | 962506.43 | 671183 | -291323.43 | 291323.43 | 1 | 2025-05-28 | 1 |  |  |  |  | 170 | Low | 116678.57 | 0.123 | 1 | 554504.43 | 6 | 1.12 | 1.51
P005 | Services | SUP019 | 2025-05 | 2025-01-21 | 837271.63 | 671183 | -166088.63 | 166088.63 | 1 | 2025-05-28 | 2 | 962506.43 | -125234.8 | DOWN | 0.1496 | 127 | Low | 177631.23 | 0.229 | 0 | 493551.77 | 6 | 1.12 | 1.51
P005 | Services | SUP019 | 2025-05 | 2025-02-11 | 758340.47 | 671183 | -87157.47 | 87157.47 | 0 | 2025-05-28 | 3 | 837271.63 | -78931.16 | DOWN | 0.1041 | 106 | Low | 224395.62 | 0.281 | 1 | 446787.38 | 6 | 1.12 | 1.51
P005 | Materials | SUP019 | 2025-06 | 2025-01-04 | 1846936.24 | 1378672 | -468264.24 | 468264.24 | 1 | 2025-06-28 | 1 |  |  |  |  | 175 | Low | 196638.73 | 0.111 | 1 | 1182033.27 | 7 | 1.1 | 1.21
P005 | Materials | SUP019 | 2025-06 | 2025-01-19 | 1654410.46 | 1378672 | -275738.46 | 275738.46 | 1 | 2025-06-28 | 2 | 1846936.24 | -192525.78 | DOWN | 0.1164 | 160 | Low | 232038.9 | 0.148 | 0 | 1146633.1 | 7 | 1.1 | 1.21
P005 | Materials | SUP019 | 2025-06 | 2025-03-04 | 1554726.96 | 1378672 | -176054.96 | 176054.96 | 0 | 2025-06-28 | 3 | 1654410.46 | -99683.5 | DOWN | 0.0641 | 116 | Low | 397250.53 | 0.257 | 0 | 981421.47 | 7 | 1.1 | 1.21
P005 | Materials | SUP019 | 2025-06 | 2025-05-03 | 1495351.94 | 1378672 | -116679.94 | 116679.94 | 0 | 2025-06-28 | 4 | 1554726.96 | -59375.02 | DOWN | 0.0397 | 56 | Low | 643618.65 | 0.405 | 4 | 735053.35 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP019 | 2025-07 | 2025-02-10 | 1695485.95 | 1222977 | -472508.95 | 472508.95 | 1 | 2025-07-28 | 1 |  |  |  |  | 168 | Low | 221258.5 | 0.127 | 0 | 1001718.5 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP019 | 2025-07 | 2025-03-09 | 1514533.31 | 1222977 | -291556.31 | 291556.31 | 1 | 2025-07-28 | 2 | 1695485.95 | -180952.64 | DOWN | 0.1195 | 141 | Low | 272550.83 | 0.193 | 2 | 950426.17 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP019 | 2025-07 | 2025-07-04 | 1393445.4 | 1222977 | -170468.4 | 170468.4 | 0 | 2025-07-28 | 3 | 1514533.31 | -121087.91 | DOWN | 0.0869 | 24 | Medium | 672641.48 | 0.48 | 3 | 550335.52 | 1 | 1.18 | 1.15
P005 | Software | SUP019 | 2025-08 | 2025-04-27 | 1925180.5 | 979341 | -945839.5 | 945839.5 | 1 | 2025-08-28 | 1 |  |  |  |  | 123 | Low | 400357.01 | 0.224 | 0 | 578983.99 | 8 | 1.7 | 1.32
P005 | Software | SUP019 | 2025-08 | 2025-04-28 | 1564412.3 | 979341 | -585071.3 | 585071.3 | 1 | 2025-08-28 | 2 | 1925180.5 | -360768.2 | DOWN | 0.2306 | 122 | Low | 348234.86 | 0.226 | 0 | 631106.14 | 8 | 1.7 | 1.32
P005 | Software | SUP019 | 2025-08 | 2025-05-04 | 1345973.59 | 979341 | -366632.59 | 366632.59 | 1 | 2025-08-28 | 3 | 1564412.3 | -218438.71 | DOWN | 0.1623 | 116 | Low | 305944.55 | 0.24 | 0 | 673396.45 | 8 | 1.7 | 1.32
P005 | Software | SUP019 | 2025-08 | 2025-05-23 | 1210400.09 | 979341 | -231059.09 | 231059.09 | 1 | 2025-08-28 | 4 | 1345973.59 | -135573.5 | DOWN | 0.112 | 97 | Low | 341002.14 | 0.284 | 0 | 638338.86 | 8 | 1.7 | 1.32
P005 | Software | SUP019 | 2025-08 | 2025-06-18 | 1127455.07 | 979341 | -148114.07 | 148114.07 | 0 | 2025-08-28 | 5 | 1210400.09 | -82945.02 | DOWN | 0.0736 | 71 | Low | 379573.9 | 0.344 | 4 | 599767.1 | 8 | 1.7 | 1.32
P005 | Logistics | SUP019 | 2025-09 | 2025-05-01 | 3304510.2 | 2112352 | -1192158.2 | 1192158.2 | 1 | 2025-09-28 | 1 |  |  |  |  | 150 | Low | 582455.49 | 0.175 | 2 | 1529896.51 | 0 | 0.5 | 0.8
P005 | Logistics | SUP019 | 2025-09 | 2025-05-05 | 2846365.4 | 2112352 | -734013.4 | 734013.4 | 1 | 2025-09-28 | 2 | 3304510.2 | -458144.8 | DOWN | 0.161 | 146 | Low | 529150.29 | 0.185 | 1 | 1583201.71 | 0 | 0.5 | 0.8
P005 | Logistics | SUP019 | 2025-09 | 2025-05-19 | 2606212.45 | 2112352 | -493860.45 | 493860.45 | 1 | 2025-09-28 | 3 | 2846365.4 | -240152.95 | DOWN | 0.0921 | 132 | Low | 591661.25 | 0.22 | 3 | 1520690.75 | 0 | 0.5 | 0.8
P005 | Logistics | SUP019 | 2025-09 | 2025-08-26 | 2431036.6 | 2112352 | -318684.6 | 318684.6 | 0 | 2025-09-28 | 4 | 2606212.45 | -175175.85 | DOWN | 0.0721 | 33 | Medium | 1186394.28 | 0.468 | 8 | 925957.72 | 0 | 0.5 | 0.8
P005 | Electronics | SUP019 | 2025-10 | 2025-06-15 | 1720225.93 | 1222328 | -497897.93 | 497897.93 | 1 | 2025-10-28 | 1 |  |  |  |  | 135 | Low | 372324.87 | 0.209 | 3 | 850003.13 | 4 | 1.15 | 0.8
P005 | Electronics | SUP019 | 2025-10 | 2025-06-22 | 1535899.64 | 1222328 | -313571.64 | 313571.64 | 1 | 2025-10-28 | 2 | 1720225.93 | -184326.29 | DOWN | 0.12 | 128 | Low | 360392.94 | 0.226 | 2 | 861935.06 | 4 | 1.15 | 0.8
P005 | Electronics | SUP019 | 2025-10 | 2025-07-31 | 1397365.45 | 1222328 | -175037.45 | 175037.45 | 0 | 2025-10-28 | 3 | 1535899.64 | -138534.19 | DOWN | 0.0991 | 89 | Low | 478069.11 | 0.322 | 1 | 744258.89 | 4 | 1.15 | 0.8
P005 | Electronics | SUP019 | 2025-10 | 2025-10-04 | 1328791.92 | 1222328 | -106463.92 | 106463.92 | 0 | 2025-10-28 | 4 | 1397365.45 | -68573.53 | DOWN | 0.0516 | 24 | Medium | 610567.88 | 0.481 | 2 | 611760.12 | 4 | 1.15 | 0.8
P005 | Electronics | SUP019 | 2025-10 | 2025-10-11 | 1267531.43 | 1222328 | -45203.43 | 45203.43 | 0 | 2025-10-28 | 5 | 1328791.92 | -61260.49 | DOWN | 0.0483 | 17 | Medium | 585345.14 | 0.499 | 0 | 636982.86 | 4 | 1.15 | 0.8
P005 | Services | SUP019 | 2025-11 | 2025-07-04 | 3082831.45 | 2115584 | -967247.45 | 967247.45 | 1 | 2025-11-28 | 1 |  |  |  |  | 147 | Low | 552211.63 | 0.175 | 1 | 1563372.37 | 4 | 1.35 | 1.5
P005 | Services | SUP019 | 2025-11 | 2025-07-29 | 2683575.85 | 2115584 | -567991.85 | 567991.85 | 1 | 2025-11-28 | 2 | 3082831.45 | -399255.6 | DOWN | 0.1488 | 122 | Low | 608123.91 | 0.235 | 0 | 1507460.09 | 4 | 1.35 | 1.5
P005 | Services | SUP019 | 2025-11 | 2025-09-27 | 2458840.76 | 2115584 | -343256.76 | 343256.76 | 0 | 2025-11-28 | 3 | 2683575.85 | -224735.09 | DOWN | 0.0914 | 62 | Low | 948826.79 | 0.379 | 1 | 1166757.21 | 4 | 1.35 | 1.5
P005 | Services | SUP019 | 2025-11 | 2025-11-11 | 2334694.34 | 2115584 | -219110.34 | 219110.34 | 0 | 2025-11-28 | 4 | 2458840.76 | -124146.42 | DOWN | 0.0532 | 17 | Medium | 1115479.55 | 0.487 | 1 | 1000104.45 | 4 | 1.35 | 1.5
P005 | Materials | SUP019 | 2025-12 | 2025-08-03 | 2618001.49 | 1670890 | -947111.49 | 947111.49 | 1 | 2025-12-28 | 1 |  |  |  |  | 147 | Low | 501293.14 | 0.182 | 0 | 1169596.86 | 7 | 0.73 | 1.27
P005 | Materials | SUP019 | 2025-12 | 2025-08-05 | 2250501.7 | 1670890 | -579611.7 | 579611.7 | 1 | 2025-12-28 | 2 | 2618001.49 | -367499.79 | DOWN | 0.1633 | 145 | Low | 419352.4 | 0.188 | 1 | 1251537.6 | 7 | 0.73 | 1.27
P005 | Materials | SUP019 | 2025-12 | 2025-08-23 | 2013233.77 | 1670890 | -342343.77 | 342343.77 | 1 | 2025-12-28 | 3 | 2250501.7 | -237267.93 | DOWN | 0.1179 | 127 | Low | 442233.05 | 0.233 | 2 | 1228656.95 | 7 | 0.73 | 1.27
P005 | Materials | SUP019 | 2025-12 | 2025-09-20 | 1885503.49 | 1670890 | -214613.49 | 214613.49 | 0 | 2025-12-28 | 4 | 2013233.77 | -127730.28 | DOWN | 0.0677 | 99 | Low | 612375.95 | 0.303 | 3 | 1058514.05 | 7 | 0.73 | 1.27
P005 | Materials | SUP019 | 2025-12 | 2025-11-29 | 1813668.35 | 1670890 | -142778.35 | 142778.35 | 0 | 2025-12-28 | 5 | 1885503.49 | -71835.14 | DOWN | 0.0396 | 29 | Medium | 819435.72 | 0.478 | 2 | 851454.28 | 7 | 0.73 | 1.27
P005 | Services | SUP032 | 2025-01 | 2024-10-03 | 2259500.17 | 1292551 | -966949.17 | 966949.17 | 1 | 2025-01-28 | 1 |  |  |  |  | 117 | Low | 511888.7 | 0.222 | 0 | 780662.3 | 8 | 1.44 | 1.07
P005 | Services | SUP032 | 2025-01 | 2024-10-23 | 2034399.1 | 1292551 | -741848.1 | 741848.1 | 1 | 2025-01-28 | 2 | 2259500.17 | -225101.07 | DOWN | 0.1106 | 97 | Low | 526026.65 | 0.266 | 0 | 766524.35 | 8 | 1.44 | 1.07
P005 | Services | SUP032 | 2025-01 | 2024-12-10 | 1824167.31 | 1292551 | -531616.31 | 531616.31 | 1 | 2025-01-28 | 3 | 2034399.1 | -210231.79 | DOWN | 0.1152 | 49 | Low | 622516.08 | 0.369 | 1 | 670034.92 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP032 | 2025-02 | 2024-09-22 | 1787226.97 | 1098056 | -689170.97 | 689170.97 | 1 | 2025-02-28 | 1 |  |  |  |  | 159 | Low | 242191.25 | 0.13 | 0 | 855864.75 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP032 | 2025-02 | 2024-10-08 | 1615513.19 | 1098056 | -517457.19 | 517457.19 | 1 | 2025-02-28 | 2 | 1787226.97 | -171713.78 | DOWN | 0.1063 | 143 | Low | 247155.23 | 0.164 | 2 | 850900.77 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP032 | 2025-02 | 2024-12-05 | 1489428.07 | 1098056 | -391372.07 | 391372.07 | 1 | 2025-02-28 | 3 | 1615513.19 | -126085.12 | DOWN | 0.0847 | 85 | Low | 410367.04 | 0.287 | 1 | 687688.96 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP032 | 2025-02 | 2025-01-04 | 1383332.59 | 1098056 | -285276.59 | 285276.59 | 1 | 2025-02-28 | 4 | 1489428.07 | -106095.48 | DOWN | 0.0767 | 55 | Low | 478547.3 | 0.351 | 0 | 619508.7 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP032 | 2025-02 | 2025-01-04 | 1296713.07 | 1098056 | -198657.07 | 198657.07 | 1 | 2025-02-28 | 5 | 1383332.59 | -86619.52 | DOWN | 0.0668 | 55 | Low | 428097.77 | 0.351 | 1 | 669958.23 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP032 | 2025-02 | 2025-02-12 | 1251054.23 | 1098056 | -152998.23 | 152998.23 | 0 | 2025-02-28 | 6 | 1296713.07 | -45658.84 | DOWN | 0.0365 | 16 | Low | 572607.75 | 0.434 | 3 | 525448.25 | 7 | 1.56 | 1.03
P005 | Materials | SUP032 | 2025-03 | 2024-11-27 | 1181271.91 | 700789 | -480482.91 | 480482.91 | 1 | 2025-03-28 | 1 |  |  |  |  | 121 | Low | 263285.37 | 0.225 | 1 | 437503.63 | 0 | 0.76 | 1.01
P005 | Materials | SUP032 | 2025-03 | 2025-01-06 | 1063811.53 | 700789 | -363022.53 | 363022.53 | 1 | 2025-03-28 | 2 | 1181271.91 | -117460.38 | DOWN | 0.1104 | 81 | Low | 360767.56 | 0.316 | 3 | 340021.44 | 0 | 0.76 | 1.01
P005 | Materials | SUP032 | 2025-03 | 2025-02-03 | 966640.71 | 700789 | -265851.71 | 265851.71 | 1 | 2025-03-28 | 3 | 1063811.53 | -97170.82 | DOWN | 0.1005 | 53 | Low | 388401.83 | 0.38 | 5 | 312387.17 | 0 | 0.76 | 1.01
P005 | Materials | SUP032 | 2025-03 | 2025-03-09 | 901284.4 | 700789 | -200495.4 | 200495.4 | 1 | 2025-03-28 | 4 | 966640.71 | -65356.31 | DOWN | 0.0725 | 19 | Low | 436608.73 | 0.457 | 2 | 264180.27 | 0 | 0.76 | 1.01
P005 | Materials | SUP032 | 2025-03 | 2025-03-11 | 855167.95 | 700789 | -154378.95 | 154378.95 | 1 | 2025-03-28 | 5 | 901284.4 | -46116.45 | DOWN | 0.0539 | 17 | Low | 411740.06 | 0.461 | 5 | 289048.94 | 0 | 0.76 | 1.01
P005 | Materials | SUP032 | 2025-03 | 2025-03-16 | 823008.43 | 700789 | -122219.43 | 122219.43 | 0 | 2025-03-28 | 6 | 855167.95 | -32159.52 | DOWN | 0.0391 | 12 | Low | 417665.06 | 0.473 | 4 | 283123.94 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP032 | 2025-04 | 2024-12-08 | 1463326.1 | 1034789 | -428537.1 | 428537.1 | 1 | 2025-04-28 | 1 |  |  |  |  | 141 | Low | 251731.96 | 0.169 | 3 | 783057.04 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP032 | 2025-04 | 2025-01-28 | 1369497.4 | 1034789 | -334708.4 | 334708.4 | 1 | 2025-04-28 | 2 | 1463326.1 | -93828.7 | DOWN | 0.0685 | 90 | Low | 394916.37 | 0.278 | 3 | 639872.63 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP032 | 2025-04 | 2025-02-11 | 1301511.85 | 1034789 | -266722.85 | 266722.85 | 1 | 2025-04-28 | 3 | 1369497.4 | -67985.55 | DOWN | 0.0522 | 76 | Low | 421525.61 | 0.308 | 4 | 613263.39 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP032 | 2025-04 | 2025-02-12 | 1235613.27 | 1034789 | -200824.27 | 200824.27 | 1 | 2025-04-28 | 4 | 1301511.85 | -65898.58 | DOWN | 0.0533 | 75 | Low | 392785.47 | 0.31 | 2 | 642003.53 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP032 | 2025-04 | 2025-02-28 | 1194426.47 | 1034789 | -159637.47 | 159637.47 | 0 | 2025-04-28 | 5 | 1235613.27 | -41186.8 | DOWN | 0.0345 | 59 | Low | 412691.72 | 0.344 | 0 | 622097.28 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP032 | 2025-04 | 2025-03-23 | 1147328.84 | 1034789 | -112539.84 | 112539.84 | 0 | 2025-04-28 | 6 | 1194426.47 | -47097.63 | DOWN | 0.041 | 36 | Low | 435575.32 | 0.394 | 6 | 599213.68 | 2 | 1.52 | 1.28
P005 | Services | SUP032 | 2025-05 | 2025-01-19 | 3620027.46 | 1851753 | -1768274.46 | 1768274.46 | 1 | 2025-05-28 | 1 |  |  |  |  | 129 | Low | 790894.53 | 0.204 | 2 | 1060858.47 | 6 | 1.12 | 1.51
P005 | Services | SUP032 | 2025-05 | 2025-03-04 | 3211986.15 | 1851753 | -1360233.15 | 1360233.15 | 1 | 2025-05-28 | 2 | 3620027.46 | -408041.31 | DOWN | 0.127 | 85 | Low | 920825.8 | 0.302 | 2 | 930927.2 | 6 | 1.12 | 1.51
P005 | Services | SUP032 | 2025-05 | 2025-03-12 | 2912667.69 | 1851753 | -1060914.69 | 1060914.69 | 1 | 2025-05-28 | 3 | 3211986.15 | -299318.46 | DOWN | 0.1028 | 77 | Low | 949444.11 | 0.32 | 1 | 902308.89 | 6 | 1.12 | 1.51
P005 | Services | SUP032 | 2025-05 | 2025-03-16 | 2633304.99 | 1851753 | -781551.99 | 781551.99 | 1 | 2025-05-28 | 4 | 2912667.69 | -279362.7 | DOWN | 0.1061 | 73 | Low | 929534.08 | 0.329 | 1 | 922218.92 | 6 | 1.12 | 1.51
P005 | Services | SUP032 | 2025-05 | 2025-03-19 | 2412396.75 | 1851753 | -560643.75 | 560643.75 | 1 | 2025-05-28 | 5 | 2633304.99 | -220908.24 | DOWN | 0.0916 | 70 | Low | 845814.08 | 0.336 | 0 | 1005938.92 | 6 | 1.12 | 1.51
P005 | Services | SUP032 | 2025-05 | 2025-03-29 | 2281491.8 | 1851753 | -429738.8 | 429738.8 | 1 | 2025-05-28 | 6 | 2412396.75 | -130904.95 | DOWN | 0.0574 | 60 | Low | 788358.31 | 0.358 | 0 | 1063394.69 | 6 | 1.12 | 1.51
P005 | Materials | SUP032 | 2025-06 | 2025-01-13 | 2068035.73 | 1194479 | -873556.73 | 873556.73 | 1 | 2025-06-28 | 1 |  |  |  |  | 166 | Low | 242380.81 | 0.121 | 0 | 952098.19 | 7 | 1.1 | 1.21
P005 | Materials | SUP032 | 2025-06 | 2025-02-15 | 1841170.78 | 1194479 | -646691.78 | 646691.78 | 1 | 2025-06-28 | 2 | 2068035.73 | -226864.95 | DOWN | 0.1232 | 133 | Low | 343302.37 | 0.195 | 2 | 851176.63 | 7 | 1.1 | 1.21
P005 | Materials | SUP032 | 2025-06 | 2025-03-20 | 1683023 | 1194479 | -488544 | 488544 | 1 | 2025-06-28 | 3 | 1841170.78 | -158147.78 | DOWN | 0.094 | 100 | Low | 456382.16 | 0.269 | 1 | 738096.84 | 7 | 1.1 | 1.21
P005 | Materials | SUP032 | 2025-06 | 2025-04-03 | 1568822.31 | 1194479 | -374343.31 | 374343.31 | 1 | 2025-06-28 | 4 | 1683023 | -114200.69 | DOWN | 0.0728 | 86 | Low | 463890.87 | 0.301 | 3 | 730588.13 | 7 | 1.1 | 1.21
P005 | Materials | SUP032 | 2025-06 | 2025-04-11 | 1480719.06 | 1194479 | -286240.06 | 286240.06 | 1 | 2025-06-28 | 5 | 1568822.31 | -88103.25 | DOWN | 0.0595 | 78 | Low | 461263.16 | 0.319 | 2 | 733215.84 | 7 | 1.1 | 1.21
P005 | Materials | SUP032 | 2025-07 | 2025-03-07 | 2242181.41 | 1400245 | -841936.41 | 841936.41 | 1 | 2025-07-28 | 1 |  |  |  |  | 143 | Low | 387291.33 | 0.171 | 1 | 1012953.67 | 1 | 1.18 | 1.15
P005 | Materials | SUP032 | 2025-07 | 2025-03-21 | 2035979.24 | 1400245 | -635734.24 | 635734.24 | 1 | 2025-07-28 | 2 | 2242181.41 | -206202.17 | DOWN | 0.1013 | 129 | Low | 407228.21 | 0.202 | 1 | 993016.79 | 1 | 1.18 | 1.15
P005 | Materials | SUP032 | 2025-07 | 2025-05-22 | 1872601.54 | 1400245 | -472356.54 | 472356.54 | 1 | 2025-07-28 | 3 | 2035979.24 | -163377.7 | DOWN | 0.0872 | 67 | Low | 659879.88 | 0.34 | 0 | 740365.12 | 1 | 1.18 | 1.15
P005 | Materials | SUP032 | 2025-07 | 2025-05-30 | 1766492.47 | 1400245 | -366247.47 | 366247.47 | 1 | 2025-07-28 | 4 | 1872601.54 | -106109.07 | DOWN | 0.0601 | 59 | Low | 625568.54 | 0.358 | 1 | 774676.46 | 1 | 1.18 | 1.15
P005 | Materials | SUP032 | 2025-07 | 2025-06-02 | 1682335.14 | 1400245 | -282090.14 | 282090.14 | 1 | 2025-07-28 | 5 | 1766492.47 | -84157.33 | DOWN | 0.05 | 56 | Low | 662027.07 | 0.365 | 0 | 738217.93 | 1 | 1.18 | 1.15
P005 | Materials | SUP032 | 2025-07 | 2025-07-10 | 1613691.68 | 1400245 | -213446.68 | 213446.68 | 0 | 2025-07-28 | 6 | 1682335.14 | -68643.46 | DOWN | 0.0425 | 18 | Low | 776389.57 | 0.449 | 6 | 623855.43 | 1 | 1.18 | 1.15
P005 | Electronics | SUP032 | 2025-08 | 2025-03-19 | 779754.67 | 430806 | -348948.67 | 348948.67 | 1 | 2025-08-28 | 1 |  |  |  |  | 162 | Low | 97050.5 | 0.122 | 0 | 333755.5 | 8 | 1.7 | 1.32
P005 | Electronics | SUP032 | 2025-08 | 2025-04-03 | 691433.7 | 430806 | -260627.7 | 260627.7 | 1 | 2025-08-28 | 2 | 779754.67 | -88320.97 | DOWN | 0.1277 | 147 | Low | 98852.08 | 0.153 | 0 | 331953.92 | 8 | 1.7 | 1.32
P005 | Electronics | SUP032 | 2025-08 | 2025-04-09 | 626979.4 | 430806 | -196173.4 | 196173.4 | 1 | 2025-08-28 | 3 | 691433.7 | -64454.3 | DOWN | 0.1028 | 141 | Low | 99193.32 | 0.166 | 6 | 331612.68 | 8 | 1.7 | 1.32
P005 | Electronics | SUP032 | 2025-08 | 2025-05-13 | 581296.23 | 430806 | -150490.23 | 150490.23 | 1 | 2025-08-28 | 4 | 626979.4 | -45683.17 | DOWN | 0.0786 | 107 | Low | 147508.65 | 0.237 | 3 | 283297.35 | 8 | 1.7 | 1.32
P005 | Electronics | SUP032 | 2025-08 | 2025-06-05 | 534368.46 | 430806 | -103562.46 | 103562.46 | 1 | 2025-08-28 | 5 | 581296.23 | -46927.77 | DOWN | 0.0878 | 84 | Low | 150394.73 | 0.285 | 3 | 280411.27 | 8 | 1.7 | 1.32
P005 | Logistics | SUP032 | 2025-09 | 2025-04-25 | 3594513.8 | 1851301 | -1743212.8 | 1743212.8 | 1 | 2025-09-28 | 1 |  |  |  |  | 156 | Low | 552574.28 | 0.145 | 1 | 1298726.72 | 0 | 0.5 | 0.8
P005 | Logistics | SUP032 | 2025-09 | 2025-05-11 | 3221156.52 | 1851301 | -1369855.52 | 1369855.52 | 1 | 2025-09-28 | 2 | 3594513.8 | -373357.28 | DOWN | 0.1159 | 140 | Low | 563984.9 | 0.182 | 1 | 1287316.1 | 0 | 0.5 | 0.8
P005 | Logistics | SUP032 | 2025-09 | 2025-06-21 | 2839662.06 | 1851301 | -988361.06 | 988361.06 | 1 | 2025-09-28 | 3 | 3221156.52 | -381494.46 | DOWN | 0.1343 | 99 | Low | 785131.97 | 0.275 | 5 | 1066169.03 | 0 | 0.5 | 0.8
P005 | Logistics | SUP032 | 2025-09 | 2025-07-28 | 2587122.83 | 1851301 | -735821.83 | 735821.83 | 1 | 2025-09-28 | 4 | 2839662.06 | -252539.23 | DOWN | 0.0976 | 62 | Low | 952670 | 0.359 | 1 | 898631 | 0 | 0.5 | 0.8
P005 | Logistics | SUP032 | 2025-09 | 2025-09-14 | 2415476.03 | 1851301 | -564175.03 | 564175.03 | 1 | 2025-09-28 | 5 | 2587122.83 | -171646.8 | DOWN | 0.0711 | 14 | Low | 1216430.2 | 0.468 | 3 | 634870.8 | 0 | 0.5 | 0.8
P005 | Services | SUP032 | 2025-10 | 2025-06-07 | 3585488.17 | 1811211 | -1774277.17 | 1774277.17 | 1 | 2025-10-28 | 1 |  |  |  |  | 143 | Low | 597417.21 | 0.172 | 3 | 1213793.79 | 4 | 1.15 | 0.8
P005 | Services | SUP032 | 2025-10 | 2025-06-21 | 3094190.49 | 1811211 | -1282979.49 | 1282979.49 | 1 | 2025-10-28 | 2 | 3585488.17 | -491297.68 | DOWN | 0.1588 | 129 | Low | 677820.62 | 0.203 | 0 | 1133390.38 | 4 | 1.15 | 0.8
P005 | Services | SUP032 | 2025-10 | 2025-08-10 | 2751648.4 | 1811211 | -940437.4 | 940437.4 | 1 | 2025-10-28 | 3 | 3094190.49 | -342542.09 | DOWN | 0.1245 | 79 | Low | 864533.07 | 0.315 | 0 | 946677.93 | 4 | 1.15 | 0.8
P005 | Logistics | SUP032 | 2025-11 | 2025-06-15 | 2837434.2 | 1307377 | -1530057.2 | 1530057.2 | 1 | 2025-11-28 | 1 |  |  |  |  | 166 | Low | 338251.04 | 0.118 | 0 | 969125.96 | 4 | 1.35 | 1.5
P005 | Logistics | SUP032 | 2025-11 | 2025-07-09 | 2410299.67 | 1307377 | -1102922.67 | 1102922.67 | 1 | 2025-11-28 | 2 | 2837434.2 | -427134.53 | DOWN | 0.1772 | 142 | Low | 378156.68 | 0.17 | 3 | 929220.32 | 4 | 1.35 | 1.5
P005 | Logistics | SUP032 | 2025-11 | 2025-08-16 | 2092317.56 | 1307377 | -784940.56 | 784940.56 | 1 | 2025-11-28 | 3 | 2410299.67 | -317982.11 | DOWN | 0.152 | 104 | Low | 531494.36 | 0.253 | 5 | 775882.64 | 4 | 1.35 | 1.5
P005 | Logistics | SUP032 | 2025-11 | 2025-10-23 | 1889795.26 | 1307377 | -582418.26 | 582418.26 | 1 | 2025-11-28 | 4 | 2092317.56 | -202522.3 | DOWN | 0.1072 | 36 | Low | 766971.47 | 0.401 | 0 | 540405.53 | 4 | 1.35 | 1.5
P005 | Materials | SUP032 | 2025-12 | 2025-07-12 | 3209869.11 | 1986036 | -1223833.11 | 1223833.11 | 1 | 2025-12-28 | 1 |  |  |  |  | 169 | Low | 348370.79 | 0.116 | 0 | 1637665.21 | 7 | 0.73 | 1.27
P005 | Materials | SUP032 | 2025-12 | 2025-09-23 | 2909894.82 | 1986036 | -923858.82 | 923858.82 | 1 | 2025-12-28 | 2 | 3209869.11 | -299974.29 | DOWN | 0.1031 | 96 | Low | 783071.02 | 0.282 | 2 | 1202964.98 | 7 | 0.73 | 1.27
P005 | Materials | SUP032 | 2025-12 | 2025-09-25 | 2693824.05 | 1986036 | -707788.05 | 707788.05 | 1 | 2025-12-28 | 3 | 2909894.82 | -216070.77 | DOWN | 0.0802 | 94 | Low | 721314.7 | 0.286 | 3 | 1264721.3 | 7 | 0.73 | 1.27
P005 | Materials | SUP032 | 2025-12 | 2025-09-29 | 2523348.17 | 1986036 | -537312.17 | 537312.17 | 1 | 2025-12-28 | 4 | 2693824.05 | -170475.88 | DOWN | 0.0676 | 90 | Low | 801975.41 | 0.295 | 1 | 1184060.59 | 7 | 0.73 | 1.27
P005 | Materials | SUP045 | 2025-01 | 2024-08-05 | 167671.84 | 134140 | -33531.84 | 33531.84 | 1 | 2025-01-28 | 1 |  |  |  |  | 176 | Low | 22992.41 | 0.148 | 6 | 111147.59 | 8 | 1.44 | 1.07
P005 | Materials | SUP045 | 2025-01 | 2024-08-17 | 147268.16 | 134140 | -13128.16 | 13128.16 | 0 | 2025-01-28 | 2 | 167671.84 | -20403.68 | DOWN | 0.1385 | 164 | Low | 27611.81 | 0.189 | 3 | 106528.19 | 8 | 1.44 | 1.07
P005 | Materials | SUP045 | 2025-01 | 2024-08-31 | 141153.14 | 134140 | -7013.14 | 7013.14 | 0 | 2025-01-28 | 3 | 147268.16 | -6115.02 | DOWN | 0.0433 | 150 | Low | 31730.81 | 0.236 | 0 | 102409.19 | 8 | 1.44 | 1.07
P005 | Materials | SUP045 | 2025-01 | 2024-12-17 | 136909.17 | 134140 | -2769.17 | 2769.17 | 0 | 2025-01-28 | 4 | 141153.14 | -4243.97 | DOWN | 0.031 | 42 | Medium | 81747.73 | 0.599 | 7 | 52392.27 | 8 | 1.44 | 1.07
P005 | Materials | SUP045 | 2025-01 | 2024-12-21 | 135030.71 | 134140 | -890.71 | 890.71 | 0 | 2025-01-28 | 5 | 136909.17 | -1878.46 | DOWN | 0.0139 | 38 | Medium | 78259.27 | 0.613 | 3 | 55880.73 | 8 | 1.44 | 1.07
P005 | Software | SUP045 | 2025-02 | 2025-01-04 | 3132312.7 | 2014149 | -1118163.7 | 1118163.7 | 1 | 2025-02-28 | 1 |  |  |  |  | 55 | Medium | 1799223.02 | 0.548 | 5 | 214925.98 | 7 | 1.56 | 1.03
P005 | Software | SUP045 | 2025-02 | 2025-01-12 | 2539848.72 | 2014149 | -525699.72 | 525699.72 | 1 | 2025-02-28 | 2 | 3132312.7 | -592463.98 | DOWN | 0.2333 | 47 | Low | 1422305.46 | 0.575 | 4 | 591843.54 | 7 | 1.56 | 1.03
P005 | Software | SUP045 | 2025-02 | 2025-02-08 | 2266701.48 | 2014149 | -252552.48 | 252552.48 | 0 | 2025-02-28 | 3 | 2539848.72 | -273147.24 | DOWN | 0.1205 | 20 | Low | 1461424.06 | 0.664 | 4 | 552724.94 | 7 | 1.56 | 1.03
P005 | Software | SUP045 | 2025-02 | 2025-02-12 | 2141069.58 | 2014149 | -126920.58 | 126920.58 | 0 | 2025-02-28 | 4 | 2266701.48 | -125631.9 | DOWN | 0.0587 | 16 | Medium | 1422076.63 | 0.678 | 2 | 592072.37 | 7 | 1.56 | 1.03
P005 | Software | SUP045 | 2025-02 | 2025-02-16 | 2098036.51 | 2014149 | -83887.51 | 83887.51 | 0 | 2025-02-28 | 5 | 2141069.58 | -43033.07 | DOWN | 0.0205 | 12 | Medium | 1442735.49 | 0.691 | 4 | 571413.51 | 7 | 1.56 | 1.03
P005 | Materials | SUP045 | 2025-03 | 2024-10-13 | 1746546.89 | 1424345 | -322201.89 | 322201.89 | 1 | 2025-03-28 | 1 |  |  |  |  | 166 | Low | 332665.04 | 0.191 | 2 | 1091679.96 | 0 | 0.76 | 1.01
P005 | Materials | SUP045 | 2025-03 | 2024-10-15 | 1581412.09 | 1424345 | -157067.09 | 157067.09 | 0 | 2025-03-28 | 2 | 1746546.89 | -165134.8 | DOWN | 0.1044 | 164 | Low | 329684.19 | 0.199 | 0 | 1094660.81 | 0 | 0.76 | 1.01
P005 | Materials | SUP045 | 2025-03 | 2024-10-27 | 1496294.62 | 1424345 | -71949.62 | 71949.62 | 0 | 2025-03-28 | 3 | 1581412.09 | -85117.47 | DOWN | 0.0569 | 152 | Low | 363877.57 | 0.241 | 1 | 1060467.43 | 0 | 0.76 | 1.01
P005 | Materials | SUP045 | 2025-03 | 2024-11-19 | 1462972.13 | 1424345 | -38627.13 | 38627.13 | 0 | 2025-03-28 | 4 | 1496294.62 | -33322.49 | DOWN | 0.0228 | 129 | Low | 481505.12 | 0.323 | 0 | 942839.88 | 0 | 0.76 | 1.01
P005 | Materials | SUP045 | 2025-03 | 2024-12-08 | 1451277.4 | 1424345 | -26932.4 | 26932.4 | 0 | 2025-03-28 | 5 | 1462972.13 | -11694.73 | DOWN | 0.0081 | 110 | Low | 575372.62 | 0.39 | 3 | 848972.38 | 0 | 0.76 | 1.01
P005 | Logistics | SUP045 | 2025-04 | 2025-01-27 | 2622202.57 | 1737000 | -885202.57 | 885202.57 | 1 | 2025-04-28 | 1 |  |  |  |  | 91 | Low | 1145692.41 | 0.431 | 3 | 591307.59 | 2 | 1.52 | 1.28
P005 | Logistics | SUP045 | 2025-04 | 2025-04-05 | 2102771.05 | 1737000 | -365771.05 | 365771.05 | 1 | 2025-04-28 | 2 | 2622202.57 | -519431.52 | DOWN | 0.247 | 23 | Low | 1337233.8 | 0.657 | 2 | 399766.2 | 2 | 1.52 | 1.28
P005 | Logistics | SUP045 | 2025-04 | 2025-04-09 | 1917198.03 | 1737000 | -180198.03 | 180198.03 | 0 | 2025-04-28 | 3 | 2102771.05 | -185573.02 | DOWN | 0.0968 | 19 | Medium | 1255666.16 | 0.671 | 5 | 481333.84 | 2 | 1.52 | 1.28
P005 | Services | SUP045 | 2025-05 | 2024-12-16 | 2839672.79 | 1822194 | -1017478.79 | 1017478.79 | 1 | 2025-05-28 | 1 |  |  |  |  | 163 | Low | 584270.67 | 0.199 | 0 | 1237923.33 | 6 | 1.12 | 1.51
P005 | Services | SUP045 | 2025-05 | 2025-02-01 | 2302238.85 | 1822194 | -480044.85 | 480044.85 | 1 | 2025-05-28 | 2 | 2839672.79 | -537433.94 | DOWN | 0.2334 | 116 | Low | 794044.35 | 0.363 | 2 | 1028149.65 | 6 | 1.12 | 1.51
P005 | Services | SUP045 | 2025-05 | 2025-03-13 | 2037785.25 | 1822194 | -215591.25 | 215591.25 | 0 | 2025-05-28 | 3 | 2302238.85 | -264453.6 | DOWN | 0.1298 | 76 | Low | 1000335.88 | 0.503 | 5 | 821858.12 | 6 | 1.12 | 1.51
P005 | Services | SUP045 | 2025-05 | 2025-03-17 | 1913059.55 | 1822194 | -90865.55 | 90865.55 | 0 | 2025-05-28 | 4 | 2037785.25 | -124725.7 | DOWN | 0.0652 | 72 | Low | 915319.75 | 0.517 | 4 | 906874.25 | 6 | 1.12 | 1.51
P005 | Services | SUP045 | 2025-05 | 2025-04-18 | 1852236.43 | 1822194 | -30042.43 | 30042.43 | 0 | 2025-05-28 | 5 | 1913059.55 | -60823.12 | DOWN | 0.0328 | 40 | Medium | 1213053.52 | 0.629 | 3 | 609140.48 | 6 | 1.12 | 1.51
P005 | Services | SUP045 | 2025-05 | 2025-05-10 | 1850010.61 | 1822194 | -27816.61 | 27816.61 | 0 | 2025-05-28 | 6 | 1852236.43 | -2225.82 | DOWN | 0.0012 | 18 | High | 1291733.26 | 0.706 | 3 | 530460.74 | 6 | 1.12 | 1.51
P005 | Services | SUP045 | 2025-06 | 2025-02-04 | 3301654.52 | 2270139 | -1031515.52 | 1031515.52 | 1 | 2025-06-28 | 1 |  |  |  |  | 144 | Low | 904732.63 | 0.266 | 0 | 1365406.37 | 7 | 1.1 | 1.21
P005 | Services | SUP045 | 2025-06 | 2025-03-18 | 2773063.49 | 2270139 | -502924.49 | 502924.49 | 1 | 2025-06-28 | 2 | 3301654.52 | -528591.03 | DOWN | 0.1906 | 102 | Low | 1079604.27 | 0.413 | 3 | 1190534.73 | 7 | 1.1 | 1.21
P005 | Services | SUP045 | 2025-06 | 2025-05-13 | 2531086.43 | 2270139 | -260947.43 | 260947.43 | 0 | 2025-06-28 | 3 | 2773063.49 | -241977.06 | DOWN | 0.0956 | 46 | Medium | 1609680.97 | 0.61 | 4 | 660458.03 | 7 | 1.1 | 1.21
P005 | Services | SUP045 | 2025-06 | 2025-05-22 | 2381677.9 | 2270139 | -111538.9 | 111538.9 | 0 | 2025-06-28 | 4 | 2531086.43 | -149408.53 | DOWN | 0.0627 | 37 | Medium | 1588192.18 | 0.641 | 6 | 681946.82 | 7 | 1.1 | 1.21
P005 | Materials | SUP045 | 2025-07 | 2025-02-03 | 803251.61 | 587069 | -216182.61 | 216182.61 | 1 | 2025-07-28 | 1 |  |  |  |  | 175 | Low | 134586.31 | 0.156 | 3 | 452482.69 | 1 | 1.18 | 1.15
P005 | Materials | SUP045 | 2025-07 | 2025-02-24 | 683704.84 | 587069 | -96635.84 | 96635.84 | 0 | 2025-07-28 | 2 | 803251.61 | -119546.77 | DOWN | 0.1749 | 154 | Low | 145054.72 | 0.229 | 0 | 442014.28 | 1 | 1.18 | 1.15
P005 | Materials | SUP045 | 2025-07 | 2025-04-04 | 633243.92 | 587069 | -46174.92 | 46174.92 | 0 | 2025-07-28 | 3 | 683704.84 | -50460.92 | DOWN | 0.0797 | 115 | Low | 244697.24 | 0.364 | 4 | 342371.76 | 1 | 1.18 | 1.15
P005 | Materials | SUP045 | 2025-07 | 2025-04-14 | 612016.05 | 587069 | -24947.05 | 24947.05 | 0 | 2025-07-28 | 4 | 633243.92 | -21227.87 | DOWN | 0.0347 | 105 | Low | 232736.97 | 0.399 | 0 | 354332.03 | 1 | 1.18 | 1.15
P005 | Materials | SUP045 | 2025-07 | 2025-05-03 | 596660.37 | 587069 | -9591.37 | 9591.37 | 0 | 2025-07-28 | 5 | 612016.05 | -15355.68 | DOWN | 0.0257 | 86 | Low | 255771.48 | 0.465 | 4 | 331297.52 | 1 | 1.18 | 1.15
P005 | Materials | SUP045 | 2025-07 | 2025-05-17 | 590001.1 | 587069 | -2932.1 | 2932.1 | 0 | 2025-07-28 | 6 | 596660.37 | -6659.27 | DOWN | 0.0113 | 72 | Low | 287661.55 | 0.514 | 5 | 299407.45 | 1 | 1.18 | 1.15
P005 | Logistics | SUP045 | 2025-08 | 2025-05-05 | 2033770.37 | 1151465 | -882305.37 | 882305.37 | 1 | 2025-08-28 | 1 |  |  |  |  | 115 | Low | 694153.45 | 0.343 | 3 | 457311.55 | 8 | 1.7 | 1.32
P005 | Logistics | SUP045 | 2025-08 | 2025-05-26 | 1525338.79 | 1151465 | -373873.79 | 373873.79 | 1 | 2025-08-28 | 2 | 2033770.37 | -508431.58 | DOWN | 0.3333 | 94 | Low | 614570.58 | 0.412 | 2 | 536894.42 | 8 | 1.7 | 1.32
P005 | Logistics | SUP045 | 2025-08 | 2025-05-26 | 1284183.57 | 1151465 | -132718.57 | 132718.57 | 0 | 2025-08-28 | 3 | 1525338.79 | -241155.22 | DOWN | 0.1878 | 94 | Low | 571559.98 | 0.412 | 2 | 579905.02 | 8 | 1.7 | 1.32
P005 | Logistics | SUP045 | 2025-08 | 2025-06-20 | 1235691.39 | 1151465 | -84226.39 | 84226.39 | 0 | 2025-08-28 | 4 | 1284183.57 | -48492.18 | DOWN | 0.0392 | 69 | Low | 579285.33 | 0.494 | 4 | 572179.67 | 8 | 1.7 | 1.32
P005 | Logistics | SUP045 | 2025-08 | 2025-06-28 | 1157670.4 | 1151465 | -6205.4 | 6205.4 | 0 | 2025-08-28 | 5 | 1235691.39 | -78020.99 | DOWN | 0.0674 | 61 | Low | 593803.14 | 0.52 | 5 | 557661.86 | 8 | 1.7 | 1.32
P005 | Logistics | SUP045 | 2025-08 | 2025-07-07 | 1156291.07 | 1151465 | -4826.07 | 4826.07 | 0 | 2025-08-28 | 6 | 1157670.4 | -1379.33 | DOWN | 0.0012 | 52 | Medium | 651811.1 | 0.549 | 7 | 499653.9 | 8 | 1.7 | 1.32
P005 | Software | SUP045 | 2025-09 | 2025-06-11 | 1990597.35 | 1265602 | -724995.35 | 724995.35 | 1 | 2025-09-28 | 1 |  |  |  |  | 109 | Low | 794874.43 | 0.394 | 3 | 470727.57 | 0 | 0.5 | 0.8
P005 | Software | SUP045 | 2025-09 | 2025-07-04 | 1609367.64 | 1265602 | -343765.64 | 343765.64 | 1 | 2025-09-28 | 2 | 1990597.35 | -381229.71 | DOWN | 0.2369 | 86 | Low | 824282.9 | 0.475 | 3 | 441319.1 | 0 | 0.5 | 0.8
P005 | Software | SUP045 | 2025-09 | 2025-07-24 | 1417946.09 | 1265602 | -152344.09 | 152344.09 | 0 | 2025-09-28 | 3 | 1609367.64 | -191421.55 | DOWN | 0.135 | 66 | Low | 791502.8 | 0.546 | 3 | 474099.2 | 0 | 0.5 | 0.8
P005 | Software | SUP045 | 2025-09 | 2025-08-03 | 1349122.84 | 1265602 | -83520.84 | 83520.84 | 0 | 2025-09-28 | 4 | 1417946.09 | -68823.25 | DOWN | 0.051 | 56 | Medium | 826101.38 | 0.581 | 3 | 439500.62 | 0 | 0.5 | 0.8
P005 | Materials | SUP045 | 2025-10 | 2025-06-13 | 2238967.57 | 1742572 | -496395.57 | 496395.57 | 1 | 2025-10-28 | 1 |  |  |  |  | 137 | Low | 664250.67 | 0.289 | 0 | 1078321.33 | 4 | 1.15 | 0.8
P005 | Materials | SUP045 | 2025-10 | 2025-07-18 | 1964065.14 | 1742572 | -221493.14 | 221493.14 | 0 | 2025-10-28 | 2 | 2238967.57 | -274902.43 | DOWN | 0.14 | 102 | Low | 862710.89 | 0.411 | 2 | 879861.11 | 4 | 1.15 | 0.8
P005 | Materials | SUP045 | 2025-10 | 2025-07-30 | 1843518.95 | 1742572 | -100946.95 | 100946.95 | 0 | 2025-10-28 | 3 | 1964065.14 | -120546.19 | DOWN | 0.0654 | 90 | Low | 845908.88 | 0.453 | 0 | 896663.12 | 4 | 1.15 | 0.8
P005 | Materials | SUP045 | 2025-10 | 2025-09-10 | 1791108.86 | 1742572 | -48536.86 | 48536.86 | 0 | 2025-10-28 | 4 | 1843518.95 | -52410.09 | DOWN | 0.0293 | 48 | Medium | 1156385.26 | 0.599 | 4 | 586186.74 | 4 | 1.15 | 0.8
P005 | Materials | SUP045 | 2025-10 | 2025-09-24 | 1765518.94 | 1742572 | -22946.94 | 22946.94 | 0 | 2025-10-28 | 5 | 1791108.86 | -25589.92 | DOWN | 0.0145 | 34 | Medium | 1229077.5 | 0.648 | 6 | 513494.5 | 4 | 1.15 | 0.8
P005 | Logistics | SUP045 | 2025-11 | 2025-08-09 | 2225388.03 | 1304013 | -921375.03 | 921375.03 | 1 | 2025-11-28 | 1 |  |  |  |  | 111 | Low | 766473.71 | 0.371 | 4 | 537539.29 | 4 | 1.35 | 1.5
P005 | Logistics | SUP045 | 2025-11 | 2025-09-25 | 1758696.08 | 1304013 | -454683.08 | 454683.08 | 1 | 2025-11-28 | 2 | 2225388.03 | -466691.95 | DOWN | 0.2654 | 64 | Low | 967487.17 | 0.531 | 1 | 336525.83 | 4 | 1.35 | 1.5
P005 | Logistics | SUP045 | 2025-11 | 2025-10-31 | 1479900.36 | 1304013 | -175887.36 | 175887.36 | 0 | 2025-11-28 | 3 | 1758696.08 | -278795.72 | DOWN | 0.1884 | 28 | Low | 996292.21 | 0.653 | 5 | 307720.79 | 4 | 1.35 | 1.5
P005 | Mechanical | SUP045 | 2025-12 | 2025-08-14 | 1982169.48 | 1542177 | -439992.48 | 439992.48 | 1 | 2025-12-28 | 1 |  |  |  |  | 136 | Low | 620488.63 | 0.298 | 2 | 921688.37 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP045 | 2025-12 | 2025-09-20 | 1743993.56 | 1542177 | -201816.56 | 201816.56 | 0 | 2025-12-28 | 2 | 1982169.48 | -238175.92 | DOWN | 0.1366 | 99 | Low | 783989.23 | 0.429 | 1 | 758187.77 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP045 | 2025-12 | 2025-09-21 | 1626280.38 | 1542177 | -84103.38 | 84103.38 | 0 | 2025-12-28 | 3 | 1743993.56 | -117713.18 | DOWN | 0.0724 | 98 | Low | 697030.75 | 0.433 | 1 | 845146.25 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP040 | 2025-01 | 2024-08-23 | 1085893.61 | 692563 | -393330.61 | 393330.61 | 1 | 2025-01-28 | 1 |  |  |  |  | 158 | Low | 189244.84 | 0.174 | 0 | 503318.16 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP040 | 2025-01 | 2024-10-04 | 913380.3 | 692563 | -220817.3 | 220817.3 | 1 | 2025-01-28 | 2 | 1085893.61 | -172513.31 | DOWN | 0.1889 | 116 | Low | 247726.63 | 0.292 | 3 | 444836.37 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP040 | 2025-01 | 2024-11-05 | 812517.78 | 692563 | -119954.78 | 119954.78 | 0 | 2025-01-28 | 3 | 913380.3 | -100862.52 | DOWN | 0.1241 | 84 | Low | 312449.1 | 0.382 | 3 | 380113.9 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP040 | 2025-01 | 2024-11-16 | 759008.06 | 692563 | -66445.06 | 66445.06 | 0 | 2025-01-28 | 4 | 812517.78 | -53509.72 | DOWN | 0.0705 | 73 | Low | 309489.48 | 0.413 | 3 | 383073.52 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP040 | 2025-01 | 2024-12-12 | 725793.42 | 692563 | -33230.42 | 33230.42 | 0 | 2025-01-28 | 5 | 759008.06 | -33214.64 | DOWN | 0.0458 | 47 | Medium | 344765.29 | 0.486 | 3 | 347797.71 | 8 | 1.44 | 1.07
P005 | Software | SUP040 | 2025-02 | 2024-09-11 | 1641269.9 | 863879 | -777390.9 | 777390.9 | 1 | 2025-02-28 | 1 |  |  |  |  | 170 | Low | 211193.82 | 0.138 | 1 | 652685.18 | 7 | 1.56 | 1.03
P005 | Software | SUP040 | 2025-02 | 2024-11-16 | 1331215.68 | 863879 | -467336.68 | 467336.68 | 1 | 2025-02-28 | 2 | 1641269.9 | -310054.22 | DOWN | 0.2329 | 104 | Low | 400770.47 | 0.321 | 5 | 463108.53 | 7 | 1.56 | 1.03
P005 | Software | SUP040 | 2025-02 | 2024-11-25 | 1110002.48 | 863879 | -246123.48 | 246123.48 | 1 | 2025-02-28 | 3 | 1331215.68 | -221213.2 | DOWN | 0.1993 | 95 | Low | 403876.51 | 0.346 | 3 | 460002.49 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP040 | 2025-03 | 2024-10-28 | 2582948.6 | 1930115 | -652833.6 | 652833.6 | 1 | 2025-03-28 | 1 |  |  |  |  | 151 | Low | 503030.02 | 0.204 | 0 | 1427084.98 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP040 | 2025-03 | 2024-12-01 | 2289110.98 | 1930115 | -358995.98 | 358995.98 | 1 | 2025-03-28 | 2 | 2582948.6 | -293837.62 | DOWN | 0.1284 | 117 | Low | 661434.31 | 0.304 | 0 | 1268680.69 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP040 | 2025-03 | 2025-01-11 | 2134842.87 | 1930115 | -204727.87 | 204727.87 | 0 | 2025-03-28 | 3 | 2289110.98 | -154268.11 | DOWN | 0.0723 | 76 | Low | 887579.95 | 0.425 | 1 | 1042535.05 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP040 | 2025-03 | 2025-01-28 | 2031481.9 | 1930115 | -101366.9 | 101366.9 | 0 | 2025-03-28 | 4 | 2134842.87 | -103360.97 | DOWN | 0.0509 | 59 | Medium | 999583.12 | 0.476 | 2 | 930531.88 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP040 | 2025-03 | 2025-02-04 | 1980060.64 | 1930115 | -49945.64 | 49945.64 | 0 | 2025-03-28 | 5 | 2031481.9 | -51421.26 | DOWN | 0.026 | 52 | Medium | 1018307.02 | 0.496 | 2 | 911807.98 | 0 | 0.76 | 1.01
P005 | Materials | SUP040 | 2025-04 | 2024-11-27 | 1989505.15 | 1299471 | -690034.15 | 690034.15 | 1 | 2025-04-28 | 1 |  |  |  |  | 152 | Low | 351804.34 | 0.189 | 2 | 947666.66 | 2 | 1.52 | 1.28
P005 | Materials | SUP040 | 2025-04 | 2024-12-11 | 1665622.8 | 1299471 | -366151.8 | 366151.8 | 1 | 2025-04-28 | 2 | 1989505.15 | -323882.35 | DOWN | 0.1945 | 138 | Low | 380732.12 | 0.228 | 3 | 918738.88 | 2 | 1.52 | 1.28
P005 | Materials | SUP040 | 2025-04 | 2025-02-03 | 1492403.44 | 1299471 | -192932.44 | 192932.44 | 0 | 2025-04-28 | 3 | 1665622.8 | -173219.36 | DOWN | 0.1161 | 84 | Low | 586875.31 | 0.378 | 3 | 712595.69 | 2 | 1.52 | 1.28
P005 | Materials | SUP040 | 2025-04 | 2025-03-15 | 1390705.82 | 1299471 | -91234.82 | 91234.82 | 0 | 2025-04-28 | 4 | 1492403.44 | -101697.62 | DOWN | 0.0731 | 44 | Medium | 649446.06 | 0.489 | 4 | 650024.94 | 2 | 1.52 | 1.28
P005 | Materials | SUP040 | 2025-04 | 2025-03-21 | 1352780.94 | 1299471 | -53309.94 | 53309.94 | 0 | 2025-04-28 | 5 | 1390705.82 | -37924.88 | DOWN | 0.028 | 38 | Medium | 725970.61 | 0.506 | 0 | 573500.39 | 2 | 1.52 | 1.28
P005 | Materials | SUP040 | 2025-04 | 2025-03-22 | 1333515.59 | 1299471 | -34044.59 | 34044.59 | 0 | 2025-04-28 | 6 | 1352780.94 | -19265.35 | DOWN | 0.0144 | 37 | Medium | 672757.7 | 0.509 | 4 | 626713.3 | 2 | 1.52 | 1.28
P005 | Electronics | SUP040 | 2025-05 | 2025-01-03 | 811525.38 | 475665 | -335860.38 | 335860.38 | 1 | 2025-05-28 | 1 |  |  |  |  | 145 | Low | 165450.63 | 0.218 | 0 | 310214.37 | 6 | 1.12 | 1.51
P005 | Electronics | SUP040 | 2025-05 | 2025-01-04 | 657794.16 | 475665 | -182129.16 | 182129.16 | 1 | 2025-05-28 | 2 | 811525.38 | -153731.22 | DOWN | 0.2337 | 144 | Low | 138906.99 | 0.221 | 2 | 336758.01 | 6 | 1.12 | 1.51
P005 | Electronics | SUP040 | 2025-05 | 2025-01-30 | 574853.23 | 475665 | -99188.23 | 99188.23 | 1 | 2025-05-28 | 3 | 657794.16 | -82940.93 | DOWN | 0.1443 | 118 | Low | 158344.82 | 0.297 | 1 | 317320.18 | 6 | 1.12 | 1.51
P005 | Electronics | SUP040 | 2025-05 | 2025-03-11 | 528981.43 | 475665 | -53316.43 | 53316.43 | 0 | 2025-05-28 | 4 | 574853.23 | -45871.8 | DOWN | 0.0867 | 78 | Low | 220653.31 | 0.414 | 0 | 255011.69 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP040 | 2025-06 | 2025-01-09 | 1094938.95 | 805096 | -289842.95 | 289842.95 | 1 | 2025-06-28 | 1 |  |  |  |  | 170 | Low | 164379.88 | 0.146 | 2 | 640716.12 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP040 | 2025-06 | 2025-01-11 | 969913.78 | 805096 | -164817.78 | 164817.78 | 1 | 2025-06-28 | 2 | 1094938.95 | -125025.17 | DOWN | 0.1289 | 168 | Low | 149047.98 | 0.152 | 0 | 656048.02 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP040 | 2025-06 | 2025-02-17 | 895497.41 | 805096 | -90401.41 | 90401.41 | 0 | 2025-06-28 | 3 | 969913.78 | -74416.37 | DOWN | 0.0831 | 131 | Low | 229669.13 | 0.26 | 0 | 575426.87 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP040 | 2025-06 | 2025-04-25 | 858298.54 | 805096 | -53202.54 | 53202.54 | 0 | 2025-06-28 | 4 | 895497.41 | -37198.87 | DOWN | 0.0433 | 64 | Low | 388571.3 | 0.455 | 1 | 416524.7 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP040 | 2025-07 | 2025-05-06 | 2145511.92 | 1213405 | -932106.92 | 932106.92 | 1 | 2025-07-28 | 1 |  |  |  |  | 83 | Low | 907724.83 | 0.396 | 1 | 305680.17 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP040 | 2025-07 | 2025-07-08 | 1723542.21 | 1213405 | -510137.21 | 510137.21 | 1 | 2025-07-28 | 2 | 2145511.92 | -421969.71 | DOWN | 0.2448 | 20 | Low | 1018131.25 | 0.578 | 5 | 195273.75 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP040 | 2025-07 | 2025-07-17 | 1508033.34 | 1213405 | -294628.34 | 294628.34 | 1 | 2025-07-28 | 3 | 1723542.21 | -215508.87 | DOWN | 0.1429 | 11 | Low | 910301.73 | 0.604 | 4 | 303103.27 | 1 | 1.18 | 1.15
P005 | Electronics | SUP040 | 2025-08 | 2025-04-04 | 1633299.83 | 1140285 | -493014.83 | 493014.83 | 1 | 2025-08-28 | 1 |  |  |  |  | 146 | Low | 318619.9 | 0.202 | 2 | 821665.1 | 8 | 1.7 | 1.32
P005 | Electronics | SUP040 | 2025-08 | 2025-06-05 | 1400739.37 | 1140285 | -260454.37 | 260454.37 | 1 | 2025-08-28 | 2 | 1633299.83 | -232560.46 | DOWN | 0.166 | 84 | Low | 502268.78 | 0.371 | 2 | 638016.22 | 8 | 1.7 | 1.32
P005 | Electronics | SUP040 | 2025-08 | 2025-06-12 | 1276799.66 | 1140285 | -136514.66 | 136514.66 | 0 | 2025-08-28 | 3 | 1400739.37 | -123939.71 | DOWN | 0.0971 | 77 | Low | 520117.79 | 0.39 | 3 | 620167.21 | 8 | 1.7 | 1.32
P005 | Electronics | SUP040 | 2025-08 | 2025-07-16 | 1198752.42 | 1140285 | -58467.42 | 58467.42 | 0 | 2025-08-28 | 4 | 1276799.66 | -78047.24 | DOWN | 0.0651 | 43 | Medium | 615190 | 0.482 | 1 | 525095 | 8 | 1.7 | 1.32
P005 | Electronics | SUP040 | 2025-08 | 2025-07-18 | 1144560.66 | 1140285 | -4275.66 | 4275.66 | 0 | 2025-08-28 | 5 | 1198752.42 | -54191.76 | DOWN | 0.0473 | 41 | Medium | 528052.73 | 0.488 | 3 | 612232.27 | 8 | 1.7 | 1.32
P005 | Services | SUP040 | 2025-09 | 2025-05-04 | 945894.28 | 666274 | -279620.28 | 279620.28 | 1 | 2025-09-28 | 1 |  |  |  |  | 147 | Low | 205457.88 | 0.216 | 0 | 460816.12 | 0 | 0.5 | 0.8
P005 | Services | SUP040 | 2025-09 | 2025-05-10 | 825631.27 | 666274 | -159357.27 | 159357.27 | 1 | 2025-09-28 | 2 | 945894.28 | -120263.01 | DOWN | 0.1457 | 141 | Low | 190802.3 | 0.233 | 2 | 475471.7 | 0 | 0.5 | 0.8
P005 | Services | SUP040 | 2025-09 | 2025-05-30 | 754681.71 | 666274 | -88407.71 | 88407.71 | 0 | 2025-09-28 | 3 | 825631.27 | -70949.56 | DOWN | 0.094 | 121 | Low | 215076.76 | 0.292 | 6 | 451197.24 | 0 | 0.5 | 0.8
P005 | Services | SUP040 | 2025-09 | 2025-07-23 | 707685.08 | 666274 | -41411.08 | 41411.08 | 0 | 2025-09-28 | 4 | 754681.71 | -46996.63 | DOWN | 0.0664 | 67 | Low | 303777.94 | 0.452 | 7 | 362496.06 | 0 | 0.5 | 0.8
P005 | Electronics | SUP040 | 2025-10 | 2025-05-25 | 1216399.02 | 728685 | -487714.02 | 487714.02 | 1 | 2025-10-28 | 1 |  |  |  |  | 156 | Low | 227870.75 | 0.186 | 0 | 500814.25 | 4 | 1.15 | 0.8
P005 | Electronics | SUP040 | 2025-10 | 2025-07-13 | 996796.54 | 728685 | -268111.54 | 268111.54 | 1 | 2025-10-28 | 2 | 1216399.02 | -219602.48 | DOWN | 0.2203 | 107 | Low | 322863.76 | 0.328 | 0 | 405821.24 | 4 | 1.15 | 0.8
P005 | Electronics | SUP040 | 2025-10 | 2025-07-19 | 873788.28 | 728685 | -145103.28 | 145103.28 | 1 | 2025-10-28 | 3 | 996796.54 | -123008.26 | DOWN | 0.1408 | 101 | Low | 301548.79 | 0.345 | 2 | 427136.21 | 4 | 1.15 | 0.8
P005 | Electronics | SUP040 | 2025-10 | 2025-07-31 | 819234.39 | 728685 | -90549.39 | 90549.39 | 0 | 2025-10-28 | 4 | 873788.28 | -54553.89 | DOWN | 0.0666 | 89 | Low | 334914.37 | 0.38 | 4 | 393770.63 | 4 | 1.15 | 0.8
P005 | Electronics | SUP040 | 2025-10 | 2025-08-23 | 775634.65 | 728685 | -46949.65 | 46949.65 | 0 | 2025-10-28 | 5 | 819234.39 | -43599.74 | DOWN | 0.0562 | 66 | Low | 348514.12 | 0.447 | 0 | 380170.88 | 4 | 1.15 | 0.8
P005 | Electronics | SUP040 | 2025-10 | 2025-10-02 | 745854.14 | 728685 | -17169.14 | 17169.14 | 0 | 2025-10-28 | 6 | 775634.65 | -29780.51 | DOWN | 0.0399 | 26 | Medium | 403208.05 | 0.563 | 3 | 325476.95 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP040 | 2025-11 | 2025-06-14 | 1840263.71 | 1261912 | -578351.71 | 578351.71 | 1 | 2025-11-28 | 1 |  |  |  |  | 167 | Low | 288517.53 | 0.15 | 1 | 973394.47 | 4 | 1.35 | 1.5
P005 | Mechanical | SUP040 | 2025-11 | 2025-06-30 | 1573630.11 | 1261912 | -311718.11 | 311718.11 | 1 | 2025-11-28 | 2 | 1840263.71 | -266633.6 | DOWN | 0.1694 | 151 | Low | 319594.62 | 0.196 | 0 | 942317.38 | 4 | 1.35 | 1.5
P005 | Mechanical | SUP040 | 2025-11 | 2025-09-20 | 1438167 | 1261912 | -176255 | 176255 | 0 | 2025-11-28 | 3 | 1573630.11 | -135463.11 | DOWN | 0.0942 | 69 | Low | 572869.86 | 0.428 | 3 | 689042.14 | 4 | 1.35 | 1.5
P005 | Electronics | SUP040 | 2025-12 | 2025-08-18 | 1822031.38 | 1114424 | -707607.38 | 707607.38 | 1 | 2025-12-28 | 1 |  |  |  |  | 132 | Low | 477656.16 | 0.26 | 2 | 636767.84 | 7 | 0.73 | 1.27
P005 | Electronics | SUP040 | 2025-12 | 2025-09-03 | 1515147.07 | 1114424 | -400723.07 | 400723.07 | 1 | 2025-12-28 | 2 | 1822031.38 | -306884.31 | DOWN | 0.2025 | 116 | Low | 449489.42 | 0.307 | 3 | 664934.58 | 7 | 0.73 | 1.27
P005 | Electronics | SUP040 | 2025-12 | 2025-09-15 | 1352037.81 | 1114424 | -237613.81 | 237613.81 | 1 | 2025-12-28 | 3 | 1515147.07 | -163109.26 | DOWN | 0.1206 | 104 | Low | 452722.75 | 0.343 | 0 | 661701.25 | 7 | 0.73 | 1.27
P005 | Electronics | SUP040 | 2025-12 | 2025-10-15 | 1241438.69 | 1114424 | -127014.69 | 127014.69 | 0 | 2025-12-28 | 4 | 1352037.81 | -110599.12 | DOWN | 0.0891 | 74 | Low | 574646.7 | 0.431 | 6 | 539777.3 | 7 | 0.73 | 1.27
P005 | Electronics | SUP040 | 2025-12 | 2025-11-27 | 1194560.81 | 1114424 | -80136.81 | 80136.81 | 0 | 2025-12-28 | 5 | 1241438.69 | -46877.88 | DOWN | 0.0392 | 31 | Medium | 710871.66 | 0.558 | 4 | 403552.34 | 7 | 0.73 | 1.27
P005 | Electronics | SUP040 | 2025-12 | 2025-12-16 | 1163896.78 | 1114424 | -49472.78 | 49472.78 | 0 | 2025-12-28 | 6 | 1194560.81 | -30664.03 | DOWN | 0.0263 | 12 | Medium | 727862.37 | 0.615 | 3 | 386561.63 | 7 | 0.73 | 1.27
P005 | Electronics | SUP013 | 2025-01 | 2024-11-09 | 262509.36 | 148432 | -114077.36 | 114077.36 | 1 | 2025-01-28 | 1 |  |  |  |  | 80 | Low | 75595.87 | 0.302 | 0 | 72836.13 | 8 | 1.44 | 1.07
P005 | Electronics | SUP013 | 2025-01 | 2025-01-03 | 231372.58 | 148432 | -82940.58 | 82940.58 | 1 | 2025-01-28 | 2 | 262509.36 | -31136.78 | DOWN | 0.1346 | 25 | Low | 101439.76 | 0.421 | 6 | 46992.24 | 8 | 1.44 | 1.07
P005 | Electronics | SUP013 | 2025-01 | 2025-01-15 | 213537.92 | 148432 | -65105.92 | 65105.92 | 1 | 2025-01-28 | 3 | 231372.58 | -17834.66 | DOWN | 0.0835 | 13 | Low | 102753.57 | 0.447 | 3 | 45678.43 | 8 | 1.44 | 1.07
P005 | Software | SUP013 | 2025-02 | 2024-09-03 | 4178412.95 | 1862457 | -2315955.95 | 2315955.95 | 1 | 2025-02-28 | 1 |  |  |  |  | 178 | Low | 392462.42 | 0.094 | 4 | 1469994.58 | 7 | 1.56 | 1.03
P005 | Software | SUP013 | 2025-02 | 2024-09-15 | 3522446.04 | 1862457 | -1659989.04 | 1659989.04 | 1 | 2025-02-28 | 2 | 4178412.95 | -655966.91 | DOWN | 0.1862 | 166 | Low | 408825.85 | 0.115 | 0 | 1453631.15 | 7 | 1.56 | 1.03
P005 | Software | SUP013 | 2025-02 | 2024-09-19 | 3098840.57 | 1862457 | -1236383.57 | 1236383.57 | 1 | 2025-02-28 | 3 | 3522446.04 | -423605.47 | DOWN | 0.1367 | 162 | Low | 374337.25 | 0.124 | 0 | 1488119.75 | 7 | 1.56 | 1.03
P005 | Software | SUP013 | 2025-02 | 2024-12-22 | 2766147.77 | 1862457 | -903690.77 | 903690.77 | 1 | 2025-02-28 | 4 | 3098840.57 | -332692.8 | DOWN | 0.1203 | 68 | Low | 874522.68 | 0.324 | 0 | 987934.32 | 7 | 1.56 | 1.03
P005 | Software | SUP013 | 2025-02 | 2025-01-31 | 2570459.6 | 1862457 | -708002.6 | 708002.6 | 1 | 2025-02-28 | 5 | 2766147.77 | -195688.17 | DOWN | 0.0761 | 28 | Low | 969403.35 | 0.409 | 0 | 893053.65 | 7 | 1.56 | 1.03
P005 | Software | SUP013 | 2025-02 | 2025-02-01 | 2442083.39 | 1862457 | -579626.39 | 579626.39 | 1 | 2025-02-28 | 6 | 2570459.6 | -128376.21 | DOWN | 0.0526 | 27 | Low | 989823.87 | 0.411 | 3 | 872633.13 | 7 | 1.56 | 1.03
P005 | Materials | SUP013 | 2025-03 | 2024-10-08 | 1904310.15 | 1067621 | -836689.15 | 836689.15 | 1 | 2025-03-28 | 1 |  |  |  |  | 171 | Low | 196039.45 | 0.111 | 2 | 871581.55 | 0 | 0.76 | 1.01
P005 | Materials | SUP013 | 2025-03 | 2024-10-31 | 1697252.33 | 1067621 | -629631.33 | 629631.33 | 1 | 2025-03-28 | 2 | 1904310.15 | -207057.82 | DOWN | 0.122 | 148 | Low | 281039.53 | 0.164 | 0 | 786581.47 | 0 | 0.76 | 1.01
P005 | Materials | SUP013 | 2025-03 | 2024-11-08 | 1539928.24 | 1067621 | -472307.24 | 472307.24 | 1 | 2025-03-28 | 3 | 1697252.33 | -157324.09 | DOWN | 0.1022 | 140 | Low | 288852.3 | 0.182 | 1 | 778768.7 | 0 | 0.76 | 1.01
P005 | Materials | SUP013 | 2025-03 | 2024-11-21 | 1433114.27 | 1067621 | -365493.27 | 365493.27 | 1 | 2025-03-28 | 4 | 1539928.24 | -106813.97 | DOWN | 0.0745 | 127 | Low | 309696.32 | 0.211 | 0 | 757924.68 | 0 | 0.76 | 1.01
P005 | Materials | SUP013 | 2025-03 | 2025-01-14 | 1337098.07 | 1067621 | -269477.07 | 269477.07 | 1 | 2025-03-28 | 5 | 1433114.27 | -96016.2 | DOWN | 0.0718 | 73 | Low | 424217.58 | 0.334 | 3 | 643403.42 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP013 | 2025-04 | 2024-11-07 | 3258026.73 | 2092741 | -1165285.73 | 1165285.73 | 1 | 2025-04-28 | 1 |  |  |  |  | 172 | Low | 348434.21 | 0.103 | 0 | 1744306.79 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP013 | 2025-04 | 2024-12-20 | 2965239.45 | 2092741 | -872498.45 | 872498.45 | 1 | 2025-04-28 | 2 | 3258026.73 | -292787.28 | DOWN | 0.0987 | 129 | Low | 567578 | 0.195 | 2 | 1525163 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP013 | 2025-04 | 2025-01-13 | 2724667.4 | 2092741 | -631926.4 | 631926.4 | 1 | 2025-04-28 | 3 | 2965239.45 | -240572.05 | DOWN | 0.0883 | 105 | Low | 694571.94 | 0.246 | 5 | 1398169.06 | 2 | 1.52 | 1.28
P005 | Logistics | SUP013 | 2025-05 | 2024-12-21 | 222363.7 | 125657 | -96706.7 | 96706.7 | 1 | 2025-05-28 | 1 |  |  |  |  | 158 | Low | 31556.27 | 0.139 | 0 | 94100.73 | 6 | 1.12 | 1.51
P005 | Logistics | SUP013 | 2025-05 | 2025-01-16 | 195194.87 | 125657 | -69537.87 | 69537.87 | 1 | 2025-05-28 | 2 | 222363.7 | -27168.83 | DOWN | 0.1392 | 132 | Low | 39510.42 | 0.197 | 2 | 86146.58 | 6 | 1.12 | 1.51
P005 | Logistics | SUP013 | 2025-05 | 2025-01-28 | 175699.18 | 125657 | -50042.18 | 50042.18 | 1 | 2025-05-28 | 3 | 195194.87 | -19495.69 | DOWN | 0.111 | 120 | Low | 41502.16 | 0.224 | 0 | 84154.84 | 6 | 1.12 | 1.51
P005 | Logistics | SUP013 | 2025-05 | 2025-02-27 | 163271.44 | 125657 | -37614.44 | 37614.44 | 1 | 2025-05-28 | 4 | 175699.18 | -12427.74 | DOWN | 0.0761 | 90 | Low | 47910.94 | 0.291 | 2 | 77746.06 | 6 | 1.12 | 1.51
P005 | Logistics | SUP013 | 2025-05 | 2025-03-13 | 156758.56 | 125657 | -31101.56 | 31101.56 | 1 | 2025-05-28 | 5 | 163271.44 | -6512.88 | DOWN | 0.0415 | 76 | Low | 54276.39 | 0.323 | 3 | 71380.61 | 6 | 1.12 | 1.51
P005 | Logistics | SUP013 | 2025-05 | 2025-05-09 | 150021.06 | 125657 | -24364.06 | 24364.06 | 1 | 2025-05-28 | 6 | 156758.56 | -6737.5 | DOWN | 0.0449 | 19 | Medium | 72214.33 | 0.45 | 3 | 53442.67 | 6 | 1.12 | 1.51
P005 | Materials | SUP013 | 2025-06 | 2025-02-07 | 2185624.86 | 1170515 | -1015109.86 | 1015109.86 | 1 | 2025-06-28 | 1 |  |  |  |  | 141 | Low | 357505.93 | 0.177 | 4 | 813009.07 | 7 | 1.1 | 1.21
P005 | Materials | SUP013 | 2025-06 | 2025-02-19 | 1930409.6 | 1170515 | -759894.6 | 759894.6 | 1 | 2025-06-28 | 2 | 2185624.86 | -255215.26 | DOWN | 0.1322 | 129 | Low | 375534.3 | 0.204 | 0 | 794980.7 | 7 | 1.1 | 1.21
P005 | Materials | SUP013 | 2025-06 | 2025-04-02 | 1755961.11 | 1170515 | -585446.11 | 585446.11 | 1 | 2025-06-28 | 3 | 1930409.6 | -174448.49 | DOWN | 0.0993 | 87 | Low | 518932.39 | 0.299 | 2 | 651582.61 | 7 | 1.1 | 1.21
P005 | Materials | SUP013 | 2025-06 | 2025-04-13 | 1608126.21 | 1170515 | -437611.21 | 437611.21 | 1 | 2025-06-28 | 4 | 1755961.11 | -147834.9 | DOWN | 0.0919 | 76 | Low | 486857.78 | 0.323 | 2 | 683657.22 | 7 | 1.1 | 1.21
P005 | Materials | SUP013 | 2025-06 | 2025-05-07 | 1505437.72 | 1170515 | -334922.72 | 334922.72 | 1 | 2025-06-28 | 5 | 1608126.21 | -102688.49 | DOWN | 0.0682 | 52 | Low | 563258.8 | 0.377 | 2 | 607256.2 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP013 | 2025-07 | 2025-02-08 | 2209173.18 | 1343822 | -865351.18 | 865351.18 | 1 | 2025-07-28 | 1 |  |  |  |  | 170 | Low | 252411.89 | 0.111 | 2 | 1091410.11 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP013 | 2025-07 | 2025-02-14 | 2000185.67 | 1343822 | -656363.67 | 656363.67 | 1 | 2025-07-28 | 2 | 2209173.18 | -208987.51 | DOWN | 0.1045 | 164 | Low | 244343.4 | 0.125 | 0 | 1099478.6 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP013 | 2025-07 | 2025-02-19 | 1845296.75 | 1343822 | -501474.75 | 501474.75 | 1 | 2025-07-28 | 3 | 2000185.67 | -154888.92 | DOWN | 0.0839 | 159 | Low | 239509.09 | 0.136 | 0 | 1104312.91 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP013 | 2025-07 | 2025-02-26 | 1731497.95 | 1343822 | -387675.95 | 387675.95 | 1 | 2025-07-28 | 4 | 1845296.75 | -113798.8 | DOWN | 0.0657 | 152 | Low | 264414.84 | 0.151 | 2 | 1079407.16 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP013 | 2025-07 | 2025-05-30 | 1639179.3 | 1343822 | -295357.3 | 295357.3 | 1 | 2025-07-28 | 5 | 1731497.95 | -92318.65 | DOWN | 0.0563 | 59 | Low | 595029.11 | 0.358 | 0 | 748792.89 | 1 | 1.18 | 1.15
P005 | Electronics | SUP013 | 2025-08 | 2025-04-03 | 1608363.12 | 1028561 | -579802.12 | 579802.12 | 1 | 2025-08-28 | 1 |  |  |  |  | 147 | Low | 257535.38 | 0.153 | 2 | 771025.62 | 8 | 1.7 | 1.32
P005 | Electronics | SUP013 | 2025-08 | 2025-05-04 | 1480370.99 | 1028561 | -451809.99 | 451809.99 | 1 | 2025-08-28 | 2 | 1608363.12 | -127992.13 | DOWN | 0.0865 | 116 | Low | 317589.11 | 0.218 | 3 | 710971.89 | 8 | 1.7 | 1.32
P005 | Electronics | SUP013 | 2025-08 | 2025-06-06 | 1350480.53 | 1028561 | -321919.53 | 321919.53 | 1 | 2025-08-28 | 3 | 1480370.99 | -129890.46 | DOWN | 0.0962 | 83 | Low | 385276.36 | 0.287 | 2 | 643284.64 | 8 | 1.7 | 1.32
P005 | Electronics | SUP013 | 2025-08 | 2025-07-06 | 1253326.24 | 1028561 | -224765.24 | 224765.24 | 1 | 2025-08-28 | 4 | 1350480.53 | -97154.29 | DOWN | 0.0775 | 53 | Low | 455742.96 | 0.35 | 5 | 572818.04 | 8 | 1.7 | 1.32
P005 | Electronics | SUP013 | 2025-08 | 2025-07-08 | 1213603.96 | 1028561 | -185042.96 | 185042.96 | 1 | 2025-08-28 | 5 | 1253326.24 | -39722.28 | DOWN | 0.0327 | 51 | Low | 461191.68 | 0.354 | 4 | 567369.32 | 8 | 1.7 | 1.32
P005 | Electronics | SUP013 | 2025-08 | 2025-07-22 | 1154931.22 | 1028561 | -126370.22 | 126370.22 | 0 | 2025-08-28 | 6 | 1213603.96 | -58672.74 | DOWN | 0.0508 | 37 | Low | 457602.87 | 0.384 | 8 | 570958.13 | 8 | 1.7 | 1.32
P005 | Electronics | SUP013 | 2025-09 | 2025-04-02 | 3283900.72 | 1838922 | -1444978.72 | 1444978.72 | 1 | 2025-09-28 | 1 |  |  |  |  | 179 | Low | 328258.73 | 0.1 | 0 | 1510663.27 | 0 | 0.5 | 0.8
P005 | Electronics | SUP013 | 2025-09 | 2025-04-10 | 2914295.82 | 1838922 | -1075373.82 | 1075373.82 | 1 | 2025-09-28 | 2 | 3283900.72 | -369604.9 | DOWN | 0.1268 | 171 | Low | 305042.57 | 0.111 | 0 | 1533879.43 | 0 | 0.5 | 0.8
P005 | Electronics | SUP013 | 2025-09 | 2025-05-01 | 2637500.98 | 1838922 | -798578.98 | 798578.98 | 1 | 2025-09-28 | 3 | 2914295.82 | -276794.84 | DOWN | 0.1049 | 150 | Low | 424001.84 | 0.159 | 1 | 1414920.16 | 0 | 0.5 | 0.8
P005 | Electronics | SUP013 | 2025-09 | 2025-05-27 | 2416572.02 | 1838922 | -577650.02 | 577650.02 | 1 | 2025-09-28 | 4 | 2637500.98 | -220928.96 | DOWN | 0.0914 | 124 | Low | 568178.12 | 0.218 | 0 | 1270743.88 | 0 | 0.5 | 0.8
P005 | Electronics | SUP013 | 2025-09 | 2025-08-21 | 2261370.16 | 1838922 | -422448.16 | 422448.16 | 1 | 2025-09-28 | 5 | 2416572.02 | -155201.86 | DOWN | 0.0686 | 38 | Low | 999014.84 | 0.414 | 6 | 839907.16 | 0 | 0.5 | 0.8
P005 | Mechanical | SUP013 | 2025-10 | 2025-06-08 | 1493620.54 | 894047 | -599573.54 | 599573.54 | 1 | 2025-10-28 | 1 |  |  |  |  | 142 | Low | 244769.8 | 0.174 | 2 | 649277.2 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP013 | 2025-10 | 2025-08-05 | 1341164.65 | 894047 | -447117.65 | 447117.65 | 1 | 2025-10-28 | 2 | 1493620.54 | -152455.89 | DOWN | 0.1137 | 84 | Low | 402739.6 | 0.304 | 7 | 491307.4 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP013 | 2025-10 | 2025-08-23 | 1231667.5 | 894047 | -337620.5 | 337620.5 | 1 | 2025-10-28 | 3 | 1341164.65 | -109497.15 | DOWN | 0.0889 | 66 | Low | 456518.2 | 0.344 | 1 | 437528.8 | 4 | 1.15 | 0.8
P005 | Services | SUP013 | 2025-11 | 2025-08-10 | 621289.15 | 328682 | -292607.15 | 292607.15 | 1 | 2025-11-28 | 1 |  |  |  |  | 110 | Low | 146205.16 | 0.24 | 2 | 182476.84 | 4 | 1.35 | 1.5
P005 | Services | SUP013 | 2025-11 | 2025-09-11 | 556331.56 | 328682 | -227649.56 | 227649.56 | 1 | 2025-11-28 | 2 | 621289.15 | -64957.59 | DOWN | 0.1168 | 78 | Low | 166977.09 | 0.31 | 4 | 161704.91 | 4 | 1.35 | 1.5
P005 | Services | SUP013 | 2025-11 | 2025-11-18 | 509582.33 | 328682 | -180900.33 | 180900.33 | 1 | 2025-11-28 | 3 | 556331.56 | -46749.23 | DOWN | 0.0917 | 10 | Medium | 242290.12 | 0.456 | 4 | 86391.88 | 4 | 1.35 | 1.5
P005 | Mechanical | SUP013 | 2025-12 | 2025-07-05 | 3138573.55 | 2012621 | -1125952.55 | 1125952.55 | 1 | 2025-12-28 | 1 |  |  |  |  | 176 | Low | 324496.18 | 0.1 | 4 | 1688124.82 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP013 | 2025-12 | 2025-08-04 | 2857348.43 | 2012621 | -844727.43 | 844727.43 | 1 | 2025-12-28 | 2 | 3138573.55 | -281225.12 | DOWN | 0.0984 | 146 | Low | 476068.81 | 0.168 | 1 | 1536552.19 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP013 | 2025-12 | 2025-09-04 | 2644076.98 | 2012621 | -631455.98 | 631455.98 | 1 | 2025-12-28 | 3 | 2857348.43 | -213271.45 | DOWN | 0.0807 | 115 | Low | 647316.54 | 0.239 | 3 | 1365304.46 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP013 | 2025-12 | 2025-10-17 | 2489791.22 | 2012621 | -477170.22 | 477170.22 | 1 | 2025-12-28 | 4 | 2644076.98 | -154285.76 | DOWN | 0.062 | 72 | Low | 790272.61 | 0.336 | 3 | 1222348.39 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP013 | 2025-12 | 2025-11-13 | 2366296.13 | 2012621 | -353675.13 | 353675.13 | 0 | 2025-12-28 | 5 | 2489791.22 | -123495.09 | DOWN | 0.0522 | 45 | Low | 890222.72 | 0.398 | 0 | 1122398.28 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP013 | 2025-12 | 2025-12-12 | 2281167.37 | 2012621 | -268546.37 | 268546.37 | 0 | 2025-12-28 | 6 | 2366296.13 | -85128.76 | DOWN | 0.0373 | 16 | Medium | 1084848.57 | 0.464 | 2 | 927772.43 | 7 | 0.73 | 1.27
P005 | Mechanical | SUP009 | 2025-01 | 2024-09-11 | 1976792.18 | 1530126 | -446666.18 | 446666.18 | 1 | 2025-01-28 | 1 |  |  |  |  | 139 | Low | 544677.47 | 0.273 | 2 | 985448.53 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP009 | 2025-01 | 2024-09-16 | 1753912.82 | 1530126 | -223786.82 | 223786.82 | 0 | 2025-01-28 | 2 | 1976792.18 | -222879.36 | DOWN | 0.1271 | 134 | Low | 515452.99 | 0.29 | 0 | 1014673.01 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP009 | 2025-01 | 2024-09-18 | 1612411.41 | 1530126 | -82285.41 | 82285.41 | 0 | 2025-01-28 | 3 | 1753912.82 | -141501.41 | DOWN | 0.0878 | 132 | Low | 490479.31 | 0.296 | 4 | 1039646.69 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP009 | 2025-01 | 2024-10-18 | 1569525.32 | 1530126 | -39399.32 | 39399.32 | 0 | 2025-01-28 | 4 | 1612411.41 | -42886.09 | DOWN | 0.0273 | 102 | Low | 657099.36 | 0.397 | 0 | 873026.64 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP009 | 2025-01 | 2024-12-11 | 1550460.35 | 1530126 | -20334.35 | 20334.35 | 0 | 2025-01-28 | 5 | 1569525.32 | -19064.97 | DOWN | 0.0123 | 48 | Medium | 871310.41 | 0.579 | 6 | 658815.59 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP009 | 2025-01 | 2024-12-14 | 1536934.12 | 1530126 | -6808.12 | 6808.12 | 0 | 2025-01-28 | 6 | 1550460.35 | -13526.23 | DOWN | 0.0088 | 45 | Medium | 973113.8 | 0.589 | 5 | 557012.2 | 8 | 1.44 | 1.07
P005 | Materials | SUP009 | 2025-02 | 2024-11-21 | 2890799.81 | 2093980 | -796819.81 | 796819.81 | 1 | 2025-02-28 | 1 |  |  |  |  | 99 | Low | 1164685.06 | 0.402 | 2 | 929294.94 | 7 | 1.56 | 1.03
P005 | Materials | SUP009 | 2025-02 | 2024-12-17 | 2480868.19 | 2093980 | -386888.19 | 386888.19 | 1 | 2025-02-28 | 2 | 2890799.81 | -409931.62 | DOWN | 0.1652 | 73 | Low | 1291470.07 | 0.488 | 4 | 802509.93 | 7 | 1.56 | 1.03
P005 | Materials | SUP009 | 2025-02 | 2024-12-22 | 2253853.43 | 2093980 | -159873.43 | 159873.43 | 0 | 2025-02-28 | 3 | 2480868.19 | -227014.76 | DOWN | 0.1007 | 68 | Low | 1147928.26 | 0.505 | 5 | 946051.74 | 7 | 1.56 | 1.03
P005 | Materials | SUP009 | 2025-02 | 2025-02-10 | 2171341.75 | 2093980 | -77361.75 | 77361.75 | 0 | 2025-02-28 | 4 | 2253853.43 | -82511.68 | DOWN | 0.038 | 18 | Medium | 1477254.16 | 0.671 | 3 | 616725.84 | 7 | 1.56 | 1.03
P005 | Materials | SUP009 | 2025-02 | 2025-02-18 | 2158352.81 | 2093980 | -64372.81 | 64372.81 | 0 | 2025-02-28 | 5 | 2171341.75 | -12988.94 | DOWN | 0.006 | 10 | Medium | 1437486.69 | 0.694 | 5 | 656493.31 | 7 | 1.56 | 1.03
P005 | Services | SUP009 | 2025-03 | 2024-11-01 | 922304.72 | 647286 | -275018.72 | 275018.72 | 1 | 2025-03-28 | 1 |  |  |  |  | 147 | Low | 239054 | 0.259 | 1 | 408232 | 0 | 0.76 | 1.01
P005 | Services | SUP009 | 2025-03 | 2025-02-20 | 769073.6 | 647286 | -121787.6 | 121787.6 | 1 | 2025-03-28 | 2 | 922304.72 | -153231.12 | DOWN | 0.1992 | 36 | Low | 491954.78 | 0.652 | 6 | 155331.22 | 0 | 0.76 | 1.01
P005 | Services | SUP009 | 2025-03 | 2025-03-02 | 694462.48 | 647286 | -47176.48 | 47176.48 | 0 | 2025-03-28 | 3 | 769073.6 | -74611.12 | DOWN | 0.1074 | 26 | Medium | 462957.72 | 0.688 | 6 | 184328.28 | 0 | 0.76 | 1.01
P005 | Services | SUP009 | 2025-03 | 2025-03-07 | 661205.85 | 647286 | -13919.85 | 13919.85 | 0 | 2025-03-28 | 4 | 694462.48 | -33256.63 | DOWN | 0.0503 | 21 | High | 486294.63 | 0.706 | 5 | 160991.37 | 0 | 0.76 | 1.01
P005 | Materials | SUP009 | 2025-04 | 2024-11-26 | 1878371.94 | 1373197 | -505174.94 | 505174.94 | 1 | 2025-04-28 | 1 |  |  |  |  | 153 | Low | 441393.93 | 0.224 | 3 | 931803.07 | 2 | 1.52 | 1.28
P005 | Materials | SUP009 | 2025-04 | 2024-11-29 | 1598020.05 | 1373197 | -224823.05 | 224823.05 | 0 | 2025-04-28 | 2 | 1878371.94 | -280351.89 | DOWN | 0.1754 | 150 | Low | 358052.75 | 0.234 | 1 | 1015144.25 | 2 | 1.52 | 1.28
P005 | Materials | SUP009 | 2025-04 | 2024-12-28 | 1471963.6 | 1373197 | -98766.6 | 98766.6 | 0 | 2025-04-28 | 3 | 1598020.05 | -126056.45 | DOWN | 0.0856 | 121 | Low | 479625.08 | 0.33 | 2 | 893571.92 | 2 | 1.52 | 1.28
P005 | Materials | SUP009 | 2025-04 | 2025-01-31 | 1395455.2 | 1373197 | -22258.2 | 22258.2 | 0 | 2025-04-28 | 4 | 1471963.6 | -76508.4 | DOWN | 0.0548 | 87 | Low | 584872.19 | 0.444 | 3 | 788324.81 | 2 | 1.52 | 1.28
P005 | Materials | SUP009 | 2025-04 | 2025-04-04 | 1394496.31 | 1373197 | -21299.31 | 21299.31 | 0 | 2025-04-28 | 5 | 1395455.2 | -958.89 | DOWN | 0.0007 | 24 | Medium | 927921.4 | 0.654 | 5 | 445275.6 | 2 | 1.52 | 1.28
P005 | Materials | SUP009 | 2025-04 | 2025-04-18 | 1390698.92 | 1373197 | -17501.92 | 17501.92 | 0 | 2025-04-28 | 6 | 1394496.31 | -3797.39 | DOWN | 0.0027 | 10 | Medium | 953953.56 | 0.697 | 6 | 419243.44 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP009 | 2025-05 | 2024-12-22 | 3074574.52 | 2388835 | -685739.52 | 685739.52 | 1 | 2025-05-28 | 1 |  |  |  |  | 157 | Low | 664355.62 | 0.22 | 2 | 1724479.38 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP009 | 2025-05 | 2025-01-12 | 2707035.3 | 2388835 | -318200.3 | 318200.3 | 0 | 2025-05-28 | 2 | 3074574.52 | -367539.22 | DOWN | 0.1358 | 136 | Low | 779339.86 | 0.294 | 4 | 1609495.14 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP009 | 2025-05 | 2025-02-18 | 2536051.32 | 2388835 | -147216.32 | 147216.32 | 0 | 2025-05-28 | 3 | 2707035.3 | -170983.98 | DOWN | 0.0674 | 99 | Low | 1122037.12 | 0.423 | 0 | 1266797.88 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP009 | 2025-05 | 2025-03-29 | 2454572.3 | 2388835 | -65737.3 | 65737.3 | 0 | 2025-05-28 | 4 | 2536051.32 | -81479.02 | DOWN | 0.0332 | 60 | Medium | 1466778.31 | 0.559 | 3 | 922056.69 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP009 | 2025-05 | 2025-04-09 | 2417083.49 | 2388835 | -28248.49 | 28248.49 | 0 | 2025-05-28 | 5 | 2454572.3 | -37488.81 | DOWN | 0.0155 | 49 | Medium | 1396812.85 | 0.598 | 7 | 992022.15 | 6 | 1.12 | 1.51
P005 | Materials | SUP009 | 2025-06 | 2025-01-01 | 2657892.34 | 1975009 | -682883.34 | 682883.34 | 1 | 2025-06-28 | 1 |  |  |  |  | 178 | Low | 382159.48 | 0.154 | 0 | 1592849.52 | 7 | 1.1 | 1.21
P005 | Materials | SUP009 | 2025-06 | 2025-02-08 | 2285717.34 | 1975009 | -310708.34 | 310708.34 | 0 | 2025-06-28 | 2 | 2657892.34 | -372175 | DOWN | 0.1628 | 140 | Low | 597209.7 | 0.28 | 1 | 1377799.3 | 7 | 1.1 | 1.21
P005 | Materials | SUP009 | 2025-06 | 2025-02-12 | 2122355.34 | 1975009 | -147346.34 | 147346.34 | 0 | 2025-06-28 | 3 | 2285717.34 | -163362 | DOWN | 0.077 | 136 | Low | 632073.74 | 0.294 | 2 | 1342935.26 | 7 | 1.1 | 1.21
P005 | Materials | SUP009 | 2025-06 | 2025-03-11 | 2038551.74 | 1975009 | -63542.74 | 63542.74 | 0 | 2025-06-28 | 4 | 2122355.34 | -83803.6 | DOWN | 0.0411 | 109 | Low | 773645.06 | 0.389 | 1 | 1201363.94 | 7 | 1.1 | 1.21
P005 | Materials | SUP009 | 2025-06 | 2025-06-14 | 1993196.71 | 1975009 | -18187.71 | 18187.71 | 0 | 2025-06-28 | 5 | 2038551.74 | -45355.03 | DOWN | 0.0228 | 14 | High | 1434002.51 | 0.722 | 5 | 541006.49 | 7 | 1.1 | 1.21
P005 | Materials | SUP009 | 2025-07 | 2025-04-22 | 1788954.97 | 1448929 | -340025.97 | 340025.97 | 1 | 2025-07-28 | 1 |  |  |  |  | 97 | Low | 730830.4 | 0.427 | 8 | 718098.6 | 1 | 1.18 | 1.15
P005 | Materials | SUP009 | 2025-07 | 2025-05-05 | 1589226.59 | 1448929 | -140297.59 | 140297.59 | 0 | 2025-07-28 | 2 | 1788954.97 | -199728.38 | DOWN | 0.1257 | 84 | Low | 784513 | 0.472 | 4 | 664416 | 1 | 1.18 | 1.15
P005 | Materials | SUP009 | 2025-07 | 2025-07-12 | 1502184.65 | 1448929 | -53255.65 | 53255.65 | 0 | 2025-07-28 | 3 | 1589226.59 | -87041.94 | DOWN | 0.0579 | 16 | High | 1031647.2 | 0.708 | 5 | 417281.8 | 1 | 1.18 | 1.15
P005 | Services | SUP009 | 2025-08 | 2025-03-08 | 1962018.03 | 1324343 | -637675.03 | 637675.03 | 1 | 2025-08-28 | 1 |  |  |  |  | 173 | Low | 279327.1 | 0.154 | 1 | 1045015.9 | 8 | 1.7 | 1.32
P005 | Services | SUP009 | 2025-08 | 2025-03-29 | 1600960.11 | 1324343 | -276617.11 | 276617.11 | 1 | 2025-08-28 | 2 | 1962018.03 | -361057.92 | DOWN | 0.2255 | 152 | Low | 366299.15 | 0.222 | 2 | 958043.85 | 8 | 1.7 | 1.32
P005 | Services | SUP009 | 2025-08 | 2025-06-06 | 1456179.1 | 1324343 | -131836.1 | 131836.1 | 0 | 2025-08-28 | 3 | 1600960.11 | -144781.01 | DOWN | 0.0994 | 83 | Low | 639194.43 | 0.448 | 2 | 685148.57 | 8 | 1.7 | 1.32
P005 | Services | SUP009 | 2025-08 | 2025-06-14 | 1403549.96 | 1324343 | -79206.96 | 79206.96 | 0 | 2025-08-28 | 4 | 1456179.1 | -52629.14 | DOWN | 0.0375 | 75 | Low | 644239.63 | 0.474 | 6 | 680103.37 | 8 | 1.7 | 1.32
P005 | Services | SUP009 | 2025-08 | 2025-06-15 | 1358820.41 | 1324343 | -34477.41 | 34477.41 | 0 | 2025-08-28 | 5 | 1403549.96 | -44729.55 | DOWN | 0.0329 | 74 | Low | 647450.33 | 0.478 | 4 | 676892.67 | 8 | 1.7 | 1.32
P005 | Services | SUP009 | 2025-08 | 2025-07-20 | 1322422.1 | 1324343 | 1920.9 | 1920.9 | 0 | 2025-08-28 | 6 | 1358820.41 | -36398.31 | DOWN | 0.0275 | 39 | Medium | 779108.23 | 0.592 | 4 | 545234.77 | 8 | 1.7 | 1.32
P005 | Services | SUP009 | 2025-09 | 2025-04-12 | 2605987.58 | 1676765 | -929222.58 | 929222.58 | 1 | 2025-09-28 | 1 |  |  |  |  | 169 | Low | 487816.36 | 0.181 | 2 | 1188948.64 | 0 | 0.5 | 0.8
P005 | Services | SUP009 | 2025-09 | 2025-07-21 | 2133083.64 | 1676765 | -456318.64 | 456318.64 | 1 | 2025-09-28 | 2 | 2605987.58 | -472903.94 | DOWN | 0.2217 | 69 | Low | 1054595.65 | 0.535 | 3 | 622169.35 | 0 | 0.5 | 0.8
P005 | Services | SUP009 | 2025-09 | 2025-08-08 | 1908812.24 | 1676765 | -232047.24 | 232047.24 | 0 | 2025-09-28 | 3 | 2133083.64 | -224271.4 | DOWN | 0.1175 | 51 | Medium | 1091717.62 | 0.599 | 3 | 585047.38 | 0 | 0.5 | 0.8
P005 | Services | SUP009 | 2025-09 | 2025-08-16 | 1776944.4 | 1676765 | -100179.4 | 100179.4 | 0 | 2025-09-28 | 4 | 1908812.24 | -131867.84 | DOWN | 0.0742 | 43 | Medium | 1109175.4 | 0.628 | 3 | 567589.6 | 0 | 0.5 | 0.8
P005 | Services | SUP009 | 2025-09 | 2025-08-16 | 1739085.66 | 1676765 | -62320.66 | 62320.66 | 0 | 2025-09-28 | 5 | 1776944.4 | -37858.74 | DOWN | 0.0218 | 43 | Medium | 1118663.44 | 0.628 | 4 | 558101.56 | 0 | 0.5 | 0.8
P005 | Software | SUP009 | 2025-10 | 2025-06-30 | 866542.78 | 502128 | -364414.78 | 364414.78 | 1 | 2025-10-28 | 1 |  |  |  |  | 120 | Low | 301436.78 | 0.348 | 3 | 200691.22 | 4 | 1.15 | 0.8
P005 | Software | SUP009 | 2025-10 | 2025-08-30 | 681653.95 | 502128 | -179525.95 | 179525.95 | 1 | 2025-10-28 | 2 | 866542.78 | -184888.83 | DOWN | 0.2712 | 59 | Low | 386677.84 | 0.561 | 8 | 115450.16 | 4 | 1.15 | 0.8
P005 | Software | SUP009 | 2025-10 | 2025-09-22 | 587838.13 | 502128 | -85710.13 | 85710.13 | 0 | 2025-10-28 | 3 | 681653.95 | -93815.82 | DOWN | 0.1596 | 36 | Low | 365633.61 | 0.641 | 3 | 136494.39 | 4 | 1.15 | 0.8
P005 | Materials | SUP009 | 2025-11 | 2025-06-15 | 901545.83 | 750890 | -150655.83 | 150655.83 | 1 | 2025-11-28 | 1 |  |  |  |  | 166 | Low | 154748.74 | 0.184 | 3 | 596141.26 | 4 | 1.35 | 1.5
P005 | Materials | SUP009 | 2025-11 | 2025-06-30 | 811475.89 | 750890 | -60585.89 | 60585.89 | 0 | 2025-11-28 | 2 | 901545.83 | -90069.94 | DOWN | 0.111 | 151 | Low | 196598.49 | 0.235 | 3 | 554291.51 | 4 | 1.35 | 1.5
P005 | Materials | SUP009 | 2025-11 | 2025-07-30 | 775195.63 | 750890 | -24305.63 | 24305.63 | 0 | 2025-11-28 | 3 | 811475.89 | -36280.26 | DOWN | 0.0468 | 121 | Low | 255701.22 | 0.337 | 2 | 495188.78 | 4 | 1.35 | 1.5
P005 | Materials | SUP009 | 2025-11 | 2025-10-19 | 761315.94 | 750890 | -10425.94 | 10425.94 | 0 | 2025-11-28 | 4 | 775195.63 | -13879.69 | DOWN | 0.0182 | 40 | Medium | 495332.39 | 0.612 | 7 | 255557.61 | 4 | 1.35 | 1.5
P005 | Materials | SUP009 | 2025-11 | 2025-10-21 | 761542.74 | 750890 | -10652.74 | 10652.74 | 0 | 2025-11-28 | 5 | 761315.94 | 226.8 | UP | 0.0003 | 38 | Medium | 438335.01 | 0.619 | 2 | 312554.99 | 4 | 1.35 | 1.5
P005 | Materials | SUP009 | 2025-11 | 2025-11-17 | 761902.49 | 750890 | -11012.49 | 11012.49 | 0 | 2025-11-28 | 6 | 761542.74 | 359.75 | UP | 0.0005 | 11 | High | 511797.69 | 0.711 | 8 | 239092.31 | 4 | 1.35 | 1.5
P005 | Electronics | SUP009 | 2025-12 | 2025-10-26 | 1093529.33 | 841479 | -252050.33 | 252050.33 | 1 | 2025-12-28 | 1 |  |  |  |  | 63 | Low | 583078.21 | 0.557 | 4 | 258400.79 | 7 | 0.73 | 1.27
P005 | Electronics | SUP009 | 2025-12 | 2025-11-09 | 948022.43 | 841479 | -106543.43 | 106543.43 | 0 | 2025-12-28 | 2 | 1093529.33 | -145506.9 | DOWN | 0.1535 | 49 | Low | 581007.65 | 0.606 | 4 | 260471.35 | 7 | 0.73 | 1.27
P005 | Electronics | SUP009 | 2025-12 | 2025-11-25 | 890425.41 | 841479 | -48946.41 | 48946.41 | 0 | 2025-12-28 | 3 | 948022.43 | -57597.02 | DOWN | 0.0647 | 33 | Medium | 586271.02 | 0.663 | 5 | 255207.98 | 7 | 0.73 | 1.27
P005 | Electronics | SUP009 | 2025-12 | 2025-11-26 | 869574.22 | 841479 | -28095.22 | 28095.22 | 0 | 2025-12-28 | 4 | 890425.41 | -20851.19 | DOWN | 0.024 | 32 | Medium | 578683.31 | 0.667 | 6 | 262795.69 | 7 | 0.73 | 1.27
P005 | Services | SUP039 | 2025-01 | 2024-11-02 | 3800604.6 | 2179341 | -1621263.6 | 1621263.6 | 1 | 2025-01-28 | 1 |  |  |  |  | 87 | Low | 1440625.18 | 0.373 | 0 | 738715.82 | 8 | 1.44 | 1.07
P005 | Services | SUP039 | 2025-01 | 2024-12-15 | 3120791.54 | 2179341 | -941450.54 | 941450.54 | 1 | 2025-01-28 | 2 | 3800604.6 | -679813.06 | DOWN | 0.2178 | 44 | Low | 1663951.77 | 0.494 | 10 | 515389.23 | 8 | 1.44 | 1.07
P005 | Services | SUP039 | 2025-01 | 2024-12-23 | 2721077.35 | 2179341 | -541736.35 | 541736.35 | 1 | 2025-01-28 | 3 | 3120791.54 | -399714.19 | DOWN | 0.1469 | 36 | Low | 1426492.66 | 0.516 | 6 | 752848.34 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP039 | 2025-02 | 2024-09-16 | 779741.7 | 456662 | -323079.7 | 323079.7 | 1 | 2025-02-28 | 1 |  |  |  |  | 165 | Low | 114419.91 | 0.152 | 0 | 342242.09 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP039 | 2025-02 | 2024-11-05 | 634773.18 | 456662 | -178111.18 | 178111.18 | 1 | 2025-02-28 | 2 | 779741.7 | -144968.52 | DOWN | 0.2284 | 115 | Low | 193857.04 | 0.291 | 3 | 262804.96 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP039 | 2025-02 | 2024-12-08 | 552155.11 | 456662 | -95493.11 | 95493.11 | 1 | 2025-02-28 | 3 | 634773.18 | -82618.07 | DOWN | 0.1496 | 82 | Low | 216736.93 | 0.382 | 2 | 239925.07 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP039 | 2025-02 | 2024-12-23 | 503500.6 | 456662 | -46838.6 | 46838.6 | 0 | 2025-02-28 | 4 | 552155.11 | -48654.51 | DOWN | 0.0966 | 67 | Low | 222696.27 | 0.424 | 2 | 233965.73 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP039 | 2025-02 | 2025-01-10 | 483325.89 | 456662 | -26663.89 | 26663.89 | 0 | 2025-02-28 | 5 | 503500.6 | -20174.71 | DOWN | 0.0417 | 49 | Medium | 223571.81 | 0.473 | 5 | 233090.19 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP039 | 2025-02 | 2025-01-12 | 470236.2 | 456662 | -13574.2 | 13574.2 | 0 | 2025-02-28 | 6 | 483325.89 | -13089.69 | DOWN | 0.0278 | 47 | Medium | 217274.15 | 0.479 | 1 | 239387.85 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP039 | 2025-03 | 2024-10-14 | 421463.99 | 259499 | -161964.99 | 161964.99 | 1 | 2025-03-28 | 1 |  |  |  |  | 165 | Low | 65975.36 | 0.163 | 0 | 193523.64 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP039 | 2025-03 | 2024-11-10 | 346889.4 | 259499 | -87390.4 | 87390.4 | 1 | 2025-03-28 | 2 | 421463.99 | -74574.59 | DOWN | 0.215 | 138 | Low | 83132.1 | 0.242 | 6 | 176366.9 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP039 | 2025-03 | 2025-01-02 | 306181.75 | 259499 | -46682.75 | 46682.75 | 1 | 2025-03-28 | 3 | 346889.4 | -40707.65 | DOWN | 0.133 | 85 | Low | 128347.05 | 0.399 | 1 | 131151.95 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP039 | 2025-03 | 2025-02-03 | 285000.5 | 259499 | -25501.5 | 25501.5 | 0 | 2025-03-28 | 4 | 306181.75 | -21181.25 | DOWN | 0.0743 | 53 | Medium | 138239.5 | 0.493 | 2 | 121259.5 | 0 | 0.76 | 1.01
P005 | Mechanical | SUP039 | 2025-04 | 2024-11-20 | 1764264.76 | 1393898 | -370366.76 | 370366.76 | 1 | 2025-04-28 | 1 |  |  |  |  | 159 | Low | 322856.24 | 0.17 | 0 | 1071041.76 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP039 | 2025-04 | 2025-01-28 | 1606476.48 | 1393898 | -212578.48 | 212578.48 | 0 | 2025-04-28 | 2 | 1764264.76 | -157788.28 | DOWN | 0.0982 | 90 | Low | 582262.91 | 0.362 | 4 | 811635.09 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP039 | 2025-04 | 2025-03-02 | 1491033.31 | 1393898 | -97135.31 | 97135.31 | 0 | 2025-04-28 | 3 | 1606476.48 | -115443.17 | DOWN | 0.0774 | 57 | Medium | 702065.79 | 0.453 | 4 | 691832.21 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP039 | 2025-04 | 2025-03-30 | 1455019.06 | 1393898 | -61121.06 | 61121.06 | 0 | 2025-04-28 | 4 | 1491033.31 | -36014.25 | DOWN | 0.0248 | 29 | Medium | 776506.03 | 0.531 | 4 | 617391.97 | 2 | 1.52 | 1.28
P005 | Electronics | SUP039 | 2025-05 | 2025-01-25 | 4521933.58 | 2581621 | -1940312.58 | 1940312.58 | 1 | 2025-05-28 | 1 |  |  |  |  | 123 | Low | 1316752.49 | 0.283 | 5 | 1264868.51 | 6 | 1.12 | 1.51
P005 | Electronics | SUP039 | 2025-05 | 2025-02-09 | 3635695.62 | 2581621 | -1054074.62 | 1054074.62 | 1 | 2025-05-28 | 2 | 4521933.58 | -886237.96 | DOWN | 0.2438 | 108 | Low | 1217106.53 | 0.326 | 2 | 1364514.47 | 6 | 1.12 | 1.51
P005 | Electronics | SUP039 | 2025-05 | 2025-02-26 | 3189390.08 | 2581621 | -607769.08 | 607769.08 | 1 | 2025-05-28 | 3 | 3635695.62 | -446305.54 | DOWN | 0.1399 | 91 | Low | 1176228.36 | 0.376 | 3 | 1405392.64 | 6 | 1.12 | 1.51
P005 | Electronics | SUP039 | 2025-05 | 2025-02-26 | 2926315.77 | 2581621 | -344694.77 | 344694.77 | 0 | 2025-05-28 | 4 | 3189390.08 | -263074.31 | DOWN | 0.0899 | 91 | Low | 1182899.77 | 0.376 | 4 | 1398721.23 | 6 | 1.12 | 1.51
P005 | Electronics | SUP039 | 2025-05 | 2025-03-11 | 2794208.96 | 2581621 | -212587.96 | 212587.96 | 0 | 2025-05-28 | 5 | 2926315.77 | -132106.81 | DOWN | 0.0473 | 78 | Low | 1226397.83 | 0.414 | 1 | 1355223.17 | 6 | 1.12 | 1.51
P005 | Electronics | SUP039 | 2025-05 | 2025-04-26 | 2705978.49 | 2581621 | -124357.49 | 124357.49 | 0 | 2025-05-28 | 6 | 2794208.96 | -88230.47 | DOWN | 0.0326 | 32 | Medium | 1577017.94 | 0.548 | 5 | 1004603.06 | 6 | 1.12 | 1.51
P005 | Software | SUP039 | 2025-06 | 2025-02-02 | 555685.24 | 309744 | -245941.24 | 245941.24 | 1 | 2025-06-28 | 1 |  |  |  |  | 146 | Low | 115120.63 | 0.216 | 7 | 194623.37 | 7 | 1.1 | 1.21
P005 | Software | SUP039 | 2025-06 | 2025-04-01 | 444420.49 | 309744 | -134676.49 | 134676.49 | 1 | 2025-06-28 | 2 | 555685.24 | -111264.75 | DOWN | 0.2504 | 88 | Low | 167636.93 | 0.385 | 4 | 142107.07 | 7 | 1.1 | 1.21
P005 | Software | SUP039 | 2025-06 | 2025-06-02 | 389628.23 | 309744 | -79884.23 | 79884.23 | 1 | 2025-06-28 | 3 | 444420.49 | -54792.26 | DOWN | 0.1406 | 26 | Low | 234773.21 | 0.566 | 6 | 74970.79 | 7 | 1.1 | 1.21
P005 | Software | SUP039 | 2025-06 | 2025-06-14 | 356530.77 | 309744 | -46786.77 | 46786.77 | 0 | 2025-06-28 | 4 | 389628.23 | -33097.46 | DOWN | 0.0928 | 14 | Medium | 207373.49 | 0.601 | 5 | 102370.51 | 7 | 1.1 | 1.21
P005 | Services | SUP039 | 2025-07 | 2025-02-12 | 1773600.68 | 1065110 | -708490.68 | 708490.68 | 1 | 2025-07-28 | 1 |  |  |  |  | 166 | Low | 275196.23 | 0.156 | 3 | 789913.77 | 1 | 1.18 | 1.15
P005 | Services | SUP039 | 2025-07 | 2025-03-30 | 1437442.96 | 1065110 | -372332.96 | 372332.96 | 1 | 2025-07-28 | 2 | 1773600.68 | -336157.72 | DOWN | 0.2339 | 120 | Low | 427230.67 | 0.289 | 4 | 637879.33 | 1 | 1.18 | 1.15
P005 | Services | SUP039 | 2025-07 | 2025-06-07 | 1288083.9 | 1065110 | -222973.9 | 222973.9 | 1 | 2025-07-28 | 3 | 1437442.96 | -149359.06 | DOWN | 0.116 | 51 | Medium | 608023.12 | 0.489 | 0 | 457086.88 | 1 | 1.18 | 1.15
P005 | Services | SUP039 | 2025-07 | 2025-06-09 | 1190000.7 | 1065110 | -124890.7 | 124890.7 | 0 | 2025-07-28 | 4 | 1288083.9 | -98083.2 | DOWN | 0.0824 | 49 | Medium | 592488.81 | 0.495 | 6 | 472621.19 | 1 | 1.18 | 1.15
P005 | Services | SUP039 | 2025-07 | 2025-06-12 | 1147477.54 | 1065110 | -82367.54 | 82367.54 | 0 | 2025-07-28 | 5 | 1190000.7 | -42523.16 | DOWN | 0.0371 | 46 | Medium | 621262.15 | 0.503 | 1 | 443847.85 | 1 | 1.18 | 1.15
P005 | Logistics | SUP039 | 2025-08 | 2025-04-02 | 2201872.55 | 1305923 | -895949.55 | 895949.55 | 1 | 2025-08-28 | 1 |  |  |  |  | 148 | Low | 430148.58 | 0.196 | 0 | 875774.42 | 8 | 1.7 | 1.32
P005 | Logistics | SUP039 | 2025-08 | 2025-06-21 | 1785620.62 | 1305923 | -479697.62 | 479697.62 | 1 | 2025-08-28 | 2 | 2201872.55 | -416251.93 | DOWN | 0.2331 | 68 | Low | 789161 | 0.414 | 0 | 516762 | 8 | 1.7 | 1.32
P005 | Logistics | SUP039 | 2025-08 | 2025-06-29 | 1521338.72 | 1305923 | -215415.72 | 215415.72 | 0 | 2025-08-28 | 3 | 1785620.62 | -264281.9 | DOWN | 0.1737 | 60 | Low | 647839.32 | 0.436 | 4 | 658083.68 | 8 | 1.7 | 1.32
P005 | Logistics | SUP039 | 2025-08 | 2025-07-06 | 1432668.56 | 1305923 | -126745.56 | 126745.56 | 0 | 2025-08-28 | 4 | 1521338.72 | -88670.16 | DOWN | 0.0619 | 53 | Medium | 632832.17 | 0.455 | 7 | 673090.83 | 8 | 1.7 | 1.32
P005 | Mechanical | SUP039 | 2025-09 | 2025-04-11 | 1079653.97 | 691528 | -388125.97 | 388125.97 | 1 | 2025-09-28 | 1 |  |  |  |  | 170 | Low | 158179.01 | 0.148 | 0 | 533348.99 | 0 | 0.5 | 0.8
P005 | Mechanical | SUP039 | 2025-09 | 2025-05-16 | 899194.47 | 691528 | -207666.47 | 207666.47 | 1 | 2025-09-28 | 2 | 1079653.97 | -180459.5 | DOWN | 0.2007 | 135 | Low | 227231.09 | 0.251 | 0 | 464296.91 | 0 | 0.5 | 0.8
P005 | Mechanical | SUP039 | 2025-09 | 2025-06-15 | 800984.91 | 691528 | -109456.91 | 109456.91 | 0 | 2025-09-28 | 3 | 899194.47 | -98209.56 | DOWN | 0.1226 | 105 | Low | 289316.51 | 0.34 | 8 | 402211.49 | 0 | 0.5 | 0.8
P005 | Mechanical | SUP039 | 2025-09 | 2025-06-27 | 748160.95 | 691528 | -56632.95 | 56632.95 | 0 | 2025-09-28 | 4 | 800984.91 | -52823.96 | DOWN | 0.0706 | 93 | Low | 276373.86 | 0.375 | 0 | 415154.14 | 0 | 0.5 | 0.8
P005 | Mechanical | SUP039 | 2025-09 | 2025-07-16 | 719677.35 | 691528 | -28149.35 | 28149.35 | 0 | 2025-09-28 | 5 | 748160.95 | -28483.6 | DOWN | 0.0396 | 74 | Low | 334615.39 | 0.431 | 3 | 356912.61 | 0 | 0.5 | 0.8
P005 | Materials | SUP039 | 2025-10 | 2025-05-14 | 1721969.65 | 964979 | -756990.65 | 756990.65 | 1 | 2025-10-28 | 1 |  |  |  |  | 167 | Low | 281309.53 | 0.154 | 0 | 683669.47 | 4 | 1.15 | 0.8
P005 | Materials | SUP039 | 2025-10 | 2025-06-26 | 1393130.63 | 964979 | -428151.63 | 428151.63 | 1 | 2025-10-28 | 2 | 1721969.65 | -328839.02 | DOWN | 0.236 | 124 | Low | 367391.09 | 0.279 | 0 | 597587.91 | 4 | 1.15 | 0.8
P005 | Materials | SUP039 | 2025-10 | 2025-10-02 | 1206357.73 | 964979 | -241378.73 | 241378.73 | 1 | 2025-10-28 | 3 | 1393130.63 | -186772.9 | DOWN | 0.1548 | 26 | Low | 638529.32 | 0.563 | 7 | 326449.68 | 4 | 1.15 | 0.8
P005 | Materials | SUP039 | 2025-10 | 2025-10-17 | 1089390.94 | 964979 | -124411.94 | 124411.94 | 0 | 2025-10-28 | 4 | 1206357.73 | -116966.79 | DOWN | 0.1074 | 11 | Medium | 685088.37 | 0.607 | 3 | 279890.63 | 4 | 1.15 | 0.8
P005 | Services | SUP039 | 2025-11 | 2025-06-16 | 2144345.1 | 1230386 | -913959.1 | 913959.1 | 1 | 2025-11-28 | 1 |  |  |  |  | 165 | Low | 337979.97 | 0.156 | 2 | 892406.03 | 4 | 1.35 | 1.5
P005 | Services | SUP039 | 2025-11 | 2025-07-22 | 1701621.6 | 1230386 | -471235.6 | 471235.6 | 1 | 2025-11-28 | 2 | 2144345.1 | -442723.5 | DOWN | 0.2602 | 129 | Low | 460247.96 | 0.258 | 0 | 770138.04 | 4 | 1.35 | 1.5
P005 | Services | SUP039 | 2025-11 | 2025-07-27 | 1474332 | 1230386 | -243946 | 243946 | 1 | 2025-11-28 | 3 | 1701621.6 | -227289.6 | DOWN | 0.1542 | 124 | Low | 379827.62 | 0.272 | 0 | 850558.38 | 4 | 1.35 | 1.5
P005 | Services | SUP039 | 2025-11 | 2025-08-28 | 1370597.16 | 1230386 | -140211.16 | 140211.16 | 0 | 2025-11-28 | 4 | 1474332 | -103734.84 | DOWN | 0.0757 | 92 | Low | 515394.98 | 0.363 | 0 | 714991.02 | 4 | 1.35 | 1.5
P005 | Services | SUP039 | 2025-11 | 2025-11-07 | 1295380.42 | 1230386 | -64994.42 | 64994.42 | 0 | 2025-11-28 | 5 | 1370597.16 | -75216.74 | DOWN | 0.0581 | 21 | Medium | 684055.83 | 0.564 | 1 | 546330.17 | 4 | 1.35 | 1.5
P005 | Services | SUP039 | 2025-12 | 2025-07-03 | 3382606.27 | 2000522 | -1382084.27 | 1382084.27 | 1 | 2025-12-28 | 1 |  |  |  |  | 178 | Low | 431276.29 | 0.13 | 0 | 1569245.71 | 7 | 0.73 | 1.27
P005 | Services | SUP039 | 2025-12 | 2025-09-13 | 2795546.05 | 2000522 | -795024.05 | 795024.05 | 1 | 2025-12-28 | 2 | 3382606.27 | -587060.22 | DOWN | 0.21 | 106 | Low | 873549.75 | 0.337 | 3 | 1126972.25 | 7 | 0.73 | 1.27
P005 | Services | SUP039 | 2025-12 | 2025-10-28 | 2450798.05 | 2000522 | -450276.05 | 450276.05 | 1 | 2025-12-28 | 3 | 2795546.05 | -344748 | DOWN | 0.1407 | 61 | Low | 1112162.21 | 0.47 | 3 | 888359.79 | 7 | 0.73 | 1.27
P005 | Services | SUP039 | 2025-12 | 2025-11-10 | 2236783.94 | 2000522 | -236261.94 | 236261.94 | 0 | 2025-12-28 | 4 | 2450798.05 | -214014.11 | DOWN | 0.0957 | 48 | Medium | 1196357.04 | 0.508 | 3 | 804164.96 | 7 | 0.73 | 1.27
P005 | Services | SUP039 | 2025-12 | 2025-12-13 | 2156002.7 | 2000522 | -155480.7 | 155480.7 | 0 | 2025-12-28 | 5 | 2236783.94 | -80781.24 | DOWN | 0.0375 | 15 | Medium | 1331899.38 | 0.606 | 4 | 668622.62 | 7 | 0.73 | 1.27
P005 | Materials | SUP050 | 2025-01 | 2024-08-02 | 2734044.49 | 1695362 | -1038682.49 | 1038682.49 | 1 | 2025-01-28 | 1 |  |  |  |  | 179 | Low | 343402.01 | 0.123 | 0 | 1351959.99 | 8 | 1.44 | 1.07
P005 | Materials | SUP050 | 2025-01 | 2024-08-31 | 2296975.68 | 1695362 | -601613.68 | 601613.68 | 1 | 2025-01-28 | 2 | 2734044.49 | -437068.81 | DOWN | 0.1903 | 150 | Low | 418252.79 | 0.196 | 4 | 1277109.21 | 8 | 1.44 | 1.07
P005 | Materials | SUP050 | 2025-01 | 2024-10-22 | 2022925.62 | 1695362 | -327563.62 | 327563.62 | 1 | 2025-01-28 | 3 | 2296975.68 | -274050.06 | DOWN | 0.1355 | 98 | Low | 662819.8 | 0.342 | 0 | 1032542.2 | 8 | 1.44 | 1.07
P005 | Materials | SUP050 | 2025-01 | 2024-12-07 | 1860228.77 | 1695362 | -164866.77 | 164866.77 | 0 | 2025-01-28 | 4 | 2022925.62 | -162696.85 | DOWN | 0.0875 | 52 | Medium | 814626 | 0.471 | 2 | 880736 | 8 | 1.44 | 1.07
P005 | Materials | SUP050 | 2025-01 | 2024-12-12 | 1789978.76 | 1695362 | -94616.76 | 94616.76 | 0 | 2025-01-28 | 5 | 1860228.77 | -70250.01 | DOWN | 0.0392 | 47 | Medium | 910917.92 | 0.486 | 5 | 784444.08 | 8 | 1.44 | 1.07
P005 | Materials | SUP050 | 2025-01 | 2024-12-25 | 1737960.83 | 1695362 | -42598.83 | 42598.83 | 0 | 2025-01-28 | 6 | 1789978.76 | -52017.93 | DOWN | 0.0299 | 34 | Medium | 871741.73 | 0.522 | 6 | 823620.27 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP050 | 2025-02 | 2024-10-21 | 636369.8 | 386639 | -249730.8 | 249730.8 | 1 | 2025-02-28 | 1 |  |  |  |  | 130 | Low | 165953.37 | 0.249 | 0 | 220685.63 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP050 | 2025-02 | 2025-01-20 | 525461.84 | 386639 | -138822.84 | 138822.84 | 1 | 2025-02-28 | 2 | 636369.8 | -110907.96 | DOWN | 0.2111 | 39 | Low | 277074.11 | 0.501 | 5 | 109564.89 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP050 | 2025-02 | 2025-02-05 | 462727.42 | 386639 | -76088.42 | 76088.42 | 1 | 2025-02-28 | 3 | 525461.84 | -62734.42 | DOWN | 0.1356 | 23 | Low | 251834.76 | 0.545 | 3 | 134804.24 | 7 | 1.56 | 1.03
P005 | Logistics | SUP050 | 2025-03 | 2024-10-01 | 734650.94 | 383028 | -351622.94 | 351622.94 | 1 | 2025-03-28 | 1 |  |  |  |  | 178 | Low | 101135.3 | 0.13 | 1 | 281892.7 | 0 | 0.76 | 1.01
P005 | Logistics | SUP050 | 2025-03 | 2024-10-12 | 561460.85 | 383028 | -178432.85 | 178432.85 | 1 | 2025-03-28 | 2 | 734650.94 | -173190.09 | DOWN | 0.3085 | 167 | Low | 92039.31 | 0.157 | 1 | 290988.69 | 0 | 0.76 | 1.01
P005 | Logistics | SUP050 | 2025-03 | 2024-11-04 | 490223.65 | 383028 | -107195.65 | 107195.65 | 1 | 2025-03-28 | 3 | 561460.85 | -71237.2 | DOWN | 0.1453 | 144 | Low | 107598.13 | 0.225 | 0 | 275429.87 | 0 | 0.76 | 1.01
P005 | Logistics | SUP050 | 2025-03 | 2025-01-02 | 444933.8 | 383028 | -61905.8 | 61905.8 | 0 | 2025-03-28 | 4 | 490223.65 | -45289.85 | DOWN | 0.1018 | 85 | Low | 166505.36 | 0.399 | 3 | 216522.64 | 0 | 0.76 | 1.01
P005 | Software | SUP050 | 2025-04 | 2024-10-30 | 2587367.88 | 1472107 | -1115260.88 | 1115260.88 | 1 | 2025-04-28 | 1 |  |  |  |  | 180 | Low | 339382.47 | 0.122 | 0 | 1132724.53 | 2 | 1.52 | 1.28
P005 | Software | SUP050 | 2025-04 | 2024-11-04 | 2077116.58 | 1472107 | -605009.58 | 605009.58 | 1 | 2025-04-28 | 2 | 2587367.88 | -510251.3 | DOWN | 0.2457 | 175 | Low | 257631.77 | 0.125 | 1 | 1214475.23 | 2 | 1.52 | 1.28
P005 | Software | SUP050 | 2025-04 | 2024-11-26 | 1792188.99 | 1472107 | -320081.99 | 320081.99 | 1 | 2025-04-28 | 3 | 2077116.58 | -284927.59 | DOWN | 0.159 | 153 | Low | 335311.28 | 0.186 | 0 | 1136795.72 | 2 | 1.52 | 1.28
P005 | Software | SUP050 | 2025-04 | 2025-02-20 | 1631100.43 | 1472107 | -158993.43 | 158993.43 | 0 | 2025-04-28 | 4 | 1792188.99 | -161088.56 | DOWN | 0.0988 | 67 | Low | 659052.61 | 0.425 | 4 | 813054.39 | 2 | 1.52 | 1.28
P005 | Software | SUP050 | 2025-04 | 2025-04-10 | 1542829.28 | 1472107 | -70722.28 | 70722.28 | 0 | 2025-04-28 | 5 | 1631100.43 | -88271.15 | DOWN | 0.0572 | 18 | Medium | 821478.4 | 0.562 | 8 | 650628.6 | 2 | 1.52 | 1.28
P005 | Electronics | SUP050 | 2025-05 | 2024-12-11 | 3666387.09 | 1881594 | -1784793.09 | 1784793.09 | 1 | 2025-05-28 | 1 |  |  |  |  | 168 | Low | 571064.14 | 0.151 | 1 | 1310529.86 | 6 | 1.12 | 1.51
P005 | Electronics | SUP050 | 2025-05 | 2025-01-12 | 2879269.1 | 1881594 | -997675.1 | 997675.1 | 1 | 2025-05-28 | 2 | 3666387.09 | -787117.99 | DOWN | 0.2734 | 136 | Low | 718793.82 | 0.245 | 0 | 1162800.18 | 6 | 1.12 | 1.51
P005 | Electronics | SUP050 | 2025-05 | 2025-04-26 | 2401685.2 | 1881594 | -520091.2 | 520091.2 | 1 | 2025-05-28 | 3 | 2879269.1 | -477583.9 | DOWN | 0.1989 | 32 | Low | 1242523.68 | 0.548 | 0 | 639070.32 | 6 | 1.12 | 1.51
P005 | Electronics | SUP050 | 2025-06 | 2025-02-18 | 1763375.46 | 1122497 | -640878.46 | 640878.46 | 1 | 2025-06-28 | 1 |  |  |  |  | 130 | Low | 473427.86 | 0.263 | 3 | 649069.14 | 7 | 1.1 | 1.21
P005 | Electronics | SUP050 | 2025-06 | 2025-03-28 | 1456276.65 | 1122497 | -333779.65 | 333779.65 | 1 | 2025-06-28 | 2 | 1763375.46 | -307098.81 | DOWN | 0.2109 | 92 | Low | 560584.77 | 0.374 | 5 | 561912.23 | 7 | 1.1 | 1.21
P005 | Electronics | SUP050 | 2025-06 | 2025-05-20 | 1292049.76 | 1122497 | -169552.76 | 169552.76 | 0 | 2025-06-28 | 3 | 1456276.65 | -164226.89 | DOWN | 0.1271 | 39 | Low | 660857.52 | 0.528 | 3 | 461639.48 | 7 | 1.1 | 1.21
P005 | Software | SUP050 | 2025-07 | 2025-03-14 | 985187.39 | 538373 | -446814.39 | 446814.39 | 1 | 2025-07-28 | 1 |  |  |  |  | 136 | Low | 242860.06 | 0.243 | 2 | 295512.94 | 1 | 1.18 | 1.15
P005 | Software | SUP050 | 2025-07 | 2025-03-30 | 788697.35 | 538373 | -250324.35 | 250324.35 | 1 | 2025-07-28 | 2 | 985187.39 | -196490.04 | DOWN | 0.2491 | 120 | Low | 244145.44 | 0.289 | 7 | 294227.56 | 1 | 1.18 | 1.15
P005 | Software | SUP050 | 2025-07 | 2025-05-17 | 663424.87 | 538373 | -125051.87 | 125051.87 | 1 | 2025-07-28 | 3 | 788697.35 | -125272.48 | DOWN | 0.1888 | 72 | Low | 268227.08 | 0.428 | 3 | 270145.92 | 1 | 1.18 | 1.15
P005 | Software | SUP050 | 2025-07 | 2025-05-21 | 599777.93 | 538373 | -61404.93 | 61404.93 | 0 | 2025-07-28 | 4 | 663424.87 | -63646.94 | DOWN | 0.1061 | 68 | Low | 243702.09 | 0.44 | 5 | 294670.91 | 1 | 1.18 | 1.15
P005 | Software | SUP050 | 2025-07 | 2025-07-08 | 573529.48 | 538373 | -35156.48 | 35156.48 | 0 | 2025-07-28 | 5 | 599777.93 | -26248.45 | DOWN | 0.0458 | 20 | Medium | 357077.86 | 0.578 | 1 | 181295.14 | 1 | 1.18 | 1.15
P005 | Electronics | SUP050 | 2025-08 | 2025-03-09 | 3070584.23 | 1699887 | -1370697.23 | 1370697.23 | 1 | 2025-08-28 | 1 |  |  |  |  | 172 | Low | 430481.24 | 0.131 | 4 | 1269405.76 | 8 | 1.7 | 1.32
P005 | Electronics | SUP050 | 2025-08 | 2025-03-11 | 2522246.98 | 1699887 | -822359.98 | 822359.98 | 1 | 2025-08-28 | 2 | 3070584.23 | -548337.25 | DOWN | 0.2174 | 170 | Low | 362979.39 | 0.136 | 0 | 1336907.61 | 8 | 1.7 | 1.32
P005 | Electronics | SUP050 | 2025-08 | 2025-03-21 | 2157350.36 | 1699887 | -457463.36 | 457463.36 | 1 | 2025-08-28 | 3 | 2522246.98 | -364896.62 | DOWN | 0.1691 | 160 | Low | 368563.96 | 0.164 | 0 | 1331323.04 | 8 | 1.7 | 1.32
P005 | Electronics | SUP050 | 2025-08 | 2025-04-24 | 1984984.67 | 1699887 | -285097.67 | 285097.67 | 0 | 2025-08-28 | 4 | 2157350.36 | -172365.69 | DOWN | 0.0868 | 126 | Low | 509740.61 | 0.256 | 0 | 1190146.39 | 8 | 1.7 | 1.32
P005 | Electronics | SUP050 | 2025-08 | 2025-05-18 | 1867454.96 | 1699887 | -167567.96 | 167567.96 | 0 | 2025-08-28 | 5 | 1984984.67 | -117529.71 | DOWN | 0.0629 | 102 | Low | 578731.5 | 0.322 | 2 | 1121155.5 | 8 | 1.7 | 1.32
P005 | Electronics | SUP050 | 2025-08 | 2025-08-11 | 1800955.65 | 1699887 | -101068.65 | 101068.65 | 0 | 2025-08-28 | 6 | 1867454.96 | -66499.31 | DOWN | 0.0369 | 17 | Medium | 1075929.17 | 0.553 | 2 | 623957.83 | 8 | 1.7 | 1.32
P005 | Electronics | SUP050 | 2025-09 | 2025-05-16 | 2316750.31 | 1278496 | -1038254.31 | 1038254.31 | 1 | 2025-09-28 | 1 |  |  |  |  | 135 | Low | 558878.98 | 0.251 | 0 | 719617.02 | 0 | 0.5 | 0.8
P005 | Electronics | SUP050 | 2025-09 | 2025-05-18 | 1870660.75 | 1278496 | -592164.75 | 592164.75 | 1 | 2025-09-28 | 2 | 2316750.31 | -446089.56 | DOWN | 0.2385 | 133 | Low | 483490.93 | 0.257 | 4 | 795005.07 | 0 | 0.5 | 0.8
P005 | Electronics | SUP050 | 2025-09 | 2025-05-31 | 1618234.11 | 1278496 | -339738.11 | 339738.11 | 1 | 2025-09-28 | 3 | 1870660.75 | -252426.64 | DOWN | 0.156 | 120 | Low | 477083.5 | 0.295 | 2 | 801412.5 | 0 | 0.5 | 0.8
P005 | Electronics | SUP050 | 2025-09 | 2025-08-23 | 1468604.38 | 1278496 | -190108.38 | 190108.38 | 0 | 2025-09-28 | 4 | 1618234.11 | -149629.73 | DOWN | 0.1019 | 36 | Medium | 828303.46 | 0.544 | 8 | 450192.54 | 0 | 0.5 | 0.8
P005 | Mechanical | SUP050 | 2025-10 | 2025-05-05 | 2018295.43 | 1566084 | -452211.43 | 452211.43 | 1 | 2025-10-28 | 1 |  |  |  |  | 176 | Low | 238465.49 | 0.128 | 2 | 1327618.51 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP050 | 2025-10 | 2025-05-16 | 1818992.37 | 1566084 | -252908.37 | 252908.37 | 0 | 2025-10-28 | 2 | 2018295.43 | -199303.06 | DOWN | 0.1096 | 165 | Low | 307744.89 | 0.16 | 3 | 1258339.11 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP050 | 2025-10 | 2025-06-29 | 1703752.76 | 1566084 | -137668.76 | 137668.76 | 0 | 2025-10-28 | 3 | 1818992.37 | -115239.61 | DOWN | 0.0676 | 121 | Low | 520953.45 | 0.287 | 0 | 1045130.55 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP050 | 2025-10 | 2025-07-02 | 1639237.9 | 1566084 | -73153.9 | 73153.9 | 0 | 2025-10-28 | 4 | 1703752.76 | -64514.86 | DOWN | 0.0394 | 118 | Low | 448820.85 | 0.296 | 3 | 1117263.15 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP050 | 2025-10 | 2025-07-24 | 1609260.33 | 1566084 | -43176.33 | 43176.33 | 0 | 2025-10-28 | 5 | 1639237.9 | -29977.57 | DOWN | 0.0186 | 96 | Low | 546104.72 | 0.36 | 0 | 1019979.28 | 4 | 1.15 | 0.8
P005 | Services | SUP050 | 2025-11 | 2025-06-26 | 1296132.67 | 736530 | -559602.67 | 559602.67 | 1 | 2025-11-28 | 1 |  |  |  |  | 155 | Low | 223181.89 | 0.184 | 3 | 513348.11 | 4 | 1.35 | 1.5
P005 | Services | SUP050 | 2025-11 | 2025-07-04 | 1056012.31 | 736530 | -319482.31 | 319482.31 | 1 | 2025-11-28 | 2 | 1296132.67 | -240120.36 | DOWN | 0.2274 | 147 | Low | 230683.26 | 0.207 | 3 | 505846.74 | 4 | 1.35 | 1.5
P005 | Services | SUP050 | 2025-11 | 2025-08-25 | 918761.98 | 736530 | -182231.98 | 182231.98 | 1 | 2025-11-28 | 3 | 1056012.31 | -137250.33 | DOWN | 0.1494 | 95 | Low | 337467.39 | 0.354 | 4 | 399062.61 | 4 | 1.35 | 1.5
P005 | Services | SUP050 | 2025-11 | 2025-11-04 | 824860.31 | 736530 | -88330.31 | 88330.31 | 0 | 2025-11-28 | 4 | 918761.98 | -93901.67 | DOWN | 0.1138 | 24 | Medium | 457559.87 | 0.556 | 3 | 278970.13 | 4 | 1.35 | 1.5
P005 | Software | SUP050 | 2025-12 | 2025-11-13 | 1401105.2 | 785264 | -615841.2 | 615841.2 | 1 | 2025-12-28 | 1 |  |  |  |  | 45 | Medium | 703255.42 | 0.517 | 4 | 82008.58 | 7 | 0.73 | 1.27
P005 | Software | SUP050 | 2025-12 | 2025-11-18 | 1135422.44 | 785264 | -350158.44 | 350158.44 | 1 | 2025-12-28 | 2 | 1401105.2 | -265682.76 | DOWN | 0.234 | 40 | Low | 608816.04 | 0.532 | 4 | 176447.96 | 7 | 0.73 | 1.27
P005 | Software | SUP050 | 2025-12 | 2025-12-12 | 973287.27 | 785264 | -188023.27 | 188023.27 | 1 | 2025-12-28 | 3 | 1135422.44 | -162135.17 | DOWN | 0.1666 | 16 | Low | 594061.13 | 0.603 | 4 | 191202.87 | 7 | 0.73 | 1.27
P005 | Logistics | SUP021 | 2025-01 | 2024-09-21 | 2132611.4 | 1274393 | -858218.4 | 858218.4 | 1 | 2025-01-28 | 1 |  |  |  |  | 129 | Low | 612228.92 | 0.306 | 2 | 662164.08 | 8 | 1.44 | 1.07
P005 | Logistics | SUP021 | 2025-01 | 2024-10-03 | 1702594.89 | 1274393 | -428201.89 | 428201.89 | 1 | 2025-01-28 | 2 | 2132611.4 | -430016.51 | DOWN | 0.2526 | 117 | Low | 563636.09 | 0.347 | 5 | 710756.91 | 8 | 1.44 | 1.07
P005 | Logistics | SUP021 | 2025-01 | 2024-10-20 | 1462564.18 | 1274393 | -188171.18 | 188171.18 | 0 | 2025-01-28 | 3 | 1702594.89 | -240030.71 | DOWN | 0.1641 | 100 | Low | 635217.11 | 0.404 | 3 | 639175.89 | 8 | 1.44 | 1.07
P005 | Logistics | SUP021 | 2025-01 | 2024-11-10 | 1341571.93 | 1274393 | -67178.93 | 67178.93 | 0 | 2025-01-28 | 4 | 1462564.18 | -120992.25 | DOWN | 0.0902 | 79 | Low | 683214.85 | 0.475 | 3 | 591178.15 | 8 | 1.44 | 1.07
P005 | Logistics | SUP021 | 2025-01 | 2024-11-24 | 1284074.8 | 1274393 | -9681.8 | 9681.8 | 0 | 2025-01-28 | 5 | 1341571.93 | -57497.13 | DOWN | 0.0448 | 65 | Low | 722232.38 | 0.522 | 5 | 552160.62 | 8 | 1.44 | 1.07
P005 | Logistics | SUP021 | 2025-01 | 2025-01-03 | 1266659.93 | 1274393 | 7733.07 | 7733.07 | 0 | 2025-01-28 | 6 | 1284074.8 | -17414.87 | DOWN | 0.0137 | 25 | Medium | 782814.81 | 0.657 | 5 | 491578.19 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP021 | 2025-02 | 2024-10-03 | 2848118.46 | 2235571 | -612547.46 | 612547.46 | 1 | 2025-02-28 | 1 |  |  |  |  | 148 | Low | 711618.21 | 0.239 | 1 | 1523952.79 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP021 | 2025-02 | 2024-11-03 | 2503510.73 | 2235571 | -267939.73 | 267939.73 | 0 | 2025-02-28 | 2 | 2848118.46 | -344607.73 | DOWN | 0.1376 | 117 | Low | 847983.44 | 0.342 | 2 | 1387587.56 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP021 | 2025-02 | 2025-01-11 | 2367687.29 | 2235571 | -132116.29 | 132116.29 | 0 | 2025-02-28 | 3 | 2503510.73 | -135823.44 | DOWN | 0.0574 | 48 | Medium | 1441507.75 | 0.571 | 3 | 794063.25 | 7 | 1.56 | 1.03
P005 | Services | SUP021 | 2025-03 | 2024-10-13 | 1207530.78 | 819349 | -388181.78 | 388181.78 | 1 | 2025-03-28 | 1 |  |  |  |  | 166 | Low | 231038.58 | 0.191 | 1 | 588310.42 | 0 | 0.76 | 1.01
P005 | Services | SUP021 | 2025-03 | 2024-11-30 | 1005320.5 | 819349 | -185971.5 | 185971.5 | 1 | 2025-03-28 | 2 | 1207530.78 | -202210.28 | DOWN | 0.2011 | 118 | Low | 379520.48 | 0.362 | 4 | 439828.52 | 0 | 0.76 | 1.01
P005 | Services | SUP021 | 2025-03 | 2025-03-07 | 892321.76 | 819349 | -72972.76 | 72972.76 | 0 | 2025-03-28 | 3 | 1005320.5 | -112998.74 | DOWN | 0.1266 | 21 | Low | 588939.73 | 0.706 | 4 | 230409.27 | 0 | 0.76 | 1.01
P005 | Electronics | SUP021 | 2025-04 | 2025-01-04 | 1144532.98 | 758265 | -386267.98 | 386267.98 | 1 | 2025-04-28 | 1 |  |  |  |  | 114 | Low | 420388.51 | 0.354 | 4 | 337876.49 | 2 | 1.52 | 1.28
P005 | Electronics | SUP021 | 2025-04 | 2025-02-11 | 926975.4 | 758265 | -168710.4 | 168710.4 | 1 | 2025-04-28 | 2 | 1144532.98 | -217557.58 | DOWN | 0.2347 | 76 | Low | 424131.09 | 0.481 | 2 | 334133.91 | 2 | 1.52 | 1.28
P005 | Electronics | SUP021 | 2025-04 | 2025-04-17 | 838196.73 | 758265 | -79931.73 | 79931.73 | 0 | 2025-04-28 | 3 | 926975.4 | -88778.67 | DOWN | 0.1059 | 11 | Medium | 597760.24 | 0.697 | 4 | 160504.76 | 2 | 1.52 | 1.28
P005 | Services | SUP021 | 2025-05 | 2024-12-23 | 2331289.76 | 1534422 | -796867.76 | 796867.76 | 1 | 2025-05-28 | 1 |  |  |  |  | 156 | Low | 492300.14 | 0.224 | 1 | 1042121.86 | 6 | 1.12 | 1.51
P005 | Services | SUP021 | 2025-05 | 2025-01-16 | 1922973.18 | 1534422 | -388551.18 | 388551.18 | 1 | 2025-05-28 | 2 | 2331289.76 | -408316.58 | DOWN | 0.2123 | 132 | Low | 565667.18 | 0.308 | 2 | 968754.82 | 6 | 1.12 | 1.51
P005 | Services | SUP021 | 2025-05 | 2025-02-12 | 1692259.35 | 1534422 | -157837.35 | 157837.35 | 0 | 2025-05-28 | 3 | 1922973.18 | -230713.83 | DOWN | 0.1363 | 105 | Low | 690016.65 | 0.402 | 4 | 844405.35 | 6 | 1.12 | 1.51
P005 | Services | SUP021 | 2025-05 | 2025-02-16 | 1619013.59 | 1534422 | -84591.59 | 84591.59 | 0 | 2025-05-28 | 4 | 1692259.35 | -73245.76 | DOWN | 0.0452 | 101 | Low | 686599.2 | 0.416 | 3 | 847822.8 | 6 | 1.12 | 1.51
P005 | Services | SUP021 | 2025-05 | 2025-04-15 | 1565366.66 | 1534422 | -30944.66 | 30944.66 | 0 | 2025-05-28 | 5 | 1619013.59 | -53646.93 | DOWN | 0.0343 | 43 | Medium | 1018404.73 | 0.619 | 6 | 516017.27 | 6 | 1.12 | 1.51
P005 | Services | SUP021 | 2025-05 | 2025-04-21 | 1542992.98 | 1534422 | -8570.98 | 8570.98 | 0 | 2025-05-28 | 6 | 1565366.66 | -22373.68 | DOWN | 0.0145 | 37 | Medium | 1028920.95 | 0.64 | 8 | 505501.05 | 6 | 1.12 | 1.51
P005 | Services | SUP021 | 2025-06 | 2025-01-30 | 2756268.58 | 2026897 | -729371.58 | 729371.58 | 1 | 2025-06-28 | 1 |  |  |  |  | 149 | Low | 699196.45 | 0.249 | 2 | 1327700.55 | 7 | 1.1 | 1.21
P005 | Services | SUP021 | 2025-06 | 2025-02-23 | 2346144.54 | 2026897 | -319247.54 | 319247.54 | 0 | 2025-06-28 | 2 | 2756268.58 | -410124.04 | DOWN | 0.1748 | 125 | Low | 752045.47 | 0.333 | 4 | 1274851.53 | 7 | 1.1 | 1.21
P005 | Services | SUP021 | 2025-06 | 2025-02-26 | 2145135.67 | 2026897 | -118238.67 | 118238.67 | 0 | 2025-06-28 | 3 | 2346144.54 | -201008.87 | DOWN | 0.0937 | 122 | Low | 781501.83 | 0.343 | 2 | 1245395.17 | 7 | 1.1 | 1.21
P005 | Services | SUP021 | 2025-06 | 2025-04-12 | 2091377.78 | 2026897 | -64480.78 | 64480.78 | 0 | 2025-06-28 | 4 | 2145135.67 | -53757.89 | DOWN | 0.0257 | 77 | Low | 1040714.33 | 0.501 | 0 | 986182.67 | 7 | 1.1 | 1.21
P005 | Software | SUP021 | 2025-07 | 2025-02-07 | 2812452.81 | 1831131 | -981321.81 | 981321.81 | 1 | 2025-07-28 | 1 |  |  |  |  | 171 | Low | 508311.59 | 0.17 | 0 | 1322819.41 | 1 | 1.18 | 1.15
P005 | Software | SUP021 | 2025-07 | 2025-02-26 | 2283710.26 | 1831131 | -452579.26 | 452579.26 | 1 | 2025-07-28 | 2 | 2812452.81 | -528742.55 | DOWN | 0.2315 | 152 | Low | 540664.3 | 0.236 | 5 | 1290466.7 | 1 | 1.18 | 1.15
P005 | Software | SUP021 | 2025-07 | 2025-04-16 | 2074924.41 | 1831131 | -243793.41 | 243793.41 | 0 | 2025-07-28 | 3 | 2283710.26 | -208785.85 | DOWN | 0.1006 | 103 | Low | 854561.13 | 0.406 | 4 | 976569.87 | 1 | 1.18 | 1.15
P005 | Software | SUP021 | 2025-07 | 2025-04-23 | 1909095.07 | 1831131 | -77964.07 | 77964.07 | 0 | 2025-07-28 | 4 | 2074924.41 | -165829.34 | DOWN | 0.0869 | 96 | Low | 832528.84 | 0.43 | 5 | 998602.16 | 1 | 1.18 | 1.15
P005 | Software | SUP021 | 2025-07 | 2025-06-05 | 1866425.38 | 1831131 | -35294.38 | 35294.38 | 0 | 2025-07-28 | 5 | 1909095.07 | -42669.69 | DOWN | 0.0229 | 53 | Medium | 1071238.38 | 0.58 | 3 | 759892.62 | 1 | 1.18 | 1.15
P005 | Software | SUP021 | 2025-07 | 2025-07-02 | 1845407.58 | 1831131 | -14276.58 | 14276.58 | 0 | 2025-07-28 | 6 | 1866425.38 | -21017.8 | DOWN | 0.0114 | 26 | High | 1242725.94 | 0.673 | 7 | 588405.06 | 1 | 1.18 | 1.15
P005 | Mechanical | SUP021 | 2025-08 | 2025-04-23 | 1418710.6 | 1137081 | -281629.6 | 281629.6 | 1 | 2025-08-28 | 1 |  |  |  |  | 127 | Low | 433347.09 | 0.304 | 0 | 703733.91 | 8 | 1.7 | 1.32
P005 | Mechanical | SUP021 | 2025-08 | 2025-05-25 | 1277532.55 | 1137081 | -140451.55 | 140451.55 | 0 | 2025-08-28 | 2 | 1418710.6 | -141178.05 | DOWN | 0.1105 | 95 | Low | 488425.66 | 0.409 | 0 | 648655.34 | 8 | 1.7 | 1.32
P005 | Mechanical | SUP021 | 2025-08 | 2025-08-17 | 1214704.61 | 1137081 | -77623.61 | 77623.61 | 0 | 2025-08-28 | 3 | 1277532.55 | -62827.94 | DOWN | 0.0517 | 11 | Medium | 892973.55 | 0.684 | 7 | 244107.45 | 8 | 1.7 | 1.32
P005 | Software | SUP021 | 2025-09 | 2025-05-24 | 2063735.84 | 1286826 | -776909.84 | 776909.84 | 1 | 2025-09-28 | 1 |  |  |  |  | 127 | Low | 723652.32 | 0.33 | 0 | 563173.68 | 0 | 0.5 | 0.8
P005 | Software | SUP021 | 2025-09 | 2025-08-09 | 1661355.41 | 1286826 | -374529.41 | 374529.41 | 1 | 2025-09-28 | 2 | 2063735.84 | -402380.43 | DOWN | 0.2422 | 50 | Low | 1026329.56 | 0.603 | 6 | 260496.44 | 0 | 0.5 | 0.8
P005 | Software | SUP021 | 2025-09 | 2025-08-23 | 1482285.81 | 1286826 | -195459.81 | 195459.81 | 0 | 2025-09-28 | 3 | 1661355.41 | -179069.6 | DOWN | 0.1208 | 36 | Low | 916646.29 | 0.652 | 7 | 370179.71 | 0 | 0.5 | 0.8
P005 | Software | SUP021 | 2025-09 | 2025-09-08 | 1368239.24 | 1286826 | -81413.24 | 81413.24 | 0 | 2025-09-28 | 4 | 1482285.81 | -114046.57 | DOWN | 0.0834 | 20 | Medium | 999618.44 | 0.709 | 2 | 287207.56 | 0 | 0.5 | 0.8
P005 | Electronics | SUP021 | 2025-10 | 2025-05-08 | 3789146.6 | 2647966 | -1141180.6 | 1141180.6 | 1 | 2025-10-28 | 1 |  |  |  |  | 173 | Low | 634231.99 | 0.164 | 2 | 2013734.01 | 4 | 1.15 | 0.8
P005 | Electronics | SUP021 | 2025-10 | 2025-06-15 | 3172721.28 | 2647966 | -524755.28 | 524755.28 | 1 | 2025-10-28 | 2 | 3789146.6 | -616425.32 | DOWN | 0.1943 | 135 | Low | 927482.85 | 0.296 | 0 | 1720483.15 | 4 | 1.15 | 0.8
P005 | Electronics | SUP021 | 2025-10 | 2025-08-01 | 2883115.53 | 2647966 | -235149.53 | 235149.53 | 0 | 2025-10-28 | 3 | 3172721.28 | -289605.75 | DOWN | 0.1004 | 88 | Low | 1350550.88 | 0.46 | 1 | 1297415.12 | 4 | 1.15 | 0.8
P005 | Electronics | SUP021 | 2025-10 | 2025-08-02 | 2785340.23 | 2647966 | -137374.23 | 137374.23 | 0 | 2025-10-28 | 4 | 2883115.53 | -97775.3 | DOWN | 0.0351 | 87 | Low | 1232410.23 | 0.463 | 5 | 1415555.77 | 4 | 1.15 | 0.8
P005 | Electronics | SUP021 | 2025-10 | 2025-10-06 | 2709351.82 | 2647966 | -61385.82 | 61385.82 | 0 | 2025-10-28 | 5 | 2785340.23 | -75988.41 | DOWN | 0.028 | 22 | High | 1801583.77 | 0.69 | 3 | 846382.23 | 4 | 1.15 | 0.8
P005 | Services | SUP021 | 2025-11 | 2025-06-08 | 2379654.74 | 1499941 | -879713.74 | 879713.74 | 1 | 2025-11-28 | 1 |  |  |  |  | 173 | Low | 365379.67 | 0.16 | 0 | 1134561.33 | 4 | 1.35 | 1.5
P005 | Services | SUP021 | 2025-11 | 2025-09-23 | 1896608.32 | 1499941 | -396667.32 | 396667.32 | 1 | 2025-11-28 | 2 | 2379654.74 | -483046.42 | DOWN | 0.2547 | 66 | Low | 1032150.65 | 0.524 | 6 | 467790.35 | 4 | 1.35 | 1.5
P005 | Services | SUP021 | 2025-11 | 2025-11-09 | 1694082.69 | 1499941 | -194141.69 | 194141.69 | 0 | 2025-11-28 | 3 | 1896608.32 | -202525.63 | DOWN | 0.1195 | 19 | Medium | 1211070.93 | 0.684 | 0 | 288870.07 | 4 | 1.35 | 1.5
P005 | Electronics | SUP021 | 2025-12 | 2025-07-12 | 1190616.58 | 837604 | -353012.58 | 353012.58 | 1 | 2025-12-28 | 1 |  |  |  |  | 169 | Low | 220198.51 | 0.181 | 1 | 617405.49 | 7 | 0.73 | 1.27
P005 | Electronics | SUP021 | 2025-12 | 2025-08-29 | 995172.09 | 837604 | -157568.09 | 157568.09 | 1 | 2025-12-28 | 2 | 1190616.58 | -195444.49 | DOWN | 0.1964 | 121 | Low | 369038.63 | 0.351 | 1 | 468565.37 | 7 | 0.73 | 1.27
P005 | Electronics | SUP021 | 2025-12 | 2025-09-14 | 916904.63 | 837604 | -79300.63 | 79300.63 | 0 | 2025-12-28 | 3 | 995172.09 | -78267.46 | DOWN | 0.0854 | 105 | Low | 371566.92 | 0.408 | 0 | 466037.08 | 7 | 0.73 | 1.27
P005 | Software | SUP011 | 2025-01 | 2024-08-12 | 1972472.39 | 1263873 | -708599.39 | 708599.39 | 1 | 2025-01-28 | 1 |  |  |  |  | 169 | Low | 304413.32 | 0.143 | 0 | 959459.68 | 8 | 1.44 | 1.07
P005 | Software | SUP011 | 2025-01 | 2024-08-26 | 1654816.53 | 1263873 | -390943.53 | 390943.53 | 1 | 2025-01-28 | 2 | 1972472.39 | -317655.86 | DOWN | 0.192 | 155 | Low | 319561.51 | 0.182 | 0 | 944311.49 | 8 | 1.44 | 1.07
P005 | Software | SUP011 | 2025-01 | 2024-09-09 | 1472685.69 | 1263873 | -208812.69 | 208812.69 | 0 | 2025-01-28 | 3 | 1654816.53 | -182130.84 | DOWN | 0.1237 | 141 | Low | 351453.53 | 0.222 | 2 | 912419.47 | 8 | 1.44 | 1.07
P005 | Software | SUP011 | 2025-01 | 2024-11-10 | 1362808.06 | 1263873 | -98935.06 | 98935.06 | 0 | 2025-01-28 | 4 | 1472685.69 | -109877.63 | DOWN | 0.0806 | 79 | Low | 542461.05 | 0.396 | 5 | 721411.95 | 8 | 1.44 | 1.07
P005 | Mechanical | SUP011 | 2025-02 | 2024-10-16 | 1255286.78 | 916147 | -339139.78 | 339139.78 | 1 | 2025-02-28 | 1 |  |  |  |  | 135 | Low | 308016.55 | 0.235 | 4 | 608130.45 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP011 | 2025-02 | 2024-10-24 | 1093143.23 | 916147 | -176996.23 | 176996.23 | 1 | 2025-02-28 | 2 | 1255286.78 | -162143.55 | DOWN | 0.1483 | 127 | Low | 283165.87 | 0.257 | 5 | 632981.13 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP011 | 2025-02 | 2024-10-28 | 1019622.07 | 916147 | -103475.07 | 103475.07 | 0 | 2025-02-28 | 3 | 1093143.23 | -73521.16 | DOWN | 0.0721 | 123 | Low | 284564.4 | 0.269 | 5 | 631582.6 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP011 | 2025-02 | 2024-11-23 | 969243.96 | 916147 | -53096.96 | 53096.96 | 0 | 2025-02-28 | 4 | 1019622.07 | -50378.11 | DOWN | 0.052 | 97 | Low | 305243.3 | 0.341 | 5 | 610903.7 | 7 | 1.56 | 1.03
P005 | Mechanical | SUP011 | 2025-02 | 2024-12-08 | 947461.96 | 916147 | -31314.96 | 31314.96 | 0 | 2025-02-28 | 5 | 969243.96 | -21782 | DOWN | 0.023 | 82 | Low | 337063.78 | 0.382 | 1 | 579083.22 | 7 | 1.56 | 1.03
P005 | Logistics | SUP011 | 2025-03 | 2024-10-26 | 2892624.99 | 1704561 | -1188063.99 | 1188063.99 | 1 | 2025-03-28 | 1 |  |  |  |  | 153 | Low | 584542.6 | 0.198 | 1 | 1120018.4 | 0 | 0.76 | 1.01
P005 | Logistics | SUP011 | 2025-03 | 2024-11-24 | 2309515.36 | 1704561 | -604954.36 | 604954.36 | 1 | 2025-03-28 | 2 | 2892624.99 | -583109.63 | DOWN | 0.2525 | 124 | Low | 693825.5 | 0.284 | 5 | 1010735.5 | 0 | 0.76 | 1.01
P005 | Logistics | SUP011 | 2025-03 | 2024-12-31 | 1992602.11 | 1704561 | -288041.11 | 288041.11 | 0 | 2025-03-28 | 3 | 2309515.36 | -316913.25 | DOWN | 0.159 | 87 | Low | 836176.28 | 0.393 | 3 | 868384.72 | 0 | 0.76 | 1.01
P005 | Services | SUP011 | 2025-04 | 2024-11-11 | 1808212.81 | 1024092 | -784120.81 | 784120.81 | 1 | 2025-04-28 | 1 |  |  |  |  | 168 | Low | 240752.98 | 0.145 | 2 | 783339.02 | 2 | 1.52 | 1.28
P005 | Services | SUP011 | 2025-04 | 2025-01-13 | 1463333.21 | 1024092 | -439241.21 | 439241.21 | 1 | 2025-04-28 | 2 | 1808212.81 | -344879.6 | DOWN | 0.2357 | 105 | Low | 438481.26 | 0.32 | 3 | 585610.74 | 2 | 1.52 | 1.28
P005 | Services | SUP011 | 2025-04 | 2025-02-12 | 1274124.38 | 1024092 | -250032.38 | 250032.38 | 1 | 2025-04-28 | 3 | 1463333.21 | -189208.83 | DOWN | 0.1485 | 75 | Low | 506504.7 | 0.403 | 0 | 517587.3 | 2 | 1.52 | 1.28
P005 | Services | SUP011 | 2025-04 | 2025-03-12 | 1169348.08 | 1024092 | -145256.08 | 145256.08 | 0 | 2025-04-28 | 4 | 1274124.38 | -104776.3 | DOWN | 0.0896 | 47 | Medium | 575270.26 | 0.481 | 2 | 448821.74 | 2 | 1.52 | 1.28
P005 | Services | SUP011 | 2025-04 | 2025-03-12 | 1105534.06 | 1024092 | -81442.06 | 81442.06 | 0 | 2025-04-28 | 5 | 1169348.08 | -63814.02 | DOWN | 0.0577 | 47 | Medium | 554954.2 | 0.481 | 5 | 469137.8 | 2 | 1.52 | 1.28
P005 | Mechanical | SUP011 | 2025-05 | 2024-12-13 | 545112.96 | 379323 | -165789.96 | 165789.96 | 1 | 2025-05-28 | 1 |  |  |  |  | 166 | Low | 80834.97 | 0.157 | 1 | 298488.03 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP011 | 2025-05 | 2025-01-07 | 471158.18 | 379323 | -91835.18 | 91835.18 | 1 | 2025-05-28 | 2 | 545112.96 | -73954.78 | DOWN | 0.157 | 141 | Low | 107171.8 | 0.23 | 0 | 272151.2 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP011 | 2025-05 | 2025-02-15 | 427760.94 | 379323 | -48437.94 | 48437.94 | 0 | 2025-05-28 | 3 | 471158.18 | -43397.24 | DOWN | 0.1015 | 102 | Low | 147817.64 | 0.344 | 5 | 231505.36 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP011 | 2025-05 | 2025-03-24 | 403750.08 | 379323 | -24427.08 | 24427.08 | 0 | 2025-05-28 | 4 | 427760.94 | -24010.86 | DOWN | 0.0595 | 65 | Low | 172817.26 | 0.451 | 1 | 206505.74 | 6 | 1.12 | 1.51
P005 | Mechanical | SUP011 | 2025-06 | 2025-01-12 | 1631987.09 | 1146579 | -485408.09 | 485408.09 | 1 | 2025-06-28 | 1 |  |  |  |  | 167 | Low | 235656.87 | 0.155 | 5 | 910922.13 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP011 | 2025-06 | 2025-02-22 | 1411619.64 | 1146579 | -265040.64 | 265040.64 | 1 | 2025-06-28 | 2 | 1631987.09 | -220367.45 | DOWN | 0.1561 | 126 | Low | 398244.57 | 0.274 | 2 | 748334.43 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP011 | 2025-06 | 2025-02-27 | 1293060.68 | 1146579 | -146481.68 | 146481.68 | 0 | 2025-06-28 | 3 | 1411619.64 | -118558.96 | DOWN | 0.0917 | 121 | Low | 388880.3 | 0.289 | 2 | 757698.7 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP011 | 2025-06 | 2025-03-26 | 1227747.43 | 1146579 | -81168.43 | 81168.43 | 0 | 2025-06-28 | 4 | 1293060.68 | -65313.25 | DOWN | 0.0532 | 94 | Low | 424280.34 | 0.368 | 3 | 722298.66 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP011 | 2025-06 | 2025-04-25 | 1191472.3 | 1146579 | -44893.3 | 44893.3 | 0 | 2025-06-28 | 5 | 1227747.43 | -36275.13 | DOWN | 0.0304 | 64 | Low | 555788.16 | 0.455 | 2 | 590790.84 | 7 | 1.1 | 1.21
P005 | Mechanical | SUP011 | 2025-06 | 2025-05-06 | 1174434.92 | 1146579 | -27855.92 | 27855.92 | 0 | 2025-06-28 | 6 | 1191472.3 | -17037.38 | DOWN | 0.0145 | 53 | Medium | 586240.58 | 0.488 | 4 | 560338.42 | 7 | 1.1 | 1.21
P005 | Software | SUP011 | 2025-07 | 2025-02-17 | 4091490.46 | 2259668 | -1831822.46 | 1831822.46 | 1 | 2025-07-28 | 1 |  |  |  |  | 161 | Low | 645962.06 | 0.171 | 2 | 1613705.94 | 1 | 1.18 | 1.15
P005 | Software | SUP011 | 2025-07 | 2025-03-16 | 3283572.21 | 2259668 | -1023904.21 | 1023904.21 | 1 | 2025-07-28 | 2 | 4091490.46 | -807918.25 | DOWN | 0.246 | 134 | Low | 807272.63 | 0.249 | 2 | 1452395.37 | 1 | 1.18 | 1.15
P005 | Software | SUP011 | 2025-07 | 2025-03-22 | 2874380.25 | 2259668 | -614712.25 | 614712.25 | 1 | 2025-07-28 | 3 | 3283572.21 | -409191.96 | DOWN | 0.1424 | 128 | Low | 765532.54 | 0.266 | 2 | 1494135.46 | 1 | 1.18 | 1.15
P005 | Software | SUP011 | 2025-07 | 2025-03-29 | 2582099.95 | 2259668 | -322431.95 | 322431.95 | 0 | 2025-07-28 | 4 | 2874380.25 | -292280.3 | DOWN | 0.1132 | 121 | Low | 731714.66 | 0.286 | 2 | 1527953.34 | 1 | 1.18 | 1.15
P005 | Software | SUP011 | 2025-07 | 2025-06-11 | 2470952.28 | 2259668 | -211284.28 | 211284.28 | 0 | 2025-07-28 | 5 | 2582099.95 | -111147.67 | DOWN | 0.045 | 47 | Medium | 1190308.16 | 0.5 | 2 | 1069359.84 | 1 | 1.18 | 1.15
P005 | Software | SUP011 | 2025-07 | 2025-06-16 | 2392859.28 | 2259668 | -133191.28 | 133191.28 | 0 | 2025-07-28 | 6 | 2470952.28 | -78093 | DOWN | 0.0326 | 42 | Medium | 1160792.7 | 0.515 | 8 | 1098875.3 | 1 | 1.18 | 1.15
P005 | Logistics | SUP011 | 2025-08 | 2025-04-01 | 2977700.54 | 1460919 | -1516781.54 | 1516781.54 | 1 | 2025-08-28 | 1 |  |  |  |  | 149 | Low | 570370.05 | 0.194 | 2 | 890548.95 | 8 | 1.7 | 1.32
P005 | Logistics | SUP011 | 2025-08 | 2025-05-08 | 2328843.44 | 1460919 | -867924.44 | 867924.44 | 1 | 2025-08-28 | 2 | 2977700.54 | -648857.1 | DOWN | 0.2786 | 112 | Low | 711522.11 | 0.294 | 0 | 749396.89 | 8 | 1.7 | 1.32
P005 | Logistics | SUP011 | 2025-08 | 2025-05-29 | 1936666.04 | 1460919 | -475747.04 | 475747.04 | 1 | 2025-08-28 | 3 | 2328843.44 | -392177.4 | DOWN | 0.2025 | 91 | Low | 664847.81 | 0.352 | 2 | 796071.19 | 8 | 1.7 | 1.32
P005 | Logistics | SUP011 | 2025-08 | 2025-06-08 | 1730621.76 | 1460919 | -269702.76 | 269702.76 | 1 | 2025-08-28 | 4 | 1936666.04 | -206044.28 | DOWN | 0.1191 | 81 | Low | 689773.73 | 0.379 | 1 | 771145.27 | 8 | 1.7 | 1.32
P005 | Logistics | SUP011 | 2025-08 | 2025-06-14 | 1591579.67 | 1460919 | -130660.67 | 130660.67 | 0 | 2025-08-28 | 5 | 1730621.76 | -139042.09 | DOWN | 0.0874 | 75 | Low | 677212.72 | 0.395 | 4 | 783706.28 | 8 | 1.7 | 1.32
P005 | Logistics | SUP011 | 2025-08 | 2025-06-14 | 1540484.82 | 1460919 | -79565.82 | 79565.82 | 0 | 2025-08-28 | 6 | 1591579.67 | -51094.85 | DOWN | 0.0332 | 75 | Low | 598952.7 | 0.395 | 3 | 861966.3 | 8 | 1.7 | 1.32
P005 | Materials | SUP011 | 2025-09 | 2025-04-01 | 2762174.22 | 1747129 | -1015045.22 | 1015045.22 | 1 | 2025-09-28 | 1 |  |  |  |  | 180 | Low | 343617.7 | 0.13 | 1 | 1403511.3 | 0 | 0.5 | 0.8
P005 | Materials | SUP011 | 2025-09 | 2025-05-22 | 2293974.89 | 1747129 | -546845.89 | 546845.89 | 1 | 2025-09-28 | 2 | 2762174.22 | -468199.33 | DOWN | 0.2041 | 129 | Low | 598967.51 | 0.269 | 3 | 1148161.49 | 0 | 0.5 | 0.8
P005 | Materials | SUP011 | 2025-09 | 2025-05-27 | 2037120.51 | 1747129 | -289991.51 | 289991.51 | 0 | 2025-09-28 | 3 | 2293974.89 | -256854.38 | DOWN | 0.1261 | 124 | Low | 583839.19 | 0.284 | 1 | 1163289.81 | 0 | 0.5 | 0.8
P005 | Materials | SUP011 | 2025-09 | 2025-06-27 | 1908670.92 | 1747129 | -161541.92 | 161541.92 | 0 | 2025-09-28 | 4 | 2037120.51 | -128449.59 | DOWN | 0.0673 | 93 | Low | 729279.59 | 0.375 | 4 | 1017849.41 | 0 | 0.5 | 0.8
P005 | Materials | SUP011 | 2025-09 | 2025-08-07 | 1838331.05 | 1747129 | -91202.05 | 91202.05 | 0 | 2025-09-28 | 5 | 1908670.92 | -70339.87 | DOWN | 0.0383 | 52 | Medium | 891564.63 | 0.496 | 2 | 855564.37 | 0 | 0.5 | 0.8
P005 | Mechanical | SUP011 | 2025-10 | 2025-06-05 | 1733256.64 | 1027343 | -705913.64 | 705913.64 | 1 | 2025-10-28 | 1 |  |  |  |  | 145 | Low | 359094.09 | 0.218 | 2 | 668248.91 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP011 | 2025-10 | 2025-07-19 | 1410950.39 | 1027343 | -383607.39 | 383607.39 | 1 | 2025-10-28 | 2 | 1733256.64 | -322306.25 | DOWN | 0.2284 | 101 | Low | 478261.46 | 0.345 | 7 | 549081.54 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP011 | 2025-10 | 2025-07-24 | 1247350.75 | 1027343 | -220007.75 | 220007.75 | 1 | 2025-10-28 | 3 | 1410950.39 | -163599.64 | DOWN | 0.1312 | 96 | Low | 475680.03 | 0.36 | 3 | 551662.97 | 4 | 1.15 | 0.8
P005 | Mechanical | SUP011 | 2025-10 | 2025-10-15 | 1140329.74 | 1027343 | -112986.74 | 112986.74 | 0 | 2025-10-28 | 4 | 1247350.75 | -107021.01 | DOWN | 0.0939 | 13 | Medium | 661828.29 | 0.601 | 5 | 365514.71 | 4 | 1.15 | 0.8
P005 | Logistics | SUP011 | 2025-11 | 2025-06-11 | 4365651.88 | 2273452 | -2092199.88 | 2092199.88 | 1 | 2025-11-28 | 1 |  |  |  |  | 170 | Low | 583911.61 | 0.142 | 0 | 1689540.39 | 4 | 1.35 | 1.5
P005 | Logistics | SUP011 | 2025-11 | 2025-06-19 | 3386523.74 | 2273452 | -1113071.74 | 1113071.74 | 1 | 2025-11-28 | 2 | 4365651.88 | -979128.14 | DOWN | 0.2891 | 162 | Low | 517214.08 | 0.164 | 1 | 1756237.92 | 4 | 1.35 | 1.5
P005 | Logistics | SUP011 | 2025-11 | 2025-06-19 | 2910606.15 | 2273452 | -637154.15 | 637154.15 | 1 | 2025-11-28 | 3 | 3386523.74 | -475917.59 | DOWN | 0.1635 | 162 | Low | 513586.5 | 0.164 | 0 | 1759865.5 | 4 | 1.35 | 1.5
P005 | Logistics | SUP011 | 2025-11 | 2025-06-25 | 2665157.37 | 2273452 | -391705.37 | 391705.37 | 0 | 2025-11-28 | 4 | 2910606.15 | -245448.78 | DOWN | 0.0921 | 156 | Low | 488827.85 | 0.181 | 0 | 1784624.15 | 4 | 1.35 | 1.5
P005 | Logistics | SUP011 | 2025-11 | 2025-09-06 | 2536657.26 | 2273452 | -263205.26 | 263205.26 | 0 | 2025-11-28 | 5 | 2665157.37 | -128500.11 | DOWN | 0.0507 | 83 | Low | 945354.53 | 0.388 | 4 | 1328097.47 | 4 | 1.35 | 1.5
P005 | Logistics | SUP011 | 2025-11 | 2025-10-30 | 2387752.63 | 2273452 | -114300.63 | 114300.63 | 0 | 2025-11-28 | 6 | 2536657.26 | -148904.63 | DOWN | 0.0624 | 29 | Medium | 1319457.85 | 0.542 | 7 | 953994.15 | 4 | 1.35 | 1.5
P005 | Materials | SUP011 | 2025-12 | 2025-07-22 | 3542452.55 | 1940377 | -1602075.55 | 1602075.55 | 1 | 2025-12-28 | 1 |  |  |  |  | 159 | Low | 616986.77 | 0.18 | 4 | 1323390.23 | 7 | 0.73 | 1.27
P005 | Materials | SUP011 | 2025-12 | 2025-08-21 | 2843971.49 | 1940377 | -903594.49 | 903594.49 | 1 | 2025-12-28 | 2 | 3542452.55 | -698481.06 | DOWN | 0.2456 | 129 | Low | 822485.54 | 0.269 | 0 | 1117891.46 | 7 | 0.73 | 1.27
P005 | Materials | SUP011 | 2025-12 | 2025-09-28 | 2460230.16 | 1940377 | -519853.16 | 519853.16 | 1 | 2025-12-28 | 3 | 2843971.49 | -383741.33 | DOWN | 0.156 | 91 | Low | 932331.97 | 0.381 | 2 | 1008045.03 | 7 | 0.73 | 1.27
P005 | Materials | SUP011 | 2025-12 | 2025-10-27 | 2246783.13 | 1940377 | -306406.13 | 306406.13 | 0 | 2025-12-28 | 4 | 2460230.16 | -213447.03 | DOWN | 0.095 | 62 | Low | 1097901.31 | 0.467 | 1 | 842475.69 | 7 | 0.73 | 1.27
P005 | Materials | SUP011 | 2025-12 | 2025-11-10 | 2102279.11 | 1940377 | -161902.11 | 161902.11 | 0 | 2025-12-28 | 5 | 2246783.13 | -144504.02 | DOWN | 0.0687 | 48 | Medium | 1031369.15 | 0.508 | 4 | 909007.85 | 7 | 0.73 | 1.27
P005 | Materials | SUP011 | 2025-12 | 2025-11-23 | 2046862.96 | 1940377 | -106485.96 | 106485.96 | 0 | 2025-12-28 | 6 | 2102279.11 | -55416.15 | DOWN | 0.0271 | 35 | Medium | 1043695.47 | 0.547 | 0 | 896681.53 | 7 | 0.73 | 1.27

## Supplier_Attributes
Supplier_ID | Contract_Type | Strategic_Flag | New_Supplier_Flag | Supplier_Profile | Region | Payment_Terms | OTIF_Pct | Avg_Lead_Time_Days | Quality_Incidents_YTD
SUP001 | Fixed Price | Yes | Yes | Stable | EU | 90 days | 90.1 | 52 | 2
SUP002 | Framework | Yes | Yes | Stable | EU | 90 days | 87.4 | 24 | 0
SUP003 | Fixed Price | Yes | No | Chronic Fade | APAC | 60 days | 67.9 | 74 | 10
SUP004 | Framework | Yes | Yes | Chronic Fade | US | 90 days | 66.9 | 79 | 9
SUP005 | Fixed Price | Yes | No | Stable | UK | 45 days | 94.1 | 54 | 1
SUP006 | T&M | No | Yes | Volatile | APAC | 60 days | 86 | 85 | 4
SUP007 | T&M | No | No | Late Spender | APAC | 45 days | 89.2 | 37 | 1
SUP008 | T&M | Yes | Yes | Stable | UK | 45 days | 87.4 | 44 | 2
SUP009 | Fixed Price | No | No | Stable | US | 30 days | 91.3 | 29 | 2
SUP010 | Framework | Yes | No | Optimistic | UK | 45 days | 89.8 | 65 | 1
SUP011 | T&M | Yes | Yes | Optimistic | APAC | 90 days | 84.8 | 47 | 3
SUP012 | Framework | No | Yes | Stable | US | 90 days | 88.6 | 28 | 2
SUP013 | Cost Plus | No | Yes | Chronic Fade | UK | 60 days | 82.4 | 106 | 9
SUP014 | Fixed Price | Yes | Yes | Volatile | APAC | 90 days | 83.3 | 65 | 2
SUP015 | Cost Plus | No | Yes | Stable | US | 45 days | 89.6 | 34 | 0
SUP016 | Fixed Price | No | No | Volatile | EU | 60 days | 85.8 | 80 | 6
SUP017 | Fixed Price | Yes | Yes | Optimistic | EU | 90 days | 88.1 | 31 | 4
SUP018 | Cost Plus | No | No | Optimistic | APAC | 30 days | 92.8 | 29 | 3
SUP019 | Cost Plus | No | No | Volatile | UK | 90 days | 82.3 | 54 | 1
SUP020 | Cost Plus | No | No | Chronic Fade | UK | 60 days | 74.6 | 103 | 9
SUP021 | T&M | No | Yes | Stable | US | 60 days | 91.4 | 52 | 2
SUP022 | Fixed Price | Yes | Yes | Volatile | UK | 45 days | 87.2 | 61 | 6
SUP023 | Fixed Price | No | No | Stable | EU | 30 days | 91 | 25 | 1
SUP024 | T&M | No | Yes | Optimistic | US | 30 days | 86.3 | 32 | 2
SUP025 | Framework | Yes | Yes | Volatile | US | 60 days | 70.4 | 81 | 7
SUP026 | T&M | Yes | No | Optimistic | APAC | 60 days | 83.3 | 55 | 0
SUP027 | Fixed Price | No | Yes | Optimistic | UK | 60 days | 80.8 | 28 | 0
SUP028 | Framework | Yes | Yes | Stable | EU | 60 days | 93.9 | 42 | 0
SUP029 | T&M | No | No | Stable | US | 45 days | 90.7 | 52 | 1
SUP030 | T&M | No | No | Optimistic | EU | 90 days | 81.6 | 60 | 2
SUP031 | Framework | Yes | Yes | Stable | US | 60 days | 93 | 20 | 1
SUP032 | Framework | No | No | Chronic Fade | APAC | 90 days | 75.1 | 73 | 6
SUP033 | Fixed Price | Yes | No | Optimistic | UK | 60 days | 81.7 | 41 | 3
SUP034 | Framework | No | No | Stable | US | 60 days | 86.5 | 33 | 2
SUP035 | Cost Plus | Yes | No | Optimistic | UK | 30 days | 84.4 | 62 | 1
SUP036 | Fixed Price | No | Yes | Volatile | APAC | 60 days | 84.2 | 59 | 5
SUP037 | Fixed Price | No | No | Stable | UK | 30 days | 89.7 | 30 | 1
SUP038 | Fixed Price | No | No | Late Spender | US | 45 days | 74.3 | 61 | 3
SUP039 | Fixed Price | Yes | Yes | Optimistic | UK | 90 days | 92.5 | 65 | 4
SUP040 | T&M | No | Yes | Optimistic | APAC | 45 days | 87.3 | 28 | 2
SUP041 | T&M | Yes | No | Volatile | UK | 30 days | 81.4 | 67 | 3
SUP042 | T&M | No | Yes | Stable | UK | 30 days | 91 | 22 | 1
SUP043 | Fixed Price | No | No | Optimistic | EU | 60 days | 87.5 | 49 | 4
SUP044 | Cost Plus | No | Yes | Stable | UK | 45 days | 95 | 22 | 2
SUP045 | Framework | Yes | Yes | Stable | US | 30 days | 89.6 | 28 | 1
SUP046 | Fixed Price | Yes | No | Stable | EU | 90 days | 86 | 24 | 0
SUP047 | Fixed Price | Yes | Yes | Stable | APAC | 60 days | 89.5 | 41 | 1
SUP048 | T&M | Yes | No | Chronic Fade | APAC | 90 days | 83.3 | 102 | 9
SUP049 | Cost Plus | No | Yes | Volatile | US | 90 days | 86.2 | 74 | 7
SUP050 | Cost Plus | Yes | No | Optimistic | APAC | 30 days | 80.4 | 53 | 2

## Programme_Attributes
Programme_ID | Programme_Phase | Programme_Value_GBP | Delivery_Risk
P001 | Design | 1200000000 | Medium
P002 | Design | 900000000 | High
P003 | Execution | 1800000000 | Medium
P004 | Execution | 650000000 | Low
P005 | Closeout | 420000000 | Low

## Portfolio_Funding_Envelope
Period | Total_Envelope_GBP | Ringfenced_GBP | Flexible_GBP | CFO_Confidence_Target
2025-01 | 227856744 | 142266768 | 85589976 | Medium
2025-02 | 230036085 | 142972308 | 87063777 | High
2025-03 | 231850345 | 151076176 | 80774169 | Medium
2025-04 | 224414807 | 137164071 | 87250736 | High
2025-05 | 229985490 | 136383026 | 93602464 | High
2025-06 | 252481205 | 142201142 | 110280063 | High
2025-07 | 220708071 | 152132811 | 68575260 | High
2025-08 | 228672611 | 155892622 | 72779989 | High
2025-09 | 231038375 | 148020030 | 83018345 | High
2025-10 | 219874513 | 143814997 | 76059516 | High
2025-11 | 225808939 | 128954540 | 96854399 | High
2025-12 | 250458629 | 166260349 | 84198280 | High

## Programme_Budget
Programme_ID | Annual_SupplyChain_Budget_GBP
P001 | 95866496
P002 | 74772429
P003 | 192252755
P004 | 76309876
P005 | 30249321

## Programme_Month_Change
Programme_ID | Period | Change_Count | Change_Impact_Index | Scope_Churn_Index
P001 | 2025-01 | 19 | 1.9 | 1.97
P001 | 2025-02 | 18 | 1.54 | 1.81
P001 | 2025-03 | 20 | 1.57 | 0.93
P001 | 2025-04 | 22 | 1.91 | 2.23
P001 | 2025-05 | 21 | 0.96 | 1.86
P001 | 2025-06 | 18 | 1.8 | 1.75
P001 | 2025-07 | 17 | 1.46 | 1.27
P001 | 2025-08 | 21 | 1.03 | 1.54
P001 | 2025-09 | 15 | 1.5 | 1.16
P001 | 2025-10 | 18 | 1.33 | 1.81
P001 | 2025-11 | 26 | 1.53 | 1.11
P001 | 2025-12 | 17 | 1.29 | 1.45
P002 | 2025-01 | 20 | 1.35 | 1.45
P002 | 2025-02 | 23 | 1.5 | 1.4
P002 | 2025-03 | 25 | 1.97 | 2.28
P002 | 2025-04 | 21 | 1.67 | 1.06
P002 | 2025-05 | 28 | 0.99 | 2.1
P002 | 2025-06 | 17 | 1.62 | 1.27
P002 | 2025-07 | 24 | 1.96 | 1.49
P002 | 2025-08 | 25 | 1.82 | 1.29
P002 | 2025-09 | 25 | 1.58 | 1.38
P002 | 2025-10 | 21 | 1.29 | 1.76
P002 | 2025-11 | 26 | 1.38 | 1.59
P002 | 2025-12 | 27 | 1.4 | 1.43
P003 | 2025-01 | 17 | 1.34 | 1.86
P003 | 2025-02 | 17 | 1.03 | 2.1
P003 | 2025-03 | 13 | 1.73 | 1.13
P003 | 2025-04 | 13 | 1.27 | 1.21
P003 | 2025-05 | 14 | 1.73 | 1.36
P003 | 2025-06 | 22 | 1.51 | 1.47
P003 | 2025-07 | 13 | 1.22 | 0.8
P003 | 2025-08 | 7 | 1.47 | 1.37
P003 | 2025-09 | 10 | 1.27 | 0.71
P003 | 2025-10 | 19 | 0.98 | 0.95
P003 | 2025-11 | 11 | 1.52 | 1.85
P003 | 2025-12 | 10 | 1.22 | 1.08
P004 | 2025-01 | 9 | 1.26 | 1
P004 | 2025-02 | 13 | 0.97 | 1.26
P004 | 2025-03 | 11 | 1.3 | 0.73
P004 | 2025-04 | 15 | 1.47 | 1.69
P004 | 2025-05 | 12 | 1.42 | 1.03
P004 | 2025-06 | 15 | 1.56 | 0.81
P004 | 2025-07 | 10 | 1 | 1.72
P004 | 2025-08 | 13 | 1.13 | 1.45
P004 | 2025-09 | 12 | 1.3 | 1.31
P004 | 2025-10 | 16 | 1.4 | 1.37
P004 | 2025-11 | 7 | 1.31 | 0.59
P004 | 2025-12 | 9 | 0.94 | 1.11
P005 | 2025-01 | 8 | 1.07 | 1.44
P005 | 2025-02 | 7 | 1.03 | 1.56
P005 | 2025-03 | 0 | 1.01 | 0.76
P005 | 2025-04 | 2 | 1.28 | 1.52
P005 | 2025-05 | 6 | 1.51 | 1.12
P005 | 2025-06 | 7 | 1.21 | 1.1
P005 | 2025-07 | 1 | 1.15 | 1.18
P005 | 2025-08 | 8 | 1.32 | 1.7
P005 | 2025-09 | 0 | 0.8 | 0.5
P005 | 2025-10 | 4 | 0.8 | 1.15
P005 | 2025-11 | 4 | 1.5 | 1.35
P005 | 2025-12 | 7 | 1.27 | 0.73

## Commitments_Summary
Programme_ID | Supplier_ID | Commodity | Forecast_Period | PO_Count | Committed_Spend | Payment_Terms | Region
P001 | SUP007 | Electronics | 2025-01 | 2 | 484457.02 | 45 days | APAC
P001 | SUP007 | Software | 2025-02 | 2 | 715418.19 | 45 days | APAC
P001 | SUP007 | Materials | 2025-03 | 2 | 146042.49 | 45 days | APAC
P001 | SUP007 | Services | 2025-04 | 3 | 592761.99 | 45 days | APAC
P001 | SUP007 | Electronics | 2025-05 | 1 | 597609.24 | 45 days | APAC
P001 | SUP007 | Services | 2025-06 | 5 | 208945.65 | 45 days | APAC
P001 | SUP007 | Logistics | 2025-07 | 2 | 980684.08 | 45 days | APAC
P001 | SUP007 | Mechanical | 2025-08 | 5 | 948984.65 | 45 days | APAC
P001 | SUP007 | Logistics | 2025-09 | 3 | 381468.32 | 45 days | APAC
P001 | SUP007 | Electronics | 2025-10 | 0 | 318004.57 | 45 days | APAC
P001 | SUP007 | Logistics | 2025-11 | 2 | 1305174.58 | 45 days | APAC
P001 | SUP007 | Electronics | 2025-12 | 0 | 671588.92 | 45 days | APAC
P001 | SUP015 | Software | 2025-01 | 4 | 1230898.97 | 45 days | US
P001 | SUP015 | Logistics | 2025-02 | 2 | 737650.58 | 45 days | US
P001 | SUP015 | Logistics | 2025-03 | 5 | 1108813.45 | 45 days | US
P001 | SUP015 | Software | 2025-04 | 4 | 656446.95 | 45 days | US
P001 | SUP015 | Materials | 2025-05 | 4 | 585637.57 | 45 days | US
P001 | SUP015 | Electronics | 2025-06 | 1 | 170623.05 | 45 days | US
P001 | SUP015 | Materials | 2025-07 | 5 | 827213.12 | 45 days | US
P001 | SUP015 | Electronics | 2025-08 | 6 | 1791005.02 | 45 days | US
P001 | SUP015 | Materials | 2025-09 | 5 | 576355.13 | 45 days | US
P001 | SUP015 | Software | 2025-10 | 7 | 823697.13 | 45 days | US
P001 | SUP015 | Mechanical | 2025-11 | 4 | 1032932.8 | 45 days | US
P001 | SUP015 | Logistics | 2025-12 | 4 | 266301.35 | 45 days | US
P001 | SUP012 | Mechanical | 2025-01 | 1 | 1484850.78 | 90 days | US
P001 | SUP012 | Software | 2025-02 | 7 | 855421.55 | 90 days | US
P001 | SUP012 | Services | 2025-03 | 2 | 563253.33 | 90 days | US
P001 | SUP012 | Services | 2025-04 | 5 | 587101.73 | 90 days | US
P001 | SUP012 | Materials | 2025-05 | 3 | 843015.02 | 90 days | US
P001 | SUP012 | Mechanical | 2025-06 | 4 | 666219.55 | 90 days | US
P001 | SUP012 | Materials | 2025-07 | 4 | 1099643.83 | 90 days | US
P001 | SUP012 | Materials | 2025-08 | 5 | 1152881.8 | 90 days | US
P001 | SUP012 | Electronics | 2025-09 | 7 | 770449.24 | 90 days | US
P001 | SUP012 | Services | 2025-10 | 5 | 320573.03 | 90 days | US
P001 | SUP012 | Software | 2025-11 | 5 | 302151.49 | 90 days | US
P001 | SUP012 | Services | 2025-12 | 1 | 171340.85 | 90 days | US
P001 | SUP048 | Mechanical | 2025-01 | 3 | 626861.54 | 90 days | APAC
P001 | SUP048 | Mechanical | 2025-02 | 2 | 255653.11 | 90 days | APAC
P001 | SUP048 | Mechanical | 2025-03 | 4 | 133567.12 | 90 days | APAC
P001 | SUP048 | Logistics | 2025-04 | 3 | 666390.08 | 90 days | APAC
P001 | SUP048 | Electronics | 2025-05 | 4 | 956431.68 | 90 days | APAC
P001 | SUP048 | Services | 2025-06 | 1 | 1656950.33 | 90 days | APAC
P001 | SUP048 | Services | 2025-07 | 3 | 1075979.14 | 90 days | APAC
P001 | SUP048 | Materials | 2025-08 | 4 | 314032.31 | 90 days | APAC
P001 | SUP048 | Logistics | 2025-09 | 1 | 344267.93 | 90 days | APAC
P001 | SUP048 | Services | 2025-10 | 1 | 392549.24 | 90 days | APAC
P001 | SUP048 | Software | 2025-11 | 2 | 289983.69 | 90 days | APAC
P001 | SUP048 | Logistics | 2025-12 | 2 | 760306.99 | 90 days | APAC
P001 | SUP006 | Mechanical | 2025-01 | 4 | 260339.85 | 60 days | APAC
P001 | SUP006 | Materials | 2025-02 | 1 | 775908.78 | 60 days | APAC
P001 | SUP006 | Services | 2025-03 | 4 | 1070640 | 60 days | APAC
P001 | SUP006 | Services | 2025-04 | 0 | 796733.52 | 60 days | APAC
P001 | SUP006 | Electronics | 2025-05 | 0 | 1217560.28 | 60 days | APAC
P001 | SUP006 | Logistics | 2025-06 | 4 | 584510.41 | 60 days | APAC
P001 | SUP006 | Mechanical | 2025-07 | 2 | 123905.29 | 60 days | APAC
P001 | SUP006 | Mechanical | 2025-08 | 3 | 1313446.08 | 60 days | APAC
P001 | SUP006 | Electronics | 2025-09 | 0 | 1547473.12 | 60 days | APAC
P001 | SUP006 | Electronics | 2025-10 | 0 | 260354.32 | 60 days | APAC
P001 | SUP006 | Electronics | 2025-11 | 2 | 709001.01 | 60 days | APAC
P001 | SUP006 | Software | 2025-12 | 5 | 194392.2 | 60 days | APAC
P001 | SUP049 | Services | 2025-01 | 2 | 458439.22 | 90 days | US
P001 | SUP049 | Mechanical | 2025-02 | 3 | 1121240.53 | 90 days | US
P001 | SUP049 | Mechanical | 2025-03 | 4 | 793550.36 | 90 days | US
P001 | SUP049 | Materials | 2025-04 | 2 | 577593.18 | 90 days | US
P001 | SUP049 | Mechanical | 2025-05 | 3 | 377190.9 | 90 days | US
P001 | SUP049 | Materials | 2025-06 | 3 | 232169.22 | 90 days | US
P001 | SUP049 | Services | 2025-07 | 2 | 491579.03 | 90 days | US
P001 | SUP049 | Software | 2025-08 | 8 | 1530795.95 | 90 days | US
P001 | SUP049 | Electronics | 2025-09 | 4 | 886711.08 | 90 days | US
P001 | SUP049 | Electronics | 2025-10 | 3 | 540907.91 | 90 days | US
P001 | SUP049 | Mechanical | 2025-11 | 5 | 1077648.57 | 90 days | US
P001 | SUP049 | Mechanical | 2025-12 | 0 | 980017.47 | 90 days | US
P001 | SUP031 | Materials | 2025-01 | 0 | 928531.39 | 60 days | US
P001 | SUP031 | Materials | 2025-02 | 3 | 1498064.19 | 60 days | US
P001 | SUP031 | Mechanical | 2025-03 | 2 | 1146426.9 | 60 days | US
P001 | SUP031 | Mechanical | 2025-04 | 7 | 288331.87 | 60 days | US
P001 | SUP031 | Mechanical | 2025-05 | 0 | 583050.31 | 60 days | US
P001 | SUP031 | Mechanical | 2025-06 | 3 | 1060217.7 | 60 days | US
P001 | SUP031 | Services | 2025-07 | 1 | 215650.9 | 60 days | US
P001 | SUP031 | Mechanical | 2025-08 | 4 | 698293.63 | 60 days | US
P001 | SUP031 | Logistics | 2025-09 | 3 | 906201.19 | 60 days | US
P001 | SUP031 | Electronics | 2025-10 | 6 | 147848.76 | 60 days | US
P001 | SUP031 | Materials | 2025-11 | 7 | 670609.94 | 60 days | US
P001 | SUP031 | Mechanical | 2025-12 | 2 | 853331.03 | 60 days | US
P001 | SUP029 | Mechanical | 2025-01 | 4 | 1063000.84 | 45 days | US
P001 | SUP029 | Mechanical | 2025-02 | 2 | 1389171.4 | 45 days | US
P001 | SUP029 | Materials | 2025-03 | 8 | 427384.67 | 45 days | US
P001 | SUP029 | Mechanical | 2025-04 | 6 | 407435.07 | 45 days | US
P001 | SUP029 | Services | 2025-05 | 2 | 713770.07 | 45 days | US
P001 | SUP029 | Mechanical | 2025-06 | 0 | 487380.43 | 45 days | US
P001 | SUP029 | Materials | 2025-07 | 5 | 661797.37 | 45 days | US
P001 | SUP029 | Software | 2025-08 | 7 | 147785.43 | 45 days | US
P001 | SUP029 | Software | 2025-09 | 3 | 1596352.98 | 45 days | US
P001 | SUP029 | Electronics | 2025-10 | 4 | 1131132.96 | 45 days | US
P001 | SUP029 | Services | 2025-11 | 5 | 1469270.98 | 45 days | US
P001 | SUP029 | Services | 2025-12 | 6 | 967147.97 | 45 days | US
P001 | SUP025 | Logistics | 2025-01 | 0 | 514177.48 | 60 days | US
P001 | SUP025 | Materials | 2025-02 | 1 | 179754.54 | 60 days | US
P001 | SUP025 | Services | 2025-03 | 2 | 1057935.99 | 60 days | US
P001 | SUP025 | Logistics | 2025-04 | 0 | 678350.06 | 60 days | US
P001 | SUP025 | Electronics | 2025-05 | 3 | 1140902.89 | 60 days | US
P001 | SUP025 | Services | 2025-06 | 7 | 263068.23 | 60 days | US
P001 | SUP025 | Materials | 2025-07 | 2 | 132230.62 | 60 days | US
P001 | SUP025 | Logistics | 2025-08 | 3 | 382280.67 | 60 days | US
P001 | SUP025 | Software | 2025-09 | 4 | 932727.94 | 60 days | US
P001 | SUP025 | Logistics | 2025-10 | 1 | 952955.4 | 60 days | US
P001 | SUP025 | Mechanical | 2025-11 | 3 | 1162303.22 | 60 days | US
P001 | SUP025 | Services | 2025-12 | 4 | 1290173.77 | 60 days | US
P001 | SUP023 | Logistics | 2025-01 | 4 | 472005.17 | 30 days | EU
P001 | SUP023 | Logistics | 2025-02 | 2 | 236757.68 | 30 days | EU
P001 | SUP023 | Electronics | 2025-03 | 6 | 620970.89 | 30 days | EU
P001 | SUP023 | Materials | 2025-04 | 6 | 719259.59 | 30 days | EU
P001 | SUP023 | Software | 2025-05 | 6 | 685806.02 | 30 days | EU
P001 | SUP023 | Software | 2025-06 | 7 | 1377836.64 | 30 days | EU
P001 | SUP023 | Materials | 2025-07 | 3 | 910184.49 | 30 days | EU
P001 | SUP023 | Services | 2025-08 | 6 | 369872.23 | 30 days | EU
P001 | SUP023 | Services | 2025-09 | 10 | 867495.54 | 30 days | EU
P001 | SUP023 | Services | 2025-10 | 3 | 1111213.26 | 30 days | EU
P001 | SUP023 | Software | 2025-11 | 3 | 784275.43 | 30 days | EU
P001 | SUP023 | Electronics | 2025-12 | 1 | 1010952.16 | 30 days | EU
P001 | SUP032 | Materials | 2025-01 | 5 | 495817.19 | 90 days | APAC
P001 | SUP032 | Software | 2025-02 | 2 | 786863.61 | 90 days | APAC
P001 | SUP032 | Electronics | 2025-03 | 0 | 925401.19 | 90 days | APAC
P001 | SUP032 | Software | 2025-04 | 2 | 871354.94 | 90 days | APAC
P001 | SUP032 | Software | 2025-05 | 0 | 392525.56 | 90 days | APAC
P001 | SUP032 | Materials | 2025-06 | 1 | 1327833.94 | 90 days | APAC
P001 | SUP032 | Electronics | 2025-07 | 5 | 870319.82 | 90 days | APAC
P001 | SUP032 | Logistics | 2025-08 | 3 | 405559.24 | 90 days | APAC
P001 | SUP032 | Electronics | 2025-09 | 0 | 491424.18 | 90 days | APAC
P001 | SUP032 | Logistics | 2025-10 | 3 | 706125.8 | 90 days | APAC
P001 | SUP032 | Materials | 2025-11 | 4 | 157026.11 | 90 days | APAC
P001 | SUP032 | Materials | 2025-12 | 4 | 1078534.22 | 90 days | APAC
P001 | SUP024 | Logistics | 2025-01 | 1 | 1035955.43 | 30 days | US
P001 | SUP024 | Electronics | 2025-02 | 4 | 1330806.95 | 30 days | US
P001 | SUP024 | Services | 2025-03 | 6 | 388266.1 | 30 days | US
P001 | SUP024 | Electronics | 2025-04 | 0 | 425391.89 | 30 days | US
P001 | SUP024 | Software | 2025-05 | 5 | 803216.85 | 30 days | US
P001 | SUP024 | Materials | 2025-06 | 5 | 761518.14 | 30 days | US
P001 | SUP024 | Software | 2025-07 | 4 | 1049172.26 | 30 days | US
P001 | SUP024 | Mechanical | 2025-08 | 4 | 954631.38 | 30 days | US
P001 | SUP024 | Software | 2025-09 | 4 | 1230953.26 | 30 days | US
P001 | SUP024 | Logistics | 2025-10 | 0 | 859973.08 | 30 days | US
P001 | SUP024 | Electronics | 2025-11 | 0 | 619846.94 | 30 days | US
P001 | SUP024 | Materials | 2025-12 | 4 | 592524.42 | 30 days | US
P001 | SUP008 | Materials | 2025-01 | 6 | 810306.1 | 45 days | UK
P001 | SUP008 | Software | 2025-02 | 2 | 492804.69 | 45 days | UK
P001 | SUP008 | Materials | 2025-03 | 7 | 1079858.41 | 45 days | UK
P001 | SUP008 | Logistics | 2025-04 | 6 | 448929.73 | 45 days | UK
P001 | SUP008 | Services | 2025-05 | 2 | 1179279.66 | 45 days | UK
P001 | SUP008 | Services | 2025-06 | 4 | 367478.44 | 45 days | UK
P001 | SUP008 | Mechanical | 2025-07 | 6 | 464693.64 | 45 days | UK
P001 | SUP008 | Services | 2025-08 | 3 | 1312326.63 | 45 days | UK
P001 | SUP008 | Electronics | 2025-09 | 6 | 1215539.25 | 45 days | UK
P001 | SUP008 | Services | 2025-10 | 2 | 387550.82 | 45 days | UK
P001 | SUP008 | Logistics | 2025-11 | 3 | 689993.6 | 45 days | UK
P001 | SUP008 | Materials | 2025-12 | 4 | 90744.22 | 45 days | UK
P001 | SUP036 | Logistics | 2025-01 | 0 | 88853.85 | 60 days | APAC
P001 | SUP036 | Services | 2025-02 | 4 | 408330.33 | 60 days | APAC
P001 | SUP036 | Logistics | 2025-03 | 1 | 767733.8 | 60 days | APAC
P001 | SUP036 | Services | 2025-04 | 5 | 727277.91 | 60 days | APAC
P001 | SUP036 | Services | 2025-05 | 5 | 1445356.33 | 60 days | APAC
P001 | SUP036 | Services | 2025-06 | 1 | 97723.02 | 60 days | APAC
P001 | SUP036 | Services | 2025-07 | 2 | 299050.99 | 60 days | APAC
P001 | SUP036 | Mechanical | 2025-08 | 0 | 189021.66 | 60 days | APAC
P001 | SUP036 | Materials | 2025-09 | 1 | 338194.05 | 60 days | APAC
P001 | SUP036 | Logistics | 2025-10 | 2 | 305043.89 | 60 days | APAC
P001 | SUP036 | Logistics | 2025-11 | 5 | 1157468.97 | 60 days | APAC
P001 | SUP036 | Services | 2025-12 | 4 | 1274336.47 | 60 days | APAC
P001 | SUP013 | Electronics | 2025-01 | 5 | 425245.6 | 60 days | UK
P001 | SUP013 | Services | 2025-02 | 3 | 1294388.88 | 60 days | UK
P001 | SUP013 | Mechanical | 2025-03 | 2 | 266952.37 | 60 days | UK
P001 | SUP013 | Services | 2025-04 | 2 | 947673.83 | 60 days | UK
P001 | SUP013 | Materials | 2025-05 | 4 | 89529.69 | 60 days | UK
P001 | SUP013 | Logistics | 2025-06 | 4 | 587199.42 | 60 days | UK
P001 | SUP013 | Logistics | 2025-07 | 4 | 555893.52 | 60 days | UK
P001 | SUP013 | Software | 2025-08 | 4 | 1189488.18 | 60 days | UK
P001 | SUP013 | Software | 2025-09 | 2 | 696978.01 | 60 days | UK
P001 | SUP013 | Logistics | 2025-10 | 1 | 1254916.5 | 60 days | UK
P001 | SUP013 | Logistics | 2025-11 | 2 | 621671.45 | 60 days | UK
P001 | SUP013 | Services | 2025-12 | 0 | 254206.78 | 60 days | UK
P001 | SUP028 | Electronics | 2025-01 | 6 | 1086484.44 | 60 days | EU
P001 | SUP028 | Materials | 2025-02 | 2 | 902931.64 | 60 days | EU
P001 | SUP028 | Electronics | 2025-03 | 7 | 1015840.31 | 60 days | EU
P001 | SUP028 | Services | 2025-04 | 5 | 317781.1 | 60 days | EU
P001 | SUP028 | Software | 2025-05 | 3 | 1128707.43 | 60 days | EU
P001 | SUP028 | Materials | 2025-06 | 0 | 1317293.26 | 60 days | EU
P001 | SUP028 | Mechanical | 2025-07 | 3 | 365185.37 | 60 days | EU
P001 | SUP028 | Logistics | 2025-08 | 4 | 155218.7 | 60 days | EU
P001 | SUP028 | Services | 2025-09 | 5 | 195254.25 | 60 days | EU
P001 | SUP028 | Electronics | 2025-10 | 4 | 692275.19 | 60 days | EU
P001 | SUP028 | Mechanical | 2025-11 | 4 | 238315.06 | 60 days | EU
P001 | SUP028 | Services | 2025-12 | 0 | 1065920.77 | 60 days | EU
P001 | SUP020 | Logistics | 2025-01 | 0 | 1203588.01 | 60 days | UK
P001 | SUP020 | Software | 2025-02 | 2 | 351075.6 | 60 days | UK
P001 | SUP020 | Mechanical | 2025-03 | 2 | 849727.12 | 60 days | UK
P001 | SUP020 | Logistics | 2025-04 | 2 | 842627.84 | 60 days | UK
P001 | SUP020 | Software | 2025-05 | 1 | 426899.51 | 60 days | UK
P001 | SUP020 | Electronics | 2025-06 | 4 | 150151.28 | 60 days | UK
P001 | SUP020 | Services | 2025-07 | 2 | 940143.28 | 60 days | UK
P001 | SUP020 | Electronics | 2025-08 | 3 | 1226001.04 | 60 days | UK
P001 | SUP020 | Logistics | 2025-09 | 2 | 112986.97 | 60 days | UK
P001 | SUP020 | Materials | 2025-10 | 3 | 277293.17 | 60 days | UK
P001 | SUP020 | Services | 2025-11 | 4 | 932871.49 | 60 days | UK
P001 | SUP020 | Software | 2025-12 | 3 | 1283651.68 | 60 days | UK
P001 | SUP010 | Services | 2025-01 | 4 | 759393.8 | 45 days | UK
P001 | SUP010 | Logistics | 2025-02 | 2 | 225034.97 | 45 days | UK
P001 | SUP010 | Software | 2025-03 | 7 | 1053995.03 | 45 days | UK
P001 | SUP010 | Electronics | 2025-04 | 2 | 1083856 | 45 days | UK
P001 | SUP010 | Services | 2025-05 | 4 | 87231.05 | 45 days | UK
P001 | SUP010 | Materials | 2025-06 | 3 | 299212.41 | 45 days | UK
P001 | SUP010 | Electronics | 2025-07 | 6 | 259959.08 | 45 days | UK
P001 | SUP010 | Services | 2025-08 | 4 | 296490.56 | 45 days | UK
P001 | SUP010 | Electronics | 2025-09 | 6 | 1021524.44 | 45 days | UK
P001 | SUP010 | Software | 2025-10 | 0 | 906804.36 | 45 days | UK
P001 | SUP010 | Materials | 2025-11 | 4 | 1125926.4 | 45 days | UK
P001 | SUP010 | Mechanical | 2025-12 | 5 | 1107784.32 | 45 days | UK
P002 | SUP027 | Services | 2025-01 | 0 | 203594.62 | 60 days | UK
P002 | SUP027 | Electronics | 2025-02 | 0 | 338621.2 | 60 days | UK
P002 | SUP027 | Electronics | 2025-03 | 3 | 215453.95 | 60 days | UK
P002 | SUP027 | Materials | 2025-04 | 4 | 236640.85 | 60 days | UK
P002 | SUP027 | Software | 2025-05 | 2 | 914850.75 | 60 days | UK
P002 | SUP027 | Logistics | 2025-06 | 5 | 578893.31 | 60 days | UK
P002 | SUP027 | Materials | 2025-07 | 3 | 917444.96 | 60 days | UK
P002 | SUP027 | Materials | 2025-08 | 2 | 664772.05 | 60 days | UK
P002 | SUP027 | Mechanical | 2025-09 | 6 | 1036117.24 | 60 days | UK
P002 | SUP027 | Materials | 2025-10 | 1 | 571105.35 | 60 days | UK
P002 | SUP027 | Services | 2025-11 | 3 | 974356.77 | 60 days | UK
P002 | SUP027 | Services | 2025-12 | 2 | 1241706.61 | 60 days | UK
P002 | SUP050 | Software | 2025-01 | 4 | 666785.22 | 30 days | APAC
P002 | SUP050 | Logistics | 2025-02 | 6 | 429316.03 | 30 days | APAC
P002 | SUP050 | Software | 2025-03 | 2 | 834322.72 | 30 days | APAC
P002 | SUP050 | Mechanical | 2025-04 | 3 | 627469.79 | 30 days | APAC
P002 | SUP050 | Mechanical | 2025-05 | 2 | 1130887.02 | 30 days | APAC
P002 | SUP050 | Software | 2025-06 | 2 | 1233542.49 | 30 days | APAC
P002 | SUP050 | Software | 2025-07 | 5 | 90534.35 | 30 days | APAC
P002 | SUP050 | Software | 2025-08 | 4 | 1360783.99 | 30 days | APAC
P002 | SUP050 | Software | 2025-09 | 2 | 472311.71 | 30 days | APAC
P002 | SUP050 | Services | 2025-10 | 5 | 958068.63 | 30 days | APAC
P002 | SUP050 | Electronics | 2025-11 | 2 | 728562.38 | 30 days | APAC
P002 | SUP050 | Software | 2025-12 | 2 | 1580230.98 | 30 days | APAC
P002 | SUP028 | Mechanical | 2025-01 | 3 | 1410169.39 | 60 days | EU
P002 | SUP028 | Materials | 2025-02 | 6 | 377635.73 | 60 days | EU
P002 | SUP028 | Mechanical | 2025-03 | 4 | 160941.3 | 60 days | EU
P002 | SUP028 | Software | 2025-04 | 7 | 1835485.85 | 60 days | EU
P002 | SUP028 | Software | 2025-05 | 5 | 469154.23 | 60 days | EU
P002 | SUP028 | Mechanical | 2025-06 | 7 | 882773.04 | 60 days | EU
P002 | SUP028 | Services | 2025-07 | 3 | 869797.05 | 60 days | EU
P002 | SUP028 | Electronics | 2025-08 | 5 | 1022999.11 | 60 days | EU
P002 | SUP028 | Mechanical | 2025-09 | 3 | 808820.1 | 60 days | EU
P002 | SUP028 | Materials | 2025-10 | 3 | 1638946.31 | 60 days | EU
P002 | SUP028 | Electronics | 2025-11 | 6 | 378877.02 | 60 days | EU
P002 | SUP028 | Logistics | 2025-12 | 0 | 2115099.47 | 60 days | EU
P002 | SUP045 | Electronics | 2025-01 | 7 | 1134304.37 | 30 days | US
P002 | SUP045 | Logistics | 2025-02 | 3 | 2191637.67 | 30 days | US
P002 | SUP045 | Logistics | 2025-03 | 4 | 1446651.39 | 30 days | US
P002 | SUP045 | Software | 2025-04 | 5 | 1757656.5 | 30 days | US
P002 | SUP045 | Software | 2025-05 | 6 | 112882.36 | 30 days | US
P002 | SUP045 | Materials | 2025-06 | 4 | 1738381.01 | 30 days | US
P002 | SUP045 | Services | 2025-07 | 5 | 1929357.86 | 30 days | US
P002 | SUP045 | Mechanical | 2025-08 | 0 | 2423317.76 | 30 days | US
P002 | SUP045 | Services | 2025-09 | 9 | 684069.91 | 30 days | US
P002 | SUP045 | Mechanical | 2025-10 | 2 | 1408472.51 | 30 days | US
P002 | SUP045 | Materials | 2025-11 | 4 | 825597.41 | 30 days | US
P002 | SUP045 | Services | 2025-12 | 5 | 2004723.86 | 30 days | US
P002 | SUP047 | Services | 2025-01 | 5 | 171528.41 | 60 days | APAC
P002 | SUP047 | Electronics | 2025-02 | 3 | 1733405.94 | 60 days | APAC
P002 | SUP047 | Services | 2025-03 | 5 | 775906.21 | 60 days | APAC
P002 | SUP047 | Mechanical | 2025-04 | 1 | 308365.36 | 60 days | APAC
P002 | SUP047 | Services | 2025-05 | 0 | 361477.92 | 60 days | APAC
P002 | SUP047 | Materials | 2025-06 | 8 | 1140276.58 | 60 days | APAC
P002 | SUP047 | Logistics | 2025-07 | 5 | 899046.46 | 60 days | APAC
P002 | SUP047 | Software | 2025-08 | 2 | 465456.48 | 60 days | APAC
P002 | SUP047 | Mechanical | 2025-09 | 4 | 515776.88 | 60 days | APAC
P002 | SUP047 | Materials | 2025-10 | 5 | 1814090.82 | 60 days | APAC
P002 | SUP047 | Mechanical | 2025-11 | 6 | 710203.22 | 60 days | APAC
P002 | SUP047 | Electronics | 2025-12 | 5 | 380225.85 | 60 days | APAC
P002 | SUP022 | Electronics | 2025-01 | 4 | 213720.71 | 45 days | UK
P002 | SUP022 | Software | 2025-02 | 3 | 1240926.08 | 45 days | UK
P002 | SUP022 | Software | 2025-03 | 0 | 1279270.89 | 45 days | UK
P002 | SUP022 | Services | 2025-04 | 3 | 696759.22 | 45 days | UK
P002 | SUP022 | Materials | 2025-05 | 4 | 668863.95 | 45 days | UK
P002 | SUP022 | Services | 2025-06 | 4 | 744772.97 | 45 days | UK
P002 | SUP022 | Mechanical | 2025-07 | 4 | 910416.74 | 45 days | UK
P002 | SUP022 | Mechanical | 2025-08 | 4 | 311489.27 | 45 days | UK
P002 | SUP022 | Software | 2025-09 | 3 | 559047.79 | 45 days | UK
P002 | SUP022 | Services | 2025-10 | 4 | 270073.78 | 45 days | UK
P002 | SUP022 | Software | 2025-11 | 1 | 401987.77 | 45 days | UK
P002 | SUP022 | Materials | 2025-12 | 3 | 1028643.87 | 45 days | UK
P002 | SUP002 | Software | 2025-01 | 5 | 1321979.96 | 90 days | EU
P002 | SUP002 | Materials | 2025-02 | 4 | 925983.51 | 90 days | EU
P002 | SUP002 | Logistics | 2025-03 | 2 | 105314.47 | 90 days | EU
P002 | SUP002 | Logistics | 2025-04 | 7 | 1820214.7 | 90 days | EU
P002 | SUP002 | Electronics | 2025-05 | 4 | 427813.41 | 90 days | EU
P002 | SUP002 | Materials | 2025-06 | 0 | 720896 | 90 days | EU
P002 | SUP002 | Materials | 2025-07 | 7 | 1664516.17 | 90 days | EU
P002 | SUP002 | Logistics | 2025-08 | 5 | 434856.16 | 90 days | EU
P002 | SUP002 | Mechanical | 2025-09 | 7 | 272405.76 | 90 days | EU
P002 | SUP002 | Logistics | 2025-10 | 4 | 406538.47 | 90 days | EU
P002 | SUP002 | Logistics | 2025-11 | 3 | 758235.41 | 90 days | EU
P002 | SUP002 | Electronics | 2025-12 | 0 | 2192554.88 | 90 days | EU
P002 | SUP008 | Services | 2025-01 | 0 | 1518312.04 | 45 days | UK
P002 | SUP008 | Services | 2025-02 | 5 | 985940.41 | 45 days | UK
P002 | SUP008 | Mechanical | 2025-03 | 7 | 1027279.89 | 45 days | UK
P002 | SUP008 | Software | 2025-04 | 4 | 445469.75 | 45 days | UK
P002 | SUP008 | Materials | 2025-05 | 9 | 451472.05 | 45 days | UK
P002 | SUP008 | Software | 2025-06 | 2 | 1330196.96 | 45 days | UK
P002 | SUP008 | Services | 2025-07 | 4 | 1110176.76 | 45 days | UK
P002 | SUP008 | Logistics | 2025-08 | 6 | 368952.82 | 45 days | UK
P002 | SUP008 | Mechanical | 2025-09 | 5 | 632228.37 | 45 days | UK
P002 | SUP008 | Electronics | 2025-10 | 0 | 625699.88 | 45 days | UK
P002 | SUP008 | Software | 2025-11 | 1 | 976450.3 | 45 days | UK
P002 | SUP008 | Electronics | 2025-12 | 6 | 578298.45 | 45 days | UK
P002 | SUP048 | Mechanical | 2025-01 | 1 | 707242.75 | 90 days | APAC
P002 | SUP048 | Services | 2025-02 | 0 | 749518.67 | 90 days | APAC
P002 | SUP048 | Mechanical | 2025-03 | 1 | 927513.88 | 90 days | APAC
P002 | SUP048 | Services | 2025-04 | 4 | 1525203.21 | 90 days | APAC
P002 | SUP048 | Materials | 2025-05 | 2 | 601709 | 90 days | APAC
P002 | SUP048 | Logistics | 2025-06 | 2 | 1080023.41 | 90 days | APAC
P002 | SUP048 | Services | 2025-07 | 1 | 538215.29 | 90 days | APAC
P002 | SUP048 | Services | 2025-08 | 4 | 748615.4 | 90 days | APAC
P002 | SUP048 | Services | 2025-09 | 5 | 605581.38 | 90 days | APAC
P002 | SUP048 | Materials | 2025-10 | 0 | 1132531.79 | 90 days | APAC
P002 | SUP048 | Materials | 2025-11 | 0 | 688869.48 | 90 days | APAC
P002 | SUP048 | Mechanical | 2025-12 | 4 | 899923.18 | 90 days | APAC
P002 | SUP046 | Software | 2025-01 | 4 | 368194.94 | 90 days | EU
P002 | SUP046 | Mechanical | 2025-02 | 5 | 1831633.22 | 90 days | EU
P002 | SUP046 | Materials | 2025-03 | 4 | 1158699.81 | 90 days | EU
P002 | SUP046 | Services | 2025-04 | 7 | 1973613.42 | 90 days | EU
P002 | SUP046 | Logistics | 2025-05 | 4 | 533260.03 | 90 days | EU
P002 | SUP046 | Software | 2025-06 | 5 | 1868494.7 | 90 days | EU
P002 | SUP046 | Logistics | 2025-07 | 3 | 1920180.99 | 90 days | EU
P002 | SUP046 | Logistics | 2025-08 | 3 | 1518460.72 | 90 days | EU
P002 | SUP046 | Services | 2025-09 | 3 | 615426.01 | 90 days | EU
P002 | SUP046 | Materials | 2025-10 | 4 | 916327.38 | 90 days | EU
P002 | SUP046 | Materials | 2025-11 | 2 | 498310.13 | 90 days | EU
P002 | SUP046 | Services | 2025-12 | 8 | 1468126.81 | 90 days | EU
P002 | SUP041 | Logistics | 2025-01 | 5 | 355520.19 | 30 days | UK
P002 | SUP041 | Logistics | 2025-02 | 5 | 629854.28 | 30 days | UK
P002 | SUP041 | Software | 2025-03 | 5 | 226862.17 | 30 days | UK
P002 | SUP041 | Electronics | 2025-04 | 5 | 309834.28 | 30 days | UK
P002 | SUP041 | Mechanical | 2025-05 | 2 | 798763.01 | 30 days | UK
P002 | SUP041 | Logistics | 2025-06 | 2 | 630887.25 | 30 days | UK
P002 | SUP041 | Mechanical | 2025-07 | 3 | 417622.4 | 30 days | UK
P002 | SUP041 | Logistics | 2025-08 | 6 | 1026897.58 | 30 days | UK
P002 | SUP041 | Services | 2025-09 | 4 | 982732.17 | 30 days | UK
P002 | SUP041 | Services | 2025-10 | 2 | 525238.2 | 30 days | UK
P002 | SUP041 | Electronics | 2025-11 | 3 | 845880.64 | 30 days | UK
P002 | SUP041 | Electronics | 2025-12 | 1 | 357097.13 | 30 days | UK
P002 | SUP015 | Materials | 2025-01 | 4 | 1662570.9 | 45 days | US
P002 | SUP015 | Materials | 2025-02 | 1 | 1805774.33 | 45 days | US
P002 | SUP015 | Software | 2025-03 | 8 | 1326648.28 | 45 days | US
P002 | SUP015 | Materials | 2025-04 | 4 | 636725.68 | 45 days | US
P002 | SUP015 | Software | 2025-05 | 5 | 447994.93 | 45 days | US
P002 | SUP015 | Mechanical | 2025-06 | 2 | 440152.9 | 45 days | US
P002 | SUP015 | Materials | 2025-07 | 4 | 1236964.57 | 45 days | US
P002 | SUP015 | Services | 2025-08 | 4 | 129909.65 | 45 days | US
P002 | SUP015 | Software | 2025-09 | 4 | 356016.15 | 45 days | US
P002 | SUP015 | Electronics | 2025-10 | 7 | 239649.42 | 45 days | US
P002 | SUP015 | Mechanical | 2025-11 | 4 | 994771.44 | 45 days | US
P002 | SUP015 | Mechanical | 2025-12 | 4 | 409641.78 | 45 days | US
P002 | SUP001 | Services | 2025-01 | 2 | 1014370.77 | 90 days | EU
P002 | SUP001 | Services | 2025-02 | 5 | 871846.4 | 90 days | EU
P002 | SUP001 | Logistics | 2025-03 | 5 | 453778.94 | 90 days | EU
P002 | SUP001 | Electronics | 2025-04 | 2 | 300234.8 | 90 days | EU
P002 | SUP001 | Mechanical | 2025-05 | 1 | 612394.71 | 90 days | EU
P002 | SUP001 | Services | 2025-06 | 2 | 1926260.67 | 90 days | EU
P002 | SUP001 | Services | 2025-07 | 7 | 762891.51 | 90 days | EU
P002 | SUP001 | Services | 2025-08 | 7 | 395824.97 | 90 days | EU
P002 | SUP001 | Logistics | 2025-09 | 1 | 1298980.9 | 90 days | EU
P002 | SUP001 | Materials | 2025-10 | 4 | 183691.09 | 90 days | EU
P002 | SUP001 | Services | 2025-11 | 3 | 919246.36 | 90 days | EU
P002 | SUP001 | Materials | 2025-12 | 6 | 1562148.33 | 90 days | EU
P002 | SUP029 | Software | 2025-01 | 3 | 1615286.68 | 45 days | US
P002 | SUP029 | Software | 2025-02 | 6 | 1521320.54 | 45 days | US
P002 | SUP029 | Logistics | 2025-03 | 6 | 635826.31 | 45 days | US
P002 | SUP029 | Mechanical | 2025-04 | 3 | 1508676.01 | 45 days | US
P002 | SUP029 | Electronics | 2025-05 | 6 | 383780.5 | 45 days | US
P002 | SUP029 | Mechanical | 2025-06 | 9 | 1449827.77 | 45 days | US
P002 | SUP029 | Mechanical | 2025-07 | 3 | 187265.44 | 45 days | US
P002 | SUP029 | Materials | 2025-08 | 2 | 1044753.94 | 45 days | US
P002 | SUP029 | Logistics | 2025-09 | 3 | 1243791.98 | 45 days | US
P002 | SUP029 | Services | 2025-10 | 6 | 1452701.66 | 45 days | US
P002 | SUP029 | Software | 2025-11 | 4 | 1576770.49 | 45 days | US
P002 | SUP029 | Electronics | 2025-12 | 2 | 1839386.24 | 45 days | US
P002 | SUP044 | Services | 2025-01 | 7 | 1309619.18 | 45 days | UK
P002 | SUP044 | Logistics | 2025-02 | 1 | 584457.82 | 45 days | UK
P002 | SUP044 | Mechanical | 2025-03 | 6 | 122424.96 | 45 days | UK
P002 | SUP044 | Logistics | 2025-04 | 5 | 713535.9 | 45 days | UK
P002 | SUP044 | Logistics | 2025-05 | 8 | 1231381.83 | 45 days | UK
P002 | SUP044 | Materials | 2025-06 | 5 | 1192175.45 | 45 days | UK
P002 | SUP044 | Mechanical | 2025-07 | 0 | 1380991.27 | 45 days | UK
P002 | SUP044 | Logistics | 2025-08 | 3 | 758214.91 | 45 days | UK
P002 | SUP044 | Electronics | 2025-09 | 7 | 809361.21 | 45 days | UK
P002 | SUP044 | Software | 2025-10 | 3 | 892106.76 | 45 days | UK
P002 | SUP044 | Services | 2025-11 | 3 | 1420103.72 | 45 days | UK
P002 | SUP044 | Software | 2025-12 | 0 | 715646.6 | 45 days | UK
P002 | SUP025 | Materials | 2025-01 | 2 | 825439.59 | 60 days | US
P002 | SUP025 | Electronics | 2025-02 | 2 | 1052323.08 | 60 days | US
P002 | SUP025 | Software | 2025-03 | 5 | 1225264.12 | 60 days | US
P002 | SUP025 | Electronics | 2025-04 | 2 | 90812.64 | 60 days | US
P002 | SUP025 | Logistics | 2025-05 | 0 | 1521204.95 | 60 days | US
P002 | SUP025 | Materials | 2025-06 | 0 | 235782.61 | 60 days | US
P002 | SUP025 | Logistics | 2025-07 | 4 | 1381935.43 | 60 days | US
P002 | SUP025 | Logistics | 2025-08 | 1 | 373061.39 | 60 days | US
P002 | SUP025 | Software | 2025-09 | 4 | 375483.48 | 60 days | US
P002 | SUP025 | Services | 2025-10 | 4 | 1169953.08 | 60 days | US
P002 | SUP025 | Electronics | 2025-11 | 2 | 531602.09 | 60 days | US
P002 | SUP025 | Logistics | 2025-12 | 6 | 300986.54 | 60 days | US
P002 | SUP042 | Logistics | 2025-01 | 0 | 144323.52 | 30 days | UK
P002 | SUP042 | Electronics | 2025-02 | 0 | 1157203.07 | 30 days | UK
P002 | SUP042 | Logistics | 2025-03 | 4 | 1038689.93 | 30 days | UK
P002 | SUP042 | Materials | 2025-04 | 3 | 156952.62 | 30 days | UK
P002 | SUP042 | Services | 2025-05 | 1 | 811166.03 | 30 days | UK
P002 | SUP042 | Services | 2025-06 | 9 | 363615.45 | 30 days | UK
P002 | SUP042 | Mechanical | 2025-07 | 7 | 414288.62 | 30 days | UK
P002 | SUP042 | Mechanical | 2025-08 | 6 | 597536.58 | 30 days | UK
P002 | SUP042 | Software | 2025-09 | 9 | 365116.91 | 30 days | UK
P002 | SUP042 | Electronics | 2025-10 | 6 | 614206.48 | 30 days | UK
P002 | SUP042 | Logistics | 2025-11 | 7 | 1163921.33 | 30 days | UK
P002 | SUP042 | Mechanical | 2025-12 | 8 | 956235.85 | 30 days | UK
P002 | SUP037 | Services | 2025-01 | 5 | 1830735.83 | 30 days | UK
P002 | SUP037 | Materials | 2025-02 | 5 | 455531.24 | 30 days | UK
P002 | SUP037 | Services | 2025-03 | 5 | 288215.98 | 30 days | UK
P002 | SUP037 | Logistics | 2025-04 | 4 | 2130327.14 | 30 days | UK
P002 | SUP037 | Software | 2025-05 | 7 | 510119.15 | 30 days | UK
P002 | SUP037 | Mechanical | 2025-06 | 3 | 190678.67 | 30 days | UK
P002 | SUP037 | Electronics | 2025-07 | 5 | 191304.12 | 30 days | UK
P002 | SUP037 | Mechanical | 2025-08 | 3 | 1358657.9 | 30 days | UK
P002 | SUP037 | Electronics | 2025-09 | 5 | 785913.5 | 30 days | UK
P002 | SUP037 | Electronics | 2025-10 | 0 | 1397032.09 | 30 days | UK
P002 | SUP037 | Logistics | 2025-11 | 3 | 655735.89 | 30 days | UK
P002 | SUP037 | Services | 2025-12 | 6 | 1058571.2 | 30 days | UK
P002 | SUP035 | Services | 2025-01 | 3 | 600212.75 | 30 days | UK
P002 | SUP035 | Mechanical | 2025-02 | 5 | 1505132.06 | 30 days | UK
P002 | SUP035 | Software | 2025-03 | 2 | 164064.28 | 30 days | UK
P002 | SUP035 | Software | 2025-04 | 8 | 1169419.81 | 30 days | UK
P002 | SUP035 | Materials | 2025-05 | 1 | 774974.05 | 30 days | UK
P002 | SUP035 | Mechanical | 2025-06 | 5 | 947505.71 | 30 days | UK
P002 | SUP035 | Electronics | 2025-07 | 4 | 1049007.51 | 30 days | UK
P002 | SUP035 | Services | 2025-08 | 4 | 196704.1 | 30 days | UK
P002 | SUP035 | Materials | 2025-09 | 5 | 326963.48 | 30 days | UK
P002 | SUP035 | Services | 2025-10 | 4 | 539278.77 | 30 days | UK
P002 | SUP035 | Services | 2025-11 | 5 | 737637.29 | 30 days | UK
P002 | SUP035 | Software | 2025-12 | 6 | 1296904.16 | 30 days | UK
P003 | SUP010 | Electronics | 2025-01 | 2 | 1342255.45 | 45 days | UK
P003 | SUP010 | Software | 2025-02 | 4 | 571241.11 | 45 days | UK
P003 | SUP010 | Materials | 2025-03 | 1 | 459584.41 | 45 days | UK
P003 | SUP010 | Software | 2025-04 | 2 | 304327.02 | 45 days | UK
P003 | SUP010 | Materials | 2025-05 | 2 | 1242734.81 | 45 days | UK
P003 | SUP010 | Services | 2025-06 | 7 | 680163.42 | 45 days | UK
P003 | SUP010 | Electronics | 2025-07 | 5 | 220128.47 | 45 days | UK
P003 | SUP010 | Logistics | 2025-08 | 4 | 148625.92 | 45 days | UK
P003 | SUP010 | Software | 2025-09 | 0 | 1253812.96 | 45 days | UK
P003 | SUP010 | Logistics | 2025-10 | 4 | 1019061.59 | 45 days | UK
P003 | SUP010 | Electronics | 2025-11 | 5 | 411995.78 | 45 days | UK
P003 | SUP010 | Logistics | 2025-12 | 2 | 217467.11 | 45 days | UK
P003 | SUP039 | Materials | 2025-01 | 3 | 712112.13 | 90 days | UK
P003 | SUP039 | Logistics | 2025-02 | 1 | 352965.07 | 90 days | UK
P003 | SUP039 | Materials | 2025-03 | 3 | 459190.34 | 90 days | UK
P003 | SUP039 | Services | 2025-04 | 5 | 1106843.23 | 90 days | UK
P003 | SUP039 | Logistics | 2025-05 | 0 | 1153544.2 | 90 days | UK
P003 | SUP039 | Electronics | 2025-06 | 3 | 704716.52 | 90 days | UK
P003 | SUP039 | Software | 2025-07 | 2 | 476982.96 | 90 days | UK
P003 | SUP039 | Services | 2025-08 | 2 | 457311.12 | 90 days | UK
P003 | SUP039 | Logistics | 2025-09 | 4 | 262417.03 | 90 days | UK
P003 | SUP039 | Software | 2025-10 | 2 | 381992.56 | 90 days | UK
P003 | SUP039 | Logistics | 2025-11 | 5 | 366484.89 | 90 days | UK
P003 | SUP039 | Electronics | 2025-12 | 5 | 485958.82 | 90 days | UK
P003 | SUP036 | Logistics | 2025-01 | 4 | 599978.67 | 60 days | APAC
P003 | SUP036 | Electronics | 2025-02 | 3 | 460873.51 | 60 days | APAC
P003 | SUP036 | Logistics | 2025-03 | 3 | 696521.19 | 60 days | APAC
P003 | SUP036 | Services | 2025-04 | 1 | 232669.4 | 60 days | APAC
P003 | SUP036 | Logistics | 2025-05 | 2 | 1193598.85 | 60 days | APAC
P003 | SUP036 | Logistics | 2025-06 | 2 | 435126.19 | 60 days | APAC
P003 | SUP036 | Services | 2025-07 | 6 | 111921.35 | 60 days | APAC
P003 | SUP036 | Software | 2025-08 | 1 | 688655.84 | 60 days | APAC
P003 | SUP036 | Electronics | 2025-09 | 6 | 469805.63 | 60 days | APAC
P003 | SUP036 | Mechanical | 2025-10 | 5 | 160142.66 | 60 days | APAC
P003 | SUP036 | Electronics | 2025-11 | 3 | 802001.78 | 60 days | APAC
P003 | SUP036 | Mechanical | 2025-12 | 3 | 1301736.74 | 60 days | APAC
P003 | SUP031 | Logistics | 2025-01 | 6 | 1525999.02 | 60 days | US
P003 | SUP031 | Software | 2025-02 | 3 | 188084.32 | 60 days | US
P003 | SUP031 | Mechanical | 2025-03 | 2 | 641091.91 | 60 days | US
P003 | SUP031 | Materials | 2025-04 | 8 | 1362300 | 60 days | US
P003 | SUP031 | Materials | 2025-05 | 7 | 1753068.45 | 60 days | US
P003 | SUP031 | Materials | 2025-06 | 6 | 245272.84 | 60 days | US
P003 | SUP031 | Logistics | 2025-07 | 2 | 330374.51 | 60 days | US
P003 | SUP031 | Logistics | 2025-08 | 4 | 448895.06 | 60 days | US
P003 | SUP031 | Materials | 2025-09 | 6 | 1194869.4 | 60 days | US
P003 | SUP031 | Materials | 2025-10 | 5 | 409960.69 | 60 days | US
P003 | SUP031 | Electronics | 2025-11 | 1 | 383128.6 | 60 days | US
P003 | SUP031 | Mechanical | 2025-12 | 6 | 1753103.51 | 60 days | US
P003 | SUP013 | Electronics | 2025-01 | 3 | 1231083.19 | 60 days | UK
P003 | SUP013 | Electronics | 2025-02 | 4 | 718871.19 | 60 days | UK
P003 | SUP013 | Electronics | 2025-03 | 6 | 114770.57 | 60 days | UK
P003 | SUP013 | Materials | 2025-04 | 9 | 1113372.48 | 60 days | UK
P003 | SUP013 | Materials | 2025-05 | 2 | 1240551.67 | 60 days | UK
P003 | SUP013 | Materials | 2025-06 | 2 | 461126.58 | 60 days | UK
P003 | SUP013 | Software | 2025-07 | 0 | 1415866.21 | 60 days | UK
P003 | SUP013 | Electronics | 2025-08 | 2 | 1029243.92 | 60 days | UK
P003 | SUP013 | Electronics | 2025-09 | 7 | 494589.24 | 60 days | UK
P003 | SUP013 | Electronics | 2025-10 | 3 | 770746.85 | 60 days | UK
P003 | SUP013 | Software | 2025-11 | 0 | 267818.47 | 60 days | UK
P003 | SUP013 | Mechanical | 2025-12 | 0 | 820624.52 | 60 days | UK
P003 | SUP045 | Software | 2025-01 | 0 | 1031466.07 | 30 days | US
P003 | SUP045 | Logistics | 2025-02 | 5 | 993215.27 | 30 days | US
P003 | SUP045 | Electronics | 2025-03 | 5 | 1000663.96 | 30 days | US
P003 | SUP045 | Logistics | 2025-04 | 8 | 126904.73 | 30 days | US
P003 | SUP045 | Electronics | 2025-05 | 2 | 723117.98 | 30 days | US
P003 | SUP045 | Logistics | 2025-06 | 3 | 1330866.38 | 30 days | US
P003 | SUP045 | Services | 2025-07 | 7 | 927699.62 | 30 days | US
P003 | SUP045 | Logistics | 2025-08 | 5 | 1276276.12 | 30 days | US
P003 | SUP045 | Materials | 2025-09 | 8 | 1380461.47 | 30 days | US
P003 | SUP045 | Electronics | 2025-10 | 8 | 1178592.9 | 30 days | US
P003 | SUP045 | Software | 2025-11 | 2 | 931000.42 | 30 days | US
P003 | SUP045 | Logistics | 2025-12 | 5 | 1409214.43 | 30 days | US
P003 | SUP034 | Electronics | 2025-01 | 4 | 1112675.61 | 60 days | US
P003 | SUP034 | Electronics | 2025-02 | 7 | 1053911.47 | 60 days | US
P003 | SUP034 | Logistics | 2025-03 | 4 | 2597244.91 | 60 days | US
P003 | SUP034 | Services | 2025-04 | 5 | 246352.25 | 60 days | US
P003 | SUP034 | Electronics | 2025-05 | 5 | 401513.68 | 60 days | US
P003 | SUP034 | Materials | 2025-06 | 3 | 541270.7 | 60 days | US
P003 | SUP034 | Logistics | 2025-07 | 3 | 2117139.15 | 60 days | US
P003 | SUP034 | Materials | 2025-08 | 6 | 1120859.8 | 60 days | US
P003 | SUP034 | Software | 2025-09 | 6 | 830848.6 | 60 days | US
P003 | SUP034 | Logistics | 2025-10 | 6 | 668108.83 | 60 days | US
P003 | SUP034 | Software | 2025-11 | 3 | 255319.53 | 60 days | US
P003 | SUP034 | Mechanical | 2025-12 | 4 | 409097.78 | 60 days | US
P003 | SUP044 | Services | 2025-01 | 4 | 121379.12 | 45 days | UK
P003 | SUP044 | Logistics | 2025-02 | 2 | 864703.1 | 45 days | UK
P003 | SUP044 | Materials | 2025-03 | 3 | 190946.53 | 45 days | UK
P003 | SUP044 | Mechanical | 2025-04 | 2 | 1097079.24 | 45 days | UK
P003 | SUP044 | Materials | 2025-05 | 0 | 711621.14 | 45 days | UK
P003 | SUP044 | Electronics | 2025-06 | 6 | 1378151.3 | 45 days | UK
P003 | SUP044 | Services | 2025-07 | 7 | 388820.47 | 45 days | UK
P003 | SUP044 | Materials | 2025-08 | 6 | 1821125.24 | 45 days | UK
P003 | SUP044 | Software | 2025-09 | 6 | 459379.85 | 45 days | UK
P003 | SUP044 | Software | 2025-10 | 5 | 928000.13 | 45 days | UK
P003 | SUP044 | Mechanical | 2025-11 | 3 | 700966.34 | 45 days | UK
P003 | SUP044 | Electronics | 2025-12 | 4 | 497362.64 | 45 days | UK
P003 | SUP050 | Services | 2025-01 | 1 | 392015.91 | 30 days | APAC
P003 | SUP050 | Logistics | 2025-02 | 2 | 512850.9 | 30 days | APAC
P003 | SUP050 | Services | 2025-03 | 6 | 565663.72 | 30 days | APAC
P003 | SUP050 | Electronics | 2025-04 | 3 | 97068.24 | 30 days | APAC
P003 | SUP050 | Materials | 2025-05 | 3 | 92905.3 | 30 days | APAC
P003 | SUP050 | Materials | 2025-06 | 1 | 225561.61 | 30 days | APAC
P003 | SUP050 | Software | 2025-07 | 3 | 1141990.75 | 30 days | APAC
P003 | SUP050 | Logistics | 2025-08 | 3 | 1053347.13 | 30 days | APAC
P003 | SUP050 | Services | 2025-09 | 3 | 1115387.46 | 30 days | APAC
P003 | SUP050 | Services | 2025-10 | 4 | 548449.35 | 30 days | APAC
P003 | SUP050 | Materials | 2025-11 | 0 | 532257.16 | 30 days | APAC
P003 | SUP050 | Materials | 2025-12 | 4 | 265347.05 | 30 days | APAC
P003 | SUP007 | Mechanical | 2025-01 | 0 | 826099.45 | 45 days | APAC
P003 | SUP007 | Electronics | 2025-02 | 6 | 469601.87 | 45 days | APAC
P003 | SUP007 | Mechanical | 2025-03 | 2 | 479962.43 | 45 days | APAC
P003 | SUP007 | Software | 2025-04 | 7 | 466380.22 | 45 days | APAC
P003 | SUP007 | Logistics | 2025-05 | 4 | 1021340.48 | 45 days | APAC
P003 | SUP007 | Logistics | 2025-06 | 2 | 652422.47 | 45 days | APAC
P003 | SUP007 | Services | 2025-07 | 4 | 1349227.18 | 45 days | APAC
P003 | SUP007 | Electronics | 2025-08 | 3 | 124385.97 | 45 days | APAC
P003 | SUP007 | Services | 2025-09 | 6 | 1305352.45 | 45 days | APAC
P003 | SUP007 | Logistics | 2025-10 | 5 | 1046302.89 | 45 days | APAC
P003 | SUP007 | Mechanical | 2025-11 | 6 | 622537.12 | 45 days | APAC
P003 | SUP007 | Logistics | 2025-12 | 5 | 1066838.92 | 45 days | APAC
P003 | SUP037 | Services | 2025-01 | 4 | 223434.91 | 30 days | UK
P003 | SUP037 | Materials | 2025-02 | 5 | 1022900.8 | 30 days | UK
P003 | SUP037 | Services | 2025-03 | 3 | 256765.17 | 30 days | UK
P003 | SUP037 | Materials | 2025-04 | 7 | 777697.49 | 30 days | UK
P003 | SUP037 | Services | 2025-05 | 6 | 1784919.96 | 30 days | UK
P003 | SUP037 | Logistics | 2025-06 | 6 | 1273641.07 | 30 days | UK
P003 | SUP037 | Services | 2025-07 | 0 | 1192966.62 | 30 days | UK
P003 | SUP037 | Logistics | 2025-08 | 2 | 653103.03 | 30 days | UK
P003 | SUP037 | Materials | 2025-09 | 5 | 666623.32 | 30 days | UK
P003 | SUP037 | Electronics | 2025-10 | 3 | 1224098.2 | 30 days | UK
P003 | SUP037 | Services | 2025-11 | 2 | 327070.66 | 30 days | UK
P003 | SUP037 | Mechanical | 2025-12 | 11 | 592968.81 | 30 days | UK
P003 | SUP025 | Logistics | 2025-01 | 3 | 994383.05 | 60 days | US
P003 | SUP025 | Logistics | 2025-02 | 6 | 685620.67 | 60 days | US
P003 | SUP025 | Materials | 2025-03 | 6 | 129096.72 | 60 days | US
P003 | SUP025 | Software | 2025-04 | 3 | 572036.46 | 60 days | US
P003 | SUP025 | Logistics | 2025-05 | 1 | 131974.97 | 60 days | US
P003 | SUP025 | Logistics | 2025-06 | 6 | 778929.49 | 60 days | US
P003 | SUP025 | Logistics | 2025-07 | 4 | 213395.58 | 60 days | US
P003 | SUP025 | Materials | 2025-08 | 7 | 233369.83 | 60 days | US
P003 | SUP025 | Logistics | 2025-09 | 2 | 589246.41 | 60 days | US
P003 | SUP025 | Logistics | 2025-10 | 2 | 1262727.96 | 60 days | US
P003 | SUP025 | Electronics | 2025-11 | 3 | 465329.07 | 60 days | US
P003 | SUP025 | Services | 2025-12 | 3 | 291802.9 | 60 days | US
P003 | SUP043 | Logistics | 2025-01 | 0 | 1321569.54 | 60 days | EU
P003 | SUP043 | Logistics | 2025-02 | 5 | 513843.87 | 60 days | EU
P003 | SUP043 | Logistics | 2025-03 | 2 | 915586.94 | 60 days | EU
P003 | SUP043 | Mechanical | 2025-04 | 3 | 600215.2 | 60 days | EU
P003 | SUP043 | Services | 2025-05 | 5 | 298120.99 | 60 days | EU
P003 | SUP043 | Services | 2025-06 | 2 | 145968.18 | 60 days | EU
P003 | SUP043 | Electronics | 2025-07 | 5 | 1320658.87 | 60 days | EU
P003 | SUP043 | Logistics | 2025-08 | 2 | 1141487.11 | 60 days | EU
P003 | SUP043 | Software | 2025-09 | 4 | 154490.2 | 60 days | EU
P003 | SUP043 | Electronics | 2025-10 | 3 | 400527.66 | 60 days | EU
P003 | SUP043 | Mechanical | 2025-11 | 3 | 929512.6 | 60 days | EU
P003 | SUP043 | Services | 2025-12 | 5 | 1060413.99 | 60 days | EU
P003 | SUP032 | Services | 2025-01 | 2 | 242727.24 | 90 days | APAC
P003 | SUP032 | Services | 2025-02 | 8 | 217851.35 | 90 days | APAC
P003 | SUP032 | Services | 2025-03 | 3 | 131157.9 | 90 days | APAC
P003 | SUP032 | Logistics | 2025-04 | 2 | 174896.42 | 90 days | APAC
P003 | SUP032 | Mechanical | 2025-05 | 0 | 199760.71 | 90 days | APAC
P003 | SUP032 | Logistics | 2025-06 | 3 | 243735.66 | 90 days | APAC
P003 | SUP032 | Software | 2025-07 | 0 | 318718.21 | 90 days | APAC
P003 | SUP032 | Mechanical | 2025-08 | 0 | 331141.77 | 90 days | APAC
P003 | SUP032 | Mechanical | 2025-09 | 4 | 1073410.81 | 90 days | APAC
P003 | SUP032 | Mechanical | 2025-10 | 4 | 93723.99 | 90 days | APAC
P003 | SUP032 | Services | 2025-11 | 2 | 597071.62 | 90 days | APAC
P003 | SUP032 | Materials | 2025-12 | 4 | 835743.73 | 90 days | APAC
P003 | SUP002 | Services | 2025-01 | 6 | 1134000.71 | 90 days | EU
P003 | SUP002 | Logistics | 2025-02 | 6 | 876301.4 | 90 days | EU
P003 | SUP002 | Mechanical | 2025-03 | 7 | 812680.95 | 90 days | EU
P003 | SUP002 | Electronics | 2025-04 | 2 | 1487755.55 | 90 days | EU
P003 | SUP002 | Logistics | 2025-05 | 1 | 1314205.65 | 90 days | EU
P003 | SUP002 | Software | 2025-06 | 4 | 1948838.04 | 90 days | EU
P003 | SUP002 | Logistics | 2025-07 | 4 | 1104372.13 | 90 days | EU
P003 | SUP002 | Software | 2025-08 | 4 | 1232015.76 | 90 days | EU
P003 | SUP002 | Logistics | 2025-09 | 5 | 163456.91 | 90 days | EU
P003 | SUP002 | Logistics | 2025-10 | 4 | 304318.68 | 90 days | EU
P003 | SUP002 | Materials | 2025-11 | 4 | 723980.39 | 90 days | EU
P003 | SUP002 | Software | 2025-12 | 3 | 1440912.34 | 90 days | EU
P003 | SUP021 | Logistics | 2025-01 | 2 | 968652.66 | 60 days | US
P003 | SUP021 | Mechanical | 2025-02 | 0 | 1239771.69 | 60 days | US
P003 | SUP021 | Logistics | 2025-03 | 1 | 107603.92 | 60 days | US
P003 | SUP021 | Electronics | 2025-04 | 5 | 321525.65 | 60 days | US
P003 | SUP021 | Software | 2025-05 | 3 | 66501.82 | 60 days | US
P003 | SUP021 | Services | 2025-06 | 5 | 1076782.92 | 60 days | US
P003 | SUP021 | Materials | 2025-07 | 4 | 873808.37 | 60 days | US
P003 | SUP021 | Services | 2025-08 | 4 | 201482.48 | 60 days | US
P003 | SUP021 | Materials | 2025-09 | 5 | 708832.12 | 60 days | US
P003 | SUP021 | Materials | 2025-10 | 4 | 155046.67 | 60 days | US
P003 | SUP021 | Materials | 2025-11 | 0 | 1279747.98 | 60 days | US
P003 | SUP021 | Materials | 2025-12 | 2 | 1110031.28 | 60 days | US
P003 | SUP014 | Mechanical | 2025-01 | 3 | 636391.55 | 90 days | APAC
P003 | SUP014 | Materials | 2025-02 | 0 | 988357.36 | 90 days | APAC
P003 | SUP014 | Materials | 2025-03 | 1 | 52030.44 | 90 days | APAC
P003 | SUP014 | Software | 2025-04 | 7 | 120116.32 | 90 days | APAC
P003 | SUP014 | Logistics | 2025-05 | 0 | 303512.65 | 90 days | APAC
P003 | SUP014 | Materials | 2025-06 | 5 | 472329.71 | 90 days | APAC
P003 | SUP014 | Services | 2025-07 | 3 | 436978.88 | 90 days | APAC
P003 | SUP014 | Software | 2025-08 | 0 | 366887.33 | 90 days | APAC
P003 | SUP014 | Materials | 2025-09 | 6 | 409693.65 | 90 days | APAC
P003 | SUP014 | Mechanical | 2025-10 | 0 | 248310.16 | 90 days | APAC
P003 | SUP014 | Services | 2025-11 | 8 | 754198.93 | 90 days | APAC
P003 | SUP014 | Materials | 2025-12 | 1 | 108653.82 | 90 days | APAC
P003 | SUP003 | Logistics | 2025-01 | 0 | 1192830.98 | 60 days | APAC
P003 | SUP003 | Services | 2025-02 | 3 | 1009330.62 | 60 days | APAC
P003 | SUP003 | Mechanical | 2025-03 | 1 | 472455.38 | 60 days | APAC
P003 | SUP003 | Electronics | 2025-04 | 2 | 633545.91 | 60 days | APAC
P003 | SUP003 | Materials | 2025-05 | 2 | 193541.35 | 60 days | APAC
P003 | SUP003 | Services | 2025-06 | 4 | 699001.68 | 60 days | APAC
P003 | SUP003 | Logistics | 2025-07 | 0 | 980361.49 | 60 days | APAC
P003 | SUP003 | Materials | 2025-08 | 4 | 330682.92 | 60 days | APAC
P003 | SUP003 | Materials | 2025-09 | 1 | 141612.11 | 60 days | APAC
P003 | SUP003 | Services | 2025-10 | 0 | 62639.71 | 60 days | APAC
P003 | SUP003 | Electronics | 2025-11 | 0 | 997322.21 | 60 days | APAC
P003 | SUP003 | Software | 2025-12 | 2 | 282362.68 | 60 days | APAC
P003 | SUP022 | Logistics | 2025-01 | 2 | 674028.52 | 45 days | UK
P003 | SUP022 | Logistics | 2025-02 | 2 | 629811.45 | 45 days | UK
P003 | SUP022 | Software | 2025-03 | 3 | 1236475.11 | 45 days | UK
P003 | SUP022 | Materials | 2025-04 | 0 | 491335.51 | 45 days | UK
P003 | SUP022 | Services | 2025-05 | 0 | 590208.22 | 45 days | UK
P003 | SUP022 | Logistics | 2025-06 | 4 | 93583.51 | 45 days | UK
P003 | SUP022 | Software | 2025-07 | 1 | 1740790.85 | 45 days | UK
P003 | SUP022 | Software | 2025-08 | 4 | 987031.27 | 45 days | UK
P003 | SUP022 | Services | 2025-09 | 3 | 777330.83 | 45 days | UK
P003 | SUP022 | Mechanical | 2025-10 | 3 | 407214.44 | 45 days | UK
P003 | SUP022 | Software | 2025-11 | 1 | 316772.2 | 45 days | UK
P003 | SUP022 | Mechanical | 2025-12 | 5 | 146205.73 | 45 days | UK
P003 | SUP018 | Mechanical | 2025-01 | 2 | 126019.18 | 30 days | APAC
P003 | SUP018 | Software | 2025-02 | 2 | 128572.12 | 30 days | APAC
P003 | SUP018 | Materials | 2025-03 | 0 | 873974.62 | 30 days | APAC
P003 | SUP018 | Software | 2025-04 | 1 | 479382.24 | 30 days | APAC
P003 | SUP018 | Materials | 2025-05 | 3 | 630955.5 | 30 days | APAC
P003 | SUP018 | Software | 2025-06 | 6 | 1587834.14 | 30 days | APAC
P003 | SUP018 | Services | 2025-07 | 0 | 367255.25 | 30 days | APAC
P003 | SUP018 | Software | 2025-08 | 1 | 1473443.25 | 30 days | APAC
P003 | SUP018 | Software | 2025-09 | 0 | 289664.95 | 30 days | APAC
P003 | SUP018 | Logistics | 2025-10 | 7 | 1445015.05 | 30 days | APAC
P003 | SUP018 | Services | 2025-11 | 6 | 1062252.56 | 30 days | APAC
P003 | SUP018 | Services | 2025-12 | 8 | 463621.49 | 30 days | APAC
P003 | SUP033 | Electronics | 2025-01 | 4 | 656516.09 | 60 days | UK
P003 | SUP033 | Services | 2025-02 | 4 | 878771.8 | 60 days | UK
P003 | SUP033 | Logistics | 2025-03 | 4 | 1010185.97 | 60 days | UK
P003 | SUP033 | Electronics | 2025-04 | 3 | 1175361.11 | 60 days | UK
P003 | SUP033 | Electronics | 2025-05 | 4 | 1126653.76 | 60 days | UK
P003 | SUP033 | Electronics | 2025-06 | 2 | 181715.38 | 60 days | UK
P003 | SUP033 | Logistics | 2025-07 | 1 | 946303.36 | 60 days | UK
P003 | SUP033 | Software | 2025-08 | 8 | 421410.31 | 60 days | UK
P003 | SUP033 | Software | 2025-09 | 7 | 146224.08 | 60 days | UK
P003 | SUP033 | Materials | 2025-10 | 8 | 327591.95 | 60 days | UK
P003 | SUP033 | Mechanical | 2025-11 | 5 | 1215364.36 | 60 days | UK
P003 | SUP033 | Materials | 2025-12 | 1 | 449048.74 | 60 days | UK
P003 | SUP042 | Mechanical | 2025-01 | 5 | 972398.69 | 30 days | UK
P003 | SUP042 | Mechanical | 2025-02 | 5 | 360908 | 30 days | UK
P003 | SUP042 | Logistics | 2025-03 | 0 | 638924.83 | 30 days | UK
P003 | SUP042 | Mechanical | 2025-04 | 6 | 1393127.46 | 30 days | UK
P003 | SUP042 | Services | 2025-05 | 5 | 867491.74 | 30 days | UK
P003 | SUP042 | Software | 2025-06 | 6 | 233771.24 | 30 days | UK
P003 | SUP042 | Logistics | 2025-07 | 3 | 959841.09 | 30 days | UK
P003 | SUP042 | Logistics | 2025-08 | 6 | 599950.84 | 30 days | UK
P003 | SUP042 | Materials | 2025-09 | 6 | 511981.55 | 30 days | UK
P003 | SUP042 | Logistics | 2025-10 | 2 | 607024.94 | 30 days | UK
P003 | SUP042 | Logistics | 2025-11 | 5 | 953367.79 | 30 days | UK
P003 | SUP042 | Electronics | 2025-12 | 6 | 345894.6 | 30 days | UK
P003 | SUP012 | Mechanical | 2025-01 | 7 | 213441.52 | 90 days | US
P003 | SUP012 | Mechanical | 2025-02 | 3 | 1401127.48 | 90 days | US
P003 | SUP012 | Services | 2025-03 | 3 | 968937.08 | 90 days | US
P003 | SUP012 | Materials | 2025-04 | 5 | 371287.77 | 90 days | US
P003 | SUP012 | Electronics | 2025-05 | 1 | 364146.88 | 90 days | US
P003 | SUP012 | Logistics | 2025-06 | 5 | 979273.34 | 90 days | US
P003 | SUP012 | Services | 2025-07 | 1 | 1815669.17 | 90 days | US
P003 | SUP012 | Services | 2025-08 | 5 | 205274.31 | 90 days | US
P003 | SUP012 | Services | 2025-09 | 5 | 1394730.24 | 90 days | US
P003 | SUP012 | Services | 2025-10 | 2 | 877666.55 | 90 days | US
P003 | SUP012 | Services | 2025-11 | 4 | 370906.98 | 90 days | US
P003 | SUP012 | Services | 2025-12 | 3 | 368581.53 | 90 days | US
P003 | SUP020 | Electronics | 2025-01 | 3 | 569658.06 | 60 days | UK
P003 | SUP020 | Mechanical | 2025-02 | 0 | 758575.56 | 60 days | UK
P003 | SUP020 | Logistics | 2025-03 | 3 | 1755177.42 | 60 days | UK
P003 | SUP020 | Materials | 2025-04 | 2 | 78682.44 | 60 days | UK
P003 | SUP020 | Logistics | 2025-05 | 2 | 68007.26 | 60 days | UK
P003 | SUP020 | Software | 2025-06 | 0 | 1468254.76 | 60 days | UK
P003 | SUP020 | Mechanical | 2025-07 | 4 | 140289.44 | 60 days | UK
P003 | SUP020 | Logistics | 2025-08 | 5 | 1197436.87 | 60 days | UK
P003 | SUP020 | Logistics | 2025-09 | 3 | 793307.39 | 60 days | UK
P003 | SUP020 | Electronics | 2025-10 | 2 | 839970.56 | 60 days | UK
P003 | SUP020 | Mechanical | 2025-11 | 3 | 544617.08 | 60 days | UK
P003 | SUP020 | Software | 2025-12 | 1 | 53558.79 | 60 days | UK
P003 | SUP017 | Materials | 2025-01 | 3 | 825375.34 | 90 days | EU
P003 | SUP017 | Materials | 2025-02 | 1 | 328803.72 | 90 days | EU
P003 | SUP017 | Logistics | 2025-03 | 3 | 626040.16 | 90 days | EU
P003 | SUP017 | Software | 2025-04 | 6 | 897984.81 | 90 days | EU
P003 | SUP017 | Materials | 2025-05 | 4 | 522344.73 | 90 days | EU
P003 | SUP017 | Mechanical | 2025-06 | 1 | 373546.53 | 90 days | EU
P003 | SUP017 | Mechanical | 2025-07 | 3 | 1001547.84 | 90 days | EU
P003 | SUP017 | Services | 2025-08 | 3 | 322322.21 | 90 days | EU
P003 | SUP017 | Software | 2025-09 | 3 | 742745.08 | 90 days | EU
P003 | SUP017 | Software | 2025-10 | 4 | 1060945.08 | 90 days | EU
P003 | SUP017 | Mechanical | 2025-11 | 6 | 75169.97 | 90 days | EU
P003 | SUP017 | Materials | 2025-12 | 1 | 1360082.19 | 90 days | EU
P003 | SUP006 | Materials | 2025-01 | 1 | 197144.05 | 60 days | APAC
P003 | SUP006 | Logistics | 2025-02 | 2 | 856710.68 | 60 days | APAC
P003 | SUP006 | Electronics | 2025-03 | 2 | 1181634.67 | 60 days | APAC
P003 | SUP006 | Software | 2025-04 | 4 | 1029989.66 | 60 days | APAC
P003 | SUP006 | Services | 2025-05 | 4 | 881804.94 | 60 days | APAC
P003 | SUP006 | Electronics | 2025-06 | 5 | 1166570.68 | 60 days | APAC
P003 | SUP006 | Logistics | 2025-07 | 6 | 378655.95 | 60 days | APAC
P003 | SUP006 | Mechanical | 2025-08 | 1 | 798888.03 | 60 days | APAC
P003 | SUP006 | Electronics | 2025-09 | 2 | 813266.38 | 60 days | APAC
P003 | SUP006 | Services | 2025-10 | 3 | 582277.97 | 60 days | APAC
P003 | SUP006 | Mechanical | 2025-11 | 2 | 851561.9 | 60 days | APAC
P003 | SUP006 | Materials | 2025-12 | 5 | 420716.4 | 60 days | APAC
P003 | SUP001 | Mechanical | 2025-01 | 6 | 1024011.86 | 90 days | EU
P003 | SUP001 | Electronics | 2025-02 | 8 | 367910.35 | 90 days | EU
P003 | SUP001 | Software | 2025-03 | 7 | 520522.36 | 90 days | EU
P003 | SUP001 | Services | 2025-04 | 4 | 1262824.31 | 90 days | EU
P003 | SUP001 | Services | 2025-05 | 7 | 498939.93 | 90 days | EU
P003 | SUP001 | Materials | 2025-06 | 6 | 67869.05 | 90 days | EU
P003 | SUP001 | Materials | 2025-07 | 6 | 460638.32 | 90 days | EU
P003 | SUP001 | Software | 2025-08 | 7 | 1106158.65 | 90 days | EU
P003 | SUP001 | Software | 2025-09 | 6 | 184020 | 90 days | EU
P003 | SUP001 | Software | 2025-10 | 0 | 1250691.2 | 90 days | EU
P003 | SUP001 | Logistics | 2025-11 | 4 | 776738.5 | 90 days | EU
P003 | SUP001 | Logistics | 2025-12 | 6 | 840726.46 | 90 days | EU
P003 | SUP040 | Services | 2025-01 | 2 | 293940.93 | 45 days | APAC
P003 | SUP040 | Software | 2025-02 | 2 | 746534.39 | 45 days | APAC
P003 | SUP040 | Materials | 2025-03 | 1 | 552248.39 | 45 days | APAC
P003 | SUP040 | Services | 2025-04 | 5 | 1078932.73 | 45 days | APAC
P003 | SUP040 | Software | 2025-05 | 2 | 1214285.79 | 45 days | APAC
P003 | SUP040 | Materials | 2025-06 | 4 | 759488.7 | 45 days | APAC
P003 | SUP040 | Software | 2025-07 | 8 | 99967.43 | 45 days | APAC
P003 | SUP040 | Software | 2025-08 | 8 | 146491.38 | 45 days | APAC
P003 | SUP040 | Software | 2025-09 | 3 | 776881.66 | 45 days | APAC
P003 | SUP040 | Logistics | 2025-10 | 6 | 89008.93 | 45 days | APAC
P003 | SUP040 | Services | 2025-11 | 4 | 440147.41 | 45 days | APAC
P003 | SUP040 | Software | 2025-12 | 2 | 771525.21 | 45 days | APAC
P004 | SUP013 | Software | 2025-01 | 4 | 1317717.67 | 60 days | UK
P004 | SUP013 | Electronics | 2025-02 | 4 | 441677.79 | 60 days | UK
P004 | SUP013 | Mechanical | 2025-03 | 3 | 102671.84 | 60 days | UK
P004 | SUP013 | Mechanical | 2025-04 | 4 | 753330.91 | 60 days | UK
P004 | SUP013 | Logistics | 2025-05 | 0 | 518156.84 | 60 days | UK
P004 | SUP013 | Mechanical | 2025-06 | 4 | 175774.56 | 60 days | UK
P004 | SUP013 | Software | 2025-07 | 2 | 1057369.87 | 60 days | UK
P004 | SUP013 | Logistics | 2025-08 | 0 | 323013.35 | 60 days | UK
P004 | SUP013 | Services | 2025-09 | 3 | 1241830.45 | 60 days | UK
P004 | SUP013 | Logistics | 2025-10 | 3 | 339213.04 | 60 days | UK
P004 | SUP013 | Electronics | 2025-11 | 1 | 606231.08 | 60 days | UK
P004 | SUP013 | Mechanical | 2025-12 | 4 | 629000.2 | 60 days | UK
P004 | SUP002 | Software | 2025-01 | 2 | 196997.03 | 90 days | EU
P004 | SUP002 | Electronics | 2025-02 | 8 | 1405359.07 | 90 days | EU
P004 | SUP002 | Mechanical | 2025-03 | 3 | 388127.63 | 90 days | EU
P004 | SUP002 | Logistics | 2025-04 | 2 | 976975.84 | 90 days | EU
P004 | SUP002 | Mechanical | 2025-05 | 8 | 2007736.67 | 90 days | EU
P004 | SUP002 | Electronics | 2025-06 | 1 | 1064090.03 | 90 days | EU
P004 | SUP002 | Electronics | 2025-07 | 4 | 650451.25 | 90 days | EU
P004 | SUP002 | Mechanical | 2025-08 | 3 | 797805.84 | 90 days | EU
P004 | SUP002 | Software | 2025-09 | 3 | 656015.1 | 90 days | EU
P004 | SUP002 | Services | 2025-10 | 2 | 1951261.71 | 90 days | EU
P004 | SUP002 | Services | 2025-11 | 5 | 65479.65 | 90 days | EU
P004 | SUP002 | Software | 2025-12 | 8 | 318970.4 | 90 days | EU
P004 | SUP022 | Electronics | 2025-01 | 8 | 273910.2 | 45 days | UK
P004 | SUP022 | Logistics | 2025-02 | 0 | 699205.97 | 45 days | UK
P004 | SUP022 | Services | 2025-03 | 5 | 803867.92 | 45 days | UK
P004 | SUP022 | Services | 2025-04 | 5 | 187983.33 | 45 days | UK
P004 | SUP022 | Electronics | 2025-05 | 1 | 922512.44 | 45 days | UK
P004 | SUP022 | Software | 2025-06 | 1 | 609336.69 | 45 days | UK
P004 | SUP022 | Mechanical | 2025-07 | 2 | 302611.54 | 45 days | UK
P004 | SUP022 | Materials | 2025-08 | 5 | 495342.93 | 45 days | UK
P004 | SUP022 | Electronics | 2025-09 | 4 | 849472.87 | 45 days | UK
P004 | SUP022 | Mechanical | 2025-10 | 1 | 307383.64 | 45 days | UK
P004 | SUP022 | Services | 2025-11 | 4 | 275066.34 | 45 days | UK
P004 | SUP022 | Electronics | 2025-12 | 4 | 287296.29 | 45 days | UK
P004 | SUP009 | Mechanical | 2025-01 | 8 | 153893.38 | 30 days | US
P004 | SUP009 | Logistics | 2025-02 | 4 | 937553.16 | 30 days | US
P004 | SUP009 | Materials | 2025-03 | 5 | 631506.43 | 30 days | US
P004 | SUP009 | Logistics | 2025-04 | 3 | 666313.54 | 30 days | US
P004 | SUP009 | Services | 2025-05 | 3 | 97539.33 | 30 days | US
P004 | SUP009 | Software | 2025-06 | 7 | 1010424.91 | 30 days | US
P004 | SUP009 | Logistics | 2025-07 | 1 | 444201.78 | 30 days | US
P004 | SUP009 | Logistics | 2025-08 | 1 | 380995.8 | 30 days | US
P004 | SUP009 | Mechanical | 2025-09 | 5 | 999128.91 | 30 days | US
P004 | SUP009 | Electronics | 2025-10 | 2 | 824475.54 | 30 days | US
P004 | SUP009 | Software | 2025-11 | 1 | 879895.48 | 30 days | US
P004 | SUP009 | Services | 2025-12 | 6 | 1003407.86 | 30 days | US
P004 | SUP003 | Software | 2025-01 | 3 | 345917.4 | 60 days | APAC
P004 | SUP003 | Logistics | 2025-02 | 3 | 377775.42 | 60 days | APAC
P004 | SUP003 | Mechanical | 2025-03 | 6 | 277590.32 | 60 days | APAC
P004 | SUP003 | Electronics | 2025-04 | 1 | 874830.14 | 60 days | APAC
P004 | SUP003 | Electronics | 2025-05 | 2 | 267329.26 | 60 days | APAC
P004 | SUP003 | Electronics | 2025-06 | 7 | 982603.96 | 60 days | APAC
P004 | SUP003 | Mechanical | 2025-07 | 2 | 250854.65 | 60 days | APAC
P004 | SUP003 | Services | 2025-08 | 0 | 599390.23 | 60 days | APAC
P004 | SUP003 | Services | 2025-09 | 2 | 717753.41 | 60 days | APAC
P004 | SUP003 | Software | 2025-10 | 0 | 237006.42 | 60 days | APAC
P004 | SUP003 | Electronics | 2025-11 | 0 | 338961.75 | 60 days | APAC
P004 | SUP003 | Services | 2025-12 | 0 | 572016.79 | 60 days | APAC
P004 | SUP039 | Software | 2025-01 | 4 | 1387058.71 | 90 days | UK
P004 | SUP039 | Electronics | 2025-02 | 6 | 601343.46 | 90 days | UK
P004 | SUP039 | Software | 2025-03 | 4 | 1276308.06 | 90 days | UK
P004 | SUP039 | Services | 2025-04 | 5 | 711698.62 | 90 days | UK
P004 | SUP039 | Logistics | 2025-05 | 0 | 277022.23 | 90 days | UK
P004 | SUP039 | Electronics | 2025-06 | 0 | 303589.44 | 90 days | UK
P004 | SUP039 | Software | 2025-07 | 1 | 805474.87 | 90 days | UK
P004 | SUP039 | Mechanical | 2025-08 | 5 | 186393.32 | 90 days | UK
P004 | SUP039 | Materials | 2025-09 | 7 | 1223725.74 | 90 days | UK
P004 | SUP039 | Electronics | 2025-10 | 0 | 384786.72 | 90 days | UK
P004 | SUP039 | Electronics | 2025-11 | 4 | 306694.4 | 90 days | UK
P004 | SUP039 | Logistics | 2025-12 | 2 | 964907.68 | 90 days | UK
P004 | SUP017 | Mechanical | 2025-01 | 1 | 371635.72 | 90 days | EU
P004 | SUP017 | Services | 2025-02 | 6 | 518809.39 | 90 days | EU
P004 | SUP017 | Electronics | 2025-03 | 0 | 470893.65 | 90 days | EU
P004 | SUP017 | Logistics | 2025-04 | 5 | 844266.69 | 90 days | EU
P004 | SUP017 | Materials | 2025-05 | 2 | 1107830.45 | 90 days | EU
P004 | SUP017 | Software | 2025-06 | 5 | 369055.49 | 90 days | EU
P004 | SUP017 | Software | 2025-07 | 5 | 573348.69 | 90 days | EU
P004 | SUP017 | Electronics | 2025-08 | 3 | 737540.61 | 90 days | EU
P004 | SUP017 | Logistics | 2025-09 | 3 | 458688.39 | 90 days | EU
P004 | SUP017 | Materials | 2025-10 | 0 | 182273.65 | 90 days | EU
P004 | SUP017 | Software | 2025-11 | 2 | 813075.84 | 90 days | EU
P004 | SUP017 | Software | 2025-12 | 1 | 218932.46 | 90 days | EU
P004 | SUP038 | Electronics | 2025-01 | 2 | 662464.34 | 45 days | US
P004 | SUP038 | Electronics | 2025-02 | 1 | 781306.57 | 45 days | US
P004 | SUP038 | Logistics | 2025-03 | 6 | 164559.48 | 45 days | US
P004 | SUP038 | Software | 2025-04 | 6 | 475121.02 | 45 days | US
P004 | SUP038 | Software | 2025-05 | 2 | 898491.07 | 45 days | US
P004 | SUP038 | Logistics | 2025-06 | 4 | 240727.56 | 45 days | US
P004 | SUP038 | Logistics | 2025-07 | 2 | 41732.43 | 45 days | US
P004 | SUP038 | Software | 2025-08 | 3 | 430578.74 | 45 days | US
P004 | SUP038 | Materials | 2025-09 | 7 | 1222719.98 | 45 days | US
P004 | SUP038 | Electronics | 2025-10 | 3 | 1540013.96 | 45 days | US
P004 | SUP038 | Materials | 2025-11 | 5 | 218521.5 | 45 days | US
P004 | SUP038 | Software | 2025-12 | 3 | 1528234.56 | 45 days | US
P004 | SUP029 | Electronics | 2025-01 | 3 | 1036441.93 | 45 days | US
P004 | SUP029 | Services | 2025-02 | 5 | 1576515.18 | 45 days | US
P004 | SUP029 | Logistics | 2025-03 | 5 | 1578956.78 | 45 days | US
P004 | SUP029 | Mechanical | 2025-04 | 2 | 832439.92 | 45 days | US
P004 | SUP029 | Services | 2025-05 | 5 | 359253.52 | 45 days | US
P004 | SUP029 | Electronics | 2025-06 | 4 | 1324789.95 | 45 days | US
P004 | SUP029 | Mechanical | 2025-07 | 2 | 361878.65 | 45 days | US
P004 | SUP029 | Mechanical | 2025-08 | 6 | 1204563.48 | 45 days | US
P004 | SUP029 | Services | 2025-09 | 3 | 1348301.35 | 45 days | US
P004 | SUP029 | Services | 2025-10 | 9 | 1285217.84 | 45 days | US
P004 | SUP029 | Services | 2025-11 | 6 | 163352.78 | 45 days | US
P004 | SUP029 | Software | 2025-12 | 8 | 628108.34 | 45 days | US
P004 | SUP034 | Mechanical | 2025-01 | 6 | 1819231.41 | 60 days | US
P004 | SUP034 | Mechanical | 2025-02 | 4 | 932423.86 | 60 days | US
P004 | SUP034 | Electronics | 2025-03 | 4 | 1106847.17 | 60 days | US
P004 | SUP034 | Electronics | 2025-04 | 7 | 1028383.54 | 60 days | US
P004 | SUP034 | Mechanical | 2025-05 | 3 | 957744.05 | 60 days | US
P004 | SUP034 | Logistics | 2025-06 | 5 | 1488776.53 | 60 days | US
P004 | SUP034 | Mechanical | 2025-07 | 2 | 545630.7 | 60 days | US
P004 | SUP034 | Electronics | 2025-08 | 3 | 926827.94 | 60 days | US
P004 | SUP034 | Software | 2025-09 | 1 | 953690.12 | 60 days | US
P004 | SUP034 | Services | 2025-10 | 2 | 1057733.67 | 60 days | US
P004 | SUP034 | Mechanical | 2025-11 | 5 | 1275454.12 | 60 days | US
P004 | SUP034 | Services | 2025-12 | 5 | 1772640.99 | 60 days | US
P004 | SUP049 | Mechanical | 2025-01 | 6 | 819696.65 | 90 days | US
P004 | SUP049 | Materials | 2025-02 | 3 | 526897.49 | 90 days | US
P004 | SUP049 | Mechanical | 2025-03 | 4 | 1322803.92 | 90 days | US
P004 | SUP049 | Electronics | 2025-04 | 4 | 787696.07 | 90 days | US
P004 | SUP049 | Materials | 2025-05 | 0 | 488236.41 | 90 days | US
P004 | SUP049 | Logistics | 2025-06 | 1 | 509349.75 | 90 days | US
P004 | SUP049 | Software | 2025-07 | 4 | 620708.33 | 90 days | US
P004 | SUP049 | Logistics | 2025-08 | 5 | 499190.76 | 90 days | US
P004 | SUP049 | Logistics | 2025-09 | 10 | 734789.77 | 90 days | US
P004 | SUP049 | Logistics | 2025-10 | 1 | 189211.45 | 90 days | US
P004 | SUP049 | Electronics | 2025-11 | 8 | 483194.83 | 90 days | US
P004 | SUP049 | Electronics | 2025-12 | 1 | 253498.74 | 90 days | US
P004 | SUP006 | Services | 2025-01 | 7 | 743546.64 | 60 days | APAC
P004 | SUP006 | Electronics | 2025-02 | 5 | 229968.13 | 60 days | APAC
P004 | SUP006 | Materials | 2025-03 | 4 | 776755.37 | 60 days | APAC
P004 | SUP006 | Electronics | 2025-04 | 1 | 1106417.26 | 60 days | APAC
P004 | SUP006 | Services | 2025-05 | 5 | 188857.68 | 60 days | APAC
P004 | SUP006 | Logistics | 2025-06 | 2 | 1029457.87 | 60 days | APAC
P004 | SUP006 | Materials | 2025-07 | 0 | 489617.97 | 60 days | APAC
P004 | SUP006 | Materials | 2025-08 | 2 | 198480.54 | 60 days | APAC
P004 | SUP006 | Electronics | 2025-09 | 3 | 300141.94 | 60 days | APAC
P004 | SUP006 | Mechanical | 2025-10 | 3 | 758209.81 | 60 days | APAC
P004 | SUP006 | Logistics | 2025-11 | 0 | 53578.13 | 60 days | APAC
P004 | SUP006 | Mechanical | 2025-12 | 0 | 39771 | 60 days | APAC
P004 | SUP031 | Services | 2025-01 | 7 | 116906.97 | 60 days | US
P004 | SUP031 | Mechanical | 2025-02 | 2 | 1263450.89 | 60 days | US
P004 | SUP031 | Services | 2025-03 | 7 | 370049.16 | 60 days | US
P004 | SUP031 | Software | 2025-04 | 5 | 113747.35 | 60 days | US
P004 | SUP031 | Electronics | 2025-05 | 3 | 738890.69 | 60 days | US
P004 | SUP031 | Logistics | 2025-06 | 6 | 370587.45 | 60 days | US
P004 | SUP031 | Mechanical | 2025-07 | 5 | 73012.08 | 60 days | US
P004 | SUP031 | Mechanical | 2025-08 | 6 | 829142.51 | 60 days | US
P004 | SUP031 | Services | 2025-09 | 7 | 1264634.71 | 60 days | US
P004 | SUP031 | Software | 2025-10 | 7 | 70182.07 | 60 days | US
P004 | SUP031 | Mechanical | 2025-11 | 3 | 491269.88 | 60 days | US
P004 | SUP031 | Mechanical | 2025-12 | 5 | 343522.83 | 60 days | US
P004 | SUP024 | Logistics | 2025-01 | 4 | 1141691.52 | 30 days | US
P004 | SUP024 | Services | 2025-02 | 1 | 1087639.98 | 30 days | US
P004 | SUP024 | Electronics | 2025-03 | 4 | 625551.11 | 30 days | US
P004 | SUP024 | Software | 2025-04 | 8 | 518171.33 | 30 days | US
P004 | SUP024 | Electronics | 2025-05 | 1 | 572326.24 | 30 days | US
P004 | SUP024 | Services | 2025-06 | 2 | 1135811.75 | 30 days | US
P004 | SUP024 | Software | 2025-07 | 5 | 232515.89 | 30 days | US
P004 | SUP024 | Materials | 2025-08 | 5 | 1269191.15 | 30 days | US
P004 | SUP024 | Electronics | 2025-09 | 8 | 253252.15 | 30 days | US
P004 | SUP024 | Materials | 2025-10 | 4 | 641552.36 | 30 days | US
P004 | SUP024 | Software | 2025-11 | 5 | 196059.75 | 30 days | US
P004 | SUP024 | Software | 2025-12 | 2 | 405653.2 | 30 days | US
P004 | SUP005 | Materials | 2025-01 | 4 | 1906309.19 | 45 days | UK
P004 | SUP005 | Software | 2025-02 | 7 | 817186.33 | 45 days | UK
P004 | SUP005 | Electronics | 2025-03 | 7 | 210766.43 | 45 days | UK
P004 | SUP005 | Software | 2025-04 | 3 | 706919.21 | 45 days | UK
P004 | SUP005 | Electronics | 2025-05 | 3 | 1084609.3 | 45 days | UK
P004 | SUP005 | Materials | 2025-06 | 3 | 409324.4 | 45 days | UK
P004 | SUP005 | Logistics | 2025-07 | 4 | 796589.3 | 45 days | UK
P004 | SUP005 | Software | 2025-08 | 0 | 691599.99 | 45 days | UK
P004 | SUP005 | Electronics | 2025-09 | 4 | 1760822.58 | 45 days | UK
P004 | SUP005 | Materials | 2025-10 | 5 | 1209978.7 | 45 days | UK
P004 | SUP005 | Software | 2025-11 | 6 | 1610076.87 | 45 days | UK
P004 | SUP005 | Logistics | 2025-12 | 2 | 1274271.61 | 45 days | UK
P004 | SUP036 | Logistics | 2025-01 | 4 | 218652.3 | 60 days | APAC
P004 | SUP036 | Materials | 2025-02 | 4 | 749728.12 | 60 days | APAC
P004 | SUP036 | Materials | 2025-03 | 5 | 672649.99 | 60 days | APAC
P004 | SUP036 | Services | 2025-04 | 2 | 809879.47 | 60 days | APAC
P004 | SUP036 | Mechanical | 2025-05 | 5 | 169055.33 | 60 days | APAC
P004 | SUP036 | Electronics | 2025-06 | 4 | 939871.13 | 60 days | APAC
P004 | SUP036 | Software | 2025-07 | 0 | 957585.07 | 60 days | APAC
P004 | SUP036 | Software | 2025-08 | 3 | 507591.42 | 60 days | APAC
P004 | SUP036 | Mechanical | 2025-09 | 4 | 438210.71 | 60 days | APAC
P004 | SUP036 | Logistics | 2025-10 | 4 | 185657.56 | 60 days | APAC
P004 | SUP036 | Materials | 2025-11 | 0 | 825180.42 | 60 days | APAC
P004 | SUP036 | Services | 2025-12 | 5 | 392529.92 | 60 days | APAC
P004 | SUP046 | Logistics | 2025-01 | 8 | 941843.91 | 90 days | EU
P004 | SUP046 | Materials | 2025-02 | 6 | 116203.13 | 90 days | EU
P004 | SUP046 | Electronics | 2025-03 | 3 | 355047 | 90 days | EU
P004 | SUP046 | Software | 2025-04 | 3 | 287009.06 | 90 days | EU
P004 | SUP046 | Mechanical | 2025-05 | 9 | 1823855.88 | 90 days | EU
P004 | SUP046 | Materials | 2025-06 | 4 | 205028.73 | 90 days | EU
P004 | SUP046 | Logistics | 2025-07 | 6 | 1471015.32 | 90 days | EU
P004 | SUP046 | Mechanical | 2025-08 | 5 | 187324.31 | 90 days | EU
P004 | SUP046 | Electronics | 2025-09 | 6 | 81348.47 | 90 days | EU
P004 | SUP046 | Materials | 2025-10 | 4 | 272834.43 | 90 days | EU
P004 | SUP046 | Mechanical | 2025-11 | 1 | 188327.36 | 90 days | EU
P004 | SUP046 | Materials | 2025-12 | 4 | 770556.7 | 90 days | EU
P004 | SUP040 | Services | 2025-01 | 0 | 268688.08 | 45 days | APAC
P004 | SUP040 | Mechanical | 2025-02 | 4 | 1268966.99 | 45 days | APAC
P004 | SUP040 | Materials | 2025-03 | 6 | 933453.02 | 45 days | APAC
P004 | SUP040 | Services | 2025-04 | 4 | 1175812.59 | 45 days | APAC
P004 | SUP040 | Mechanical | 2025-05 | 2 | 1184316.35 | 45 days | APAC
P004 | SUP040 | Services | 2025-06 | 1 | 1060214.95 | 45 days | APAC
P004 | SUP040 | Services | 2025-07 | 2 | 1264452.5 | 45 days | APAC
P004 | SUP040 | Software | 2025-08 | 1 | 234471.22 | 45 days | APAC
P004 | SUP040 | Materials | 2025-09 | 4 | 803294.14 | 45 days | APAC
P004 | SUP040 | Software | 2025-10 | 5 | 464155.14 | 45 days | APAC
P004 | SUP040 | Services | 2025-11 | 5 | 695766.66 | 45 days | APAC
P004 | SUP040 | Logistics | 2025-12 | 7 | 302091.64 | 45 days | APAC
P004 | SUP007 | Logistics | 2025-01 | 3 | 428385.48 | 45 days | APAC
P004 | SUP007 | Services | 2025-02 | 3 | 503319.11 | 45 days | APAC
P004 | SUP007 | Electronics | 2025-03 | 2 | 549392.39 | 45 days | APAC
P004 | SUP007 | Logistics | 2025-04 | 3 | 589673.5 | 45 days | APAC
P004 | SUP007 | Electronics | 2025-05 | 0 | 393483.35 | 45 days | APAC
P004 | SUP007 | Software | 2025-06 | 6 | 283355.84 | 45 days | APAC
P004 | SUP007 | Services | 2025-07 | 4 | 948304.65 | 45 days | APAC
P004 | SUP007 | Electronics | 2025-08 | 1 | 204450.4 | 45 days | APAC
P004 | SUP007 | Logistics | 2025-09 | 3 | 1666926.96 | 45 days | APAC
P004 | SUP007 | Materials | 2025-10 | 3 | 1084211.97 | 45 days | APAC
P004 | SUP007 | Electronics | 2025-11 | 2 | 1153297.83 | 45 days | APAC
P004 | SUP007 | Materials | 2025-12 | 6 | 733300.44 | 45 days | APAC
P004 | SUP030 | Electronics | 2025-01 | 3 | 466363.88 | 90 days | EU
P004 | SUP030 | Electronics | 2025-02 | 2 | 1607173.3 | 90 days | EU
P004 | SUP030 | Logistics | 2025-03 | 3 | 697048.43 | 90 days | EU
P004 | SUP030 | Services | 2025-04 | 3 | 877248.17 | 90 days | EU
P004 | SUP030 | Materials | 2025-05 | 1 | 761895.76 | 90 days | EU
P004 | SUP030 | Logistics | 2025-06 | 0 | 393381.32 | 90 days | EU
P004 | SUP030 | Materials | 2025-07 | 5 | 125820.73 | 90 days | EU
P004 | SUP030 | Mechanical | 2025-08 | 4 | 267646.95 | 90 days | EU
P004 | SUP030 | Services | 2025-09 | 5 | 1737858.13 | 90 days | EU
P004 | SUP030 | Services | 2025-10 | 5 | 1136949.92 | 90 days | EU
P004 | SUP030 | Materials | 2025-11 | 0 | 308207.26 | 90 days | EU
P004 | SUP030 | Electronics | 2025-12 | 4 | 1116720.49 | 90 days | EU
P004 | SUP011 | Logistics | 2025-01 | 6 | 796927.54 | 90 days | APAC
P004 | SUP011 | Logistics | 2025-02 | 6 | 434502.41 | 90 days | APAC
P004 | SUP011 | Logistics | 2025-03 | 9 | 501327.03 | 90 days | APAC
P004 | SUP011 | Services | 2025-04 | 2 | 878499.54 | 90 days | APAC
P004 | SUP011 | Mechanical | 2025-05 | 4 | 723042.9 | 90 days | APAC
P004 | SUP011 | Software | 2025-06 | 5 | 800258.88 | 90 days | APAC
P004 | SUP011 | Logistics | 2025-07 | 2 | 797767.09 | 90 days | APAC
P004 | SUP011 | Materials | 2025-08 | 4 | 433844.7 | 90 days | APAC
P004 | SUP011 | Electronics | 2025-09 | 5 | 464932.98 | 90 days | APAC
P004 | SUP011 | Mechanical | 2025-10 | 4 | 865166.43 | 90 days | APAC
P004 | SUP011 | Logistics | 2025-11 | 6 | 1142063.54 | 90 days | APAC
P004 | SUP011 | Mechanical | 2025-12 | 3 | 899659.29 | 90 days | APAC
P004 | SUP004 | Mechanical | 2025-01 | 6 | 429585.4 | 90 days | US
P004 | SUP004 | Services | 2025-02 | 4 | 723452.99 | 90 days | US
P004 | SUP004 | Services | 2025-03 | 4 | 236536.06 | 90 days | US
P004 | SUP004 | Services | 2025-04 | 3 | 485943.3 | 90 days | US
P004 | SUP004 | Services | 2025-05 | 5 | 338658.49 | 90 days | US
P004 | SUP004 | Mechanical | 2025-06 | 5 | 899235.9 | 90 days | US
P004 | SUP004 | Logistics | 2025-07 | 3 | 169945.8 | 90 days | US
P004 | SUP004 | Materials | 2025-08 | 0 | 367674.16 | 90 days | US
P004 | SUP004 | Logistics | 2025-09 | 1 | 131939.45 | 90 days | US
P004 | SUP004 | Services | 2025-10 | 1 | 895322.14 | 90 days | US
P004 | SUP004 | Logistics | 2025-11 | 0 | 714183.33 | 90 days | US
P004 | SUP004 | Mechanical | 2025-12 | 5 | 1110148.84 | 90 days | US
P004 | SUP016 | Materials | 2025-01 | 1 | 391093.43 | 60 days | EU
P004 | SUP016 | Materials | 2025-02 | 6 | 145670.98 | 60 days | EU
P004 | SUP016 | Services | 2025-03 | 4 | 94809.37 | 60 days | EU
P004 | SUP016 | Materials | 2025-04 | 5 | 104200.89 | 60 days | EU
P004 | SUP016 | Software | 2025-05 | 2 | 740496.75 | 60 days | EU
P004 | SUP016 | Electronics | 2025-06 | 5 | 456240.59 | 60 days | EU
P004 | SUP016 | Services | 2025-07 | 1 | 119372.89 | 60 days | EU
P004 | SUP016 | Software | 2025-08 | 4 | 606939.99 | 60 days | EU
P004 | SUP016 | Electronics | 2025-09 | 8 | 739316.26 | 60 days | EU
P004 | SUP016 | Electronics | 2025-10 | 0 | 100510.59 | 60 days | EU
P004 | SUP016 | Software | 2025-11 | 4 | 143099.09 | 60 days | EU
P004 | SUP016 | Materials | 2025-12 | 4 | 924053.32 | 60 days | EU
P004 | SUP012 | Mechanical | 2025-01 | 8 | 667511.43 | 90 days | US
P004 | SUP012 | Software | 2025-02 | 2 | 1405933.47 | 90 days | US
P004 | SUP012 | Mechanical | 2025-03 | 5 | 1368438.76 | 90 days | US
P004 | SUP012 | Electronics | 2025-04 | 2 | 442690.38 | 90 days | US
P004 | SUP012 | Software | 2025-05 | 3 | 815994.7 | 90 days | US
P004 | SUP012 | Mechanical | 2025-06 | 0 | 876226.86 | 90 days | US
P004 | SUP012 | Materials | 2025-07 | 5 | 857401.37 | 90 days | US
P004 | SUP012 | Electronics | 2025-08 | 7 | 1614009.27 | 90 days | US
P004 | SUP012 | Mechanical | 2025-09 | 1 | 1062737.25 | 90 days | US
P004 | SUP012 | Materials | 2025-10 | 4 | 1727265.99 | 90 days | US
P004 | SUP012 | Electronics | 2025-11 | 1 | 1292030.22 | 90 days | US
P004 | SUP012 | Logistics | 2025-12 | 2 | 999511.69 | 90 days | US
P004 | SUP047 | Software | 2025-01 | 2 | 544117.43 | 60 days | APAC
P004 | SUP047 | Mechanical | 2025-02 | 5 | 1350383.89 | 60 days | APAC
P004 | SUP047 | Logistics | 2025-03 | 4 | 1544400.44 | 60 days | APAC
P004 | SUP047 | Software | 2025-04 | 10 | 813173.3 | 60 days | APAC
P004 | SUP047 | Services | 2025-05 | 9 | 1979933.59 | 60 days | APAC
P004 | SUP047 | Services | 2025-06 | 7 | 635260.19 | 60 days | APAC
P004 | SUP047 | Services | 2025-07 | 3 | 846756.85 | 60 days | APAC
P004 | SUP047 | Materials | 2025-08 | 5 | 1302473.6 | 60 days | APAC
P004 | SUP047 | Services | 2025-09 | 0 | 314331.54 | 60 days | APAC
P004 | SUP047 | Logistics | 2025-10 | 5 | 164930.74 | 60 days | APAC
P004 | SUP047 | Logistics | 2025-11 | 2 | 984606.34 | 60 days | APAC
P004 | SUP047 | Materials | 2025-12 | 2 | 663177.78 | 60 days | APAC
P004 | SUP041 | Software | 2025-01 | 3 | 841114.03 | 30 days | UK
P004 | SUP041 | Electronics | 2025-02 | 1 | 1051738.48 | 30 days | UK
P004 | SUP041 | Logistics | 2025-03 | 1 | 840787.33 | 30 days | UK
P004 | SUP041 | Logistics | 2025-04 | 1 | 71905.84 | 30 days | UK
P004 | SUP041 | Materials | 2025-05 | 1 | 516465.24 | 30 days | UK
P004 | SUP041 | Electronics | 2025-06 | 5 | 499954.41 | 30 days | UK
P004 | SUP041 | Logistics | 2025-07 | 0 | 121702.46 | 30 days | UK
P004 | SUP041 | Materials | 2025-08 | 2 | 684968.02 | 30 days | UK
P004 | SUP041 | Materials | 2025-09 | 2 | 1188618.29 | 30 days | UK
P004 | SUP041 | Software | 2025-10 | 3 | 80776.17 | 30 days | UK
P004 | SUP041 | Software | 2025-11 | 1 | 734925.6 | 30 days | UK
P004 | SUP041 | Mechanical | 2025-12 | 3 | 739473.68 | 30 days | UK
P004 | SUP043 | Electronics | 2025-01 | 5 | 235730.64 | 60 days | EU
P004 | SUP043 | Logistics | 2025-02 | 4 | 1281857.31 | 60 days | EU
P004 | SUP043 | Materials | 2025-03 | 6 | 1398904.75 | 60 days | EU
P004 | SUP043 | Logistics | 2025-04 | 4 | 411745.94 | 60 days | EU
P004 | SUP043 | Logistics | 2025-05 | 0 | 782891.26 | 60 days | EU
P004 | SUP043 | Electronics | 2025-06 | 2 | 1244142.55 | 60 days | EU
P004 | SUP043 | Software | 2025-07 | 2 | 328852.63 | 60 days | EU
P004 | SUP043 | Mechanical | 2025-08 | 3 | 528657.21 | 60 days | EU
P004 | SUP043 | Electronics | 2025-09 | 0 | 384676.19 | 60 days | EU
P004 | SUP043 | Mechanical | 2025-10 | 6 | 65109.48 | 60 days | EU
P004 | SUP043 | Logistics | 2025-11 | 0 | 751266.14 | 60 days | EU
P004 | SUP043 | Software | 2025-12 | 4 | 403192.41 | 60 days | EU
P004 | SUP048 | Logistics | 2025-01 | 3 | 1265414.04 | 90 days | APAC
P004 | SUP048 | Mechanical | 2025-02 | 3 | 266591.47 | 90 days | APAC
P004 | SUP048 | Logistics | 2025-03 | 3 | 390757.36 | 90 days | APAC
P004 | SUP048 | Materials | 2025-04 | 6 | 994701.43 | 90 days | APAC
P004 | SUP048 | Software | 2025-05 | 3 | 187634.34 | 90 days | APAC
P004 | SUP048 | Mechanical | 2025-06 | 3 | 802720.86 | 90 days | APAC
P004 | SUP048 | Electronics | 2025-07 | 1 | 498001.14 | 90 days | APAC
P004 | SUP048 | Materials | 2025-08 | 6 | 101573.23 | 90 days | APAC
P004 | SUP048 | Logistics | 2025-09 | 0 | 889693.96 | 90 days | APAC
P004 | SUP048 | Logistics | 2025-10 | 6 | 865602.06 | 90 days | APAC
P004 | SUP048 | Software | 2025-11 | 4 | 806060.88 | 90 days | APAC
P004 | SUP048 | Electronics | 2025-12 | 2 | 1133744.01 | 90 days | APAC
P005 | SUP044 | Mechanical | 2025-01 | 5 | 127568.29 | 45 days | UK
P005 | SUP044 | Logistics | 2025-02 | 3 | 150060.62 | 45 days | UK
P005 | SUP044 | Services | 2025-03 | 5 | 822054.53 | 45 days | UK
P005 | SUP044 | Electronics | 2025-04 | 6 | 633625.26 | 45 days | UK
P005 | SUP044 | Materials | 2025-05 | 5 | 1348440.01 | 45 days | UK
P005 | SUP044 | Services | 2025-06 | 5 | 1388258.26 | 45 days | UK
P005 | SUP044 | Services | 2025-07 | 5 | 1020522.89 | 45 days | UK
P005 | SUP044 | Electronics | 2025-08 | 2 | 733373.2 | 45 days | UK
P005 | SUP044 | Materials | 2025-09 | 4 | 1227984.23 | 45 days | UK
P005 | SUP044 | Materials | 2025-10 | 5 | 801628.92 | 45 days | UK
P005 | SUP044 | Logistics | 2025-11 | 6 | 1014974.5 | 45 days | UK
P005 | SUP044 | Software | 2025-12 | 9 | 1279777.48 | 45 days | UK
P005 | SUP034 | Logistics | 2025-01 | 2 | 1193135.56 | 60 days | US
P005 | SUP034 | Services | 2025-02 | 2 | 120779.05 | 60 days | US
P005 | SUP034 | Materials | 2025-03 | 2 | 118964.03 | 60 days | US
P005 | SUP034 | Services | 2025-04 | 7 | 1291111.42 | 60 days | US
P005 | SUP034 | Materials | 2025-05 | 4 | 524020.76 | 60 days | US
P005 | SUP034 | Logistics | 2025-06 | 8 | 1058590.66 | 60 days | US
P005 | SUP034 | Logistics | 2025-07 | 4 | 1040439.79 | 60 days | US
P005 | SUP034 | Mechanical | 2025-08 | 6 | 1706746.47 | 60 days | US
P005 | SUP034 | Electronics | 2025-09 | 4 | 699710.84 | 60 days | US
P005 | SUP034 | Materials | 2025-10 | 1 | 636450.32 | 60 days | US
P005 | SUP034 | Software | 2025-11 | 9 | 203908.75 | 60 days | US
P005 | SUP034 | Services | 2025-12 | 7 | 1869134.29 | 60 days | US
P005 | SUP030 | Software | 2025-01 | 0 | 800323.44 | 90 days | EU
P005 | SUP030 | Materials | 2025-02 | 6 | 1407809.71 | 90 days | EU
P005 | SUP030 | Materials | 2025-03 | 4 | 531887.66 | 90 days | EU
P005 | SUP030 | Materials | 2025-04 | 1 | 845349.61 | 90 days | EU
P005 | SUP030 | Software | 2025-05 | 7 | 394670.36 | 90 days | EU
P005 | SUP030 | Materials | 2025-06 | 2 | 184192.27 | 90 days | EU
P005 | SUP030 | Logistics | 2025-07 | 4 | 111553.51 | 90 days | EU
P005 | SUP030 | Materials | 2025-08 | 5 | 674593.02 | 90 days | EU
P005 | SUP030 | Logistics | 2025-09 | 0 | 970609.13 | 90 days | EU
P005 | SUP030 | Software | 2025-10 | 2 | 1186434.26 | 90 days | EU
P005 | SUP030 | Electronics | 2025-11 | 3 | 203917.76 | 90 days | EU
P005 | SUP030 | Mechanical | 2025-12 | 5 | 1097829.79 | 90 days | EU
P005 | SUP015 | Services | 2025-01 | 6 | 1191206.86 | 45 days | US
P005 | SUP015 | Materials | 2025-02 | 4 | 322449.07 | 45 days | US
P005 | SUP015 | Software | 2025-03 | 3 | 1130866.65 | 45 days | US
P005 | SUP015 | Software | 2025-04 | 0 | 735404.52 | 45 days | US
P005 | SUP015 | Logistics | 2025-05 | 6 | 253555.54 | 45 days | US
P005 | SUP015 | Software | 2025-06 | 6 | 595907.85 | 45 days | US
P005 | SUP015 | Mechanical | 2025-07 | 7 | 1171156.49 | 45 days | US
P005 | SUP015 | Logistics | 2025-08 | 4 | 1004807.49 | 45 days | US
P005 | SUP015 | Materials | 2025-09 | 7 | 1062714.83 | 45 days | US
P005 | SUP015 | Software | 2025-10 | 1 | 213977.44 | 45 days | US
P005 | SUP015 | Logistics | 2025-11 | 7 | 524815.59 | 45 days | US
P005 | SUP015 | Mechanical | 2025-12 | 8 | 1913203.32 | 45 days | US
P005 | SUP041 | Mechanical | 2025-01 | 1 | 127594.95 | 30 days | UK
P005 | SUP041 | Services | 2025-02 | 1 | 874942.54 | 30 days | UK
P005 | SUP041 | Materials | 2025-03 | 2 | 265973.05 | 30 days | UK
P005 | SUP041 | Mechanical | 2025-04 | 3 | 838362.52 | 30 days | UK
P005 | SUP041 | Electronics | 2025-05 | 8 | 524633.92 | 30 days | UK
P005 | SUP041 | Materials | 2025-06 | 2 | 351557.8 | 30 days | UK
P005 | SUP041 | Electronics | 2025-07 | 8 | 806723.8 | 30 days | UK
P005 | SUP041 | Services | 2025-08 | 5 | 366046.75 | 30 days | UK
P005 | SUP041 | Services | 2025-09 | 5 | 1066132.18 | 30 days | UK
P005 | SUP041 | Software | 2025-10 | 4 | 1186813.92 | 30 days | UK
P005 | SUP041 | Materials | 2025-11 | 2 | 308236.94 | 30 days | UK
P005 | SUP041 | Software | 2025-12 | 4 | 764215.03 | 30 days | UK
P005 | SUP002 | Electronics | 2025-01 | 5 | 1259974.47 | 90 days | EU
P005 | SUP002 | Software | 2025-02 | 1 | 857744.58 | 90 days | EU
P005 | SUP002 | Services | 2025-03 | 3 | 401603.81 | 90 days | EU
P005 | SUP002 | Mechanical | 2025-04 | 5 | 792716.81 | 90 days | EU
P005 | SUP002 | Logistics | 2025-05 | 5 | 456768.72 | 90 days | EU
P005 | SUP002 | Software | 2025-06 | 4 | 1460602.27 | 90 days | EU
P005 | SUP002 | Materials | 2025-07 | 6 | 1652852.91 | 90 days | EU
P005 | SUP002 | Software | 2025-08 | 5 | 1501161.67 | 90 days | EU
P005 | SUP002 | Logistics | 2025-09 | 5 | 1455885.26 | 90 days | EU
P005 | SUP002 | Logistics | 2025-10 | 3 | 1375828.66 | 90 days | EU
P005 | SUP002 | Electronics | 2025-11 | 1 | 1075767.96 | 90 days | EU
P005 | SUP002 | Materials | 2025-12 | 5 | 1659174.09 | 90 days | EU
P005 | SUP006 | Electronics | 2025-01 | 1 | 918040.18 | 60 days | APAC
P005 | SUP006 | Mechanical | 2025-02 | 1 | 260339.15 | 60 days | APAC
P005 | SUP006 | Software | 2025-03 | 1 | 451172.01 | 60 days | APAC
P005 | SUP006 | Logistics | 2025-04 | 3 | 687361.77 | 60 days | APAC
P005 | SUP006 | Services | 2025-05 | 5 | 581196.97 | 60 days | APAC
P005 | SUP006 | Services | 2025-06 | 6 | 64337.01 | 60 days | APAC
P005 | SUP006 | Materials | 2025-07 | 6 | 72642.11 | 60 days | APAC
P005 | SUP006 | Electronics | 2025-08 | 5 | 67994.6 | 60 days | APAC
P005 | SUP006 | Logistics | 2025-09 | 1 | 314814.76 | 60 days | APAC
P005 | SUP006 | Electronics | 2025-10 | 3 | 348400.61 | 60 days | APAC
P005 | SUP006 | Services | 2025-11 | 6 | 837614.74 | 60 days | APAC
P005 | SUP006 | Mechanical | 2025-12 | 4 | 876580.7 | 60 days | APAC
P005 | SUP003 | Software | 2025-01 | 1 | 277362.85 | 60 days | APAC
P005 | SUP003 | Logistics | 2025-02 | 0 | 712160.66 | 60 days | APAC
P005 | SUP003 | Electronics | 2025-03 | 4 | 121204.88 | 60 days | APAC
P005 | SUP003 | Services | 2025-04 | 1 | 451623.87 | 60 days | APAC
P005 | SUP003 | Materials | 2025-05 | 3 | 748569.38 | 60 days | APAC
P005 | SUP003 | Logistics | 2025-06 | 3 | 1253302.02 | 60 days | APAC
P005 | SUP003 | Materials | 2025-07 | 7 | 648130.55 | 60 days | APAC
P005 | SUP003 | Software | 2025-08 | 3 | 384723.92 | 60 days | APAC
P005 | SUP003 | Software | 2025-09 | 2 | 1074172.42 | 60 days | APAC
P005 | SUP003 | Electronics | 2025-10 | 1 | 717142.79 | 60 days | APAC
P005 | SUP003 | Software | 2025-11 | 0 | 147087.01 | 60 days | APAC
P005 | SUP003 | Logistics | 2025-12 | 5 | 242168.25 | 60 days | APAC
P005 | SUP019 | Services | 2025-01 | 2 | 381253.92 | 90 days | UK
P005 | SUP019 | Software | 2025-02 | 0 | 748700.75 | 90 days | UK
P005 | SUP019 | Mechanical | 2025-03 | 4 | 1223305.59 | 90 days | UK
P005 | SUP019 | Mechanical | 2025-04 | 2 | 614096.8 | 90 days | UK
P005 | SUP019 | Services | 2025-05 | 1 | 224395.62 | 90 days | UK
P005 | SUP019 | Materials | 2025-06 | 4 | 643618.65 | 90 days | UK
P005 | SUP019 | Mechanical | 2025-07 | 3 | 672641.48 | 90 days | UK
P005 | SUP019 | Software | 2025-08 | 4 | 379573.9 | 90 days | UK
P005 | SUP019 | Logistics | 2025-09 | 8 | 1186394.28 | 90 days | UK
P005 | SUP019 | Electronics | 2025-10 | 0 | 585345.14 | 90 days | UK
P005 | SUP019 | Services | 2025-11 | 1 | 1115479.55 | 90 days | UK
P005 | SUP019 | Materials | 2025-12 | 2 | 819435.72 | 90 days | UK
P005 | SUP032 | Services | 2025-01 | 1 | 622516.08 | 90 days | APAC
P005 | SUP032 | Mechanical | 2025-02 | 3 | 572607.75 | 90 days | APAC
P005 | SUP032 | Materials | 2025-03 | 4 | 417665.06 | 90 days | APAC
P005 | SUP032 | Mechanical | 2025-04 | 6 | 435575.32 | 90 days | APAC
P005 | SUP032 | Services | 2025-05 | 0 | 788358.31 | 90 days | APAC
P005 | SUP032 | Materials | 2025-06 | 2 | 461263.16 | 90 days | APAC
P005 | SUP032 | Materials | 2025-07 | 6 | 776389.57 | 90 days | APAC
P005 | SUP032 | Electronics | 2025-08 | 3 | 150394.73 | 90 days | APAC
P005 | SUP032 | Logistics | 2025-09 | 3 | 1216430.2 | 90 days | APAC
P005 | SUP032 | Services | 2025-10 | 0 | 864533.07 | 90 days | APAC
P005 | SUP032 | Logistics | 2025-11 | 0 | 766971.47 | 90 days | APAC
P005 | SUP032 | Materials | 2025-12 | 1 | 801975.41 | 90 days | APAC
P005 | SUP045 | Materials | 2025-01 | 3 | 78259.27 | 30 days | US
P005 | SUP045 | Software | 2025-02 | 4 | 1442735.49 | 30 days | US
P005 | SUP045 | Materials | 2025-03 | 3 | 575372.62 | 30 days | US
P005 | SUP045 | Logistics | 2025-04 | 5 | 1255666.16 | 30 days | US
P005 | SUP045 | Services | 2025-05 | 3 | 1291733.26 | 30 days | US
P005 | SUP045 | Services | 2025-06 | 6 | 1588192.18 | 30 days | US
P005 | SUP045 | Materials | 2025-07 | 5 | 287661.55 | 30 days | US
P005 | SUP045 | Logistics | 2025-08 | 7 | 651811.1 | 30 days | US
P005 | SUP045 | Software | 2025-09 | 3 | 826101.38 | 30 days | US
P005 | SUP045 | Materials | 2025-10 | 6 | 1229077.5 | 30 days | US
P005 | SUP045 | Logistics | 2025-11 | 5 | 996292.21 | 30 days | US
P005 | SUP045 | Mechanical | 2025-12 | 1 | 697030.75 | 30 days | US
P005 | SUP040 | Mechanical | 2025-01 | 3 | 344765.29 | 45 days | APAC
P005 | SUP040 | Software | 2025-02 | 3 | 403876.51 | 45 days | APAC
P005 | SUP040 | Mechanical | 2025-03 | 2 | 1018307.02 | 45 days | APAC
P005 | SUP040 | Materials | 2025-04 | 4 | 672757.7 | 45 days | APAC
P005 | SUP040 | Electronics | 2025-05 | 0 | 220653.31 | 45 days | APAC
P005 | SUP040 | Mechanical | 2025-06 | 1 | 388571.3 | 45 days | APAC
P005 | SUP040 | Mechanical | 2025-07 | 4 | 910301.73 | 45 days | APAC
P005 | SUP040 | Electronics | 2025-08 | 3 | 528052.73 | 45 days | APAC
P005 | SUP040 | Services | 2025-09 | 7 | 303777.94 | 45 days | APAC
P005 | SUP040 | Electronics | 2025-10 | 3 | 403208.05 | 45 days | APAC
P005 | SUP040 | Mechanical | 2025-11 | 3 | 572869.86 | 45 days | APAC
P005 | SUP040 | Electronics | 2025-12 | 3 | 727862.37 | 45 days | APAC
P005 | SUP013 | Electronics | 2025-01 | 3 | 102753.57 | 60 days | UK
P005 | SUP013 | Software | 2025-02 | 3 | 989823.87 | 60 days | UK
P005 | SUP013 | Materials | 2025-03 | 3 | 424217.58 | 60 days | UK
P005 | SUP013 | Mechanical | 2025-04 | 5 | 694571.94 | 60 days | UK
P005 | SUP013 | Logistics | 2025-05 | 3 | 72214.33 | 60 days | UK
P005 | SUP013 | Materials | 2025-06 | 2 | 563258.8 | 60 days | UK
P005 | SUP013 | Mechanical | 2025-07 | 0 | 595029.11 | 60 days | UK
P005 | SUP013 | Electronics | 2025-08 | 8 | 457602.87 | 60 days | UK
P005 | SUP013 | Electronics | 2025-09 | 6 | 999014.84 | 60 days | UK
P005 | SUP013 | Mechanical | 2025-10 | 1 | 456518.2 | 60 days | UK
P005 | SUP013 | Services | 2025-11 | 4 | 242290.12 | 60 days | UK
P005 | SUP013 | Mechanical | 2025-12 | 2 | 1084848.57 | 60 days | UK
P005 | SUP009 | Mechanical | 2025-01 | 5 | 973113.8 | 30 days | US
P005 | SUP009 | Materials | 2025-02 | 5 | 1437486.69 | 30 days | US
P005 | SUP009 | Services | 2025-03 | 5 | 486294.63 | 30 days | US
P005 | SUP009 | Materials | 2025-04 | 6 | 953953.56 | 30 days | US
P005 | SUP009 | Mechanical | 2025-05 | 7 | 1396812.85 | 30 days | US
P005 | SUP009 | Materials | 2025-06 | 5 | 1434002.51 | 30 days | US
P005 | SUP009 | Materials | 2025-07 | 5 | 1031647.2 | 30 days | US
P005 | SUP009 | Services | 2025-08 | 4 | 779108.23 | 30 days | US
P005 | SUP009 | Services | 2025-09 | 4 | 1118663.44 | 30 days | US
P005 | SUP009 | Software | 2025-10 | 3 | 365633.61 | 30 days | US
P005 | SUP009 | Materials | 2025-11 | 8 | 511797.69 | 30 days | US
P005 | SUP009 | Electronics | 2025-12 | 6 | 578683.31 | 30 days | US
P005 | SUP039 | Services | 2025-01 | 6 | 1426492.66 | 90 days | UK
P005 | SUP039 | Mechanical | 2025-02 | 1 | 217274.15 | 90 days | UK
P005 | SUP039 | Mechanical | 2025-03 | 2 | 138239.5 | 90 days | UK
P005 | SUP039 | Mechanical | 2025-04 | 4 | 776506.03 | 90 days | UK
P005 | SUP039 | Electronics | 2025-05 | 5 | 1577017.94 | 90 days | UK
P005 | SUP039 | Software | 2025-06 | 5 | 207373.49 | 90 days | UK
P005 | SUP039 | Services | 2025-07 | 1 | 621262.15 | 90 days | UK
P005 | SUP039 | Logistics | 2025-08 | 7 | 632832.17 | 90 days | UK
P005 | SUP039 | Mechanical | 2025-09 | 3 | 334615.39 | 90 days | UK
P005 | SUP039 | Materials | 2025-10 | 3 | 685088.37 | 90 days | UK
P005 | SUP039 | Services | 2025-11 | 1 | 684055.83 | 90 days | UK
P005 | SUP039 | Services | 2025-12 | 4 | 1331899.38 | 90 days | UK
P005 | SUP050 | Materials | 2025-01 | 6 | 871741.73 | 30 days | APAC
P005 | SUP050 | Mechanical | 2025-02 | 3 | 251834.76 | 30 days | APAC
P005 | SUP050 | Logistics | 2025-03 | 3 | 166505.36 | 30 days | APAC
P005 | SUP050 | Software | 2025-04 | 8 | 821478.4 | 30 days | APAC
P005 | SUP050 | Electronics | 2025-05 | 0 | 1242523.68 | 30 days | APAC
P005 | SUP050 | Electronics | 2025-06 | 3 | 660857.52 | 30 days | APAC
P005 | SUP050 | Software | 2025-07 | 1 | 357077.86 | 30 days | APAC
P005 | SUP050 | Electronics | 2025-08 | 2 | 1075929.17 | 30 days | APAC
P005 | SUP050 | Electronics | 2025-09 | 8 | 828303.46 | 30 days | APAC
P005 | SUP050 | Mechanical | 2025-10 | 0 | 546104.72 | 30 days | APAC
P005 | SUP050 | Services | 2025-11 | 3 | 457559.87 | 30 days | APAC
P005 | SUP050 | Software | 2025-12 | 4 | 594061.13 | 30 days | APAC
P005 | SUP021 | Logistics | 2025-01 | 5 | 782814.81 | 60 days | US
P005 | SUP021 | Mechanical | 2025-02 | 3 | 1441507.75 | 60 days | US
P005 | SUP021 | Services | 2025-03 | 4 | 588939.73 | 60 days | US
P005 | SUP021 | Electronics | 2025-04 | 4 | 597760.24 | 60 days | US
P005 | SUP021 | Services | 2025-05 | 8 | 1028920.95 | 60 days | US
P005 | SUP021 | Services | 2025-06 | 0 | 1040714.33 | 60 days | US
P005 | SUP021 | Software | 2025-07 | 7 | 1242725.94 | 60 days | US
P005 | SUP021 | Mechanical | 2025-08 | 7 | 892973.55 | 60 days | US
P005 | SUP021 | Software | 2025-09 | 2 | 999618.44 | 60 days | US
P005 | SUP021 | Electronics | 2025-10 | 3 | 1801583.77 | 60 days | US
P005 | SUP021 | Services | 2025-11 | 0 | 1211070.93 | 60 days | US
P005 | SUP021 | Electronics | 2025-12 | 0 | 371566.92 | 60 days | US
P005 | SUP011 | Software | 2025-01 | 5 | 542461.05 | 90 days | APAC
P005 | SUP011 | Mechanical | 2025-02 | 1 | 337063.78 | 90 days | APAC
P005 | SUP011 | Logistics | 2025-03 | 3 | 836176.28 | 90 days | APAC
P005 | SUP011 | Services | 2025-04 | 5 | 554954.2 | 90 days | APAC
P005 | SUP011 | Mechanical | 2025-05 | 1 | 172817.26 | 90 days | APAC
P005 | SUP011 | Mechanical | 2025-06 | 4 | 586240.58 | 90 days | APAC
P005 | SUP011 | Software | 2025-07 | 8 | 1160792.7 | 90 days | APAC
P005 | SUP011 | Logistics | 2025-08 | 3 | 598952.7 | 90 days | APAC
P005 | SUP011 | Materials | 2025-09 | 2 | 891564.63 | 90 days | APAC
P005 | SUP011 | Mechanical | 2025-10 | 5 | 661828.29 | 90 days | APAC
P005 | SUP011 | Logistics | 2025-11 | 7 | 1319457.85 | 90 days | APAC
P005 | SUP011 | Materials | 2025-12 | 0 | 1043695.47 | 90 days | APAC